## Internal
Checklist -Enabling Internal Services Works
checklist | Enabling Works Services
Section | Ceiling Tiles Removal ( pass when all complete)
checkpoint | Relevant ceiling tiles removed
checkpoint | Ceiling tiles stored safely
Section | Connection to Existing Sprinkler System
Checkpoint | Existing Sprinkler line for connection located ( add photos and markup)
checkpoint | New work Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
Checkpoint | As built markups done
Section | Connection to Existing Alarm System
Checkpoint | Existing Alarms power for connection located ( add photos and markup)
checkpoint | New work Reference Drawings ( add photo and include drawing numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
Checkpoint | As built markups done
Section | Connection to Data System
Checkpoint | Existing Alarms power for connection located ( add photos and markup)
checkpoint | New work Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
Checkpoint | As built markups done
Section | Connection to Data System
Checkpoint | Existing Alarms power for connection located ( add photos and markup)
checkpoint | New work Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
Checkpoint | As built markups done
Section | Connection to Fibre
Checkpoint | Existing Fibre main for connection located ( add photos and markup)
checkpoint | New work Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
Checkpoint | As built markups done
Section | Connections to Existing Water Main
Checkpoint | Existing water main for connection located ( add photos and markup)
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Commissioning/Testing results received , reviewed attached
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
Checkpoint | As built markups done
Checkpoint | All tiles are cleaned and reinstated
Section | Connection to Existing Sewer System
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
checkpoint | As built markups done
Section | Connection to Existing Stormwater System
checkpoint | Existing Sprinkler line for connection located (add photos and markup).
checkpoint | New work Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
checkpoint | Witness testing of pipework by Hawkins
checkpoint | Consultants Inspection sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Council inspection and testing complete and signed off
checkpoint | As built markups done
Section | Reinstatement of Tiles
checkpoint | All tiles are cleaned and reinstated

## External
Checklist -Enabling External Services Works
Section | Connection to Existing Sewer System
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | All open ends capped
checkpoint | Pipework bedded correctly
checkpoint | Tidy work areas
checkpoint | Pressure test pipework
checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint | Backfill around pipework with fines
checkpoint | Any additional photos, comments and observations
checkpoint | installers name & date works done
text | Installers name:
text | Date :
checkpoint | Witness testing of pipework by Hawkins & Council or Consultant
text | Testing by
text | date tested
checkpoint | Consultants Inspection sign off
checkpoint | Council inspection and testing complete and signed off
checkpoint | Backfilling around pipework completed
Checkpoint | As built markups done
Section | Connection to Existing Stormwater System
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA/Testing results received, reviewed, attached and approved
checkpoint | All open ends capped
checkpoint | Pipework bedded correctly
checkpoint | Tidy work areas
checkpoint | Pressure test pipework
checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint | Backfill around pipework with fines
checkpoint | Any additional photos, comments and observations
checkpoint | installers name & date works done
text | Installers name:
text | Date :
checkpoint | Witness testing of pipework by Hawkins & Council or Consultant
text | Testing by
text | date tested
checkpoint | Consultants Inspection sign off
checkpoint | Council inspection and testing complete and signed off
checkpoint | Backfilling around pipework completed
Checkpoint | As built markups done