## Project Breakdown
|  | PROJECT BREAKDOWN |  |  | CHECKLISTS
Project Build QC/QA
Site Establishment
Site Setout / Survey
Setout / Surveying - GPS coordination points for temporary fencing
Site fencing
Removal of Fill / Spoil haul roads and laydown areas
Removal of Fill/Spoil - Enabling works
Total volumn
Proof roll
Excavation checklist
Welfare facilities
Container installation
Services installation
Laydown areas/mobile crane base
Excavation checklist
Whare
Foundations
Phase 1.1 Setout / Surveying (Building location)
Phase 1.1 Excavation Checklist
Pre-excavation
Post-excavation
Phase 1.1 Site Concrete Checklist
Phase 1.1 and 1.2 Concrete Pour
Phase 1.2 Setout / Surveying grid lines
Phase 1.2 Excavation Checklist
Phase 1.2 Site Concrete Checklist
Phase 1.2 Waterproofing Checklist
underground services
QA - Underground services Checklist
set out and/ Surveying
Excavation

## Checklists
checklist | Setout / Surveying -
checkpoint | Any RL's setout are correct, labelled and photographed
checkpoint | Any grid setout are correct, labelled and photographed
checkpoint | Any other relevant setout/ survey documentation attached
checkpoint | Survey work completed, checked and accurate
Site fencing as per surveyed plans
checklist | Removal of Fill/Spoil -
checkpoint | Removal of Fill / Spoil recorded
text | Date(s)
text | Total Volume
button | Any supporting documentation attached
Ground disturbance permit
checklist | RITS Form -
checkpoint | RITS Form Completed & Attached
checklist | Concrete Pour -
section | Concrete - Pre Pour
checkpoint | Concrete pour details
text | Drawing Ref:
text | Specification Ref:
text | Inspection Ref:
checkpoint | Area Accessible & Approval to start
checkpoint | Formwork - Correct Dimensions & Heights
checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint | Reinforcing checked and correct
button | Size and type correct to specification
bool | Reinforcing spacing and location correct
bool | Specified covers checked/correct
bool | Splice laps checked/correct
bool | Any starter bars are installed correctly (location, size and spacing )
bool | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Waterproofing (checked and correct)
checkpoint | Bottom of concrete pour is clean and free of debris/roughened
checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
holdpoint | Request Signoff
section | Concrete - Pour /Post Pour
checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
bool | All concrete dockets photographed/attached here
checkpoint | General photos/comments/observations during placement
checkpoint | Concrete surface finish to specifications
checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
bool | Trades QA received & attached as applicable
checklist | QA - Excavation Checklist (V1)
section | Pre-excavation
checkpoint | Location of QA check (take a photo of a marked up plan and add here)
label | Key pre-excavation tasks
bool | Approval given to dig? (Ground disturbance permit in place)
bool | Relevant services identified and isolated / clearly marked?
bool | Has saw cutting been completed?
checkpoint | Excavation setout checked and correct to detail
checkpoint | Additional photos/ observations / reports attached
holdpoint | Request signoff
section | Post-excavation
checkpoint | Completed excavation checked and correct to detail
bool | Location accurate
bool | Depth correct (allow for site concrete if required).
bool | Width correct (allow for boxing if required)
checkpoint | Excess Material Cleaned up and removed as required
checkpoint | General Photos / Comments / Observations during excavation
holdpoint | Request Sign Off
checklist | QA - Site Concrete Checklist (V1)
checkpoint | Location of QA check (take a photo of a marked up plan and add here)
checkpoint | 100mm of pile above site concrete level
checkpoint | Are the pile heads clean
checkpoint | Formwork - Correct Dimensions & Heights
checkpoint | Height pegs installed to correct height
checkpoint | Local area clear of debris, safe access and ready for work
checkpoint | General photos/comments during install
holdpoint | Request Signoff
checklist | QA - Waterproofing Checklist (V1)
checkpoint | Location of QA check (take a photo of a marked up plan and add here)
checkpoint | Preparation / Substrate acceptable (site concrete poured and ready)
checkpoint | Correct product delivered and checked - approval given to install
checkpoint | Formwork ready for tanking
checkpoint | General photos/comments during install
checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
label | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
bool | Trades QA received & attached as applicable
holdpoint | Request Signoff
checklist | QA - Underground services Checklist (V1)
checkpoint | Location of QA check (take a photo of a marked up plan and add here)
checkpoint | Area Accessible & Approval to start (upload a photo of the area being assessed)
checkpoint | Preparation of substrate
checkpoint | Correct product delivered and checked
checkpoint | Ramps entry exit efficient for subs
checkpoint | General photos/comments during install
checkpoint | Any inspections/observations documented, reviewed and closed out
checkpoint | Sub-trade QA received and signed
checkpoint | Set out of services correct to grids/RL (Refer to drawings and install photo)
checklist | Crane Briefing Plan
section | Attendance
checkpoint | Attendance Information (Pass once all inputted)
select | Crane Co-ordinator
text | Crane Co-ordinator - if other, type here
select | Cranage Lead
text | Cranage Lead - if other, type here
select | Operator TC1
text | Operator TC1 - if other, type here
section | Critical Risks/Daily lifting schedule
checkpoint | Daily Lifting Schedule TC1
bool | Shutters
bool | Precast -unislab
bool | Precast- Double T
bool | Precast wall
bool | Concrete Skip
bool | Structural steel
bool | Scaffold moving
bool | Structural steel delivery
bool | Precast Balcony
bool | Waste bins
bool | Mancage
bool | SWL checked
bool | Reinforcing Delivery
bool | Moving Reinforcing
text | If other, specify:
checkpoint | Photos/Additional Comments
checkpoint | Radius chart or lift plan attached (Pass once attached)
section | Health & Safety controls for lifting
checkpoint | Crane operators /Dogman ticketed
checkpoint | Tower crane /Equipment have current certificate
checkpoint | New Hazards/risk/control
text | Hazard One:
text | Hazard Two:
section | Weather Conditions
checkpoint | Conditions (Pass once recorded)
bool | Rain forecast
bool | Wind plus 35 km/h
text | If other, specify:
section | Lifting Gear/Hazard check For today
checkpoint | Lifting Gear/Hazard Check complete
bool | Taglines ok
bool | Lifting gear ok
bool | Crane operation ok
bool | Anti-clash working ok
bool | Hook camera Woking ok
bool | Rigging methodology discussed
bool | Operator quick check complete
bool | Radio working ok
checkpoint | Photos/Additional Comments
section | Complex Lifts Today
checkpoint | Complex Lifts Today (Pass once relevant complex lifts are selected and any planning by engineer are done-to be attached)
bool | Irregular loads or loads with unusual weight distribution (centre of gravity)
bool | Using one or more cranes(winches)
bool | A lift with less than the recommended multicrane safety factors
bool | A lift out of view of the crane operator
bool | Technically difficult rigging
bool | Lifting personnel
bool | Lifting hazardous materials
bool | Lifting submerged loads
bool | Lift with no or partial outrigger
bool | lifting on rubber
bool | Lift weights if required
bool | Or any lift the crane operator feels should be classed as such
checklist | Daily Site Report -
checkpoint | Hours Worked & Weather Conditions Recorded
text | Hours Worked
select | Weather Conditions AM
select | Weather Conditions PM
checkpoint | Any Delays - design changes, outstanding information or other reasons causing delays recorded
label | If no reasons causing delays are identified select "N/A"
label | If items are identified to be causing delays, identify below then select "PASS"
text | Reason for delay
checkpoint | General progress photos - minimum of 3 attached
text | General progress on site today
checkpoint | Visitors to Site (Record name, company & purpose)
checkpoint | Day Works Agreed (Any relevant Day Works issued are documented here)
checkpoint | Subcontractors on site (all recorded area, man power, name)
button | SAYER DRAINAGE - On Site
text | Area (SAYER DRAINAGE)
text | Man Power (SAYER DRAINAGE)
button | WAIKATO DEMOLITION - On Site
text | Area (WAIKATO DEMOLITION)
text | Man Power (WAIKATO DEMOLITION)
button | SHICK (Earthworks) - On Site
text | Area (SHICK (Earthworks) )
text | Man Power (SHICK (Earthworks) )
button | STEEL & TUBE - On Site
text | Area (STEEL & TUBE)
text | Man Power (STEEL & TUBE)
button | HARRIS DOWD GIBBONS (Concrete) - On Site
text | Area (HARRIS DOWD GIBBONS (Concrete))
text | Man Power (HARRIS DOWD GIBBONS (Concrete))
button | ARID (Waterproofing) - On Site
text | Area (ARID (Waterproofing))
text | Man Power (ARID (Waterproofing))
button | WAIKATO STEEL FAB - On Site
text | Area (WAIKATO STEEL FAB)
text | Man Power (WAIKATO STEEL FAB )
button | FB HALL (Plumbing) - On Site
text | Area (FB HALL)
text | Man Power (FB HALL)
button | DOWNER CRANES (Crane) - On Site
text | Area (DOWNER CRANES)
text | Man Power (DOWNER CRANES)
button | FESSIT GROUP (Electrical and Data) - On Site
text | Area (FESSIT GROUP)
text | Man Power (FESSIT GROUP)
button | LEADER SCAFF (Scaffold) - On Site
text | Area (LEADER SCAFF)
text | Man Power (LEADER SCAFF)
button | Hawkins carpentry - On Site
text | Names of workers (Hawkins carpentry)
text | Area (Hawkins carpentry)
text | Man Power (Hawkins carpentry)
label | Trade - Other 1
text | Trade Name (Other 1)
text | Area (Other 1)
text | Man Power (Other 1)
label | Trade - Other 2
text | Trade Name (Other 2)
text | Area (Other 2)
text | Man Power (Other 2)
label | Trade - Other 3
text | Trade Name (Other 3)
text | Area (Other 3)
text | Man Power (Other 3)
label | Trade - Other 4
text | Trade Name (Other 4)
text | Area (Other 4)
text | Man Power (Other 4)
label | Trade - Other 5
text | Trade Name (Other 5)
text | Area (Other 5)
text | Man Power (Other 5)
label | Trade - Other 6
text | Trade Name (Other 6)
text | Area (Other 6)
text | Man Power (Other 6)
checklist | Safety & Environment Checklist -
checkpoint | Safety & Environment Details Recorded
text | Safety and Environmental Supervisor
text | Inspection by
text | Distribution
checkpoint | Site Control
button | Risk Register & Safety Notice Board up to date
button | PSEP & Environmental Plan current
button | Date of last toolbox meeting
button | Inductions being completed
checkpoint | Traffic Management
button | Traffic management measures set up in accordance with the TMP
checkpoint | Sediment and Erosion Control
button | Silt control Plan in place
button | Sediment control measures (e.g. sediment ponds, silt fences, drain protection installed and maintained
button | Wheel wash facilities, Carriageways Clear
button | Dust controlled
button | Construction noise being monitored
checkpoint | Hygiene
button | Clean offices, break sheds, Toilets
checkpoint | Housekeeping
button | Clear, safe access to work areas
button | Hoardings/perimeter fence and gates secure
button | Material stored away from edge and secured
checkpoint | Personal Safety Equipment
button | Signage displayed and legible
button | PPE being used (glasses/earmuffs/vests/masks/Hard hat/Boots/Gloves)
checkpoint | First Aid/Fire Prevention
button | First aid box
bool | Clean Sufficient supplies
button | Accident Register up to date
button | Fire Extinguishers
bool | Sufficient number
bool | Up to Date
button | Evacuation procedure in place, and current
bool | Last evacuation trial within 6 months
checkpoint | Sun Exposure
button | Shade cover or screens available
button | Workers wearing clothing to prevent sun exposure
button | Sunscreen available on site (SPF30 or more)
checkpoint | Cranes/Hoist/Lifting equipment
button | Certification up to date
button | Slings/chains certified
button | Lift Plan in place
button | MEWP’s, Logbook completed, Check 6-month cert.
button | Man cage available where required & Certified
button | Emergency plan in place
checkpoint | Compressed Air Equipment
button | Good condition, Competent user
checkpoint | Excavation
button | Correctly shored (Also See Fall Hazards)
checkpoint | Welding/Gas Cutting
button | Hot works permits being issued
button | Fire extinguishers on hand
button | Operators using Correct PPE
button | Flash Back arrestors
checkpoint | Electrical Equipment
button | Leads safely placed
button | Leads, Lights & Tools tagged and current
button | Lifeguards certified and current
button | Guards & Equipment in good condition
checkpoint | Chemicals
button | Correctly stored, SDS Available
button | Operators using PPE
button | Spill kit available
checkpoint | Powder Powered Tools
button | WOF current
button | Tools being used correctly, staff trained
button | Tools in good condition
checkpoint | Working at height
button | Harness being worn and in Good Condition
button | Harness fixing/anchor points adequate
button | Personnel trained in height and harness use
button | Emergency plan in place
button | Tools and equipment secured (tool bags, tethers, lanyards)
checkpoint | Scaffolding and Temporary Works
button | Register complete/updated weekly
button | Engineers sign-off where applicable
button | Handrails/mid-rails/Platforms/toe boards (front and back)
button | Access Ladders – secured top and base
button | Base sound
button | Platforms free of trip hazards
button | Planks tied down
button | Ties/bracing adequate (As per design?)
checkpoint | Ladders
button | Correct equipment for height access
checkpoint | Fall Hazards
button | Floor edges
bool | Handrails
bool | Toe Boards
bool | Covered
text | Person to Action (if required)
button | Lift shafts
bool | Handrails
bool | Toe Boards
bool | Covered
text | Person to Action (if required)
button | Floor openings
bool | Handrails
bool | Toe Boards
bool | Covered
text | Person to Action (if required)
button | Excavations
bool | Handrails
bool | Toe Boards
bool | Covered
text | Person to Action (if required)
button | Stairs
bool | Handrails
bool | Toe Boards
bool | Covered
text | Person to Action (if required)
button | Penetration protection reviewed and noted on registered
checkpoint | Safety & Environment Checklist Completed & Closed Out
label | Select "Pass" once all above safety & environment checks have been completed and/or closed out
checklist | Site Establishment
section | Site Establishment Checks
checkpoint | Existing site conditions captured (pass once relevant information documented)
checkpoint | Attach relevant site establishment photos/ documents
checkpoint | Appropriate site fencing installed
checkpoint | Consider and enact any H&S pre commencment setup / controlls
checkpoint | Consider and enact any environmental pre commencment setup / controlls
checkpoint | Site establishment completed
holdpoint | Raise Remedial / Request Signoff
section | Service Location / Isolation
checkpoint | Power located / Isolated
holdpoint | Raise remedial / request trades QA / signoff
checkpoint | Water Supply located / Isolated
holdpoint | Raise remedial / request trades QA / signoff
checkpoint | Sewer located / Isolated
holdpoint | Raise remedial / request trades QA / signoff
checkpoint | Stormwater located / Isolated
holdpoint | Raise remedial / request trades QA / signoff
checkpoint | Telecommunication/Fibre located / Isolated
holdpoint | Raise remedial / request trades QA / signoff
checkpoint | Any other relevant services located/ isolated
holdpoint | Raise remedial / request trades QA / signoff
checkpoint | All Services located/ isolated (Pass once all services are located/isolated)
holdpoint | Raise remedial / Request signoff
checklist | Pre Excavation
checkpoint | Location of QA check (take a photo of a marked up plan and add here)
label | Key pre-excavation tasks
bool | Approval given to dig? (Ground disturbance permit in place)
bool | Relevant services identified and isolated / clearly marked?
bool | Has saw cutting been completed?
checkpoint | Excavation setout checked and correct to detail
checkpoint | Additional photos/ observations / reports attached
holdpoint | Request signoff
checklist | Post Excavation
checkpoint | Completed excavation checked and correct to detail
bool | Location accurate
bool | Depth correct (allow for site concrete if required).
bool | Width correct (allow for boxing if required)
checkpoint | Excess Material Cleaned up and removed as required
checkpoint | General Photos / Comments / Observations during excavation
holdpoint | Request Sign Off

## Whare
Whare
checklist | Setout / Surveying -
checkpoint | Any RL's setout are correct, labelled and photographed
checkpoint | Any grid setout are correct, labelled and photographed
checkpoint | Any other relevant setout/ survey documentation attached
checkpoint | Survey work completed, checked and accurate
Site fencing as per surveyed plans
checklist | QA - Excavation Checklist (V1)
checkpoint | Location of QA check (take a photo of a marked up plan and add here)
bool | Approval given to dig? (Ground disturbance permit in place)
bool | Relevant services identified and isolated / clearly marked?
bool | Has saw cutting been completed?
checkpoint | Excavation setout checked and correct to detail
checkpoint | Completed excavation checked and correct to detail
bool | Depth correct (allow for site concrete if required).
bool | Width correct (allow for boxing if required)
checkpoint | General Photos / Comments / Observations during excavation
holdpoint | Request Sign Off
checklist | Concrete Pour -
checkpoint | Formwork - Correct Dimensions & Heights
checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint | Reinforcing checked and correct
bool | Reinforcing spacing and location correct
bool | Specified covers checked/correct
bool | Splice laps checked/correct
bool | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Waterproofing (checked and correct)
checkpoint | Bottom of concrete pour is clean and free of debris/roughened
checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
holdpoint | Request Signoff
section | Concrete - Pour /Post Pour
checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
bool | All concrete dockets photographed/attached here
checkpoint | General photos/comments/observations during placement
checkpoint | Concrete surface finish to specifications
label | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
bool | Trades QA received & attached as applicable
Speed form Installation
Grid Lines sureveyed
RL's checked
Hold downs set out
Engineer sign off
Hamilton City Council signoff
Concrete Pre Pour check = m3 checked - MPA checked
Check in fill material compacted
Sub Floor Framing
Check layout
check all connections
Sign off engineer
HCC
DPC Installed
Sign off HCC
Install Flooring
DPC Installed
Fixing Type check
Cranage methodoly
Glulam Portals Installed
Temporary Prpping Approval
Cranage methodoly/Briefing
Portals sealed
Hold down checked & bolted
Roof Structure
Purlins
Bracing
Cladding
HCC/Engineer sign off
Wall Cladding
Framing correct
Trim sizes checked
Build wrap installed
Cavity batten
Cladding
Window treatments including flush
Joinery installation
Build water tight
Interior finshes
first fix all trades signed off
Interior cladding as per specs checked
All bracing correct
HCC Preline checked
Engineer preline checked