## Sheet1
WEIR HOUSE EXTERIOR PATCH AND REPAIR RENDERSPEC
EAST ELEVATION GRID 1-8 A
- Diamond grind areas where the repair bandage is failing.
- Ensure that an area of 75mm either side of the existing bandage is exposed, to allow new coating to blend in.
- Waterblast surface to remove any contaminants etc.
- Apply a slurry coat of Resin and Multistop bedding to act as a sealer/key coat.
- Mix a solution of Acrylbond and Rockcote MultiStop together and apply using a roller .
- Bandage area with 75mm fiberglass joint mesh and RCS bedding compound.
- Mix a 50:50 mix of acrylbond/water and a 1 kg of MultiStop/Adhesive to the mix.
- Apply a coat of RCS Hydroplast over the bandaged area.
- Do not apply more than 2mm per coat.
- Mix ratio: Trowellable - 10kg plaster requires approx. 3L of water (trowellable)/Brushable - 10kg plaster requires approx. 3.3L of water.
- Ensure that an overlap of 50mm is achieved either side of the bandage.
- Apply a finishing coat of RCS Torino Sands texture to match existing finish.
- Check colour before use
- Ensure same batch numbers are used on a single wall where possible
- Should not be applied in temperatures below 5ºC or above 35ºC
- Apply plaster only when the temperature is between 5°C and 30°C and will be in that range for the 24 hours period following application.
- Painting as per Resene Specification.
NORTH ELEVATION GRIDS A-D 8
- Diamond grind areas where the repair bandage is failing.
- Ensure that an area of 75mm either side of the existing bandage is exposed, to allow new coating to blend in.
- Waterblast surface to remove any contaminants etc.
- Apply a slurry coat of Resin and Multistop bedding to act as a sealer/key coat.
- Mix a solution of Acrylbond and Rockcote MultiStop together and apply using a roller .
- Bandage area with 75mm fiberglass joint mesh and RCS bedding compound.
- Mix a 50:50 mix of acrylbond/water and a 1 kg of MultiStop/Adhesive to the mix.
- Apply a coat of RCS Hydroplast over the bandaged area.
- Do not apply more than 2mm per coat.
- Mix ratio: Trowellable - 10kg plaster requires approx. 3L of water (trowellable)/Brushable - 10kg plaster requires approx. 3.3L of water.
- Ensure that an overlap of 50mm is achieved either side of the bandage.
- Apply a finishing coat of RCS Torino Sands texture to match existing finish.
- Check colour before use
- Ensure same batch numbers are used on a single wall where possible
- Should not be applied in temperatures below 5ºC or above 35ºC
- Apply plaster only when the temperature is between 5°C and 30°C and will be in that range for the 24 hours period following application.
- Painting as per Resene Specification.
NORTH ELEVATION D-J 13
- Diamond grind areas where the repair bandage is failing.
- Ensure that an area of 75mm either side of the existing bandage is exposed, to allow new coating to blend in.
- Waterblast surface to remove any contaminants etc.
- Apply a slurry coat of Resin and Multistop bedding to act as a sealer/key coat.
- Mix a solution of Acrylbond and Rockcote MultiStop together and apply using a roller .
- Bandage area with 75mm fiberglass joint mesh and RCS bedding compound.
- Mix a 50:50 mix of acrylbond/water and a 1 kg of MultiStop/Adhesive to the mix.
- Apply a coat of RCS Hydroplast over the bandaged area.
- Do not apply more than 2mm per coat.
- Mix ratio: Trowellable - 10kg plaster requires approx. 3L of water (trowellable)/Brushable - 10kg plaster requires approx. 3.3L of water.
- Ensure that an overlap of 50mm is achieved either side of the bandage.
- Apply a finishing coat of RCS Torino Sands texture to match existing finish.
- Check colour before use
- Ensure same batch numbers are used on a single wall where possible
- Should not be applied in temperatures below 5ºC or above 35ºC
- Apply plaster only when the temperature is between 5°C and 30°C and will be in that range for the 24 hours period following application.
- Painting as per Resene Specification.
SOUTH ELEVATION D-A 1
- Diamond grind areas where the repair bandage is failing.
- Ensure that an area of 75mm either side of the existing bandage is exposed, to allow new coating to blend in.
- Waterblast surface to remove any contaminants etc.
- Apply a slurry coat of Resin and Multistop bedding to act as a sealer/key coat.
- Mix a solution of Acrylbond and Rockcote MultiStop together and apply using a roller .
- Bandage area with 75mm fiberglass joint mesh and RCS bedding compound.
- Mix a 50:50 mix of acrylbond/water and a 1 kg of MultiStop/Adhesive to the mix.
- Apply a coat of RCS Hydroplast over the bandaged area.
- Do not apply more than 2mm per coat.
- Mix ratio: Trowellable - 10kg plaster requires approx. 3L of water (trowellable)/Brushable - 10kg plaster requires approx. 3.3L of water.
- Ensure that an overlap of 50mm is achieved either side of the bandage.
- Apply a finishing coat of RCS Torino Sands texture to match existing finish.
- Check colour before use
- Ensure same batch numbers are used on a single wall where possible
- Should not be applied in temperatures below 5ºC or above 35ºC
- Apply plaster only when the temperature is between 5°C and 30°C and will be in that range for the 24 hours period following application.
- Painting as per Resene Specification.
WEST/SOUTH ELEVATION GRID 3-1 D
- Diamond grind areas where the repair bandage is failing.
- Ensure that an area of 75mm either side of the existing bandage is exposed, to allow new coating to blend in.
- Waterblast surface to remove any contaminants etc.
- Apply a slurry coat of Resin and Multistop bedding to act as a sealer/key coat.
- Mix a solution of Acrylbond and Rockcote MultiStop together and apply using a roller .
- Bandage area with 75mm fiberglass joint mesh and RCS bedding compound.
- Mix a 50:50 mix of acrylbond/water and a 1 kg of MultiStop/Adhesive to the mix.
- Apply a coat of RCS Hydroplast over the bandaged area.
- Do not apply more than 2mm per coat.
- Mix ratio: Trowellable - 10kg plaster requires approx. 3L of water (trowellable)/Brushable - 10kg plaster requires approx. 3.3L of water.
- Ensure that an overlap of 50mm is achieved either side of the bandage.
- Apply a finishing coat of RCS Torino Sands texture to match existing finish.
- Check colour before use
- Ensure same batch numbers are used on a single wall where possible
- Should not be applied in temperatures below 5ºC or above 35ºC
- Apply plaster only when the temperature is between 5°C and 30°C and will be in that range for the 24 hours period following application.
- Painting as per Resene Specification.
SOUTH ELEVATION J-E 10
- Diamond grind areas where the repair bandage is failing.
- Ensure that an area of 75mm either side of the existing bandage is exposed, to allow new coating to blend in.
- Waterblast surface to remove any contaminants etc.
- Apply a slurry coat of Resin and Multistop bedding to act as a sealer/key coat.
- Mix a solution of Acrylbond and Rockcote MultiStop together and apply using a roller .
- Bandage area with 75mm fiberglass joint mesh and RCS bedding compound.
- Mix a 50:50 mix of acrylbond/water and a 1 kg of MultiStop/Adhesive to the mix.
- Apply a coat of RCS Hydroplast over the bandaged area.
- Do not apply more than 2mm per coat.
- Mix ratio: Trowellable - 10kg plaster requires approx. 3L of water (trowellable)/Brushable - 10kg plaster requires approx. 3.3L of water.
- Ensure that an overlap of 50mm is achieved either side of the bandage.
- Apply a finishing coat of RCS Torino Sands texture to match existing finish.
- Check colour before use
- Ensure same batch numbers are used on a single wall where possible
- Should not be applied in temperatures below 5ºC or above 35ºC
- Apply plaster only when the temperature is between 5°C and 30°C and will be in that range for the 24 hours period following application.
- Painting as per Resene Specification.
WEST ELEVATION 8-5 D
- Diamond grind areas where the repair bandage is failing.
- Ensure that an area of 75mm either side of the existing bandage is exposed, to allow new coating to blend in.
- Waterblast surface to remove any contaminants etc.
- Apply a slurry coat of Resin and Multistop bedding to act as a sealer/key coat.
- Mix a solution of Acrylbond and Rockcote MultiStop together and apply using a roller .
- Bandage area with 75mm fiberglass joint mesh and RCS bedding compound.
- Mix a 50:50 mix of acrylbond/water and a 1 kg of MultiStop/Adhesive to the mix.
- Apply a coat of RCS Hydroplast over the bandaged area.
- Do not apply more than 2mm per coat.
- Mix ratio: Trowellable - 10kg plaster requires approx. 3L of water (trowellable)/Brushable - 10kg plaster requires approx. 3.3L of water.
- Ensure that an overlap of 50mm is achieved either side of the bandage.
- Apply a finishing coat of RCS Torino Sands texture to match existing finish.
- Check colour before use
- Ensure same batch numbers are used on a single wall where possible
- Should not be applied in temperatures below 5ºC or above 35ºC
- Apply plaster only when the temperature is between 5°C and 30°C and will be in that range for the 24 hours period following application.
- Painting as per Resene Specification.