## Project Structure
Site QA | Checklist
Site Establishment
Setout/Surveying checklist
Excauation Checklist
Backfill
Asbestos removal
Demolition
Foundation
Structural Steel
Wall Framing
First Fix Services
Wall lining
Second Fix
Finishing and Painting
Extrernal Work
Commisoning

## Resources
checklist | Site Establishment Checklist
checkpoint | Any relevant dilapidation requirements captured
checkpoint | Attach relevant site establishment photos/ documents
checkpoint | Appropriate isolation of site (hoardings / fencing)
checkpoint | Sufficient & Appropriate site/H&S signage erected
checkpoint | Site establishment completed
checklist | Setout / Surveying Checklist
checkpoint | Any RL's setout are correct, labelled and photographed
checkpoint | Any grid setout are correct, labelled and photographed
checkpoint | Any other relevant setout/ survey documentation attached
checkpoint | Survey work completed, checked and accurate
checklist | Service Location / Isolation Checklist
checkpoint | Power located/Isolated
checkpoint | Hydraulic services located/isolated
checkpoint | Gas located/isolated
checkpoint | Telecommunication/Fibre located/isolated
checkpoint | Any other relevant services located/ isolated
checkpoint | All Services located/ isolated (Pass once all services are located/isolated)
checklist | Bulk Excavation Checklist
checkpoint | Excavation depth determined using appropriate RL's
checkpoint | Confirm location and isolation of relevant services
checkpoint | General excavation documentation and photos attached
checkpoint | Any batters formed correctly
checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint | Trades QA received, attached, reviewed and approved
checkpoint | Excavation completed - Correct locations and RL's achieved
checklist | Detailed Excavation Checklist
checkpoint | Location accurate
checkpoint | Depth correct (allow for site concrete if required)
checkpoint | Width correct (allow for boxing if required)
checkpoint | Any relevant excavation for services is completed and accurate
checkpoint | Excess Material Cleaned up and removed as required
checkpoint | Detailed excavation completed, reviewed and approved
checklist | Backfill Checklist
checkpoint | Backfill methodology and material confirmed
checkpoint | Any formwork/ debris removed from area
checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint | General photos and observations during backfill
checkpoint | Backfill completed correctly and heights checked/ correct
checklist | Demolition Checklist
section | Pre Demolition QA
checkpoint | Traffic management in place (attach TMP)
checkpoint | NVMP completed and attached
checkpoint | Attach any other relevant pre start documentation
checkpoint | All relevant services isolated
bool | Power isolated
bool | Waste/storm water isolated
bool | Gas isolated
bool | Telecommunication/Fibre isolated
bool | Any other relevant services isolated
text | Specify which other services were isolated
checkpoint | General Photos of controls (attach and label)
checkpoint | All pre demolition QA completed and approval given to commence demolition
section | Demolition QA
checkpoint | Prior to demolition, all pre start checks have been completed
checkpoint | General photos and observations of demo (attached and labelled)
section | Demolition Complete
checkpoint | All rubbish/debris removed and area left clean and tidy
checkpoint | Trade Contractor QA received, attached, reviewed and approved
checkpoint | All demolition works completed, checked and approved
checklist | Asbestos Removal Checklist
checkpoint | Initial Environment/Planning Asbestos report attached
checkpoint | Asbestos Removal approved to commence (all pre-commencement considerations allowed for)
checkpoint | Attach relevant asbestos removal photos (Label all photos with relevant location)
checkpoint | Independent asbestos report completed and attached
checkpoint | Trade contractor QA received, attached, reviewed and approved
checkpoint | Any remedial requirements actioned and completed / closed out
checkpoint | All asbestos removed and approval given to progress with work
checklist | Foundation
section | Reinforcing
checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | Raise Remedial / Request trades QA / Signoff
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Welding certificates sited and attached
checkpoint | Mill certificate reviewed, attached and approved
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pour Details
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Pre-Pour Completion (Approval to pour)
checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | All relevant inspections completed and attached
checkpoint | Main contractor inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
text | Supplier Name:
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
checkpoint | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Concrete Distribution
checkpoint | General distribution photos, documents and observations attached
checkpoint | All concrete distributed correctly (area left clean and tidy)
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint | Area left clean and tidy
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
Checklist | Structural Steel
Checklist | Structural Steel
Section | Pre-Erection Checklist
checkpoint | Latest drawings available, checked and referenced
checkpoint | Steel Deliveed to Site & Inspected
checkpoint | Correct elements received
checkpoint | Coating condition acceptable
checkpoint | Dispatch docket correct and photographed
checkpoint | Work area acceptable
checkpoint | Set Out Checked with Architectural Drawings
checkpoint | Checked for Level and RL
checkpoint | Alterations Required On Site / Welds
checkpoint | Steel Set Out & Clashes Resolved
checkpoint | Steel hoisted as per agreed lifting procedure
checkpoint | Steel secured before taking off hook
checkpoint | Crane operated within rating chart capacity
Section | Steel Erection Checks
checkpoint | Correct location and orientation
checkpoint | Steel erected level, plumb and correct pitch
checkpoint | Temporary props, turfers, bracing etc. installed/removed
checkpoint | All fixings appropriately installed
checkpoint | Epoxy and mechanical anchors drilled to correct depths
checkpoint | Epoxy and mechanical anchors tightened
checkpoint | Taper wahers installed, if required
checkpoint | All bolts secure / correctly tensioned
checkpoint | All on-site welding completed correctly
checkpoint | Damaged coatings repaired / touched-up
checklist | Timber Framing
Section | Framing
checkpoint | Room set outs and wall locations consistent with approved plans
checkpoint | Check framing for straigthness
checkpoint | bracing installed
checkpoint | Nogs installed correctly
checkpoint | General photos during installion
checkpoint | Trades QA received, reviewed, attached and approved
Section | COMPACT - Insulation Checklist prior to lining
checkpoint | Area accessible, substrate acceptable and approval to start works (If not comment below)
checkpoint | All delivered materials checked & aligning with consented design and specifications prior to install
checkpoint | General photos, comments and observations during insulation install (Add below)
checkpoint | Double check product once installed & attach relevant evidence
checkpoint | Correct product & R value as per specification (R-Value label attached to wall)
checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s) (Photographic evidence provided)
checklist | Services First Fix Checklist
section | ELECTRICAL - POWER & LIGHTING
checkpoint | Guarantees submitted
checkpoint | Switchboard shop drawings approved
checkpoint | Colour schedules approved
checkpoint | Sound rating details
checkpoint | Number of units per area
checkpoint | Unit position
checkpoint | Clipping
checkpoint | Cable tray supports
checkpoint | Pre-wire inspection
checkpoint | Height of fittings
checkpoint | Fit off
checkpoint | Alignment
checkpoint | Penetrations
checkpoint | Fire wall details
checkpoint | Ceiling lights
checkpoint | Security Wiring
checkpoint | Phone wiring
checkpoint | Data and computer wiring
checkpoint | Compliance certificate provided
checkpoint | As built drawings
checkpoint | Engineer’s inspection booked
checkpoint | Building inspector booked
checkpoint | Clean up work area.
section | ELECTRICAL - SECURITY SYSTEMS
checkpoint | Shop drawing received and approved
checkpoint | Guarantees submitted
checkpoint | Prototypes / approvals
checkpoint | Colour schedule approved
checkpoint | Off site manufacture
checkpoint | Delivery inspection
checkpoint | Visual inspection
checkpoint | Welding / electroplated / coatings / finishes
checkpoint | Fixings / fit
checkpoint | Test
checkpoint | Protection
checkpoint | As built drawings
checkpoint | Engineer’s inspection booked
checkpoint | Building inspector booked
checkpoint | Clean up work area.
section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint | Shop drawing received and approved
checkpoint | Guarantees submitted
checkpoint | Layout approval - shop drawings
checkpoint | Pipework damage / corrosion / scale
checkpoint | Seismic security batteries control panels
checkpoint | Ensure installation check carried out
checkpoint | Ensure pressure test check carried out
checkpoint | Identification wiring / pipework
checkpoint | Completion certificates, insurance / local body approvals
checkpoint | Security system master keys to local fire service
checkpoint | As built drawings
checkpoint | Producer Statements
checkpoint | Engineer’s inspection booked
checkpoint | Building inspector booked
checkpoint | Clean up work area
section | QA - Plumbing First Fix
checkpoint | Shop drawing received and approved
checkpoint | Guarantees submitted
checkpoint | Materials comply with specs
checkpoint | Material storage okay
checkpoint | Appliances comply with specs
checkpoint | Appliance storage okay
checkpoint | Pipes cut clean and square
checkpoint | Supports, anchors, hangers and clips
checkpoint | Pipe alignment
checkpoint | Pipe clearance above future ceilings
checkpoint | Pipework protected at holes and notches
checkpoint | Pipe joints
checkpoint | Joint and caulking compound
checkpoint | Lagging
checkpoint | Appliances
checkpoint | Spouting and gutters
checkpoint | Vents and outlets
checkpoint | Appearance and layout
checkpoint | Pipe runs clean before test
checkpoint | Test to authorities satisfaction
checkpoint | As built drawings
checkpoint | Engineer’s inspection booked
checkpoint | Building inspector booked
checkpoint | Clean up work area
section | Security / Data / Comms
checkpoint | Shop drawing received and approved
checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
checkpoint | Consultant inspection
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
section | MECHANICAL SERVICES - HVAC
checkpoint | Shop drawing received and approved
checkpoint | Guarantees submitted
checkpoint | Unit location
checkpoint | Access for installation
checkpoint | Unit support brackets
checkpoint | Pipe type
checkpoint | Pipe alignment
checkpoint | Fixings
checkpoint | Pipe support brackets
checkpoint | Pipe connections
checkpoint | Pipe insulation
checkpoint | Wall insulations
checkpoint | Boot locations
checkpoint | Inlet and outlet locations
checkpoint | Labelling
checkpoint | Unit wiring
checkpoint | Testing
checkpoint | Grilles
checkpoint | Isolating valves
checkpoint | Fire dampers switch boards and controls
checkpoint | Fireproofing
checkpoint | As built drawings
checkpoint | Engineer’s inspection booked
checkpoint | Building inspector booked
checkpoint | Clean up work area
checklist | Wall lining
section | Gib Lining
checkpoint | All preline services completed and approval given to line
checkpoint | moisture content checked, recorded and acceptable
checkpoint | Correct lining (Checked and approved)
checkpoint | Correct fixings used and installed at correct centres
checkpoint | Any bracing elements completed to design specification
checkpoint | check if service are required in this location
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All lining completed, checked and approved
section | Gib Stopping Checklist
checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint | Correct stopping product and applied correctly
checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All Stopping completed and specified level of finish achieved
checklist | WINDOWS & DOORS Installation
section | Window Installation
checkpoint | Shop drawings submitted and approved
checkpoint | Shop drawings - approved issue No.
checkpoint | Sealant type approved
checkpoint | Dimensions
checkpoint | Fixings
checkpoint | Set out
checkpoint | Joints
checkpoint | Drainage apertures
checkpoint | alignment
checkpoint | sealant
checkpoint | glazing
checkpoint | hardware
checkpoint | draught seals
checkpoint | Test Operation
checkpoint | Cleaned
checkpoint | Protection
checkpoint | Engineer’s inspection booked
checkpoint | Building inspector booked
checkpoint | Clean up work area
section | Door Installation
checkpoint | Shop drawings submitted and approved
checkpoint | Shop drawings - approved issue No.
checkpoint | Dimensions
checkpoint | Fixings
checkpoint | Set out
checkpoint | Joints
checkpoint | alignment
checkpoint | sealant
checkpoint | glazing
checkpoint | hardware
checkpoint | Door Installation complete
checklist | Services Second Fix Checklist
section | Electrical
checkpoint | Second Fix Completed
checkpoint | Trades QA received, reviewed, attached and approved
section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint | Second Fix Completed
checkpoint | Trades QA received, reviewed, attached and approved
section | QA - Plumbing First Fix
checkpoint | Second Fix Completed
checkpoint | Trades QA received, reviewed, attached and approved
section | Security / Data / Comms
checkpoint | Second Fix Completed
checkpoint | Trades QA received, reviewed, attached and approved
section | Mechanical Services First Fix
checkpoint | Second Fix Completed
checkpoint | Trades QA received, reviewed, attached and approved
section | Ceiling Grid Checklist
checkpoint | Service markout completed, checked and acceptable (clashes considered)
checkpoint | Ceiling Height confirmed
checkpoint | Appropriate fixings used and installed as per required specification
checkpoint | Appropriate spacings for respective grid elements
checkpoint | All ceiling grid completed in respective area to required specification (Attach photograph of respective completed grid)
checkpoint | Trades QA received, reviewed, attached and approved
section | Ceiling Tile Checklist
checkpoint | Correct tiles installed as per design
checkpoint | Services tiles installed, clean & tidy
checkpoint | All other tiles installed, clean & tidy
checkpoint | All tiles installed, mark/damage free and area completed to required specification (attach relevant photos)
checkpoint | All tiles installed and area left clean and tidy (attach relevant photos)
checkpoint | Trades QA received, reviewed, attached and approved
checklist | Finishing and Painting
Section | Painting
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Second Fix Completed
checkpoint | Painting inspection completed & issues closed out
Section | Flooring
checkpoint | Material inspection (on site)
checkpoint | Storage and protection
checkpoint | Inspect and accept surfaces
checkpoint | Surface preparation
checkpoint | Mortar
checkpoint | Installation methods
checkpoint | Movement joints
checkpoint | Bedding
checkpoint | Grouting
checkpoint | Finished surface inspection
checkpoint | Protection
checkpoint | Barrier protection
checkpoint | Clean up work area
checkpoint | Flooring inspection completed & issues closed out
Section | Joinery
checkpoint | Shop drawing received and approved
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Second Fix Completed
checkpoint | Joinery inspection completed & issues closed out
checklist | External Work
Section | Roofing and Cladding
checkpoint | Colour scheme approved
checkpoint | Coil ordered
checkpoint | Roof cladding materials
checkpoint | Battens/purlins
checkpoint | Size, quality, rafter fixings
checkpoint | Other framing
checkpoint | Building paper, netting insulation
checkpoint | Fixings
checkpoint | Expansion joints, laps
checkpoint | Spouting, gutters, downpipes
checkpoint | Rain heads, overflows, wire baskets
checkpoint | Bird proofing
checkpoint | Alignment ridge, hip, valley, and falls
checkpoint | Surface treatment
checkpoint | Mechanical damage protection
checkpoint | Accessories flashings
checkpoint | Weathering Details, air passages
checkpoint | Engineer’s inspection booked
checkpoint | Building inspector booked
checkpoint | Clean up work area
checklist | Compliance certificate
Section | Electrical
checkpoint | Energy Works Certificate - Electrical
checkpoint | Emergency lighting
checkpoint | Emergency power supply
checkpoint | Asbuilts and Manual
checkpoint | Request Documentation / Signoff
checkpoint | Producer Statement (PS3)
section | Data
checkpoint | Data test result
checkpoint | As built Plan (ICT)
checkpoint | ICT Test cabling test results
checkpoint | Request Documentation / Signoff
checkpoint | Producer Statement (PS3)
section | Hydraulics/Plumbing
checkpoint | Pressure Testing of Piping
checkpoint | Request Documentation / Signoff
checkpoint | Producer Statement (PS3)
section | Fire
checkpoint | Fire Sprinkler System Certification
checkpoint | Request Documentation / Signoff
checkpoint | Producer Statement (PS3)
checkpoint | Fire Alarm System Certification
checkpoint | Request Documentation / Signoff
checkpoint | Installation, Testing and Commissioning Certificates for Fire Safety Systems
checkpoint | Producer Statement (PS3)
section | Storm Water
checkpoint | Producer statement construction (PS3) is to be submitted by the certifying plumber or drain layer
checkpoint | Request Documentation / Signoff
section | Acoustic Testing
checkpoint | A test certificate is to be submitted by the acoustic engineer to demonstrate compliance with the acoustic requirements
checkpoint | Request Documentation / Signoff
section | Mechanical
checkpoint | Commissioning
checkpoint | Request Documentation / Signoff
checkpoint | Producer Statement (PS3)
section | Structural Steel
checkpoint | Material certificate
checkpoint | Site QA from Sub contractor
checkpoint | Producer Statement (PS3)
section | Ceiling
checkpoint | Material certificate
checkpoint | Site QA from Sub contractor
checkpoint | Producer Statement (PS3)