## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Services First Fix Checklist |  |  |  |  | Yes | Services First Fix Checklist | 0515c4a3-127b-499e-8177-7561d906f9c8
checkpoint-group |  |  | section | ELECTRICAL - POWER & LIGHTING
checkpoint-status |  |  | checkpoint | Guarantees submitted
checkpoint-status |  |  | checkpoint | Switchboard shop drawings approved
checkpoint-status |  |  | checkpoint | Colour schedules approved
checkpoint-status |  |  | checkpoint | Sound rating details
checkpoint-status |  |  | checkpoint | Number of units per area
checkpoint-status |  |  | checkpoint | Unit position
checkpoint-status |  |  | checkpoint | Clipping
checkpoint-status |  |  | checkpoint | Cable tray supports
checkpoint-status |  |  | checkpoint | Pre-wire inspection
checkpoint-status |  |  | checkpoint | Height of fittings
checkpoint-status |  |  | checkpoint | Fit off
checkpoint-status |  |  | checkpoint | Alignment
checkpoint-status |  |  | checkpoint | Penetrations
checkpoint-status |  |  | checkpoint | Fire wall details
checkpoint-status |  |  | checkpoint | Ceiling lights
checkpoint-status |  |  | checkpoint | Security Wiring
checkpoint-status |  |  | checkpoint | Phone wiring
checkpoint-status |  |  | checkpoint | Data and computer wiring
checkpoint-status |  |  | checkpoint | Compliance certificate provided
checkpoint-status |  |  | checkpoint | As built drawings
checkpoint-status |  |  | checkpoint | Engineer’s inspection booked
checkpoint-status |  |  | checkpoint | Building inspector booked
checkpoint-status |  |  | checkpoint | Clean up work area.
checkpoint-group |  |  | section | ELECTRICAL - SECURITY SYSTEMS
checkpoint-status |  |  | checkpoint | Shop drawing received and approved
checkpoint-status |  |  | checkpoint | Guarantees submitted
checkpoint-status |  |  | checkpoint | Prototypes / approvals
checkpoint-status |  |  | checkpoint | Colour schedule approved
checkpoint-status |  |  | checkpoint | Off site manufacture
checkpoint-status |  |  | checkpoint | Delivery inspection
checkpoint-status |  |  | checkpoint | Visual inspection
checkpoint-status |  |  | checkpoint | Welding / electroplated / coatings / finishes
checkpoint-status |  |  | checkpoint | Fixings / fit
checkpoint-status |  |  | checkpoint | Test
checkpoint-status |  |  | checkpoint | Protection
checkpoint-status |  |  | checkpoint | As built drawings
checkpoint-status |  |  | checkpoint | Engineer’s inspection booked
checkpoint-status |  |  | checkpoint | Building inspector booked
checkpoint-status |  |  | checkpoint | Clean up work area.
checkpoint-group |  |  | section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint-status |  |  | checkpoint | Shop drawing received and approved
checkpoint-status |  |  | checkpoint | Guarantees submitted
checkpoint-status |  |  | checkpoint | Layout approval - shop drawings
checkpoint-status |  |  | checkpoint | Pipework damage / corrosion / scale
checkpoint-status |  |  | checkpoint | Seismic security batteries control panels
checkpoint-status |  |  | checkpoint | Ensure installation check carried out
checkpoint-status |  |  | checkpoint | Ensure pressure test check carried out
checkpoint-status |  |  | checkpoint | Identification wiring / pipework
checkpoint-status |  |  | checkpoint | Completion certificates, insurance / local body approvals
checkpoint-status |  |  | checkpoint | Security system master keys to local fire service
checkpoint-status |  |  | checkpoint | As built drawings
checkpoint-status |  |  | checkpoint | Producer Statements
checkpoint-status |  |  | checkpoint | Engineer’s inspection booked
checkpoint-status |  |  | checkpoint | Building inspector booked
checkpoint-status |  |  | checkpoint | Clean up work area
checkpoint-group |  |  | section | QA - Plumbing First Fix
checkpoint-status |  |  | checkpoint | Shop drawing received and approved
checkpoint-status |  |  | checkpoint | Guarantees submitted
checkpoint-status |  |  | checkpoint | Materials comply with specs
checkpoint-status |  |  | checkpoint | Material storage okay
checkpoint-status |  |  | checkpoint | Appliances comply with specs
checkpoint-status |  |  | checkpoint | Appliance storage okay
checkpoint-status |  |  | checkpoint | Pipes cut clean and square
checkpoint-status |  |  | checkpoint | Supports, anchors, hangers and clips
checkpoint-status |  |  | checkpoint | Pipe alignment
checkpoint-status |  |  | checkpoint | Pipe clearance above future ceilings
checkpoint-status |  |  | checkpoint | Pipework protected at holes and notches
checkpoint-status |  |  | checkpoint | Pipe joints
checkpoint-status |  |  | checkpoint | Joint and caulking compound
checkpoint-status |  |  | checkpoint | Lagging
checkpoint-status |  |  | checkpoint | Appliances
checkpoint-status |  |  | checkpoint | Spouting and gutters
checkpoint-status |  |  | checkpoint | Vents and outlets
checkpoint-status |  |  | checkpoint | Appearance and layout
checkpoint-status |  |  | checkpoint | Pipe runs clean before test
checkpoint-status |  |  | checkpoint | Test to authorities satisfaction
checkpoint-status |  |  | checkpoint | As built drawings
checkpoint-status |  |  | checkpoint | Engineer’s inspection booked
checkpoint-status |  |  | checkpoint | Building inspector booked
checkpoint-status |  |  | checkpoint | Clean up work area
checkpoint-group |  |  | section | Security / Data / Comms
checkpoint-status |  |  | checkpoint | Shop drawing received and approved
checkpoint-status |  |  | checkpoint | First Fix checks with Subcontractor - tick when all below are checked and complete
checkpoint-status |  |  | checkpoint | Consultant inspection
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All required testing complete
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Consultant sign off
checkpoint-group |  |  | section | MECHANICAL SERVICES - HVAC
checkpoint-status |  |  | checkpoint | Shop drawing received and approved
checkpoint-status |  |  | checkpoint | Guarantees submitted
checkpoint-status |  |  | checkpoint | Unit location
checkpoint-status |  |  | checkpoint | Access for installation
checkpoint-status |  |  | checkpoint | Unit support brackets
checkpoint-status |  |  | checkpoint | Pipe type
checkpoint-status |  |  | checkpoint | Pipe alignment
checkpoint-status |  |  | checkpoint | Fixings
checkpoint-status |  |  | checkpoint | Pipe support brackets
checkpoint-status |  |  | checkpoint | Pipe connections
checkpoint-status |  |  | checkpoint | Pipe insulation
checkpoint-status |  |  | checkpoint | Wall insulations
checkpoint-status |  |  | checkpoint | Boot locations
checkpoint-status |  |  | checkpoint | Inlet and outlet locations
checkpoint-status |  |  | checkpoint | Labelling
checkpoint-status |  |  | checkpoint | Unit wiring
checkpoint-status |  |  | checkpoint | Testing
checkpoint-status |  |  | checkpoint | Grilles
checkpoint-status |  |  | checkpoint | Isolating valves
checkpoint-status |  |  | checkpoint | Fire dampers switch boards and controls
checkpoint-status |  |  | checkpoint | Fireproofing
checkpoint-status |  |  | checkpoint | As built drawings
checkpoint-status |  |  | checkpoint | Engineer’s inspection booked
checkpoint-status |  |  | checkpoint | Building inspector booked
checkpoint-status |  |  | checkpoint | Clean up work area
checklist-flat |  |  | checklist | Setout / Surveying Checklist |  |  |  |  | Yes | Setout / Surveying Checklist | 079ff2a9-8675-4b6a-9f69-e4c75458e008
checkpoint-status |  |  | checkpoint | Any RL's setout are correct, labelled and photographed
checkpoint-status |  |  | checkpoint | Any grid setout are correct, labelled and photographed
checkpoint-status |  |  | checkpoint | Any other relevant setout/ survey documentation attached
checkpoint-status |  |  | checkpoint | Survey work completed, checked and accurate
checklist-sectioned |  |  | checklist | External Work |  |  |  |  | Yes | External Work | 166943e5-35a9-4dd5-8557-9ca6521ad8c8
checkpoint-group |  |  | section | Roofing and Cladding
checkpoint-status |  |  | checkpoint | Colour scheme approved
checkpoint-status |  |  | checkpoint | Coil ordered
checkpoint-status |  |  | checkpoint | Roof cladding materials
checkpoint-status |  |  | checkpoint | Battens/purlins
checkpoint-status |  |  | checkpoint | Size, quality, rafter fixings
checkpoint-status |  |  | checkpoint | Other framing
checkpoint-status |  |  | checkpoint | Building paper, netting insulation
checkpoint-status |  |  | checkpoint | Fixings
checkpoint-status |  |  | checkpoint | Expansion joints, laps
checkpoint-status |  |  | checkpoint | Spouting, gutters, downpipes
checkpoint-status |  |  | checkpoint | Rain heads, overflows, wire baskets
checkpoint-status |  |  | checkpoint | Bird proofing
checkpoint-status |  |  | checkpoint | Alignment ridge, hip, valley, and falls
checkpoint-status |  |  | checkpoint | Surface treatment
checkpoint-status |  |  | checkpoint | Mechanical damage protection
checkpoint-status |  |  | checkpoint | Accessories flashings
checkpoint-status |  |  | checkpoint | Weathering Details, air passages
checkpoint-status |  |  | checkpoint | Engineer’s inspection booked
checkpoint-status |  |  | checkpoint | Building inspector booked
checkpoint-status |  |  | checkpoint | Clean up work area
checklist-sectioned |  |  | checklist | Wall lining |  |  |  |  | Yes | Wall lining | 2a21eb00-b38b-4054-8e25-1376c69681ff
checkpoint-group |  |  | section | Gib Lining
checkpoint-status |  |  | checkpoint | All preline services completed and approval given to line
checkpoint-status |  |  | checkpoint | moisture content checked, recorded and acceptable
checkpoint-status |  |  | checkpoint | Correct lining (Checked and approved)
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | check if service are required in this location
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All lining completed, checked and approved
checkpoint-group |  |  | section | Gib Stopping Checklist
checkpoint-status |  |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | All Stopping completed and specified level of finish achieved
checklist-flat |  |  | checklist | Asbestos Removal Checklist |  |  |  |  | Yes | Asbestos Removal Checklist | 36a36e4e-f91b-44a8-a318-b2a7ae9c7ebd
checkpoint-status |  |  | checkpoint | Initial Environment/Planning Asbestos report attached
checkpoint-status |  |  | checkpoint | Asbestos Removal approved to commence (all pre-commencement considerations allowed for)
checkpoint-status |  |  | checkpoint | Attach relevant asbestos removal photos (Label all photos with relevant location)
checkpoint-status |  |  | checkpoint | Independent asbestos report completed and attached
checkpoint-status |  |  | checkpoint | Trade contractor QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Any remedial requirements actioned and completed / closed out
checkpoint-status |  |  | checkpoint | All asbestos removed and approval given to progress with work
checklist-sectioned |  |  | checklist | Compliance certificate |  |  |  |  | Yes | Compliance certificate | 3c1103b6-df04-4721-802f-ef49bdb7a29e
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Energy Works Certificate - Electrical?
checkpoint-status |  |  | checkpoint | Emergency lighting
checkpoint-status |  |  | checkpoint | Emergency power supply
checkpoint-status |  |  | checkpoint | Asbuilts and Manual
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checkpoint-group |  |  | section | Data
checkpoint-status |  |  | checkpoint | Data test result
checkpoint-status |  |  | checkpoint | As built Plan (ICT)
checkpoint-status |  |  | checkpoint | ICT Test cabling test results
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checkpoint-group |  |  | section | Hydraulics/Plumbing
checkpoint-status |  |  | checkpoint | Pressure Testing of Piping
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checkpoint-group |  |  | section | Fire
checkpoint-status |  |  | checkpoint | Fire Sprinkler System Certification
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checkpoint-status |  |  | checkpoint | Fire Alarm System Certification
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-status |  |  | checkpoint | Installation, Testing and Commissioning Certificates for Fire Safety Systems
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | Producer statement construction (PS3) is to be submitted by the certifying plumber or drain layer
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-group |  |  | section | Acoustic Testing
checkpoint-status |  |  | checkpoint | A test certificate is to be submitted by the acoustic engineer to demonstrate compliance with the acoustic requirements
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-group |  |  | section | Mechanical
checkpoint-status |  |  | checkpoint | Commissioning
checkpoint-status |  |  | checkpoint | Request Documentation / Signoff
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checkpoint-group |  |  | section | Structural Steel
checkpoint-status |  |  | checkpoint | Material certificate
checkpoint-status |  |  | checkpoint | Site QA from Sub contractor
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checkpoint-group |  |  | section | Ceiling
checkpoint-status |  |  | checkpoint | Material certificate
checkpoint-status |  |  | checkpoint | Site QA from Sub contractor
checkpoint-status |  |  | checkpoint | Producer Statement (PS3)
checklist-sectioned |  |  | checklist | Foundation |  |  |  |  | Yes | Foundation | 59ad80c3-edc0-49a5-a685-eb72abd7d7dc
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request trades QA / Signoff
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Welding certificates sited and attached
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group |  |  | section | Pour Details
text | fd7c8a17-9ed2-5df9-89ef-16eb621e8932 | Data not allowed on checkpoint-group. | textbox | Area to be poured:
text | 740ddf9d-1c8c-5a84-9eb3-76ceddec9a83 | Data not allowed on checkpoint-group. | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed (locations checked and accurate)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
text | 7d3496a7-521c-5a47-abfa-2fc501393245 | Data not allowed on checkpoint-group. | textbox | Supplier Name:
text | 06f55d7a-2af3-55e9-8d41-b870f1ba7eb7 | Data not allowed on checkpoint-group. | textbox | Specified concrete strength:
text | 89220adb-d7c6-5354-b951-e2aa287a6a6e | Data not allowed on checkpoint-group. | textbox | Concrete strength ordered:
text | 4336e09b-fd39-54dd-80c5-1b73c1ed05b1 | Data not allowed on checkpoint-group. | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status |  |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | 6961cd39-9908-56df-a74e-46d79c5ee55c | DataPoint is missing 'button' values | button | Is the cover correct to specification
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat |  |  | checklist | Site Establishment Checklist |  |  |  |  | Yes | Site Establishment Checklist | 637563c9-bb1a-40ae-a90b-32e69459ebd3
checkpoint-status |  |  | checkpoint | Any relevant dilapidation requirements captured
checkpoint-status |  |  | checkpoint | Attach relevant site establishment photos/ documents
checkpoint-status |  |  | checkpoint | Appropriate isolation of site (hoardings / fencing)
checkpoint-status |  |  | checkpoint | Sufficient & Appropriate site/H&S signage erected
checkpoint-status |  |  | checkpoint | Site establishment completed
checklist-sectioned |  |  | checklist | Timber Framing |  |  |  |  | Yes | Timber Framing | 768f6028-3cd1-483b-bd71-3441da700eb4
checkpoint-group |  |  | section | Framing
checkpoint-status |  |  | checkpoint | Room set outs and wall locations consistent with approved plans
checkpoint-status |  |  | checkpoint | Check framing for straigthness
checkpoint-status |  |  | checkpoint | bracing installed
checkpoint-status |  |  | checkpoint | Nogs installed correctly
checkpoint-status |  |  | checkpoint | General photos during installion
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group |  |  | section | COMPACT - Insulation Checklist prior to lining
checkpoint-status |  |  | checkpoint | Area accessible, substrate acceptable and approval to start works (If not comment below)
checkpoint-status |  |  | checkpoint | All delivered materials checked & aligning with consented design and specifications prior to install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during insulation install (Add below)
checkpoint-status |  |  | checkpoint | Double check product once installed & attach relevant evidence
checkpoint-status |  |  | checkpoint | Correct product & R value as per specification (R-Value label attached to wall)
checkpoint-status |  |  | checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s) (Photographic evidence provided)
checklist-flat |  |  | checklist | Service Location / Isolation Checklist |  |  |  |  | Yes | Service Location / Isolation Checklist | 7bff7ad5-a51f-4e0f-a615-6821e5433e37
checkpoint-status |  |  | checkpoint | Power located/Isolated
checkpoint-status |  |  | checkpoint | Hydraulic services located/isolated
checkpoint-status |  |  | checkpoint | Gas located/isolated
checkpoint-status |  |  | checkpoint | Telecommunication/Fibre located/isolated
checkpoint-status |  |  | checkpoint | Any other relevant services located/ isolated
checkpoint-status |  |  | checkpoint | All Services located/ isolated (Pass once all services are located/isolated)
checklist-sectioned |  |  | checklist | Structural Steel |  |  |  |  | Yes | Structural Steel | 8ca30d5d-7d7d-4ad4-aff8-2adff316a569
checkpoint-group |  |  | section | Pre-Erection Checklist
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-status |  |  | checkpoint | Steel Deliveed to Site & Inspected
checkpoint-status |  |  | checkpoint | Correct elements received
checkpoint-status |  |  | checkpoint | Coating condition acceptable
checkpoint-status |  |  | checkpoint | Dispatch docket correct and photographed
checkpoint-status |  |  | checkpoint | Work area acceptable
checkpoint-status |  |  | checkpoint | Set Out Checked with Architectural Drawings
checkpoint-status |  |  | checkpoint | Checked for Level and RL
checkpoint-status |  |  | checkpoint | Alterations Required On Site / Welds
checkpoint-status |  |  | checkpoint | Steel Set Out & Clashes Resolved
checkpoint-status |  |  | checkpoint | Steel hoisted as per agreed lifting procedure
checkpoint-status |  |  | checkpoint | Steel secured before taking off hook
checkpoint-status |  |  | checkpoint | Crane operated within rating chart capacity
checkpoint-group |  |  | section | Steel Erection Checks
checkpoint-status |  |  | checkpoint | Correct location and orientation
checkpoint-status |  |  | checkpoint | Steel erected level, plumb and correct pitch
checkpoint-status |  |  | checkpoint | Temporary props, turfers, bracing etc. installed/removed
checkpoint-status |  |  | checkpoint | All fixings appropriately installed
checkpoint-status |  |  | checkpoint | Epoxy and mechanical anchors drilled to correct depths
checkpoint-status |  |  | checkpoint | Epoxy and mechanical anchors tightened
checkpoint-status |  |  | checkpoint | Taper wahers installed, if required
checkpoint-status |  |  | checkpoint | All bolts secure / correctly tensioned
checkpoint-status |  |  | checkpoint | All on-site welding completed correctly
checkpoint-status |  |  | checkpoint | Damaged coatings repaired / touched-up
checklist-flat |  |  | checklist | Bulk Excavation Checklist |  |  |  |  | Yes | Bulk Excavation Checklist | 93a118d8-3d7b-4304-b4f7-e15426d53973
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | General excavation documentation and photos attached
checkpoint-status |  |  | checkpoint | Any batters formed correctly
checkpoint-status |  |  | checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-sectioned |  |  | checklist | Finishing and Painting |  |  |  |  | Yes | Finishing and Painting | 96d60834-8bbe-4605-a83f-f928c6ed8fee
checkpoint-group |  |  | section | Painting
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Second Fix Completed
checkpoint-status |  |  | checkpoint | Painting inspection completed & issues closed out
checkpoint-group |  |  | section | Flooring
checkpoint-status |  |  | checkpoint | Material inspection (on site)
checkpoint-status |  |  | checkpoint | Storage and protection
checkpoint-status |  |  | checkpoint | Inspect and accept surfaces
checkpoint-status |  |  | checkpoint | Surface preparation
checkpoint-status |  |  | checkpoint | Mortar
checkpoint-status |  |  | checkpoint | Installation methods
checkpoint-status |  |  | checkpoint | Movement joints
checkpoint-status |  |  | checkpoint | Bedding
checkpoint-status |  |  | checkpoint | Grouting
checkpoint-status |  |  | checkpoint | Finished surface inspection
checkpoint-status |  |  | checkpoint | Protection
checkpoint-status |  |  | checkpoint | Barrier protection
checkpoint-status |  |  | checkpoint | Clean up work area
checkpoint-status |  |  | checkpoint | Flooring inspection completed & issues closed out
checkpoint-group |  |  | section | Joinery
checkpoint-status |  |  | checkpoint | Shop drawing received and approved
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Second Fix Completed
checkpoint-status |  |  | checkpoint | Joinery inspection completed & issues closed out
checklist-flat |  |  | checklist | Backfill Checklist |  |  |  |  | Yes | Backfill Checklist | aa3d1ecb-4d3e-4227-8f37-6d62a26040b4
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned |  |  | checklist | WINDOWS & DOORS Installation |  |  |  |  | Yes | WINDOWS & DOORS Installation | b1dc08dd-4c0b-4926-bdc6-484433ed6647
checkpoint-group |  |  | section | Window Installation
checkpoint-status |  |  | checkpoint | Shop drawings submitted and approved
checkpoint-status |  |  | checkpoint | Shop drawings - approved issue No.
checkpoint-status |  |  | checkpoint | Sealant type approved
checkpoint-status |  |  | checkpoint | Dimensions
checkpoint-status |  |  | checkpoint | Fixings
checkpoint-status |  |  | checkpoint | Set out
checkpoint-status |  |  | checkpoint | Joints
checkpoint-status |  |  | checkpoint | Drainage apertures
checkpoint-status |  |  | checkpoint | alignment
checkpoint-status |  |  | checkpoint | sealant
checkpoint-status |  |  | checkpoint | glazing
checkpoint-status |  |  | checkpoint | hardware
checkpoint-status |  |  | checkpoint | draught seals
checkpoint-status |  |  | checkpoint | Test Operation
checkpoint-status |  |  | checkpoint | Cleaned
checkpoint-status |  |  | checkpoint | Protection
checkpoint-status |  |  | checkpoint | Engineer’s inspection booked
checkpoint-status |  |  | checkpoint | Building inspector booked
checkpoint-status |  |  | checkpoint | Clean up work area
checkpoint-group |  |  | section | Door Installation
checkpoint-status |  |  | checkpoint | Shop drawings submitted and approved
checkpoint-status |  |  | checkpoint | Shop drawings - approved issue No.
checkpoint-status |  |  | checkpoint | Dimensions
checkpoint-status |  |  | checkpoint | Fixings
checkpoint-status |  |  | checkpoint | Set out
checkpoint-status |  |  | checkpoint | Joints
checkpoint-status |  |  | checkpoint | alignment
checkpoint-status |  |  | checkpoint | sealant
checkpoint-status |  |  | checkpoint | glazing
checkpoint-status |  |  | checkpoint | hardware
checkpoint-status |  |  | checkpoint | Door Installation complete
checklist-sectioned |  |  | checklist | Services Second Fix Checklist |  |  |  |  | Yes | Services Second Fix Checklist | b6415f30-bf15-4321-ad9e-84d693bfa9bc
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Second Fix Completed
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group |  |  | section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint-status |  |  | checkpoint | Second Fix Completed
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group |  |  | section | QA - Plumbing First Fix
checkpoint-status |  |  | checkpoint | Second Fix Completed
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group |  |  | section | Security / Data / Comms
checkpoint-status |  |  | checkpoint | Second Fix Completed
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group |  |  | section | Mechanical Services First Fix
checkpoint-status |  |  | checkpoint | Second Fix Completed
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group |  |  | section | Ceiling Grid Checklist
checkpoint-status |  |  | checkpoint | Service markout completed, checked and acceptable (clashes considered)
checkpoint-status |  |  | checkpoint | Ceiling Height confirmed
checkpoint-status |  |  | checkpoint | Appropriate fixings used and installed as per required specification
checkpoint-status |  |  | checkpoint | Appropriate spacings for respective grid elements
checkpoint-status |  |  | checkpoint | All ceiling grid completed in respective area to required specification (Attach photograph of respective completed grid)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checkpoint-group |  |  | section | Ceiling Tile Checklist
checkpoint-status |  |  | checkpoint | Correct tiles installed as per design
checkpoint-status |  |  | checkpoint | Services tiles installed, clean & tidy
checkpoint-status |  |  | checkpoint | All other tiles installed, clean & tidy
checkpoint-status |  |  | checkpoint | All tiles installed, mark/damage free and area completed to required specification (attach relevant photos)
checkpoint-status |  |  | checkpoint | All tiles installed and area left clean and tidy (attach relevant photos)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
checklist-sectioned |  |  | checklist | Demolition Checklist |  |  |  |  | Yes | Demolition Checklist | e2aebba6-addb-4572-ae42-0dcd315200b4
checkpoint-group |  |  | section | Pre Demolition QA
checkpoint-status |  |  | checkpoint | Traffic management in place (attach TMP)
checkpoint-status |  |  | checkpoint | NVMP completed and attached
checkpoint-status |  |  | checkpoint | Attach any other relevant pre start documentation
checkpoint-status |  |  | checkpoint | All relevant services isolated
boolean | 7c3c62d5-0705-5428-9c2e-32fbac91691b |  | tickbox | Power isolated
boolean | e15de51d-749b-55d4-8837-6cb7f89633da |  | tickbox | Waste/storm water isolated
boolean | 932d3adb-49f9-5cda-a84b-2ecae76cb0a9 |  | tickbox | Gas isolated
boolean | 14ac7a6e-2046-5fef-b8a9-aa1c44dbc9c0 |  | tickbox | Telecommunication/Fibre isolated
boolean | 6755aa20-23ca-5438-9224-c7c5e74c9407 |  | tickbox | Any other relevant services isolated
text | c92b68b1-57af-5225-9228-5d411faaace5 |  | textbox | Specify which other services were isolated
checkpoint-status |  |  | checkpoint | General Photos of controls (attach and label)
checkpoint-status |  |  | checkpoint | All pre demolition QA completed and approval given to commence demolition
checkpoint-group |  |  | section | Demolition QA
checkpoint-status |  |  | checkpoint | Prior to demolition, all pre start checks have been completed
checkpoint-status |  |  | checkpoint | General photos and observations of demo (attached and labelled)
checkpoint-group |  |  | section | Demolition Complete
checkpoint-status |  |  | checkpoint | All rubbish/debris removed and area left clean and tidy
checkpoint-status |  |  | checkpoint | Trade Contractor QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | All demolition works completed, checked and approved
checklist-flat |  |  | checklist | Detailed Excavation Checklist |  |  |  |  | Yes | Detailed Excavation Checklist | fd8f1e2c-c8e9-47c8-a24a-f220501d1536
checkpoint-status |  |  | checkpoint | Location accurate
checkpoint-status |  |  | checkpoint | Depth correct (allow for site concrete if required)
checkpoint-status |  |  | checkpoint | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Any relevant excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess Material Cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved