## Sheet1
Onslow College
Phase 2 Block N &K
Stage 2
Upper Roof
Delap photos
Clean roof
Remove existing cap flashings
Install screws to substrate
Install Trough Infill PIR
New Vapour Barrier
New 40mm PIR
New Fibretite Membrane
New Fascias
Parapet flashing
Gutters and Down pipies
Lower Roof
Delap photos
Clean Roof
Remove existing cap flashings
Install screws to substrate
Install Trough Infill PIR
New Vapour Barrier
New 40mm PIR
New Fibretite Membrane
New Fascias
Parapet flashing
Gutters and Down pipies
Windows
nAJ05
Window removed
New Window Opening
Sill chamered to form Fall
Window Tape
Sill Flashing Installed
Cavity Batten Installed
Window Installed
Head Flashing Installed
Gib and Architraves
Window opener installed
nAJ06
Window removed
New Window Opening
Sill chamered to form Fall
Window Tape
Sill Flashing Installed
Cavity Batten Installed
Window Installed
Head Flashing Installed
Gib and Architraves
Window opener installed
nAJ07
Window removed
New Window Opening
Sill chamered to form Fall
Window Tape
Sill Flashing Installed
Cavity Batten Installed
Window Installed
Head Flashing Installed
Gib and Architraves
Window opener installed
nJA08
Window removed
New Window Opening
Sill chamered to form Fall
Window Tape
Sill Flashing Installed
Cavity Batten Installed
Window Installed
Head Flashing Installed
Gib and Architraves
Window opener installed
|  |  | nJA09 | Window removed
New Window Opening
Sill chamered to form Fall
Window Tape
Sill Flashing Installed
Cavity Batten Installed
Window Installed
Head Flashing Installed
Gib and Architraves
Window opener installed
|  |  | nJA10 | Window removed
New Window Opening
Sill chamered to form Fall
Window Tape
Sill Flashing Installed
Cavity Batten Installed
Window Installed
Head Flashing Installed
Gib and Architraves
Window opener installed
Block N East Elevation 2
Remove Asbestos
Inspect timber framing
Install Rigid Wall Underlay
Install Cavity Battens
Install 9mm Fibre Cement board
Install Trims
Paint
Block N & K South Elevation Infills
|  |  |  | No. 3 | Remove asbestos panels
|  |  |  | No. 4 | Inspect Timber Framing
|  |  |  | No. 5 | Install Rigid Wall Underlay
|  |  |  | No. 6 | Install Flashing tape
|  |  |  | No. 7 | Install Cavity Battens
|  |  |  | No. 8 | Install Cavbat Battens
|  |  |  | No. 9 | Install Powder Coated Aluminium Flashing
Weatherboard Replacement
Northern Elevation
Existing damaged weatherboard
New replacement
Paint
|  |  | Fume Cupboards | 1
2
Commissioned Results
Remove existing Fume Vents
Install Ply upstand
Membrane and Cricket
Install Fume Vent
Welded Aluminium Cap flashing
Boot Flashing and drive clamp
Recomissioned results