## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Ngatea Pavement Rehab ITP |  |  |  |  | Yes | Ngatea Pavement Rehab ITP | 2896609b-4824-4a98-ba3f-5eb9b95f5e0d
checkpoint-group |  |  | section | Before starting work
checkpoint-status |  |  | checkpoint | Daily Work Briefing, confirm scope, location, that you have all staff, materials and plant needed
label | e8ace73b-be77-4792-92fe-9c05fd5821e0 |  | note | Ref/Spec-HSMP
label | 871b80de-2724-46f9-a6b7-eae317275f6d |  | note | Method/Test-Brief all team members on day’s work plan
label | 70af7ca6-b475-4ceb-82f6-523c0739fc20 |  | note | Frequency-Each morning
label | 9b40e97a-4fd2-4559-96cf-2dd39e712458 |  | note | Records required-Daily diary
label | fe464c24-ff49-4045-a8d2-c719f547dca5 |  | note | Responsibility-Supervisor
label | d18b4af4-b18e-4e8d-b1b7-bf09eae076ca |  | note | Type-Hold Point
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 2.1 Job start, identify risks and mitigations, communicate to team
label | 959cb9e5-c076-4112-94c5-3dcd4263327b |  | note | Ref/Spec-HSMP
label | 41ba5948-6c66-4783-aa08-d6b3064ef90e |  | note | Method/Test-Record all hazards on JSEA and brief team
label | 81472e99-4496-44ca-abd5-9c366d3d434b |  | note | Frequency-Each morning
label | ecde1136-a31f-47ba-b64b-bf42ee08db18 |  | note | Records required-Job start form
label | 0dc4cfff-89a3-4075-bd36-6c308df35e0a |  | note | Responsibility-Supervisor
label | 3d20a95b-91ca-47c9-86d4-a0f2d9d7086c |  | note | Type-Hold Point
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 2.2 Set up traffic management to plan
label | d8bca349-8bda-4fc2-87f8-163c16c71f1a |  | note | Ref/Spec-TMP
label | bf07d600-3741-498a-9c4f-29cf6ce7f399 |  | note | Method/Test-Perform Site audit post-set up
label | 367a4b09-af39-4b00-9841-fa3506e4d50a |  | note | Frequency-Each site
label | 4b3c6b1b-03f8-445b-a665-f1907b2963bf |  | note | Records required-Daily Diary
label | e3b01baf-de7f-4ea6-b5bf-6ae000278374 |  | note | Responsibility-STMS
label | 093cdef2-462b-44e5-b16e-06cab8fda98f |  | note | Type-Inspection
checkpoint-status |  |  | checkpoint | 2.3 Assess environmental requirements of site and install sediment and erosion control measures if required
label | 35808c48-6ba2-4c8a-8549-9b451b8163df |  | note | Ref/Spec-ESMP
label | 541233d5-377e-4b2b-9e6c-ebc52d17ae14 |  | note | Method/Test-Identify areas at risk and install control measures
label | 22281a3f-b549-42ca-8a41-8846923cefbc |  | note | Frequency-Each site
label | ea61c68b-4dac-4531-aa75-77e19d4eaedb |  | note | Records required-Daily diary
label | 32e34c6e-112a-4e5e-9c8c-852fedc2d02e |  | note | Responsibility-Supervisor
label | 0be241f3-0cc9-4cc5-bac5-7a3b7190b28a |  | note | Type-Inspection
checkpoint-group |  |  | section | Pavement Excavation
checkpoint-status |  |  | checkpoint | 3.1 Excavation Depth (455mm)
label | 4639cbae-a7af-4208-877a-3db2cad270da |  | note | Ref/Spec-Design
label | 90da3701-37b0-4177-a375-105de3fb3441 |  | note | Method/Test-+10 / -30mm
label | 55a145ed-b24a-4c9d-b984-b38bad25611b |  | note | Frequency-Every 5m
label | b913700a-0e69-4457-adc6-1c14e0bcfc34 |  | note | Records required-Dip Sheet
label | 045e4380-37f3-4917-9e5f-4c92cbc43af1 |  | note | Responsibility-Site Engineer
label | 39afe56d-1371-4ea3-8c78-fa077bec3492 |  | note | Type-Inspection
checkpoint-status |  |  | checkpoint | 3.2 Subgrade Condition
label | 9159a1d0-6803-4c64-bb03-1426c164737c |  | note | Ref/Spec-Design
label | 574694f1-fd76-4f7f-8409-7a36012545af |  | note | Method/Test-Inspection
label | e7a4f5ed-9390-4b82-b9cd-72d56a7829ff |  | note | Frequency-Once per section
label | 887ee5dd-b9bd-4a1e-93f8-716cd9b0de21 |  | note | Records required-Email
label | ea981fb8-b01f-477f-83c2-90de8bce39f2 |  | note | Responsibility-Renewals Manager
label | ff04811e-df61-4a0f-96aa-a2758cefb996 |  | note | Type-Inspection
checkpoint-group |  |  | section | 4.0 Geocloth/grid
checkpoint-status |  |  | checkpoint | 4.1 Place GridTex Fabric
label | 7511643a-3c56-4ff7-a1e9-624c0b860e50 |  | note | Ref/Spec-Design
label | 3f59b761-8289-4733-b8eb-11124b2a8bdc |  | note | Method/Test-Photo
label | a6c11554-73a5-4194-874f-c79a65e8e98a |  | note | Frequency-Each site
label | dd3a4f16-613f-4cea-a970-a9dbef0ddf3b |  | note | Records required-Photo
label | 069ee9cd-0a4d-4ad7-9d9e-4c6b2caa6e5a |  | note | Responsibility-Supervisor
label | 9cf0f03c-7d56-4070-aa11-06d66adfc768 |  | note | Type-Inspection
checkpoint-group |  |  | section | 4.0 Concrete Inlay
checkpoint-status |  |  | checkpoint | 4.3 LMC Depth
label | f8451476-818b-4ff2-8354-e9845a256a16 |  | note | Ref/Spec-Design
label | 7275299f-c6d3-44a3-8919-2dbc3ac8d610 |  | note | Method/Test-+10/-10mm
label | 44dbb9de-378f-4f80-835a-b67cbe708c9b |  | note | Frequency-Every 5m
label | 14e2aa26-1327-46e8-b3f8-f766adf5f14d |  | note | Records required-Dip Sheet
label | 482ec49d-e3bc-4627-aa6e-0dd4fa4ef2aa |  | note | Responsibility-Site Engineer
label | d2540822-dab4-4e6b-b86a-c8a471fd4fb6 |  | note | Type-Test
checkpoint-status |  |  | checkpoint | 4.3 LMC Dry Joins
label | 0c8f23f7-bb2f-4327-b7be-0e48a0eceed1 |  | note | Ref/Spec-Design (Rough tapered join)
label | 22b5a98b-1732-40c7-8daa-73b9ae999ad6 |  | note | Method/Test-Inspections
label | fcbe48a5-ee84-483a-ab01-0d1f7e8d80e5 |  | note | Frequency-Every dry join
label | 86ef873a-6299-4743-9eb8-0bf9876da3c8 |  | note | Records required-Photo
label | a37f3682-4035-4677-884e-916e19cb6f70 |  | note | Responsibility-Supervisor
label | ed1d776f-4e2a-4789-867a-e7c0ef26a2e7 |  | note | Type-Inspection
checkpoint-group |  |  | section | 5.0 SP20 Inlay
checkpoint-status |  |  | checkpoint | Air voids (Mat) 2-7%
label | 75d32f76-5798-41c4-95aa-0cf134fa9663 |  | note | Ref/Spec-NZTA M/10
label | c731ce75-8e76-40d1-aa69-bca19e030e56 |  | note | Method/Test-Test
label | 8ca143c2-e321-4a50-90be-e0859c17e632 |  | note | Frequency-1/300m2 (min 11 per lot)
label | 34263fbf-bd68-4058-a954-00dae1d478fc |  | note | Records required-Record Sheet
label | 25c1606e-b1c2-47e3-823e-f268c541543f |  | note | Responsibility-AC Supervisor
label | f748a200-48e5-4c94-a94d-cfbebf15287b |  | note | Type-Test
checkpoint-status |  |  | checkpoint | Layer Thickness
label | b1c481b1-b4cd-424b-ad07-1087d8ad0e07 |  | note | Ref/Spec-NZTA M/10
label | d23b6cbd-e517-41fe-bc90-eebaf0747822 |  | note | Method/Test-Test
label | 0620fa89-f254-4657-9b50-670226459031 |  | note | Frequency-1/300m2 (min 8 cores per lot)
label | 3cab748d-7610-4d9e-a716-593a71e05516 |  | note | Records required-Record Sheet
label | d9feeec1-a663-4213-ba63-44ce2c5fa8f6 |  | note | Responsibility-AC Supervisor
label | 2c65240e-b40b-4b03-a098-4dac8fb1726a |  | note | Type-Test
checkpoint-status |  |  | checkpoint | Air voids (Joint) 2-9%
label | 8f1e1eeb-ef2a-4e3b-a645-70705c11d0d4 |  | note | Ref/Spec-NZTA M/10
label | 16eb8f90-08d9-4c10-a969-4602941d2f4e |  | note | Method/Test-Test
label | be63785d-cab3-4601-9a72-1c103d155d0e |  | note | Frequency-1/300m2 (min 11 per lot)
label | 1a0781ae-324f-4776-9f5d-efefc77c535d |  | note | Records required-Record Sheet
label | b4ab6ffb-1760-4e60-b9c9-7771647005fa |  | note | Responsibility-AC Supervisor
label | 8cfe28ed-9948-44fd-a39d-48a92f5fa4df |  | note | Type-Test
checkpoint-status |  |  | checkpoint | Density 2.446-2.548T/m3
label | 7409aee9-4d97-4a21-a339-cb092959c9a5 |  | note | Ref/Spec-NZTA M/10
label | 6a5df525-122c-442f-84fd-86a6b0963690 |  | note | Method/Test-Test
label | bf669359-9472-4492-bc2c-4da15635588e |  | note | Frequency-1/300m2 (min 11 per lot)
label | e94d46b7-3d16-4431-a142-2aac654127de |  | note | Records required-Record Sheet
label | aad4f1b1-ec67-4bdb-9d60-b31bc8f9fd17 |  | note | Responsibility-AC Supervisor
label | f48c1919-3249-43b1-80d9-44d18fbd7e3b |  | note | Type-Test
checkpoint-group |  |  | section | 6.0 SMA
checkpoint-status |  |  | checkpoint | Air voids (Mat) 2-7%
label | bf1666a6-595b-4a6d-9ca2-5ade1094606a |  | note | Ref/Spec-NZTA M/10
label | 5c4995ff-f7bb-4914-bea5-c0d37c9733e3 |  | note | Method/Test-Test
label | eb833a70-2df4-42fc-99b1-122e40a4439a |  | note | Frequency-1/300m2 (min 11 per lot)
label | 1361b805-518f-4c5f-a6ee-d84088110a02 |  | note | Records required-Record Sheet
label | f26b8502-93d3-4a68-a4ee-92ec7eaa473a |  | note | Responsibility-AC Supervisor
label | e89b4ac6-5635-47d6-a252-4b30a59489cd |  | note | Type-Test
checkpoint-status |  |  | checkpoint | Density 2.574-2.690T/m3
label | ba381c33-d441-4c5d-87bc-c0d2e487bef2 |  | note | Ref/Spec-NZTA M/10
label | f6e7bbbb-e66a-4098-8ddd-7af44001e84f |  | note | Method/Test-Test
label | bef0d047-1c45-45eb-a62a-605f6ebb41c1 |  | note | Frequency-1/300m2 (min 11 per lot)
label | c900a54d-8ebd-4a1c-824c-0282249285c5 |  | note | Records required-Record Sheet
label | 660270c4-09ba-435a-b04f-0c2f30bb9635 |  | note | Responsibility-AC Supervisor
label | eac9b276-c19f-4f91-bba4-71023c325eca |  | note | Type-Test
checkpoint-group |  |  | section | 7.0 Site Close-out
checkpoint-status |  |  | checkpoint | 7.2 Collect RAMM Data
label | e1581f98-3b86-4d42-b33c-a0768e741367 |  | note | Ref/Spec-SHDOM / Data Quality Plan
label | ae5fdbf9-f9c9-41b4-8904-6021d44b9606 |  | note | Method/Test-L1 Accredited Personnel
label | f99794c9-a68a-4acf-8164-56fe1febc1ef |  | note | Frequency-All Jobs
label | de01a625-d60c-4b0a-8580-7d667b1fd777 |  | note | Records required-SHDOM Specs
label | f7e7bb7d-764c-440f-b48e-d6e328699331 |  | note | Responsibility-Foreman/ Supervisor
label | ee4650de-0653-4809-aed5-da73d8c99d37 |  | note | Type-Inspection
checklist-sectioned |  |  | checklist | Rehab Quality |  |  |  |  | Yes | Pavement Rehab | 3754ba8a-d30b-4c21-a10c-7bd7ce391f12
checkpoint-group |  |  | section | Before starting work
checkpoint-status |  |  | checkpoint | Daily Work Briefing, confirm scope, location, that you have all staff, materials and plant needed
label | e33ad109-99fb-41e7-b1a3-dfef818d3375 |  | note | Specification-HSMP
label | e96bc37c-0383-414f-bd73-8c7bd3d550da |  | note | Method/Test-Brief all team members on day’s work plan
label | 08498418-db6c-4e77-a27c-ff8c79eca837 |  | note | Frequency-Each morning
label | bae2f79e-4045-4197-b521-f804e30d4121 |  | note | Records required-Daily diary
label | c6e38bda-304e-4a3f-bc26-93436665450c |  | note | Responsibility-Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 1.0 AP 40 M4 – Raw Aggregate Testing
checkpoint-status |  |  | checkpoint | 1.1 Sand equivalent, or
label | 33ee07ab-6961-4376-8fdb-ffdaa319278c |  | note | Specification-Design
label | 1dc512a5-e9a8-4840-8e0e-fe095484b478 |  | note | Method/Test-≥35 Unit of measure?
label | 08afc9f4-88d5-4c12-87ce-fa411cfb5127 |  | note | Frequency-1 sample per 500m3
label | 70c2b27d-a475-4678-8e9d-28d7e1495214 |  | note | Records required-Test Report
label | e9ab2344-3163-49fa-b3cd-1585314ca66a |  | note | Responsibility-Supplier
label | 4e0eaf1b-060c-461a-ac8a-a28901f2f0b8 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.2 Clay Index (passing 0.075 mm), or
label | 0f17038a-4b8a-42f9-8596-42f801e3b719 |  | note | Specification-Design
label | 1284818a-5bc7-4c02-bccb-135677f503eb |  | note | Method/Test-<=3 Unit of measure?
label | 6ab6c89f-3860-4a6b-b172-3b7ad72714e9 |  | note | Frequency-
label | 3641f97c-d4ad-4183-818a-427250e5b3be |  | note | Records required-Test Report
label | d38cea5e-685b-4168-898c-91280352b8f1 |  | note | Responsibility-Supplier
label | 15e631f7-9996-44f2-b1e4-3d294c593b22 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.3 Plasticity Index
label | 1d01fa9d-9af1-4707-9646-0bfb00cab158 |  | note | Specification-Design
label | 760353d5-6f21-421e-997c-466f3ffaaa13 |  | note | Method/Test-
label | 6d12ed31-c1be-4871-94d0-aeba967bc433 |  | note | Frequency-
label | e48b3067-58dd-4a14-a354-04169d3a8cac |  | note | Records required-Test Report
label | 8921041f-8464-418b-b76d-59719ffa80aa |  | note | Responsibility-Supplier
label | 8401df17-9610-47ee-bbe5-9bab1a2b449e |  | note | Test
checkpoint-status |  |  | checkpoint | 1.4 Particle size distribution
label | 66b4457e-c65e-40bf-9968-fd83af760494 |  | note | Specification-Design
label | 26bddbf0-b57c-429e-94b8-6a63fa0aebc5 |  | note | Method/Test-100% passing 63mm
label | d58be226-4818-4d16-a941-68e53bd1b1d8 |  | note | 40% ≥ 65%passing 19mm
label | 6f6bd7a6-0490-4746-b704-a758cc6ad0a4 |  | note | ≤ 10% passing 0.425mm425µm
label | f8f5e27e-8981-49db-bd53-0be0a1214b92 |  | note | Frequency-1 sample per 250m3
label | a2949e56-0dc1-4358-9cc9-0413f7b48bef |  | note | Records required-Test Report
label | 1779e9f7-85a6-4ea8-a1e1-14d637e5a4b2 |  | note | Responsibility-Supplier
label | 4785a8fd-a5e7-464c-b254-cb637a9b9163 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.5 Solid Density
label | 278e55a0-1ff6-4329-bd0b-f6e6409c9516 |  | note | Specification-NZTA B/2 7.5
label | 1432190d-5f47-4c26-8a33-56de887d00a5 |  | note | Method/Test-Unit of measure?
label | 07e56372-9106-4258-8c59-6860fba523b3 |  | note | Tolerance?
label | f19799d8-9265-499f-adf3-d66753b49e6f |  | note | Frequency-1 test
label | e55c079d-7774-43a6-a8ae-0d64b21ab500 |  | note | Records required-Test Report
label | 0d09bc30-d2f5-46f3-8094-bd619ebd280c |  | note | Responsibility-Supplier
label | 169c66fe-26d9-415d-aa67-0d2e6ea38c4b |  | note | Test
checkpoint-status |  |  | checkpoint | 1.6 Determination of MDD & OWC
label | 30eb570a-6bd8-42ca-9a14-4bc3d71bf08e |  | note | Specification-NZTA B/2 7.5
label | b6a16b3c-d911-44a9-bc9a-e4f366e10dc3 |  | note | Method/Test-Unit of measure?
label | 722f0c93-4af1-45ca-b8f4-8e840929bc91 |  | note | Tolerance?
label | 63e88d0f-10a0-4c71-ab62-1e468f9e68b5 |  | note | Frequency-1 test
label | a00c37fb-1266-47ed-83b3-bfe405335845 |  | note | Records required-Test Report
label | 40c8e2ba-3bdf-45a2-a754-4afb682574dc |  | note | Responsibility-Supplier
label | a999218b-4bf2-44bc-9508-c6314552fb45 |  | note | Test
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | 2.1 Job start, identify risks and mitigations, communicate to team
label | 583ed866-96a3-4e19-9614-4be8b0997e10 |  | note | Specification-HSMP
label | 9fa844da-9671-4a98-92f1-8b2fc700f852 |  | note | Method/Test-Record all hazards on JSEA and brief team
label | 738689c9-0765-4f19-b6d3-9f87e95b5ef8 |  | note | Frequency-Each morning
label | 4a9a58c8-55a6-4dbf-8275-f6e606333ed2 |  | note | Records required-Job start form
label | 212c9c34-5d6d-48c0-80ee-504c4a7bdb70 |  | note | Responsibility-Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 2.2 Set up traffic management to plan
label | 9543eb4f-f3f9-4151-ad9e-eda0ca9373a1 |  | note | Specification-TMP
label | e8ffe031-0244-4865-b001-644b0a2f733c |  | note | Method/Test-Perform Site audit post-set up
label | 3d8e1549-1074-4a10-be8f-12368fc9af3a |  | note | Frequency-Each site
label | a83dc8d5-c6fa-4243-9336-e769faaca480 |  | note | Records required-Daily Diary
label | 6efd480f-0c37-4799-917f-21c09d7eb810 |  | note | Responsibility-STMS
label | 58e55107-a301-4996-9990-df08c9bc59a8 |  | note | Test
checkpoint-status |  |  | checkpoint | 2.3 Assess environmental requirements of site and install sediment and erosion control measures if required
label | 663207bb-7966-4253-89b9-1c80731c19a4 |  | note | Specification-ESMP
label | 51b26e7e-8411-4176-9dc7-b5e1989797be |  | note | Method/Test-Identify areas at risk and install control measures
label | 04f590d8-e22a-43f9-98bc-46988c3e85ca |  | note | Frequency-Each site
label | bbdc5490-c460-4e0c-9366-4bb513373cfa |  | note | Records required-Daily diary
label | f272a1dd-4578-4df7-889e-44800e545d6d |  | note | Responsibility-Supervisor
label | f3ca5232-5e2b-4fd0-a180-8a9a464aa44e |  | note | Inspection
checkpoint-group |  |  | section | 3.0 Sub-base Stabilization Inlay
checkpoint-status |  |  | checkpoint | 3.1 Cement Spread Rate
label | dbb4387b-efd2-4511-8563-64205fc07bae |  | note | Specification-NZTA B/6 7.3
label | 80027a11-3e66-42fb-958c-bf092e9ca81f |  | note | Method/Test-±0.5kg/m2, Weigh mat
label | f4a97a12-89a8-4d3a-9252-b8a5bfe6c602 |  | note | Frequency-Per run
label | f2d03ea0-3605-4608-9efd-64c9d14eb917 |  | note | Records required-Cement Sheet
label | 34503dd8-0588-4437-bf88-90fc8255fbeb |  | note | Responsibility-Stabilising Supervisor
label | 7247d2a4-ba7a-4eb5-ac11-279752cc4d41 |  | note | Test
checkpoint-status |  |  | checkpoint | 3.2 Hoe and stabilise to design depth
label | ab565836-d8bc-404c-8427-2accbbb7793a |  | note | Specification-NZTA B/6 7.5.1
label | 79192bed-6fa5-4d22-b46c-e16d79a3f8ca |  | note | Method/Test--0mm / +20mm
label | 96d8c933-1eb6-4ffb-b899-db442be69d5d |  | note | Frequency-Per run
label | 71691b31-a944-46cf-a7d4-e2e023924408 |  | note | Records required-Cement Sheet
label | 1aaac9c5-8232-4fbc-98ba-f7bac4d73d61 |  | note | Responsibility-Stabilising Supervisor
label | b738c879-63b9-4780-b39c-bb6b85384eaf |  | note | Inspection
checkpoint-status |  |  | checkpoint | 3.3 Overlap longitudinal joints
label | 28485582-9214-4d29-bd58-3e11f0edd489 |  | note | Specification-NZTA B/6 7.5.2
label | 8a482753-cfb6-4548-a175-a7e168a59245 |  | note | Method/Test-200mm overlap
label | 9262f5e7-8eb1-4de3-a5d6-80618e3152ca |  | note | Frequency-20m centres each side
label | 17530c1f-d971-4f0d-9acf-f0c2380fc22c |  | note | Records required-Stringline Sheet
label | 33864bd3-4bcb-46dd-bb89-ab7f0f61f0de |  | note | Responsibility-Stabilising Supervisor
label | 89ce0af3-af9e-4f07-a524-a139317540d0 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 3.4 Plateau density test
label | ee71510e-038f-4991-ba74-4731aa03a36d |  | note | Specification-NZTA B/6 7.6
label | b27cf971-b1bb-487b-9be2-d03122b89079 |  | note | Method/Test-Nuclear Densometer, Tolerance?
label | 8aa6eca3-ff22-4f89-a1d5-9fd2aff37812 |  | note | Frequency-20m alternating wheel tracks
label | 87c7d7f1-b1c7-49d6-8584-3d621d1c48ce |  | note | Records required-Plateau Density Sheet
label | 5658ab05-0587-41c3-86b8-27623ca1c491 |  | note | Responsibility-Quality Engineer
label | 6ee25c47-352e-4295-8ebc-d632a20e9e21 |  | note | Test
checkpoint-status |  |  | checkpoint | 3.5 Confirm layer thickness
label | 0e8e6a0e-ddef-4b2e-8e25-0fec7b89f1cd |  | note | Specification-NZTA B/6 8.2.2
label | a2d0226f-f547-4472-9c0a-f063110f3941 |  | note | Method/Test--0mm / +20mm
label | b4024c6e-362b-4dfe-a662-0a16d705a323 |  | note | Frequency-Every 20m, full width
label | e4bc5db3-8487-4ee0-8b55-359644348f5b |  | note | Records required-Stringline Sheet
label | 916cf6f6-3b70-4734-a722-03935e2a14ab |  | note | Responsibility-Rehab Manager
label | 9662fe5a-1aca-4a55-a910-2ed053c11d6d |  | note | Test
checkpoint-status |  |  | checkpoint | 3.6 Confirm surface levels
label | 7b92816a-a5c1-4c01-bbb4-80c7e913ece6 |  | note | Specification-NZTA B/6 8.2.2
label | 8c789e9d-42bc-4a1b-8d0f-90c17129b55d |  | note | Method/Test--5mm / +10mm
label | a4e4e73e-d71f-49ec-91ec-88185df6c54d |  | note | Frequency-Every 20m, full width
label | 25f4ecc2-3345-44e2-9d47-105216ebf8a9 |  | note | Records required-Stringline Sheet
label | fe7c3a2e-be4c-4b47-af4f-2919c2261aa0 |  | note | Responsibility-Rehab Manager
label | 63c917d1-cbee-4e9b-b515-df207859d4fe |  | note | Test
checkpoint-status |  |  | checkpoint | 3.7 Compaction as per the results of the plateau density test/or
label | b911e9e1-88ce-4d02-bd49-b74551c1ac8a |  | note | Specification-NZTA B/6 7.5.2
label | ab64cbbb-46e3-4788-be16-2e13bea336d4 |  | note | Method/Test-Mean ≥95%
label | 4bbf3d50-2497-4e0e-8ca5-8c7c3c285768 |  | note | Minimum ≥92%
label | 153b7281-ea34-42d4-b2c9-1eef8013316d |  | note | Frequency-Every 20m alternating wheel tracks
label | e7449629-7e38-4cef-a47b-11283d0c868c |  | note | Records required-NDM Sheet
label | 45fb825d-851a-412d-a59e-3522660c800a |  | note | Responsibility-Quality Engineer
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 3.8 Impact hammer test
label | e4d42b08-1752-4d1e-965c-641a96b94916 |  | note | Specification-Spec?
label | bd27c20a-4a2b-4566-98f0-d05779b76af0 |  | note | Method/Test-≥70 CIV
label | 5c0d2886-2eba-4bfe-8ab4-d55a0fcbe329 |  | note | Frequency-Every 20m alternating wheel tracks
label | 71d89561-bb5a-48fe-9205-c7b0fb6bcf4c |  | note | Records required-Clegg Sheet
label | ee363fe4-9935-4545-9a21-3bab79df7345 |  | note | Responsibility-Quality Engineer
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 4.0 Basecourse Overlay
checkpoint-status |  |  | checkpoint | 4.1 Cement Spread Rate
label | 17bcafa2-03fe-4d62-86df-76ef8d74fd68 |  | note | Specification-NZTA B/6 7.3
label | 29746f6c-a39e-4b69-bd65-f0f01133da5b |  | note | Method/Test-±0.5kg/m2, Weigh mat
label | e9b42907-0ae5-46c1-a7aa-e39dc95182dd |  | note | Frequency-Per run
label | 12e22b29-27b0-4f45-b057-d333a0b71bea |  | note | Records required-Cement Sheet
label | 6c07a109-e6b5-4ea0-bf43-44b45ac63ebb |  | note | Responsibility-Stabilizing Supervisor
label | f8fb90d9-521a-40dc-9ec0-beefc6dee2f2 |  | note | Test
checkpoint-status |  |  | checkpoint | 4.2 Hoe and stabilise to design depth
label | 25c7c820-93f3-4b30-a676-e049b86cd17e |  | note | Specification-NZTA B/6 7.5.1
label | d33b57e5-6751-4a07-88d1-736adde4b55b |  | note | Method/Test--0mm / +20mm
label | 39581c80-dd60-46d8-9097-675a41e784be |  | note | Record hoe-depth setting
label | 45321875-ba05-43e0-bc44-468c6a0dc464 |  | note | Frequency-Per run
label | 647eed09-edcd-4390-97ca-6bc239b5eef0 |  | note | Records required-Cement Sheet
label | e2d4e290-1b90-48e0-858f-7b15a587e1d1 |  | note | Responsibility-Stabilizing Supervisor
label | bac67587-2061-44a4-a70e-0f1b165c14ff |  | note | Inspection
checkpoint-status |  |  | checkpoint | 4.3 Overlap longitudinal joints
label | 18c02438-013d-40d5-b3f9-7b79eb59e9b7 |  | note | Specification-NZTA B/6 7.5.2
label | 24f21e3d-762b-4dba-9c10-321e4ff2fd87 |  | note | Method/Test-200mm overlap
label | 8933f193-f25b-4ae7-a0a1-cb886a3752a5 |  | note | Frequency-20m centres each side
label | aadfa261-5bb9-44d0-a474-cf26e06779bc |  | note | Records required-Stringline Sheet
label | ddc50756-a0ca-4bc3-bda9-04a5f0e849f9 |  | note | Responsibility-Stabilizing Supervisor
label | 93df8f92-624e-4c22-b150-178695e87e99 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 4.4 Plateau density test
label | 4da99efa-0cf3-4113-a8e2-3ecb6792bef1 |  | note | Specification-NZTA B/6 7.6
label | aecaa4c3-b411-45fb-91b2-db567ae6728d |  | note | Method/Test-Nuclear Densometer
label | 2d3a1b28-9401-4aae-9beb-c29911759d17 |  | note | Tolerance?
label | 9b9f8e76-b09a-43de-ba88-624c0e631093 |  | note | Frequency-20m alternating wheel tracks
label | a91e0a5a-9eec-4da1-bdcd-b239078957a1 |  | note | Records required-Plateau Density Sheet
label | e371e22f-a6b0-424e-b0a7-26a048db4cfe |  | note | Responsibility-Quality Engineer
label | 57a60a87-cca7-4787-86c5-9704136f3d13 |  | note | Test
checkpoint-status |  |  | checkpoint | 4.5 Confirm layer thickness
label | f340f60f-3f90-4c53-aa01-2a442bcc6d45 |  | note | Specification-NZTA B/6 8.2.2
label | cfe54fe3-deb3-4b81-84e9-944ab30c0b84 |  | note | Method/Test--0mm / +20mm
label | 4d389913-798b-4dec-bf08-f1a376314c7c |  | note | Frequency-Every 20m, full width
label | dbb548be-8618-4581-a187-107e78088435 |  | note | Records required-Stringline Sheet
label | 293c4c0f-9caa-4263-9c72-01fb8f70ebc2 |  | note | Responsibility-Rehab Manager
label | 2cc45d8f-724e-4f0d-9c8a-deef0c0d09e7 |  | note | Test
checkpoint-status |  |  | checkpoint | 4.6 Compaction as per sample test results
label | 627705e4-83ae-4298-9b15-33828650b544 |  | note | Specification-NZTA B/6 7.5.2
label | d5981e32-c682-4b11-ba97-17be1f417abe |  | note | Method/Test-Mean ≥95%
label | 97351caf-3aa6-4e1f-b1e2-1fb5da8e31e0 |  | note | Minimum ≥92%
label | 4d24d7b1-3cfa-49a4-bde9-1915479ae5a9 |  | note | Frequency-Every 20m alternating wheel tracks
label | 829647cc-227d-4600-8a40-4734c78bacc6 |  | note | Records required-NDM Sheet
label | cc0d6d9b-3e42-4fec-9ff8-17d5e765b9e0 |  | note | Responsibility-IANZ Accredited Lab
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 4.7 Impact hammer test
label | 679a6c19-0895-48c5-9f38-ae9fdaba15de |  | note | Specification-Spec?
label | cbdd9c42-34b3-449d-b0f5-2c5e8edc70b0 |  | note | Method/Test-≥70 CIV
label | 3b777a9a-80f6-4707-b122-700077e53506 |  | note | Frequency-Every 20m alternating wheel tracks
label | 7655a6d1-4b06-40ac-a361-f94199061631 |  | note | Records required-Clegg Sheet
label | 39294903-8c4f-41e6-a6c9-f139a52d78a3 |  | note | Responsibility-IANZ Accredited Lab
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 4.8 Confirm surface levels
label | 893db4bd-2e97-47f0-9913-b7cb32dc4f0a |  | note | Specification-NZTA B/2 5.1
label | f8aa9f41-2a60-49bb-8faa-8ae2985e0694 |  | note | Method/Test--5mm / +15mm
label | 2c439d38-07dd-47d3-b6db-99b0cbeaa827 |  | note | Frequency-Every 20m, full width
label | 928a47d4-b9f1-47da-afdd-b885eed38115 |  | note | Records required-Stringline Sheet
label | d735df69-fb53-4a73-9813-c20abb4c1a1c |  | note | Responsibility-Rehab Manager
label | 6dd6c697-6063-4a9d-9c70-23d3048eb7bf |  | note | Test
checkpoint-status |  |  | checkpoint | 4.9 Surface Finish
label | 34ac6899-33e9-4144-8301-f9d489066cd1 |  | note | Specification-NZTA B/2
label | 0676657e-a4f1-4f84-8c3f-cc9faf2c3158 |  | note | Method/Test-Sealing Supervisor to inspect
label | 9595d93c-16de-4b13-93c3-0a4a930a4827 |  | note | Frequency-Per site
label | 6648547f-6cd0-4936-99cc-a3e60ed9a936 |  | note | Records required-
label | db876d43-ff7c-406e-a9a4-65d32e3c7dfe |  | note | Responsibility-Sealing Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 5.0 Aggregate Testing – Sealing Chip
checkpoint-status |  |  | checkpoint | 5.1 Crushing Strength
label | db28ae89-d948-40e0-b579-edce903c8455 |  | note | Specification-NZTA M/6 3.2
label | 9a1f76b5-d82e-4502-908c-788e26258faa |  | note | Method/Test-<10% fines passing 2.36mm under 230 KN load
label | fea133a8-7ff9-4fa9-861f-d5d95bcbaae2 |  | note | Frequency-1 Test
label | 883ee536-e552-41d2-9e67-a02d815b7581 |  | note | Records required-Test Report
label | 1f1c588c-5f14-4315-a918-bdf09939c74e |  | note | Responsibility-IANZ accredited laboratory
label | f9333f7b-1cc4-4a67-a231-da8c6c361915 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.2 Weathering Quality
label | 705c1fbc-9f95-453c-b225-442f7c48bbe0 |  | note | Specification-NZTA M/6 3.3
label | 86b89e14-8915-40ea-bf9c-91461c7b78e9 |  | note | Method/Test-AA or BA
label | 34d21885-3611-4d2e-b977-996b994e8cd5 |  | note | Frequency-1 Test
label | a3634ce1-857f-4c98-8a01-3a78936d3b97 |  | note | Records required-Test Report
label | a4828998-0b02-41a7-9c8f-6ef3bb82f9fd |  | note | Responsibility-IANZ accredited laboratory
label | 121d794f-d565-4400-93e6-17ad6ed6f9b5 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.3 Polished Stone Value
label | 6f5f122c-c563-428e-9381-ff265d1ef5b6 |  | note | Specification-NZTA M/6 3.5
label | 3d06530d-a552-481a-8e67-4b7403ca32c4 |  | note | Method/Test-PSV Required = 52 min
label | 4e84fb69-4626-4a9c-90ac-25f1b8064129 |  | note | Frequency-1 Test
label | f98840e1-4fed-43dd-8b73-de63e4c04b57 |  | note | Records required-Test Report
label | ca456979-6ad1-4796-b7b7-5320f1fa1adf |  | note | Responsibility-Accredited PSV Testing Agency
label | 63c5a597-ec08-4efd-bb80-ded83b30f802 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.4 Cleanliness
label | 5a3dd1e4-a745-4b08-bc56-e79e4b628af1 |  | note | Specification-NZTA M/6 4.1.1
label | 3a221337-d405-470d-a0cc-4870c70ec770 |  | note | Method/Test-Grade 5 – 89 min Grade 3 – 87 min Grade 4 – 85 min
label | 721af52c-81c7-4891-8091-d37d7fc5a989 |  | note | Frequency-1 Test
label | 5c57f55f-5e01-4069-b0d2-23308f89ebab |  | note | Records required-Test Report
label | 184d8cdb-b838-4c88-9c21-029801f51b4e |  | note | Responsibility-IANZ accredited laboratory
label | af7c87d4-721d-404d-b9e0-d10629f6b011 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.5 Grading
label | 0e8aa8d8-dac0-4ebb-83ea-8574ca4ca97e |  | note | Specification-NZTA M/6 4.2.1
label | f8ee08b4-7039-4b42-81e2-b204e321da1e |  | note | Method/Test-See NZTA M/6 4.2.1
label | e7ef26af-f312-4f0b-8c2c-33c01e891244 |  | note | Frequency-1 Test
label | 752ed930-9fc9-4e2a-9458-a548ec8c372b |  | note | Records required-Test Report
label | c951ae84-5c03-4fd2-abb7-3c29737f28ad |  | note | Responsibility-IANZ accredited laboratory
label | dfe436e6-d220-46db-bf86-5927ea7102ef |  | note | Test
checkpoint-group |  |  | section | 6.0 Chipseal Control
checkpoint-status |  |  | checkpoint | 6.1 Confirm viscosity of bitumen
label | 748642ec-c899-4343-9250-9142aa79d69a |  | note | Specification-NZTA M/1 Table 1
label | 5ad2987f-ecb7-420c-841d-2731839025a8 |  | note | Method/Test-Viscosity PaS at 60°C
label | c5236d1e-35c1-4aed-9e58-c248b9ebfb47 |  | note | Frequency-1 Test
label | 1af8b834-810c-4aa1-86ee-4cc905adbd4f |  | note | Records required-Construction
label | db9b70c4-5562-492f-a52d-8164fa306a25 |  | note | Responsibility-IANZ accredited laboratory
label | f10668c5-32f6-48d0-9966-d83a5bfd2feb |  | note | Test
checkpoint-status |  |  | checkpoint | 6.2 Confirm penetration grade of bitumen
label | 88dd928b-df15-4ff8-9d99-b55101a8e4f6 |  | note | Specification-NZTA M/1 Table 1
label | 70dde9e3-b7b8-4bd3-911c-8c470f896ebd |  | note | Method/Test-Penetration at 25°C,100g, five seconds
label | 8ecdeb0a-ef22-4920-ae66-6542b3d136e6 |  | note | Frequency-1 Test
label | 7a7f44d9-2b78-4977-9ef8-68a354e0ce74 |  | note | Records required-Construction
label | 6cb13746-b13a-4cb5-9ca4-b5a29b67a169 |  | note | Responsibility-IANZ accredited laboratory
label | 7c68b450-462c-4ac6-85d6-a62e38e951a9 |  | note | Test
checkpoint-status |  |  | checkpoint | 6.3 Spray bitumen, then place chip *and roll – refer design for chipseal grade
label | aa86310f-5cb1-4095-aee0-f441c65e6db9 |  | note | Specification-Design
label | 9f6f5bd4-e73c-4432-b830-8ca55073bb6b |  | note | Method/Test-Visual check
label | 76e9db7f-f0d9-4d13-9658-8996192a8078 |  | note | Frequency-1 Test
label | 3a9058e0-bce0-4ab7-b877-e18309c5b568 |  | note | Records required-Following construction of chipseal
label | 4373cc72-8586-446c-a111-a98d9220c969 |  | note | Responsibility-Sealing Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 6.4 Check for excessive “windows”
checkpoint-group |  |  | section | 7.0 Site Close-out
checkpoint-status |  |  | checkpoint | 7.1 Field Quality Review
label | 812df860-17e3-4564-bb00-40415d1f0edd |  | note | Specification-QMP
label | 5eda4cc8-285a-47ed-9a17-9abc514d8167 |  | note | Method/Test-Verification of Work Standards
label | 775a1ff9-3e8a-4a99-b9c6-5d76d14aadfa |  | note | Frequency-10% of sites
label | 0fb74497-dc70-46c9-aee3-f440ae55edd4 |  | note | Records required-Record in Audit Field of RAMM Contractor
label | 76c96cc9-ce10-4967-8365-71b167366fc2 |  | note | Responsibility-Supervisor
label | 910b2977-4763-414e-b376-c91857bbddac |  | note | Inspection
checkpoint-status |  |  | checkpoint | 7.2 Collect RAMM Data
label | a5697dfd-b5bb-40f5-906e-6be94a85b42f |  | note | Specification-SHDOM / Data Quality Plan
label | a731d40e-53eb-4c8b-a0d4-83339a088b52 |  | note | Method/Test-L1 Accredited Personnel
label | 8fd20ea3-bfff-46d3-8afb-304cb404f36a |  | note | Frequency-All Jobs
label | f08b09b4-2858-488c-a4e1-d3119869f2ac |  | note | Records required-SHDOM Specs
label | fffeee0b-dbd7-4d59-aa8d-f3bb6f0b26d2 |  | note | Responsibility-Foreman/ Supervisor
label | 194c1ffd-5aeb-4872-8f42-9e4f8666104a |  | note | Inspection
checkpoint-status |  |  | checkpoint | 7.3 Verify RAMM Data
label | 0869b347-1180-4519-8e5a-dd03b1b3f9c2 |  | note | Specification-SHDOM / Data Quality Plan
label | d5ec7ed3-2dc7-4f5c-8141-60e1759b57df |  | note | Method/Test-Level 2 Accredited Personnel
label | 51467fc8-a8c1-4894-941d-449d593dfe41 |  | note | Frequency-All Jobs
label | 458fa019-0823-4279-84db-0a1aae98421d |  | note | Records required-SHDOM Specs
label | 4d875596-cda5-44eb-9e71-ce47ce048de9 |  | note | Responsibility-RAMM Manager
label | a118d8f9-7dc9-4ec5-8b51-30b19e1fca85 |  | note | Inspection
checklist-sectioned |  |  | checklist | TNZ M/10:2014 - Specification for Dense Graded and Stone Mastic Asphalts |  |  |  |  | Yes | TNZ M/10:2014 - Specification for Dense Graded and Stone Mastic Asphalts | 385b0127-b5a7-4a17-a198-31b64242966c
checkpoint-group |  |  | section | Procurement - Table 2.1 Coarse Aggregate requirement for Dense Graded Asphalt
checkpoint-status |  |  | checkpoint | Source Property Test - Crushing Resistance
label | d1ee0101-6230-442b-b0f1-6d2914cc151e |  | note | Controlling Documents-NZTA M/10:2014
label | 4f5941f1-a448-44c0-9fe3-baf66cc4de84 |  | note | Acceptance Criteria- ≥200kN
label | e17782fa-0d9b-44d4-b1a8-0ff43d28b2dc |  | note | Method-Crushing Resistance
label | 270b2f0e-a64c-4a87-8b85-fd50e1000cfe |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | 3fd47642-b9e2-4e41-b1fb-bf4021d7467e |  | note | Responsible-Project Manager
label | dacd83cc-6d4a-4679-8439-c0774e58c0e6 |  | note | Verifying Document-IANZ Report
label | b77aff2f-65d7-4113-906c-c26ac221c3fc |  | note | Test Conducting Authority-Subcontractor
label | a328844e-d1e3-4d4d-bfb2-0e1b44383c3a |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Source Property Test - Weathering Quality Index
label | 3e423f56-900f-4b2d-ac28-b5bcb78c1a24 |  | note | Controlling Documents-NZTA M/10:2014
label | c1bf4d8a-6944-400e-8643-cf8d649a96d2 |  | note | Acceptance Criteria-AA or BA
label | 454c8778-ca9d-4399-b933-17d454e59f54 |  | note | Method-Weathering Quality Index
label | a9cc50ef-5c72-42b6-bf64-4330c45057cb |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | 17e37d51-a23d-4936-818b-654107a8834d |  | note | Responsible-Project Manager
label | 2f6bed83-ae23-48cd-b20d-3add6bf30273 |  | note | Verifying Document-IANZ Report
label | e4a5e845-9c9d-41bd-8b1c-019e6ce4aadf |  | note | Test Conducting Authority-Subcontractor
label | f06cce9c-7079-49e0-8e76-c19502d03a1b |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Polished Stone Value
label | 9d54a121-6cc9-437d-a959-157a7302154a |  | note | Controlling Documents-NZTA M/10:2014
label | eb6b9c62-c8ec-4122-96c2-a553f70eacf6 |  | note | Acceptance Criteria-Specific Contract Requirements
label | 082bffde-37d2-477c-8b36-121e468701af |  | note | Method-Polished Stone Value
label | 246fdfb4-8b96-4700-9c26-213098548a9e |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | 57c7ce90-b14b-48ad-98f1-3b5e3cac3a6e |  | note | Responsible-Project Manager
label | d3713e31-4e17-4670-8186-78f75a4bff37 |  | note | Verifying Document-IANZ Report
label | 212bb9d7-3093-4f27-a63b-b96e65bd02d2 |  | note | Test Conducting Authority-Subcontractor
label | cbd9ee91-3d14-4dfd-932b-31286de996ac |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Single Broken Faces
label | a3486d4b-7417-44cc-a090-4e8b13de0766 |  | note | Controlling Documents-NZTA M/10:2014
label | 0fabb2c8-0d0b-4556-96a5-fc2e71652cee |  | note | Acceptance Criteria-98% min
label | de2b8a38-7423-4c1e-8bda-e334c7eb29a3 |  | note | Method-Single Broken Faces
label | 06c5cb5c-00f7-4ad4-a4a9-c3af5f00b188 |  | note | Frequency-1/1,000m3
label | ca55971e-16df-4d58-bdf1-ebc835784393 |  | note | Responsible-Project Manager
label | 6317bdf9-2a21-4ca7-944d-e04a375904d4 |  | note | Verifying Document-IANZ Report
label | 481f5bbe-5b66-468b-9440-5767f1596800 |  | note | Test Conducting Authority-Subcontractor
label | b4d49e7e-c53a-459e-a9c9-c08f9e3b1f35 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Two Broken faces
label | d26261a8-809b-4b7f-8c1a-35205efbceaf |  | note | Controlling Documents-NZTA M/10:2014
label | ce92b486-383e-4a0d-8040-fec39c609600 |  | note | Acceptance Criteria-60% min
label | f5392fcb-c2b2-4870-9339-7f0ec36f0583 |  | note | Method-Two Broken Faces
label | 8fe901b9-9378-4970-b022-c48b281f9c11 |  | note | Frequency-1/1,000m3
label | 4424f9c8-7d78-4b61-b820-811e94f808cc |  | note | Responsible-Project Manager
label | 1843cc74-59bc-4081-9c3a-475875d61d1d |  | note | Verifying Document-IANZ Report
label | dd06c995-d6c1-410d-9b2c-4d4c47de048b |  | note | Test Conducting Authority-Subcontractor
label | ee3e42da-8eb5-45a9-9302-ef68514b383a |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - LA Abrasion loss
label | 6d53b47f-fd2e-4f50-8d50-ce71aff83594 |  | note | Controlling Documents-NZTA M/10:2014
label | 5dfe943a-3873-4722-8524-3c4a19267a7d |  | note | Acceptance Criteria-Report Value
label | 5c33325e-e56f-4029-90d7-b3f0085a64cb |  | note | Method-Los Angeles Abrasion Loss
label | cc2824b5-8c91-4324-a39a-5b0e38625004 |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | 9147bc3f-bdf3-4f04-9606-a0c13690d361 |  | note | Responsible-Project Manager
label | 0cf6ea8f-1913-4a14-85c8-ba9b8388d971 |  | note | Verifying Document-IANZ Report
label | a2f16ae9-09e0-4e13-b7f7-e6207ec83202 |  | note | Test Conducting Authority-Subcontractor
label | 49ea956d-3d30-43a9-b1b9-17a4738c0482 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Wet/Dry Strength variations
label | 21300b73-0506-4962-999d-712d16ec0aa8 |  | note | Controlling Documents-NZTA M/10:2014
label | 41e8f3b9-42a7-41d0-9fb2-866cbb04da15 |  | note | Acceptance Criteria-Report Value
label | 7c7cecc5-46c9-4266-86ff-9f8d72bfae84 |  | note | Method-Wet/Dry strength variation
label | 9adfb0e4-8a4e-4174-a957-07600a3b0f38 |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | 2accb9dd-3ec5-405f-a071-241c20307488 |  | note | Responsible-Project Manager
label | 3b4a783c-e8e5-40e3-917c-1119de2eab74 |  | note | Verifying Document-IANZ Report
label | 5268a42f-4fcf-43f7-8018-118715b870ab |  | note | Test Conducting Authority-Subcontractor
label | 254ae47e-bb04-43ba-a0b4-0500fce90e1a |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Water Absorption
label | e5087ff6-fe61-4523-afe9-5f00c41a41e6 |  | note | Controlling Documents-NZTA M/10:2014
label | 2c5d0aea-92b2-43fb-b8e0-c94fc4402c09 |  | note | Acceptance Criteria-Report Value
label | cccb051e-8126-4fb6-a358-36c5d1637aac |  | note | Method-Water Absorption
label | 42870bf0-7ecd-48e9-8e03-de3bfbee0a39 |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | b4f10301-1fbb-4d84-b6f6-a066835b3a06 |  | note | Responsible-Project Manager
label | 63798b1f-e430-4cd6-8e38-8363d13987f6 |  | note | Verifying Document-IANZ Report
label | 32d4ffef-1d2a-4006-8e74-ceb23db2ff38 |  | note | Test Conducting Authority-Subcontractor
label | f98f9385-cb18-422a-a8a9-1450ac0eac13 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-group |  |  | section | Procurement - Table 2.2 Coarse Aggregate Requirements for SMA
checkpoint-status |  |  | checkpoint | Source Property Test - Crushing Resistance
label | 1e515423-3132-4abd-8208-38a242284360 |  | note | Controlling Documents-TNZ M/10:2014
label | 043734b4-391c-4c23-970c-2999e6a27eb0 |  | note | Acceptance Criteria- ≥230kN
label | 19806de1-a3b1-4c74-b827-b58a35c70ef7 |  | note | Method-Crushing Resistance
label | a71560b0-1405-4aff-bd4a-69a0bd655bb6 |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | f018de8a-e468-4edf-9f77-d26a398ac812 |  | note | Responsible-Project Manager
label | d1869411-0824-4079-bb99-1cf3df65cff5 |  | note | Test Conducting Authority-Subcontractor
label | 8a2f0aa6-92b8-42e4-a092-41f22fd06135 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Source Property Test - Weathering Quality Index
label | 1f4bc4c9-e0c9-4781-8b0e-4aaa45444dec |  | note | Controlling Documents-TNZ M/10:2014
label | 5a57bc28-e9d1-4c90-b819-e2170446babb |  | note | Acceptance Criteria-AA or BA
label | 7d9b8cb9-54a4-43be-90fb-8ce266720cb4 |  | note | Method-Weathering Quality Index
label | 8bd97a28-1296-4510-8dff-73853325e079 |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | a6c307b1-64bb-4177-ba2c-b955078588da |  | note | Responsible-Project Manager
label | 88ef1d7f-4ee0-4d0b-b864-1b47550e4380 |  | note | Test Conducting Authority-Subcontractor
label | fb2fbf06-5447-4efd-8462-83fe583b7e80 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test
label | c2d83815-3ea5-4aad-aff0-5a2a0c038ed9 |  | note | Controlling Documents-TNZ M/10:2014
label | deaa3983-a09f-49f8-b138-1860349322f6 |  | note | Acceptance Criteria-Contract Requirements
label | 38ea9761-bcf7-42f5-bc5e-007c679de826 |  | note | Method-PSV
label | 661808d1-9441-47b8-9e6b-d9b97f59b92e |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | 9f531c4a-e269-46ab-8179-ea63243fa266 |  | note | Responsible-Project Manager
label | cb437341-2731-46df-b7a4-4b27524d1887 |  | note | Test Conducting Authority-Subcontractor
label | b804d112-60e7-4253-9cb1-d5a3d2a672ad |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Weak Particle Test
label | ad066a43-3f91-4fb1-96d6-bc8d7b64c806 |  | note | Controlling Documents-TNZ M/10:2014
label | 13f57f68-cde8-454b-ad68-847d97955947 |  | note | Acceptance Criteria-1% max
label | 22bfb632-624f-4b29-a29e-a372a2fa4662 |  | note | Method-Weak Particle Test
label | 5a53439d-1da9-4da4-b377-2014c167d4ce |  | note | Frequency-1/1,000m3
label | 210f66f6-30b4-4327-a534-9ea1140243da |  | note | Responsible-Project Manager
label | 09e422e6-d0e5-4573-869d-d8191a19925f |  | note | Test Conducting Authority-Subcontractor
label | f1d1b029-bf8e-45eb-9b4c-706612bc3f78 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Particle Shape
label | 6e0c4f69-24f1-4a64-9846-14f83751510b |  | note | Controlling Documents-TNZ M/10:2014
label | 8e73e759-7e43-4b12-ac1e-313da1660de1 |  | note | Acceptance Criteria-2.25 max
label | d55acab2-fb25-4638-9759-dde15b1b0146 |  | note | Method-Particle Shape
label | 1d7b236f-3494-4d42-90c7-b0a3cce94224 |  | note | Frequency-1/1,000m3
label | 6931bf9f-e121-4041-8a14-f7668d528f68 |  | note | Responsible-Project Manager
label | 4baf73b0-a3ae-47f8-9f41-825f831f062d |  | note | Test Conducting Authority-Subcontractor
label | 3b86ae3b-5ee6-4e7a-aa6c-4a460d02b0d9 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Two Broken faces
label | 5130c0b9-2f47-4757-9c2c-a0a817866571 |  | note | Controlling Documents-TNZ M/10:2014
label | 9dc510ca-1c85-42df-8f0d-344aa57ed181 |  | note | Acceptance Criteria-98% min.
label | 11f6dbc6-a553-48bf-8014-7662fdd4ee22 |  | note | Method-Two Broken Faces
label | 123742e0-6a7d-43be-b426-35085dc3028e |  | note | Frequency-1/1,000m3
label | 19afae29-80dd-4d29-a55b-ccb7723f0653 |  | note | Responsible-Project Manager
label | 8db5eb48-dd9b-4d34-8a4f-bbc3e49a7b41 |  | note | Test Conducting Authority-Subcontractor
label | 03311591-af83-4f22-a236-d8027093f0d2 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - LA Abrasion loss
label | 49418050-41f4-4f06-8d42-789d8fa95524 |  | note | Controlling Documents-TNZ M/10:2014
label | 6a874fb1-12e1-4148-b6a8-982b9fc4b03b |  | note | Acceptance Criteria-Report Value
label | ae723981-ea97-4dd6-b204-ecf752376cc5 |  | note | Method-Los Angeles Abrasion Loss
label | 2a383ba0-b3d5-445f-888c-10dd826f884e |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | dd3275ec-69fa-491d-997e-c412b6f14988 |  | note | Responsible-Project Manager
label | 63285080-b570-40c7-8cd3-4411e9d50fd9 |  | note | Test Conducting Authority-Subcontractor
label | 18d11cc4-6671-444d-9016-af554aff9a38 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Wet/Dry Strength variations
label | d8b295cb-8567-4b45-886b-8bf8fb6af192 |  | note | Controlling Documents-TNZ M/10:2014
label | 120d46d0-b28d-451f-bddb-e356fee7c289 |  | note | Acceptance Criteria-Report Value
label | 41b96f59-7846-4a23-90b2-d882f182fd9e |  | note | Method-Wet/Dry strength variation
label | c0c609ac-fcd5-4215-bb16-2d16d1702c2b |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | f33228a0-05bb-41db-b51a-4b96d4b1dda5 |  | note | Responsible-Project Manager
label | 1c6b4586-8a3a-4da7-bdeb-f5624f0956d9 |  | note | Test Conducting Authority-Subcontractor
label | 4cdab149-950d-4b4e-983e-5d43fca5b4ce |  | note | Test Record Producing Authority-Subcontractor
checkpoint-status |  |  | checkpoint | Production Property Test - Water Absorption
label | 58545f90-66d8-4982-b90b-3d1c5c4643bb |  | note | Controlling Documents-TNZ M/10:2014
label | 8cbaf6cd-f06b-4889-a701-431221a77249 |  | note | Acceptance Criteria-Report Value
label | 3f2a448c-05b4-4aca-8f40-7d009c5adb47 |  | note | Method-Water Absorption
label | aa21d437-0487-4561-ae2c-149247380be9 |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | e26f9864-9a00-4846-b99d-8dfb8fedeab8 |  | note | Responsible-Project Manager
label | 80060e26-d900-49a1-a0e5-a7ee3f214f44 |  | note | Test Conducting Authority-Subcontractor
label | 0b10645d-ca39-49df-a2f5-fb8eae23c314 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-group |  |  | section | Procurement - Table 2.3 Fine Aggregate Requirements
checkpoint-status |  |  | checkpoint | Source Property Test
label | fdd0c70b-efc8-4e13-b212-b0cebefa0820 |  | note | Controlling Documents-NZTA M/10:2014
label | acfaffc1-19a8-49fe-9531-cd6868f89c2c |  | note | Acceptance Criteria-200kN min
label | dec3e627-c3f7-4ffe-9892-a70660375dae |  | note | Method-Crushing Resistance
label | c81ad4e6-1f8e-4a8d-a890-220af1164a31 |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | 2b38bebf-6528-4e03-81f3-45a571d66b37 |  | note | Responsible-Project Manager
label | 197e4a02-b4b8-4262-8ea9-fb5afb6d2443 |  | note | Verifying Document-IANZ Report
label | 15925649-1853-4627-84b1-1cf71e58a0e0 |  | note | Test Conducting Authority-Contractor
label | b1a93a39-f4f8-4db2-aad2-7282b82da344 |  | note | Test Record Producing Authority-Contractor
checkpoint-status |  |  | checkpoint | Production Property Test - Sand Equivalent
label | a29c88ca-878b-4d60-8cd3-4902e087091e |  | note | Controlling Documents-NZTA M/10:2014
label | e176693a-1b8a-4c68-878f-5d5650f1dd2d |  | note | Acceptance Criteria-35 min, or
label | 520569cb-f102-4c9c-a29a-9687d196a06b |  | note | Method-Sand Equivalent, or
label | ec653233-5a5a-49a2-9b48-64e593e476b0 |  | note | Frequency-1/1,000m3
label | ad586c13-6553-4e6e-bac5-5b92273e736c |  | note | Responsible-Project Manager
label | 16784998-2094-4c82-81be-2252f2eb6b70 |  | note | Verifying Document-IANZ Report
label | dc5c99c6-0350-4371-9aff-e376854382a2 |  | note | Test Conducting Authority-Contractor
label | f525450a-5dbc-40d9-a6de-ac72bb0fffc4 |  | note | Test Record Producing Authority-Contractor
checkpoint-status |  |  | checkpoint | Production Property Test - Clay Index
label | b1ec5499-4cc0-45bd-9e95-82ced8600f7a |  | note | Controlling Documents-NZTA M/10:2014
label | 3667f999-b498-4718-945c-8227572727d9 |  | note | Acceptance Criteria-3 max
label | f6d90f0b-0a38-4cb5-a513-46388c5d0d24 |  | note | Method-Clay Index ((<0.075mm)
label | 1ff120e3-86bb-401e-a1f8-ec409bde02c4 |  | note | Frequency-1/1,000m3
label | 7fdf18af-a42a-496d-a4eb-5964a2745385 |  | note | Responsible-Project Manager
label | af597e4f-6a3c-446f-83cb-4bdf8a416020 |  | note | Verifying Document-IANZ Report
label | dffb475d-35cf-4fc7-b894-1fe986ff497c |  | note | Test Conducting Authority-Contractor
label | 20c0fadb-7faf-4a85-ad55-3e0f44558a60 |  | note | Test Record Producing Authority-Contractor
checkpoint-status |  |  | checkpoint | Production Property Test - Water Absorption
label | 80abfd2d-bc09-4acf-b076-2f82262d0242 |  | note | Controlling Documents-NZTA M/10:2014
label | 283a5388-4586-4fdc-8057-bf9d58b08b19 |  | note | Acceptance Criteria-Report Value
label | b0e4887f-7bd7-4bf7-b657-c01262f1de93 |  | note | Method-Water Absorption
label | e8aed596-db16-4c22-b86d-fd98ffd56709 |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | 4f718408-40f4-45dc-a6db-ad5d99b67315 |  | note | Responsible-Project Manager
label | 360a0506-ddab-4f38-9fa2-83d44cdca4c7 |  | note | Verifying Document-IANZ Report
label | 39cbd2a7-eb0e-48b5-a30d-0b9d1cc679b2 |  | note | Test Conducting Authority-Contractor
label | 5413d189-15af-4e6c-8fd7-08b2118d1b6b |  | note | Test Record Producing Authority-Contractor
checkpoint-status |  |  | checkpoint | Production Property Test - Degradation Factor
label | 17d11e11-409f-47eb-b4a8-cc2fe1232474 |  | note | Controlling Documents-NZTA M/10:2014
label | eb54ea46-5705-4f3e-9af9-760bc8261ab1 |  | note | Acceptance Criteria-Report Value
label | a653eab7-7f50-42d5-87e6-e59fa47f6c71 |  | note | Method-Degradation Factor
label | c0b7da16-811b-4563-9305-b8b07b4ab807 |  | note | Frequency-Representative test values of the aggregates to be used in the contract
label | 852c40fc-25a9-4f90-8c05-fdeb1002e420 |  | note | Responsible-Project Manager
label | e061ca9e-e07e-4cac-a4a5-1e4f1b2b8115 |  | note | Verifying Document-IANZ Report
label | 34dc31d2-52ed-4fe0-ab32-260b1322c96d |  | note | Test Conducting Authority-Contractor
label | 04a58f41-22f7-4fdb-b0cd-5451c4e8ead3 |  | note | Test Record Producing Authority-Contractor
checkpoint-status |  |  | checkpoint | Bitumen Binder
label | 2dd9b609-9580-406b-9ce8-910878a7d618 |  | note | Controlling Documents-TNZ M/1:2011
label | 620bf6e4-3b6c-4a84-9c53-b37bd6d1adc4 |  | note | Acceptance Criteria-Table 1
label | 601d2e23-d34a-45cf-909f-3faf98019253 |  | note | Method-As listed e.g Penetration, Viscosity, Flash point etc
label | 295f10cf-c77a-48d5-a5e8-caa0c5cd0758 |  | note | Frequency-Approvals are for a period of 5 years after which time resubmission is required
label | fda402c0-71e1-422a-b924-be237c35900b |  | note | Responsible-Bitumen Supplier/Operations Manager
label | 990438ce-2f2d-484d-a142-fe7f185216c3 |  | note | Verifying Document-IANZ Report
label | 0758f4cf-5cce-4ebc-ab66-8037a18cd032 |  | note | Test Conducting Authority-Subcontractor
label | e10bd59b-2db6-4059-8a58-4d97f9d26753 |  | note | Test Record Producing Authority-Subcontractor
checkpoint-group |  |  | section | Temporary Works
checkpoint-status |  |  | checkpoint | Updated drawings available
checkpoint-status |  |  | checkpoint | Work completed as per specification and photos attached
checkpoint-group |  |  | section | Construction - Asphalt Concrete (AC) & SMA
checkpoint-status |  |  | checkpoint | Production trial
label | a1255275-d7c0-4221-a4ba-fb4c36106ba9 |  | note | Method-Binder, grading and volumetric analysis
label | 0a14263e-ba31-4907-96e9-ad7d0c7e9d90 |  | note | Frequency-2 days minimum prior to site paving works
label | 0dc7d887-320f-4309-a787-cbcfc53b5291 |  | note | Responsible-Laboratory Manager
label | 81e004be-6b38-4bfc-a505-c7fa85efe850 |  | note | Verifying Document-IANZ Report
label | 99aa7e4d-b6e5-4e85-80ae-28f67d24c56d |  | note | Test Conducting Authority-Contractor
label | 33f0206a-58b0-42a5-9f7c-890375f598bf |  | note | Test Record Producing Authority-Contractor
label | 78441ad7-3941-4952-90cd-5f578838079c |  | note | Test Approval Authority-Engineer / Client Rep
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | Trial Laydown- two 3m wide paving runs x 30m long at specified thickness with 1 longitudinal joint
label | 72154695-c868-4f3d-a4a0-39c7e9758304 |  | note | Acceptance Criteria-Contract Specification
label | 4393560b-43a2-4132-a57b-ae715c13188d |  | note | Method-Air Voids and Thickness; Mean Profile Depth (MPD)
label | 183c33c2-bf43-4d46-a948-9df2f205165e |  | note | Frequency-2 days minimum prior to site paving works
label | d22539c6-b1e9-4531-9f1e-446534696711 |  | note | Responsible-Laboratory Manager
label | 0815286e-9773-4d44-bd42-5ca79a131ecb |  | note | Verifying Document-IANZ Report
label | 7f725e9f-2348-443e-bc1d-48eb838697cf |  | note | Test Conducting Authority-Contractor
label | 45de1282-c5e7-421c-a654-94d0a4d17c59 |  | note | Test Record Producing Authority-Contractor
label | ba00f7ff-5f37-4d50-9606-a669b10d0b86 |  | note | Test Approval Authority-Engineer / Client Rep
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | Asphalt- Production Test - Particle Size Distribution
label | 92ea4442-42bd-4ecb-a44a-88222a296c42 |  | note | Controlling Documents-NZTA M/10:2014
label | 7e1a4c5f-6251-433b-af58-6084f0a36bcf |  | note | Acceptance Criteria-Compliance with the approved JMF applying:- Table 5.3 Production Tolerance for AC and DG grades Table 5.4 Production Tolerance for SMA
label | 3b441c64-c0bf-481f-ad2a-45641d413bec |  | note | Method-Particle size distribution
label | a6773ae8-6992-4690-8dba-ad73d074b2a6 |  | note | Frequency-Normal Frequency - 1 per 200t of production. 3 samples (32kg samples) max per lot. Lot consist of a day's or a shift production.
label | 27310fdf-e75c-4b1a-a1fe-b2c125ef9fd8 |  | note | Responsible-Project Manager
label | 3f6150c3-e9b1-4831-ab43-4f44e5e62d93 |  | note | Verifying Document-IANZ Report
label | 96fe9480-9ba0-41ef-8098-96b171e5f1ec |  | note | Test Conducting Authority-Contractor
label | 4a16313d-0857-4487-a186-d46b8abfdc52 |  | note | Test Record Producing Authority-Contractor
label | 03bb1e44-333b-451f-95d6-25f35d0381a0 |  | note | Test Approval Authority-Engineer / Client Rep
checkpoint-status |  |  | checkpoint | Asphalt- Production Test - Binder Content
label | 04399b2c-3b39-490a-8c2c-fa621278899b |  | note | Controlling Documents-NZTA M/10:2014
label | df7e9917-e4e3-4be8-8fb2-5339f1496b54 |  | note | Acceptance Criteria-Compliance with the approved JMF applying:- Table 5.3 Production Tolerance for AC and DG grades Table 5.4 Production Tolerance for SMA
label | 8b5757ee-e470-4a67-ba8f-a0f76023de7a |  | note | Method-Binder content
label | 4e1afc70-83ce-4215-a6e5-d9807791362c |  | note | Frequency-Normal Frequency - 1 per 200t of production. 3 samples (32kg samples) max per lot. Lot consist of a day's or a shift production.
label | 24791f4c-196c-4005-b579-ce1ae570d72d |  | note | Responsible-Project Manager
label | 318397f9-511c-4232-8441-a8dcdc483e9d |  | note | Verifying Document-IANZ Report
label | ef26806d-60d9-4a1b-8092-ab862d8063a2 |  | note | Test Conducting Authority-Contractor
label | 6617784f-56bf-4b74-8615-806bb99d6ea2 |  | note | Test Record Producing Authority-Contractor
label | 183599a4-a410-4a5b-87cf-1ee3bba813a2 |  | note | Test Approval Authority-Engineer / Client Rep
checkpoint-status |  |  | checkpoint | Asphalt- Production Test - Max Density
label | 5fae000b-baa5-4a81-82ec-e2ace352576d |  | note | Controlling Documents-NZTA M/10:2014
label | b12eef5c-17f5-43d6-a8cf-af0c81d2bd13 |  | note | Acceptance Criteria-Compliance with the approved JMF applying:- Table 5.3 Production Tolerance for AC and DG grades Table 5.4 Production Tolerance for SMA
label | 9011edeb-d5e8-4328-9af8-8b9bae2f4064 |  | note | Method-Max Density
label | f6533a4d-5bfe-439a-9dbb-989388762325 |  | note | Frequency-Normal Frequency - 1 per 200t of production. 3 samples (32kg samples) max per lot. Lot consist of a day's or a shift production.
label | ee6eae2a-59db-467f-b842-0f3862893ca6 |  | note | Responsible-Project Manager
label | 5c76e2cd-8a77-4402-bd81-7755fd8297e7 |  | note | Verifying Document-IANZ Report
label | 30df7b0e-17a0-4528-af15-5a78fa1477d4 |  | note | Test Conducting Authority-Contractor
label | e2996605-2050-48dc-b19f-5b277aba4ae9 |  | note | Test Record Producing Authority-Contractor
label | f07f69b5-856e-4971-a236-6aa124c947c4 |  | note | Test Approval Authority-Engineer / Client Rep
checkpoint-status |  |  | checkpoint | Asphalt- Production Test - Mixing Discharge Temperature
label | cf22920f-29a8-46c4-adf0-ff98075c7b8e |  | note | Controlling Documents-NZTA M/10:2014
label | 31b7e1df-04b4-45c6-9bd8-05d7088d55ed |  | note | Acceptance Criteria-Compliance with the approved JMF applying:- Table 5.3 Production Tolerance for AC and DG grades Table 5.4 Production Tolerance for SMA
label | e9afa102-c9a8-49ed-b98e-401c4972bc4f |  | note | Method-Mixing Discharge Temperature
label | cd0fda15-7ecf-4a20-9375-69c48ae5bb77 |  | note | Frequency-1 test / 200t of production
label | 84d4e18c-91aa-42a0-a277-fb6204e96e38 |  | note | Responsible-Project Manager
label | 5c0929a2-a867-47be-bc44-21fa658c1cd8 |  | note | Verifying Document-IANZ Report
label | 9261ba23-be14-4500-9e98-9755b94aa664 |  | note | Test Conducting Authority-Contractor
label | 2ecb8ab9-ea65-40ce-a426-39a14d96d7eb |  | note | Test Record Producing Authority-Contractor
label | 48b95f88-c262-417b-ae32-901f0a20670b |  | note | Test Approval Authority-Engineer / Client Rep
checkpoint-status |  |  | checkpoint | Asphalt - Production trial
label | 8fe6689b-b438-44f8-8747-dbc0cd88952d |  | note | Controlling Documents-NZTA M/10:2014
label | f325efe8-d74c-4f40-81e6-bfa3ab090858 |  | note | Acceptance Criteria-Ndes air voids value +1.0% , -0.8% Nmax air voids value >2.0%
label | e2e86695-b17b-47d5-b99a-47a24dec37e5 |  | note | Method-Volumetric
label | 8ed54664-377d-4c17-93f2-10a707acea7d |  | note | Frequency-1 test / 600t per Asphalt
label | 04fe6070-484c-4d99-ba30-c24e1adc469d |  | note | Responsible-Project Manager
label | 1d99e243-4449-4c8d-bebc-e5c585692333 |  | note | Verifying Document-Check Compliance
label | 39ab68e4-3595-4711-83e4-bd1c7d870f23 |  | note | Test Conducting Authority-Contractor
label | 3022876e-734e-459d-8ab4-bb057a5a4ff5 |  | note | Test Record Producing Authority-Contractor
label | 130acecc-8a51-428b-bd7b-6852e9df47eb |  | note | Test Approval Authority-Engineer / Client Rep
checkpoint-status |  |  | checkpoint | Ensure setting out is in place
label | 72a2ece9-95a7-4134-b15e-061bb87e60e6 |  | note | Method-Visual
label | 3c695c5c-4c55-462c-ae5f-b3ed85cfda7c |  | note | Frequency-Prior to start paving
label | 06f941e8-224a-4de7-8ca1-2c852b4a8b67 |  | note | Responsible-Project Manager
label | 2b3e4b47-aa1f-4771-8ab6-53cc1eee308d |  | note | Verifying Document-Survey Records
label | 6c92b1fa-6c6b-4244-b39a-c2682ddb59ac |  | note | Test Conducting Authority-Contractor
label | 3e31f8e2-e8e1-45e0-88ba-433212b34616 |  | note | Test Record Producing Authority-Contractor
checkpoint-status |  |  | checkpoint | Check weather forecast
label | 5fe012a2-0e19-4458-ba1e-181db83c06f0 |  | note | Acceptance Criteria-Not foggy, raining or wet surface.
label | 7d232b96-165b-4ded-bdb7-86df44a346b8 |  | note | Method-Weather Forecast
label | 9b92a874-6ac5-401a-b0ef-c2a10c5ca0c9 |  | note | Frequency-Prior to start paving
label | d3a8ab18-5a9e-4a9a-b3b8-769a5755af82 |  | note | Responsible-Project Manager
label | cc9cd652-315d-415d-ab05-4a43427299bf |  | note | Test Record Producing Authority-
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | Check surface temp
label | 31405937-653b-4b08-a44b-64648b238723 |  | note | Acceptance Criteria-Structural layer- surface temp ≥ 5ºC. Wearing course ≥ 10ºC
label | fcd56d6d-8e79-40d6-8f0b-4357cd4a625f |  | note | Method-Weather Forecast
label | 4fb37c48-0e8e-4e55-b98a-39d4254ec812 |  | note | Frequency-Prior to start paving
label | 4bee01d9-1e51-475f-8752-3dc815610d33 |  | note | Responsible-Project Manager
checkpoint-status |  |  | checkpoint | Ensure previous layer was signed off and broomed clean
label | d5404c99-40fe-4cd9-974c-d5fa3b07d09d |  | note | Method-Visual
label | 6650c05b-6ea8-474f-8bd5-83f78de2fd3b |  | note | Frequency-Prior to start paving
label | 61ef629b-d6f4-44fa-b4ca-74a6ad82f56f |  | note | Responsible-Site Supervisor
label | 99f5674e-1d5c-470d-afef-276244637e0d |  | note | Verifying Document-Record Sheet
label | b04e8a9f-8b18-498b-9f27-6b1f20f466f2 |  | note | Test Conducting Authority-Contractor
label | ea6244e3-9cb0-43f4-bb8a-bec757f3b6cd |  | note | Test Witness Authority-Engineer / Client Rep
label | 3c42ecec-8214-4a11-a931-b43314821a5a |  | note | Test Record Producing Authority-
label | 22b24b8d-8d1f-464f-9274-dd3f7bfc8055 |  | note | Test Approval Authority-Engineer / Client Rep
checkpoint-status |  |  | checkpoint | As-built records - structural patches
label | f042cd64-d8c5-44f4-afa1-f69a4d356bf5 |  | note | Controlling Documents-NZTA M/10:2014
label | abb67ce5-0fc3-4a1f-9e0e-3440c777d848 |  | note | Acceptance Criteria-NDM and core tests where required
label | c379938a-8939-49fa-8ed5-484d2915b49e |  | note | Method-Record as-built patch dimensions and RPs
label | 99ff81e2-7fbd-4511-a149-88ff8f781ab3 |  | note | Frequency-Per site
label | e72d2495-f724-4018-a797-3a6de7a92af0 |  | note | Responsible-Site Supervisor
label | 934ac410-682b-4214-b100-29e8b3b1d884 |  | note | Verifying Document-Record Sheet
label | c0ad7511-895f-45ce-b287-81f490ecd3b1 |  | note | Test Record Producing Authority-Contractor
checkpoint-status |  |  | checkpoint | Provide updates re site completion
label | f1289ba5-b375-4998-9a67-5ee6d1ac2d31 |  | note | Acceptance Criteria-Acceptable /unacceptable
label | 30dd3802-e443-4db3-9289-ad38267439e2 |  | note | Method-Phone call or text
label | 14e8ad07-6338-4f00-9620-f02eda8a35c0 |  | note | Frequency-per night or day
label | dd08e9e1-9731-4e64-904a-c4ac22dfac5a |  | note | Responsible-Site Supervisor
label | 7745f21c-e299-4f07-9bd7-9df647580938 |  | note | Test Record Producing Authority-
label | 762918f6-7577-477c-864f-f48d0e581ddb |  | note | Test Approval Authority-Engineer / Client Rep
checkpoint-status |  |  | checkpoint | Air Voids
label | d4719bb0-5630-4b82-aad4-ce19f76dbe99 |  | note | Controlling Documents-Table 9.2 Limits for characteristic values of in-situ air voids
label | 14db1855-c07f-4386-8913-62ddb795331f |  | note | Acceptance Criteria-Mat Density - Mix design air voids value +3% , -2%; Joint Density - Mix design air voids value +5% , -2%
label | 1efca35f-2509-4da7-b7c4-76603b7b714a |  | note | Method-Cores
label | 023eae54-90b7-460b-a973-1c8357f6083c |  | note | Frequency-1/300m2 with minimum 8 cores/lot
label | a7598add-ce8f-4a2d-85ac-e5af5f61f5c9 |  | note | Responsible-Project Manager
label | 0404761a-8a30-4a17-ac14-f4f84db1f5f8 |  | note | Verifying Document-Record Sheet
label | 97daf840-911f-4e58-9b7c-5f3909b677e5 |  | note | Test Conducting Authority-Contractor
label | 468cc393-2e6a-47d6-b36a-753de629c2fd |  | note | Test Record Producing Authority-Contractor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | Layer Thickness
label | 452c9aa5-42fa-4541-b7f3-cbd1071617f2 |  | note | Controlling Documents-Clause 10.3 NZTA M/10:2014
label | c06c35d7-df7e-4289-8615-dcbd32d278e0 |  | note | Acceptance Criteria-Non structural layer:; Structural Layer - average height of individual layer ≥90% of specified thickness.; Individual core ≤5mm than specified thickness
label | 603ec0c5-e1be-43a1-808f-bcb4ed516188 |  | note | Method-Cores
label | 77e67740-c9d9-4667-90e6-8073e5ccc978 |  | note | Frequency-1/300m2 with minimum 8 cores/lot
label | 00a7794f-cc17-4fe3-8e55-a2587f30184b |  | note | Responsible-Project Manager
label | 33902d55-d5bc-44d1-ab94-0ea3f6fc9b42 |  | note | Verifying Document-Record Sheet
label | 7953ac18-24ff-4006-a0a2-94b733ec69c9 |  | note | Test Conducting Authority-Contractor
label | ce1a9a68-a00e-4854-ad04-1ff24fdfac35 |  | note | Test Record Producing Authority-Contractor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | Ride Quality
label | 882649a1-199c-4bb1-a0c3-45473b2791b6 |  | note | Responsible-Renewals Manager
label | 55927743-abae-413f-94cc-28e1159367f4 |  | note | Verifying Document-Record Sheet
label | 93dcfc18-96ad-4dbd-b339-f85b88a535b3 |  | note | Test Conducting Authority-Contractor
label | b43607fa-3341-4b6b-8bf8-912d5bde170e |  | note | Test Record Producing Authority-Contractor
checkpoint-group |  |  | section | Additional Actions
checkpoint-status |  |  | checkpoint | Collect RAMM Data
label | f71416c3-7468-472f-9a39-93a97eaee087 |  | note | Method-Summarise as-built data in RAMM update spreadsheets
label | a972e346-006d-44f5-97f3-6dcda8ffc85c |  | note | Responsible-Renewals Manager
checklist-flat |  |  | checklist | ITP - In-plant Modified BC |  |  |  |  | Yes | ITP - In-plant Modified BC | 686010a5-0d37-4d1d-b727-2c8230eb0e0c
checkpoint-status |  |  | checkpoint | 4 - Modification Agent(s) Optimisation
label | 889e82eb-8ebf-44b2-a72a-a48d8674ae25 |  | note | Detail of Activity - Stabilised material strength - ITS
label | a07bb193-d4fb-47e7-8f3d-0d4e7e28af94 |  | note | Action (Hold, Monitor, Witness) - H
label | 4ca5a803-7503-447b-a5a1-67949fd6a0f6 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 Optimisation test per aggregate type
label | fca9b224-0965-448d-bf44-e6752252e34d |  | note | Inspection / Test method - NZTA T/19: 2020
label | d7e995d0-56f0-48bb-9528-f0ec3b5f753d |  | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa Soaked ITS: 150 kPa to 350 kPa
label | 5e6df133-5fce-467d-9d5f-e56a6b918d55 |  | note | Record documents - IANZ Report
label | a2ae0b39-ac35-46ba-b04f-f438421db22e |  | note | Responsibility - Client
label | 91b1ec14-368c-4f9c-b17b-85e3175ff6ee |  | note | Comments - Must be submitted to the pavement designer for approval at least 5 working days before modification works commence
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.1.1 - Check raw materials (whichever applicable)
label | df24df5d-7c48-4134-87fe-baebff423e94 |  | note | Detail of Activity - Cement
label | c63eadea-bb57-4100-8eb0-b58b9f961880 |  | note | Action (Hold, Monitor, Witness) - M
label | 5e8544a4-29af-4809-925d-2cc6a6857ce7 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Per Batch
label | d2179c66-19cc-4592-a902-5cd6ebe364f2 |  | note | Inspection / Test method - NZ 3122
label | 11b10a42-e5a6-4114-80c7-1ebcc88c486b |  | note | Record documents - Certificate in contractor's site folder
label | 8dc7e23f-6d50-4c36-a4d5-6b05b793def2 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.1.2 - Check raw materials (whichever applicable)
label | 041297a2-9bd1-47a0-b863-7cad8a944bba |  | note | Detail of Activity - AP40 Basecourse Aggregates
label | eda8ffcb-dc24-4023-900f-1c2dcb08c696 |  | note | Action (Hold, Monitor, Witness) - M
label | 14bc8158-9bd2-4f42-958c-403bad45aba0 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per 10,000 m2
label | 9fa4a77a-602f-4a09-8a0d-43372af0a90f |  | note | Inspection / Test method - PSD Plasticity Index Sand Equivalent MDD / OMC CBR
label | dfda170b-e290-49d5-9c3b-773385270583 |  | note | Acceptance Criteria - NZTA M04 / Project Spec
label | 06807593-8fcb-4397-86ff-4541df42ad6a |  | note | Record documents - IANZ Report
label | 83e6a92f-4102-400e-a01e-902487f96652 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.1 - Modified Basecourse
label | 0e79d754-7d9a-44a3-9c2e-2fa55ba0d808 |  | note | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents
label | f8ecc1c8-1870-4d46-b665-7e63f66a26e2 |  | note | Action (Hold, Monitor, Witness) - M
label | 3fd53a62-8da0-42cd-adae-623afa0c99ca |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Prior to works
label | b076430d-8b5c-4f69-a8aa-84b0af834b12 |  | note | Inspection / Test method - Measurement
label | 0fe2632f-f71d-4a93-93b0-54fd5fcc40e1 |  | note | Acceptance Criteria - Document existing furniture
label | c3c9d9d9-05ae-4ac1-b860-67812d56adeb |  | note | Record documents - ITP
label | 48b6f92a-309f-462a-b597-0b1ba6a7b559 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.2 - Modified Basecourse
label | 96bc75ee-87e6-435c-a123-82ecb99d654f |  | note | Detail of Activity - Depth of stabilisation
label | 953e2356-507e-4124-9220-20e65f0ae37e |  | note | Action (Hold, Monitor, Witness) - M
label | 08f39907-ea6e-43c6-894e-4bddfd5863ff |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Dips every 20m of surface before placing and after compaction of modified layer
label | c02bbd24-e1b5-4ebf-bf4b-44c8eb3499d9 |  | note | Inspection / Test method - Measurement
label | 7e64a8e7-2d3e-4a62-ab11-b3cfc5ffc957 |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | 1c007bad-071a-4c74-8251-0f23b1b94aaf |  | note | Record documents - Daily work Log
label | db0088ff-947e-42b1-8e21-4c6bd45a57a9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.3 - Modified Basecourse
label | 25be65e6-3650-415b-8e3a-53a1c4a6fc60 |  | note | Detail of Activity - Modified Maximum Dry Density
label | d3f06f8c-d414-4091-a599-33b810fc444c |  | note | Action (Hold, Monitor, Witness) - M
label | 65d0466e-85dc-417f-8f64-598f56e96523 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | 48e8750a-69cf-42d1-9f05-99f444a9befb |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 003578dc-5454-4c36-a167-92d1992bb23b |  | note | Acceptance Criteria - For analysis of DoC
label | a9fa3707-d37c-43ea-bd4d-88ae2d351a53 |  | note | Record documents - IANZ Report
label | cc1f763f-3615-43eb-b844-835a8794e25f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Modified Basecourse
label | d1531b7e-1a08-40b2-b18d-0bfa20faea04 |  | note | Detail of Activity - Plateau Density Test
label | 080a5348-417a-4ad5-b9e3-834a608a6170 |  | note | Action (Hold, Monitor, Witness) - W
label | e9603efa-fd02-48c9-b166-8a391bbef632 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | a5ded4bc-8c40-4e12-b382-c41f726126ad |  | note | Inspection / Test method - Draft Guide
label | 49c280f9-3db2-420a-8572-8d365fe4bfa1 |  | note | Acceptance Criteria - To establish roller pattern
label | 0cd4e1ec-3d39-4dfb-8ee3-db4b5b75f8cb |  | note | Record documents - test report
label | 4c16acc3-9fcc-4879-a007-51b17a320285 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.4 - Modified Basecourse
label | 6c3bcac5-214c-4495-89b4-5473f0b45bfb |  | note | Detail of Activity - Degree of Compaction (Nuke)
label | 287bb43d-b8d8-47f4-b3ca-0d8227093317 |  | note | Action (Hold, Monitor, Witness) - H
label | 8c6ee2ed-1d45-404e-9eca-0095640c0261 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 9 per Lot
label | f26d4452-367a-4d3a-adca-17517f979b38 |  | note | Inspection / Test method - NZS 4407.4.2.1 (to 150mm) and NZS 4407.4.2.2
label | f1954f66-40af-427a-86a9-bcc9231d3aba |  | note | Acceptance Criteria - NZTA B02: DoC ≥98%
label | 404c0d79-d362-4f12-a3be-9075e980a5af |  | note | Record documents - IANZ Report
label | 0f0aff1f-e73c-4efa-83cd-0284e7295a7e |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.1 - Modified Basecourse
label | 7f6e402c-054b-48f8-9ad6-e1edafffbbf8 |  | note | Detail of Activity - Layer Width
label | e1e64a54-c773-4bf2-8178-3ec588e94857 |  | note | Action (Hold, Monitor, Witness) - H
label | 22519834-8fa8-4fee-81d4-3f00f4417ad4 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 951165ae-d6af-4124-b614-d582800d703f |  | note | Inspection / Test method - Measurement
label | 9f16ca3b-b9b0-4907-af88-1b93b2181bbf |  | note | Acceptance Criteria - ± 10 mm
label | 9633c332-85fa-49ee-9a9b-ca2f64029f27 |  | note | Record documents - Survey
label | f37b10f7-dc08-4c87-808c-ee7ef94ac267 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.2 - Modified Basecourse
label | cbbd0177-8156-4ffa-b957-39a703609323 |  | note | Detail of Activity - Surface Shape
label | 907d86a7-5117-4bcc-b098-d973a92f4136 |  | note | Action (Hold, Monitor, Witness) - H
label | b4aa4dcf-943a-4e52-9f77-fcac9a795a70 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | d932e5fa-3405-43a3-8aed-d8c2c898de72 |  | note | Inspection / Test method - Measurement
label | a4e845d0-44a0-45f1-b24e-a592a71c31a8 |  | note | Acceptance Criteria - < 6mm using 3m straight edge
label | 2464d39c-f723-489b-8a40-c9aeeaa1e38d |  | note | Record documents - Worksheet
label | db69e777-69b3-44c0-9580-6fe6adfd5477 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.3 - Modified Basecourse
label | 3717a471-4b9e-4159-93df-4b411b52c906 |  | note | Detail of Activity - Surface Levels
label | 5821c2b8-756c-4ffa-bb9a-f76ee887ad75 |  | note | Action (Hold, Monitor, Witness) - H
label | 49542fae-cac0-4e6c-9a27-82fd30d30239 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | f23058c8-a778-4a67-9648-67196af55151 |  | note | Inspection / Test method - Measurement
label | 7b1e59ba-3dc2-465e-b547-6daad2ec3612 |  | note | Acceptance Criteria - +5mm, - 10mm
label | 0b18abee-7189-4d6b-bb81-b454b09060c3 |  | note | Record documents - Survey
label | 9401a456-5df5-43fd-bb64-07984a73de0f |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.4 - Modified Basecourse
label | 64f26098-423d-4497-aabc-28b0a65fc544 |  | note | Detail of Activity - Stabilised material strength - ITS
label | c0a994d1-2845-4e09-a737-b0ec72a9219c |  | note | Action (Hold, Monitor, Witness) - S
label | 19c05f1f-de5a-42ef-8be4-4f88c136e14d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 3 soaked ITS + 3 dry ITS per Lot
label | 7d934fb6-1f59-4928-815a-cfb39bdfe225 |  | note | Inspection / Test method - NZTA T/19 : 2020
label | 9609ae69-c01d-4ebf-8747-869131075d5c |  | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa Soaked ITS: 150 kPa to 350 kPa
label | 033c995f-709a-43a7-9c7f-8c36aba85015 |  | note | Record documents - IANZ Report
label | b5f8c08a-0ec0-40c0-8619-1458df8b1377 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.3 - Non-conforming results
label | 5ce5c325-1004-4305-9739-d8b7a20929e4 |  | note | Detail of Activity - Assessment of all test results for conformity
label | 4aa0919d-1c31-4d37-bfa3-20a5208e6d84 |  | note | Action (Hold, Monitor, Witness) - H
label | 1cf4055c-37e5-4e9f-a509-5129958160e8 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Each Lot
label | cc068129-9e1f-479c-9c68-3b2ffaf480ac |  | note | Inspection / Test method - Site Inspection
label | 545c8040-535e-4706-8197-2a61406972f4 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | aaff4b37-c7a9-4d37-98e3-d6b3812d5454 |  | note | Record documents - NCR
label | 2f054aff-bb40-4405-a0b6-a70da7b6f1ca |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 9494e03b-9939-4639-a0c8-5d032f0297aa |  | textbox | Contractor's Rep Name:
text | 28e2f138-3ead-4f55-a273-3533160cf209 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - AC Mix Design |  |  |  |  | Yes | ITP - AC Mix Design | 930a3fb4-7a0c-4648-b1e5-d37872d934ba
checkpoint-group |  |  | section | Asphalt Constituents
checkpoint-status |  |  | checkpoint | 7.0.1 - Course Aggregates
label | 1978954a-8ca7-4ef1-9158-12906498f896 |  | note | Detail of Activity - Crushing resistance
label | 2a1d70bd-70c3-44af-b7bb-f59f66d6a693 |  | note | Action (Hold, Monitor, Witness) - M
label | 9a0b024c-34e0-4331-854b-33f06621635b |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 384b66cd-6bc6-486a-9d62-d72362595925 |  | note | Inspection / Test method - NZS 4407 Test 3.10
label | f3d7d70c-07a3-4d34-be74-b353bbb06a7f |  | note | Acceptance Criteria - ≥ 200kN [NZTA M/10]
label | 2e1ca06e-78ab-4612-9c5a-464b21cfae23 |  | note | Record documents - IANZ accredited test cert
label | cc16cca4-5369-44f2-baf0-add51b0be7db |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.2 - Course Aggregates
label | af8331f3-816e-4b66-a70e-fd5192333623 |  | note | Detail of Activity - Weathering Quality Index
label | da0d2cc2-a1f5-4220-91a3-1a9161e33a0a |  | note | Action (Hold, Monitor, Witness) - M
label | 2e37f9ef-3dc2-40de-bef8-6726d8280e4d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 9016b71e-4015-4f68-bbad-7e00e8bfccf1 |  | note | Inspection / Test method - NZS 4407 Test 3.11
label | 0d83fab9-d176-45f2-9e3e-d521ecafe8ff |  | note | Acceptance Criteria - AA or BA [NZTA M/10]
label | dd61d577-2ba3-4d92-a7e6-81c6dddc475f |  | note | Record documents - IANZ accredited test cert
label | 167c29a4-1467-4fbb-90f8-3d85f68058cd |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.3 - Course Aggregates
label | 2333a1ac-b64f-4775-8679-a313665e2c96 |  | note | Detail of Activity - Single Broken Faces
label | d3155455-4be4-498e-81f9-6071d970406a |  | note | Action (Hold, Monitor, Witness) - M
label | c6fec48f-9a65-48f8-abfd-35971c7bd088 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 4162b5d6-00ef-4cd1-8a22-cc0d2800a7eb |  | note | Inspection / Test method - NZS 4407 Test 3.14
label | cfa4364c-3eb2-4cf1-9171-4fc24166228a |  | note | Acceptance Criteria - ≥ 98% [NZTA M/10]
label | 307ccb83-d706-491a-920b-2b5d8d084f3f |  | note | Record documents - IANZ accredited test cert
label | c355d52c-ce00-4875-ad2d-6acf3c5f01ab |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.4 - Course Aggregates
label | 666f9cc1-9ef7-4d42-ba68-0b7d96be44f0 |  | note | Detail of Activity - Two Broken Faces
label | 82510640-113f-4540-b424-2eb03c956d49 |  | note | Action (Hold, Monitor, Witness) - M
label | 03a0af5f-10e6-4c7c-bbc2-2e3cc8f94480 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 11e42000-8077-4553-8b55-b23c37e8f83c |  | note | Inspection / Test method - NZS 4407 Test 3.14
label | 8ae4c1ca-b93b-444b-b2d6-a239f1086f4f |  | note | Acceptance Criteria - ≥ 60% [NZTA M/10]
label | 21cae3fe-93e7-492d-a704-c83d476eecbd |  | note | Record documents - IANZ accredited test cert
label | 5ab27b9a-b032-4f75-ae8c-ecf70d2aba5e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.5 - Course Aggregates
label | 8e27332f-dffc-49b1-a940-8034e3351c07 |  | note | Detail of Activity - Polished Stone Value (AC14 surfacing only)
label | 189efe2e-da3e-425e-b411-7bdfc8583627 |  | note | Action (Hold, Monitor, Witness) - M
label | 3000665c-1dd2-4bd2-a9e4-ef8ec24f9c79 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 343d2f76-a06b-45ef-a53f-94c5014c27db |  | note | Inspection / Test method - BS EN 1097 Part 8
label | f8dc1a3d-f87f-455d-9040-73aeafac7677 |  | note | Acceptance Criteria - As per specific contract requirements
label | cf79efa6-2069-482f-8a99-af838cf706c0 |  | note | Record documents - IANZ accredited test cert
label | 75fd3d55-31fd-4bfe-94d8-dff29f037749 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.6 - Course Aggregates
label | 6b4ee9ad-511e-45bd-adeb-e230bf2f0f44 |  | note | Detail of Activity - Los Angeles Abrasion Loss
label | 5f2ad7c6-cfd2-46f4-8e68-73b5a955ceba |  | note | Action (Hold, Monitor, Witness) - M
label | 74b0d46c-dd0b-46e2-85d3-427530307500 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | ccef467a-b4d9-4a11-bc84-ce36c8a815de |  | note | Inspection / Test method - NZS 4407 Test 3.12
label | 33cfcf68-2ff0-4526-a596-7689b5a30e8a |  | note | Acceptance Criteria - Report Value
label | 4c2d4037-d00d-47c1-af25-9968fe0ecfcd |  | note | Record documents - IANZ accredited test cert
label | 7ea6c0ca-3fcf-43be-b5d2-6d09f45ecf30 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.7 - Course Aggregates
label | 220598fb-937b-4b5b-91a5-e1f824eec478 |  | note | Detail of Activity - Wet/Dry Strength variation
label | 8108ceb2-e428-4a1d-88a3-6cbdc7dd810b |  | note | Action (Hold, Monitor, Witness) - M
label | 106ec99c-7ede-4e3c-ae5e-4a7f9d1542f6 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 0c219e5e-58a7-40bd-a5d8-2e76906d15d3 |  | note | Inspection / Test method - AS 2558 Part 5
label | 78d00f0c-b7ec-43c6-843c-336f6c67c54a |  | note | Acceptance Criteria - Report Value
label | 3ec31869-c189-4ba6-b8a7-48a0e613baed |  | note | Record documents - IANZ accredited test cert
label | ade22050-b943-409d-a1b5-126f4060ef81 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.8 - Course Aggregates
label | 6a67dceb-2b30-45b8-bb64-8ff1b29be9df |  | note | Detail of Activity - Water Absorption
label | 1c93acad-b39b-4f59-9d1b-753a325083ad |  | note | Action (Hold, Monitor, Witness) - M
label | 5f12f40f-9718-4cdc-bd12-df8619ee9944 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | c1ba2fb8-a615-4095-a7df-c18f704ac960 |  | note | Inspection / Test method - AS 1141 or ASTM C127
label | e5f38fdf-d8ed-4352-abe0-cb4f4bdfdf07 |  | note | Acceptance Criteria - Report Value
label | b1460fdb-fb0c-4fd4-8880-5891b6810ab1 |  | note | Record documents - IANZ accredited test cert
label | 27e23c3d-26ef-458a-87fa-31572906f024 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.9 - Fine Aggregates
label | 7e395a48-2d1f-4274-bd52-46d310ec7d79 |  | note | Detail of Activity - Crushing resistance
label | 5684c6c8-eb99-4bf7-b5f4-efd6ed8d7512 |  | note | Action (Hold, Monitor, Witness) - M
label | 663b5c35-adef-4a5f-9d41-1a51c0c6981c |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 5024516c-5662-4cab-9659-cb1a7a62bde7 |  | note | Inspection / Test method - NZS 4407 Test 3.10
label | 0f3cb806-fe46-47b1-bf7d-8cc5de342ada |  | note | Acceptance Criteria - ≥ 200kN [NZTA M/10]
label | 92557e65-efba-4b3c-9349-6723ecfd46f6 |  | note | Record documents - IANZ accredited test cert
label | d5056e68-4694-4c20-baee-398eb3b5036e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.10 - Fine Aggregates
label | c773c44b-ec97-46cc-b619-bc5024188874 |  | note | Detail of Activity - Sand Equivalent
label | 64b3bd48-96f9-43a6-b8ff-8a71a13c1a43 |  | note | Action (Hold, Monitor, Witness) - M
label | c173453a-4f7a-487e-8578-ab8dff8c6886 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 8cae2c36-a046-429e-b65d-ff809eae2bc2 |  | note | Inspection / Test method - NZS 4407 Test 3.6
label | f4482ae9-aec9-4d95-9907-9d6330a8faec |  | note | Acceptance Criteria - ≥ 35 [NZTA M/10]
label | 8f05270a-b05d-4a17-b9a2-3f99d8676a25 |  | note | Record documents - IANZ accredited test cert
label | 5657ddf1-8792-4d79-bddf-71aeca31540a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.11 - Fine Aggregates
label | afc83f1c-304a-4bbd-8fff-f982d7d4587a |  | note | Detail of Activity - Clay Index
label | c88eb87c-df45-4106-b431-d9f720d2ec7c |  | note | Action (Hold, Monitor, Witness) - M
label | 7dad1952-6f73-4e32-a4da-73a56fb60e1e |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 51afb1a4-ea24-4be9-8d62-c7f765712397 |  | note | Inspection / Test method - NZS 4407 Test 3.5
label | fccca929-97ed-411c-af15-7f47521b8272 |  | note | Acceptance Criteria - ≤ 3 [NZTA M/10]
label | 8fe7ce03-7404-4512-b7c7-7caa26a2e270 |  | note | Record documents - IANZ accredited test cert
label | 1a454209-f727-4231-b363-3a771a3a22de |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.12 - Fine Aggregates
label | 8a8b40b2-271f-4536-a698-3dc510491d03 |  | note | Detail of Activity - Water Absorption
label | 71cc3bdb-547f-4acc-984d-e6450d83144e |  | note | Action (Hold, Monitor, Witness) - M
label | 77c2bb7f-4f01-409e-a725-575671c3eeb6 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 907ae34b-23fc-4617-b312-c0e2900df099 |  | note | Inspection / Test method - AS 1141 or ASTM C127
label | 0594bfd6-01dc-4707-ad5a-f8acadba9641 |  | note | Acceptance Criteria - Report Value
label | 8eb1c39e-39b3-4396-99d6-938c2da3300c |  | note | Record documents - IANZ accredited test cert
label | 829a50c5-b4ee-4d79-8024-56930ee67844 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.12 - Fine Aggregates
label | aff3f92e-89ba-4b66-a369-b734a93474fb |  | note | Detail of Activity - Degradation factor
label | 660a07e5-54fa-486a-ae1f-8b3bb004fbd5 |  | note | Action (Hold, Monitor, Witness) - M
label | 9a0b8d9f-5d6d-4a64-a186-d18298e31839 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | c4826e91-f32c-4ca1-a546-489fd3f1f1a4 |  | note | Inspection / Test method - AS 1141.25.3
label | 31ac60ca-7253-4afe-8ed1-e2de0d357737 |  | note | Acceptance Criteria - Report Value
label | ce3a18e9-9a54-4069-9e2d-a870ccb61c31 |  | note | Record documents - IANZ accredited test cert
label | 6e552629-87b3-4bc4-b03b-4d5740f7615c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.14 - Mineral Filler
label | 40d03bc1-2da0-4442-a29b-4248832cab23 |  | note | Detail of Activity - Particle Size Distribution
label | 8a759ef9-5103-4a7b-b46b-bbb62a3e4beb |  | note | Action (Hold, Monitor, Witness) - M
label | a441e7e2-9cb0-4acf-8ca1-84ba2228f6d5 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 5801039c-0778-4dae-b2ea-2bb1a220c73d |  | note | Inspection / Test method - NZS 4407
label | 215b0b54-52c3-4827-b391-910bc1c8c2d6 |  | note | Acceptance Criteria - Table 2.4 NZTA M/10
label | 56cc3ba4-3c26-4c76-968f-7655794ec2e4 |  | note | Record documents - IANZ accredited test cert
label | 545a3c79-7248-44df-9a27-e8f74f3c4c8b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.15 - Binder
label | 44260154-ad70-4a8f-887f-15064934847e |  | note | Detail of Activity - Flash point
label | 50f1b3ea-40bb-45b7-9ce1-fc7e846cbbaa |  | note | Action (Hold, Monitor, Witness) - M
label | cec175b7-be4c-4f1e-bdb7-48191bed6ac5 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | bf00d9cc-3c72-49a3-9c08-5f28a2b5750b |  | note | Inspection / Test method - AASHTO T48 or ASTM D92
label | c0adc75e-3584-431f-8aff-20849fc841a3 |  | note | Acceptance Criteria - ≥ 230 ⁰C [NZTA M1-A]
label | 1c83970d-bb2b-4d52-9f4d-dcd8637b58cb |  | note | Record documents - IANZ accredited test cert
label | b0fa0360-c358-4000-b7ad-9fc2fef65cb0 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.16 - Binder
label | 8e6bdc85-9573-4817-90c2-9562cb243a49 |  | note | Detail of Activity - Viscosity at 135 ⁰C
label | 19521e1e-a4f1-4a99-9c25-979380207283 |  | note | Action (Hold, Monitor, Witness) - M
label | 8c70458e-0a03-46a1-8488-6ebd1bdef0d2 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | ca8f214b-f224-455e-9b5e-911a306a5ecd |  | note | Inspection / Test method - AASHTO T316 or ASTM D4402
label | ef5f74e4-f95c-4461-94f4-fc99e16cebee |  | note | Acceptance Criteria - ≤ 3 Pa.s [NZTA M1-A]
label | e374d8c3-ff31-4bba-b31f-d21364aff81b |  | note | Record documents - IANZ accredited test cert
label | a4da5dea-8e28-46bc-9c0b-52a3e48cf28b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.17 - Binder
label | a66b0f27-692b-428c-bc86-192f082ca4ac |  | note | Detail of Activity - G*/sinδ at 64⁰C @ 10 rad/s
label | ae895526-b515-4e5b-bc93-70ed79d0e0a9 |  | note | Action (Hold, Monitor, Witness) - M
label | e07c7ab9-7889-4741-917e-455306e2f89e |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | 24018c5f-c665-4d8d-b439-6eb13902e72b |  | note | Inspection / Test method - AASHTO T315 or ASTM D7175
label | 1ef510cb-78c9-454a-bdfd-18c2c25d1df5 |  | note | Acceptance Criteria - ≥ 1.00 kPa [NZTA M1-A]
label | 8a268edc-f877-4fea-80e8-ae7128b324fc |  | note | Record documents - IANZ accredited test cert
label | 614e4285-f496-465f-a7a7-ebf518e9cdc9 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.18 - Binder
label | d45812ec-8144-499f-b5f8-5e5d5c5bd8b8 |  | note | Detail of Activity - RTFOF residue: Mass change (+ve and -ve)
label | 29f1d30f-154c-41b0-aed4-c137c37fd1d5 |  | note | Action (Hold, Monitor, Witness) - M
label | 5e4e6e92-8682-4789-855d-c5bec57e624e |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | 491192d9-0b1d-41cd-a132-ede8109b7910 |  | note | Inspection / Test method - AASHTO T240 or ASTM D2872
label | fd2dcc5a-3680-42b9-a586-9e3a4d2caf2d |  | note | Acceptance Criteria - ≤ 1.00% [NZTA M1-A]
label | 7965dc5e-5b6c-457e-9a99-17caaa4c472f |  | note | Record documents - IANZ accredited test cert
label | 8c5ca47f-8c6e-49ff-b492-aafb298d707e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.19 - Binder
label | 4f6f9591-f7d2-4940-b344-eccbae5dd7f7 |  | note | Detail of Activity - Jnr3.2 at 64⁰C
label | d3888fc0-7104-46de-82fa-7ca1900e6af0 |  | note | Action (Hold, Monitor, Witness) - M
label | 03c21ffc-9d11-4fcb-bc50-992d8145c098 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | e49fd408-3751-4e98-9fdf-f043b8882a57 |  | note | Inspection / Test method - AASHTO T350
label | 32b2837b-3e8d-4c16-bf74-ec1cbc899bbf |  | note | Acceptance Criteria - ≤ 4.5 kPa (S); ≤ 2.0 kPa (H); ≤ 1.0 kPa (V) ≤ 0.5 kPa (E) [NZTA M1-A]
label | e4463ee1-27e2-4fa7-b64b-07e5aa7089cd |  | note | Record documents - IANZ accredited test cert
label | 94ea459f-3b14-4912-b089-5ac5b1688b75 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.20 - Binder
label | 89cb53e9-aaf5-4a9f-b07f-ffafeb22a253 |  | note | Detail of Activity - Jnr3.2 at 64⁰C
label | 8dcf5a00-ab17-442d-a5b0-ff3b6a6ff6d3 |  | note | Action (Hold, Monitor, Witness) - M
label | 98b3b214-af19-49c5-b0c0-8550bf5fbbd8 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | 5b061698-e7a0-4a3c-a32a-b5198ef8c572 |  | note | Inspection / Test method - AASHTO T350
label | 2b1a8bab-aa52-42e5-8568-4161baded0be |  | note | Acceptance Criteria - Report Value
label | 52c80c7f-7564-4b43-b507-07b416a9c009 |  | note | Record documents - IANZ accredited test cert
label | cff3d8ff-d5b9-4730-8e55-1a9fb4a70e7d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.21 - Binder
label | 97f09cfd-637f-4cd0-b009-7a9b98b0d3d3 |  | note | Detail of Activity - PAV residue (aging temp of 100⁰C) G*/sinδ at 28⁰C @ 10 rad/s
label | ebc24841-dbad-46b0-94a4-38798fab1bf4 |  | note | Action (Hold, Monitor, Witness) - M
label | ec07828d-bc05-4842-889a-29596ee91057 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | d9b8d0f5-7a61-4772-b8c6-1835e38b565b |  | note | Inspection / Test method - AASHTO T315 or ASTM D7175
label | 0880bd95-bd08-43fe-863c-435f8b1ecc13 |  | note | Acceptance Criteria - ≤ 5000 kPa (S); ≤ 6000 kPa (H, V, E) [NZTA m1-A]
label | d07d4fc0-633f-4c36-9313-31a8e1e35fab |  | note | Record documents - IANZ accredited test cert
label | 1167210c-95ad-4882-83fc-f9eb575db322 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.22 - Binder
label | 9ac84949-9235-46c8-8693-9eeaef8c7c4f |  | note | Detail of Activity - S at -6⁰C @ 60s
label | 5ef388f2-3928-4ca7-ad8f-b447031a48b9 |  | note | Action (Hold, Monitor, Witness) - M
label | c8522de9-0084-4636-b046-30306891c634 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | 859fce23-0e3d-4247-964a-ca58a4876ec3 |  | note | Inspection / Test method - AASHTO T313 or ASTM D6648
label | 0cb538a3-19b0-4177-95ed-bbf35d88a465 |  | note | Acceptance Criteria - ≤ 6000 kPa [NZTA M1-A]
label | 07de5363-031a-4b6a-9ef8-1772ce054c8f |  | note | Record documents - IANZ accredited test cert
label | 444c3593-a7d7-479c-a264-b57a35b01c43 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.23 - Binder
label | 9a9b9b80-1c67-4b56-b47d-0dd316ba6688 |  | note | Detail of Activity - m-value at -6⁰C @ 60s
label | da5dec9b-ae5e-4ffc-80db-cf6573049213 |  | note | Action (Hold, Monitor, Witness) - M
label | 3814ea94-2023-471e-a72f-f3bfb66ddf4a |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | 135887d6-19ec-4b0f-a0ac-ddc8359bcb39 |  | note | Inspection / Test method - AASHTO T313 or ASTM D6648
label | a3214112-7076-4177-9bad-25141bb87cb9 |  | note | Acceptance Criteria - ≥ 0.300 [NZTA 1-A]
label | 15f21b12-f053-442b-aa3c-b67b174cde1a |  | note | Record documents - IANZ accredited test cert
label | 55e4cca1-4d4b-4ba4-9606-1098d3b1d102 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.0.24 - Binder
label | f694b7b7-8d60-4182-8765-170acedb07d5 |  | note | Detail of Activity - Failure strain at -6⁰C @ 1.0 mm/min
label | 9d64311a-25f6-4cd6-a700-dbfe3bb5e928 |  | note | Action (Hold, Monitor, Witness) - M
label | f0ec47e3-dc49-422f-a88b-9ce56cbb184d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per batch of bitumen
label | 2d8604bb-ed56-41db-a1b1-c6e799473148 |  | note | Inspection / Test method - AASHTO T314 or ASTM D6723
label | e7ef8f88-ccc8-4b07-a622-30909eff9e0d |  | note | Acceptance Criteria - ≥ 1.0% [NZTA m1-A]
label | fd30fe07-40c7-4ca2-9044-8c61aeac81fb |  | note | Record documents - IANZ accredited test cert
label | ba517fbc-addc-4bfb-963b-be76bc43cd54 |  | note | Responsibility - Contractor
checkpoint-group |  |  | section | Asphalt Mix Design
checkpoint-status |  |  | checkpoint | 7.1.1 - Asphalt mix
label | a84b7e11-cc31-4414-ad2d-f7c2d48777a5 |  | note | Detail of Activity - Mix design report and JMF
label | 864278af-a006-4dea-8fb0-3a059fca1d7c |  | note | Action (Hold, Monitor, Witness) - H
label | 4a160e8c-362d-4622-bfee-309019086f80 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per site location
label | 738bf312-90a8-465f-a936-f6a098b1e66b |  | note | Inspection / Test method - Review
label | 1c1b20ec-f0f2-4805-91b6-1353fc5a7bc9 |  | note | Acceptance Criteria - NZTA M/10
label | d06722fd-ab1e-4eba-b47b-35200049ff80 |  | note | Record documents - Mix Design report
label | 9ca4eddf-a9e0-4a0d-8ab4-4f3b2f137ebd |  | note | Responsibility - Contractor
label | 6ee31fe0-0705-495d-8578-bc5cd07835a3 |  | note | Comments - Mix Design report including all testing outlined in this ITP and table 3.10 [NZTA M/10] to be issued to the Engineers Rep at least 7 days prior to paving
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1.2 - Asphalt mix
label | 77124478-6cb9-45f2-bf47-a4ba91e3719e |  | note | Detail of Activity - Aggregate Particle Size Distribution
label | 0a91716e-cd68-40f4-bb2a-4e32884029e0 |  | note | Action (Hold, Monitor, Witness) - H
label | eba114f9-aca3-42f5-9bfb-288edb47cf1b |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per site location
label | cd5706cc-83f5-431e-b28a-a59d89d800bb |  | note | Inspection / Test method - NZS 4407 Test 3.8.1
label | 5267968f-23d4-4154-9beb-1ba4578b7e48 |  | note | Acceptance Criteria - Table 3.1 NZTA M/10
label | 58a86548-8d94-4a06-9d39-45933710c813 |  | note | Record documents - IANZ accredited test cert
label | 11d5bf2d-97d5-4ef1-956a-e4da5cdc75aa |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1.3 - Asphalt mix
label | 07ae6932-5bd1-4c0f-9ecb-c2de2217d5c7 |  | note | Detail of Activity - Binder Content
label | 10c61cde-37b8-47cb-9468-b9126b044683 |  | note | Action (Hold, Monitor, Witness) - H
label | 7b68cf6d-8bdc-49a7-9e80-4db988fb5f9d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per site location
label | 83496825-7359-4e3b-b28c-ca2f200b0cdf |  | note | Acceptance Criteria - Table 3.1 NZTA M/10
label | 0684313f-5a2d-4640-94af-0da4b2d75132 |  | note | Record documents - IANZ accredited test cert
label | 8869784d-bfc3-400a-a2dd-9a8f97842186 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1.4 - Asphalt mix
label | 82ff0676-2014-413c-8fe9-7ea37b903fae |  | note | Detail of Activity - Target Design Air Voids
label | 7a58affd-ccf5-4ad3-a723-860ba22c3d01 |  | note | Action (Hold, Monitor, Witness) - H
label | 67996ae4-002c-42e9-aedc-76e3d42c0f2d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per site location
label | 81a4242b-b3c6-422d-9bbd-9ecd741dc1dc |  | note | Inspection / Test method - Gyratory Servopac or
label | 092114ea-49b9-45d3-b387-a64ba03ba3ff |  | note | Acceptance Criteria - Table 3.4 [NZTA M/10) Light = 4% Voids 40 cycles Medium, Heavy = 4% Voids 80/120 cycles V.Heavy = 5% Voids 120 cycles
label | fc4bc762-f7ec-4f45-a8ff-4efab0ca7f6e |  | note | Record documents - IANZ accredited test cert
label | 3b5eec42-e0d7-4ebc-b987-157e34f3d42c |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1.5 - Asphalt mix
label | b0873b43-f5b4-4dbf-acda-b089bda83fa2 |  | note | Detail of Activity - Target Design Air Voids
label | 8b1016e2-327f-4e09-b197-37fb3b5e2c4c |  | note | Action (Hold, Monitor, Witness) - H
label | 05c0859d-03ac-46ce-8064-92357e810db1 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per site location
label | 5ff34b19-efce-4c1e-8628-1c9d6814c2a8 |  | note | Inspection / Test method - Marshall
label | a0eb03fe-1cec-42d1-8a14-9895ef6eee60 |  | note | Acceptance Criteria - Table 3.5 [NZTA M/10)
label | c2b22f05-fd26-450c-85eb-ec1f452cc4d9 |  | note | Record documents - IANZ accredited test cert
label | 89b4db0c-7210-4131-94ab-79a04cfdc1e4 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1.6 - Asphalt mix
label | 9a2d4bd5-c08f-49a6-9de6-4ef565c25ed2 |  | note | Detail of Activity - VMA for DGA mixes
label | 439b2e04-833d-4e64-a42a-e2a2ca690e7a |  | note | Action (Hold, Monitor, Witness) - H
label | 087c02b6-ef97-448e-8f34-b80b830c8989 |  | note | Acceptance Criteria - Table 3.6 [NZTA M/10]
label | 9b05cdfd-adf3-4c29-adde-58165bf4df72 |  | note | Record documents - IANZ accredited test cert
label | f4671169-0bc4-4f10-a87a-6d4235554b36 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1.7 - Asphalt mix
label | cc1ba01b-4563-4128-8e19-67ac44a7bb02 |  | note | Detail of Activity - TSR - Tensile Strength Ratio (only for DGA mizes)
label | fb000f17-d495-4e7d-bf06-f0ad83335530 |  | note | Action (Hold, Monitor, Witness) - H
label | 26b30c5a-2e60-4146-a27f-75bc023b71de |  | note | Acceptance Criteria - ≥ 75% [NZTA M/10]
label | e08c63d9-1e4d-4678-81d4-42222bd80a74 |  | note | Record documents - IANZ accredited test cert
label | c84c6540-45e9-481b-afba-ca12a7645ab4 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.1.8 - Asphalt mix
label | 713efdf2-95fe-46aa-ba3d-d2db07271e85 |  | note | Detail of Activity - Wheel Tracking (only for H and V.H DGA mixes)
label | 328ebd52-f85b-4489-b9c7-a2939d78d124 |  | note | Action (Hold, Monitor, Witness) - H
label | cf30bd72-dae1-4c21-9af7-2304cb139f91 |  | note | Inspection / Test method - AS2891.2.1; AS 2891.9.2;AG:PT/T220; AG:PT/T231
label | 3884302a-9c8a-492c-89cb-96b5222277ca |  | note | Acceptance Criteria - ≤ 6.0mm [NZTA M/10]
label | 693ee3ce-09ae-469b-af52-3e1ba7a40379 |  | note | Record documents - IANZ accredited test cert
label | e3037300-a85f-426a-8943-1400d5f2d87c |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Asphalt Mix Design Acceptance
checkpoint-status |  |  | checkpoint | 7.2 - Asphalt Mix Acceptance
label | bc5365ae-45af-42af-8b26-28cc189a29a8 |  | note | Detail of Activity - Assessment of all test results for conformity
label | ac2a5dda-3d91-4842-a682-b778e5ca54b4 |  | note | Action (Hold, Monitor, Witness) - H
label | 462d3f06-3ce0-4dc0-b961-bf96b79642d7 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - For each mix used on the project
label | a8c5c2c1-77c2-4cb7-b745-35af920a2143 |  | note | Inspection / Test method - Review
label | 8ccc5862-6b01-4d67-9bee-902aa64d3c19 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 45b8bb62-fd1c-426b-bb8a-c756e16ea2cd |  | note | Record documents - NCR
label | b550ce1d-f368-4bf3-a58a-cff28a67ef2c |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 1b6926d2-9500-4369-aaf1-ed08fa8eef5a |  | textbox | Contractor's Rep Name:
text | 57f5a84a-475f-47a0-ab48-c83f06ef1254 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP - In-situ Modified BC |  |  |  |  | Yes | ITP - In-situ Modified BC | 96207e46-ce8c-4866-9a5d-81210c171119
checkpoint-status |  |  | checkpoint | 4 - Modification Agent(s) Optimisation
label | 4b6e8f81-4b74-4e6d-8caf-c59b62d2fe63 |  | note | Detail of Activity - Stabilised material strength - ITS
label | b5038497-5945-4103-a2df-96c0ea075ead |  | note | Action (Hold, Monitor, Witness) - H
label | cc3215f1-3581-4e14-a0a1-d448d9bd6d06 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 Optimisation test per aggregate type
label | 82d77e2c-9365-4df0-80a1-ca6aa181d33f |  | note | Inspection / Test method - NZTA T/19: 2020
label | 4d8a579c-8d6d-4ba4-b129-73ef593dfea3 |  | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa Soaked ITS: 150 kPa to 350 kPa
label | 5088e276-03e6-435b-ba8f-c0aa121f48f1 |  | note | Record documents - IANZ Report
label | 28ff10b1-0d4a-4059-b7ff-fc14575528f4 |  | note | Responsibility - Client
label | d701f914-631f-4060-b3f7-e853867bd111 |  | note | Comments - Must be submitted to the pavement designer for approval at least 5 working days before modification works commence
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.1.1 - Check raw materials (whichever applicable)
label | e87e8040-135a-4280-b259-589e39247c13 |  | note | Detail of Activity - Lime
label | 1e35df58-f5d2-424b-a5bd-e6e87cdfcbf1 |  | note | Action (Hold, Monitor, Witness) - M
label | d6f8acf9-a542-4247-947b-cc3e8d7444ed |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Per Batch
label | b8f7d040-2ad1-46a6-a383-d156b37220e4 |  | note | Inspection / Test method - TNZ M/15
label | bf47bec9-199e-464f-85cb-ff8ac4576400 |  | note | Acceptance Criteria - Conform to Specification
label | 72645a13-45eb-4c60-87b6-890b232cffd7 |  | note | Record documents - Certificate in contractor's site folder
label | 8a165125-11b6-44d9-b8a2-d091b91bc137 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Check raw materials (whichever applicable)
label | 66dde547-3f0a-4c9a-8b77-2ff332a46391 |  | note | Detail of Activity - Cement, GP
label | 8972cf52-af5e-4ec4-ad3f-b43a9b9aeb54 |  | note | Action (Hold, Monitor, Witness) - M
label | e00db4a3-3abe-43b0-a184-1f2fb4f3b978 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Per Batch
label | be453b26-2b38-4dc1-acea-0e13ca59bd48 |  | note | Inspection / Test method - NZS 3122
label | b6b91a31-a14d-4b71-884b-5438a3a18228 |  | note | Acceptance Criteria - Conform to Specification
label | 195eb13c-8cf2-43e4-af24-25bd54889e04 |  | note | Record documents - Certificate in contractor's site folder
label | 703e8069-26c0-4845-96ac-94b8bbd02a6f |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Check raw materials (whichever applicable)
label | 3f4bbace-22bd-4f6b-b1ce-0ab52222c30f |  | note | Detail of Activity - Bitumen (80/100 or 180/200)
label | 857539c1-fa26-4449-b640-fcc3b3170c57 |  | note | Action (Hold, Monitor, Witness) - M
label | bceb4047-f4eb-4de7-889f-aeef4c72d9d3 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Per Batch
label | 291bc834-cdcc-4b9d-a9cb-a54afcef1a5a |  | note | Inspection / Test method - TNZ M/1
label | d8239c1f-1a89-480f-ba3f-b9ae6c90ce7a |  | note | Acceptance Criteria - Record binder grade. Conform to Specification
label | 14ab4d06-54b0-45b5-90f1-53e79303fcd5 |  | note | Record documents - Certificate in contractor's site folder
label | d1acb799-bff9-4258-998a-01b68575ad81 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Check raw materials (whichever applicable)
label | 973a6624-9d35-4afa-a9f9-ac8d7afae39e |  | note | Detail of Activity - Bitumen Emulsion (Base Bitumen 80/100 or 180/200)
label | 1e15d4c4-bc0d-4e2f-aa1e-2a84b110d7b2 |  | note | Action (Hold, Monitor, Witness) - M
label | 173ca9ef-7941-4e43-aebc-473df133c77e |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Per Batch
label | c722690a-d690-438b-8d53-91766369f0c9 |  | note | Inspection / Test method - TNZ M/1
label | 6782531a-04c8-4b9f-89b4-f915cdc6b64a |  | note | Acceptance Criteria - Record binder grade. Conform to Specification
label | bea48c44-2f8d-454d-8b73-fc23a8fc44f1 |  | note | Record documents - Certificate in contractor's site folder
label | 0cf7e5d1-187c-4786-aa58-d82c609d434b |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.1.2 - Check raw materials (whichever applicable)
label | 4f50ee8e-ed97-48dd-9a30-f7171b2d229c |  | note | Detail of Activity - Basecourse Aggregates
label | 5501ddb0-7909-4d69-8609-dc918305d74d |  | note | Action (Hold, Monitor, Witness) - M
label | 0423b569-94b4-472e-92cd-4619b90f6c93 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per 10,000 m2
label | 81716bc3-a1b1-469d-8e7f-99bd802b69db |  | note | Inspection / Test method - PSD Plasticity Index Sand Equivalent MDD / OMC CBR
label | 5d8daf69-dc31-4c9e-aaf9-8395949f5a03 |  | note | Acceptance Criteria - NZTA M04 / Project Spec
label | c7978c36-6856-43a5-83e7-9e00bef50850 |  | note | Record documents - IANZ Report
label | 50717779-758f-40e5-96d1-8e8e15796489 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.1 - Modified Basecourse
label | 7fa1f05d-c0e9-4b95-b6fb-4d7fa63644f7 |  | note | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | 6273d59d-cc53-4bce-b595-65b34709614e |  | note | Action (Hold, Monitor, Witness) - M
label | 09dbc73c-e5e9-46ae-87ba-cd9b5ebeee71 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Prior to works
label | fadee1db-8c9f-419b-a60e-2296b1b1ec5a |  | note | Inspection / Test method - Measurement
label | 3e9d4a6d-653f-4433-bb11-a7d889fbbaae |  | note | Acceptance Criteria - Document existing furniture
label | 9afaf1a4-557b-4d46-a74a-bee2a5f9b10a |  | note | Record documents - ITP
label | 89de26f1-197b-4848-b64d-0ecbc30f854a |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Modified Basecourse
label | ac46a68d-e733-4284-9c81-c77533346c1b |  | note | Detail of Activity - Ambient Temperature (C&L) Material to be stabilised (BE&FBS)
label | 95b596f6-fbdd-40f2-b51e-1a8e05884466 |  | note | Action (Hold, Monitor, Witness) - M
label | 9842b546-6590-4147-911e-8331f96923c7 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Prior to spreading
label | 548d543b-a776-49e8-beeb-457d54957cad |  | note | Inspection / Test method - Measurement
label | 0f5083d4-136f-4b47-a0d2-d2cd62964705 |  | note | Acceptance Criteria - Ambient Temperatures: Cement: > 5°C, Lime: > 10°C Material to be stabilised: BE: > 20°C, FB: > 20°C
label | acbd48ad-b036-4cbb-b3a9-758a909a9ab2 |  | note | Record documents - Daily work Log
label | e371e662-1d66-4f89-a003-7de7567504e5 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.2 - Modified Basecourse
label | c6eb2a12-3ff3-4db3-b77b-10f043d1dd7e |  | note | Detail of Activity - Spreading of powdered stabilising agent
label | c707daa9-f419-4770-8a4f-85439e6fdb63 |  | note | Action (Hold, Monitor, Witness) - M
label | 5c466255-3c29-40c7-bf71-dc56e77f1374 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - On-going measurement by computer/load cells
label | 64b302b4-4a47-4322-9616-14abf77f09e0 |  | note | Inspection / Test method - Measurement each run
label | 167ac439-99a5-448b-aee9-e1aa66827700 |  | note | Acceptance Criteria - ± 5% of specified rate
label | 2117ac54-8385-4875-a3ff-0dca3280b208 |  | note | Record documents - Worksheet
label | 2a06a8a2-af86-4312-a1d5-37c9c8d5bc50 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.3 - Modified Basecourse
label | e16753bd-6066-4ba5-9139-8394e9427b72 |  | note | Detail of Activity - Mixing process
label | ac544519-899f-44ec-962f-0ee75dd38e74 |  | note | Action (Hold, Monitor, Witness) - M
label | c60e76b9-eaa1-4bfb-a713-3b57eec7c9b7 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - On-going visual assessment
label | dee00fbf-7963-47a9-b7e1-71e0e003ccdf |  | note | Inspection / Test method - Visual Inspection
label | 3c607a5e-7885-41bb-8373-e263d0091914 |  | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps and construction joints as per spec
label | 12fbdf0b-1853-4980-a958-1ec7668a6244 |  | note | Record documents - ITP / Daily work Log
label | a698e618-b8c1-44b3-b4ca-60379e8cc7aa |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.4 - Modified Basecourse
label | 2e53be1f-14cc-4b8c-92e5-3537dbac76ea |  | note | Detail of Activity - Depth of stabilisation
label | e3f16a2a-13a6-4106-9565-140633205d2b |  | note | Action (Hold, Monitor, Witness) - M
label | e11c8b2a-6a59-4dfa-84f8-00cdf1bcfca5 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 9 per Lot
label | 280878c3-bc82-41de-8f69-4be47c18aa88 |  | note | Inspection / Test method - Measurement
label | be023e2f-a615-491b-9b8e-0dac6ba0bbef |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | 82033412-de1e-41a3-9cae-ec1ad509aaf5 |  | note | Record documents - Daily work Log
label | fc375e07-76b1-4ea6-ba2f-2719efd63802 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.5 - Modified Basecourse
label | f651703c-c850-47ed-9e1d-ae7c2517b87d |  | note | Detail of Activity - Modified Maximum Dry Density
label | a75df949-ad88-4777-bf61-da55a95107cd |  | note | Action (Hold, Monitor, Witness) - M
label | 275fd662-c741-41a9-b0fd-7880ad794e24 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | 22ef7715-4bbd-4b94-a72c-b90f33f74a64 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 032b5ce9-15a5-45d7-bb09-e524cf895364 |  | note | Acceptance Criteria - For analysis of DoC
label | 45ff5a13-737a-4967-afe8-dedef306d65c |  | note | Record documents - IANZ Report
label | 57469e66-e34b-44f6-8690-faf57accd32c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | Modified Basecourse
label | be8ac8b1-d5e1-411c-b40a-9f206a8a0755 |  | note | Detail of Activity - Plateau Density Test
label | 0948d1fe-3d84-4698-9f83-c166fed156a4 |  | note | Action (Hold, Monitor, Witness) - W
label | 77258a7b-7e37-4ffc-9307-fe0971acd553 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | d2d0c605-4d83-465b-a091-6e891b18d125 |  | note | Inspection / Test method - Draft Guide
label | 1331480c-ad50-43fb-85a4-4ca2f8a06f30 |  | note | Acceptance Criteria - To establish roller pattern
label | 0c0a9713-8de5-44ab-b139-19b9f54dc6ba |  | note | Record documents - test report
label | 31dee857-f988-4096-8f0e-c4fa2441636c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.2.6 - Modified Basecourse
label | 4294f7f8-77a9-459d-940e-72935d1f6fdd |  | note | Detail of Activity - Degree of Compaction (Nuke)
label | c9ea1f6b-3fdf-401e-ba6c-a819e6774c86 |  | note | Action (Hold, Monitor, Witness) - H
label | b2372eb3-28e8-495a-8d1a-20357f7d5e2a |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 9 per Lot
label | 61d6fa42-32be-436e-bc5a-0dcd6822018a |  | note | Inspection / Test method - NZS 4407.4.2.1 (to 200mm) and NZS 4407.4.2.2
label | df914e33-79a7-4bee-8faa-3303953d6bcb |  | note | Acceptance Criteria - NZTA B02: Average DoC ≥98% Min.DoC ≥95%
label | c3bbd2d7-cf2e-4770-b127-6f430a4b705f |  | note | Record documents - IANZ Report
label | f63c2576-79b8-416c-a8bb-776c0ac05d0d |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.7 - Modified Basecourse
label | 1aa24642-6524-436f-bcb6-ca0bc4f93607 |  | note | Detail of Activity - Layer Width
label | a3af467d-2901-4c89-9258-0d06304a24b9 |  | note | Action (Hold, Monitor, Witness) - H
label | 9a3146a6-2d1d-40b2-a7c7-447f5d52e43f |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 7b0df704-1745-49fe-9ce4-3129289f35aa |  | note | Inspection / Test method - Measurement
label | a4e512fd-8000-4718-bd4f-b7554e89451e |  | note | Acceptance Criteria - ± 10 mm
label | d99f5397-1237-481b-a3d4-38ba119b5998 |  | note | Record documents - Survey
label | b75b4e00-0a49-40d8-b510-b61ecfb3ac97 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.8 - Modified Basecourse
label | c2a11705-055a-43cf-b321-f9f15a6043d3 |  | note | Detail of Activity - Surface Shape
label | acdf1ac4-94a8-4b74-9864-7fd89778ec3e |  | note | Action (Hold, Monitor, Witness) - H
label | 4f4e188b-4291-442c-b60d-25e5ef798540 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 0a247f6e-4cac-4470-8bde-ff94fba368e8 |  | note | Inspection / Test method - Measurement
label | 0f200e46-41c8-4a5b-baef-2b1167e6277c |  | note | Acceptance Criteria - < 6mm using 3m straight edge
label | 612bdd93-a341-46c9-a3bc-71830cda5f89 |  | note | Record documents - Worksheet
label | c1199a0d-f075-4359-8155-e22bf2e3703b |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.9 - Modified Basecourse
label | 6130651c-6da9-45d0-85e5-404c28c34eb8 |  | note | Detail of Activity - Surface Levels
label | f72d9230-d35e-4f40-9ff9-14d635a304e0 |  | note | Action (Hold, Monitor, Witness) - H
label | 44bac52f-72fb-4151-894b-800461617d52 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | f87a2fc9-2503-405c-b9a4-dc0266c442e5 |  | note | Inspection / Test method - Measurement
label | 9b6475f6-b20b-4939-b687-605a2a5bd3cc |  | note | Acceptance Criteria - +5mm, - 10mm
label | b543bd7d-d8dd-4a31-9b81-5ffcdc133f16 |  | note | Record documents - Survey
label | 5659be36-271a-4c39-8d18-957e4b4b4a7f |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2.10 - Modified Basecourse
label | 51415f84-0f60-40c4-9d50-916d0a22620b |  | note | Detail of Activity - Stabilised material strength - ITS
label | 2cdd5d56-f13f-463c-9d7c-80d377d89998 |  | note | Action (Hold, Monitor, Witness) - S
label | 69019496-7b26-478b-9471-3fa170389511 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 3 soaked ITS + 3 dry ITS per Lot
label | fc951a96-069f-4b9c-8b78-045ee194b155 |  | note | Inspection / Test method - NZTA T/19: 2020
label | 2d7079c4-dfd0-4e92-a21c-d293005e85cd |  | note | Acceptance Criteria - Dry ITS: 175kPa to 400 kPa Soaked ITS: 150 kPa to 350 kPa
label | 9ec61153-2a53-43fa-91a0-666fc717a5ab |  | note | Record documents - IANZ Report
label | 6a9c60a4-f8a3-4cf7-acc8-1e659057cdaf |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 4.3 - Non-conforming results
label | e2d42771-80f9-48b3-92d0-26ec2e916c7c |  | note | Detail of Activity - Assessment of all test results for conformity
label | 7a800b09-c394-45c6-94b7-d1c9a3063544 |  | note | Action (Hold, Monitor, Witness) - H
label | 56cba1b0-588a-417c-a348-816365d46485 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Each Lot
label | 99eaeb40-9be3-46c1-ab37-550769ff0b84 |  | note | Inspection / Test method - Site Inspection
label | df4ed846-5229-42ee-b9ce-5c6a73c94fe3 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 606717f4-e5c1-4932-8ec7-24c89fb933bf |  | note | Record documents - NCR
label | f8472a21-182f-475c-a61f-74ce14f9b5e5 |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 9b8ddba2-438b-4869-a970-55faeed80f8b |  | textbox | Contractor's Rep Name:
text | e134b9bb-2f73-41f5-9ebb-7d0c9797987e |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - AC Placement |  |  |  |  | Yes | ITP - AC Placement | a830db4b-4531-4f9d-a48b-800937d60c59
checkpoint-group |  |  | section | Asphalt Constituents - Pre-Paving Inspection
checkpoint-status |  |  | checkpoint | 7.2.1 - Pre-paving inspection
label | 3beb74ce-31a1-4740-820c-95080c6842a9 |  | note | Detail of Activity - Visual inspection of surface to be sealed
label | 0dfdf573-693b-4617-802f-04fb92c62bd4 |  | note | Action (Hold, Monitor, Witness) - W
label | 6f3feafa-cfc2-4cba-9070-03fc5b38857b |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - per paving schedule. 1 Lot = 1 day's production and < 1500m2
label | 807d3247-cf14-42c6-a0c3-666ed50c4e38 |  | note | Inspection / Test method - Visual Inspection
label | d16245ea-c12b-4cf5-8b57-3bf478da06c8 |  | note | Acceptance Criteria - If surface is sealed or asphalt then surface must be clean and free of any dust. If surface is unsealed then the surface must be tight (checked by Clegg Hammer) and have a stone mosaic finish for the tack coat and asphalt to stick to.
label | 9ebd33b4-b926-462f-8934-ee8dc70f5c9c |  | note | Record documents - Contractor's site diary
label | cdacb67c-730d-4b66-8267-284777dd1fe9 |  | note | Responsibility - Engineer's Rep.
label | 86b24558-3b08-4c3f-b1e5-0e21deaa3b71 |  | note | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing / paving
checkpoint-status |  |  | checkpoint | 7.2.2 - Pre-paving inspection
label | 97bcb636-7f47-4be5-9242-c8202a6aac51 |  | note | Detail of Activity - Dry back Moisture Content
label | 727de184-a23f-4498-8105-dcba19fcebe5 |  | note | Action (Hold, Monitor, Witness) - H
label | 47762386-1e00-46ad-a4e9-ea653568db76 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 9 per Lot
label | ef2efe8c-8de8-400c-8e60-258d2d87ff72 |  | note | Inspection / Test method - NZS 4407.4.2.1
label | 8ffcea82-532e-4b55-b581-43e81bd741ce |  | note | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | a301470a-70a6-4454-a5b8-79710e073a7f |  | note | Record documents - Test Results
label | b24615a3-0244-40f2-9210-03da1323f7c8 |  | note | Responsibility - Contractor
label | 4c7d18d6-84ec-4dd7-912d-1ba089eee266 |  | note | Comments - Only required if substate is a granular or stabilised layer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7.2.3 - Pre-paving inspection
label | 287b33a1-f5f2-43c1-b633-d5d3cbfa8e81 |  | note | Detail of Activity - Clegg Hammer
label | c295f880-3239-4f07-83c3-75ed11ba3988 |  | note | Action (Hold, Monitor, Witness) - M
label | 8ea9866e-37e1-49c8-b568-25072afca0de |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 CIV per 10m 1 Lot < 300m
label | 91710dd3-6b0f-43b1-beb9-69a6ec5c785d |  | note | Inspection / Test method - Clegg Impact Value Test
label | 9ee84f60-68f7-4c43-a138-e34c97600176 |  | note | Acceptance Criteria - Average CIV > 50 Min. CIV > 40
label | 8d04310e-cee1-4ac5-a185-f9d2fff01c95 |  | note | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | d4aad5cd-2271-48d1-940e-3ab1fa906c19 |  | note | Responsibility - Contractor
label | 8ac19056-b905-4002-84eb-e098c364c6b3 |  | note | Comments - Only required if substate is a granular or stabilised layer
checkpoint-group |  |  | section | Production
checkpoint-status |  |  | checkpoint | 7.3.1 - Production mix
label | c736550a-96a0-46a5-b418-d4eb9cb61108 |  | note | Detail of Activity - Particle Size Distribution
label | 4d1dafa7-66c6-4df5-af4b-7006317085df |  | note | Action (Hold, Monitor, Witness) - M
label | ef7691ae-151f-474c-b986-77c52f3b233d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per 200 t at asphalt plant
label | 041246a8-8285-4e42-9072-33be52dcb8f2 |  | note | Inspection / Test method - NZS 4407 Test 3.8.1
label | f488dba1-5477-4ef4-b8ae-afe5487d538a |  | note | Acceptance Criteria - Table 3.1 NZTA M/10
label | 719e6894-0713-4b97-b626-b6ce8ee63de1 |  | note | Record documents - IANZ accredited test cert
label | dd638376-872b-4391-b6af-f21f28142b64 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.3.2 - Production mix
label | 48f69206-7796-4b7a-97cd-b25443703c85 |  | note | Detail of Activity - Binder Content
label | cda7029b-b8cf-4e52-af07-c9fd921f1dd4 |  | note | Action (Hold, Monitor, Witness) - M
label | 0ed244ad-2fcd-4c6b-97fe-1bc8c5117104 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per 200 t at asphalt plant
label | a3bbbdc0-05f3-4289-9efa-d5b4290b7555 |  | note | Acceptance Criteria - Table 3.1 NZTA M/10
label | 70bbbb8d-a105-4845-87e7-8418fcaea768 |  | note | Record documents - IANZ accredited test cert
label | c0aba2f8-defb-44dc-a180-0eb343edb94c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 7.3.3 - Production mix
label | 5b878d29-d675-40b6-9e9d-e44846ae6c2a |  | note | Detail of Activity - Max. Specific Gravity
label | 43d653a3-6cd3-4d59-aa03-4ba8710e86b5 |  | note | Action (Hold, Monitor, Witness) - M
label | 2d80f860-e9e2-4a78-af33-7754fb3aded9 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per 200 t at asphalt plant
checkpoint-status |  |  | checkpoint | 7.3.4 - Production mix
label | 6f39ef8c-7206-40d9-94fa-982c7e9fb467 |  | note | Detail of Activity - Mix discharge temperature
label | bf8d9deb-04a5-429a-a9ec-318e02291312 |  | note | Action (Hold, Monitor, Witness) - M
label | 930ae1df-0aa5-4c63-beb0-df5f82989eda |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per 200 t at asphalt plant
checkpoint-status |  |  | checkpoint | 7.4
label | 23414b20-ce63-4bb0-af2d-8362f5c7a867 |  | note | Detail of Activity - Refer to Table 5.2 of NZTA M/10
label | cd740b30-c0e0-4747-b452-68108d9bc647 |  | note | Action (Hold, Monitor, Witness) - M
label | f75cf3f5-2ecf-4a23-a1db-553b3291f519 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - As per Table 5.2 of NZTA M/10
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 94382dc1-9edb-48b2-a9da-1c8ef425f8bb |  | textbox | Contractor's Rep Name:
text | 673c129a-be79-437b-ba74-6aebdb9827bc |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - GAP 65 Lower SB |  |  |  |  | Yes | ITP - GAP 65 Lower SB | b78fc083-e793-4974-95ac-52d1b21f7199
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 3 - Mark out and approve
label | 622d0174-f9de-44cf-8567-cbb1790098e9 |  | note | Detail of Activity - Set out and mark up of treatment area
label | b8acfd96-be66-4e01-ab66-276b25024731 |  | note | Action (Hold, Monitor, Witness) - W
label | 2a22a3ea-7a8a-452a-94fe-7214f23d249a |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All areas of unbound granular pavement layers
label | 45ad66cd-fcc2-4d75-bdf2-426b6158c2dc |  | note | Inspection / Test method - Visual Inspection
label | ea9dd026-21d2-4a42-949b-f517076b1943 |  | note | Acceptance Criteria - N/A
label | e564e97b-aa66-4adb-aa21-a96e95ffc7c5 |  | note | Record documents - Contractor's site diary
label | 20f53f05-739e-4805-a6fb-6ae873617562 |  | note | Responsibility - Contractor
label | eb56a130-bfe7-4063-95b8-1a1807c8cdd0 |  | note | Comments - Treatment area marked up jointly by Contractor and Eng.Rep.
checkpoint-status |  |  | checkpoint | 3.1.1 - Unbound Granular Subbase
label | a0a886ee-7f04-4357-8015-a4fea1600927 |  | note | Detail of Activity - GAP65 material
label | ae8d40d8-44b7-43c0-aff5-4efeefe54aab |  | note | Action (Hold, Monitor, Witness) - M
label | bb8fe06e-0fd7-4c3c-af5d-986ad13b6050 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | e186767c-0c58-405b-a865-b633f4c4a290 |  | note | Inspection / Test method - PSD Plasticity Index Sand Equivalent MDD / OMC CBR
label | 13db809b-05de-418c-bbb5-3918f436593c |  | note | Acceptance Criteria - Refer to Project Specifications on Drawing number 17002-TS-1200 & 1201
label | fbccb811-2e4a-42a8-b7f3-7bf0d5efd474 |  | note | Record documents - IANZ Report
label | 887de4db-6094-4473-a6ff-7366d570f1f4 |  | note | Responsibility - Contractor
label | 3cff5d4d-544c-4306-b5b3-f6d80e2a2ced |  | note | Comments - Test certificate(s) to include PSD, PI, SE, MDD, OMC on material sampled from the loaded stockpile and not more than 3 months old
checkpoint-status |  |  | checkpoint | 3.1.2 - Unbound Granular Subbase
label | 487ce3d8-3fff-45e2-83ac-14de35f43fdc |  | note | Detail of Activity - Modified Maximum Dry Density
label | 0f8032b5-1321-4e1b-a587-56e7c04d5c71 |  | note | Action (Hold, Monitor, Witness) - M
label | 417f2074-1f69-4a9e-86c2-b545f71c451a |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | 16f51690-4531-4410-9011-20b0293cca0c |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 399d966b-47ef-4a16-878c-6a146c0745d8 |  | note | Acceptance Criteria - For analysis of DoC
label | dfedf6ac-620c-427f-9f36-07ade8938add |  | note | Record documents - IANZ Report
label | 7d03f075-b887-42e5-bf39-8688c4a8170e |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.1 - Unbound Granular Subbase Construction
label | bfc7aa13-c46d-4ce8-9d85-55ed565ee753 |  | note | Detail of Activity - Plateau Density Test
label | 80a49219-f0cf-4fa1-aaea-555ce08ea2b9 |  | note | Action (Hold, Monitor, Witness) - W
label | 0b79cedb-466a-4387-81b9-46b46daf24d5 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | 1eb3a736-e7b6-4095-b178-592c12c0d88c |  | note | Inspection / Test method - Draft Guide
label | 58fc9230-0e65-469c-b733-f6a87db4b68e |  | note | Acceptance Criteria - To establish roller pattern
label | 077b2cba-f7b7-42d5-8b91-054cbf2eb39d |  | note | Record documents - test report
label | a408b6f6-60d7-401c-914e-4fe370d963d6 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.2 - Unbound Granular Subbase Construction
label | 1ad8e447-2900-41cc-80f4-af4700d94f57 |  | note | Detail of Activity - Degree of Compaction (Nuke)
label | e1e2c030-9ec8-4b15-a5e7-f00eaeea4650 |  | note | Action (Hold, Monitor, Witness) - H
label | 5cc8636c-3d1d-43a1-9786-7032efa973a2 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 9 per Lot
label | dcb6f2b0-3087-44c1-ab10-7da6ced9095a |  | note | Inspection / Test method - NZS 4407.4.2.1
label | 370981f5-681e-46fb-91f1-2fbb71750ea2 |  | note | Acceptance Criteria - NZTA B02: DoC ≥98%
label | fe677bb0-7d7a-47e4-86bf-cfd2ce75b931 |  | note | Record documents - IANZ Report
label | ade4d887-cbbe-4276-842c-faf30b1b9820 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.2.3 - Unbound Granular Subbase Construction
label | 1ed5e6a5-1751-4556-8ed3-104e65ff5858 |  | note | Detail of Activity - Layer Depth
label | 3e505ea1-521b-4b83-9456-71b4e9962d49 |  | note | Action (Hold, Monitor, Witness) - W
label | 444e7865-04d4-4cdb-88f2-106c65bd8c89 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Dips every 20m of surface before placing and after compaction of modified layer
label | 16ca1efb-6479-4561-9512-69a67d249eb6 |  | note | Inspection / Test method - Measurement
label | e7d13d9a-45a5-47b5-b96a-983baa4a4067 |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | ad648976-0cca-4117-8d96-4ee4f24e9d47 |  | note | Record documents - Daily work Log
label | 7ef0922b-d9ce-4e53-841a-e4b307be6c78 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.4 - Unbound Granular Subbase Construction
label | a900f8c7-cb17-4e0e-924f-28a65e0c0d0a |  | note | Detail of Activity - Layer Width
label | 9ba1fa64-8d65-4ed7-9cca-ac0f0035d8f1 |  | note | Action (Hold, Monitor, Witness) - W
label | 50d7bd91-a996-4626-bcc7-b990a9ecf7fa |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 212703c5-9930-4a47-97ab-d936bf75b877 |  | note | Inspection / Test method - Measurement
label | 93e9b66c-b72a-43b7-8835-a55b611f4cea |  | note | Acceptance Criteria - ± 10 mm
label | 2613a421-e442-4834-a4e9-b830250f8b95 |  | note | Record documents - Survey
label | f34e3409-b02c-4d4c-9804-4c5151511310 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.5 - Unbound Granular Subbase Construction
label | 4994221e-44e4-4dd9-81d6-77a234a9f4d3 |  | note | Detail of Activity - Surface Shape
label | 30a87d6a-1c7d-479b-b570-64ff4d77957e |  | note | Action (Hold, Monitor, Witness) - W
label | 92cba55e-7dab-45eb-9312-5aee9f42ab17 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 471f3bc6-3489-4c75-af13-d29a8931b270 |  | note | Inspection / Test method - Measurement
label | 3110c42b-b18a-48b7-b2cb-e46d5cd35a1f |  | note | Acceptance Criteria - < 6mm using 3m straight edge
label | ba07b407-402e-4f0c-9acc-8b476cde1e58 |  | note | Record documents - Worksheet
label | 7fbde5df-b8f8-4c26-92b5-e1d550a59683 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.6 - Unbound Granular Subbase Construction
label | ae0522f5-044c-4ac4-a945-90c5ca794832 |  | note | Detail of Activity - Surface Levels
label | 76318dc7-06e8-41a9-acec-00c8b852e6f0 |  | note | Action (Hold, Monitor, Witness) - W
label | aa5e8162-3e26-45a9-bd89-9ff4c08d7b5d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 72d9b329-4dac-437b-852a-c6a559aba5b4 |  | note | Inspection / Test method - Measurement
label | 57583e13-6c37-45e3-b05b-5a831f609255 |  | note | Acceptance Criteria - -5mm, + 10mm
label | 271d382d-3512-4647-890b-ebd96f66ed87 |  | note | Record documents - Survey
label | 1ba66e61-9c52-420d-a1da-515ef4b7e085 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.3 - Non-conforming results
label | 6f8f7d6c-af5f-4c5c-a2f1-801bff017081 |  | note | Detail of Activity - Assessment of all test results for conformity
label | ed2921f6-5876-4ff7-be9e-23698d5dd4ac |  | note | Action (Hold, Monitor, Witness) - H
label | 9456878c-600b-4453-a911-d6eb9c4d4eff |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Each Lot
label | 0d086766-6402-4398-8d87-501f2567c88b |  | note | Inspection / Test method - Site Inspection
label | 578c6cda-eac8-43c0-bcd2-b277b99e79cf |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 5157172e-2ccc-449f-b30e-0c96c0217f79 |  | note | Record documents - NCR
label | b14e5f50-dbb7-4b00-9ee2-6b4e194a5a46 |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 01f237f9-b545-496e-a075-d5210d644a65 |  | textbox | Contractor's Rep Name:
text | f565786c-53d3-4def-b8d1-fc8c9c5cda01 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - GAP 40 Upper SB |  |  |  |  | Yes | ITP - GAP 40 Upper SB | c08638d9-b79c-4a1f-a27c-1290c649f595
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 3 - Mark out and approve
label | a97fe4d2-e06f-4b01-b82d-cdfd95739b7c |  | note | Detail of Activity - Set out and mark up of treatment area
label | af94c179-156e-4264-b85c-446f697d4145 |  | note | Action (Hold, Monitor, Witness) - W
label | a45a68bc-133f-4746-8d2b-e72a44ddda04 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All areas of unbound granular pavement layers
label | e20db5f4-239b-4106-9170-b17a74df3a12 |  | note | Inspection / Test method - Visual Inspection
label | 5f516bbb-e5e3-44b7-8824-43968481a992 |  | note | Acceptance Criteria - N/A
label | 0e7264fa-a9e8-41a1-b941-ccfdd592de24 |  | note | Record documents - Contractor's site diary
label | 7d8c7976-f8a2-43fa-99f8-e503f7eb51db |  | note | Responsibility - Contractor
label | 2ea4a763-54d9-4bea-aa8a-aa9c1c28c120 |  | note | Comments - Treatment area marked up jointly by Contractor and Eng.Rep.
checkpoint-status |  |  | checkpoint | 3.1.1 - Unbound Granular Subbase
label | acb1e94c-8c48-4b5a-b76e-a4516b1bbbd6 |  | note | Detail of Activity - GAP65 material
label | 31bb7979-2021-4b9f-acea-7865fd734251 |  | note | Action (Hold, Monitor, Witness) - M
label | bda333d3-8df7-4f82-9019-11143453c0ab |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 462cfa4a-1e21-479e-9352-d5a7d2b8fa81 |  | note | Inspection / Test method - PSD Plasticity Index Sand Equivalent MDD / OMC CBR
label | 08515c18-842f-45f1-8b18-21d066661bb2 |  | note | Acceptance Criteria - Refer to Project Specifications on Drawing number 17002-TS-1200 & 1201
label | 89b506f0-d2b2-4ace-b0c8-1ed004986cd6 |  | note | Record documents - IANZ Report
label | 9020959c-11f3-404b-8d80-d65b13d93df4 |  | note | Responsibility - Contractor
label | eef17ba2-7f60-4f3f-974e-2f4eabdfa70d |  | note | Comments - Test certificate(s) to include PSD, PI, SE, MDD, OMC on material sampled from the loaded stockpile and not more than 3 months old
checkpoint-status |  |  | checkpoint | 3.1.2 - Unbound Granular Subbase
label | dfadd627-4913-428d-9e05-a42cf53e531e |  | note | Detail of Activity - Modified Maximum Dry Density
label | e2d0acac-173a-46ef-9f7c-6ead49106a73 |  | note | Action (Hold, Monitor, Witness) - M
label | 60863523-c9d9-4f98-9abc-529afdb7aba7 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | 257a78b8-44e5-41ef-939b-31dbec224949 |  | note | Inspection / Test method - NZS 4402.4.1.3
label | 02ad988c-7bdd-412f-bb20-150e3d6293b9 |  | note | Acceptance Criteria - For analysis of DoC
label | 5e0a5df3-1f92-4c41-8457-b1366cda21c6 |  | note | Record documents - IANZ Report
label | 88a8a99d-139f-4363-ab98-7a41791cc4e3 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.1 - Unbound Granular Subbase Construction
label | f8f91c50-e192-448b-9bc2-7485baa63e65 |  | note | Detail of Activity - Plateau Density Test
label | 4801051b-caaa-4ec5-929a-9b94568caccb |  | note | Action (Hold, Monitor, Witness) - W
label | f5b1b921-39d8-436d-9712-d7d70ef1b813 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per Lot
label | 7de7ae5a-1ba6-4aad-b269-2eec11b31c9c |  | note | Inspection / Test method - Draft Guide
label | abe5335f-cf91-459d-a490-07228d12757a |  | note | Acceptance Criteria - To establish roller pattern
label | 76a77451-ad4b-4aed-a23e-8aceda52cfee |  | note | Record documents - test report
label | 21403ffd-3ec5-49f4-8747-fbded0099a63 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.2 - Unbound Granular Subbase Construction
label | a60021f7-104e-4d19-a5db-8fc7602dff3d |  | note | Detail of Activity - Degree of Compaction (Nuke)
label | 7719a9e1-d100-49a9-abb2-a6e846a2898b |  | note | Action (Hold, Monitor, Witness) - H
label | 4bd92137-a689-4be7-8972-ff833bc4cc37 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 9 per Lot
label | 2de9186a-b701-499f-883f-5a39353b2eb7 |  | note | Inspection / Test method - NZS 4407.4.2.1
label | 8f1bc331-cdb6-4fce-ada1-219640d7725e |  | note | Acceptance Criteria - NZTA B02: DoC ≥98%
label | 73d20ede-c428-4784-bd2c-ad1e1766c01a |  | note | Record documents - IANZ Report
label | 7fc82f74-1bbb-4702-a1fc-ef6d392b6d1f |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.2.3 - Unbound Granular Subbase Construction
label | f0881bd9-4d7f-4351-a80d-7950c3124cee |  | note | Detail of Activity - Layer Depth
label | b212c282-c59d-4723-a509-ccf0e5904ec1 |  | note | Action (Hold, Monitor, Witness) - W
label | fabda92c-1b9c-47bc-a5f5-9a7e141636d3 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Dips every 20m of surface before placing and after compaction of modified layer
label | bb55ed58-2808-4009-b13e-c03a82868a80 |  | note | Inspection / Test method - Measurement
label | 906ddbd3-b918-4ac5-a7da-129d9f076965 |  | note | Acceptance Criteria - +15mm / -5mm from specified depth
label | 5f6226af-0d65-4a35-a1bc-62fc74aac121 |  | note | Record documents - Daily work Log
label | cbed96db-8b12-4de9-91cb-c37f638128c3 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.4 - Unbound Granular Subbase Construction
label | a25bf586-d2a1-49a8-b4b4-43ef59fd18cb |  | note | Detail of Activity - Layer Width
label | 00af2e9c-4673-420d-892c-17ed6763606a |  | note | Action (Hold, Monitor, Witness) - W
label | 0c297ebc-fd97-488a-989b-d8aec9c5a1b6 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 2ce67fa9-a73c-4259-ab0b-25b36201d05e |  | note | Inspection / Test method - Measurement
label | 87dcd0ff-0ecb-4f7a-ab3f-d5b78be542c8 |  | note | Acceptance Criteria - ± 10 mm
label | 25622ec1-963e-4e72-932f-cc0be822ba38 |  | note | Record documents - Survey
label | b61aec8c-d10e-4577-a18e-48ae6c899f09 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.5 - Unbound Granular Subbase Construction
label | 8022bc88-8800-4294-85a8-bc741913a3f0 |  | note | Detail of Activity - Surface Shape
label | aacb4bf0-3545-4999-8211-369353d75524 |  | note | Action (Hold, Monitor, Witness) - W
label | e5d9259c-961d-4ddf-86ba-cd25edc0a8cd |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | ef70c270-5d7f-4d18-9874-df4f2dfa5b4b |  | note | Inspection / Test method - Measurement
label | 7cc86209-ae92-4bf5-8c1d-b0fc76c4ebf3 |  | note | Acceptance Criteria - < 6mm using 3m straight edge
label | e7b6f9d0-ebbd-4d33-9cc7-fd291cc266c8 |  | note | Record documents - Worksheet
label | e2c56301-668f-45dd-a4e0-b7f39aeb671d |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.2.6 - Unbound Granular Subbase Construction
label | 998b6550-fd41-4050-abeb-799705217492 |  | note | Detail of Activity - Surface Levels
label | 6da2baee-96a3-4421-a3e5-9abf1b461b84 |  | note | Action (Hold, Monitor, Witness) - W
label | c1740c19-9674-457d-93ab-ec681a4ead9b |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - every 20m
label | 8a5dfb04-a49b-441d-ade7-4596328723a4 |  | note | Inspection / Test method - Measurement
label | 936135d5-de96-4f76-b40f-d63a9238060c |  | note | Acceptance Criteria - -5mm, + 10mm
label | 65d17066-c6c9-4911-90c2-47089ee82180 |  | note | Record documents - Survey
label | 684e8324-89d9-498f-9007-a0b3c4e167db |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 3.3 - Non-conforming results
label | 5dd80854-3487-47f8-ac19-5c69b8f32251 |  | note | Detail of Activity - Assessment of all test results for conformity
label | a1319079-7afe-451e-83a6-a1ef1699b4a2 |  | note | Action (Hold, Monitor, Witness) - H
label | 3a2d5577-4d9e-4621-a810-28075be325a1 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Each Lot
label | b1e812af-c455-45e1-ac82-34ee643f4d81 |  | note | Inspection / Test method - Site Inspection
label | b7114d25-13d5-4631-884b-70f21c3f47f3 |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 4ffeb316-a0e0-46e3-9c8c-ec0f7397bddd |  | note | Record documents - NCR
label | fac692f2-25e0-4809-a6f4-9a2a110f66f8 |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 044553b0-9294-4830-9856-5d78f643a45a |  | textbox | Contractor's Rep Name:
text | 483433fc-74e8-40ef-916f-652f2e93b69c |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | Rehab Quality |  |  |  |  | Yes | Rehab Quality SH 29 | c553b7f5-651e-4e68-a8af-8cfd02336d38
checkpoint-group |  |  | section | Before starting work
checkpoint-status |  |  | checkpoint | Daily Work Briefing, confirm scope, location, that you have all staff, materials and plant needed
label | bc3d6753-326d-4874-ad6b-333875e8c222 |  | note | Specification-HSMP
label | 73c1916c-d8e5-4bf9-b2d2-480e54a9cdd1 |  | note | Method/Test-Brief all team members on day’s work plan
label | d9f2b162-b243-4bf9-be9f-e65f1df09511 |  | note | Frequency-Each morning
label | 183cd195-de3b-4357-9616-78e6d3c6d9d7 |  | note | Records required-Daily diary
label | bfe9e8b2-52eb-4d45-b847-ce2fc937c82c |  | note | Responsibility-Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 1.0 AP 40 M4 – Raw Aggregate Testing
checkpoint-status |  |  | checkpoint | 1.1 Sand equivalent, or
label | 4567d6f7-d29d-4604-b5ae-bb82e8657abe |  | note | Specification-Design
label | 383be2bd-5519-4592-bbb0-1b0208874420 |  | note | Method/Test-≥35 Unit of measure?
label | 40cd863e-cbe3-4345-821d-859829acf11a |  | note | Frequency-1 sample per 500m3
label | e4bfb1cd-8390-4885-a3af-36cd5b69a0f8 |  | note | Records required-Test Report
label | 3a22ec88-4ff5-40d8-a8b9-dc51c737c2b1 |  | note | Responsibility-Supplier
label | a54d4477-ad80-434d-9c41-955ff2bb71a6 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.2 Clay Index (passing 0.075 mm), or
label | 9c94c666-d2d4-451b-9901-d9b6dfe38ed8 |  | note | Specification-Design
label | ca0c8c31-2148-4a8f-b0eb-fbe9e5103abf |  | note | Method/Test-<=3 Unit of measure?
label | e6935f8e-aa20-4544-ac6f-99e48860ce31 |  | note | Frequency-
label | f808e4b4-e33c-4111-bedf-24e4f8d0844b |  | note | Records required-Test Report
label | d5536194-72dc-43e5-8d51-e20ca9e7aad0 |  | note | Responsibility-Supplier
label | a4ec9697-5d63-484a-a92b-6ab09cad4024 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.3 Plasticity Index
label | 393c7b5d-e14e-48cc-a65d-9e1253f1f9e0 |  | note | Specification-Design
label | d2fcac09-2048-44f4-ba42-89d4b7cc8253 |  | note | Method/Test-
label | 7ddba156-688c-4fb2-b422-40e6df35f565 |  | note | Frequency-
label | 88a63888-97c6-4aa8-b56b-9901aac255b1 |  | note | Records required-Test Report
label | c25ce7ca-0588-4fcc-ac0f-df196c220768 |  | note | Responsibility-Supplier
label | a5554a2c-2dfe-4635-9ad1-51b709281c00 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.4 Particle size distribution
label | 29910696-afea-4083-a497-cfe425dc90f3 |  | note | Specification-Design
label | 571b8889-5833-4e09-bfd8-fdd0a2eae4dc |  | note | Method/Test-100% passing 63mm
label | 68b9c584-a492-494d-aebe-3dab9fdc241b |  | note | 40% ≥ 65%passing 19mm
label | 77ccb710-856d-47b2-8aaf-5a4ddc5cf83a |  | note | ≤ 10% passing 0.425mm425µm
label | b6013817-2469-4b51-9677-006a4db2b1f5 |  | note | Frequency-1 sample per 250m3
label | 9319c8f8-8f98-40e1-aa18-4f2bc45a9c34 |  | note | Records required-Test Report
label | 210a2a87-3cfc-4351-80f0-edd04bd33d82 |  | note | Responsibility-Supplier
label | 13f7e806-53b9-494d-ad5d-5f15a1359049 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.5 Solid Density
label | 4df4e390-5aa8-4c16-b6e9-b05325a6a998 |  | note | Specification-NZTA B/2 7.5
label | 42b47c7c-0623-46a3-b5c8-fbd83d43ae41 |  | note | Method/Test-Unit of measure?
label | 168a8331-570e-4ed8-a9b6-670fdca80d14 |  | note | Tolerance?
label | 3546fd85-0f6d-4de1-bf7a-776f558a73dc |  | note | Frequency-1 test
label | b7559f96-71da-4b7a-8c9f-4cfb20221dc1 |  | note | Records required-Test Report
label | fcd4960d-ba1a-4784-8c88-f73220e08e78 |  | note | Responsibility-Supplier
label | 1a7a20a0-b79a-4edd-becc-2e8161cf9d14 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.6 Determination of MDD & OWC
label | 65e3384c-6b1a-4f34-9338-10ae3571a0d7 |  | note | Specification-NZTA B/2 7.5
label | 56abad85-c556-490f-8f7c-b68630dfe4b9 |  | note | Method/Test-Unit of measure?
label | 82762a27-b71e-46f6-88a0-2227939286ac |  | note | Tolerance?
label | 662cf47c-384d-4dc4-a691-4e56810e061a |  | note | Frequency-1 test
label | 73db77d6-88ef-433f-9590-6f31397da7d5 |  | note | Records required-Test Report
label | be39af05-c360-4f1d-856f-1adea02b40ef |  | note | Responsibility-Supplier
label | 7e163ccf-9847-4ff0-be3d-baa8f14faeba |  | note | Test
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | 2.1 Job start, identify risks and mitigations, communicate to team
label | c4c7a8a5-c4f6-4bcc-b92f-a415d4dfb7d8 |  | note | Specification-HSMP
label | 1358639d-f83d-4d00-98fc-85edc4e3c8b3 |  | note | Method/Test-Record all hazards on JSEA and brief team
label | a907e433-a7d2-4135-9b5d-b639df784168 |  | note | Frequency-Each morning
label | 1804e191-bb7c-46c6-8403-51f7791ca0be |  | note | Records required-Job start form
label | ea359d32-6f59-4069-a2d8-dd14cac2d831 |  | note | Responsibility-Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 2.2 Set up traffic management to plan
label | 896144d8-eea0-4377-b86d-bcc20cc77013 |  | note | Specification-TMP
label | 8ce9f209-5fc2-44b6-8e33-d01f4efaad36 |  | note | Method/Test-Perform Site audit post-set up
label | 40234d16-05eb-4d3c-a408-2d315f2a5025 |  | note | Frequency-Each site
label | 7275e5d7-16d9-4d8e-9872-8de79d29732d |  | note | Records required-Daily Diary
label | 95fc6f08-f8f8-4aa5-b601-42515b120baf |  | note | Responsibility-STMS
label | de477b5d-254b-47e3-b7e0-6206ab711482 |  | note | Test
checkpoint-status |  |  | checkpoint | 2.3 Assess environmental requirements of site and install sediment and erosion control measures if required
label | 076a3dc9-e21d-4cdf-a61c-a118da55b338 |  | note | Specification-ESMP
label | cce7179e-c4c6-4405-b389-84bd66747b71 |  | note | Method/Test-Identify areas at risk and install control measures
label | d7def663-ffde-4fab-84f2-55b62edf21ec |  | note | Frequency-Each site
label | 64fb89ef-f0ff-42f5-b4e1-9ac5bf8120e4 |  | note | Records required-Daily diary
label | 5c8975e4-10a7-4aac-8392-77f467dd5ff4 |  | note | Responsibility-Supervisor
label | 775d3428-6d1f-4b7f-9a35-c032f312fc86 |  | note | Inspection
checkpoint-group |  |  | section | 3.0 Sub-base Stabilization Inlay
checkpoint-status |  |  | checkpoint | 3.1 Cement Spread Rate
label | 41ccb9f6-914f-4538-b452-b2d495728a58 |  | note | Specification-NZTA B/6 7.3
label | a50630ed-aaf5-49b3-ba30-490701596353 |  | note | Method/Test-±0.5kg/m2, Weigh mat
label | 2064eb59-8241-45c4-89a0-31a4f3c4bb86 |  | note | Frequency-Per run
label | 13e80b84-db1a-4ab5-954c-882e578906d4 |  | note | Records required-Cement Sheet
label | 595afb87-a805-4a93-87d7-2d69a6f987bb |  | note | Responsibility-Stabilising Supervisor
label | 576b9fdf-0172-42dd-87e6-ccf549160d8c |  | note | Test
checkpoint-status |  |  | checkpoint | 3.2 Hoe and stabilise to design depth
label | 2e7dfe01-0e32-4642-bfe4-45d5a2824dc2 |  | note | Specification-NZTA B/6 7.5.1
label | 31ca0612-75f5-47ae-83d1-7eab349ce648 |  | note | Method/Test--0mm / +20mm
label | 32dfb210-4158-4463-b300-32b3c58acf7f |  | note | Frequency-Per run
label | 5c74bf27-b607-42da-9f34-ca812d9a3f52 |  | note | Records required-Cement Sheet
label | c36dae67-d8d5-41d5-8a83-238af32b4a18 |  | note | Responsibility-Stabilising Supervisor
label | c023b460-8161-4b21-88e1-5e9aa21043d4 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 3.3 Overlap longitudinal joints
label | eb73694d-79ae-4405-b7ab-d4e6a48f544e |  | note | Specification-NZTA B/6 7.5.2
label | cf3b8bb7-e07c-4f0d-b365-22fc532f5314 |  | note | Method/Test-200mm overlap
label | a5bca535-07cd-4bca-b9e9-26a2c7cbe07a |  | note | Frequency-20m centres each side
label | 7afee4ef-b2e4-421d-82d2-ed353be12fd2 |  | note | Records required-Stringline Sheet
label | 027c8a20-8fd4-4fdc-a8ca-d123a9688082 |  | note | Responsibility-Stabilising Supervisor
label | f781da02-1e64-488d-b0dc-c6f4415814db |  | note | Inspection
checkpoint-status |  |  | checkpoint | 3.4 Plateau density test
label | 9dc3add3-2bf2-42aa-ab30-63a8ca6d978c |  | note | Specification-NZTA B/6 7.6
label | bcd12283-1b08-4fa6-8bd6-cce12dc004f0 |  | note | Method/Test-Nuclear Densometer, Tolerance?
label | 1fa395e5-4b03-44c9-ae8e-e03452899175 |  | note | Frequency-20m alternating wheel tracks
label | 6918f5aa-0647-426c-9dec-de969445f093 |  | note | Records required-Plateau Density Sheet
label | 8d288fdc-4cfb-4e98-b30f-f0f1eb162245 |  | note | Responsibility-Quality Engineer
label | 84baacdf-aa1f-4c24-a447-64803e52c5c4 |  | note | Test
checkpoint-status |  |  | checkpoint | 3.5 Confirm layer thickness
label | 7dbb0c0d-532c-4a78-99fe-966acfd59463 |  | note | Specification-NZTA B/6 8.2.2
label | f96884cd-c84d-4349-8a62-ca4f56dbdec6 |  | note | Method/Test--0mm / +20mm
label | 508fd6c2-7323-4988-bcda-64bea3351671 |  | note | Frequency-Every 20m, full width
label | c5eb282d-df01-49eb-942b-a3b33eb39200 |  | note | Records required-Stringline Sheet
label | 2f6a19e4-e174-4082-b7cf-35a983f1b537 |  | note | Responsibility-Rehab Manager
label | fad6f596-0e0a-4eba-8baf-d8c72e01915e |  | note | Test
checkpoint-status |  |  | checkpoint | 3.6 Confirm surface levels
label | 2bbaba20-309e-4c21-9b0c-a4ac639d0422 |  | note | Specification-NZTA B/6 8.2.2
label | 0b608d53-8002-4c5d-93b1-16a70bd7412d |  | note | Method/Test--5mm / +10mm
label | 7d3b2510-c041-4319-acc2-78e12df8009e |  | note | Frequency-Every 20m, full width
label | 88a721f8-a5cd-4ae9-9941-92d488ec54b3 |  | note | Records required-Stringline Sheet
label | 33d3437f-d429-488c-8548-e264bf6a1299 |  | note | Responsibility-Rehab Manager
label | 00e18dee-e107-400c-8f8c-58e222a1d80c |  | note | Test
checkpoint-status |  |  | checkpoint | 3.7 Compaction as per the results of the plateau density test/or
label | 401a3276-feaa-405a-8747-844c869e9030 |  | note | Specification-NZTA B/6 7.5.2
label | 21776206-91ca-495c-b62b-01021fdabfd3 |  | note | Method/Test-Mean ≥95%
label | 1208bc58-bf30-46a9-9f0b-f347ca4bd137 |  | note | Minimum ≥92%
label | b9be02a5-32f3-4157-9b4a-87f67c16658c |  | note | Frequency-Every 20m alternating wheel tracks
label | a2c039a0-4c75-425f-bdd9-d6606312a6fd |  | note | Records required-NDM Sheet
label | c7a8b4e5-1504-48f9-95ad-9f1e86efdd05 |  | note | Responsibility-Quality Engineer
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 3.8 Impact hammer test
label | fe59f34e-8827-40f5-93f3-5faabbeb287e |  | note | Specification-Spec?
label | 40955687-d0ed-458c-bc7c-32c6d2ad0897 |  | note | Method/Test-≥70 CIV
label | 7e9de4b5-039d-414f-a51a-07372ebd684a |  | note | Frequency-Every 20m alternating wheel tracks
label | b2079492-49c4-4b2f-8c99-aee2a4e07174 |  | note | Records required-Clegg Sheet
label | cd45b59c-b609-4b18-84eb-0177839e4627 |  | note | Responsibility-Quality Engineer
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 4.0 Basecourse Overlay
checkpoint-status |  |  | checkpoint | 4.1 Cement Spread Rate
label | 47c52f9b-7b45-40e9-9f62-64c344a1ffdd |  | note | Specification-NZTA B/6 7.3
label | a4d3bd27-e3db-478b-ac65-941c9bebcd13 |  | note | Method/Test-±0.5kg/m2, Weigh mat
label | 3b2b64bd-521c-4abc-ad6a-b35514b8b703 |  | note | Frequency-Per run
label | f8a527f9-6d98-4bd1-a70d-a010af3eab8f |  | note | Records required-Cement Sheet
label | 9def3b8d-0929-41ab-a3b7-1853c48b8da0 |  | note | Responsibility-Stabilizing Supervisor
label | a8b24720-934d-4bb3-9103-74299fb8114b |  | note | Test
checkpoint-status |  |  | checkpoint | 4.2 Hoe and stabilise to design depth
label | 2d17c155-60da-489f-901f-7cd1cdc2fc9d |  | note | Specification-NZTA B/6 7.5.1
label | a4819c85-d79e-4ae5-bd80-94772f63f57e |  | note | Method/Test--0mm / +20mm
label | 26646ab8-ae51-4e37-abf7-d048c187bcf0 |  | note | Record hoe-depth setting
label | 61703c20-6ca5-491b-9c36-cbc17db52ad8 |  | note | Frequency-Per run
label | f4bdf309-eafd-497d-aee9-29dd006eb3d0 |  | note | Records required-Cement Sheet
label | 2766b5ac-f979-4a89-a6de-e41397a8c477 |  | note | Responsibility-Stabilizing Supervisor
label | 1d3db381-707a-4406-b948-3bcf12d93676 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 4.3 Overlap longitudinal joints
label | 666f362e-0a89-4c47-9426-1367c84813b1 |  | note | Specification-NZTA B/6 7.5.2
label | 5c1ae36c-73f5-4864-9217-2f60c9c3403e |  | note | Method/Test-200mm overlap
label | 0a8d727d-b05b-4ac4-9740-564eb98b9c32 |  | note | Frequency-20m centres each side
label | ce7a1ad2-13cc-43d7-b9a9-02319dcd80ee |  | note | Records required-Stringline Sheet
label | 3178c3f8-90b8-48e3-b8c3-faf99bed3b1c |  | note | Responsibility-Stabilizing Supervisor
label | 9cec1b46-8b3f-429e-8bbc-154abdb34e0b |  | note | Inspection
checkpoint-status |  |  | checkpoint | 4.4 Plateau density test
label | f63f5b85-b845-432f-9809-c81675f49d81 |  | note | Specification-NZTA B/6 7.6
label | 22428c17-da31-4b75-a90b-8bb2d2562f40 |  | note | Method/Test-Nuclear Densometer
label | 6456c3db-7ed6-46f5-a186-2593b6468be1 |  | note | Tolerance?
label | 4b7a04df-1469-4024-9367-bde29bfbd761 |  | note | Frequency-20m alternating wheel tracks
label | 81a9c086-ae11-4967-be11-a4bae585a00e |  | note | Records required-Plateau Density Sheet
label | 48410c54-53ca-478b-9a33-076885ba31f1 |  | note | Responsibility-Quality Engineer
label | cc2b2c81-4eeb-4433-b862-1bc25dfc9238 |  | note | Test
checkpoint-status |  |  | checkpoint | 4.5 Confirm layer thickness
label | ae576eeb-aba4-463b-8b6e-8c3e10355d1d |  | note | Specification-NZTA B/6 8.2.2
label | e15ab925-622d-4020-90ea-26b3b18ab317 |  | note | Method/Test--0mm / +20mm
label | 72ae7d16-1914-49f3-9b36-17f89c97c426 |  | note | Frequency-Every 20m, full width
label | ee8a359c-9aa0-40e8-a114-ef66cc8c658b |  | note | Records required-Stringline Sheet
label | e98882b8-1c61-42e4-8f88-0123c36a57f8 |  | note | Responsibility-Rehab Manager
label | 55f401e6-39e8-4c6d-8da5-f4410025072c |  | note | Test
checkpoint-status |  |  | checkpoint | 4.6 Compaction as per sample test results
label | cba46c39-da19-4bc1-a5f2-57061dedee89 |  | note | Specification-NZTA B/6 7.5.2
label | 007ecb9a-ec19-4b2e-9e0c-fb273250b4a3 |  | note | Method/Test-Mean ≥95%
label | 5d16eada-febb-4d0d-927e-2af883d13e07 |  | note | Minimum ≥92%
label | 459be6f8-1f1a-47c6-8fdc-08be8209411a |  | note | Frequency-Every 20m alternating wheel tracks
label | f22c9102-815a-4709-a80e-4dde469b00e2 |  | note | Records required-NDM Sheet
label | 52f55bde-e1a1-4784-8d25-bd0171d646e2 |  | note | Responsibility-IANZ Accredited Lab
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 4.7 Impact hammer test
label | fedef3b0-0a51-4257-95b0-4fd7bf945291 |  | note | Specification-Spec?
label | a771f211-2b2a-4a2c-a130-50eadd2a5ec5 |  | note | Method/Test-≥70 CIV
label | b83c3e4c-1b4e-4f10-9630-861a5173b067 |  | note | Frequency-Every 20m alternating wheel tracks
label | 036c81d5-6817-4f6f-8381-ad4dd4b7c5cf |  | note | Records required-Clegg Sheet
label | c5e9038c-5cfa-4588-aaed-a7132eeef0aa |  | note | Responsibility-IANZ Accredited Lab
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 4.8 Confirm surface levels
label | 18c0cfdd-450a-49b5-8144-9ebdb205433d |  | note | Specification-NZTA B/2 5.1
label | 5cdcfaea-5a9a-424b-b95e-7d7f8c7375a7 |  | note | Method/Test--5mm / +15mm
label | 8d95770b-04c1-4b8c-8944-301f29552c68 |  | note | Frequency-Every 20m, full width
label | cee66dcc-7515-41bc-9459-b92f16ac1042 |  | note | Records required-Stringline Sheet
label | 7adabb7e-a80c-424f-9b59-76f5310b8dda |  | note | Responsibility-Rehab Manager
label | 37c4d765-2939-4e44-9086-fdf3b86fcf3e |  | note | Test
checkpoint-status |  |  | checkpoint | 4.9 Surface Finish
label | 8478e7d4-23b4-471d-83c9-b61991d5357e |  | note | Specification-NZTA B/2
label | 322b4060-80fd-4c73-b223-1d24b8dde2cf |  | note | Method/Test-Sealing Supervisor to inspect
label | 2ff8f9c6-c229-4698-956c-ca9160cf7b75 |  | note | Frequency-Per site
label | 670d5ff7-dc6d-47c7-aa10-879608fc6e77 |  | note | Records required-
label | 29091767-7fde-4058-8774-1a9336313045 |  | note | Responsibility-Sealing Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 5.0 Aggregate Testing – Sealing Chip
checkpoint-status |  |  | checkpoint | 5.1 Crushing Strength
label | 2ce9ed7b-858b-4e1f-969b-7ac8eeb809c8 |  | note | Specification-NZTA M/6 3.2
label | 73e719d7-2f80-4af6-87f9-8f9021633d1b |  | note | Method/Test-<10% fines passing 2.36mm under 230 KN load
label | b5e417dc-1097-412f-96d5-49733fe83c7d |  | note | Frequency-1 Test
label | 89932d58-0c14-42f2-97eb-7779fa7d8fca |  | note | Records required-Test Report
label | ce4135cd-340d-4d2b-b844-1df6b48216ec |  | note | Responsibility-IANZ accredited laboratory
label | 92b803ff-5c3d-40d0-9ea7-dc2de4895615 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.2 Weathering Quality
label | 8aedcf0b-a48d-4440-b05e-dff1dd544ab0 |  | note | Specification-NZTA M/6 3.3
label | fc9d3dc0-478b-4038-aad3-eec905d95a53 |  | note | Method/Test-AA or BA
label | b48cecaf-f3cc-4a33-a2ad-4c48aa7b548c |  | note | Frequency-1 Test
label | 33999320-e2c8-438f-9b08-289cccebbfb8 |  | note | Records required-Test Report
label | f15c09af-933a-4aa2-88cf-05271d89803b |  | note | Responsibility-IANZ accredited laboratory
label | e111d584-892f-4b2d-b8b7-1239b7179858 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.3 Polished Stone Value
label | 2b3c0656-c59a-47d1-b872-80a5532ae7f1 |  | note | Specification-NZTA M/6 3.5
label | 1ed213b7-8d93-439c-a25a-746ed0742557 |  | note | Method/Test-PSV Required = 52 min
label | ea6e4fd9-438b-4b89-8aad-408930d7ad0e |  | note | Frequency-1 Test
label | 22c17b1e-9071-4a2f-8901-cd53c9a3cb41 |  | note | Records required-Test Report
label | 28269bf5-e2c7-447c-a871-039179137d8e |  | note | Responsibility-Accredited PSV Testing Agency
label | ce4cbb7f-7088-4536-9635-dc2b3b820ad7 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.4 Cleanliness
label | e5cefa6f-2281-4568-b73d-734aa13ba6f5 |  | note | Specification-NZTA M/6 4.1.1
label | eee98b3f-c410-4ab0-85d8-2201e2e3e411 |  | note | Method/Test-Grade 5 – 89 min Grade 3 – 87 min Grade 4 – 85 min
label | f1870c71-40f1-434c-902f-ee9a165c423d |  | note | Frequency-1 Test
label | 05a51297-cb36-47f4-90b8-48ab2883bb5e |  | note | Records required-Test Report
label | c0c79adf-7444-46a4-998f-ff0628d304de |  | note | Responsibility-IANZ accredited laboratory
label | d841bba6-ad0d-4376-8139-c05e5f518169 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.5 Grading
label | 6da0f632-89a0-4b0f-8021-9b58cf0cb147 |  | note | Specification-NZTA M/6 4.2.1
label | 05605d70-8d95-4ab9-82e1-4f7b5d243d27 |  | note | Method/Test-See NZTA M/6 4.2.1
label | ebeb9595-0333-4027-ae76-bd3cefb13da5 |  | note | Frequency-1 Test
label | 3373ae2a-f612-42c4-8856-39236ce20993 |  | note | Records required-Test Report
label | cd9833ef-252d-452f-8e0b-2af07db92dcd |  | note | Responsibility-IANZ accredited laboratory
label | b56cf882-7c55-47c0-a20d-9b4880521b87 |  | note | Test
checkpoint-group |  |  | section | 6.0 Chipseal Control
checkpoint-status |  |  | checkpoint | 6.1 Confirm viscosity of bitumen
label | 17eed410-0dca-4519-9cd7-44f9f87e9fa1 |  | note | Specification-NZTA M/1 Table 1
label | a06d73dc-4bef-4e5d-bcf0-54780333c417 |  | note | Method/Test-Viscosity PaS at 60°C
label | e2e2a047-307d-43dc-b76f-dfd75b5d847d |  | note | Frequency-1 Test
label | a660b940-bc9b-4794-bada-5c57966cb353 |  | note | Records required-Construction
label | 0fb155cf-7d1d-477a-9d7b-e5d289dc66a2 |  | note | Responsibility-IANZ accredited laboratory
label | 99c11636-0e77-4217-9992-5c8ba7708604 |  | note | Test
checkpoint-status |  |  | checkpoint | 6.2 Confirm penetration grade of bitumen
label | 036959b2-7727-4393-86c7-bb9c5a8c8fec |  | note | Specification-NZTA M/1 Table 1
label | 3c3b9eca-2807-46f4-bf78-3491466fc751 |  | note | Method/Test-Penetration at 25°C,100g, five seconds
label | 6b91c790-b47c-4b98-b946-2386612de83b |  | note | Frequency-1 Test
label | 129c536f-2afc-4e8f-af3f-ad06d9a5b2b1 |  | note | Records required-Construction
label | cdc1ce3b-d67c-4871-84a9-e7c34b0037a3 |  | note | Responsibility-IANZ accredited laboratory
label | 90619996-59e8-49a4-92c5-e3dffb5e6374 |  | note | Test
checkpoint-status |  |  | checkpoint | 6.3 Spray bitumen, then place chip *and roll – refer design for chipseal grade
label | 3d394773-78e2-40a2-83f9-f3f411aa0ab5 |  | note | Specification-Design
label | d8c8ad78-8d8a-457f-ac88-543ef6cef4bf |  | note | Method/Test-Visual check
label | 58fe46d2-d755-46f9-8a1b-cc2de59a83e0 |  | note | Frequency-1 Test
label | f1a36431-96c2-4a7f-9d2f-b8ae9fa76e75 |  | note | Records required-Following construction of chipseal
label | 8f708cf6-3289-43a3-bd61-3f9ee4ff1434 |  | note | Responsibility-Sealing Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 6.4 Check for excessive “windows”
checkpoint-group |  |  | section | 7.0 Site Close-out
checkpoint-status |  |  | checkpoint | 7.1 Field Quality Review
label | 92262956-7dca-4646-8e37-f55482dff4ff |  | note | Specification-QMP
label | b3d53cfb-5a0c-4125-91db-078ca2179609 |  | note | Method/Test-Verification of Work Standards
label | 5ad2ffbd-aa8c-46b9-9954-2b2d63b676e5 |  | note | Frequency-10% of sites
label | d4a9658a-0bcd-4cfd-b297-95e591a488ae |  | note | Records required-Record in Audit Field of RAMM Contractor
label | 8883633e-beb0-4921-a272-e4f21094738b |  | note | Responsibility-Supervisor
label | 58f536d3-bd4f-4019-a200-3d25c28b9822 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 7.2 Collect RAMM Data
label | e6a82e2a-0da5-41ad-823e-e93199bc08d9 |  | note | Specification-SHDOM / Data Quality Plan
label | 4c22410c-b25f-4d7b-b459-8471fcfd5029 |  | note | Method/Test-L1 Accredited Personnel
label | bbf2c5c3-1940-4a31-bb3e-7dfb567b60ac |  | note | Frequency-All Jobs
label | e81d3024-34d3-4825-a0e5-ed8dde3a0c23 |  | note | Records required-SHDOM Specs
label | a050e4b3-772b-4490-8ad1-08b87d9c8a32 |  | note | Responsibility-Foreman/ Supervisor
label | b0513564-952e-4fbe-adfd-38c8500a8a87 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 7.3 Verify RAMM Data
label | a03ca3c1-914f-46c1-a033-e3460e3c5a5f |  | note | Specification-SHDOM / Data Quality Plan
label | ab79a5bc-92b7-4eaf-b639-a12d7054ff86 |  | note | Method/Test-Level 2 Accredited Personnel
label | ed197078-f7f1-43e7-b81b-4051eecca75f |  | note | Frequency-All Jobs
label | 887e82da-8ca9-42ee-88ea-2531c699cd57 |  | note | Records required-SHDOM Specs
label | bf55c14d-161f-424d-aa17-9ba1254be2e7 |  | note | Responsibility-RAMM Manager
label | 3ce18a17-698b-4858-9222-1396c7eb80d6 |  | note | Inspection
checklist-sectioned |  |  | checklist | ITP - Subgrade Improvement Layer |  |  |  |  | Yes | ITP - Subgrade Improvement Layer | cda771fd-6059-4888-92b8-fff1e5d2e03b
checkpoint-group |  |  | section | Setout, Materials and Preparation
checkpoint-status |  |  | checkpoint | 2.0 - Mark out and approve
label | 57329609-449b-4801-95c7-0fd0be5080b4 |  | note | Detail of Activity - Set out and mark up of treatment area
label | 5f3bdb9c-43be-4f8c-915f-62ee91afe3b5 |  | note | Action (Hold, Monitor, Witness) - H
label | 05303be9-896d-4693-8171-0d4eba796837 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All earthworks areas
label | c24cb23b-c866-4989-867b-b1fe8925eb88 |  | note | Inspection / Test method - Visual Inspection
label | a444d7c1-1820-479f-ad93-97fe045c103d |  | note | Acceptance Criteria - N/A
label | 489dd490-434f-4231-b829-582b7831e643 |  | note | Record documents - Contractor's site diary
label | 7efe06f1-afd4-4420-98d8-74a87d7e800a |  | note | Responsibility - Contractor
label | ae2d6a0d-b49f-449e-a5ec-2c57c8a3a6c3 |  | note | Comments - Treatment area marked up jointly by Contractor and Eng.Rep.
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.1 - Underground services
label | cf878435-a2ef-4c56-a461-8fecc746427d |  | note | Detail of Activity - Identify and positively locate services
label | e8fac28c-0026-45b2-8dc5-59a027c500ce |  | note | Action (Hold, Monitor, Witness) - H
label | ef158a97-ebd2-4175-8e52-f5541906253c |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All earthworks areas
label | 21d1bae4-c6e1-4222-ae26-90b07325463f |  | note | Inspection / Test method - Hydoexcavation
label | ca24966f-e552-423c-af46-fbdae22b68fe |  | note | Acceptance Criteria - N/A
label | 613ffdf2-c7a3-4a77-90dc-834644bb73c1 |  | note | Record documents - Drawings
label | 08aa97ff-4ec1-4575-bde3-59344a31b7ad |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.2 - Determine Embankment / Subgrade Strength
label | 5e84314b-5315-4908-a525-b3e0c6a396f0 |  | note | Detail of Activity - Determine bearing strength of subgrade before placing Brown Rock
label | fe49ac99-3088-4507-8c16-e67d1c89e0b8 |  | note | Action (Hold, Monitor, Witness) - H
label | b3046eb8-685d-4bdc-9688-9255f8612441 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 Scala per 70 m2 (typically 1 per 10m staggered between lanes)
label | 6e4124b1-b6c4-4ff5-be4d-ad77ead054d1 |  | note | Inspection / Test method - NZS 4402.6.5.2
label | fb651bf9-9dfe-4bdf-ac29-7d0a863d444e |  | note | Acceptance Criteria - For Final Design verification
label | f294ec4c-91c6-49b3-9a32-c7afc0c06d84 |  | note | Record documents - IANZ Report
label | 66ca3f44-0cee-4253-a030-4ec189258041 |  | note | Responsibility - Contractor
label | b0e435ee-1d5a-40ab-935a-fd649adb2905 |  | note | Comments - Scalas to be carried out to check consistency and determine inferred CBR before placing the SIL or subbase material and after placing, shaping and pre-compacting the subbase layer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | Subgrade Improvement Layer material
checkpoint-status |  |  | checkpoint | 2.3.1 - Brown Rock
label | c23e7de7-aec9-410d-8380-0bbb9e2ecec3 |  | note | Detail of Activity - Properties of Brown Rock
label | 11dc914f-292b-4847-b4f0-b1e6e9a7d894 |  | note | Action (Hold, Monitor, Witness) - H
label | c26b76cc-ebfb-470e-b31e-eb01f4a270ba |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 2 per source
label | 1eb8f72c-34f0-4969-88cb-d97715d5f53b |  | note | Inspection / Test method - PSD Plasticity Index MDD / OMC CBR
label | 7ae00f8a-23e7-439d-81f5-dedef5e0406e |  | note | Record documents - IANZ Report
label | 017a708f-c014-4e38-8146-80b458a84133 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3.2 - Brown Rock
label | 6d7fea6a-aca5-4967-9af0-abb3a46f4add |  | note | Detail of Activity - Range of Crushing resistance of Brown Rock
label | 4f3ff315-11d4-45ce-a1e1-47e2a92a39a7 |  | note | Action (Hold, Monitor, Witness) - H
label | 86155801-b057-444c-847d-d1c7583e056f |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 2 per source
label | bdfe2957-9367-4085-bee4-fc36091630a4 |  | note | Inspection / Test method - Crushing resistance
label | 209faebf-31af-4424-ba6b-94822487fc48 |  | note | Record documents - IANZ Report
label | 5cc7417c-f375-4d55-a7e9-fbdecd32a809 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3.3 - Brown Rock
label | a41c967e-ad08-42ea-987d-9cde9592dc37 |  | note | Detail of Activity - Binder Optimisation for Stabilised SIL
label | 7a5b7e02-07be-46b5-bee4-ef02968d4b28 |  | note | Action (Hold, Monitor, Witness) - H
label | 443eedcf-527a-4828-98f5-27a6bc581a47 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source
label | fb92c281-bb7b-4b06-950c-e6e290346c18 |  | note | Inspection / Test method - CBR with varying stabilising agent contents
label | dbad7540-0774-4d99-ad59-b88d5a67ef57 |  | note | Acceptance Criteria - 4-day Soaked CBR ≥ 20%
label | 5ba33c80-cea6-4336-9525-3f1ffa4bdcbb |  | note | Record documents - Laboratory Report
label | ac43dbcf-f362-4296-8c6e-ec03888f8906 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3.4 - Brown Rock
label | 9e84830a-82db-4dc0-a657-e448b43f0e86 |  | note | Detail of Activity - Proof roll of placed material before Stabilisation
label | 1271bcf9-941c-4a3c-82bf-c715bcbbb231 |  | note | Action (Hold, Monitor, Witness) - W
label | ecd916d0-24c6-4bcc-90b9-55b46f7297d3 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All SIL areas per 0.5m lift
label | 5a533c79-8615-4320-90d7-bc92a2b60682 |  | note | Inspection / Test method - Visual inspection
label | 3ed91052-32b7-443c-ae13-7077c019f5c6 |  | note | Acceptance Criteria - No significant visual deformation under the wheel load
label | 34e82856-2290-4ccb-ac03-9be2bc80efbf |  | note | Record documents - Contractor's site diary
label | dbc3b79e-3a10-485b-8379-46146bc598da |  | note | Responsibility - Contractor
label | 49756f3f-a0fa-4175-8ead-1963a0d6d8e9 |  | note | Comments - Witnessed by Engineers Representative and signed off in daily diary
checkpoint-group |  |  | section | Construction and Finishing (Subgrade Improvement Layer)
checkpoint-status |  |  | checkpoint | 2.4.1 - Testing of placed and Stabilised SIL
label | 5cabdb20-e51a-4522-9a87-ce8a17fe9a51 |  | note | Detail of Activity - Particle Size Distribution after In-situ Stabilisation
label | 6940283c-2b76-4455-a5d3-45c50168d5c6 |  | note | Action (Hold, Monitor, Witness) - H
label | 28209c6c-2f9c-47eb-8a2d-066a996dbda4 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per lot
label | 91e0c778-7713-4581-85bf-646378668505 |  | note | Inspection / Test method - PSD
label | b1cd137f-61cc-4f23-b5a2-7d9f816f0933 |  | note | Record documents - IANZ Report
label | 9500c1c6-623b-44ee-8929-0fccd660a186 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4.2 - Testing of placed and Stabilised SIL
label | 230b8d88-a9fb-4916-afbc-671aadc55652 |  | note | Detail of Activity - Percentage of Blue Rock content
label | 16febe50-b593-4532-9698-4c2de59e25f7 |  | note | Action (Hold, Monitor, Witness) - W
label | d25f877a-492c-4286-94b0-e0ca26b01690 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per lot
label | 7ac7f165-ccee-45dc-aad0-e67206ebdf59 |  | note | Inspection / Test method - Visual
label | 9e917d05-fd09-4da9-911a-5138a0280387 |  | note | Record documents - IANZ Report
label | 4ab25ae3-c43d-4a9a-ba8c-9e0f6f7de7cd |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 2.4.3 - All earthworks areas 1 lot < 500m2 per 0.5m lift
label | 43fe7858-ec3c-41ec-b371-9027bb48672b |  | note | Detail of Activity - Target density
label | 802f9f78-6a13-4ee8-b894-2a33e922109f |  | note | Action (Hold, Monitor, Witness) - H
label | fc22679b-fe85-40c8-b0a0-c51e8fc07f85 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All earthworks areas 1 lot < 500m2 per 0.5m lift
label | bd9a1b71-978d-4a34-ac26-5ee381334576 |  | note | Inspection / Test method - MDD / OMC
label | b67bf9c5-4424-4bc6-800a-be4f8c401bad |  | note | Record documents - IANZ Report
label | bdced4c0-3c41-4c1a-bbd4-967676bd00e9 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4.3 - All earthworks areas 1 lot < 500m2 per 0.5m lift
label | 360c4bfe-6ebb-43b6-9859-dde635f3a405 |  | note | Detail of Activity - Degree of Compaction
label | cc2f4297-2b79-44a2-9525-d9c3f867ece5 |  | note | Action (Hold, Monitor, Witness) - H
label | 465cfe39-d6fa-4bf4-aa1f-ad8f131e38c6 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All SIL areas 1 lot < 500m2 per 0.5m lift
label | 62c56ba8-3f40-4377-acac-adf613737482 |  | note | Inspection / Test method - Nuclear Density Meter
label | c4bcf1b5-eaf7-4841-b7f4-94f712026248 |  | note | Acceptance Criteria - Minimum field density of 95% of maximum dry density (MDD) obtained by standard compaction
label | 9732ea3b-362c-41fc-b046-db49b964306b |  | note | Record documents - Contractor's site diary
label | b31d6505-7129-45d5-8943-96c9ffed1ac5 |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4.4 - All earthworks areas 1 lot < 500m2 per 0.5m lift
label | e7486360-c5e1-4382-9c04-53cb67300ac3 |  | note | Detail of Activity - Deflection of Stabilised SIL after 7 days of stabilisation
label | ec323e89-3cc4-486f-af2a-881c5fb9b597 |  | note | Action (Hold, Monitor, Witness) - H
label | 69d968b6-af62-43c1-84e2-ef3e55449915 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - All SIL areas 1 lot < 500m2 per 0.5m lift
label | ccafa5f0-64ff-4846-a071-173a8807583d |  | note | Inspection / Test method - Benkelman Beam
label | 5da25d4e-102a-4ce7-9415-d181e92ea800 |  | note | Acceptance Criteria - Benkelman Beam deflection ≤ 1.5mm
label | 431973a4-59fd-4b8d-ba03-c8097558af0c |  | note | Record documents - Test report
label | 1b16d387-e8ae-4777-a4ef-1569140a942f |  | note | Responsibility - Contractor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Non-conforming results
label | ecd88ff1-17ab-4d4c-9b90-0fcc651ccd55 |  | note | Detail of Activity - Assessment of all test results for conformity
label | 84dd20c6-c439-4825-bc87-8a9ef6e6849a |  | note | Action (Hold, Monitor, Witness) - H
label | 095fe447-c180-40e7-a570-b1f04d7e0eab |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Each Lot
label | bc476240-9594-45cc-a9b3-9d0842685943 |  | note | Inspection / Test method - Site Inspection
label | 53b16d8a-e102-4984-bd8d-9a5687d8a73a |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | 43f9d142-84d5-4cd5-8aa2-033a69faae22 |  | note | Record documents - NCR
label | e2813fd1-ba6d-4386-bb93-970dd2061457 |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 812aef1e-34af-4237-a77e-4dcf4c584e31 |  | textbox | Contractor's Rep Name:
text | 7aa38494-74d0-476f-8059-0f8e6e46d3a1 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Test Results |  |  |  |  | Yes | Test Results | cff80c42-8e26-4b9d-bd86-1993aad563ec
checkpoint-status |  |  | checkpoint | Attached
checklist-sectioned |  |  | checklist | ITP - Bituminous Seal Coat |  |  |  |  | Yes | ITP - Bituminous Seal Coat | d07cbaf6-597f-4cca-8c21-1d6dce43b2e4
checkpoint-group |  |  | section | Sealing
checkpoint-status |  |  | checkpoint | 6 - Seal Design
label | 22add1f3-0dd5-4dd8-beef-1dd145c3585d |  | note | Detail of Activity - Seal design outlining all design assumptions
label | 4f88c96d-1290-493b-9028-c65327edc81d |  | note | Action (Hold, Monitor, Witness) - H
label | 7ee71cc6-642d-4afc-ac22-ace7e211f559 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per seal application type
label | 387e004c-8c2f-4c14-abe4-3558a7784ae8 |  | note | Inspection / Test method - Review
label | 1bba4e66-1270-4a51-acfa-28fba583712c |  | note | Acceptance Criteria - New Zealand Chip Sealing Handbook
label | 8e1e799c-2bcc-4dfe-98c0-24b87be8ab69 |  | note | Record documents - Seal design in contractor's site folder
label | 5042cfc1-8686-4840-ac8e-ee3d574ee088 |  | note | Responsibility - Designer / Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6.1.1 - Check raw materials
label | 96518840-f2a0-4197-b707-9b33c2c40460 |  | note | Detail of Activity - Sealing Aggregates
label | 9bdfb53e-ea34-4b08-90c6-ecc93ef29a69 |  | note | Action (Hold, Monitor, Witness) - M
label | 13f2e06c-df0c-4623-8543-6dd1c461a333 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 33c9add8-7a31-4416-b891-91523c6fb93d |  | note | Inspection / Test method - Source Properties
label | 11912d46-cfcf-46d8-a504-3c32d39be3d7 |  | note | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | 855b9c1d-d212-4bde-95b7-d3eaee6b7e60 |  | note | Record documents - Certificate in contractor's site folder
label | 6bbfc3d8-c9a3-45b6-9873-e53ea6dc2221 |  | note | Responsibility - Contractor
label | 36fcd977-a797-4b2b-923b-07989e1f43dc |  | note | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint-status |  |  | checkpoint | 6.1.2 - Check raw materials
label | 5f24ff69-5f09-4a18-9b80-4627f5371bfe |  | note | Detail of Activity - Sealing Aggregates
label | 50e9e9d9-97e4-40d7-8cf3-9a2029c30645 |  | note | Action (Hold, Monitor, Witness) - M
label | 35947ca1-4aa0-4a6f-b855-753288b6ce2a |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 per source stockpile
label | 8fdf7899-4031-4c28-804d-e65738ad5c05 |  | note | Inspection / Test method - Production Properties
label | 430c77c9-dcc5-486d-93a5-76ea72d202ef |  | note | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | dae6fd7f-d93f-43d2-bf40-5c910b1c4127 |  | note | Record documents - Certificate in contractor's site folder
label | 1d9d7b98-7cfa-41b6-b03a-32b9ee52a3e7 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 6.1.3 - Check raw materials
label | eb9986e0-925c-497f-9c99-82404aa9e37c |  | note | Detail of Activity - Adhesion Agents
label | 54a763f1-59c4-45f2-8a58-933f6b211641 |  | note | Action (Hold, Monitor, Witness) - M
label | fc995650-abc5-47b2-9375-b24124a4cc08 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Prior to use
label | 40dfae2b-e74f-46e7-b54e-ec416aea65da |  | note | Acceptance Criteria - NZTA M06 / NZTA M13
label | 36df5724-37a7-4eb5-802e-dd32025212f6 |  | note | Record documents - Certificate in contractor's site folder
label | 7de9124a-ed5f-491d-962f-89f285199db1 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 6.1.4 - Check raw materials
label | 8599f38e-7f51-466c-8e1a-f68c78117053 |  | note | Detail of Activity - Audit samples
label | b24ad44e-b55d-412e-8700-838294681c4d |  | note | Action (Hold, Monitor, Witness) - M
label | 1b540f37-fd97-468a-969d-49d4aa3a0104 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 20 kg per stockpile
label | 0fae039c-e6ea-42fe-b05d-e1153f731ad3 |  | note | Inspection / Test method - N/A
label | 89e0dd25-5620-4dbd-957d-0a7f6e10cd51 |  | note | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | 2b48b1b8-6a3e-4289-8fcd-e0e1215dab0d |  | note | Record documents - ITP
label | 983ec05a-ff2c-401e-b033-3a6c6b622018 |  | note | Responsibility - Contractor
label | b86779b0-3518-4a53-9d5d-c1881aa93bea |  | note | Comments - Retain for testing if required
checkpoint-status |  |  | checkpoint | 6.2.1 - Pre-Seal requirements
label | 5d49ae65-2eaa-4509-984f-4f03d90bd293 |  | note | Detail of Activity - Visual inspection of surface to be sealed
label | 8824a051-b901-40a7-9751-a8483551535e |  | note | Action (Hold, Monitor, Witness) - W
label | 8146ff96-af42-4336-9dd2-4250c150bf65 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - per sealing schedule. 1 Lot = 1 day's production and < 1500m2
label | a4a01c11-0aaa-494a-b2f2-ef12cfe056b3 |  | note | Inspection / Test method - Visual Inspection
label | 959e250b-511e-41ef-be72-2dbe76f05a6f |  | note | Acceptance Criteria - NZTA B02
label | 40b1f9f8-ed0a-4122-9454-325a6eed1611 |  | note | Record documents - Contractor's site diary
label | 14cf304d-b134-486a-b683-8a9ceb659bca |  | note | Responsibility - Engineers Rep
label | 5538587b-11fb-48af-9383-bef904c06425 |  | note | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint-status |  |  | checkpoint | 6.2.2 - Pre-Seal requirements
label | 53fbc2bf-5614-4a6a-a46f-4b603cf198d5 |  | note | Detail of Activity - Dry back Moisture Content
label | b5e38607-8c32-496c-a71c-7aa8585b3869 |  | note | Action (Hold, Monitor, Witness) - H
label | 9b400d52-c9c4-471b-aba3-a5231bf19142 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 9 per Lot
label | 71997297-5490-483d-bc7f-414a3cb29b78 |  | note | Inspection / Test method - NZS 4407.4.2.1
label | a9d83440-e128-47b4-958b-6a844ed55655 |  | note | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | cf0b828f-61eb-4cad-a717-3f84e9f3673f |  | note | Record documents - IANZ Report
label | f406df43-dc39-46f7-b49b-d94cb3cbb679 |  | note | Responsibility - Contractor
label | 492aca0a-128d-4d88-bb8a-6738368dcccd |  | note | Comments - Only required if pavement widening extends into trafficked lane
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6.2.3 - Pre-Seal requirements
label | ccda972d-82aa-4a5f-9f98-0fdcb8cdbd8e |  | note | Detail of Activity - Clegg Hammer
label | 13535e3b-c4ba-4169-8d96-fc994abbef1e |  | note | Action (Hold, Monitor, Witness) - M
label | 724bc1e2-4828-4c7d-8812-6e41f8445a8f |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 1 CIV per 10m 1 Lot < 300m
label | 3774917f-0b61-49c7-8211-1124b6fefdb8 |  | note | Inspection / Test method - Clegg Impact Value Test
label | 5db2003d-a281-4eb8-af27-e611ce21cd6f |  | note | Acceptance Criteria - Average CIV > 40 Min. CIV > 35
label | 7f6955a7-ae90-43f5-a3dd-e720645410f1 |  | note | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | 014a3c47-d6a0-4090-a32c-986d12410f0c |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 6.3.1 - Sealing
label | bfc1a8e5-96e3-4762-ad4d-f2b9069d83f5 |  | note | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | 6c4f8174-70e8-458e-acd2-4110d81664d7 |  | note | Action (Hold, Monitor, Witness) - M
label | 4f08d3c8-b135-4970-8921-6aca518f74a9 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 2 samples per distributor
label | 9f3c1979-ee93-477f-8907-91a4e970b83a |  | note | Inspection / Test method - Penetration grade testing
label | dae8a6bf-ad3f-4b77-88cd-148125e0d5eb |  | note | Acceptance Criteria - NZTA M01 - Tables 1, 2, 3 and 5
label | cdeecda9-7dd4-44ef-aa94-84fd90c47ee3 |  | note | Record documents - Certificate in contractor's site folder
label | 7d7362d5-993c-41c5-9a06-0866493ab29a |  | note | Responsibility - Contractor
label | d7599dfc-0e3c-4b5d-81c5-be51be7259c0 |  | note | Comments - Sampling as per ASTM D140 or equivalent
checkpoint-status |  |  | checkpoint | 6.3.2 - Sealing
label | 83940e34-ee1d-4214-83d3-c2580db907d9 |  | note | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | 9b10e1f1-b1ac-4d2b-892f-e9699707cb39 |  | note | Action (Hold, Monitor, Witness) - M
label | fa60a4f1-6116-47a1-a01f-9550a43bfd8d |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - 2 samples per distributor
label | 7c07d091-9a6d-438a-baec-0462f6fff52e |  | note | Inspection / Test method - Durability
label | 832d6ea4-faed-47f4-abd1-811355f35ef6 |  | note | Acceptance Criteria - NZTA M01 - Table 5
label | 65aecc4b-37de-4225-8789-46abd3e3fbfe |  | note | Record documents - Certificate in contractor's site folder
label | 505c0804-c754-4876-8802-c7197957df77 |  | note | Responsibility - Contractor
label | 2cb53cb4-8a94-48b7-befe-b7c1abe2c89e |  | note | Comments - Refer notes in clause 5 of NZTA M01
checkpoint-status |  |  | checkpoint | 6.3.3 - Sealing
label | fddb4f59-84f8-442c-a5ef-00b0def245df |  | note | Detail of Activity - Spraying Temperature (Bitumen only)
label | db5401ef-8b35-425b-9233-1db73c9d3b7e |  | note | Action (Hold, Monitor, Witness) - W
label | c583fca2-9913-445d-b5e1-7407c8671069 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Ongoing with non-going heat sensing gauge
label | c6b8f770-713c-45f0-8749-114b99d80138 |  | note | Inspection / Test method - Non-contact heat sensing gun
label | bd9b6b54-b4df-48b7-a3a1-b9823fc582cc |  | note | Acceptance Criteria - NZTA P03 - Table 2
label | 9b1a045a-a44a-4d22-91c6-587e3c4de71b |  | note | Record documents - ITP
label | 779eb7e2-d205-45f0-a520-6b1e754a0434 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 6.3.4 - Sealing
label | d49259ff-b9ad-4d0d-9c85-72b37be4ecd1 |  | note | Detail of Activity - Residual Bitumen Application Rate
label | fe97e2db-dcaa-4720-bf5f-fc98479a6606 |  | note | Action (Hold, Monitor, Witness) - M
label | dfc67979-e5d9-45dc-a8ed-3f415546e1b5 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Reconcile day's production
label | dae1396d-c079-4e1f-808e-1ce947d3f6a0 |  | note | Inspection / Test method - Dockets vs Area
label | 82fe92a5-3e74-4e14-aca2-f6bb7b31efb4 |  | note | Acceptance Criteria - ± 0.1 L/m2
label | eca9b802-cec7-4cef-a7ff-f78d3759e3f8 |  | note | Record documents - Site diary
label | 3b134ba8-a31f-41ba-bc1b-5a7d233319c3 |  | note | Responsibility - Contractor
checkpoint-status |  |  | checkpoint | 6.4 - Non-conforming results
label | c49ffb2c-384b-4cf4-99cb-9c83f3d7c4cd |  | note | Detail of Activity - Assessment of all test results for conformity
label | 366a6cfb-d116-474b-a6d6-67007a4e3469 |  | note | Action (Hold, Monitor, Witness) - H
label | a9f279e3-0cbc-4528-adff-69815882f040 |  | note | Minimum Test Frequency (Lot is the lesser of 1 day’s production or 500 m2) - Each Lot
label | 870def1e-31be-4f48-8571-cce65a11fb8b |  | note | Inspection / Test method - Site Inspection
label | a8a6c7ff-e178-4505-a771-0fc5f82e77da |  | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | d2024f24-5727-410b-a2ed-2f08edaedadd |  | note | Record documents - NCR
label | 4abe3514-2d0a-4cef-8c8f-b239fe464d15 |  | note | Responsibility - Engineer's Rep
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
text | 6aae3e7b-042c-44c8-bb24-5660aba2825a |  | textbox | Contractor's Rep Name:
text | 4abd7492-7103-4dae-b72e-55faf99ed2d9 |  | textbox | Engineer's Rep. Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | Rehab Quality |  |  |  |  | Yes | Pavement Rehabilitation SH27 | d22d5654-5fd7-49ea-abe9-47c0f9788421
checkpoint-group |  |  | section | Before starting work
checkpoint-status |  |  | checkpoint | Daily Work Briefing, confirm scope, location, that you have all staff, materials and plant needed
label | 75a4a7ad-34cd-44eb-9319-bfd210d535b1 |  | note | Specification-HSMP
label | fd006e2f-cf55-4809-b9d8-9b8bc4486a61 |  | note | Method/Test-Brief all team members on day’s work plan
label | ad260436-f585-4a09-8aea-2ea2434c0905 |  | note | Frequency-Each morning
label | fec33d64-ef78-4bf4-9a04-5ba9226c1dc1 |  | note | Records required-Daily diary
label | 65150aa2-44a9-4d01-964a-189c9b5a53a0 |  | note | Responsibility-Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 1.0 AP 40 M4 – Raw Aggregate Testing
checkpoint-status |  |  | checkpoint | 1.1 Sand equivalent, or
label | 11a42446-9aac-487b-a538-3bcddc053dee |  | note | Specification-Design
label | dd2090cf-b01e-4efd-a991-d19946f36949 |  | note | Method/Test-≥35 Unit of measure?
label | 6c67a86a-c4ba-4460-8374-0384156f6d1a |  | note | Frequency-1 sample per 500m3
label | 11c53661-89c0-4a75-91ed-69a86fc9331d |  | note | Records required-Test Report
label | 585500c8-7a6a-4bf8-9b87-a72278bc600b |  | note | Responsibility-Supplier
label | 000b74a1-207b-4139-bd75-5039b571062a |  | note | Test
checkpoint-status |  |  | checkpoint | 1.2 Clay Index (passing 0.075 mm), or
label | ff03a9b5-3571-413c-86c2-6713f76ed1ae |  | note | Specification-Design
label | d5fb150f-ea96-4c19-ba5d-289d8932c07f |  | note | Method/Test-<=3 Unit of measure?
label | 3b32db25-9c5b-43ce-b1ea-64c0c306b1ad |  | note | Frequency-
label | 724d93a0-14ca-4bdb-8d4f-fd78aeb353eb |  | note | Records required-Test Report
label | d8445e9b-9252-427a-86ef-143667d3d120 |  | note | Responsibility-Supplier
label | 4f3cfde8-cce3-4f9c-8cc4-7ca46550f886 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.3 Plasticity Index
label | 87f2857c-9ffc-4e4f-ba15-11d9a6f9af37 |  | note | Specification-Design
label | 529147f8-ed9b-45c8-a990-d14fd2f492ee |  | note | Method/Test-
label | c45e6816-88d0-4c72-a691-f2d5f3aef517 |  | note | Frequency-
label | a05e9174-6b8e-42b5-867c-0c8990189f7a |  | note | Records required-Test Report
label | 5b48bd1c-302a-4410-845a-ee83cd90ef56 |  | note | Responsibility-Supplier
label | 62f8e0b5-2aed-4983-b83f-0853981736cb |  | note | Test
checkpoint-status |  |  | checkpoint | 1.4 Particle size distribution
label | d7cc3b67-02c6-4172-91cd-f37409d784d8 |  | note | Specification-Design
label | 703feaad-824b-43b7-9d9a-3bf8490da355 |  | note | Method/Test-100% passing 63mm
label | b46828fb-c9dc-4b36-92a0-c3a8977cc422 |  | note | 40% ≥ 65%passing 19mm
label | 19699dfe-5225-4016-971e-902032b192d0 |  | note | ≤ 10% passing 0.425mm425µm
label | ed54a2d0-6618-4e07-bfb3-322cfe067e80 |  | note | Frequency-1 sample per 250m3
label | 6c1121ab-c6cc-465a-be49-25ed3ccf6748 |  | note | Records required-Test Report
label | 7f07b34e-b825-4d9d-bc44-9e2ba18aeec7 |  | note | Responsibility-Supplier
label | 8d209516-2625-4ca5-8dd3-26d1cea614ab |  | note | Test
checkpoint-status |  |  | checkpoint | 1.5 Solid Density
label | 63e191cd-2981-4bfa-9969-bb744c0c2107 |  | note | Specification-NZTA B/2 7.5
label | cb372811-d274-4dec-b36f-dd8e91b6a51d |  | note | Method/Test-Unit of measure?
label | 2d47c54e-f462-469f-99c4-7e5154f59ac3 |  | note | Tolerance?
label | 53e2eba7-fe01-4670-874f-2aa4f3b6120b |  | note | Frequency-1 test
label | dabed77c-c15c-4e42-8869-772f1218eb2b |  | note | Records required-Test Report
label | 9e62e57b-78a5-440b-909a-c44bceffd7f6 |  | note | Responsibility-Supplier
label | 875cd9dd-a650-4d93-b69b-adf44dae2697 |  | note | Test
checkpoint-status |  |  | checkpoint | 1.6 Determination of MDD & OWC
label | 4c925a19-ab26-4c03-bf86-6ecf4326548b |  | note | Specification-NZTA B/2 7.5
label | fcd6730e-ddd2-4f75-b0d3-7a8d6fb9fb5b |  | note | Method/Test-Unit of measure?
label | a056d172-415a-4f2c-a187-55ee113fb190 |  | note | Tolerance?
label | c70949c9-17e0-4c8d-89ae-c9a14daf1be5 |  | note | Frequency-1 test
label | 2525ba14-757c-4401-b114-19267f2b9bcc |  | note | Records required-Test Report
label | d4258cbb-4235-4273-b46d-83f6abcf850b |  | note | Responsibility-Supplier
label | 019adfab-ea55-474f-b987-c2a0bbeced10 |  | note | Test
checkpoint-group |  |  | section | 2.0 Site set up
checkpoint-status |  |  | checkpoint | 2.1 Stakeholder notifications undertaken
label | 00c25bb7-dafd-444b-8545-d3f90ad3fef9 |  | note | Specification-CSCMP
label | a426abc0-6d80-4e05-ae9b-392766889019 |  | note | Method/Test-Stakeholder notification emails and letter drops
label | 2affabeb-8bbe-4844-9686-7ff13cce564a |  | note | Frequency-Each Site
label | 8b1fe7b0-803e-47b0-857b-06f21e365cbe |  | note | Records required- Evidence of Notice
label | 5abe4fca-a9a7-453c-8e42-c503203ed33f |  | note | Responsibility-Network Manager
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 2.2 Mark-out of services and Permits in place
label | 864be7d7-eb4d-458b-a3e9-740e13b48a17 |  | note | Specification-HSMP
label | bcd41091-dd3f-400b-b7f0-b8959aef8f65 |  | note | Method/Test-Physical mark-out of all services and signed permits
label | f39ad997-add9-45f8-b019-ef26919dba81 |  | note | Frequency-Each Site
label | 94116384-a2be-4a81-a8fd-8172f6080f85 |  | note | Records required- Signed permit
label | ba0df8ac-242b-459b-ac6f-46a68db2b7f4 |  | note | Responsibility-Renewals Engineer
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 2.3 Job start, identify risks and mitigations, communicate to team
label | 499cdb8e-dd39-452d-b977-4f3322fe5f11 |  | note | Specification-HSMP
label | 9c5fa163-c636-4946-9952-06da48baf877 |  | note | Method/Test-Record all hazards on JSEA and brief team
label | a03557bb-d35e-4c7c-ac70-8fde59c78d74 |  | note | Frequency-Each morning
label | 4f3fe63e-6e99-40e7-94fd-162d62143a67 |  | note | Records required-Job start form
label | 446bec72-f3e4-4099-91e9-97554e75de04 |  | note | Responsibility-Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 2.4 Set up traffic management to plan
label | 1fb6f0dc-8942-4952-a118-3d952503dfc7 |  | note | Specification-TMP
label | e1985bc1-18ed-40ce-96d9-478e557d475f |  | note | Method/Test-Perform Site audit post-set up
label | 8502a2e1-3827-405f-8cdf-9aad183097e0 |  | note | Frequency-Each site
label | 3d66347e-8caa-44fb-9918-1ff91cc5a18f |  | note | Records required-Daily Diary
label | 595419c7-5218-4bb4-90fe-031d044c4a77 |  | note | Responsibility-STMS
label | b7fd5474-80c5-4d7d-a67b-17012003bd1f |  | note | Test
checkpoint-status |  |  | checkpoint | 2.5 Assess environmental requirements of site and install sediment and erosion control measures if required
label | 340e6e58-4e08-4fd2-a303-ea7bc5a10094 |  | note | Specification-ESMP
label | 403deb99-7ee8-413e-88a8-45b78b81ea82 |  | note | Method/Test-Identify areas at risk and install control measures
label | 85256749-c7b4-4f73-b11a-e0416f1c266b |  | note | Frequency-Each site
label | 409448a8-f998-420d-b359-3265295eacc9 |  | note | Records required-Daily diary
label | e34ab358-467a-4575-b82b-0d6e4bdebba9 |  | note | Responsibility-Supervisor
label | de36fde1-8637-449c-8bc3-b77c9f338da1 |  | note | Inspection
checkpoint-group |  |  | section | 3.0 Sub-base Stabilization Inlay
checkpoint-status |  |  | checkpoint | 3.1 Cement Spread Rate
label | dea2faeb-445d-477e-8064-334e5c2db091 |  | note | Specification-NZTA B/6 7.3
label | fe3e4b71-90bc-4461-afbb-e7cbc2c34262 |  | note | Method/Test-±0.5kg/m2, Weigh mat
label | f39fb5ee-a5da-4211-bed2-f2f45bdc0895 |  | note | Frequency-Per run
label | d9c24715-0874-4f1c-b5ad-7251c7dcc4cd |  | note | Records required-Cement Sheet
label | 597a5be4-3694-4c31-8fe2-796e196affa1 |  | note | Responsibility-Stabilising Supervisor
label | eb69e4b0-7928-41d9-a876-00017a03903e |  | note | Test
checkpoint-status |  |  | checkpoint | 3.2 Hoe and stabilise to design depth
label | 6be778ad-f45e-44df-af1f-cd520e3c9452 |  | note | Specification-NZTA B/6 7.5.1
label | 17431ff3-f524-4317-8cad-50ba5040e1fa |  | note | Method/Test--0mm / +20mm
label | 3fe714a8-bf48-44fd-883a-a0032579f2f3 |  | note | Frequency-Per run
label | 60cd6fe9-52b7-4da8-a97a-e3db59852962 |  | note | Records required-Cement Sheet
label | 88a7f39a-8931-4ed8-844e-bf6ba8fb7465 |  | note | Responsibility-Stabilising Supervisor
label | da158585-083f-4e65-882b-213265679844 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 3.3 Overlap longitudinal joints
label | 38fcde37-3d44-49e8-a764-7151df0c3495 |  | note | Specification-NZTA B/6 7.5.2
label | 39e051cb-f6a1-4680-b630-03abfc1ec2ff |  | note | Method/Test-200mm overlap
label | ed1d66b7-c1bb-4af4-a079-74bc86ecea06 |  | note | Frequency-20m centres each side
label | ed316ffe-a269-44b1-90d8-db720a3a3a11 |  | note | Records required-Stringline Sheet
label | 7e20f909-0f22-4c00-b922-cb63842ffb22 |  | note | Responsibility-Stabilising Supervisor
label | 7eb8caa3-667e-4b6e-b7f9-b780fa3c861d |  | note | Inspection
checkpoint-status |  |  | checkpoint | 3.4 Plateau density test
label | a7f10b7d-6b51-4e04-ae86-1bba6aaa7b3b |  | note | Specification-NZTA B/6 7.6
label | dc8bd069-522b-466e-99fa-9e48a6138816 |  | note | Method/Test-Nuclear Densometer, Tolerance?
label | e9b75fde-2585-41f7-87aa-352c33b9840d |  | note | Frequency-20m alternating wheel tracks
label | 378ec9d1-2186-4c64-9d95-9c0160c6e820 |  | note | Records required-Plateau Density Sheet
label | 3fa37fcf-ea13-4583-bfb5-b84b1c487c0c |  | note | Responsibility-Quality Engineer
label | 3afa25dd-82b3-477b-b31d-57493d24be82 |  | note | Test
checkpoint-status |  |  | checkpoint | 3.5 Confirm layer thickness
label | aba58af2-60a2-47b2-994e-09be3be117c4 |  | note | Specification-NZTA B/6 8.2.2
label | fbb6a511-4d38-407a-8986-eeb6153bce43 |  | note | Method/Test--0mm / +20mm
label | ebfd2d6e-fb51-4e5e-8eb3-d6f497bd9d29 |  | note | Frequency-Every 20m, full width
label | 6cec47fa-f6f3-4c59-9529-fb31df432a9b |  | note | Records required-Stringline Sheet
label | 2ca432fb-4c30-46c4-ae80-0588cba90c7e |  | note | Responsibility-Rehab Manager
label | 1aab40be-a39d-41ae-a94d-c78853ce29f2 |  | note | Test
checkpoint-status |  |  | checkpoint | 3.6 Confirm surface levels
label | 61b582b0-8a6c-48f3-9629-1e0bc1ab1678 |  | note | Specification-NZTA B/6 8.2.2
label | 206fdfa5-3fc7-4136-8abe-835978a59c38 |  | note | Method/Test--5mm / +10mm
label | 608a6cb8-e4f0-4274-9678-56b4f6f22d7e |  | note | Frequency-Every 20m, full width
label | 785fce10-025a-4b6f-a76a-45320406358b |  | note | Records required-Stringline Sheet
label | cd95f8ba-3c0f-4049-9039-5cff9eb265b1 |  | note | Responsibility-Rehab Manager
label | e619e06f-f877-405d-87a8-9c583b4a31e7 |  | note | Test
checkpoint-status |  |  | checkpoint | 3.7 Compaction as per the results of the plateau density test/or
label | d5f26caa-99f1-4849-9c44-9c93d3548491 |  | note | Specification-NZTA B/6 7.5.2
label | 8fe6751c-c940-40fd-806f-87ecaa4b3356 |  | note | Method/Test-Mean ≥95%
label | c7df4e83-5229-4ee8-ba4b-dc23fcc4acdc |  | note | Minimum ≥92%
label | 61587688-f01d-41e4-ad77-1451dc622b2a |  | note | Frequency-Every 20m alternating wheel tracks
label | 1dda1a10-f5d7-446f-96b0-d4e9aef3594c |  | note | Records required-NDM Sheet
label | b7ae7273-1ef1-45b3-af17-718b37ca71b4 |  | note | Responsibility-Quality Engineer
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 3.8 Impact hammer test
label | 7d7669d8-eed9-4dbf-8d91-f026206ee604 |  | note | Specification-Spec?
label | ce553e00-0cb1-43e3-9753-7ab8720afc22 |  | note | Method/Test-≥70 CIV
label | 9974d53a-c29c-4fe0-9eee-7c48e85d01be |  | note | Frequency-Every 20m alternating wheel tracks
label | 15787486-76a6-4573-8343-557f333c8ad2 |  | note | Records required-Clegg Sheet
label | c5d58fae-20ea-43f1-b7ca-daafab4a1093 |  | note | Responsibility-Quality Engineer
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 4.0 Basecourse Overlay
checkpoint-status |  |  | checkpoint | 4.1 Cement Spread Rate
label | 8e26f642-c3b7-4c03-93a3-8b943b1feb46 |  | note | Specification-NZTA B/6 7.3
label | 2a381a13-2312-4b71-afaa-a2053951ef1a |  | note | Method/Test-±0.5kg/m2, Weigh mat
label | 113a4b37-4fd6-40c7-a024-e48151d0c274 |  | note | Frequency-Per run
label | 09beee82-e4f1-4781-a9b2-487ca0571ab9 |  | note | Records required-Cement Sheet
label | ada25f09-4832-4483-9b8c-f3cdd58bc217 |  | note | Responsibility-Stabilizing Supervisor
label | 7de073b3-8f14-4a59-8f95-2578abcd6cbe |  | note | Test
checkpoint-status |  |  | checkpoint | 4.2 Hoe and stabilise to design depth
label | 3b06f24e-2ffc-4f27-a010-7a22fa16010a |  | note | Specification-NZTA B/6 7.5.1
label | 8d85d383-fda0-4917-a70b-03bcb5a37893 |  | note | Method/Test--0mm / +20mm
label | 654f0771-6952-4c31-8da2-9e167abd134d |  | note | Record hoe-depth setting
label | 5a769f6a-0153-4436-a2ee-3a25dcbb1b40 |  | note | Frequency-Per run
label | 9377338c-6b9d-4942-a601-81e32b283b74 |  | note | Records required-Cement Sheet
label | 9a465a81-c3b2-46a0-80dd-682f47daf661 |  | note | Responsibility-Stabilizing Supervisor
label | b652b84a-9080-4e64-8f58-95f6793c9e95 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 4.3 Overlap longitudinal joints
label | 7057842f-ecd2-4342-8a8b-a62a40fbbd47 |  | note | Specification-NZTA B/6 7.5.2
label | 175e40c2-b26e-45ae-9a01-1d442ff9f2ce |  | note | Method/Test-200mm overlap
label | 891a8323-8bec-4fd6-9707-e1f5b6872229 |  | note | Frequency-20m centres each side
label | a4917e42-0d9c-425d-9730-e3f92e131e4d |  | note | Records required-Stringline Sheet
label | 5601752e-014a-4c0a-b632-bc6bdbf91222 |  | note | Responsibility-Stabilizing Supervisor
label | 36c09b7e-2d2c-46c2-bb28-f54c9b3b9ed3 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 4.4 Plateau density test
label | e3cbdb6d-2173-4b4a-92a5-bdb2ae1708ef |  | note | Specification-NZTA B/6 7.6
label | b9cc7fbc-448f-4771-a2e1-e5adaa6c899f |  | note | Method/Test-Nuclear Densometer
label | df5f8d6a-7d88-4b39-b5e1-d6a9c683b184 |  | note | Tolerance?
label | 0521a3cf-94fd-4649-93dd-3a3ce10c074f |  | note | Frequency-20m alternating wheel tracks
label | 3de1c3a9-22ca-4967-89e7-04da6e3171d3 |  | note | Records required-Plateau Density Sheet
label | 07a3a7d6-20bc-4515-a595-d99f3da2f9f6 |  | note | Responsibility-Quality Engineer
label | 13c623e2-2907-4dd4-a68a-e5bb009036a6 |  | note | Test
checkpoint-status |  |  | checkpoint | 4.5 Confirm layer thickness
label | c011eed0-5f12-4045-bd8d-778d5e71a9d8 |  | note | Specification-NZTA B/6 8.2.2
label | cdf339b3-3888-482c-975d-216b394cb1f8 |  | note | Method/Test--0mm / +20mm
label | ff185702-80ea-4381-9aea-0e27f225c1ef |  | note | Frequency-Every 20m, full width
label | 7b239ed0-0243-4cc3-8cd6-59cabfdb777c |  | note | Records required-Stringline Sheet
label | dfe1ca17-0473-49b9-8f61-895432110215 |  | note | Responsibility-Rehab Manager
label | e986a38d-4ecc-47df-81ee-f25696f3968f |  | note | Test
checkpoint-status |  |  | checkpoint | 4.6 Compaction as per sample test results
label | 08b7211e-7cd7-42f1-920f-3fcc4758ea7d |  | note | Specification-NZTA B/6 7.5.2
label | 23f45ae0-34e8-4b0d-925a-ecc7b1b5f895 |  | note | Method/Test-Mean ≥95%
label | 31bef1a1-86c0-48d2-ac9c-d75c56709ea7 |  | note | Minimum ≥92%
label | 3b7e3d73-7f88-4389-8146-d2e1f11bd17e |  | note | Frequency-Every 20m alternating wheel tracks
label | 1ac8cf20-44cf-4e71-9ca7-298cdaf9a6ca |  | note | Records required-NDM Sheet
label | 289c25b5-3ea6-4f70-8c5e-27b2e9b0fe3f |  | note | Responsibility-IANZ Accredited Lab
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 4.7 Impact hammer test
label | 33f70467-596a-4e67-879a-faec5aefc72e |  | note | Specification-Spec?
label | 7b5156a2-c2f5-41d8-b853-1bcb7fcdb8b2 |  | note | Method/Test-≥70 CIV
label | 63f3146b-6818-447a-b5ce-21258f7692c3 |  | note | Frequency-Every 20m alternating wheel tracks
label | 47d7187f-c35c-4e60-a3cc-63f542a1e07c |  | note | Records required-Clegg Sheet
label | 662711e5-63f4-4364-8018-95230ba21a68 |  | note | Responsibility-IANZ Accredited Lab
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 4.8 Confirm surface levels
label | 5e0ab3fb-fac2-40f4-af89-af9320c59d95 |  | note | Specification-NZTA B/2 5.1
label | 6c3397c4-554e-4b6c-bac6-2f09cf3fce05 |  | note | Method/Test--5mm / +15mm
label | 612c983f-d9fd-4151-866c-af8705186054 |  | note | Frequency-Every 20m, full width
label | c0b86d69-911a-4fda-921d-90253dc235dd |  | note | Records required-Stringline Sheet
label | 7cfe10af-d491-49d4-8a5c-f31a57cb124f |  | note | Responsibility-Rehab Manager
label | ae67dca9-0809-4200-9f3c-93de533982b1 |  | note | Test
checkpoint-status |  |  | checkpoint | 4.9 Surface Finish
label | 4def77de-988a-4d5c-9dd0-eacd74ee21b7 |  | note | Specification-NZTA B/2
label | ed09f0ad-e155-496e-9a92-4dfa258a7450 |  | note | Method/Test-Sealing Supervisor to inspect
label | ad901dce-0cb4-4a3d-9771-f7057ccb31a4 |  | note | Frequency-Per site
label | 852fb676-51ad-4cfd-b30d-0ce75a37c146 |  | note | Records required-
label | 96f67ea6-0207-4642-83ae-513f6e7ee3c6 |  | note | Responsibility-Sealing Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | 5.0 Aggregate Testing – Sealing Chip
checkpoint-status |  |  | checkpoint | 5.1 Crushing Strength
label | 6ae55fa1-be16-4b86-b2fd-7593f2afb60b |  | note | Specification-NZTA M/6 3.2
label | f7f8f778-887d-496b-a32c-3ef1a6393c2b |  | note | Method/Test-<10% fines passing 2.36mm under 230 KN load
label | e1769cf6-3e10-43da-88dc-aab23d62d42c |  | note | Frequency-1 Test
label | 96eda512-cd3b-46f6-9742-5fede5ea69e9 |  | note | Records required-Test Report
label | f489919f-452b-435e-94e7-9318a24140a9 |  | note | Responsibility-IANZ accredited laboratory
label | 9a17ef3a-7e9b-4f68-8a68-5a9eafc93b63 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.2 Weathering Quality
label | 944dfcab-7f6d-4fed-91d4-36cf963ebd55 |  | note | Specification-NZTA M/6 3.3
label | 480f9f0c-2bbf-411d-aadf-930152e6b155 |  | note | Method/Test-AA or BA
label | f89cb9bf-0eaa-4adf-9b4a-d3f22e1be4bd |  | note | Frequency-1 Test
label | 2ee72545-82b8-4144-a1a9-bda9b3c9a6ef |  | note | Records required-Test Report
label | 7981dd1f-20fb-46a5-b770-99e0063482c8 |  | note | Responsibility-IANZ accredited laboratory
label | 69c2a134-23ca-4231-a92f-a2681c330ede |  | note | Test
checkpoint-status |  |  | checkpoint | 5.3 Polished Stone Value
label | 9982123c-4edf-4f8b-a31f-d25eb6849f10 |  | note | Specification-NZTA M/6 3.5
label | a888ff91-a9a5-4ad7-b4ca-8468435de0b4 |  | note | Method/Test-PSV Required = 52 min
label | 70dc2ea4-4dcf-4689-af84-e4a1489d30dd |  | note | Frequency-1 Test
label | 2e213546-f656-42c5-b5a9-8073a6e7bce8 |  | note | Records required-Test Report
label | d70bae98-df7b-4592-b0b8-bf97425f54c7 |  | note | Responsibility-Accredited PSV Testing Agency
label | fe3021f9-c177-44ee-9ba8-b32f0b3a8829 |  | note | Test
checkpoint-status |  |  | checkpoint | 5.4 Cleanliness
label | a4177e02-b2b0-43be-95ba-5f63a7e1452a |  | note | Specification-NZTA M/6 4.1.1
label | 206191a9-eec5-4179-8044-6cefb82cd808 |  | note | Method/Test-Grade 5 – 89 min Grade 3 – 87 min Grade 4 – 85 min
label | 2c77e0ac-d18a-47c0-87ca-8fd133ea4568 |  | note | Frequency-1 Test
label | 8b997650-7701-46ed-adcf-6cab500061a4 |  | note | Records required-Test Report
label | f6f3ab21-6171-4d61-9267-1e9b5a454da1 |  | note | Responsibility-IANZ accredited laboratory
label | 00296ef0-4519-4828-90e9-cabc25e7066d |  | note | Test
checkpoint-status |  |  | checkpoint | 5.5 Grading
label | 9dce2b6b-e4ef-436d-b8fc-4669ee90a5a1 |  | note | Specification-NZTA M/6 4.2.1
label | 78f6c7b3-b54d-4117-ac3f-4a361a077371 |  | note | Method/Test-See NZTA M/6 4.2.1
label | 41aead7a-01c3-4c24-a54f-298f7577d141 |  | note | Frequency-1 Test
label | 3ada0414-5353-4033-b1da-1ac52def3fee |  | note | Records required-Test Report
label | a5ea8152-9783-432d-b13d-5982586bb387 |  | note | Responsibility-IANZ accredited laboratory
label | a30e651c-d36f-41ce-9a58-0a853456c472 |  | note | Test
checkpoint-group |  |  | section | 6.0 Chipseal Control
checkpoint-status |  |  | checkpoint | 6.1 Confirm viscosity of bitumen
label | c11bac5a-747a-4c4d-a8e5-f94d9b337b34 |  | note | Specification-NZTA M/1 Table 1
label | e525325b-c113-4e4a-8545-e5fb05b898a3 |  | note | Method/Test-Viscosity PaS at 60°C
label | 5a6f9e1f-2b96-4dc6-8c2f-bbb1aea65697 |  | note | Frequency-1 Test
label | 2d17277e-0780-4a4f-a05d-437d215ab98d |  | note | Records required-Construction
label | e3c6c9b0-85f1-4a0f-8dad-a5e241cf39ca |  | note | Responsibility-IANZ accredited laboratory
label | a4b8f656-bb00-46ad-99c3-64201666f9ac |  | note | Test
checkpoint-status |  |  | checkpoint | 6.2 Confirm penetration grade of bitumen
label | c0b6cb41-ecbf-44f9-bd19-1818e417d811 |  | note | Specification-NZTA M/1 Table 1
label | 5e38abd5-d4cb-4cbd-81e2-32abffdebad5 |  | note | Method/Test-Penetration at 25°C,100g, five seconds
label | 8d080db4-4c2d-4180-8ce3-bb5156fe027d |  | note | Frequency-1 Test
label | 0fc7178e-a166-46de-b417-f252ed0c0510 |  | note | Records required-Construction
label | 16406e49-a7b1-493d-b296-ba8fcee57def |  | note | Responsibility-IANZ accredited laboratory
label | 30c540fd-654b-4230-ada4-1d0051fd029b |  | note | Test
checkpoint-status |  |  | checkpoint | 6.3 Spray bitumen, then place chip *and roll – refer design for chipseal grade
label | 19ec835d-9fe6-41b9-9572-3609e9fd978b |  | note | Specification-Design
label | 0f2066ab-014a-4cdf-9e52-84db565b2a3e |  | note | Method/Test-Visual check
label | 3748220a-dc2a-480c-a5b3-b8b039e82bbe |  | note | Frequency-1 Test
label | 17317a84-9df0-49a8-b598-2547f6755f7e |  | note | Records required-Following construction of chipseal
label | 7c627a58-0098-4d64-896a-45b6e6ad3805 |  | note | Responsibility-Sealing Supervisor
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 6.4 Check for excessive “windows”
checkpoint-group |  |  | section | 7.0 Site Close-out
checkpoint-status |  |  | checkpoint | 7.1 Field Quality Review
label | cb83c72c-fafb-48a6-9059-1aa2026c93f1 |  | note | Specification-QMP
label | a25011bc-d9c3-4eff-bd31-f7df68200ab1 |  | note | Method/Test-Verification of Work Standards
label | 1f046bd8-a093-4c0a-8694-9e7460986ce4 |  | note | Frequency-10% of sites
label | 1234a075-f2b6-412b-9e15-bc1e8911df3c |  | note | Records required-Record in Audit Field of RAMM Contractor
label | 394c5f4b-6a5f-4cef-a913-7f1b13f1c53c |  | note | Responsibility-Supervisor
label | 8cf6c669-645c-44fe-8a80-3dc40789f645 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 7.2 Collect RAMM Data
label | 76bf386c-ccf1-4d60-a63b-28936619b0ad |  | note | Specification-SHDOM / Data Quality Plan
label | 4f1d5170-e1bc-45ab-9919-db38339aa3be |  | note | Method/Test-L1 Accredited Personnel
label | 4d893396-65f4-4f36-a931-f11bf098895b |  | note | Frequency-All Jobs
label | 91bde56c-83e0-437b-99d5-b1ec9b088f0b |  | note | Records required-SHDOM Specs
label | 5bdc90d3-3c58-4c0f-b75e-fe156aeaf75c |  | note | Responsibility-Foreman/ Supervisor
label | 6c186612-6f15-4cd4-9702-bc89ac776597 |  | note | Inspection
checkpoint-status |  |  | checkpoint | 7.3 Verify RAMM Data
label | 26aff93e-b9db-419c-850f-2ea7d0308928 |  | note | Specification-SHDOM / Data Quality Plan
label | 189f1df5-51b3-4281-b6e8-c3c55aa4fa6e |  | note | Method/Test-Level 2 Accredited Personnel
label | 19f57cdc-55e5-44e8-94fa-cbbeaa575807 |  | note | Frequency-All Jobs
label | 6aff43ea-227f-41e2-8c74-043104a24d27 |  | note | Records required-SHDOM Specs
label | c2c2082e-e3a6-4945-9898-54ce445b6218 |  | note | Responsibility-RAMM Manager
label | aa9839bd-f50d-48d3-b15d-e047d3bed2e5 |  | note | Inspection
checklist-sectioned |  |  | checklist | Structural AC - SP20 |  |  |  |  | Yes | Structural AC - SP20 | fb973a12-6054-44f2-8c00-331e64f217cb
checkpoint-group |  |  | section | Production
checkpoint-status |  |  | checkpoint | 2.1 Source Property Test
label | 0943b007-cf0d-451a-ab4a-5313b7dd8d14 |  | note | Controlling Docs-NZTA M/10:2014
label | 905cce84-4743-459c-a2d6-cd6cfc8f138d |  | note | Test Method and Acceptance Criteria-Crushing Resistance - >/200kN; Weathering Quality Index - AA or BA
label | beac0855-4a2d-4f37-9850-4f809ade58f6 |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | e1dedfc8-52b0-4090-a959-a37815aad25e |  | note | Responsible Person-Higgins Project Manager
label | ac607110-b4d9-4723-ba6a-1e4a612c9289 |  | note | Verifying document-IANZ Report
label | 9b9f7d64-4263-4989-9673-864d10dff8ec |  | note | Inspection/Test
label | 5aa60607-3e9f-465c-894e-4dc45b9404f7 |  | note | Conduct-Higgins
label | 0ff89393-7e9a-4379-b269-5d55e897b034 |  | note | Witness-NZTA
label | 1c181396-9311-4be9-ba8a-663d238e1f66 |  | note | Produce Record-S
label | dc93ef8d-458e-4175-83b7-5eb6b72b2321 |  | note | Approve-NZTA
label | ed8e4696-676d-4e21-9660-bd59bd33c616 |  | note | Witness
checkpoint-status |  |  | checkpoint | 2.2 Production Property Test
label | 6b74c36f-a3b2-4620-b3db-5f017a0ba0bb |  | note | Controlling Docs-NZTA M/10:2014
label | e5c2a1c5-dc54-4a77-a8bc-5750a7c1ed9a |  | note | Test Method and Acceptance Criteria-Broken Faces - 98% min - Single Broken Faces, 60% min - Two Broken Faces
label | 6feacdef-0fe0-4d7c-aa34-9776c29104c0 |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier
label | d200e3ce-085d-4908-af56-55366f562fd1 |  | note | Responsible Person-Higgins Project Manager
label | ac3ece2f-1abc-49d8-937b-704c6d3cf824 |  | note | Verifying document-IANZ Report
label | 8a09f3be-df03-460f-a1a1-2719208eb696 |  | note | Inspection/Test
label | 4e3b6588-ad72-4490-b712-fa03fbe90a6a |  | note | Conduct-Higgins
label | 013b92cf-65fe-4898-a10f-7a47eea8e125 |  | note | Witness-NZTA
label | 11e8f718-db73-4db3-83fc-902e43681584 |  | note | Produce Record-S
label | 3725da0f-93d4-48cd-9045-70de810dcbf6 |  | note | Approve-NZTA
label | b27ad5bc-0a85-498c-92d7-b88cf0a5e40f |  | note | Witness
checkpoint-status |  |  | checkpoint | 2.3 Source Property Test
label | ef2ebe01-98fd-4d6c-9820-4e567b4e042a |  | note | Controlling Docs-NZTA M/10:2014
label | 58f2f217-4669-4799-a81e-c37c92870c70 |  | note | Test Method and Acceptance Criteria-Crushing Resistance - >/200kN;
label | d1dfa1d6-1465-43b1-9526-52fea973ab4b |  | note | Frequency-1/10,000m3 or 1 per annum whichever is earlier;
label | 96e8ff9d-80f2-4824-8662-878f37238ba9 |  | note | Responsible Person-Higgins Project Manager
label | 7865453b-7f33-4757-a657-7113bd50752d |  | note | Verifying document-IANZ Report
label | 20b048ee-31da-45b5-a48a-c0f4f6c2ebc7 |  | note | Inspection/Test
label | 912cbd9c-1523-4652-ace2-1a9f4c2e172e |  | note | Conduct-Higgins
label | bd432f59-bf11-48b8-822c-0e137522295a |  | note | Witness-NZTA
label | 6da0c9b3-b769-48fa-a9d1-8a584aedc20d |  | note | Produce Record-Higgins
label | 57777d37-07e4-4bb2-bd61-1703544de826 |  | note | Approve-NZTA
label | e96d3742-9817-427c-beea-ff6b59a7b9d7 |  | note | Witness
checkpoint-status |  |  | checkpoint | 2.4 Production Property Test
label | aa9219df-2564-4cd2-b34f-62d1bc58b8ef |  | note | Controlling Docs-NZTA M/10:2014
label | eebf614f-33c5-4024-8b45-7b5c3a33b8eb |  | note | Test Method and Acceptance Criteria-Sand Equivalent - 25 min; Clay Index - 3 max; Water Absorption - Report Value; Degradation factor - Report Value
label | 43076698-ebcc-4e68-a18c-541824ea0b0f |  | note | Frequency-1/1,000m3; Representative test values of the aggregates to be used in the Contract
label | 8b5e15b3-2ad3-4f9e-813e-f0d1e04cdf65 |  | note | Responsible Person-Higgins Project Manager
label | 8e1fa5e1-6327-4a29-a97b-08fb22db50f6 |  | note | Verifying document-IANZ Report
label | c4852f04-9bdf-4b8a-b3cc-bce2617312b2 |  | note | Inspection/Test
label | 03ee5211-6f38-460f-b64a-4e2c9729d578 |  | note | Conduct-Higgins
label | 6d6ff713-352f-40d9-80b7-9a4da18ce18f |  | note | Witness-NZTA
label | 6efb622c-82ef-4b84-8fd3-a3a94166021d |  | note | Produce Record-Higgins
label | 7cbe6610-2f49-409e-98b8-3d12377dfbb5 |  | note | Approve-NZTA
label | 32c20c98-ea48-402a-bfa8-69933d5de0bb |  | note | Witness
checkpoint-status |  |  | checkpoint | 2.5 Bitumen Binder
label | 5ea53752-9df5-4327-b2b2-1c129d79bdda |  | note | Controlling Docs-TNZ M/1:2011
label | 53b7e7a3-3943-462e-beec-31cb392ac610 |  | note | Test Method and Acceptance Criteria-Standard Penetration Grades - Table 1
label | 44b256c6-ddcd-49bf-9741-7774bdc3de97 |  | note | Frequency-Approvals are for a period of 5 years
label | 28be69f3-985b-4aaa-b817-6ffd83ddde8f |  | note | Responsible Person-Bitumen Supplier/ Operations Manager
label | c11f7394-120e-4a2d-844f-8a8786f30ca6 |  | note | Verifying document-IANZ Report
label | 8abfb5cd-92a7-417a-ba34-2fb10e199b94 |  | note | Inspection/Test
label | 5b98d698-7078-4444-a140-e17828e08335 |  | note | Conduct-Higgins
label | fa5f1bf2-204e-4f76-8a1c-8e27f4aa14b6 |  | note | Witness-NZTA
label | df16bfcf-1e27-421b-8c7e-1d7529c8cf4f |  | note | Produce Record-Higgins
label | d81566a6-f046-441a-a997-dea4d0c3f76e |  | note | Approve-NZTA
label | e58722d8-0880-47ea-b26f-63dc28ff9580 |  | note | Witness
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 3.1 Asphalt - Production Test
label | d2ac471b-edf2-4f21-aba0-c12408127535 |  | note | Controlling Docs-NZTA M/10:2014
label | 5c9153f7-f589-4899-a08b-ec85dea99702 |  | note | Test Method and Acceptance Criteria-Particle size distribution - Compliance with the approved JMF applying Table 5.3 Production Tolerances for AC and DG grades; Binder content Individual test +/- 0.5% Rolling Mean of three +/- 0.3%; Max specific gravity - Report Value
label | ce012379-37e5-4de9-8381-27769307a692 |  | note | Frequency-1/300t. 3 samples max per lot
label | 106af749-6146-477c-a7a4-fabd81cc0f74 |  | note | Responsible Person-Higgins Project Manager
label | 88f87f98-8cb0-4cdc-bdc4-bf96c6ef2d8a |  | note | Verifying document-Prelim followed by IANZ Report
label | ec17373f-fcc8-44a8-8e56-cdd8fd376143 |  | note | Inspection/Test
label | 8ef1d712-b164-4a69-ae67-d09a8278330c |  | note | Conduct-Higgins
label | b729bded-2268-469a-a883-7436ca34d730 |  | note | Witness-NZTA
label | 06cd397a-1064-4f41-9d88-0600f66a6173 |  | note | Produce Record-Higgins
label | 3f1a2f70-6276-45d3-a510-3ba75482c4b0 |  | note | Approve-NZTA
label | e38ee013-756f-41c7-b038-6f018b9301a6 |  | note | Witness
checkpoint-status |  |  | checkpoint | 3.2 Ensure setting out is in place.
label | 1b74b4f8-ce25-47ca-9fec-19c9ebc65da1 |  | note | Controlling Docs-Latest drawings/ set out data
label | 73a0db47-2c35-4f6f-99e1-0efeb556cef9 |  | note | Test Method and Acceptance Criteria-Visual
label | e31ebcf8-fcfc-4d14-9832-eda5a27ee3ef |  | note | Frequency-Prior to starting paving
label | b2e09f6d-f6a8-480a-84e3-252687c9dc00 |  | note | Responsible Person-Higgins Project Manager
label | 86789317-b1cd-48c9-b2d4-95a0f4e66489 |  | note | Verifying document-NA
label | db856d0a-00d3-45be-abad-c5e245267abb |  | note | Inspection/Test
label | c96f1ca0-9f02-4f48-bba0-46cb40f64dfa |  | note | Conduct-Higgins
label | 5d4b35db-9bb6-4eea-80a0-1e4096ae576a |  | note | Witness-NZTA
label | e5db4f14-0aaf-4411-965b-d9451c604d8a |  | note | Produce Record-Higgins
label | 1d36afaa-bb4d-4a7d-8226-3c54d7b5b105 |  | note | Approve-NZTA
label | 7f11c8f8-293e-4548-b0e1-5b2c24925ab1 |  | note | Witness
checkpoint-status |  |  | checkpoint | 3.3 Ensure previous layer is signed off and broomed clean
label | 6d85805e-82c6-4075-9e72-8609ee3af875 |  | note | Controlling Docs-
label | 1035c143-7322-4936-b71b-97603e8c337d |  | note | Test Method and Acceptance Criteria-See subgrade/subbase/ base course ITP
label | f7562c89-699e-4497-a0b7-0c25169fd144 |  | note | Frequency-Prior to SP20 Asphalt Layer - Sign off meeting
label | 12604ce1-0743-45a4-a9db-2f274907e895 |  | note | Responsible Person-Higgins Project Manager
label | 97d6bf4b-e5aa-4963-9ba7-c40e03ae1d9b |  | note | Verifying document-Higgins Sign off sheet
label | cbe8342d-5abc-4d96-86ef-fe110436e7b0 |  | note | Inspection/Test
label | e4e3359a-bada-4adf-b204-74cbf90e90ce |  | note | Conduct-Higgins
label | d97ccbe0-811b-4675-9f92-0f07eff34a11 |  | note | Witness-NZTA
label | 2197a103-f933-498c-9e6e-3fb61c966c4f |  | note | Produce Record-Higgins
label | bc72461e-8515-41e0-9e09-34497682e11c |  | note | Approve-NZTA
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 3.4 Site extents to be marked
label | ea0b34db-a064-47c1-8178-62370fac4ab4 |  | note | Controlling Docs-Latest drawings/ set out data
label | 41a6f1e5-50a4-42e7-8826-68f6f83db855 |  | note | Test Method and Acceptance Criteria-Ensure site extent is marked out
label | ce543f09-dbbf-4783-b596-35a7ebf3a1b6 |  | note | Frequency-Prior to placing asphalt
label | f88165f9-b4a1-4db3-8055-9a15c02aac5c |  | note | Responsible Person-Supervisor/Noc
label | 231dda16-6e94-4415-b101-8f5f16d932cc |  | note | Verifying document-Visual
label | 5c9a9be7-2166-45b8-9aa2-55436d96e2b3 |  | note | Inspection/Test
label | 95dfe2d6-be34-48ca-9768-6d417c2c241f |  | note | Conduct-Higgins
label | 69a56663-81b7-46ab-a748-70e6d62f9bb2 |  | note | Witness-NA
label | c317ce6f-ea69-4ccd-962c-f968246c3881 |  | note | Produce Record-Higgins
label | 72e37465-8b27-4996-bce7-c59231ee8d6a |  | note | Approve-NA
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 3.5 Gr5 chipseal membrane on CRS-2 emulsion
label | 369ffadb-2b14-4993-8b30-2e91f44d10a7 |  | note | Controlling Docs-
label | 52890155-93d6-4fce-86fa-a7d4ebbbc37f |  | note | Test Method and Acceptance Criteria-Sprayer truck - 0.5l/m2 residual rate
label | ee555552-cc54-4d79-b7ea-073078d1d3a5 |  | note | Frequency-Prior to SP20 Asphalt Layer - Sign off meeting
label | 0bde81e9-360e-4772-8950-f4b242bf528e |  | note | Responsible Person-Supervisor/Noc
label | 26807c34-7d6a-44ba-930d-886301c63f11 |  | note | Verifying document-Record Sheet
label | abda3452-5ac0-4749-96f8-89334deaa402 |  | note | Inspection/Test
label | c9d1fb53-24a0-4524-8145-933631739086 |  | note | Conduct-Higgins
label | 44b54bb5-c92a-4dc7-9c57-b27afa62324f |  | note | Witness-NA
label | ebbf3d67-a9ed-437c-a7b2-74559f0e5c9b |  | note | Produce Record-Higgins
label | d489ccf7-3af6-4269-babc-877f267743e0 |  | note | Approve-NA
label | f5c3f0f6-a835-4036-9e82-e7fa1751b45e |  | note | Witness
checkpoint-status |  |  | checkpoint | 3.6 Air Voids
label | e90d9a42-e25b-4466-86d6-a0085b2cd0c5 |  | note | Controlling Docs-NZTA M/10:2014
label | 96c9b1ea-d335-48a7-b284-27295731a993 |  | note | Test Method and Acceptance Criteria-Cores + Higgins spread rate form - For Mat - JMF Design AV -2% + 3%; For Joint - JMF Design AV -2% +3%
label | fbf5f30f-2df6-4b13-8141-ea93a4964164 |  | note | Frequency-1/3000m2 with minimum of 3 cores/lot
label | ca281f48-d7ba-4218-bf6e-b30db709b695 |  | note | Responsible Person-Site QA
label | 5cd9f7db-fe98-4de6-9418-5a3067d27e72 |  | note | Verifying document-Prelim followed by IANZ Report
label | 14151185-9391-4e1c-913a-34ec53b76cdd |  | note | Inspection/Test
label | 84aeeab6-85b8-40b4-9683-5ed5621fa9ba |  | note | Conduct-Higgins
label | ceac72ba-e4bd-45ae-8e1b-6aae8bf29b89 |  | note | Witness-NZTA
label | 4ab06af2-fde3-4e48-9b2f-230e977dc2db |  | note | Produce Record-Higgins
label | aee23dae-1077-4f62-801c-ffbe305b0e5d |  | note | Approve-NZTA
label | 5f41c5c3-2d01-43e4-b977-d902cc5c8b40 |  | note | Witness
checkpoint-status |  |  | checkpoint | 3.7 Layer thickness
label | 476daa99-bf69-4f94-9cae-09c29dc526bc |  | note | Controlling Docs-Higgins Methodology (not: in line with TNZ M/10:2014 clause 10.3)
label | 7ae77c22-da41-4d72-a238-86197d8bcdd7 |  | note | Test Method and Acceptance Criteria-Cores + Higgins spread rate form - Total 140mm (2x70mm layers) average >/-90% of specified thickness
label | 8a9a6ae0-5e2b-4d30-bb79-91714f95a11f |  | note | Frequency-1/100mm of joint with minimum of 3 cores/lot
label | ff063bed-04f6-4cd5-9bcf-9778e23fd355 |  | note | Responsible Person-Site QA
label | 392c926a-e65a-4d07-b57a-5e12bcc55bb1 |  | note | Verifying document-Prelim followed by IANZ Report
label | c0fbb42e-5486-45cb-9431-e5b276ec86b7 |  | note | Inspection/Test
label | f11b649c-86df-4995-9299-881a79bf5533 |  | note | Conduct-Higgins
label | b797e8f8-c3bf-42d5-b274-bbb6afce5e19 |  | note | Witness-NZTA
label | 5cd49884-adca-4ea1-915f-3cce56f728ee |  | note | Produce Record-Higgins
label | 4851555f-93ee-4936-be8c-9e652d76a3e9 |  | note | Approve-NZTA
label | 061d7837-50c2-4cec-9ba5-db2d5c962fa8 |  | note | Witness
checkpoint-status |  |  | checkpoint | 3.8 Surface shape
label | 9f94301e-1f42-46cf-89b1-7d7a14dae826 |  | note | Controlling Docs-NZTA M/10:2014 9.7
label | 7334936e-d9f2-4b00-808d-6193a945e597 |  | note | Test Method and Acceptance Criteria-3m straight edge - Surface shape
label | 666f529c-a5f6-420f-b574-31d4122a84c8 |  | note | Frequency-1/20m - no more than 5 mm under straight edge longitudinally and transversely
label | 30d2b82e-ad5e-43ec-a5c6-10738795aeb0 |  | note | Responsible Person-Site QA
label | ef583492-13da-41cc-a8fd-5ca44eb93baa |  | note | Verifying document-Record Sheet
label | cdf9d8bc-adae-401d-85ca-205cb26d8526 |  | note | Inspection/Test
label | 1c7f44c7-13b3-498c-9969-0d996530aed2 |  | note | Conduct-Higgins
label | 12765aa7-0f44-4cc9-9ec0-8e2efc25750a |  | note | Witness-NZTA
label | 4ec39907-3b93-4ec3-bc38-879c1ed587e7 |  | note | Produce Record-Higgins
label | a0062552-1165-4ca1-af22-a1d0b888b773 |  | note | Approve-NZTA
holdpoint |  |  | signoff | Hold point
checkpoint-status |  |  | checkpoint | 3.8 Level - String line check
label | 1d9351c2-4c67-49c7-a796-11baf28ae7bb |  | note | Controlling Docs-NZTA M/10:2014
label | 194dd76a-7495-46cf-ba40-70240fb1e6b2 |  | note | Test Method and Acceptance Criteria-Each 20m cross-section with a minimum of two readings per lane - Surface shape
label | e58474f3-043b-4add-a8d4-70f83811e928 |  | note | Frequency-Tolerance on each layer +/-10mm
label | 2a30e6a9-e89f-4b6e-812e-5a3433380567 |  | note | Responsible Person-Site QA
label | 15e739f2-14b5-4c4c-a27a-b421ea916087 |  | note | Verifying document-Record Sheet
label | 7c1e43dc-cbbd-491e-b266-773d05a72505 |  | note | Inspection/Test
label | 3848e783-8c68-4ac6-b619-63a18cfbda74 |  | note | Conduct-Higgins
label | f9ff3c1f-f784-4bb5-85b4-bdaae77fa553 |  | note | Witness-NZTA
label | dfa787f1-3c13-4966-87b8-5ecab9f7862c |  | note | Produce Record-Higgins
label | e1a84d6a-754f-4adc-a78f-9e5887400023 |  | note | Approve-NZTA
holdpoint |  |  | signoff | Hold point