## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Sub-base Construction (Carriageway) - AP65/AP75 |  |  |  |  | Yes | Sub-base Construction (Carriageway) - AP65/AP75 | 06565598-5f16-4eee-866c-2006dce093a4
checkpoint-status |  |  | checkpoint | Location
text | 512a687e-e021-5d03-ba63-c1ba75dcaf6e |  | textbox | Location Details - Chainage
checkpoint-status |  |  | checkpoint | Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Straight Edge
checkpoint-status |  |  | checkpoint | Proof Roll
checkpoint-status |  |  | checkpoint | Nuclear Density Meter
checkpoint-status |  |  | checkpoint | Scala
checkpoint-status |  |  | checkpoint | Undercut / Fill
checkpoint-status |  |  | checkpoint | Light Weight Deflectometer
checkpoint-status |  |  | checkpoint | Falling Weight Deflectometer
checkpoint-status |  |  | checkpoint | Benkelman Beam
checkpoint-status |  |  | checkpoint | Additional Information
text | 7654237c-e37b-5a79-ba06-55d8d93c4088 |  | textbox | Additional Information
checklist-sectioned |  |  | checklist | ITP 004 - Construct AP75/ AP65 Sub Base |  |  |  |  | Yes | ITP 004 - Construct AP75/ AP65 Sub Base | 0ecc084f-e449-4b48-b9bb-c172562d9bcc
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | AP75/ AP65 - Sub Base
label | a348485b-4e80-533c-9a79-15390eae6894 |  | note | Reference: Signed Contract - Volume 1
label | a4da19d7-8d49-506d-9a28-fba0e3f42cc1 |  | note | Section 6 - Employers Requirements
label | bbef8b5f-ca77-50fb-8a3e-0c3822f2556e |  | note | Section 300 - Pavement Construction
label | 5d2e1f61-7f47-5133-ade7-ed9d4648cbc3 |  | note | Section 6 - Employers Requirements
label | 59b3e8d1-51e0-521b-9302-e82e337e7586 |  | note | Fiji Roads Authority
label | 7318088b-4122-5807-a1f0-c05879f44ee5 |  | note | Section 301 - Materials for Pavement Construction
label | 44677862-72f7-508c-9202-dfc370a434f1 |  | note | Requirement: AP40 with reduced fines to comply with the specification requirement as per below
label | 248c8fd5-e36e-5a73-92f0-f6d41911b9ae |  | note | Particle Size Distribution - Table 301.052
label | 3a12c486-d6ce-50e7-a4ff-c40aa4afcdee |  | note | Crushing Resistance greater than 100KN and wet/ dry strength ratio greater than 60%
label | cb99e1f1-29b9-5b2b-979e-b5e9c05297f5 |  | note | Los Angeles Abrasion - Max. 40%
label | 0e960685-2c3b-56a0-82a3-0e21d663164d |  | note | Plasticity Index - 2 - 12%
label | 4e4fb398-032f-50da-aecd-750bf575d434 |  | note | Liquid Limit - Max. 40%
label | 22b32c3d-7749-5ead-a704-8d7620fea912 |  | note | California Bearing Ratio - Min. 80%
label | 56877357-db3e-5178-a067-4b512b98e8d7 |  | note | Flakiness Index - Max. 35%
label | a57a399d-167e-5f52-956c-bfb875ad4d46 |  | note | Frequency:
label | 483d77c5-032e-5cbe-869e-56e90c73eb57 |  | note | Grading and Atterberg Limits = On each production day - One per 750 tonnes or part thereof
label | c037a8db-909a-54ce-9693-2717fbb6da79 |  | note | Moisture Content = On each production day - One per 750 tonnes
label | d4c8575a-3923-5a20-b98e-90af34f4a677 |  | note | California Bearing Ratio = One per 2000 tonnes
label | 1a6d32fe-2978-5038-97d7-f3a136c3bac8 |  | note | Degradation Factor = One per 2000 tonnes on each production day
label | 8ed15e83-0995-5fee-a2a8-62ff78713b70 |  | note | Los Angeles Value = One per 2000 tonnes on each production day
label | 7b16ecfc-4b5b-5be0-9349-df5b84ee19a9 |  | note | Sand Equivalent = One per production fortnight
label | cad839ee-e298-5546-b42f-32110d7a2894 |  | note | Flakiness Index = One per production fortnight
label | acb48cb1-e645-5e08-994f-53d49a328786 |  | note | Crushed Particles = One per production fortnight
label | 691cb8dd-2804-514b-9e6a-b8ea5b1eb07d |  | note | Polished Stone Value = Not used
label | acf5bc66-36e6-51d1-b233-ec565f9788d3 |  | note | Hold point
label | 2e19db5d-5c15-5638-b721-85d33447aa3c |  | note | Responsibility: Higgins Project Manager/ Smec
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Stabilization of Existing unbound Layer
checkpoint-status |  |  | checkpoint | Milling - Remove existing Seal
label | 8e19141b-1674-5e6b-ab60-fe56bcfe9be6 |  | note | Requirement: Remove and disposal of existing chip seal to approved stockpile or as instructed by the Engineer to Contract
label | e210c6b9-6685-5919-b71a-9e794b15ca32 |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Stabilisation - Stabilise Existing unbound layer
label | 70ad8403-736c-5a93-9c64-23db229704ac |  | note | Reference: FRA Roadworks Standards and Specification; Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | f0a07e82-e0e7-5b8e-a03c-e0ab3b6d8bc4 |  | note | Requirement: Insitu stabilization with 3% cement of the top of existing unbound pavement layers compacted in 200mm layers max.
label | 76e52cd8-22c1-56a0-bc90-ce374ba1ed0b |  | note | Where extra over cement required, confirmation from Engineer to contract to be taken.
label | ff392ec1-3e90-58f2-ae06-e379e41bf7e8 |  | note | Frequency: 4000m2
label | 7895d50f-be57-5c9f-909d-453ae813da4f |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Level Check - Dipping
label | 55c69828-c907-56f4-baf9-f595e019022a |  | note | Reference: FRA Roadworks Standards and Specification; Section 304 - InSitu Stabilisation of pavements with Cementitious Binders 304.03 - Conformity with Drawings
label | 480f1850-e1ba-5791-9249-69e76d586e08 |  | note | Requirement: Table 304.031 Level Tolerances at the Surface of Pavement Courses
label | 3b781d13-e9cb-57ab-844f-656cd14411d6 |  | note | Subbase (mm) + 10 to -25 / Base (mm) +15
label | 030255bf-8b2b-51c2-b129-59f74c8a6eed |  | note | Frequency: 4000m2 per lot Every 20m longitudinal
label | c21b65f9-c3e7-565f-939f-7b8e58ec317b |  | note | Hold Point
label | fcdbf95e-994e-599d-95d4-cb69a799168c |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | dbf5bc26-7302-5d4c-8526-7faf47ad6b21 |  | note | Reference: FRA Roadworks Standards and Specification Section 304 - InSitu Stabilisation of pavements with Cementitious Binders 304.10 - Test Rolling
label | 9c1faab7-78ca-54ef-bc0e-d77dba3331fc |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | a44ddd56-08c4-540f-a776-0e427858c17e |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | 8e818c7e-7d41-5f87-a582-4700f5718cec |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | b28e9b81-187a-5c59-9479-1e2da8424a75 |  | note | Frequency: 4000m2
label | 4444d5af-7c65-5ffd-806b-39191db737af |  | note | Hold Point
label | 2713899e-0820-5e6e-ac11-62570c7e49b9 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | 4f2b2221-0820-56c6-ad47-525a2c85c2ac |  | note | Reference: FRA Roadworks Standards and Specification Section 304 - InSitu Stabilisation of pavements with Cementitious Binders 304.13 - Requirement for testing and acceptance of compaction and strength.
label | b606a6a3-e3e1-5153-8273-6105da466e6a |  | note | Requirement: density ratio obtained from six randomly selected test sites within the lot is not less than 95%
label | 2d5c392f-888b-5256-b600-92478387f519 |  | note | Frequency: 6 test per Lot
label | 8dc327be-97cd-5c9c-86b2-dc0eac2e3b08 |  | note | Hold Point
label | 7f5671ed-c6aa-558c-b5e4-6de7679c99c0 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction of AP75/ AP65
checkpoint-status |  |  | checkpoint | AP40 Layer - AP 40 layer unbound
label | 23f547e4-caee-52f6-b764-32950573446c |  | note | Reference: FRA Roadworks Standards and Specification Section 302 - Construction of Base and Sub Base Pavement Courses
label | bc0eee9c-9501-5689-8db5-e17808464136 |  | note | Requirement: Construct AP75/ AP65 compacted in layers (typical 150mm)
label | 52b59f17-f2c6-5b9a-89d6-fbde6b917e05 |  | note | Frequency: 4000m2
label | 481eb3a4-00ea-531e-9771-404c0d1125d3 |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Dipping - Level Tolerance
label | 4701d614-21d3-50c5-87bf-1d55a1b5a0d2 |  | note | Reference: FRA Roadworks Standards and Specification Section 302 - Construction of Base and Sub Base Pavement Courses 304.041 - Level tolerances at the surface of pavement courses
label | e2bcc62f-eba9-5301-9a08-34225e04fbb7 |  | note | Requirement: Table 304.041 Level Tolerances at the Surface of Pavement Courses
label | 6f5638b2-a7dc-5a07-bfb6-5184b1f63357 |  | note | Lower Subbase (mm) +15 to -25 / Upper Subbase (mm) +10 to -25 / Base (mm) +15
label | bb77ff30-8a0a-58cf-aa27-0f053afbc76b |  | note | Frequency: 4000m2 per lot Every 20m longitudinal
label | 44736e2d-5645-572d-9e37-eb986c4ffd1f |  | note | Hold Point
label | ae64819a-65f2-5bf7-b88e-8516a0a8a6e4 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | 0d4346f7-7a24-5a10-9ec0-c7c183560ca0 |  | note | Reference: FRA Roadworks Standards and Specification Section 302 - Construction of Base and Sub Base Pavement Courses 302.13 - Compaction Procedure and requirements for testing and acceptance of compaction
label | fee0a75b-491a-540b-aba7-5eedcf39bff9 |  | note | Requirement: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six (6)
label | 801d7378-d653-5c0f-b937-770029a4dc96 |  | note | Frequency: 4000m2
label | 25bb3ade-087e-5e2d-af80-987cea3162db |  | note | Hold Point
label | 470cfdab-2fad-5440-a05d-5958ef1d75a6 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | fa73853a-ff1d-55d0-8c8f-02de324362f5 |  | note | Reference: FRA Roadworks Standards and Specification Section 302 - Construction of Base and Sub Base Pavement Courses 302.14 - Test Rolling
label | 0ae3d33c-011a-5818-a373-e2b9cabe3dbb |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | 956eeaf5-ae4d-504d-95c1-0f0ff82a0c3a |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | 5c55afec-9224-5238-b2bc-32bc6829e923 |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | 3839809a-750a-5409-bbed-98894c4f9187 |  | note | Frequency: 4000m2
label | 3d361850-5691-5c6a-a7a6-2e4147e29588 |  | note | Hold Point
label | e0953ed1-1e68-576d-b4e3-4f29286b0f42 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | Subgrade (Shoulder) - AP65/AP75 |  |  |  |  | Yes | Subgrade (Shoulder) - AP65/AP75 | 142e1c88-a3e9-4fdc-8e9e-7d06d170358f
checkpoint-status |  |  | checkpoint | Location
text | 02e27a79-b54a-5279-a169-e77cc8651eff |  | textbox | Location Details - Chainage
checkpoint-status |  |  | checkpoint | Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Straight Edge
checkpoint-status |  |  | checkpoint | Proof Roll
checkpoint-status |  |  | checkpoint | Nuclear Density Meter
checkpoint-status |  |  | checkpoint | Scala
checkpoint-status |  |  | checkpoint | Undercut / Fill
checkpoint-status |  |  | checkpoint | Light Weight Deflectometer
checkpoint-status |  |  | checkpoint | Falling Weight Deflectometer
checkpoint-status |  |  | checkpoint | Benkelman Beam
checkpoint-status |  |  | checkpoint | Additional Information
text | aa8cb120-2d27-5d13-a699-c2049f2fa7bc |  | textbox | Additional Information
checklist-sectioned |  |  | checklist | ITP 002 - Sub Base |  |  |  |  | Yes | ITP 002 - Sub Base | 4b847c68-c384-443c-ae89-a5e3a968e950
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | AP75/ AP65 - Sub Base
label | 3def77aa-e8a9-4ad3-957c-fe644fc752da |  | note | Reference: Signed Contract - Volume 1; Section 6 - Employer's Requirements; Section 300 - Pavement Construction; Section 6 ; Employers Requirements; Fiji Roads Authority; Section 301 - Materials for Pavement Construction
label | 7e935353-abe3-4f88-ad5a-f3538c03d662 |  | note | Requirement: AP40 with reduced fines to comply with the specification requirement as per below
label | ebf2319b-572b-432f-ad8f-cb168cbc8056 |  | note | Particle Size Distribution - Table 301.052
label | 6b564e4d-ff1c-4d74-8b64-f757f5d13575 |  | note | Crushing Resistance greater than 100KN and wet/ dry strength ratio greater than 60%
label | b25bf838-c13a-419f-a6f6-2d49238e7680 |  | note | Los Angeles Abrasion - Max. 40%
label | 7b1355cc-5add-4e77-af66-c248a22c5284 |  | note | Plasticity Index - 2 - 12%
label | 889188d5-4915-4108-b573-052e14e11d29 |  | note | Liquid Limit - Max. 40%
label | 612c7646-25f1-442c-a8e4-cf05e7f1bd60 |  | note | California Bearing Ratio - Min. 80%
label | aadbb205-de4b-42a6-8dc1-4b9e5f60b543 |  | note | Flakiness Index - Max. 35%
label | 203161d6-e786-42c4-b806-23dcf535e54c |  | note | Frequency: As per table
label | cf95bdde-40c7-4a9e-aafe-030d3a9b14fd |  | note | hold Point
label | 662854f3-18a2-4389-8d13-e0488c7320e1 |  | note | Responsibility: Higgins Project Manager/ Smec
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Stabilization of Existing unbound Layer
checkpoint-status |  |  | checkpoint | Milling - Remove existing Seal
label | 6ed4c347-3ecc-4dd0-b7d5-881f1d022e89 |  | note | Requirement: Remove and disposal of existing chip seal to approved stockpile or as instructed by the Engineer to Contract
label | 1fa07151-79c5-4cef-9717-2a0fd9b1b26f |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Stabilisation - Stabilise Existing unbound layer
label | 8e67eba8-748e-464e-bf5c-ac3e0a276869 |  | note | Reference: FRA Roadworks Standards and Specification; Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | 8205cac2-94dc-4ff1-ab2a-9c5069b2a541 |  | note | Requirement: Insitu stabilization with 3% cement of the top of existing unbound pavement layers compacted in 200mm layers max. Where extra over cement required, confirmation from Engineer to contract to be taken.
label | 0c015587-938a-4380-bfb9-82ecace89fdc |  | note | Frequency: 4000m2
label | 364037a8-8802-4950-9013-0f5dd93297e1 |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Level Check - Dipping
label | 13bd2c87-d3e5-4b2f-b454-9e3e1ef83141 |  | note | Reference: FRA Roadworks Standards and Specification; Section 304 - InSitu Stabilisation of pavements with Cementitious Binder; 304.03 - Conformity with Drawings
label | a4d2833b-9522-4227-8b94-ea037bc26bef |  | note | Requirement: Table 304.031 Level Tolerances at the Surface of Pavement Courses
label | 10686357-ad14-4b4a-93e6-0e07fa751de0 |  | note | Frequency: 4000m2 per lot; Every 20m longitudinal
label | 8523d872-e72e-4010-8b07-e1e0f06e6ee5 |  | note | Hold Point
label | e7c44af5-5c85-4263-9db2-d8775fa1fd16 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | c5b08345-cf51-4831-9aad-a75a1c59e111 |  | note | Reference: FRA Roadworks Standards and Specification; Section 304 - InSitu Stabilisation of pavements with Cementitious Binders; 304.10 - Test Rolling
label | 4757cf49-297b-4d00-b245-fd70172df51a |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer. Steel smooth wheeled roller - mass not less than 12 tonne. Pneumatic Tyred Plant - mass not less than 20 tonne
label | b5674632-4d64-443e-a8f3-86480ab3cb07 |  | note | Frequency: 4000m2
label | 3c890910-622f-41ca-aa8c-a63dacfec6e4 |  | note | Hold Point
label | 5b5cc861-e942-41af-a656-6ad8c9737a9e |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | 71e94568-953b-406d-be04-ef9d70f36d3b |  | note | Reference: FRA Roadworks Standards and Specification; Section 304 - InSitu Stabilisation of pavements with Cementitious Binder; 304.13 - Requirement for testing and acceptance of compaction and strength.
label | 3cd559ab-3911-44b2-a3d2-376afc11dbb1 |  | note | Requirement: density ratio obtained from six randomly selected test sites within the lot is not less than 95%
label | 788ca4e5-1444-4513-87fc-36af3ed93436 |  | note | Frequency: 6 test per Lot
label | e8e95bc6-2b27-40fb-9b5f-829ece4e858f |  | note | Hold Point
label | fd49765e-63b2-4f7c-a39c-f6d2bb91806f |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction of AP75/ AP65
checkpoint-status |  |  | checkpoint | AP40 Layer - AP 40 layer unbound
label | c9cececd-198a-4fc5-879e-5a6469d7ce18 |  | note | Reference: FRA Roadworks Standards and Specification. Section 302 - Construction of Base and Sub Base Pavement Courses
label | db6810f7-50c7-461a-a904-9b0ec252d64c |  | note | Requirement: Construct AP75/ AP65 compacted in layers (typical 150mm)
label | d212b9f2-d3f5-469a-8255-52752ef98a63 |  | note | Frequency: 4000m2
label | 84ad4baf-40e4-4ea8-8f68-8490df1b6285 |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Dipping - Level Tolerance
label | 82493190-3586-47d3-b058-1c1f1d8036d3 |  | note | Reference: FRA Roadworks Standards and Specification. Section 302 - Construction of Base and Sub Base Pavement Courses. 304.041 - Level tolerances at the surface of pavement courses
label | f0ecc1da-d072-44ac-a6a0-0d96d7208034 |  | note | Requirement: Table 304.031 Level Tolerances at the Surface of Pavement Courses
label | 126ada2b-201a-447e-90d9-526b51291500 |  | note | Frequency: 4000m2 per lot. Every 20m longitudinal
label | ddec07f3-f769-4115-84f5-9d560ecd847d |  | note | Hold Point
label | 8afabc00-7960-4a3a-bdda-0d73b2487a79 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | cf715fb9-2cdf-49c9-9611-2f6686cc6570 |  | note | Reference: FRA Roadworks Standards and Specification. Section 302 - Construction of Base and Sub Base Pavement Courses. 302.13 - Compaction Procedure and requirements for testing and acceptance of compaction
label | 01bb629e-ad88-49f2-9df3-fd6d9577413a |  | note | Requirement: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six (6)
label | 0c54d222-aef9-4ca1-a1f7-06939e1b253c |  | note | Frequency: 4000m2
label | ec96f46f-f1f8-4521-b231-e7bb81167b57 |  | note | Hold Point
label | 699455e6-5cf1-49fd-90ae-e5f8d7ae8039 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | 48355d18-0dba-4826-adf7-e5a7a3b7ed18 |  | note | Reference: FRA Roadworks Standards and Specification. Section 302 - Construction of Base and Sub Base Pavement Courses. 302.14 - Test Rolling
label | 475cfcbe-6304-47b8-91a5-671fac5a449d |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer. Steel smooth wheeled roller - mass not less than 12 tonne. Pneumatic Tyred Plant - mass not less than 20 tonne
label | 70ddc550-cd23-4b69-908e-a3c8d6ec9495 |  | note | Frequency: 4000m2
label | 2bc28a2f-2732-497d-9b33-1577c212cbb0 |  | note | Hold Point
label | 24e9cdbc-383c-42c4-90e4-db8afb0d6d26 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | Site Location |  |  |  |  | Yes | Site Location | 7ac1df74-f706-4f19-aee4-949416f448d7
checkpoint-status |  |  | checkpoint | Site Location
text | 53da3f26-6ad7-58e9-bb18-ee15e8f737ae |  | textbox | Location Details - Contract, Site, Map, Chainage
checkpoint-status |  |  | checkpoint | Scope of Work
text | 5e1bebf6-257d-5719-9e57-654671f6340f |  | textbox | Description of Work
checkpoint-status |  |  | checkpoint | Inspection Test Plan
text | eb897c9a-c135-5493-9903-12acff81d0db |  | textbox | Relevant ITPs
checkpoint-status |  |  | checkpoint | QA Tracker (Excel)
checkpoint-status |  |  | checkpoint | Additional Information
text | fd492ee5-45b0-58b8-bd3b-7b24602d4da1 |  | textbox | Additional Information
checklist-flat |  |  | checklist | Sub-base Construction (Shoulder) - AP65/AP75 |  |  |  |  | Yes | Sub-base Construction (Shoulder) - AP65/AP75 | 7d7b026d-0fd5-4f0f-bd90-3e2d49dd4d74
checkpoint-status |  |  | checkpoint | Location
text | 1bffa98c-0b19-5ec3-bd85-4493798f5130 |  | textbox | Location Details - Chainage
checkpoint-status |  |  | checkpoint | Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Straight Edge
checkpoint-status |  |  | checkpoint | Proof Roll
checkpoint-status |  |  | checkpoint | Nuclear Density Meter
checkpoint-status |  |  | checkpoint | Scala
checkpoint-status |  |  | checkpoint | Undercut / Fill
checkpoint-status |  |  | checkpoint | Light Weight Deflectometer
checkpoint-status |  |  | checkpoint | Falling Weight Deflectometer
checkpoint-status |  |  | checkpoint | Benkelman Beam
checkpoint-status |  |  | checkpoint | Additional Information
text | c862ac66-c03c-5c6f-b478-0286d438ad31 |  | textbox | Additional Information
checklist-flat |  |  | checklist | Upper Basecourse Construction - AP40 |  |  |  |  | Yes | Upper Basecourse Construction - AP40 | 83e2e0e5-d6df-4733-90c2-5e8f5c53d4fc
checkpoint-status |  |  | checkpoint | Location
text | b70e3cf7-b4df-59dc-8bb8-819088eab911 |  | textbox | Location Details - Chainage
checkpoint-status |  |  | checkpoint | Pre Construction Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Straight Edge
checkpoint-status |  |  | checkpoint | Proof Roll
checkpoint-status |  |  | checkpoint | Nuclear Density Meter
checkpoint-status |  |  | checkpoint | Light Weight Deflectometer
checkpoint-status |  |  | checkpoint | Falling Weight Deflectometer
checkpoint-status |  |  | checkpoint | Benkelman Beam
checkpoint-status |  |  | checkpoint | Additional Information
text | 61fc397a-4f6d-5cea-9a88-b1bd4b2b3b5d |  | textbox | Additional Information
checklist-flat |  |  | checklist | ITP - Earthworks - Shoulder Works | itp |  |  |  | Yes | ITP - Earthworks - Shoulder Works | 869b407c-f749-44c1-951d-ae39ae2e68ed
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - Sub Contract and suppliers
label | b87364f1-9f92-5a13-aadb-d5bce987da1a |  | note | Reference: Higgins
label | 2808404e-1d3f-5f09-8bee-f9258bf9848f |  | note | Requirement: Ensure that Sub contract and supplier agreements are signed
label | 73b2a017-077b-5802-aeab-16e177d5c990 |  | note | Frequency: As Required
label | 97e4a602-2fc7-587e-929c-2389406ba776 |  | note | Hold Point
label | 5e83edbb-59b3-532d-a311-4bedea15201e |  | note | Responsibility: Project Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - TMP
label | 823f9cba-21b3-5ea6-a151-bb87bcfc9faf |  | note | Reference: Higgins
label | eb5d4a27-9888-5d11-b810-f22521090721 |  | note | Requirement: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | a62bb634-fbaf-59c8-a19e-ed4e2bad8bce |  | note | Frequency: As Required
label | 3a2732d2-a2e4-5841-9a7b-5a2546e3be85 |  | note | Hold Point
label | b5d3391e-2398-583b-9ef7-817ce7f27d62 |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - Induction
label | 0a55abdd-f9f8-59e9-b3d7-db776ef8220f |  | note | Reference: Higgins
label | edbf3c26-f4d0-52d5-b8e7-a6b1aab6dc4a |  | note | Requirement: Ensure all sub-contractors and suppliers go through Kings Road Upgrade Project A induction.
label | 748231a4-ba8a-5bea-8f5c-a0e7c4ac0b00 |  | note | Frequency: As required
label | 51434d6e-f362-5971-94d3-a83a6946ac72 |  | note | Hold Point
label | 59c05de7-81ab-5e40-b3db-43d06a43dc3e |  | note | Responsibility: Supervisor/ Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Design - Design
label | 12e9e7c1-0d84-5f26-86ee-1b75e7f5976c |  | note | Reference: Higgins
label | 7591019c-e89a-5baa-8750-685732194250 |  | note | Requirement: Ensure that Design is approved and Drawings are of the latest revision. Check drawing Register.
label | 4710645b-5bc3-5fcd-8dd5-e7d670199516 |  | note | Frequency: Prior to Commencement
label | e744ed80-18b9-5a2e-b511-66b29ed5dbb8 |  | note | Hold Point
label | f87727cd-4f75-5b4d-9eb0-4512ac1d7bf4 |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Installation of Erosion and sediment controls - Erosion and sediment control
label | a915ff39-8ff9-56dd-9ed8-c6423d7c4139 |  | note | Reference: Higgins
label | 0e5578d0-3bad-509d-ab2d-4c81d3c92daa |  | note | Requirement: Ensure that Erosion & Sediment Control ITP & Checksheets have been completed and submitted to the Territorial Authority
label | 9faa7feb-bb6d-514b-b80d-9921a028f6f5 |  | note | Frequency: Prior to commencement
label | a1576762-5b3b-5912-b6f7-060a7bd9af9e |  | note | Hold Point
label | 9a294f94-c062-5394-b8e6-6948997c485a |  | note | Responsibility: Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Survey setout - Setting out works
label | 4d2109dd-ec4d-5a71-a185-d3faa426e31e |  | note | Reference: Higgins
label | fbaca0ec-19f2-5b25-b66e-e2ccbbbaac71 |  | note | Requirement: Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | 2d139431-6cdb-5394-a621-893d49a02e61 |  | note | Frequency: Prior to commencement
label | 1656bd30-31fa-509b-ad9e-a7e9e443724a |  | note | Hold Point
label | e86e0e12-465a-5c53-9052-6f5695de7788 |  | note | Responsibility: Surveyor/ Site Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Locate existing services by hand digging - Existing Services
label | aa309717-4c5a-54f1-b492-a991d9e2eb69 |  | note | Reference: Higgins
label | 853628bf-de48-50aa-ad9f-94e338d3780e |  | note | Requirement: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 0f24d1d6-9ae5-5dea-a208-8147acff6dea |  | note | Frequency: Prior to commencement
label | 9eef9550-3c31-5413-b3b9-5be9907ca077 |  | note | Hold Point
label | 5680fdac-d458-504b-bfda-eff8da324fdc |  | note | Responsibility: Supervisor
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Material - Suitable Material (AP65)
label | 1668c310-d041-59ed-a8d3-7ad12e253ec8 |  | note | Reference: Signed Contract - Volume 1 Section 6 - Employers Requirements Section 200 - Earthworks
label | 8a332ca7-3c65-5b75-a582-6675ec09783e |  | note | Requirement: backfill material shall comply with clause 202.04 of FRA specification requirements
label | abe702ab-8724-5a73-a383-77d011d2fe5f |  | note | Frequency: each Lot
label | 019b0e69-b9b4-537b-8421-13ee2ae6ae6b |  | note | Responsibility: Higgins Project Engineer/ Smec
checkpoint-status |  |  | checkpoint | Excavation - Excavation of existing shoulder
label | 78363484-4979-506a-b7cc-019a9bb3fc4c |  | note | Reference: FRA Roadworks Standards and Specification Section 202
label | a436e883-67dd-5ec6-a94f-d94401ac1f7b |  | note | Requirement: excavate existing shoulder to the depth of 200mm from the existing seal level. compact excavated shoulder to achieve a strength of 95% compaction for NDM testing
label | 53fc3557-34b0-5f4c-9d8f-073f5094e7e6 |  | note | Frequency: each lot
label | 7ca70fbe-9887-5b2b-9e59-6080622cec7c |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Excavation - Compaction test - NDM testing on excavated layer
label | c906e0d5-8340-5d60-9a15-1b3026d68f9c |  | note | Reference: FRA Roadworks Standards and Specification Section 202.15 - Requirements for testing
label | 6b6971fa-6e26-544c-a6e8-480d78f56003 |  | note | Requirement: NDM test to be carried out in the presence of SMEC Engineer and a strength of 95% shall be achieved prior to construction of shoulder.
label | 5108145e-8536-5695-937c-eeae8838703f |  | note | Frequency: every 20 m
label | fc63894f-4048-50bc-8024-625bbb1a3600 |  | note | Hold Point
label | 12f05f53-e06b-566d-ae59-3c613be502f6 |  | note | Responsibility: SMEC Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Excavation - Light Weight Deflectometer - After Excavation
label | e097c4c9-1c29-5110-b359-d1e59bc3cc8f |  | note | Reference: SMEC Requirement
label | c1b8c497-594c-5cea-bd74-6e5f9b647dc1 |  | note | Requirement: LWD test shall be be carried out by SMEC Engineer prior to backfilling and compacting shoulder with AP65
label | 3069e986-139b-5767-8ab0-29d0f30d85da |  | note | Frequency: Every 20m
label | 672254a5-c92e-53d5-a759-cc247a3cc2e4 |  | note | Hold Point
label | b356ae3f-b627-5bed-a802-1c34db2db81c |  | note | Responsibility: SMEC Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Shoulder Construction - Fill Construction
label | f7375601-2395-56ea-b883-c2157be7c58a |  | note | Reference: FRA Roadworks Standards and Specification Section 202.12 - Fill Construction
label | c0887c73-9f87-5f36-bd4d-045378f680f1 |  | note | Requirement: Ap65 unbound layer compacted in Layers( Max. 200mm/ layer)
label | ebe2ab5c-bd1a-5b5e-929f-550537541008 |  | note | Frequency: Each Lot
label | 2dfc14eb-af33-549f-8cf2-cba664b4c26f |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Testing - Compaction NDM Testing - After backfill
label | 887f54b6-1517-5756-a28a-4422f60495fd |  | note | Reference: FRA Roadworks Standards and Specification Section 202.15 - Requirements for testing
label | c439958b-bf10-5854-930a-2792c1e7665d |  | note | Requirement: NDM test to be carried out in the presence of SMEC Engineer and a strength of 98% shall be achieved prior to construction of shoulder.
label | 6c458af4-6442-5290-875b-c9a92550a542 |  | note | Frequency: Each Lot
label | c851117a-6ff1-5ee9-8dba-8e49dbb78c2e |  | note | Hold Point
label | 94561864-0a47-5d68-8418-a9ec997bde49 |  | note | Responsibility: SMEC Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Testing - Light Weight Deflectometer - After Construction
label | 94b9d654-db81-5331-b600-7f00d0ce5d0c |  | note | Reference: SMEC Requirement
label | 5a200b98-c20e-525f-b514-ebd7a851bcd6 |  | note | Requirement: LWD test shall be be carried out by SMEC Engineer after construction of shoulder with AP65.
label | 86b9738f-4b18-5745-867a-63fef882c11c |  | note | Frequency: Every 20m
label | ca905de3-53df-54a7-b3b0-f53996c2af6b |  | note | Hold Point
label | 83190785-254e-5386-8648-dc476723dca4 |  | note | Responsibility: SMEC Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | f987fec4-a985-5369-a7a6-c8843f5783d8 |  | note | Reference: FRA Roadworks Standards and Specification Section 202.14 - Test Rolling
label | bd786a59-e0bf-51f3-91f4-f7c5be76c68b |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer. Steel smooth wheeled roller - mass not less than 12 tonne Pneumatic Tyred Plant - mass not less than 20 tonne
label | 086bbd15-95c8-5abd-9636-e8a9d0470053 |  | note | Frequency: 4000m2
label | 3fe85116-060b-5cc9-820c-8df8e3d2b421 |  | note | Hold Point
label | a114f009-8c9d-59cb-9165-7c51e7434148 |  | note | Responsibility: SMEC Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Visual Acceptance - Inspection
label | 5cf98125-ba1d-51a4-923d-74d2a4b98a3b |  | note | Reference: FRA Roadworks Standards and Specification
label | 45a6de73-e5ae-504c-98dc-6c29bbe9f26d |  | note | Requirement: visual inspection meets engineers requirement no segregation or loose material free of surface cracks meets the required gradient
label | 48470b7b-9c72-56ba-9d30-aa89ece24ed1 |  | note | Frequency: Each Lot
label | 335b51e8-7744-5641-8add-9d4fdb71d794 |  | note | Witnessing
label | 20e4fc72-e129-5284-8005-9826f76f5d9a |  | note | Responsibility: SMEC Engineer
checkpoint-status |  |  | checkpoint | Survey As-Builts
label | 16bf4f9c-70a6-5997-8aad-ae26831930bb |  | note | Reference: FRA Roadworks Standards and Specification Section 160.17 - Contract closeout Record Documents
label | 67ab8b38-78b3-552f-8cb1-1a65000edfcd |  | note | Requirement: Ensure all drainage lines comply with design prior to carrying on with next construction process.
label | 942e1231-ad80-52de-9ccc-b8285afb38ad |  | note | Frequency: Upon Completion
label | 6d4708ae-ba7e-5b5b-93ba-1bf4d468eb7a |  | note | Responsibility: Surveyor
checkpoint-status |  |  | checkpoint | Contractors Representative
holdpoint |  |  | signoff | Add Sign Off
checkpoint-status |  |  | checkpoint | Engineers Representative
holdpoint |  |  | signoff | Add Sign Off
checklist-flat |  |  | checklist | ITP - Laying of Asphalt | itp |  |  |  | Yes | ITP - Laying of Asphalt | 89b3b0d3-29e3-4c0f-8e71-19f081e041bf
checkpoint-status |  |  | checkpoint | 1 - Bitumen for Asphalt Concrete Production
label | 43bb24a0-a8fa-4f5c-ab34-a2dfdc14d5e3 |  | note | Action - H
label | fdf7528c-0ce5-445c-8a1b-cda9801979d0 |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP)); NZTA M1 - A:2016
label | ed4c96bf-4fac-4c8b-af82-b3fc8cbdfb2e |  | note | Requirement - The asphalt concrete (AC14 and DG7) will be produced with Polymer Modified Binder (PMB), modified with SBS polymer, with performance grade of PG76 - 16V(or better) according to AASHTO M320 Table 1 and torsional recovery >55% when tested at 25°C,30s, according to method AGPT/T122
label | 1ba91333-853b-4595-a968-a10eb83d7106 |  | note | Frequency - As required
label | de2ec0bc-5c54-4c96-9c64-632cd71d67e1 |  | note | Inspection / Test Method - Submission; Review
label | 7b65558c-6dd6-47d3-baa4-50b65723a2f7 |  | note | Responsibility - Project Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - AC14 and DG7 Design
label | c0b74e45-af0e-47fc-bed2-8b39451db700 |  | note | Action - H
label | 501ab26e-aeed-4c97-9dbd-b879bb98d7a4 |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | e53492b8-a4a0-4bfd-9db6-bb22236e8793 |  | note | Requirement - As per Mix characteristics / Requirement table
label | 48cdea3e-d628-4420-a9eb-ad8588c9acd7 |  | note | Frequency - Before commencement of work
label | a78b780c-a9d7-41f2-8160-b21cf9b6cb3b |  | note | Inspection / Test Method - Submission; Review
label | 34428ad4-eeff-4353-ad2a-b42d7f2fcd3a |  | note | Responsibility - Project Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Laydown Trial
label | a2852355-1881-45c8-a80a-b1dbff9f46a6 |  | note | Action - W
label | 346ffefb-a555-4830-81a6-185ff2a2894a |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | 757d06e9-d9c0-45e2-9c33-d61e49e0d255 |  | note | Requirement - A production and construction trial shall be done prior to construction
label | bcfad369-94e0-4e6f-b842-fb69b23c6f25 |  | note | Frequency - Before commencement of work
label | 088b72cb-67e0-4efa-850a-b4abe73bc8e5 |  | note | Inspection / Test Method - Submission; Visual inspection; Testing; Review
label | f69b233d-39db-4d11-8491-58b96f731976 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | 4 - Adhesion Test
label | fdccbaf7-9bf1-482a-bc3e-2fdff9ec5d72 |  | note | Action - H
label | a9c79ffa-8676-405d-8f47-72881501ea6f |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | e92eaf45-ef22-47e6-bce4-3f8fc7d7dc6e |  | note | Requirement - The aggregate used for AC14 and DG7 and chip seal shall meet the requirements of adhesion when tested according to: VicRoads Test Method RC 112.03 ADHESION OF BINDER TO STONE (Ability of a binder to displace water from a wet stone surface) AS 1141.50:1998 Resistance to stripping of cover aggregates from binder or Another international relevant standard. If adhesion does not meet requirements, then an adhesion agent shall be added at the required rate (determinate) according ot the same test methods. Adhesion agent shall be suitable to asphalt concrete high temperature and polymer modified binder. Its type/brand requires prior approval of FRA
label | 58649e3f-2ff2-43cf-ad27-2b4627aea686 |  | note | Frequency - Before commencement of work
label | 0803d644-b332-46cb-b6b7-ba9b45c1b9e0 |  | note | Inspection / Test Method - Submission; Review
label | 2fe9f407-ad0a-45a0-aa5d-d5362b05de4b |  | note | Responsibility - Project Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Construction of Tolerance and Frequency of Testing
label | 115edc62-1aa2-4939-94d9-cad6fa0668a6 |  | note | Action - W
label | 54782293-cf1e-4f01-9f87-2d5de9c05d28 |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | f73b5998-8835-4de4-8263-761f5a6410f4 |  | note | Requirement - The applicable construction tolerances and frequency of various tests are according to the sequence of the following lists where item 1 has the highest prevalence;
label | 31e44e8a-7b3e-4fa4-beca-7f88e0a1834e |  | note | 1. Tolerances specified herein and other project specific documents;
label | fe61012c-7347-43da-aeec-7de8cc3b80e0 |  | note | 2. Tolerances specified in the Section 404 of FRA Roadworks Standards and Specifications;
label | ad4ea058-5b53-4909-9910-add57d65e4c4 |  | note | 3. Tolerances specified in NZTA M10
label | c8a7c337-c536-4af1-8818-0c820ca7e58f |  | note | Frequency - As required
label | 09d31c41-91b0-417c-92d2-197744d138bc |  | note | Inspection / Test Method - Submission; Testing; Review
label | 4a6cbe3b-50b8-4853-8d0e-b2a8bf299d68 |  | note | Responsibility - Project Manager
checkpoint-status |  |  | checkpoint | 4 - AC Macrotexture Requirements and Lot Acceptance
label | fa8978a0-4e0d-496e-a59e-07beffc47b18 |  | note | Action - W
label | 4360e090-65e7-4e42-b2cb-e447bf6b642a |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | ffc103f0-117f-4f13-94bb-d1c5c64f4228 |  | note | Requirement - The asphalt concrete macrotexture will be measured by the mean height of sand (sand patch test) according to ASTM E965 - 15, VicRoads RD 317.01 or TNZ T/3. Lot acceptance is according to the below criteria: AC14 - Lanes - 0.5min ≤ average mean height of sand ≤ 1.5mm DG7 - Shoulders - (not required) Calculation of average value is according FRA 5105:2019 specification. One test every 200m of lane performed at the external wheelpath with a minimum of 2 tests per lot.
label | f5b863e0-3231-43f3-83da-902059c58a8c |  | note | Frequency - Prior to the Tests
label | 41446677-f950-41b8-b6b4-bb7961b68ea1 |  | note | Inspection / Test Method - Submission, Testing, Review
label | 02e719e1-113e-455c-9863-2c4eeb64b253 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 5 - AC Thickness
label | 33624f57-112a-41d0-9cff-a3fa0dee494f |  | note | Action - W
label | ccb1d631-ce52-4b85-8719-f0143aaf2f08 |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | 153b4b67-edf9-4554-addb-906273dd05f0 |  | note | Requirement - Thickness to be measured in extracted AC cores. AC14 = 28mm and DG7 = 14mm
label | 09764248-ff5a-496a-be3d-65a50e68a676 |  | note | Frequency - Each lot
label | cc141b11-b77d-43a1-a512-cd74ded33085 |  | note | Inspection / Test Method - Testing
label | 28364510-6186-4dbe-813b-a47aa4167f16 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 6 - AC Roughness
label | 6119e7e4-f6e5-4f87-a65c-d0e7a8855acc |  | note | Action - H
label | 5fb5381c-6be2-4086-aba7-f9e87bf99838 |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | 8961847c-2363-42df-90d3-cde6fe189d48 |  | note | Requirement - Roughness shall be measured according to the International Roughness Index (IRI) at every lane and shoulder with a roughness device with accuracy class II or better according to ASTM E 950, or with Roughometer III device and calculated for 100m long sections. This will be performed by FRA rather than Contractor
label | ce043397-b760-43d2-8e3a-f0340a20c25a |  | note | Frequency - One week in prior to completion of base layer
label | d094e9ce-155b-47ad-8868-85b4721eb17d |  | note | Inspection / Test Method - Testing; Review
label | af0a9a41-769c-48f7-9d80-e631fd71bd56 |  | note | Responsibility - FRA Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Air Void Volume Lot Acceptance
label | e2f5e98a-012c-449b-a041-237d8797b500 |  | note | Action - W
label | 4d1199d2-0f39-4092-8856-a4bd1bfc9f24 |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | 266ea70c-7711-4515-b19a-c79636fa9c62 |  | note | Requirement -
label | 549fa0d0-db69-437f-8e0b-810e4387df32 |  | note | Frequency - Each lot
label | 3ba72404-c947-4c09-925b-649f7abef00f |  | note | Inspection / Test Method - Testing; Review
label | 2deac1ec-42ea-4347-b843-bcd88a776ef1 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 7 - Binder Content for AC Lot Acceptance
label | 2aa8e892-9bee-4bde-99d9-2f11f6bf7c6f |  | note | Action - W
label | 49e09839-fb91-49f3-bb09-5778853f3a37 |  | note | Reference - 1.8 Section 400 - Asphalt and Surface Treatment (Contract FRA TIISP 19/19A (KRUP))
label | cc2908e5-e0ed-4054-ba70-7f86273ccc97 |  | note | Requirement - Bitument content to measured in extracted AC cores
label | 2a967aab-68ac-492c-8fca-4efb23e496b1 |  | note | Frequency - Each lot
label | fc72ea7f-4623-40b6-8882-9825b3cb82fe |  | note | Inspection / Test Method - Testing; Review
label | d930652d-923c-4f13-95e6-67814135ad83 |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 8 - Temperature
label | ed884a42-003b-4a1a-8abe-8e04856f68bd |  | note | Action - H
label | fdf34e63-4850-4a60-bbf2-7c895082cf8b |  | note | Reference - Section 404.09 - Production of Asphalt (Contract FRA TIISP 19/19A (KRUP))
label | 7c93f29c-5cf9-45b5-9196-e157bf909262 |  | note | Requirement - As per Table 404.091
label | 5b97e94d-3d45-4e10-a0b7-fe999f3b4c35 |  | note | Frequency - Every production
label | 2a8e2ee0-5a06-44c6-99c2-b74c2b82ef1a |  | note | Inspection / Test Method - Visual
label | da9070e7-f104-4723-b636-06455192a41a |  | note | Responsibility - Asphalt Plant Operator; Quality Assurance
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Tack Coat
label | d43e6916-ab3e-4745-8c17-1428f0a9c8b4 |  | note | Action - W
label | aea80fc4-ae58-4726-8df8-a484ede070b6 |  | note | Reference - Section 404.15 - Tack Coat(Contract FRA TIISP 19/19A (KRUP))
label | b64f1117-5205-4d62-b79a-4b8802e6b94d |  | note | Requirement - Tack coat should be applied to the cleaned asphalt or sealed surface on which asphalt is to be placed unless the unsealed surface has been primed in which case a tack coat is not required unless otherwise directed or specified. It must be sprayed in a uniform film over the entire road surface. Application rate shall be 0.15 to 0.3L/m2 (60% bitumen content) or 0.3 to 0.6L/2 (30% bitumen content) except for joints and chases where rate shall be doubled
label | 6889c01a-0ece-4952-8e94-ff27cfbc40ff |  | note | Frequency - Every section
label | f8dc753f-24c2-4dcb-8d78-d88542ac2742 |  | note | Inspection / Test Method - Visual
label | 74cd6148-d1a7-49e6-8bed-c10a96b3ceae |  | note | Responsibility - Project Engineer; Quality Assurance
checkpoint-status |  |  | checkpoint | 10 - Delivery
label | 67879a44-e99d-4044-ab03-d804f4cca2b4 |  | note | Action - W
label | 08cec5d0-da65-43e0-b58a-ba1faf973ee0 |  | note | Reference - Section 404.16 - Delivery (Contract FRA TIISP 19/19A (KRUP))
label | c8ac018f-6842-46e6-b6c8-0e523c022b85 |  | note | Requirement - Asphalt delivered to the site which is segregated, has been overloaded, is too cold, contains separated binders or uncoated particles which does not comply with the specification shall be removed from the site at the Contractor's expense. Where asphalt is measured by other means and for lump sum contracts, the Contractor shall make delivery dockets available for inspection on request by the Engineer
label | bf019396-e5fa-45e2-bbb7-3b1a4bbf55b9 |  | note | Frequency - Each delivery
label | ab20b030-1656-4307-b314-47244b86cfab |  | note | Inspection / Test Method - Visual
label | 99e7e564-cdeb-49d3-adc4-c5feb2d7249e |  | note | Responsibility - FRA Engineer
checkpoint-status |  |  | checkpoint | 11 - Joints and Junctions
label | dd4ab7ce-cc2b-4a66-8ba6-14f553e67ac3 |  | note | Action - W
label | 4cb08ba3-5bd3-47fc-b46f-270fafc06685 |  | note | Reference - Section 404.17 - Joints and Junctions (Contract FRA TIISP 19/19A (KRUP))
label | 03f0622c-65f2-4b32-bc4a-b1b9ca5fad44 |  | note | Requirement - Location of all joints shall be planned before work commences to achieve specified offsets between layers and final position of joints in the wearing course. All joints shall be well bonded and sealed and the surface across the joint shall meet the requirement of Clause 404.23(b).All cold joints and abutting concrete edges shall be heavily tack coated. Transverse Joints - Offset from layer to layer by not less than 2m. Longitudinal Joints - Offset from layer to layer by not less than 150mm and shall be within 300mm of the traffic lane line or the cnetre of traffic lane. Shall be parallel to the traffic unless otherwise specified. Junctions - Where new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planning as pecified in Section 403. At side streets and median opening - 600mm. Through carriageway with a speed limit of 80km/h or less - 3m.
label | 86cf48d5-e6d3-47cd-8873-dbf70496f000 |  | note | Frequency - Every section
label | 541345ee-5eef-411a-ba6b-3e87a2e65bb7 |  | note | Inspection / Test Method - Visual
label | 64f5186a-23d3-4134-8566-362b08e00e7b |  | note | Responsibility - Project Engineer
checkpoint-status |  |  | checkpoint | 12 - Compacton
label | c46178f2-0e9f-44af-a63d-f98d93615aa0 |  | note | Action - W
label | e653ffd4-173c-4915-95d7-c934dcf7dfad |  | note | Reference - Section 404.22 - Requirements of testing and Acceptance of Compaction (Contract FRA TIISP 19/19A (KRUP))
label | e6dc94dc-64d3-4ac5-8092-7154f99bd031 |  | note | Requirement - Where the total quantity of particular size or type supplied under the contract exceeds 200tonnes, compaction shall be tested and accepted on a test lot basis. Unless specified or agreed by the Engineer acceptance of compaction for all asphalt work will be on procedural basis. This shall be in accordance with VicRoads Code RC 500.05 - Acceptance of Field Compaction.
label | eb14ef12-d131-4aba-816f-6fc06857c149 |  | note | Frequency - Every Lot
label | 6edbed84-d592-41e7-8449-9386c68f6623 |  | note | Inspection / Test Method - Visual
label | 27e6a76c-07d2-4849-8ee2-2804c4080532 |  | note | Responsibility - Project Engineer; Quality Assurance
checklist-flat |  |  | checklist | ITP 005 - Kerb and Channel | itp |  |  |  | Yes | ITP 005 - Kerb and Channel | a6cc9338-219c-4e75-9b29-58c2ed8d0ac0
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - Sub Contract and suppliers
label | 5f27fb7f-2073-4b4e-b6cb-81c8b47fdbb9 |  | note | Reference: Higgins
label | 8ca73f57-f4d7-41f0-bc73-2e571881a7ad |  | note | Requirement: Ensure that Sub contract and supplier agreements are signed
label | f97d1820-d7a3-41a3-8c66-35068886ad3b |  | note | Frequency: As Required
label | 2ab26ae8-23b4-4195-9e42-23696ba067b4 |  | note | Hold Point
label | 262cc0e1-5d42-43eb-bac7-b5866a0aa2f9 |  | note | Responsibility: Project Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - TMP
label | ddaa4d2f-a850-4dd3-83b9-85d0ace294a2 |  | note | Reference: Higgins
label | 07d95c2d-56ed-49d3-8ead-989b9f61ef4a |  | note | Requirement: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | cd4b2db6-227d-4ad5-8354-f628f0b99a59 |  | note | Frequency: As Required
label | 6a8fd770-4403-437b-9006-297116f70f06 |  | note | Hold Point
label | bb852747-7f97-4547-8c42-b3ae01de5367 |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Design
label | 853f04d6-73c4-40d5-bb32-249ba7d51c68 |  | note | Reference: Higgins
label | ce9cd3fa-fe78-46b9-96e4-02970eea5a68 |  | note | Requirement: Ensure that Design is approved and Drawings are of the latest revision. Check drawing Register.
label | 9db1fe6e-3786-46ef-b541-f4a7761e5074 |  | note | Frequency: Prior to Commencement
label | 50e72b45-ceb2-49cc-941f-e414cccc44fa |  | note | Hold Point
label | c73bffce-e76c-46fb-9037-763d4b47c651 |  | note | Responsibility: Supervisor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Survey setout - Setting out works
label | 9e4d5eb6-5000-4a35-b37c-8b3da6e9198e |  | note | Reference: Higgins
label | 972decfe-d43d-446a-a302-82d1fafaad5f |  | note | Requirement: Check constructed sub base is within level tolerance
label | 1eaf2bdd-4472-4660-b2e2-07eec7035fd5 |  | note | Frequency: Prior to commencement
label | 7587cf5d-9936-41f5-b077-8d229b7c60f8 |  | note | Hold Point
label | 2954ba6b-faa3-4e58-8f3b-4c90898108e0 |  | note | Responsibility: Surveyor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Survey setout
label | 8f3cd1ff-6c7e-4970-94b5-6f750f886149 |  | note | Reference: Higgins
label | a3463f40-6c96-4af9-a248-0c8c68b41de7 |  | note | Requirement: set out kerb line and level at 1m offset to EOS or to suit site/ supervisor.
label | 6798111b-75d9-48cb-b496-e5042a4ef4b6 |  | note | Frequency: Prior to commencement
label | 05d39df6-9f8a-47bd-9296-3129f0e7d122 |  | note | Hold Point
label | be788b72-c746-4e47-a405-2370a5d6f195 |  | note | Responsibility: Surveyor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material Compliance - Kerbs
label | 82702ebe-2c16-4ff3-b31d-9de0cf1ae954 |  | note | Reference: FRA Roadworks standards and Specification; Section 604 - Precast Concrete Kerb; Section 601 - Concrete for incidental construction
label | 92eae785-ce6d-4e92-b319-17153d241580 |  | note | Requirement: Ensure the concrete Mix is as per the specification requirement in section 601 of FRA roadworks standards and Specifications
label | 3848c077-a981-45c1-a148-063b8c2492ae |  | note | Frequency: As required
label | d2e68f00-5b2b-40b7-9a8e-3eb83863e82f |  | note | Hold Point
label | 4e130582-d15c-4893-897b-00426b874b7d |  | note | Responsibility: Procurement officer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material Compliance
label | b5ccb450-653c-446d-820b-4a7bd1e30c99 |  | note | Reference: Signed contract volume 2 - Contract drawings
label | 091415de-b03c-4826-9ab6-2b53968dd074 |  | note | Requirement: Ensure the slip form moulds match the dimensions of the design kerb as per drawing details on drawing number R502-4 of signed contract volume 2
label | abb09aaf-7624-4078-b124-f236bfe7a647 |  | note | Frequency: As required
label | 45e5f98e-bd6f-4eeb-a12c-e1b9f3e08add |  | note | Hold Point
label | 369d6b6c-ef88-484e-adad-7a7621b5b889 |  | note | Responsibility: Procurement officer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material Compliance - Concrete for channel and kerbs
label | 8bb3ba7e-a9cc-4795-a516-e50eb9095f0b |  | note | Reference: FRA Roadworks Standards and Specification; Section 601 - Concrete for incidental construction
label | b735e063-f521-4977-b366-87e890efc9c6 |  | note | Requirement: Concrete material requirements to meet clause 601.02 (a) and testing to be carried out as per clause 601.02 (b)
label | 354818a5-0f3d-4ce3-9631-a92b4f045d8f |  | note | Frequency: 1 test per 50m3; 1 test per strength if less than 50m3 per day
label | f8fb2318-418f-463d-bb4d-73545fb803c9 |  | note | Hold Point
label | 745f8748-9e1c-450a-bca3-d9b48df8086e |  | note | Responsibility: QA Manager/ procurement officer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Construction - Stringing
label | 67596925-cfd8-4510-9513-bc625116b5f8 |  | note | Reference: FRA Roadworks standards and Specification Section 604 - Precast Concrete Kerb
label | 4c2cfb6c-af29-4e32-b23e-6859fecc656b |  | note | Requirement: 1) Kerbing Subcontractor to set out steel pins and stringline to design levels and identify catchpit locations
label | 5661457f-5c3b-46d6-86f5-5944827d14dd |  | note | 2) Subcontractor Stringline to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | 612425c9-c066-4f62-9c93-60169b4cd720 |  | note | 3)Site Engineer to mark kerb type at transition.
label | 4253d97e-8c7b-4290-9849-50f955cdb069 |  | note | 4) Kerbing Subcontractor to place steel plate cover over catchpits.
label | af9656c0-a59b-4d22-b3c8-f7bdcda9cae9 |  | note | 5) The kerb shall be set so that the top conforms to the line and grade specified within a tolerance of 10mm.
label | ddc8dd7e-4005-4e83-b9c8-33b483619576 |  | note | Frequency: As required
label | d8367265-cfb1-4eb8-849e-14a74646ee05 |  | note | Witness Only
label | b08b7b0b-d524-4db5-8e7a-17a11ade6d50 |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction - Slip Forming
label | a10d752f-c204-40ec-b44e-8158b7ca8304 |  | note | Reference: FRA Roadworks standards and Specification. Section 604 - Precast Concrete Kerb
label | 5236ea9a-65fa-406f-93d7-d14219b47351 |  | note | Requirement: 1) Check correct Kerb & Channel profile is installed onto kerb Machine
label | 00d37316-23c8-4af0-8e02-58a29accdab9 |  | note | 2) Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | b9d43c19-cb3d-427d-a859-ca9e9d6e382e |  | note | 3) Slip form Kerb & channel to be monitored by Site Engineer and ensure the levels are within the tolerances.
label | ba2f58b2-ae48-473f-b9f6-1ec2f2a4f9a0 |  | note | 4) Cement Screed formed onto kerb & Channel to have an even and smooth steel trowel finish with no ponding.
label | 8fb42de4-4fc5-4d97-aad4-cc30b0f0f4fa |  | note | 5) Expansion joints to be formed at 5m centres.
label | 00b7c4b7-07e4-461b-bd39-e0d37a52d320 |  | note | Frequency: As required
label | 7729f4fd-6edd-4847-8d8b-8ebb087de934 |  | note | Witness Only
label | c99c4b02-fff5-4dcd-b44b-1d286df1a76f |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction - Tie in Within Pre Cast Components
label | 83452f52-5b46-43ad-a6bd-3d377b398f10 |  | note | Reference: FRA Roadworks standards and Specification. Section 604 - Precast Concrete Kerb
label | 87a4dda2-bb96-4c9b-82c9-33983cd698b1 |  | note | Requirement: 1) Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | 33fa8e42-7e80-4636-a62a-74229509a4b4 |  | note | 2) Catchpit frame, grating and back entry kerb installed at correct level
label | 27d805f2-7b86-4478-b4ba-16930b92e23e |  | note | 3) Aprons are formed around grating frames.
label | 6deec401-2bfb-400f-b42a-49d634377ef1 |  | note | Frequency: As Required
label | 0a9f923d-a0dc-42ed-9c41-4b9cbf8e42e8 |  | note | Witness Only
label | e3bde7c9-cf08-495a-96fb-eef137f9a18a |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Survey As-Builts
label | d73cdb90-ecfe-47dc-9a3b-58ffb4ff42d5 |  | note | Reference: FRA Roadworks Standards and Specification; Section 160.17 - Contract closeout Record Documents
label | e906ee64-891e-4ead-920b-cae8a002e975 |  | note | Requirement: Ensure all drainage lines comply with design prior to carrying on with next construction process
label | 148a7826-6d9a-4bf2-8c1d-1ba25ec252d6 |  | note | Frequency: Upon Completion
label | 8c9de200-cb4a-45d7-a779-6af2b092115d |  | note | Responsibility: Surveyor
checklist-flat |  |  | checklist | Lower Basecourse Construction - AP40 |  |  |  |  | Yes | Lower Basecourse Construction - AP40 | add9d1d9-9da5-4ee8-b7f1-4b9275b47fc1
checkpoint-status |  |  | checkpoint | Location
text | 6bad41fd-d59e-5bda-96ca-ebca52a58283 |  | textbox | Location Details - Chainage
checkpoint-status |  |  | checkpoint | Pre Construction Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Straight Edge
checkpoint-status |  |  | checkpoint | Proof Roll
checkpoint-status |  |  | checkpoint | Nuclear Density Meter
checkpoint-status |  |  | checkpoint | Light Weight Deflectometer
checkpoint-status |  |  | checkpoint | Falling Weight Deflectometer
checkpoint-status |  |  | checkpoint | Benkelman Beam
checkpoint-status |  |  | checkpoint | Additional Information
text | a72cbe04-8dca-59cf-ad4d-8f888d909389 |  | textbox | Additional Information
checklist-sectioned |  |  | checklist | ITP 001 - Basecourse | itp |  |  |  | Yes | ITP 001 - Basecourse | b075f95b-12ea-431b-a498-6e8451ab2b33
checkpoint-group |  |  | section | AP40 for Granular Overlay With reduced content of Fines
checkpoint-status |  |  | checkpoint | AP40 - Basecourse
label | c3820e04-ec76-4d8e-8cd9-c64c0fb5e095 |  | note | Reference: Signed Contract - Volume 1
label | 296db915-d6e4-475f-a7d9-d65acf646b34 |  | note | Section 6 - Employers Requirements
label | 060c7ebb-c2f5-4709-b822-3afc7eb183d6 |  | note | Section 300 - Pavement Construction
label | 7f68f726-a347-43ae-8273-e3df2a2f6fd3 |  | note | Section 6 - Employers Requirements
label | ef70ecb1-1a4d-41ca-99b7-3ae9bbd962e8 |  | note | Fiji Roads Authority
label | 45893b17-c2de-44ac-a937-b5d56e1f91ba |  | note | Section 301 - Materials for Pavement Construction
label | 4384964a-86c7-4202-92a5-48ee12a43f9f |  | note | Requirement: AP40 with reduced fines to comply with the specification requirement as per below
label | 4e9f8464-4576-467b-994e-60e4f2fc60e0 |  | note | Crushing Resistance greater than 100KN and wet/ dry strength ratio greater than 60%
label | 1e08ef4e-5a45-4b4a-a0e5-c5608b454e5e |  | note | Los Angeles Abrasion - Max. 40%
label | 27b4f8a2-5f9c-4d39-8313-aebb0535308f |  | note | Plasticity Index - 0 - 6%
label | 11d39528-f9de-4401-9262-e4f1650f2133 |  | note | Sand Equivalent - Min. 50%
label | 66f4a19f-751c-48b9-9c51-f89d1d771384 |  | note | Liquid Limit - Max. 30%
label | a4fb3565-1840-48ac-a893-587ab143a39a |  | note | California Bearing Ratio - Min. 80%
label | d935dfda-5f13-4ca1-b001-9ff111e79f7f |  | note | Flakiness Index - Max. 35%
label | 544a25e3-09af-4d4b-90e0-daff45924cf1 |  | note | Frequency:
label | c7cf7f5c-5a4f-4655-a568-791fe6b50994 |  | note | Grading and Atterberg Limits = On each production day - One per 750 tonnes or part thereof
label | ff46a48c-9856-402f-9435-9f48ea1b9d3f |  | note | Moisture Content = On each production day - One per 750 tonnes
label | e1643fd6-a541-4fe9-a2e0-6c3b3476cbdd |  | note | California Bearing Ratio = One per 2000 tonnes
label | 0a79d9d2-3f1a-48d5-9312-c1aaa41c9147 |  | note | Degradation Factor = One per 2000 tonnes on each production day
label | 5b049f85-177a-4bee-a191-0f0614560a1a |  | note | Los Angeles Value = One per 2000 tonnes on each production day
label | 99344c75-3568-40ff-a63f-8187f20b0263 |  | note | Sand Equivalent = One per production fortnight
label | e5c381c5-8d60-405e-82e6-f31158eb260f |  | note | Flakiness Index = One per production fortnight
label | 88cceb9a-3585-4bbc-a61b-8a145a257213 |  | note | Crushed Particles = One per production fortnight
label | 7c744fe1-c569-4f6f-b3ce-b42d63ef9519 |  | note | Polished Stone Value = Not used
label | 9a68a280-1a59-4f83-bc05-9acf50641541 |  | note | hold Point
label | d862ede5-9e45-4d0b-98ac-af0731c3e899 |  | note | Responsibility: Higgins Project Engineer/ Smec
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Granular Overlay Construction
checkpoint-status |  |  | checkpoint | Construction - Basecourse
label | be22d36e-3d68-4b0a-9c42-d689864d0e00 |  | note | Reference: FRA Roadworks Standards and Specification
label | 251d1acd-54be-49a1-aec8-3baef9f4a4b1 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | b86bea50-47d9-4827-8b2d-43c47eab6a54 |  | note | Requirement: Construct AP40 unbound, with reduced content of fines compacted in layers of maximum 200mm.
label | 23f2303c-3b55-402f-8061-b1fc19185ebc |  | note | Frequency: 4000m2
label | a6d0e29e-d205-4529-b110-1b1f7ed32d7f |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Dipping - Level Tolerance
label | b5bba46a-3f35-42fa-8e00-f6ff0cc93a78 |  | note | Reference: FRA Roadworks Standards and Specification
label | 0dca2b4b-5808-4f53-b259-318839ce4db8 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 118ed139-5c0a-4808-b9e9-05923b145f96 |  | note | 304.041 - Level tolerances at the surface of pavement courses
label | 2c6ba7e9-5047-435c-8cee-f427f18afe93 |  | note | Requirement: Table 304.041 Level Tolerances at the Surface of Pavement Courses
label | 121c0c66-5ef5-4234-9fa1-0bb9e344fc2a |  | note | Lower Subbase (mm) +15 to -25 / Upper Subbase (mm) +10 to -25 / Base (mm) +15
label | 1bd6ed8f-fccf-4c0c-8fa5-2c401e8b1a4d |  | note | Frequency: 4000m2 per lot Every 20m longitudinal
label | 842cc224-af9e-423d-af47-246c35a7eb65 |  | note | Hold Point
label | 60735b7c-607d-4c16-a90a-f37e34216f0c |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | f79a8281-631d-48ea-ae47-30f85fdc2b18 |  | note | Reference: FRA Roadworks Standards and Specification
label | 3e68fac9-5545-4b96-a2ef-9f5979581d39 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 448111c4-3b1d-43be-ab40-15f093ca4a3f |  | note | 302.13 - Compaction Procedure and requirements for testing and acceptance of compaction
label | 449c55f1-05fc-4dcb-b242-bac62382da77 |  | note | Requirement: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six (6)
label | 53899876-bf7b-4fc3-9eba-341d22fd8e4d |  | note | Frequency: 4000m2
label | 65602195-c1c9-40d9-8cfd-ecc108e31714 |  | note | Hold Point
label | ec9832cc-ef2f-4272-b69b-09437d5b9d5f |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | d61a9649-0e00-49a4-af4a-c745f484e642 |  | note | Reference: FRA Roadworks Standards and Specification
label | a1cd8cb9-c322-454b-9583-491ca3176527 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | e745e777-33ae-47bb-b8a8-5e2739412f4f |  | note | 302.14 - Test Rolling
label | 53f0f564-ca6b-427d-a83d-9029f02cf20d |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | 7850a7f4-3d8d-4e5d-a284-c3cbb36d300a |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | de05ce05-071f-4078-bb1d-fde8ea0bb257 |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | 46826c56-6359-4238-bd97-3c5d3f8d4de1 |  | note | Frequency: 4000m2
label | da8fffb5-d098-4962-88be-4decffe9e2e8 |  | note | Hold Point
label | 3c89b5fa-09e2-4110-9bfd-708081af5905 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pre Seal Requirement - Moisture Content
label | c5dde0e9-c2ee-4647-89cc-355b603acdcc |  | note | Reference: FRA Roadworks Standards and Specification
label | 7272217b-2afc-4c47-bb0a-debd2ca996bb |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 5f6ec81b-8446-465e-9e11-1d85285183a6 |  | note | 302.17 - Preparation for Sealing
label | e4b6bd38-726f-42ad-9d32-aa49bcfb1e31 |  | note | Requirement: Moisture content as specified in clause 302.17 (b) where required by the Engineer.
label | ab634520-5fd4-4b2a-9d88-912724f14781 |  | note | The mean moisture ratio shall be determined from 6 randomly selected location as a percentage of the OMC based on modified compaction.
label | 8bfe8171-858c-413d-a5bf-72ffd9050e0d |  | note | Frequency: 6 test per lot if required by the Engineer.
label | 75312f9c-e356-44aa-bbed-e11a8b2b98df |  | note | Responsibility: SMEC/ Higgins Engineer
checklist-flat |  |  | checklist | Subgrade (Carriageway) - AP65/AP75 |  |  |  |  | Yes | Subgrade (Carriageway) - AP65/AP75 | b26f46e7-7d29-4dde-b543-6bbe84781915
checkpoint-status |  |  | checkpoint | Location
text | 0e78618d-617a-5835-8183-2028575539f1 |  | textbox | Location Details - Chainage
checkpoint-status |  |  | checkpoint | Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Straight Edge
checkpoint-status |  |  | checkpoint | Proof Roll
checkpoint-status |  |  | checkpoint | Nuclear Density Meter
checkpoint-status |  |  | checkpoint | Scala
checkpoint-status |  |  | checkpoint | Undercut / Fill
checkpoint-status |  |  | checkpoint | Light Weight Deflectometer
checkpoint-status |  |  | checkpoint | Falling Weight Deflectometer
checkpoint-status |  |  | checkpoint | Benkelman Beam
checkpoint-status |  |  | checkpoint | Additional Information
text | 24f5fec8-3d8b-5032-8bb7-48ea9400b9a4 |  | textbox | Additional Information
checklist-flat |  |  | checklist | Sub-base (Existing Pavement Testing) - AP65/AP75 |  |  |  |  | Yes | Sub-base (Existing Pavement Testing) - AP65/AP75 | b2d13733-3a1d-4af6-a004-57f30d1fdc4d
checkpoint-status |  |  | checkpoint | Location
text | 301deeb8-3975-53f7-a4a9-b69cd9b8710d |  | textbox | Location Details - Chainage
checkpoint-status |  |  | checkpoint | Level Checks - Dipping / Stringline
checkpoint-status |  |  | checkpoint | Level Checks - Straight Edge
checkpoint-status |  |  | checkpoint | Proof Roll
checkpoint-status |  |  | checkpoint | Nuclear Density Meter
checkpoint-status |  |  | checkpoint | Scala
checkpoint-status |  |  | checkpoint | Undercut / Fill
checkpoint-status |  |  | checkpoint | Light Weight Deflectometer
checkpoint-status |  |  | checkpoint | Falling Weight Deflectometer
checkpoint-status |  |  | checkpoint | Benkelman Beam
checkpoint-status |  |  | checkpoint | Additional Information
text | 48486e83-f3f0-5bbc-9c6e-6fa17f1c8da5 |  | textbox | Additional Information
checklist-sectioned |  |  | checklist | ITP 002 - Basecourse Option 2 | itp |  |  |  | Yes | ITP 002 - Basecourse Option 2 | bbd750de-5e6a-4a2f-8b61-36e17903db0f
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | AP40 - Basecourse
label | e0cce45d-eff1-42f5-b59d-f150a641d172 |  | note | Reference: Signed Contract - Volume 1
label | 76e1b0de-c7a0-4ece-99dd-5483b1e0f111 |  | note | Section 6 - Employers Requirements
label | 6353a1cb-203b-401f-91bb-4b8dd4ebd038 |  | note | Section 300 - Pavement Construction
label | 871ee19d-e798-40ba-8bb7-028d2c1ee90c |  | note | Section 6 - Employers Requirements
label | 2c31437e-4f51-4023-9fe6-0e392be47645 |  | note | Fiji Roads Authority
label | 31735718-f6a1-4d85-b3f2-6c53784a1d21 |  | note | Section 301 - Materials for Pavement Construction
label | a34d7172-e8db-4140-94d2-37dd1769b021 |  | note | Requirement: AP40 with reduced fines to comply with the specification requirement as per below
label | 85dd86ad-2152-41b6-8e12-35336201e31b |  | note | Particle Size Distribution - Table 301.051
label | 72d718e0-0a42-4ac8-b1ce-a37098620e10 |  | note | Crushing Resistance greater than 100KN and wet/ dry strength ratio greater than 60%
label | 3c5f47d5-eb02-48da-b983-6e6593e99451 |  | note | Los Angeles Abrasion - Max. 40%
label | a091f65e-013d-421b-90da-4fab1e583c57 |  | note | Plasticity Index - 0 - 6%
label | b80e9860-6465-40a6-a025-5d31e3136aea |  | note | Sand Equivalent - Min. 50%
label | 53560868-1fb1-4b90-b002-1755796fad75 |  | note | Liquid Limit - Max. 30%
label | 0c883e16-29c5-4e91-aae5-2d42b5af0a1d |  | note | California Bearing Ratio - Min. 80%
label | 78cf9469-bef7-4d29-ac9f-b754dd91b6b0 |  | note | Flakiness Index - Max. 35%
label | e7861815-e59b-4329-8522-ec6226e94aef |  | note | Frequency:
label | 362c4c8c-14f8-4cdd-8f9d-6893c725b073 |  | note | Grading and Atterberg Limits = On each production day - One per 750 tonnes or part thereof
label | f4fb3bdf-d15a-42bc-bb7e-9ca1c899bc7a |  | note | Moisture Content = On each production day - One per 750 tonnes
label | a273e18e-5e39-435d-9c48-0ab94b12cf45 |  | note | California Bearing Ratio = One per 2000 tonnes
label | 5a782998-9d2d-456e-9880-0512b72736a8 |  | note | Degradation Factor = One per 2000 tonnes on each production day
label | cbe9441e-2c3e-4958-a1bb-556542c7e376 |  | note | Los Angeles Value = One per 2000 tonnes on each production day
label | 0e4e19dc-6cbc-43ac-93e9-85635a38f7ed |  | note | Sand Equivalent = One per production fortnight
label | d49c4433-74bf-40b2-a38f-af709d7d94d5 |  | note | Flakiness Index = One per production fortnight
label | c8e98da5-f27d-4bb7-bad0-c4d2174399bc |  | note | Crushed Particles = One per production fortnight
label | d73b2ead-7d57-472c-b015-ef0176c3b2c7 |  | note | Polished Stone Value = Not used
label | c10c5d5e-19a6-48fd-984b-0acb94b36e14 |  | note | hold Point
label | 9cf51e32-5324-420b-8ef0-beb16aaad033 |  | note | Responsibility: Higgins Project Manager/ Smec
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Stabilization of Existing unbound Layer
checkpoint-status |  |  | checkpoint | Milling - Remove existing Seal
label | a0bc5259-c472-41ea-9234-a8cadbfafe56 |  | note | Requirement: Remove and disposal of existing chip seal to approved stockpile or as instructed by the Engineer to Contract
label | 7b356fe5-ee06-49a4-a5d6-13d751027aa3 |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Stabilisation - Stabilise Existing unbound layer
label | 0340325a-19e0-44bf-a3fc-3a8e5bc93f0d |  | note | Reference: FRA Roadworks Standards and Specification
label | fdb523b5-2a47-4826-a2bd-4b73f6933230 |  | note | Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | 4e5281e4-5c42-4a61-a95f-5f4e80ba3b71 |  | note | Requirement: Insitu stabilization with 3% cement of the top of existing unbound pavement layers compacted in 200mm layers max.
label | ef13acc1-28fe-48bd-bfbc-2c6501738725 |  | note | Where extra over cement required, confirmation from Engineer to contract to be taken.
label | 03c1f4ed-9c19-4d29-95be-6012b2b56f87 |  | note | Frequency: 4000m2
label | d83c78f2-3549-473a-9574-b7b90c4d98d1 |  | note | Responsibility: Higgins Supervisor
label | af9940b8-e5e9-49b9-a083-b4e95f7606ec |  | note | Requirement: Table 304.031 Level Tolerances at the Surface of Pavement Courses
label | 558ca17a-f6b8-48a4-b0bb-95284f1281e6 |  | note | Subbase (mm) + 10 to -25 / Base (mm) +15
checkpoint-status |  |  | checkpoint | Level Check - Dipping
label | 1874f1c0-44a6-4858-892a-b32eab4aa069 |  | note | Reference: FRA Roadworks Standards and Specification
label | 69a201b9-26eb-46eb-9429-b88204ebf535 |  | note | Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | d0f2e611-b381-4e3d-a562-98db5a433fa3 |  | note | 304.03 - Conformity with Drawings
label | fb504c82-4fed-4aac-8c9f-c1f278c16885 |  | note | Requirement: Insitu stabilization with 3% cement of the top of existing unbound pavement layers compacted in 200mm layers max.
label | b6be16e2-2345-4ec7-b9a0-9320227d9f9d |  | note | Where extra over cement required, confirmation from Engineer to contract to be taken.
label | 9970b6a9-e39a-40d5-9713-53acde019c50 |  | note | Frequency: 4000m2 per lot Every 20m longitudinal
label | 6c2a2cb3-3dba-4194-a6b7-2332e5697852 |  | note | Hold Point
label | 7d8a1343-b25d-466d-8f62-6df5e41ff17e |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | a22433f5-0a0d-4a1b-8211-b76d2704b4be |  | note | Reference: FRA Roadworks Standards and Specification
label | 6274c917-737d-4fad-87fd-f880054b2a34 |  | note | Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | 85268f7e-6714-4847-893c-5245ed84a3ba |  | note | 304.10 - Test Rolling
label | 282ea946-72c7-4ad4-9030-9bc604720fda |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | e74b211f-dd3b-4813-875e-ebaf389fdfc0 |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | 51e79f48-f6fa-4351-9431-41022cf9b9dc |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | 899af74a-b592-47a9-bfc8-43ca9d6c3bb4 |  | note | Frequency: 4000m2
label | f1bccfc0-2655-46e7-a74d-945967eb8545 |  | note | Hold Point
label | 0932a785-0d77-4921-b01c-d766785c9ea4 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | d1b4b743-9760-4e54-a348-77123ce1531c |  | note | Reference: FRA Roadworks Standards and Specification
label | 670b1501-4d1b-49ef-926c-903fedc803ec |  | note | Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | 0ddf0580-1cbe-4efb-80f9-a745e6be1f6e |  | note | 304.13 - Requirement for testing and acceptance of compaction and strength.
label | 2afcaad7-1553-4ee8-a0de-9d08cae7a69b |  | note | Requirement: density ratio obtained from six randomly selected test sites within the lot is not less than 95%
label | a0a8ecea-8d43-4cd1-bd86-7942e31c5bde |  | note | Frequency: 6 test per Lot
label | d30e1553-4060-4931-9028-b054e6402371 |  | note | Hold Point
label | ba7c8d6b-879f-4e6a-9b93-2cd221458701 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction of AP40 Unbound Layer
checkpoint-status |  |  | checkpoint | AP40 Layer - AP 40 layer unbound
label | f6f17d65-e5fb-4546-9191-5d5512625f27 |  | note | Reference: FRA Roadworks Standards and Specification
label | 36474a0b-cb09-446e-b541-bc0f794f5040 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | e7fad299-0df8-4162-9316-137d0d46599a |  | note | Requirement: Construct Ap40 unbound pavement layer (typical 150mm) compacted in Layers( Max. 200mm/ layer)
label | 8bd447d0-7b42-4c70-81ed-461cf2cc0b7d |  | note | Frequency: 4000m2
label | bdab0831-f9fc-4e8e-83a4-8dd52ab05e22 |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Dipping - Level Tolerance
label | 1a3f50d0-a3ba-468f-99a6-e27f6ec62ccb |  | note | Reference: FRA Roadworks Standards and Specification
label | 60a12e8c-bb21-442a-8ceb-6b1dd08c2716 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 26300284-3914-4684-9cba-9e521a6e5d40 |  | note | 304.041 - Level tolerances at the surface of pavement courses
label | f91b1c23-e5fd-4871-a31a-f8554318f4ca |  | note | Requirement: Table 304.041 Level Tolerances at the Surface of Pavement Courses
label | b1736f09-5f26-4d69-9f5d-1a300f71fa1e |  | note | Lower Subbase (mm) +15 to -25 / Upper Subbase (mm) +10 to -25 / Base (mm) +15
label | 325555f8-8968-49e7-939b-b93a48cced06 |  | note | Frequency: 4000m2 per lot Every 20m longitudinal
label | 2adec525-49ed-4fdf-a6ff-e4eabf2b7702 |  | note | Hold Point
label | 9ee964b0-5518-44a5-9064-1b68b5939528 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | fe659b53-1e16-4ea4-9bdf-22fd96105d2d |  | note | Reference: FRA Roadworks Standards and Specification
label | 564bb508-c353-4cb1-b25b-66a841f80b42 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | cbda66ea-d8c2-439d-baa9-eb44cdc976fa |  | note | 302.13 - Compaction Procedure and requirements for testing and acceptance of compaction
label | f59a4155-544f-4b87-a899-9c4e07c49297 |  | note | Requirement: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six (6)
label | 45af8bf5-8769-4ef2-9cea-96bb9a1ab441 |  | note | Frequency: 4000m2
label | f8da7b89-2bb4-4f31-b10a-a8b11e40235f |  | note | Hold Point
label | 6e07b88b-aa16-49f0-b782-1d5bc0bcfe6a |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | cf86e25d-159f-49f0-84e6-4837e8ca2503 |  | note | Reference: FRA Roadworks Standards and Specification
label | 06f93dcf-8104-489f-a6f4-325f454bdac7 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | d0adac5b-b0ba-440b-a133-0829e9f731d2 |  | note | 302.14 - Test Rolling
label | efe970ca-5c93-45fc-bf3e-a63ba54ba79e |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | 3b0ac67c-ba18-4288-a64f-fcd448d7c2a4 |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | 22fdaf2b-d822-441d-9269-0a447f4c4915 |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | fd29988f-ae1c-4eb1-befa-04bc3cbfd9e1 |  | note | Frequency: 4000m2
label | 1bbd7285-8b48-423a-ab75-3a0a4f031cf0 |  | note | Hold Point
label | 1b4f551a-105e-46b6-b037-e7c776308475 |  | note | Responsibility: SMEC/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pre Seal Requirement - Moisture Content
label | 5a0fe71f-ae0d-4585-9052-6d898feca710 |  | note | Reference: FRA Roadworks Standards and Specification
label | 9bd9d4f4-1b8c-4b05-9f7a-9828a95ba5d2 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 06bcc075-e3b8-474b-9099-3275a6b3702d |  | note | 302.17 - Preparation for Sealing
label | 93a6de0b-de0e-4cb4-84c9-c0e20764ac22 |  | note | Requirement: Moisture content as specified in clause 302.17 (b) where required by the Engineer.
label | b601f19a-7f33-4e95-acd8-5b2ae720787d |  | note | The mean moisture ratio shall be determined from 6 randomly selected location as a percentage of the OMC based on modified compaction.
label | cb329966-b8c1-42b9-b5f6-fb26ebce8e90 |  | note | Frequency: 6 test per lot if required by the Engineer.
label | f79146cf-57b6-4e50-bdca-10f7deb3900a |  | note | Responsibility: SMEC/ Higgins Engineer
checklist-flat |  |  | checklist | ITP 007 - Drainage | itp |  |  |  | Yes | ITP 007 - Drainage | c4b1aed2-e1e2-467a-b061-7973a238375f
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - Sub Contract and suppliers
label | 6d111b71-dc05-418f-8f69-aedf62f71304 |  | note | Reference: Higgins
label | 54e18c27-4815-4a07-8bb2-55467fea1902 |  | note | Requirement: Ensure that Sub contract and supplier agreements are signed
label | 5a5f8676-e50e-42d6-91d8-50d2b8337fab |  | note | Frequency: As Required
label | 5fecf6ce-1528-46e0-8d37-9308fdc044e8 |  | note | Hold Point
label | 58375626-8698-4655-b2ea-b6d00bcd56eb |  | note | Responsibility: Project Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - TMP
label | 2f0786bd-a40d-4322-ae41-6fce927cdf70 |  | note | Reference: Higgins
label | c4ed170e-b08c-4fce-a7eb-a92f6f145583 |  | note | Requirement: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | d16d8263-152e-49c1-924a-ce79fc4702fc |  | note | Frequency: As Required
label | eb66ada1-5c10-4213-8440-ddf43610a217 |  | note | Hold Point
label | 3d9de863-ace5-4bef-a1ab-1badb6e17645 |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - Induction
label | a691dce9-3c75-4638-9e26-579b1bb13f83 |  | note | Reference: Higgins
label | 8ea1d56e-09f2-4e87-b876-da13f62ee6e2 |  | note | Requirement: Ensure all sub-contractors and suppliers go through Kings Road Upgrade Project A induction.
label | 36f28afd-d4c7-4a7b-8af8-0aed99bf08a4 |  | note | Frequency: As required
label | 7e1d239b-328e-4f6d-a1f3-2f0dc6359ded |  | note | Hold Point
label | 1241b222-c4b9-4342-9f92-1088681e349c |  | note | Responsibility: Supervisor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Design
label | dbeaeb17-a999-41b7-a046-1438ae2f6b93 |  | note | Reference: Higgins
label | 4c0b99a4-4473-40a5-8d41-bffa339e6942 |  | note | Requirement: Ensure that Design is approved and Drawings are of the latest revision. Check drawing Register.
label | da3fb834-9ec4-4a2d-a0e6-eb04933bb16f |  | note | Frequency: Prior to Commencement
label | 92d74a4e-d623-43fb-a740-aa54af283f1b |  | note | Hold Point
label | 973d6da3-867f-4adb-a06c-265f4a18e493 |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Installation of Erosion and sediment controls - Erosion and sediment control
label | 192b2767-6ef1-4756-8e7d-02eeab267c3c |  | note | Reference: Higgins
label | 4ec540c0-24be-4c4d-9e4f-8fa20ad73e29 |  | note | Requirement: Ensure that Erosion & Sediment Control ITP & Checksheets have been completed and submitted to the Territorial Authority
label | 9a73c6e1-ea3d-48fc-a4a2-a1082eeea8f8 |  | note | Frequency: Prior to commencement
label | 2d56d71f-4ce8-4b06-8734-0eebd3eca65b |  | note | Hold Point
label | 4b6a72c6-8381-4b13-97b7-fba87c9448b9 |  | note | Responsibility: Supervisor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Survey setout - Setting out works
label | a64aadb3-03d2-4178-8741-00eeee927249 |  | note | Reference: Higgins
label | f61359b1-cf4d-48c4-a266-2f5c7819ea5a |  | note | Requirement: Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | 1f2b4d99-13b2-4547-a8a5-526b934fa6f9 |  | note | Frequency: Prior to commencement
label | b771cb28-95d9-41a4-a7a4-042cbfad3cf5 |  | note | Hold Point
label | 32a11965-7550-4c7e-b0bc-6ca7587e8b20 |  | note | Responsibility: Surveyor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Locate existing services by hand digging - Existing Services
label | ea953bfc-163d-4081-a01f-b80e3557f357 |  | note | Reference: Higgins
label | 843c935c-cd43-4146-9ca8-94d1ccb831a0 |  | note | Requirement: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | 6a54de77-d2b4-4103-826a-fb28623da9aa |  | note | Frequency: Prior to commencement
label | 562e7747-543e-4ca1-849d-4dcfcb45f1b7 |  | note | Hold Point
label | 1830f260-352e-4df2-b422-45d40dec6643 |  | note | Responsibility: Supervisor
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Trenching and Excavation - 1.1
label | 12278e37-b554-43b8-b71f-ea3092ccac57 |  | note | Reference: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | 06d98556-8133-434f-a598-211bea1950cc |  | note | Requirement: Inspect trench profile and ensure it is correct to lines and levels to design
label | 4b82dd07-0600-4b6f-b8b6-901b33789fc0 |  | note | Frequency: As Required
label | 9d775220-20d5-405d-9bb2-ed62f61c2927 |  | note | Visual Inspection
label | 40face6c-6ce2-40bb-bc56-bf74547524ac |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Trenching and Excavation - 1.2
label | 8ac33409-0371-43b9-b05e-7cdebcd2e155 |  | note | Reference: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | 00008a6b-9f5e-45cd-9c72-66c84319de8d |  | note | Requirement: Ensure trench width is sufficient to provide enough space on either side of the pipe. The trench shall not be less than the diameter of the pipe plus 250mm and not greater than the diameter of the pipe plus 350mm.
label | 9239cb8b-675d-4548-9c8d-c4fa5e3b8e32 |  | note | Frequency: As Required
label | 5672c285-082a-4757-a82a-ff34748c4de5 |  | note | Visual Inspection
label | 1bfebbd7-e868-4d81-a2b5-ca804acebca6 |  | note | Responsibility: Supervisor
checkpoint-status |  |  | checkpoint | Foundation Compliance - 1.1
label | 93ba657e-5698-4c75-b717-5a1ab8381e3b |  | note | Reference: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | 649e5bcb-d9db-4dfb-9d97-8795d8d3df12 |  | note | Requirement: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | 46fdac4f-dbc2-44d8-90e1-97ebaa025996 |  | note | Frequency: Test formation level on completion of excavation to check if undercut required
label | 52723b95-56d7-44d4-ba5e-b64566062214 |  | note | Responsibility: Every Network
checkpoint-status |  |  | checkpoint | Foundation Compliance - 1.2
label | bc4305be-c8b2-47c5-9328-4eaedfb1d804 |  | note | Reference: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | 5621d2a9-3e67-4b7f-bb92-73e3af13e855 |  | note | Requirement: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | b4ca4af3-43f5-45ce-a1fd-2135f6169bc9 |  | note | Frequency: If water is in the trench backfill with Drainage 40/20 material ensuring Bidium cloth is pinned to the bottom of the trench. 40/20 material to extend to the mid point on the pipe or to the water table (whichever is highest).
label | de75c2ee-bc8b-4d24-8ebc-a3a20ccb888b |  | note | Responsibility: Every Network
checkpoint-status |  |  | checkpoint | Foundation Compliance - 1.3
label | 97009a99-2959-4d86-a1e0-ba9775dabe6b |  | note | Reference: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | 6a258609-ab5e-49a8-b863-2b322c598d9a |  | note | Requirement: FRA Roadworks standards and Specification. Section 502.09 - Excavation
label | b8fda480-56e0-4853-80c5-7c1838badd9d |  | note | Frequency: The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations. The Engineer shall be notified at least 24 hours prior to the inspection.
label | b83cac0f-c56e-42e9-88c7-5bb3136553f2 |  | note | Responsibility: Every Network
checkpoint-status |  |  | checkpoint | Pipe Bedding Material Compliance - bedding material
label | 7b794568-d17a-4d02-8521-0bd2e18295db |  | note | Reference: FRA Roadworks standards and Specification. Section 502.10 © Bedding for drainage pipe system
label | 3ed4b926-021a-4471-94dd-b7212a715185 |  | note | Requirement: a bedding of granular filter material of thickness between 25 mm and 50 mm shall be placed across the bottom of the trench. The bedding shall be tamped and screened or graded to level.
label | ba93d960-0111-4067-be8e-24f698364355 |  | note | Frequency: N/A
label | 227286d1-c889-4aa3-b9e4-87161eef2429 |  | note | Visual Inspection
label | af8f2416-2457-45a4-8a6b-c350478790f4 |  | note | Responsibility: Site Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | Bedding - Pacing of bedding
label | d8ad6e26-1465-427f-9aca-574302d6a2d2 |  | note | Reference: FRA Roadworks standards and Specification. Section 502.10 © Bedding for drainage pipe system
label | 3bff7d4e-492e-4a82-b6e4-e67aa5e73f40 |  | note | Requirement: 1) Ensure correct thickness of bedding is placed and compacted. For details on thickness of bedding, refer to drawing R501-16 on signed contract volume 2. 2) Ensure bedding material is compacted.
label | 227c31c1-69d5-49a8-a2bf-6e45f31c4dc6 |  | note | Frequency: Every Network
label | c1a9c61b-49d5-4ba8-bbd6-f5ff99115393 |  | note | Visual Inspection
label | 73e712bc-fb5c-4984-96b4-f2a665ab1367 |  | note | Responsibility: Site Engineer/ Supervisor
checkpoint-status |  |  | checkpoint | Material Compliance - Pipes and precast units
label | 99b19075-ce87-4b51-8bb2-0a2e68536fd2 |  | note | Reference: FRA Roadworks standards and Specification. Section 502.04
label | bafe766c-5e80-494b-a2ba-d948b0e26eac |  | note | Requirement: Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | 1ce63675-d61b-459e-8a64-fa621006b795 |  | note | Frequency: Each delivery site
label | cb074de6-80a4-490f-b23f-0302ff92e5bf |  | note | check
label | 27c5ab95-40d2-47d7-b626-815a1eaf95ec |  | note | Responsibility: Site engineer/ Engineers Representative
checkpoint-status |  |  | checkpoint | Material Compliance - cast in-situ drainage components
label | a464abb0-4cc8-4642-9896-6d7b9a1ee1df |  | note | Reference: FRA Roadworks standards and Specification. Section 502.08
label | 5a22fe8d-f8b5-4cda-8f95-6a7d03768376 |  | note | Requirement: If any cast insitu component i.e. Headwalls is to be completed on a separate ITP or inspection form Insitu Concrete
label | f517863d-151d-40f6-8f52-03888273d844 |  | note | Frequency: As required
label | 0f67704f-5197-4102-b92a-ed6721b575e6 |  | note | Hold Point
label | 0bfdcbf0-8761-4fbf-a5ca-c93dda38d4b7 |  | note | Responsibility: Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Installation - Pipe Laying
label | 0f180e8e-bbcf-4654-bd03-4aacb8d5fe87 |  | note | Reference: FRA Roadworks standards and Specification. Section 502
label | 7134763c-1458-438e-845c-be6fca0e7cc1 |  | note | Requirement: 1) Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm. 2) Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness.
label | b7a4d751-894b-4d64-917a-187c04421339 |  | note | Frequency: 1 test per 50m3. 1 test per strength if less than 50m3 per day
label | 53c7f744-e9c7-4ed2-8081-cd3efd7abc4b |  | note | Hold Point
label | 4a5e5273-eb93-46cf-9dc0-9b2eb7140c7c |  | note | Responsibility: Supervisor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Installation - Engineer Pre backfill inspection
label | 7b917138-b38f-4f15-bba8-d1e3f07c720e |  | note | Reference: FRA Roadworks standards and Specification. Section 502
label | 9d957fc6-0b8f-4f12-885b-bd30b88cb230 |  | note | Requirement: 1) Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps. 2) The pipes shall be laid with the variation between the specified invert level and invert level. 3) Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
label | 91182f2a-a7ce-467e-aed8-d380bafb01a4 |  | note | Frequency: As required
label | 4bc65344-74d4-4d74-9e73-6e506c55975b |  | note | Witness
label | 21bbea3d-b2fa-492b-a053-c7dfc5a3bee4 |  | note | Responsibility: Engineers Rep
checkpoint-status |  |  | checkpoint | Backfilling
label | 600944a5-94fc-411a-95ef-2d5e885ba1f3 |  | note | Reference: FRA Roadworks standards and Specification. Section 502.10 (h)
label | 9f08cb59-5140-4131-9d1e-359d123a0e3a |  | note | Requirement: Backfill 150mm lifts to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | 6a50b443-51cb-4902-8999-c48f69cc4c0c |  | note | Frequency: Check Every 20m
label | e1ef1403-6172-447b-b628-4812a244372f |  | note | Witness
label | bea578b9-bca4-49ab-b7b1-b674c6984ec0 |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Survey As-Builts
label | fcab2018-30d6-4788-a7c7-969f02237386 |  | note | Reference: FRA Roadworks Standards and Specification. Section 160.17 - Contract closeout Record Documents
label | 05e580d3-3b2d-408d-b76f-8b6e9347112d |  | note | Requirement: Ensure all drainage lines comply with design prior to carrying on with next construction process
label | c8b40d71-309b-43cd-82e4-d93f2b53a62d |  | note | Frequency: Upon Completion
label | 249afd08-007e-4f80-9b1b-5f0bbda28c33 |  | note | Responsibility: Surveyor
checklist-sectioned |  |  | checklist | ITP 003 - Basecourse Option 3 | itp |  |  |  | Yes | ITP 003 - Basecourse Option 3 | e0719289-826b-4cc5-a1c4-89c8271fc203
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | AP40 - Basecourse
label | 89aac7a4-43f8-4d65-b304-9180537cf885 |  | note | Reference: Signed Contract - Volume 1
label | b10e241f-3177-4e5c-a1f8-77dfae638dd0 |  | note | Section 6 - Employers Requirements
label | 4ce35f18-064e-4762-80b5-6c86c93e88f4 |  | note | Section 300 - Pavement Construction
label | cb5d6cb0-8274-4d77-96cd-518e93ac0872 |  | note | Section 6 - Employers Requirements
label | 403b45f4-c797-47ad-8fae-235357557504 |  | note | Fiji Roads Authority
label | d1703d69-9e28-4a8d-a27c-e7229d555a43 |  | note | Section 301 - Materials for Pavement Construction
label | eb2098b7-e590-4097-b95a-b997a7099078 |  | note | Requirement: AP40 with reduced fines to comply with the specification requirement as per below
label | 77ae2101-894c-4df2-a35f-47065f6c74d3 |  | note | Particle Size Distribution - Table 301.051
label | c81d8167-3150-47c5-958d-b7829a14e863 |  | note | Crushing Resistance greater than 100KN and wet/ dry strength ratio greater than 60%
label | 4ae73434-d3be-4316-ac64-ff00c1f41757 |  | note | Los Angeles Abrasion - Max. 40%
label | ad589402-4065-4312-908e-8fcd9d515a62 |  | note | Plasticity Index - 0 - 6%
label | 3e89a7bd-aa27-4d52-8f62-3e4e22532e69 |  | note | Sand Equivalent - Min. 50%
label | 7956da34-562c-403d-935c-805c4a454645 |  | note | Liquid Limit - Max. 30%
label | 63e89af4-442c-4ff4-8017-1de0afd5eacc |  | note | California Bearing Ratio - Min. 80%
label | ba23ec80-030f-4253-a946-d866666bdee9 |  | note | Flakiness Index - Max. 35%
label | f3a9aefa-8d05-41fc-aee9-7d0da95a18f6 |  | note | Frequency:
label | 88b1d2f2-cd72-403c-95db-07a0010d99fb |  | note | Grading and Atterberg Limits = On each production day - One per 750 tonnes or part thereof
label | 1d2f4289-6f7f-4295-8605-121cd8417dea |  | note | Moisture Content = On each production day - One per 750 tonnes
label | ac0a3fd9-8437-4a8d-b6b6-7300faa6b722 |  | note | California Bearing Ratio = One per 2000 tonnes
label | 785f6534-a91d-48af-a9da-65c069df19fa |  | note | Degradation Factor = One per 2000 tonnes on each production day
label | 38c8ab07-812e-409c-8330-32f1e9d1355e |  | note | Los Angeles Value = One per 2000 tonnes on each production day
label | 936a6a1a-9638-4c62-8e78-56feeaac6dd1 |  | note | Sand Equivalent = One per production fortnight
label | 5f7b4361-85d6-4806-8060-7a958bcbcf52 |  | note | Flakiness Index = One per production fortnight
label | 11744edd-f2a4-41cc-8279-72c7df9d8929 |  | note | Crushed Particles = One per production fortnight
label | 60093701-890e-4183-a2da-57fa398d5fb1 |  | note | Polished Stone Value = Not used
label | a4fe0f18-3095-4fe5-a4de-8dc63d358ff1 |  | note | hold Point
label | aaddc1f3-9b1e-4fc2-b644-b3cdfae39dfc |  | note | Responsibility: Higgins Project Engineer/ Smec
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Stabilization of Existing unbound Layer
checkpoint-status |  |  | checkpoint | Milling - Remove existing Seal
label | 9a1a85e8-97eb-4c2e-82ad-455369d65b19 |  | note | Requirement: Remove and disposal of existing chip seal to approved stockpile or as instructed by the Engineer to Contract
label | ed625dfb-63e3-432c-974b-769b23d0dd2a |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Level Check - Dipping
label | 615c7d9b-cc9a-4d42-886d-d7767dd1ea38 |  | note | Reference: FRA Roadworks Standards and Specification
label | 83daab8e-7bdd-441b-b1e9-7dfab52b51ec |  | note | Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | 47b33173-ae9a-4d2f-b409-388a83e28613 |  | note | 304.03 - Conformity with Drawings
label | 8a4081c2-0507-4e20-8b62-c4335e18a6bc |  | note | Requirement: Table 304.031 Level Tolerances at the Surface of Pavement Courses
label | 015c6c02-b70d-4b6d-ba5d-22000d453a2d |  | note | Subbase (mm) + 10 to -25 / Base (mm) +15
label | b3a0c2de-45d2-427b-97d4-0c1cb79a9329 |  | note | Frequency: 4000m2 per lot Every 20m longitudinal
label | 30277934-e32d-4e10-bd0a-3a5b2bae6213 |  | note | Hold Point
label | 9f48d190-5924-41e2-bd98-02614318c879 |  | note | Responsibility: FRA Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | 5eeb2ade-7eae-47e3-92df-3bb5b5a503b0 |  | note | Reference: FRA Roadworks Standards and Specification
label | 57ed2a86-233d-4076-bf50-857bd0257bf2 |  | note | Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | 6cc1c7c5-ad4b-44da-bb04-79e04da51fe4 |  | note | 304.10 - Test Rolling
label | eb434069-774f-4fcb-9ffb-fa7b5ed4add8 |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | 6070f07f-d75d-419e-8bd7-037cfb5c91ac |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | 95063893-508a-40bd-9284-83ac61203c48 |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | c904c0eb-0d01-4151-9b79-6b8ff3e6353a |  | note | Frequency: 4000m2
label | 6d2e201d-bc43-44f4-8cbe-a45f00c10c90 |  | note | Hold Point
label | 9218abf9-e803-4de5-aa0e-19ce8cbbb021 |  | note | Responsibility: FRA Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | af2debde-62a2-4696-bc2b-440c6c477ede |  | note | Reference: FRA Roadworks Standards and Specification
label | e605e484-0e04-45bb-af09-51b9a8cac008 |  | note | Section 304 - InSitu Stabilisation of pavements with Cementitious Binders
label | a5d7c0a2-b5c7-456b-afaa-c8fde0838304 |  | note | 304.13 - Requirement for testing and acceptance of compaction and strength.
label | b45a6ef0-f1e2-46e8-839b-2ef75f78ebb6 |  | note | Requirement: density ratio obtained from six randomly selected test sites within the lot is not less than 95%
label | 7c79dcf3-1b3a-4977-83b2-1c260aaecc75 |  | note | Frequency: 6 test per Lot
label | 5a6b9cfe-4fd3-4968-affb-0d0e9777128c |  | note | Hold Point
label | b812169f-07b8-447a-907a-b75186c3525b |  | note | Responsibility: FRA Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Reinstatement by reuse/ recycling existing stockpiled material
checkpoint-status |  |  | checkpoint | Reinstatement - Pavement layer
label | 44fbc098-eadd-4382-bcd2-3eb6ac924052 |  | note | Reference: FRA Roadworks Standards and Specification
label | d90f4b9b-885a-4ef4-bb34-2ae3d28525c0 |  | note | Section 200 - Earthworks
label | ea1f7841-dd21-4577-8eaf-3b8b634df897 |  | note | Requirement: spread and compact existing unbound pavement materials (previously stockpiled), non-stabilised in layers (max.200mm)
label | e0514b79-86b7-46b0-be48-1f831cc4937a |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | 6802a969-cd96-4640-ab58-864f25a7c632 |  | note | Reference: FRA Roadworks Standards and Specification
label | 06b2bb3b-c3ed-448d-9406-0847dfa3c038 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | d8bf6e86-40b2-46e4-b9f9-55e308ad636b |  | note | 302.14 - Test Rolling
label | 153af45b-b0f6-4d69-9900-d2ebc5f9935f |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | 626c8219-abb5-4a9d-8896-87fbc5854b13 |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | 1b035ede-9266-4b48-80f6-a872a6a294a3 |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | 028ffcc2-1ff3-4510-8881-441fbc23359a |  | note | Frequency: 4000m2
label | b75cfa5c-ecec-44a5-a37d-d44e16e7f51b |  | note | Hold Point
label | 39e8ed69-f53e-4c54-b382-cb16c4b9b029 |  | note | Responsibility: FRA Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Construction of AP40 Unbound Layer
checkpoint-status |  |  | checkpoint | AP40 Layer - AP 40 layer unbound
label | 77d62c00-159c-4698-9365-732d1b7cc0a4 |  | note | Reference: FRA Roadworks Standards and Specification
label | 6c47c4b9-4685-4a6a-99c7-95454f3c4a19 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 6f9af014-3fb8-4674-aebc-ecf97451e7fe |  | note | Requirement: Construct Ap40 unbound pavement layer (typical 150mm) compacted in Layers( Max. 200mm/ layer)
label | 0583e1f0-3ce1-44da-ad77-d89ff95c2f91 |  | note | Frequency: 4000m2
label | 1966758c-b4b3-4f2f-b1be-573916895587 |  | note | Responsibility: Higgins Supervisor
checkpoint-status |  |  | checkpoint | Dipping - Level Tolerance
label | b487d892-0ffc-47e0-bd75-a0a912f4bff9 |  | note | Reference: FRA Roadworks Standards and Specification
label | 600a1a1d-6961-41a7-8f2a-372aaa6b7e65 |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 20cd791c-a708-455b-9e03-d7bccbdca061 |  | note | 304.041 - Level tolerances at the surface of pavement courses
label | b07d51ec-c221-42d5-b444-8531b9b51ac9 |  | note | Requirement: Table 304.041 Level Tolerances at the Surface of Pavement Courses
label | 68ec981b-fa34-42f2-87bd-16d02027191a |  | note | Lower Subbase (mm) +15 to -25 / Upper Subbase (mm) +10 to -25 / Base (mm) +15
label | 5a98c21b-e98b-4771-a146-a614feecad97 |  | note | Frequency: 4000m2 per lot Every 20m longitudinal
label | 7b95204d-9133-4aa3-bea8-eff858dfb1ea |  | note | Hold Point
label | 82ea1775-f25a-4f29-b744-34032f8bb11a |  | note | Responsibility: FRA Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Compaction - NDM Testing
label | 791d8642-733f-4aa1-8789-3ad173c39245 |  | note | Reference: FRA Roadworks Standards and Specification
label | 9e8f2095-6e09-4e02-a900-947fcacfa99a |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | cba06779-dde5-4c8f-84f8-65b09019a7b6 |  | note | 302.13 - Compaction Procedure and requirements for testing and acceptance of compaction
label | f0f6a60a-31aa-4eaa-8d6b-5230378bbca7 |  | note | Requirement: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six (6)
label | 2fcabc29-5ca8-418d-80c8-aa8715a0837e |  | note | Frequency: 4000m2
label | 8a20837e-1e75-4275-b87a-25399850edf5 |  | note | Hold Point
label | 50b9d654-c539-493e-b8ca-a81459465c96 |  | note | Responsibility: FRA Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Testing - Proof Rolling
label | 49d0e224-65e5-4113-b030-2e27c976c7fd |  | note | Reference: FRA Roadworks Standards and Specification
label | b9acd394-ed25-489c-9357-c8eee915c58b |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 326d00b2-72b5-4183-a23b-c1c4b78522a7 |  | note | 302.14 - Test Rolling
label | 73e18ebb-e190-4da1-b620-ffee6089af7f |  | note | Requirement: Test rolling shall be carried out by the contractor in the presence of the Engineer prior to placing the next layer.
label | 8da45341-590a-44bf-977f-278e16de9060 |  | note | Steel smooth wheeled roller - mass not less than 12 tonne
label | 2d31a8f7-081e-4ea8-8475-3534216d8974 |  | note | Pneumatic Tyred Plant - mass not less than 20 tonne
label | 398ca022-d6bf-46a3-82d8-5e00e68fe4a4 |  | note | Frequency: 4000m2
label | 0802b5c3-b854-4141-96c2-e3fd7049b8df |  | note | Hold Point
label | fc6ce40e-c9c8-4c0f-99a2-6408af02ee75 |  | note | Responsibility: FRA Engineer/ Higgins Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pre Seal Requirement - Moisture Content
label | bb358384-805e-4af9-b853-da7ff3e81e1d |  | note | Reference: FRA Roadworks Standards and Specification
label | 3f2fadc5-d750-4847-84e1-54a97b73be0b |  | note | Section 302 - Construction of Base and Sub Base Pavement Courses
label | 58d50202-5c9c-4cff-8672-afd8a537ddfc |  | note | 302.17 - Preparation for Sealing
label | 853c9b58-1fb4-4bdd-a255-7743cdc8b566 |  | note | Requirement: Moisture content as specified in clause 302.17 (b) where required by the Engineer.
label | ca747a4f-22e1-40be-ae59-c3b6aef2273f |  | note | The mean moisture ratio shall be determined from 6 randomly selected location as a percentage of the OMC based on modified compaction.
label | dbdac841-cbf8-4b22-8ef3-b43fdde1caa9 |  | note | Frequency: 6 test per lot if required by the Engineer.
label | d7be8a98-bb13-46a8-9d3a-ff49d50f2fb9 |  | note | Responsibility: FRA Engineer/ Higgins Engineer
checklist-flat |  |  | checklist | ITP 007 - Incidental Concrete Construction | itp |  |  |  | Yes | ITP 007 - Incidental Concrete Construction | f7e16a57-4426-4434-8b60-2c41e0857272
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - Sub Contract and suppliers
label | d68b0d39-5701-4f50-b76e-9ee410b22a2c |  | note | Reference: Higgins
label | ea095be7-e0a2-4d13-b316-18a6d2235217 |  | note | Requirement: Ensure that Sub contract and supplier agreements are signed
label | dd7c4ea4-d774-400b-8a41-3256b33789ad |  | note | Frequency: As Required
label | 334610aa-1f78-40fa-8984-b6b7c4a894b5 |  | note | Hold Point
label | ce4426b2-e41b-4a5b-8a76-3aeac36e868e |  | note | Responsibility: Project Manager
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Pre-construction sign offs - TMP
label | 9589c0ee-962e-4e1b-87df-e89d1277c35a |  | note | Reference: Higgins
label | e8ec575f-3b31-4f56-bc0b-90743234152d |  | note | Requirement: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | abdad13f-16cb-4ada-9cae-cfa531554faf |  | note | Frequency: As Required
label | b982f94d-fd3d-4391-beb9-80c1c25aba2d |  | note | Hold Point
label | d6ade96b-9944-434e-9b9b-e6488226001c |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Design
label | c3ae94e7-7651-4352-8f17-fdaeccc76664 |  | note | Reference: Higgins
label | 9806a416-4708-406a-b3e8-14ab13ffa9c6 |  | note | Requirement: Ensure that Design is approved and Drawings are of the latest revision. Check drawing Register.
label | 5751730f-2cee-4cbc-b99a-5f6f7f1e0ee0 |  | note | Frequency: Prior to Commencement
label | c77dfb20-9996-4db5-8aa7-ea997b40b54d |  | note | Hold Point
label | 77208f0e-7be2-46e8-9aea-4227111a30de |  | note | Responsibility: Supervisor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Installation of Erosion and sediment controls 1.1
label | 93efd68f-554d-4e30-a04e-51d92bd6959b |  | note | Reference: Higgins
label | b79fd514-7d09-40cd-af3c-710b4748088c |  | note | Requirement: Ensure that Erosion & Sediment Control ITP & Checksheets have been completed and submitted to the Territorial Authority
label | 0e7da0fd-fc49-4c74-a0de-eb30c6710eac |  | note | Frequency: Prior to Commencement
label | aa07898d-3c7c-424f-b7b5-3f94550a9222 |  | note | Responsibility: Site Engineer/ Environmental Officer
checkpoint-status |  |  | checkpoint | Installation of Erosion and sediment controls 1.2
label | d219a653-822b-4a37-bfa2-925bd03896b6 |  | note | Reference: Higgins
label | 2afa56e2-7b76-4203-a3f9-53df8b62c7dd |  | note | Requirement: Monitor effectiveness of the ESCP Controls throughout the construction process
label | e929e89c-84c6-4cbf-84c8-7797ed88f0ce |  | note | Frequency: Prior to Commencement
label | 4470c4e8-352f-4471-bf88-49ed1128e4db |  | note | Responsibility: Site Engineer/ Environmental Officer
checkpoint-status |  |  | checkpoint | Survey setout - Setting out works
label | c0b2759e-572f-44a6-b60c-8dc808bb5fbd |  | note | Reference: FRA Roadworks standards and Specification. Section 603.04
label | fb292c0f-819e-4e51-ba8e-da8fa61d927b |  | note | Requirement: Set out design features as per contractual Construction drawings (Cast in items, Ducting, Penetrations)
label | a1605d29-ea38-4b80-85e0-d64246f4d8d7 |  | note | Frequency: Prior to commencement
label | 8297987f-be19-4ab1-a9fd-ac4cc3160676 |  | note | Hold Point
label | e0e2e3af-6357-4026-8459-e0dd2653db67 |  | note | Responsibility: Surveyor/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material Compliance - Concrete 30 Mpa
label | 2888dccc-5558-45da-9ce6-14bbc33b593a |  | note | Reference: FRA Roadworks standards and Specification. Section 601 - Concrete for incidental construction
label | ec393ea2-b2a8-416c-989c-b2fc23a484b4 |  | note | Requirement: Ensure the concrete Mix is as per the specification requirement in section 601.02 of FRA roadworks standards and Specifications
label | acaf0a3e-c87d-4134-b8c5-b8edd669fa95 |  | note | Frequency: Every Batch
label | 603c7e58-f01d-48c6-9177-eb1f9bc6ce44 |  | note | Hold Point
label | 61437894-e705-4047-9f2a-311dd8e186c5 |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material Compliance - Concrete 25 Mpa
label | e922ff51-f63d-4b03-89a3-795254f07359 |  | note | Reference: FRA Roadworks standards and Specification. Section 601 - Concrete for incidental construction
label | abf08636-88da-4b4a-872c-2bc7e6de4aa8 |  | note | Requirement: Ensure the concrete Mix is as per the specification requirement in section 601.02 of FRA roadworks standards and Specifications
label | 5722d3da-11cb-46a0-ae4e-c846c42a8990 |  | note | Frequency: Every Batch
label | 7fcc9831-56b9-42a1-bdc2-1719e17e2c10 |  | note | Hold Point
label | e4f9108e-6790-4cab-8f18-c20ed6c3b031 |  | note | Responsibility: Project Engineer/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material Compliance - Concrete strength test for footpath, Bus stop and driveways
label | 6c115cb2-2ba9-41c2-ac22-5f4c88cab6dd |  | note | Reference: FRA Roadworks Standards and Specification. Section 601 - Concrete for incidental construction
label | 6b16a4ad-d6a6-4d39-9840-5c0bd4fec6b6 |  | note | Requirement: Concrete material requirements to meet clause 601.02 (a) and testing to be carried out as per clause 601.02 (b)
label | 4c1d49a0-3f7d-4a22-9fb1-8e1a8a0a6c85 |  | note | Frequency: 1 test per 50m3 .1 test per strength if less than 50m3 per day
label | ea62bcdb-f391-4161-ae8f-7ea9f33d5f98 |  | note | Hold Point
label | 0d84d2dd-b674-43c7-9ad3-b7a2294dc3f6 |  | note | Responsibility: QA Manager/ procurement officer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Material Compliance - Reinforcements
label | eaf2955a-82d3-40f8-a35d-707fd5ac5602 |  | note | Reference: FRA Roadworks Specification. Section 803 - Steel Reinforcement for structures
label | f86d3902-6bbc-4256-b99d-107c9a402684 |  | note | Requirement: 1) Steel Reinforcement shall comply with FRA Roadwork Specifications version 5 (AS/NZS 4671) and shall be the grade called up on the drawings. 2) Any welding or mechanical splicing to be approved in writing by the Design Engineer.
label | 12f5c829-fb6d-40d2-8391-46f37a4bd06f |  | note | Frequency: As Required
label | 6b8eaa73-6d1e-4763-91da-124a02155d88 |  | note | Document Review
label | 0e7d3967-a0b2-40dc-b577-bf4261b1d10c |  | note | Responsibility: QA Manager
checkpoint-status |  |  | checkpoint | Construction - Foundation Acceptance by Engineer's Rep
label | ab71f7ef-62e8-4327-93f3-bf97d1d7be0c |  | note | Reference: FRA Roadworks standards and Specification. Section 601 - Concrete for incidental construction
label | 7959fbfe-b68a-4fe9-bdc4-8abaafa0cd89 |  | note | Requirement: Approval given by engineer's Rep and Signed off Subgrade Approval Checksheet
label | 4215d3cd-a34f-4ecc-9716-2da0c2615a26 |  | note | Frequency: As required
label | a6351c98-70f6-4d7e-9c4a-b8ea974118e2 |  | note | Hold Point
label | 89659ed6-6866-4807-9d67-2f8954695f24 |  | note | Responsibility: Engineer's Rep/ Site Engineer
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | Construction - Concrete pumping Operations
label | bf1fa62b-bfec-4670-a7ae-6ccfd108c25c |  | note | Reference: FRA Roadworks standards and Specification. Section 603.14 - Placing, Compacting and surface Finish
label | 0e740bc3-9fe9-4b9f-9d30-b51d83b3810f |  | note | Requirement: Ensure the Permit to Concrete Pump & Pump Operator Check Sheet has been completed before concrete pumping commences
label | bcbd63e6-9748-4119-84aa-dcb169f550e0 |  | note | Frequency: Every Inspection
label | 4b68dbc9-cfa4-4054-a92c-d046259a0555 |  | note | Witness Only
label | c1b26deb-2de1-4ef6-8fbc-e6090eb59fce |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction - Blinding Concrete (if - required)
label | 629e1c14-b495-4bcd-9ba1-d05f21919d62 |  | note | Reference: FRA Roadworks standards and Specification. Section 603.14 - Placing, Compacting and surface Finish
label | aac48ea3-a94b-41c5-b9cb-3b3c3778e493 |  | note | Requirement: Once blinding concrete layer has been completed the Engineer's Rep to inspect and give approval for the rest of the works to commence
label | 82de4912-52f5-4b6a-8000-bf15c0b0dda0 |  | note | Frequency: Every Inspection
label | c3eed0a9-d86c-4480-a107-a55c8eea9495 |  | note | Witness Only
label | cce05f1d-9b01-4d6b-a149-65d228e97d0a |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction - Temporary Works (Formwork)
label | 4b30ba2f-f706-42de-85c8-3f32f36dc7f5 |  | note | Reference: FRA Roadworks standards and Specification. Section 603.12 - Formwork
label | 3bc49a4d-c050-4fd5-9a65-2dfc363f180d |  | note | Requirement: Formwork to be constructed to design and set to correct line and level as set out by the surveyor
label | b37ff0ce-c036-4dc4-8dbf-dc981d64bc48 |  | note | Frequency: Every Inspection
label | b35a98f9-c689-42d7-bc50-562e8adffcc5 |  | note | Witness Only
label | 6d10319b-c2e2-41d6-b7c1-5afcb3138e67 |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction
label | 6dec6a52-c697-4e07-87f7-430550435f38 |  | note | Reference: FRA Roadworks standards and Specification. Section 603.12 - Formwork
label | 3e1c785b-d909-4f2e-b954-c8ca7f554bf0 |  | note | Requirement: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | 8c865432-ff8a-49a9-9b78-9f23b7fb68b5 |  | note | Frequency: Every Inspection
label | d8940cae-d109-47f7-aa38-a9ed03f1dc42 |  | note | Witness Only
label | d4b5ce49-8349-4db3-b454-013d6ad9fc87 |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction - Reinforcing
label | 1d21d9a8-cac1-4c8a-b337-73d4f2a95f14 |  | note | Reference: FRA Roadworks standards and Specification. Section 603.03 (steel Reinforcement
label | c5c275d0-6e8c-418c-ab14-36be53e7ad0d |  | note | Requirement: 1) Reinforcing steel shall be handled, placed and fixed as per NZS 3109. 2) Check for any cast in items and ensure they are fixed correctly
label | 44008452-ac6f-46fd-b43d-5bea8a9c8343 |  | note | Frequency: Prior to concrete pour
label | f1f407b5-b4ea-4e41-b0e8-68c7cd55b804 |  | note | Witness Only
label | 1e70735e-8edf-4fd1-b125-f739c41220d4 |  | note | Responsibility: Engineer's Rep/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction - Concreting Pumping Operation
label | 724b7f5c-f82b-4068-9dd7-78b27fa24663 |  | note | Reference: FRA Roadworks standards and Specification. Section 603.14 Placign. Compacting and surface finish
label | f7e69206-2dc4-4e94-a7b1-6aa3aacee7ea |  | note | Requirement: Ensure the Permit to Concrete Pump & Pump Operator Check Sheet has been completed before concrete pumping commences
label | ba01eec7-cc49-44ef-bde3-d5a88cadf84a |  | note | Frequency: Prior to commencement
label | cb3a38c4-56aa-40ad-b9d5-da2562b64108 |  | note | Document Review
label | 3c5bf8b6-517b-4a36-9817-c7576bf16e3f |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Construction - Concreting
label | d9643a3f-f02e-4a65-b3c1-6307731f1dd8 |  | note | Reference: FRA Roadworks standards and Specification. Section 603.14 Placign. Compacting and surface finish
label | 727c4fce-716b-4cb6-b5a3-b5052e3460eb |  | note | Requirement: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | 2df1da5b-0590-4c12-809e-30db5765112e |  | note | Frequency: Prior to commencement
label | 1dfc0045-2a78-437b-946e-75a7a7e9dccd |  | note | Document Review
label | b34b800d-8e8f-47d7-b934-9855ef47d596 |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Requirement: Concrete dockets checked for correct mix and concrete site testing undertaken.
label | f58c443a-5d65-43d4-b023-a2e228059402 |  | note | Docket No.:
label | c2730f36-4445-4a54-99ea-e9c8fd3c2829 |  | note | Concrete Mix Strength:
label | 0dc28f85-1226-497c-97cd-69c09273b8dd |  | note | Frequency: Prior to commencement
label | 65e562d1-3414-423b-a0a2-1b8e46852e01 |  | note | Document Review
label | b25b399d-93c4-4f15-a330-44cebf19f767 |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Requirement: All other concrete elements constructed with reference to Section 603 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610 Formwork for concrete.
label | 7b2f2bda-226b-4627-99a4-afa7bca25b27 |  | note | Frequency: At completion of pour
label | a6e73bf4-3d3c-4da3-b607-617fa5be7006 |  | note | Witness Only
label | 0803003e-bb6c-4890-9fcb-9f5b79d166cb |  | note | Responsibility: Engineer's Rep/ Site Engineer
checkpoint-status |  |  | checkpoint | Remove Formwork
label | 25870039-4310-4fed-a780-2cdd48b78135 |  | note | Requirement: Remove formwork as per the approved work methodology
label | 80787bb2-a3e5-43be-b72e-467f133b5290 |  | note | Frequency: Upon Completion
label | 7733aab8-9e8f-4e31-95f3-3d1eada0076e |  | note | Responsibility: Supervisor/ Site Engineer
checkpoint-status |  |  | checkpoint | Survey As-Builts
label | fba4b922-6871-4931-b88b-68d43f4f0a2c |  | note | Reference: FRA Roadworks Standards and Specification. Section 160.17 - Contract closeout Record Documents
label | a63a4c35-a781-445e-93bc-702e86cc432e |  | note | Requirement: Ensure all drainage lines comply with design prior to carrying on with next construction process
label | 6754cf9d-beae-4843-ad6a-31c0cc4553a7 |  | note | Frequency: Upon Completion
label | 4336da74-e860-45b5-b1ac-af1c53b49c62 |  | note | Responsibility: Surveyor