## In-situ Modified BC
Client's Rep. Logo in here |  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | Lot Reference number: FBS01
|  |  |  | Project Name: NOC AWPTs 2022-2023 |  |  |  |  | Date submitted: 14-09-2022
|  |  |  | Construction Process: In-Situ Modified Basecourse |  |  |  |  | Prepared By: Deen Joseph
Client's Rep.: Nigel Green |  | Contractor: Higgins |  | Specification: TS section 507 |  |  |  |  | Approved By: Derek Wisniewski
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
1.1. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
1.1.1 | M4 AP40 Basecourse Aggregates used for overlay | Quality of Fines, either PI or SE or CI | H / M* | 1 per 1,000 m2 | NZS4407:3.4 - PI NZS4407:3.5 - CI NZS4407:3.6 - SE | PI ≤ 5 CI ≤ 3 SE ≥ 40 | IANZ Report | Contractor
1.1.2 | Notes: | Broken Faces Content | H / M* | 1 per 1,000 m2 | NZS4407:3.14 | ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm | IANZ Report | Contractor
1.1.3 | H = Hold point up to approval of Optimisation Testing | Particle Size Distribution | H / M* | 1 per 1,000 m2 | NZS4407:3.8.1 | Check if 50:50 blend of average existing (from TPs) and NZTA M/4 AP40 will meet the FBS grading. | Report using IANZ Reports for AP40 and TP PSDs | Contractor to provide analysis | Designer to advise if "average" blend is acceptable.
1.1.4 | Optimisation of Stabilizing Agent | Indirect Tensile Strength, ITS | H | 1 Optimisation test per aggregate type | NZTA T/19: 2020 | Dry ITS: 175kPa to 400 kPa Soaked ITS: 150 kPa to 350 kPa TSR ≥ 70% | IANZ Report | Contractor
1.1.5 |  | Modified Maximum Dry Density | M | At Optimised Binder selection | NZS 4402.4.1.3 | To determine target density | IANZ Report | Contractor | Required before Stabilisation comences
1..2. BEFORE STABILISATION COMENCES
1.2.1 | Setout section | Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking | M | Prior to each section | Survey | Document existing furniture | Electronic survey files | Contractor
1.2.2 | Production Plan | Plan showing cut lines and sequencing of works | M | Prior to each section | Daily Report | Points covered in NZTA B/5 | Daily Production Plan | Contractor
1.2.3 | Weather conditions | Ambient Temperature (C&L) Material to be stabilised (BE&FBS) | M | Prior to spreading | Measurement | Ambient Temperatures: Cement: > 5°C, Lime: > 10°C Material after stabilisation: BE: > 20°C, FB: > 20°C | Daily work Log | Contractor
1.2.4 | Weather conditions | Wind | M | Prior to spreading cement or lime | Local weather stations | Wind speed < 25 km/hr | Daily work Log | Contractor
1.2.5 | Weather conditions | Rain | M | Prior to spreading cement or lime | Local weather stations | No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material | Daily work Log | Contractor
1.3. STABILISATION OPERATION
1.3.1 | Stabilizing Agent | Cement, GP | M | Per Batch | NZS 3122 | Conform to Specification | Certificate in contractor's site folder | Contractor
1.3.2 | Spreading of powdered stabilising agent (Cement) | Place 1m2 canvas or 0.5m x 0.5m trays along spreader run | M | every 400 m2 every 150m for a 2.4m width | Weigh mat or tray | ± 5% of specified rate | Daily work Log | Contractor
1.3.3 |  | Compare area spread with weight used for each spreader load | M | On-going measurement by computer/load cells | Measurement each run | ± 2.5% of specified rate | Daily work Log | Contractor
1.3.4 | Injection & Mixing of Water | In-situ Stabilisation process | M | On-going visual assessment | Visual and hand squeeze test | Mixed material free of pockets or streaks. Overlaps minimum of 150mm | Daily work Log | Contractor
1.3.5 | Depth of stabilisation | Depth of stabilisation | M | Every 200m | Measurement | +15mm / -5mm from specified depth | Daily work Log | Contractor
1.3.6 | Compaction | Plateau Density Test | W | On first day and then 1 per 20,000m2 unless material or anvil conditions change | Draft NZTA T/24 | To establish suitability of rollers and compaction mode / pattern | Daily work Log | Contractor
1.3.7 |  | Maximum Dry Density | M | 1 per day up to 3,000 m2, 1 per 2,000m2 thereafter | NZS 4402.4.1.3 | For analysis of DoC | IANZ Report | Contractor
1.3.8 |  | Degree of Compaction | H | 5 per 1,000m2 | NZS 4407.4.2.1 (to 100mm and 200mm) and NZS 4407.4.2.2 | Average DoC ≥ 98% Minimum DoC ≥ 95% Refer NZTA T/23 | IANZ Report | Contractor
1.3.9 | Finished Pavement | Crossfall | H | every 20m | Measurement | ± 0.5% of specified crossfall measure 2m apart | Survey | Contractor
1.3.10 |  | Stabilised width | H | 1 every 20m | Measurement | -20mm, +100mm | Survey | Contractor
1.3.11 |  | Surface Shape | H | every 20m | Measurement | < 10mm using 3m straight edge | Survey | Contractor
1.3.12 |  | Surface Levels | H | every 20m | Measurement | -5mm, +15mm | Survey | Contractor
1.3.13 |  | Surface Finish | H | Per Lot | Visual | 1. Larger aggregate held in pace with a matrix of smaller aggregate 2. Smaller aggregate held in place by fine material 3. matrix does not displace under normal trafficking and/or sweeping | Survey | Contractor
1.3.14 |  | Degree of Saturation, DOS | H | 5 per Lot | Measurement | DOS ≤ 80% | IANZ report | Contractor
1.4. FINAL SIGN OFF
1.4.1 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 1st coat CS
Client's Rep. Logo in here |  |  |  | INSPECTION AND TEST PLAN
|  |  |  | Project Name: NOC AWPT |  |  |  |  | Date submitted: 14-09-2022
|  |  |  | Construction Process: 2 coat Grade 3/5 Chipseal |  |  |  |  | Prepared By:
Client's Rep.: Nigel Green |  | Contractor: John Singleton |  | Specification: as referenced |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Engineer's Rep | Contractor | Date
Sealing
2.1.1 | Seal Design | Seal design outlining all design assumptions | H | 1 per seal application type | Review | New Zealand Chip Sealing Handbook | Seal design in contractor's site folder | Designer / Engineer's Rep
2.1.2 | Check raw materials | Sealing Aggregates | M | 1 per source stockpile | Source Properties | NZTA M06 / RNZ 9805:2009 | Certificate in contractor's site folder | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
2.1.3 |  | Sealing Aggregates | M | 1 per source stockpile | Production Properties | NZTA M06 / RNZ 9805:2009 | Certificate in contractor's site folder | Contractor
2.1.4 |  | Adhesion Agents | M | Prior to use |  | NZTA M06 / NZTA M13 | Certificate in contractor's site folder | Contractor
2.1.5 |  | Audit samples | M | 20 kg per stockpile | N/A | Stored in a sealed plastic bag in a covered environment | ITP | Contractor | Retain for testing if required
2.1.6 | Pre-Seal requirements | Visual inspection of surface to be sealed | W | per sealing schedule. 1 Lot = 1 day's production and < 1500m2 | Visual Inspection | NZTA B02 | Contractor's site diary | Engineers Rep | The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
2.1.7 |  | Dry back Moisture Content | H | 9 per Lot | NZS 4407.4.2.1 | DOS ≤ 80% preferably ≤ 70% | IANZ Report | Contractor | Only required if pavement widening extends into trafficked lane
2.1.8 |  | Clegg Hammer | M | 1 CIV per 10m 1 Lot < 300m | Clegg Impact Value Test | Average CIV > 40 Min. CIV > 35 | Contractor's CIV form appended to Contractor's daily diary | Contractor
2.1.9 | Sealing | Bitumen / Bitumen Emulsion for Chip Sealing | M | 2 samples per distributor | Penetration grade testing | NZTA M01 - Tables 1, 2, 3 and 5 | Certificate in contractor's site folder | Contractor | Sampling as per ASTM D140 or equivalent
2.1.10 |  |  | M |  | Durability | NZTA M01 - Table 5 | Certificate in contractor's site folder | Contractor | Refer notes in clause 5 of NZTA M01
2.1.11 |  | Spraying Temperature (Bitumen only) | W | Ongoing with non-going heat sensing gauge | Non-contact heat sensing gun | NZTA P03 - Table 2 | ITP | Contractor
2.1.12 |  | Residual Bitumen Application Rate | M | Reconcile day's production | Dockets vs Area | ± 0.1 L/m2 | Site diary | Contractor
2.1.13 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR | NCR | Engineer's Rep
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.