## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - In-Situ Modified Basecourse - SH57 Currins | itp |  |  |  |  | ITP - In-Situ Modified Basecourse - SH57 Currins
section | 1.1. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
checkpoint | 1.1.1 - M4 AP40 Basecourse Aggregates used for overlay
label | Detail of Activity - Quality of Fines, either PI or SE or CI
label | Action (Hold, Monitor, Witness) - H / M*
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | Inspection / Test method -
label | • NZS4407:3.4 - PI
label | • NZS4407:3.5 - CI
label | • NZS4407:3.6 - SE
label | Acceptance Criteria -
label | • PI ≤ 5
label | • CI ≤ 3
label | • SE ≥ 40
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.1.2 - Notes:
label | Detail of Activity - Broken Faces Content
label | Action (Hold, Monitor, Witness) - H / M*
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | Inspection / Test method - NZS4407:3.14
label | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.1.3 - H = Hold point up to approval of Optimisation Testing
label | Detail of Activity - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - H / M*
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - Check if 50:50 blend of average existing (from TPs) and NZTA M/4 AP40 will meet the FBS grading.
label | Record documents - Report using IANZ Reports for AP40 and TP PSDs
label | Responsibility - Contractor to provide analysis
label | Comments - Designer to advise if "average" blend is acceptable.
holdpoint | HOLD POINT
checkpoint | 1.1.4 - Optimisation of Stabilizing Agent
label | Detail of Activity - Indirect Tensile Strength, ITS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
label | Inspection / Test method - NZTA T/19: 2020
label | Acceptance Criteria -
label | • Dry ITS: 175kPa to 400 kPa
label | • Soaked ITS: 150 kPa to 350 kPa
label | • TSR ≥ 70%
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.1.5 - Optimisation of Stabilizing Agent
label | Detail of Activity - Modified Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - At Optimised Binder selection
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - To determine target density
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Required before Stabilisation comences
section | 1.2. BEFORE STABILISATION COMENCES
checkpoint | 1.2.1 - Setout section
label | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Document existing furniture
label | Record documents - Electronic survey files
label | Responsibility - Contractor
checkpoint | 1.2.2 - Production Plan
label | Detail of Activity - Plan showing cut lines and sequencing of works
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | Inspection / Test method - Daily Report
label | Acceptance Criteria - Points covered in NZTA B/5
label | Record documents - Daily Production Plan
label | Responsibility - Contractor
checkpoint | 1.2.3 - Weather conditions
label | Detail of Activity -
label | • Ambient Temperature (C&L)
label | • Material to be stabilised (BE&FBS)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading
label | Inspection / Test method - Measurement
label | Acceptance Criteria -
label | • Ambient Temperatures:
label | ○ Cement: > 5°C, Lime: > 10°C
label | • Material after stabilisation:
label | ○ BE: > 20°C, FB: > 20°C
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.2.4 - Weather conditions
label | Detail of Activity - Wind
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - Wind speed < 25 km/hr
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.2.5 - Weather conditions
label | Detail of Activity - Rain
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | Record documents - Daily work Log
label | Responsibility - Contractor
section | 1.3. STABILISATION OPERATION
checkpoint | 1.3.1 - Stabilizing Agent
label | Detail of Activity - Cement, GP
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | Inspection / Test method - NZS 3122
label | Acceptance Criteria - Conform to Specification
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 1.3.2 - Spreading of powdered stabilising agent (Cement)
label | Detail of Activity - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | • every 400 m2
label | • every 150m for a 2.4m width
label | Inspection / Test method - Weigh mat or tray
label | Acceptance Criteria - ± 5% of specified rate
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.3 - Spreading of powdered stabilising agent (Cement)
label | Detail of Activity - Compare area spread with weight used for each spreader load
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.4 - Injection & Mixing of Water
label | Detail of Activity - In-situ Stabilisation process
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
label | Inspection / Test method - Visual and hand squeeze test
label | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.5 - Depth of stabilisation
label | Detail of Activity - Depth of stabilisation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 200m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +15mm / -5mm from specified depth
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.6 - Compaction
label | Detail of Activity - Plateau Density Test
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day and then 1 per 20,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.7 - Compaction
label | Detail of Activity - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day up to 3,000 m2, 1 per 2,000m2 thereafter
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | Record documents - IANZ Report
label | Responsibility - Contractor
checkpoint | 1.3.8 - Compaction
label | Detail of Activity - Degree of Compaction
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (to 100mm and 200mm) and NZS 4407.4.2.2
label | Acceptance Criteria -
label | • Average DoC ≥ 98%
label | • Minimum DoC ≥ 95%
label | • Refer NZTA T/23
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.9 - Finished Pavement
label | Detail of Activity - Crossfall
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria -
label | • ± 0.5% of specified crossfall measure
label | • 2m apart
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.10 - Finished Pavement
label | Detail of Activity - Stabilised width
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - –20mm, +100mm
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.11 - Finished Pavement
label | Detail of Activity - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 10mm using 3m straight edge
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.12 - Finished Pavement
label | Detail of Activity - Surface Levels
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - –5mm, +15mm
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.13 - Finished Pavement
label | Detail of Activity - Surface Finish
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Lot
label | Inspection / Test method - Visual
label | Acceptance Criteria -
label | • 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | • 2. Smaller aggregate held in place by fine material
label | • 3. matrix does not displace under normal trafficking and/or sweeping
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.14 - Finished Pavement
label | Detail of Activity - Degree of Saturation, DOS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per Lot
label | Inspection / Test method - Measurement
label | Acceptance Criteria - DOS ≤ 80%
label | Record documents - IANZ report
label | Responsibility - Contractor
holdpoint | HOLD POINT
section | 1.4. FINAL SIGN OFF
checkpoint | 1.4.1 - Non-conforming results
label | Detail of Activity - Assessment of all test results for conformity
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | Inspection / Test method - Site Inspection
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents - NCR
label | Responsibility - Engineer's Rep
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
signoff | Add Signature
checklist | ITP - 2 coat Grade 3/5 Chipseal - SH57 Currins | itp |  |  |  |  | ITP - 2 coat Grade 3/5 Chipseal - SH57 Currins
section | Sealing
checkpoint | 2.1.1 - Seal Design
label | Detail of Activity - Seal design outlining all design assumptions
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per seal application type
label | Inspection / Test method - Review
label | Acceptance Criteria - New Zealand Chip Sealing Handbook
label | Record documents - Seal design in contractor's site folder
label | Responsibility - Designer / Engineer's Rep
holdpoint | HOLD POINT
checkpoint | 2.1.2 - Check raw materials
label | Detail of Activity - Sealing Aggregates
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - Source Properties
label | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 2.1.3 - Check raw materials
label | Detail of Activity - Sealing Aggregates
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - Production Properties
label | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 2.1.4 - Check raw materials
label | Detail of Activity - Adhesion Agents
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to use
label | Acceptance Criteria - NZTA M06 / NZTA M13
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 2.1.5 - Check raw materials
label | Detail of Activity - Audit samples
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 20 kg per stockpile
label | Inspection / Test method - N/A
label | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | Record documents - ITP
label | Responsibility - Contractor
label | Comments - Retain for testing if required
checkpoint | 2.1.6 - Pre-Seal requirements
label | Detail of Activity - Visual inspection of surface to be sealed
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | • per sealing schedule.
label | • 1 Lot = 1 day's production and < 1500m2
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - NZTA B02
label | Record documents - Contractor's site diary
label | Responsibility - Engineers Rep
label | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint | 2.1.7 - Pre-Seal requirements
label | Detail of Activity - Dry back Moisture Content
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | Inspection / Test method - NZS 4407.4.2.1
label | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Only required if pavement widening extends into trafficked lane
holdpoint | HOLD POINT
checkpoint | 2.1.8 - Pre-Seal requirements
label | Detail of Activity - Clegg Hammer
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | • 1 CIV per 10m
label | • 1 Lot < 300m
label | Inspection / Test method - Clegg Impact Value Test
label | Acceptance Criteria -
label | • Average CIV > 40
label | • Min. CIV > 35
label | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | Responsibility - Contractor
checkpoint | 2.1.9 - Sealing
label | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | Inspection / Test method - Penetration grade testing
label | Acceptance Criteria - NZTA M01 - Tables 1, 2, 3 and 5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Sampling as per ASTM D140 or equivalent
checkpoint | 2.1.10 - Sealing
label | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | Inspection / Test method - Durability
label | Acceptance Criteria - NZTA M01 - Table 5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Refer notes in clause 5 of NZTA M01
checkpoint | 2.1.11 - Sealing
label | Detail of Activity - Spraying Temperature (Bitumen only)
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Ongoing with non-going heat sensing gauge
label | Inspection / Test method - Non-contact heat sensing gun
label | Acceptance Criteria - NZTA P03 - Table 2
label | Record documents - ITP
label | Responsibility - Contractor
checkpoint | 2.1.12 - Sealing
label | Detail of Activity - Residual Bitumen Application Rate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Reconcile day's production
label | Inspection / Test method - Dockets vs Area
label | Acceptance Criteria - ± 0.1 L/m2
label | Record documents - Site diary
label | Responsibility - Contractor
checkpoint | 2.1.13 - Non-conforming results
label | Detail of Activity - Assessment of all test results for conformity
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | Inspection / Test method - Site Inspection
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents - NCR
label | Responsibility - Engineer's Rep
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
signoff | Add Signature
checklist | ITP - In-Situ Modified Basecourse - Stewart Rd | itp |  |  |  |  | ITP - In-Situ Modified Basecourse - Stewart Rd
section | 1.1. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
checkpoint | 1.1.1 - M4 AP40 Basecourse Aggregates used for overlay
label | Detail of Activity - Quality of Fines, either PI or SE or CI
label | Action (Hold, Monitor, Witness) - H / M*
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | Inspection / Test method -
label | • NZS4407:3.4 - PI
label | • NZS4407:3.5 - CI
label | • NZS4407:3.6 - SE
label | Acceptance Criteria -
label | • PI ≤ 5
label | • CI ≤ 3
label | • SE ≥ 40
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.1.2 - Notes:
label | Detail of Activity - Broken Faces Content
label | Action (Hold, Monitor, Witness) - H / M*
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | Inspection / Test method - NZS4407:3.14
label | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.1.3 - H = Hold point up to approval of Optimisation Testing
label | Detail of Activity - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - H / M*
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per 1,000 m2
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - Check if 50:50 blend of average existing (from TPs) and NZTA M/4 AP40 will meet the FBS grading.
label | Record documents - Report using IANZ Reports for AP40 and TP PSDs
label | Responsibility - Contractor to provide analysis
label | Comments - Designer to advise if "average" blend is acceptable.
holdpoint | HOLD POINT
checkpoint | 1.1.4 - Optimisation of Stabilizing Agent
label | Detail of Activity - Indirect Tensile Strength, ITS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Optimisation test per aggregate type
label | Inspection / Test method - NZTA T/19: 2020
label | Acceptance Criteria -
label | • Dry ITS: 175kPa to 400 kPa
label | • Soaked ITS: 150 kPa to 350 kPa
label | • TSR ≥ 70%
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.1.5 - Optimisation of Stabilizing Agent
label | Detail of Activity - Modified Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - At Optimised Binder selection
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - To determine target density
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Required before Stabilisation comences
section | 1.2. BEFORE STABILISATION COMENCES
checkpoint | 1.2.1 - Setout section
label | Detail of Activity - Install offset pegs; record centreline, edge line or mark out stabilisation extents from existing line marking
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Document existing furniture
label | Record documents - Electronic survey files
label | Responsibility - Contractor
checkpoint | 1.2.2 - Production Plan
label | Detail of Activity - Plan showing cut lines and sequencing of works
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to each section
label | Inspection / Test method - Daily Report
label | Acceptance Criteria - Points covered in NZTA B/5
label | Record documents - Daily Production Plan
label | Responsibility - Contractor
checkpoint | 1.2.3 - Weather conditions
label | Detail of Activity -
label | • Ambient Temperature (C&L)
label | • Material to be stabilised (BE&FBS)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading
label | Inspection / Test method - Measurement
label | Acceptance Criteria -
label | • Ambient Temperatures:
label | ○ Cement: > 5°C, Lime: > 10°C
label | • Material after stabilisation:
label | ○ BE: > 20°C, FB: > 20°C
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.2.4 - Weather conditions
label | Detail of Activity - Wind
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - Wind speed < 25 km/hr
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.2.5 - Weather conditions
label | Detail of Activity - Rain
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | Record documents - Daily work Log
label | Responsibility - Contractor
section | 1.3. STABILISATION OPERATION
checkpoint | 1.3.1 - Stabilizing Agent
label | Detail of Activity - Cement, GP
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Batch
label | Inspection / Test method - NZS 3122
label | Acceptance Criteria - Conform to Specification
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 1.3.2 - Spreading of powdered stabilising agent (Cement)
label | Detail of Activity - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | • every 400 m2
label | • every 150m for a 2.4m width
label | Inspection / Test method - Weigh mat or tray
label | Acceptance Criteria - ± 5% of specified rate
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.3 - Spreading of powdered stabilising agent (Cement)
label | Detail of Activity - Compare area spread with weight used for each spreader load
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.4 - Injection & Mixing of Water
label | Detail of Activity - In-situ Stabilisation process
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On-going visual assessment
label | Inspection / Test method - Visual and hand squeeze test
label | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.5 - Depth of stabilisation
label | Detail of Activity - Depth of stabilisation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Every 200m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +15mm / -5mm from specified depth
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.6 - Compaction
label | Detail of Activity - Plateau Density Test
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - On first day and then 1 per 20,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern
label | Record documents - Daily work Log
label | Responsibility - Contractor
checkpoint | 1.3.7 - Compaction
label | Detail of Activity - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per day up to 3,000 m2, 1 per 2,000m2 thereafter
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | Record documents - IANZ Report
label | Responsibility - Contractor
checkpoint | 1.3.8 - Compaction
label | Detail of Activity - Degree of Compaction
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (to 100mm and 200mm) and NZS 4407.4.2.2
label | Acceptance Criteria -
label | • Average DoC ≥ 98%
label | • Minimum DoC ≥ 95%
label | • Refer NZTA T/23
label | Record documents - IANZ Report
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.9 - Finished Pavement
label | Detail of Activity - Crossfall
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria -
label | • ± 0.5% of specified crossfall measure
label | • 2m apart
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.10 - Finished Pavement
label | Detail of Activity - Stabilised width
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - –20mm, +100mm
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.11 - Finished Pavement
label | Detail of Activity - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 10mm using 3m straight edge
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.12 - Finished Pavement
label | Detail of Activity - Surface Levels
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - –5mm, +15mm
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.13 - Finished Pavement
label | Detail of Activity - Surface Finish
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Per Lot
label | Inspection / Test method - Visual
label | Acceptance Criteria -
label | • 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | • 2. Smaller aggregate held in place by fine material
label | • 3. matrix does not displace under normal trafficking and/or sweeping
label | Record documents - Survey
label | Responsibility - Contractor
holdpoint | HOLD POINT
checkpoint | 1.3.14 - Finished Pavement
label | Detail of Activity - Degree of Saturation, DOS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per Lot
label | Inspection / Test method - Measurement
label | Acceptance Criteria - DOS ≤ 80%
label | Record documents - IANZ report
label | Responsibility - Contractor
holdpoint | HOLD POINT
section | 1.4. FINAL SIGN OFF
checkpoint | 1.4.1 - Non-conforming results
label | Detail of Activity - Assessment of all test results for conformity
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | Inspection / Test method - Site Inspection
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents - NCR
label | Responsibility - Engineer's Rep
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
signoff | Add Signature
checklist | ITP - 2 coat Grade 3/5 Chipseal - Stewart Rd | itp |  |  |  |  | ITP - 2 coat Grade 3/5 Chipseal - Stewart Rd
section | Sealing
checkpoint | 2.1.1 - Seal Design
label | Detail of Activity - Seal design outlining all design assumptions
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per seal application type
label | Inspection / Test method - Review
label | Acceptance Criteria - New Zealand Chip Sealing Handbook
label | Record documents - Seal design in contractor's site folder
label | Responsibility - Designer / Engineer's Rep
holdpoint | HOLD POINT
checkpoint | 2.1.2 - Check raw materials
label | Detail of Activity - Sealing Aggregates
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - Source Properties
label | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 2.1.3 - Check raw materials
label | Detail of Activity - Sealing Aggregates
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 per source stockpile
label | Inspection / Test method - Production Properties
label | Acceptance Criteria - NZTA M06 / RNZ 9805:2009
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 2.1.4 - Check raw materials
label | Detail of Activity - Adhesion Agents
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to use
label | Acceptance Criteria - NZTA M06 / NZTA M13
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
checkpoint | 2.1.5 - Check raw materials
label | Detail of Activity - Audit samples
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 20 kg per stockpile
label | Inspection / Test method - N/A
label | Acceptance Criteria - Stored in a sealed plastic bag in a covered environment
label | Record documents - ITP
label | Responsibility - Contractor
label | Comments - Retain for testing if required
checkpoint | 2.1.6 - Pre-Seal requirements
label | Detail of Activity - Visual inspection of surface to be sealed
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | • per sealing schedule.
label | • 1 Lot = 1 day's production and < 1500m2
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - NZTA B02
label | Record documents - Contractor's site diary
label | Responsibility - Engineers Rep
label | Comments - The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint | 2.1.7 - Pre-Seal requirements
label | Detail of Activity - Dry back Moisture Content
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 9 per Lot
label | Inspection / Test method - NZS 4407.4.2.1
label | Acceptance Criteria - DOS ≤ 80% preferably ≤ 70%
label | Record documents - IANZ Report
label | Responsibility - Contractor
label | Comments - Only required if pavement widening extends into trafficked lane
holdpoint | HOLD POINT
checkpoint | 2.1.8 - Pre-Seal requirements
label | Detail of Activity - Clegg Hammer
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) -
label | • 1 CIV per 10m
label | • 1 Lot < 300m
label | Inspection / Test method - Clegg Impact Value Test
label | Acceptance Criteria -
label | • Average CIV > 40
label | • Min. CIV > 35
label | Record documents - Contractor's CIV form appended to Contractor's daily diary
label | Responsibility - Contractor
checkpoint | 2.1.9 - Sealing
label | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | Inspection / Test method - Penetration grade testing
label | Acceptance Criteria - NZTA M01 - Tables 1, 2, 3 and 5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Sampling as per ASTM D140 or equivalent
checkpoint | 2.1.10 - Sealing
label | Detail of Activity - Bitumen / Bitumen Emulsion for Chip Sealing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 2 samples per distributor
label | Inspection / Test method - Durability
label | Acceptance Criteria - NZTA M01 - Table 5
label | Record documents - Certificate in contractor's site folder
label | Responsibility - Contractor
label | Comments - Refer notes in clause 5 of NZTA M01
checkpoint | 2.1.11 - Sealing
label | Detail of Activity - Spraying Temperature (Bitumen only)
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Ongoing with non-going heat sensing gauge
label | Inspection / Test method - Non-contact heat sensing gun
label | Acceptance Criteria - NZTA P03 - Table 2
label | Record documents - ITP
label | Responsibility - Contractor
checkpoint | 2.1.12 - Sealing
label | Detail of Activity - Residual Bitumen Application Rate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Reconcile day's production
label | Inspection / Test method - Dockets vs Area
label | Acceptance Criteria - ± 0.1 L/m2
label | Record documents - Site diary
label | Responsibility - Contractor
checkpoint | 2.1.13 - Non-conforming results
label | Detail of Activity - Assessment of all test results for conformity
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Each Lot
label | Inspection / Test method - Site Inspection
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents - NCR
label | Responsibility - Engineer's Rep
holdpoint | HOLD POINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
signoff | Add Signature