## QA Folder Structure
QA Folder Structure
Site QA - approach 1
In-Ground
|  | Inground Pressure Services |  | ITP-005 - Inground Pressure Service
|  | Inground Drainage |  | ITP-006-Inground Drainage (B)
Ground Floor
East
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
West
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
Level 1
East
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
West
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
Level 2
East
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
West
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
Level 3
East
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
West
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
Level 4
East
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
West
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
|  |  | Inwall Pipe Installation (1stFix) | Just a folder for now
|  |  | Inwall Installation Checklist | Just a folder for now
|  |  | Sanitary & Tapware Commissioning Sheet (2nd Fix) | Just a folder for now
Roof
East
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
West
|  |  | Sleeving of Penetrations | ITP-001-Sleeving of Penetrations (B)
|  |  | Suspended Drainage | ITP-002-Suspended Drainage
|  |  | Suspended Pressure Services | ITP-003-Suspended Pressure
Toolbox Meetings |  |  |  | Just a folder

## Checklists ITPs
type | name | values | prefix | postfix
checklist-flat | ITP-001-Sleeving of Penetrations (B)
checkpoint | Identify Route - Pass once completed
text | Ref HPS shop drawing number
text | Ref HPS shop drawing number
button | Co-ordination required with other trades? Mech, Elec, Fire, Structural | Yes, No
label | Reference Requirement: For Construction drawings
label | Test or Inspection Type - Check drawings are current issue
label | Frequency of Test or Inspection - Prior to start
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Site Set Out - Pass once completed
label | Surveyed Ref points (grids) done by: Engineering Surveys
label | Check & confirm penetration sizes & sleeves/fire collar required
label | Reference Requirement: Setout drawings
label | Frequency of Test or Inspection - Prior to commencing installation of Sleeves / Fire collars
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Surveyor / HPS - Click to attach signature below
checkpoint | Install Penetrations - Pass once completed
label | Requirements - Fire Collars & Materials
label | Reference Requirement - Spec - 17128-SPEC-CSB
label | Test or Inspection - Carryout visual check of materials for defects or damage.
label | Frequency of Test or Inspection - After install, prior to final sign off
label | Approvals (as applicable)
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Final Check - Pass once completed
label | Check all penetrations are installed
label | Inspection of penetrations during Concrete pour - where applicable
label | Reference Requirement - For Construction drawings
label | Frequency of Test or Inspection - Prior to concrete pour
label | Approvals (as applicable):
bool | Hindmarsh Plumbing - Click to add signature below
bool | Builder - Built Environs - Click to attach signature below
holdpoint | Click to add sign-off Signatures
checkpoint | Completion - Pass once completed
select | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | Copy to Client | Yes, No
holdpoint | Add Signature
checklist-flat | ITP-002-Suspended Drainage
checkpoint | Identify Route - Pass once completed
text | Ref HPS shop drawing number
text | Ref HPS shop drawing number
text | Ref Hydraulic drawing number - where applicable
button | Co-ordination required with other trades? Mech, Elec, Fire, Structural | Yes, No
label | Reference Requirement: For Construction drawings
label | Test or Inspection - Check drawings are current issue
label | Frequency of Test or Inspection - Prior to start
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Site Set Out - Pass once completed
label | Surveyed Ref points (grids) done by: Engineering Surveys
label | Check & confirm drain invert levels & required falls
label | Reference Requirement: Setout drawings
label | Frequency of Test or Inspection - Prior to start
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Surveyor / HPS - Click to attach signature below
checkpoint | Install Service - Pass once completed
select | Brackets Type | Walraven, ABEY, Syfonic, Other
select | Bracket Spacing's (mm) | 500, 750, 1000, 1600
select | Pipe Material | Raupiano, DWV PVC, HDPE
label | Install expansion joints - where required
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.2
label | Test or Inspection - Carry out visual check of materials for defects or damage
label | Test or Inspection - Check for correct falls
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Test - Pass once completed
label | Test - Hydrostatic Water Test to spill level as per AS/NZS 3500.2
label | Attach image or plan outlining area of test
text | OTR Booking Numbers
label | Note test date on Stack IP's
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.2
label | Frequency of Test or Inspection - As required (OTR inspector to sign below, if in attendance)
button | Inspector attendance | Yes, No
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | S.A Water/OTR - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Insulation & Identification - Pass once completed or N/A
button | Is Acoustic Insulation Required | Yes, No
text | If Yes - List insulation type/s
label | Reference Requirement - Spec - 17128-SPEC-CSB
label | Identification & Labelling - Attach photos as applicable
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Identification & Labelling - Every 3m when concealed & 6m where exposed
label | Test or Inspection - Visually check upon completion
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Record As-Built Information - Pass once completed
label | Plot & record as installed information on markup shop drawings in site office
label | Attach images below - where applicable
label | Reference Requirement - For Construction Hydraulic drawings and Specification
label | Frequency of Test or Inspection - Prior to concealment
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Completion - Pass once completed
select | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | Copy to Client | Yes, No
holdpoint | Add Signature
checklist-flat | ITP-003-Suspended Pressure
checkpoint | Identify Route - Pass once completed
text | Ref HPS shop drawing number
text | Ref HPS shop drawing number
text | Ref Hydraulic drawing number - where applicable
button | Co-ordination required with other trades? Mech, Elec, Fire, Structural | Yes, No
label | Reference Requirement: For Construction drawings
label | Test or Inspection - Check drawings are current issue
label | Frequency of Test or Inspection - Prior to start
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Site Set Out - Pass once completed
text | Surveyed Ref points (grids) done by: Engineering Surveys
label | Check & confirm route & levels
label | Requirement Reference - Setout drawings
label | Frequency of Test or Inspection - Prior to start
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Surveyor / HPS - Click to attach signature below
checkpoint | Install Service - Pass once completed
select | Brackets Type | Bi-fix, Two-piece strut, Quickclip, Other
select | Bracket Spacing (m) | 0.6, 1.5, 2.0, 2.5, 3.0, 4.0
select | Pipe Material | Copper, MDPE, Pe-X
select | Jointing System | Soldering, Electrofusion, Compression, Other
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.1
label | Test or Inspection - Carry out visual check of materials for defects or damage
label | Test or Inspection - Check for correct jointing of pipe & fittings
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Test - Pass once completed
select | Pressure Test Type | Water, Air, Nitrogen
label | Attach image or plan outlining area of test
text | OTR Booking Numbers
text | Pressure Test to (Kpa)
select | Test Duration (minutes) | 30, 60, 90+
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.1
label | Frequency of Test or Inspection - As required (OTR inspector to sign below, if in attendance)
button | Inspector attendance | Yes, No
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | S.A Water/OTR - Click to attach signature below
bool | APA - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Insulation & Identification - Pass once completed
button | Is Thermal/Acoustic Insulation Required | Yes, No
text | If Yes - List insulation type/s
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.1
label | Identification & Labelling - Attach photos as applicable
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Identification & Labelling - Every 3m when concealed & 6m where exposed
label | Test or Inspection - Visually check upon completion
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Record As built Information - Pass once completed
label | Plot & record as installed information on markup shop drawings in site office
label | Reference Requirement - For Construction Hydraulic drawings and Specification
label | Frequency of Test or Inspection - Prior to concealment
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Completion - Pass once completed
select | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | Copy to Client | Yes, No
holdpoint | Add Signature
checklist-flat | ITP-004-Inwall Pipe Installation (B)
checkpoint | Room/Site Set Out - Pass once completed
label | Identify trimmer, water point, and 1st fix item requirements
label | Reference Requirement - Setout drawings
label | Install trimmers, water poinst, and 1st fix items
label | Check & confirm pipework route
label | Reference Requirement - Setout drawings
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Install Inwall Pipework - Pass once completed
select | Pipe Material / System | Rehau, Copper
select | Brackets Type | QuickClip, Saddle Clip
select | Bracket Spacing's (mm) | 600, 1000, 1500
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Test or Inspection - Carryout visual check of materials for defects or damage.
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
bool | Consultant - Click to attach signature below
checkpoint | Carryout Installation Checks - Pass once completed
label | Requirements - Install pipework to all fixtures and check the following:
button | Correct fixtures and fittings installed | Yes, No
button | Cross connections | Yes, No
button | Pipes rubbing against sharp surface | Yes, No
button | Screws hitting or rubbing on pipes | Yes, No
button | Screwed joints in wall are tight | Yes, No
button | Ensure all joints have been crimped / welded correctly | Yes, No
button | Pipes do not stick out beyond studs | Yes, No
button | Pipes are not in a position that will increase the chances of being screwed through by wall contractor | Yes, No
label | Attach images of inwall installation
label | Reference Requirement - Spec - 17128-SPEC-CSB & Setout drawings
label | Frequency of Test or Inspection - Prior to concealment
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Test - Pass once completed
select | Pressure Test Type | Water, Air, Nitrogen
label | Attach image or plan outlining area of test
text | Pressure Test to (Kpa)
text | Test Duration
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Test or Inspection - As required (OTR/Inspector to sign below, if in attendance)
button | Inspector attendance | Yes, No
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
bool | OTR/Inspector - Click to attach signature below
checkpoint | Insulation & Identification - Pass once completed
button | Is Insulation Required | Yes, No
select | If yes, Type? (N/A if not required) | Armaflex, Thermobreak, Acoustic, N/A
label | Identification & Labelling
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Test or Inspection - Every 3m when concealed & 6m where exposed
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Fill Out Inwall Installation Check Sheet - Pass once completed
label | Requirements - Refer Inwall Pipework Installation, Process & Check Sheet
button | Test or Inspection - Inwall Installation Check Sheet complete? | Yes, No
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
checkpoint | Sign Room/Wall/Ceiling Sign Off Sheet - Pass once completed
label | Requirements - Once all checks are completed, sign builders room/wall/ceiling sign off sheet (if applicable)
label | Frequency of Test or Inspection - Once in wall pipework, test & checks are complete, prior to concealment
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
checkpoint | Completion - Pass once completed
select | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | Copy to Client | Yes, No
holdpoint | Add Signature
checklist-flat | ITP-005 - Inground Pressure Service
checkpoint | Identify Route - Pass once completed
text | Ref HPS shop drawing number
text | Ref HPS shop drawing number
text | Ref Hydraulic drawing number - where applicable
button | Co-ordination required with other trades? Footings, Elec, Fire, Structural | Yes, No
label | Reference Requirement: For Construction drawings
label | Test or Inspection - Check drawings are current issue
label | Frequency of Test or Inspection - Prior to start
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Site Set Out - Pass once completed
label | Surveyed Ref points (grids) done by: Engineering Surveys
button | Check & confirm route levels | Yes, No
button | Identify and locate existing services | Yes, No, N/A
label | Reference Requirement - For Construction drawings & Existing Services drawings
label | Frequency of Test or Inspection - Prior to set out of trench and Prior to any excavations beginning
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Surveyor / HPS - Click to attach signature below
checkpoint | Excavate Trench - Pass once completed
label | Excavate to 50mm (max) below pipe invert
label | Separate contaminated fill from clean fill
button | Spoil to be - Removed | Yes, No
button | Spoil to be - Stockpiled | Yes, No
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Test or Inspection - Check spoil for suitability to re-use as backfill or to determine off-site dumping requirements
label | Frequency of Test or Inspection - Prior to backfill
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Place Service Bedding - Pass once completed
button | Ensure trench base is free from large rocks & debris that may damage the pipe | Yes, No
label | Requirements - Place 50mm Sand bedding for pipe
label | Sand Type - PM64
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Test or Inspection - Prior to installation of service
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Install Service - Pass once completed
select | Material Type | MDPE, HDPE, Copper, PVC-Pressure
select | Corrosion Protection Type (N/A if not required) | Denso & Overwrap, Other, N/A
button | Thrust Blocks required | Yes, No
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Test or Inspection - Carryout visual check of materials for defects or damage
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Test - Pass once completed
select | Pressure Test Type | Water, Air, Nitrogen
text | Pressure Test Services to (Kpa)
select | Test Duration (minutes) | 30, 60, 90+
label | Attach image or plan outlining area of test
text | OTR Booking Numbers
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Test or Inspection - As required
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | S.A Water/OTR - Click to attach signature below
bool | APA - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Backfill - Pass once completed
label | Requirements - Blind off pipe with sand to a depth of 300mm above overt of pipe
label | Sand Type - PM64
label | Install detectable ID tape at 300mm (or 1 layer) above overt of pipe
label | Backfill trench to 100mm below finished surface with cleanfill
button | Compaction tests required | Yes, No
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500 & For Construction hydraulic drawings
label | Test or Inspection - All services, external of building in 300mm deep layers
label | Frequency of Test or Inspection - Per layer, per service
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Record As built Information - Pass once completed
label | Requirements - Plot & record as installed information on markup shop drawings in site office
label | Reference Requirement - For Construction Hydraulic drawings and Specification
label | Frequency of Test or Inspection - Prior to backfill
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Completion - Pass once completed
select | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | Copy to Client | Yes, No
holdpoint | Add Signature
checklist-flat | ITP-006-Inground Drainage (B)
checkpoint | Identify Route - Pass once completed
text | Ref HPS shop drawing number
text | Ref HPS shop drawing number
text | Ref Hydraulic drawing number - where applicable
button | Co-ordination required with other trades? Footings, Elec, Fire, Structural | Yes, No
label | Reference Requirement: For Construction drawings
label | Test or Inspection - Check drawings are current issue
label | Frequency of Test or Inspection - Prior to start
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Site Set Out - Pass once completed
text | Surveyed Ref points (grids) done by: Engineering Surveys
button | Check & confirm drain invert levels & required falls | Yes, No
button | Identify and locate existing services | Yes, No, N/A
label | Reference Requirement - For Construction drawings & Existing Services drawings
label | Frequency of Test or Inspection - Prior to set out of trench and Prior to any excavations beginning
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
bool | Builder - Surveyor / HPS - Click to attach signature below
checkpoint | Excavate Trench - Pass once completed
label | Excavate to 50mm (max) below pipe invert
button | Excavate hole for Tank/ Pit (if required) | Yes, No, N/A
button | Shoring or Benching required for trench over 1.5m deep | Yes, N/A
label | Separate contaminated fill from clean fill
button | Spoil to be - Removed | Yes, No
button | Spoil to be - Stockpiled | Yes, No
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Test or Inspection - Check spoil for suitability to re-use as backfill or to determine off site dumping requirements
label | Frequency of Test or Inspection - Prior to backfill
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Place Service Bedding - Pass once completed
button | Ensure trench base is free from large rocks & debris that may damage the pipe | Yes, No
label | Requirements - Place 50mm Sand bedding for pipe
text | Sand Type - PM64
select | Bedding for Tank (if required) | Yes, No, N/A
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Test or Inspection - Prior to installation of service
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Install Service - Pass once completed
select | Material Type | HDPE, DWV PVC,MDPE, Other
button | Concrete beneath IO's | Yes, No
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Test or Inspection - Carryout visual check of materials for defects or damage.
label | Check invert/RL's of tank to ensure correct levels (if required)
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Test - Pass once completed
label | Test - Hydrostatic Water Test to spill level as per AS/NZS 3500.2
label | Attach image or plan outlining area of test
text | OTR Booking Numbers
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | Frequency of Test or Inspection - As required
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | S.A Water/OTR - Click to attach signature below
bool | APA - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Backfill - Pass once completed
label | Requirements - Blind off pipe with sand to a depth of 300mm above overt of pipe
label | Sand Type - PM64
label | Install detectable ID tape at 300mm (or 1 layer) above overt of pipe
label | Backfill trench to 100mm below finished surface with cleanfill
button | Compaction tests required | Yes, No
label | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500 & For Construction hydraulic drawings
text | Test or Inspection - All services, external of building in 300mm deep layers
label | Frequency of Test or Inspection - Per layer, per service
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Record As built Information - Pass once completed
label | Requirements - Plot & record as installed information on markup shop drawings in site office
label | Requirement Reference - For Construction Hydraulic drawings and Specification
label | Frequency of Test or Inspection - Prior to backfill
label | Approvals (as applicable) - Add signature below
bool | Hindmarsh Plumbing - Click to attach signature below
bool | Builder - Built Environs - Click to attach signature below
checkpoint | Completion - Pass once completed
select | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | Copy to Client | Yes, No
holdpoint | Add Signature
checklist-flat | In Wall Pipework Installation Checklist
checkpoint | In Wall Pipework Installation - Pass once completed
select | Confirm Pipe System | Copper, Rehau, MDPE, Other (Specify below)
text | Other (Specify here)
button | Check trimmers for correct locations & length | Yes, No
checkpoint | Install pipework to all fixtures watching for the following - Pass once ALL completed
button | Cross connections | Yes, No
button | Pipes rubbing against sharp surface | Yes, No
button | Screws hitting or rubbing on pipes | Yes, No
button | Screwed joints in wall are tight | Yes, No
button | Ensure all joints have been crimped / welded correctly | Yes, No
button | Pipes do not stick out beyond studs | Yes, No
button | Pipes are not in a position that will increase the chances of being screwed through by wall contractor | Yes, No
button | Pipes to fixtures come directly down in line with the water outlet | Yes, No
button | Ensure second piece of piping is split and fitted over pipe where brackets or grommets can't be installed through metal studs | Yes, N/A
checkpoint | Re-Check in wall water drawings to make sure all items have been installed
checkpoint | Brackets installed as per pipe system manufacturers recommendations
select | Type | QuickClip, Saddle Clip, Grommet, Macrofix
select | Spacing | 600, 1000, 1500
checkpoint | Pipework has been tested, to maximum of 1500 KPA
checkpoint | Check room for following - Pass once completed
button | Check all fixture measurements off stud wall are correct | Yes, No
button | Broken pipes (Advise site manager if there are) | Yes, No
button | Check all pipes have caps fitted (Drainage and water pipes) | Yes, No
button | Check for any pipes that aren't connected below(If unsure, advise site manager) | Yes, No
button | Check ID stickers to stormwater & sewer stacks in voids. Fit if required | Yes, No, N/A
button | Grey tape or insulate any copper pipes touching steel studs (Check before leaving) | Yes, No, N/A
checkpoint | In-Wall Pipework & First Fix Works completed to specification/drawings
label | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
bool | Clean up & remove all HPS rubbish from rooms (Straight to bins)
text | Room Completed & Inspected by
holdpoint | Hindmarsh Sign-Off - click to Add signature(s)
checklist-flat | Sanitary & Tapware Commissioning Sheet
checkpoint | Basin - Pass once completed
button | Check for leaks - Basin mixer, trap & waste | Yes, No, N/A
button | Basin mixer & handle is secure | Yes, No, N/A
button | Silicone neat and complete | Yes, No, N/A
button | Extended lever for access mixer (if applicable) | Yes, No, N/A
button | Remove & clean strainer, flush mixer & replace strainer | Yes, No, N/A
button | Check red and blue indications for tempered/cold water | Yes, No, N/A
button | Check flexi hoses are tight - no kinks | Yes, No, N/A
select | Check completed for multiple basins - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | Comments:
checkpoint | Water Closet/Pan - Pass once completed
button | Check for leaks - WC/Pan water connection | Yes, No, N/A
button | Silicone bedding around pan | Yes, No, N/A
button | Silicone seal pan to wall (neat) | Yes, No, N/A
button | Check proper WC flush (single & dual or Disabled) | Yes, No, N/A
button | Flush toilet paper to test | Yes, No, N/A
button | Check tightness of seat & buttons - and backrest for Access WC | Yes, No, N/A
button | Check WC is secure | Yes, No, N/A
button | Check flexi hoses are tight and cistern cock is open | Yes, No, N/A
select | Check completed for multiple WC's - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | Comments:
checkpoint | Urinal - Pass once completed
button | Flush water from valve before connection to solenoid | Yes, No, N/A
button | Check for leaks - water connections & flush pipes | Yes, No, N/A
button | Silicone urinal to wall (neat) | Yes, No, N/A
button | Check urinal fixed securely to wall | Yes, No, N/A
button | Check sensor function - water/wave test | Yes, No, N/A
button | Set delay and flush time - in valve box | Yes, No, N/A
select | Check completed for multiple Urinals - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | Comments:
checkpoint | Shower - Pass once completed
button | Check for leaks - hose connections | Yes, No, N/A
button | Check shower mixer trim & handle is secure | Yes, No, N/A
button | Check shower rail is secure and plumb for Access shower | Yes, No, N/A
button | Check operation of hand/wall shower | Yes, No, N/A
button | Remove strainer and flush shower rose | Yes, No, N/A
button | Check red and blue indications for tempered/cold water | Yes, No, N/A
select | Check completed for multiple Showers - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | Comments:
checkpoint | Kitchen or Cleaners Sink - Pass once completed
button | Check for leaks - Sink mixer, trap & waste | Yes, No, N/A
button | Sink mixer is secure | Yes, No, N/A
button | Clean silicone from P&W | Yes, No, N/A
button | Remove & clean strainer, flush mixer & replace strainer | Yes, No, N/A
button | Check red and blue indications for hot/cold water | Yes, No, N/A
button | Check flexi hoses are tight - no kinks | Yes, No, N/A
select | Check completed for multiple Sinks - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | Comments:
checkpoint | BCWU - Pass once completed
button | Tap is secure | Yes, No, N/A
button | Check flexi hoses are tight - no kinks | Yes, No, N/A
button | Set & commission BCWU (per manufacturers instructions) | Yes, No, N/A
button | Remove strainer and flush tap | Yes, No, N/A
button | Check for leaks - Pipework & tap | Yes, No, N/A
text | Comments:
checkpoint | Equipment - Pass once completed
button | Check cover/door fixed firmly and open/shut correctly | Yes, No, N/A
button | TMV commissioning sheet complete (attach, if required) | Yes, No, N/A
button | Check operation of Auto Trap Primer | Yes, No, N/A
button | Check TMV/Trap Primer connections for leaks | Yes, No, N/A
text | Comments:
checkpoint | Other final checks - Pass once completed
button | Remove tape from floor grates/IP covers and check | Yes, No, N/A
button | Remove tape from Bolted trap screws | Yes, No, N/A
button | Remove all labels & stickers | Yes, No, N/A
button | Check floor waste for debris & clean (if applicable) | Yes, No, N/A
button | Check grates & IP covers are installed and clean | Yes, No, N/A
button | Check tundish cover installed (if applicable) | Yes, No, N/A
button | Check all fixtures for damage | Yes, No, N/A
button | Ensure all fixtures are protected | Yes, No, N/A
button | Remove all HPS rubbish from room | Yes, No, N/A
text | Comments:
checkpoint | Compliance Verification - Pass once completed
button | Complies with criteria | Yes, No, N/A
button | Corrective actions required | Yes, No, N/A
button | All works completed | Yes, No, N/A
checkpoint | Completion - Pass once completed
text | Room Completed & Inspected by
select | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | Copy to Client | Yes, No
holdpoint | Add Signature
checklist | Toolbox Meeting Checklist
section | Attendance
checkpoint | Attendance - add signoffs for each person in attendance below
checkpoint | Apologies - comment names of non-attendees below
section | Actions from last meeting
checkpoint | Action 1
checkpoint | Action 2
checkpoint | Action 3
checkpoint | Action 4
checkpoint | Action 5
checkpoint | Administration
checkpoint | Point 1
checkpoint | Point 2
checkpoint | Point 3
checkpoint | Point 4
checkpoint | Point 5
section | HR
checkpoint | Site recognition
checkpoint | Any HR Issues
checkpoint | Additional Items
section | Safety: (including hazards / near misses / controls / site specific)
checkpoint | Discuss recent Incidents
checkpoint | HSE Monthly Reports
checkpoint | SDS – Of the week (list which SDS you have reviewed)
checkpoint | Additional Items
section | Environment: (including hazards / controls / incidents / impacts)
checkpoint | Point 1
checkpoint | Point 2
checkpoint | Point 3
checkpoint | Point 4
checkpoint | Point 5
section | Training
checkpoint | Competency Assessment Guides (Apprentices) – are they up to date?
checkpoint | Additional Items
section | Plant & Equipment
checkpoint | Point 1
checkpoint | Point 2
checkpoint | Point 3
checkpoint | Point 4
checkpoint | Point 5
section | Issues & Customer Feedback
checkpoint | Point 1
checkpoint | Point 2
checkpoint | Point 3
checkpoint | Point 4
checkpoint | Point 5
section | Client/Job specific information:
checkpoint | Point 1
checkpoint | Point 2
checkpoint | Point 3
checkpoint | Point 4
checkpoint | Point 5
section | HSE Committee: (key points from minutes / questions / feedback to be raised at next meeting)
checkpoint | Discuss recent HSE Committee Minutes
checkpoint | Additional Items
section | Memo’s and other office correspondence
checkpoint | Point 1
checkpoint | Point 2
checkpoint | Point 3
checkpoint | Point 4
checkpoint | Point 5
section | Site documentation review (JSEA, MSDS or SOP):
checkpoint-no-status | Document 1 Details
text | Document Name
text | Comments or changes
checkpoint-no-status | Document 2 Details
text | Document Name
text | Comments or changes
checkpoint-no-status | Document 3 Details
text | Document Name
text | Comments or changes
checkpoint-no-status | Any additional document details / review commented below
section | New Business / Other
checkpoint | Point 1
checkpoint | Point 2
checkpoint | Point 3
checkpoint | Point 4
checkpoint | Point 5
checkpoint | Point 6
checkpoint | Point 7
checkpoint | Point 8
checkpoint | Point 9
checkpoint | Point 10
section | Meeting Closure
checkpoint | Meeting Closed
text | Meeting Closed time
text | Date for next meeting
text | Minutes taken by (Name)