## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP-002-Suspended Drainage |  |  |  |  | Yes | ITP-002-Suspended Drainage | 94ce5035-2ffe-48f9-b656-88841ccc24eb
checkpoint-status |  |  | checkpoint | Identify Route - Pass once completed
text | 1ac59e81-9c79-5c2d-bb55-2c7c82e80a17 |  | textbox | Ref HPS shop drawing number
text | bd1eade5-4b0c-5c31-a1eb-1da96799c767 |  | textbox | Ref HPS shop drawing number
text | 969ecd5c-3111-5b51-8fc4-f101e56c05e5 |  | textbox | Ref Hydraulic drawing number - where applicable
button | 6a06592b-eed7-5c31-9e10-e230f7d892c5 |  | button | Co-ordination required with other trades? Mech, Elec, Fire, Structural | Yes, No
label | e12e0ca2-d8b4-5590-ab7f-6bb8f9704af0 |  | note | Reference Requirement: For Construction drawings
label | c83cd818-91c8-50a0-9c93-ddd16641999a |  | note | Test or Inspection - Check drawings are current issue
label | b2a497ab-40e2-51df-a4a5-d3095d8fd7e5 |  | note | Frequency of Test or Inspection - Prior to start
label | 295db573-1460-5f5c-a8cc-47dbbc1051fe |  | note | Approvals (as applicable) - Add signature below
boolean | c5b92914-8aac-5ae6-9698-113530b7192c |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 279da4d0-9694-52cc-9570-14c3f126c222 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Site Set Out - Pass once completed
label | 76167fbe-29ab-56a3-ad11-b96aad00b5b0 |  | note | Surveyed Ref points (grids) done by: Engineering Surveys
label | d914ec35-9327-535a-a600-7c0cb947eccb |  | note | Check & confirm drain invert levels & required falls
label | fc3ca873-fc83-5dd9-aae4-376d3fa0a400 |  | note | Reference Requirement: Setout drawings
label | b0545c77-3ffd-5dba-808a-e6802d11f670 |  | note | Frequency of Test or Inspection - Prior to start
label | 4e76c9b5-d5a7-55f9-a1ee-3afb5ba71686 |  | note | Approvals (as applicable) - Add signature below
boolean | e78cdb12-5a99-5d5b-a078-0f819507a5be |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 7a3d45b8-5580-5761-bb81-8be0f8598ba7 |  | tickbox | Builder - Surveyor / HPS - Click to attach signature below
checkpoint-status |  |  | checkpoint | Install Service - Pass once completed
select | b17d6ef9-4069-568b-9651-8159b6e59c41 |  | dropdown | Brackets Type | Walraven, ABEY, Syfonic, Other
select | 7bbd8432-52f2-527a-8a9c-ead5a524fc26 |  | dropdown | Bracket Spacing's (mm) | 500, 750, 1000, 1600
select | 2b81595c-4aaa-57a6-b26e-7fa16a6bb4ed |  | dropdown | Pipe Material | Raupiano, DWV PVC, HDPE
label | 3f3e6321-6b62-5e5f-acea-373ce4d4627c |  | note | Install expansion joints - where required
label | c050a2d0-fa52-5676-b74d-565a20221330 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.2
label | 26ad3f24-7081-527a-86f6-aeb43d769885 |  | note | Test or Inspection - Carry out visual check of materials for defects or damage
label | 757d3e34-efaa-5f98-a3a7-fa3edee3c314 |  | note | Test or Inspection - Check for correct falls
label | 7ec9a292-d7f0-57ad-8905-88eb4c4630fb |  | note | Approvals (as applicable) - Add signature below
boolean | d8e7c5e7-472e-5ece-a5f7-390fa941803f |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 50fc9d6b-2d79-592d-b6f6-5e63404d7ece |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Test - Pass once completed
label | 7612c56b-464c-5c41-835b-cfb1c61c8826 |  | note | Test - Hydrostatic Water Test to spill level as per AS/NZS 3500.2
label | 9a12c448-7cff-5bf0-9c13-9aab07235a46 |  | note | Attach image or plan outlining area of test
text | 37de66c9-9a0c-53fb-917b-b59fe81cd1a6 |  | textbox | OTR Booking Numbers
label | 1fccea5f-6377-5b19-b17c-02af8715c901 |  | note | Note test date on Stack IP's
label | 13052367-8e29-5364-8f48-38feb3a92815 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.2
label | 8e0e4107-4b9a-5ffa-a02b-816d68da35a7 |  | note | Frequency of Test or Inspection - As required (OTR inspector to sign below, if in attendance)
button | 188199c6-8a3e-5d15-8e45-7332bbb3b643 |  | button | Inspector attendance | Yes, No
label | 61b97f63-034d-5f1e-b0c8-2f8860d8fd9e |  | note | Approvals (as applicable) - Add signature below
boolean | cbe184e9-9752-5ec1-8ca2-a74d69a015f6 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | c52037be-1125-5d92-8027-7c31498c0e55 |  | tickbox | S.A Water/OTR - Click to attach signature below
boolean | 9fb002d9-d1b8-540d-92a6-fdf0d0c63615 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Insulation & Identification - Pass once completed or N/A
button | 52a08f2d-58ec-5059-bd33-08599c351819 |  | button | Is Acoustic Insulation Required | Yes, No
text | 513cfaf9-92b3-5191-8685-21b03946a038 |  | textbox | If Yes - List insulation type/s
label | a249342f-a212-5d34-8f2b-8557fd8479da |  | note | Reference Requirement - Spec - 17128-SPEC-CSB
label | 536c59ff-f0b8-51c8-8969-358d09869eac |  | note | Identification & Labelling - Attach photos as applicable
label | 00aae81e-c40e-5dcc-9a67-ac22dd774e36 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 89249a47-f376-5db2-8167-a323516af9d9 |  | note | Frequency of Identification & Labelling - Every 3m when concealed & 6m where exposed
label | 8535dc71-4874-5fb0-86f3-a0931fe0c58a |  | note | Test or Inspection - Visually check upon completion
label | 69e0b97d-5216-539f-bcf3-3b657f986923 |  | note | Approvals (as applicable) - Add signature below
boolean | 3ea776e2-8d15-5668-a611-b9133508aab7 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | cf679f4e-4dbf-5873-bc23-238dce7e7313 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Record As-Built Information - Pass once completed
label | 9d5a5b1d-3a63-59d8-8df6-a1e1c841ed45 |  | note | Plot & record as installed information on markup shop drawings in site office
label | 0bf7ddc9-1bee-52c9-ace2-51c8f7aee154 |  | note | Attach images below - where applicable
label | bed63ae0-a141-51e9-8617-022586464b3b |  | note | Reference Requirement - For Construction Hydraulic drawings and Specification
label | 4fe41338-32f1-597f-8a27-b0ea0007d6f7 |  | note | Frequency of Test or Inspection - Prior to concealment
label | 4fd21f9a-29f9-5c45-9eef-b4e946a10439 |  | note | Approvals (as applicable) - Add signature below
boolean | d5921bff-79ab-56ac-a4a4-393aeac524d1 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 93a8c4cb-65fc-5202-84ac-66a54f7db341 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Completion - Pass once completed
select | a3b2ba95-23a5-51c8-99f0-c294808deb37 |  | dropdown | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | 6b318e55-edf0-579a-ae4a-f00b1910b9b9 |  | button | Copy to Client | Yes, No
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP-006-Inground Drainage (B) |  |  |  |  | Yes | ITP-006-Inground Drainage (B) | 99e6ae2c-040b-4699-b677-b60533c95cd4
checkpoint-status |  |  | checkpoint | Identify Route - Pass once completed
text | 53b47a1b-5bed-548b-8203-fba85fc03f57 |  | textbox | Ref HPS shop drawing number
text | 31e04315-dc74-581b-94f3-4f2d7fdc2957 |  | textbox | Ref HPS shop drawing number
text | 7e61d12b-3129-5ed2-b2b5-42c3710cfe24 |  | textbox | Ref Hydraulic drawing number - where applicable
button | 508846b5-26c9-5eae-87ee-d59f5e1faabc |  | button | Co-ordination required with other trades? Footings, Elec, Fire, Structural | Yes, No
label | 3cb15366-f518-51f1-bcf8-d6417673581a |  | note | Reference Requirement: For Construction drawings
label | e72e2561-e6f9-53ab-b7a5-06771ad00275 |  | note | Test or Inspection - Check drawings are current issue
label | b553db94-32c1-529e-bd38-9dbfbba33d76 |  | note | Frequency of Test or Inspection - Prior to start
label | 46cc13d9-9089-53e6-b9dc-8fde7c4a7ad1 |  | note | Approvals (as applicable) - Add signature below
boolean | 681fb862-59c2-5fe0-9c70-f9ca7299c19a |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | c4e9a8ec-171a-584d-9202-3783a434732e |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Site Set Out - Pass once completed
text | c525a556-ed57-5d74-a62a-7927fbc3fb82 |  | textbox | Surveyed Ref points (grids) done by: Engineering Surveys
button | 99f74c35-af93-5558-b510-0a887b90dc19 |  | button | Check & confirm drain invert levels & required falls | Yes, No
button | 4bf76392-cece-551a-8dd4-4b377ec19471 |  | button | Identify and locate existing services | Yes, No, N/A
label | 342d1b99-5db7-5743-8d78-4a61dfc7770c |  | note | Reference Requirement - For Construction drawings & Existing Services drawings
label | 74a5c2c4-7149-5578-98dc-823ae2b1d1ed |  | note | Frequency of Test or Inspection - Prior to set out of trench and Prior to any excavations beginning
label | a79c5066-e77d-5809-aee8-98db123913b3 |  | note | Approvals (as applicable) - Add signature below
boolean | 15883ebc-3949-5f16-a48e-b94fbf5bc815 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 5044db04-b24a-50be-8538-1c66de751ee9 |  | tickbox | Builder - Built Environs - Click to attach signature below
boolean | 3855224e-c92d-5f3f-9fcb-c5fdf6ffbfe5 |  | tickbox | Builder - Surveyor / HPS - Click to attach signature below
checkpoint-status |  |  | checkpoint | Excavate Trench - Pass once completed
label | ff8114bd-bab6-5304-8f93-c6f519285fad |  | note | Excavate to 50mm (max) below pipe invert
button | 27685148-d179-5c2f-a561-9dbb98ae9bbf |  | button | Excavate hole for Tank/ Pit (if required) | Yes, No, N/A
button | 4ffa28ae-af05-507a-8c4c-2b8352209928 |  | button | Shoring or Benching required for trench over 1.5m deep | Yes, N/A
label | a4acd071-8bef-530a-acdd-e1b68302721f |  | note | Separate contaminated fill from clean fill
button | 410ed82b-a3cc-5007-9de1-52d6b952e498 |  | button | Spoil to be - Removed | Yes, No
button | 71831d39-e549-5f75-a9b2-5a03bbe86fa7 |  | button | Spoil to be - Stockpiled | Yes, No
label | f70c840e-2fc2-5523-9302-e8c41ea156a7 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 7f59cda5-42f5-5730-9279-2aa98da3b7bb |  | note | Test or Inspection - Check spoil for suitability to re-use as backfill or to determine off site dumping requirements
label | 8f02b123-8ac4-5be8-9ecb-861f145fc1b7 |  | note | Frequency of Test or Inspection - Prior to backfill
label | 7780ff80-1c4f-57be-9796-bbdf26a832be |  | note | Approvals (as applicable) - Add signature below
boolean | 25ba0e43-92cf-50db-9e05-27b5da2c3597 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | aa02cd18-b99a-5cb3-b891-48a566f6407c |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Place Service Bedding - Pass once completed
button | c4180b8b-5f13-58e8-b8ee-a35104a3c046 |  | button | Ensure trench base is free from large rocks & debris that may damage the pipe | Yes, No
label | 71188704-ed59-5b0a-ae8a-1754fdeb6eb6 |  | note | Requirements - Place 50mm Sand bedding for pipe
text | 5c2c5e48-45fe-58a5-9998-e097807650e8 |  | textbox | Sand Type - PM64
select | 19905b7c-6878-5c78-87c9-479825d44a7d |  | dropdown | Bedding for Tank (if required) | Yes, No, N/A
label | ad82fb8e-20e5-5d3e-ac4e-42bb2d988e16 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | f8f462ad-445b-59f7-b4ab-ee984e8ac1d4 |  | note | Frequency of Test or Inspection - Prior to installation of service
label | cfcdcd87-76ec-5222-a342-e3db2141b99c |  | note | Approvals (as applicable) - Add signature below
boolean | 13c1c395-a250-5043-9f31-a9f80b62cc42 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | b15f17e5-42b4-5e42-a29d-06925bec3011 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Install Service - Pass once completed
select | 3fb5f121-e4f6-51aa-8d52-c5fd5abca401 |  | dropdown | Material Type | HDPE, DWV PVC,MDPE, Other
button | 40fba6ee-9f4c-5222-b3f2-deef0dcc85ea |  | button | Concrete beneath IO's | Yes, No
label | ff4988f9-5fa2-59d5-b08e-46d11c5f7f87 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 2961d1ab-1709-55e9-810e-fe696e544aa8 |  | note | Test or Inspection - Carryout visual check of materials for defects or damage.
label | e626310b-1c0b-5cf7-90fe-930b1abd5bfd |  | note | Check invert/RL's of tank to ensure correct levels (if required)
label | 1ec5a890-05c7-525c-a231-b3d0203ff06a |  | note | Approvals (as applicable) - Add signature below
boolean | 6ec59be1-7e40-51d0-82d1-573305289a27 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 71293786-48dd-5e1a-9102-350a5aac5313 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Test - Pass once completed
label | 31a293fb-35b6-5e85-aa8f-1d88a5b2a8c9 |  | note | Test - Hydrostatic Water Test to spill level as per AS/NZS 3500.2
label | c126a7d0-e6ac-5147-a242-0dfe9eb1b589 |  | note | Attach image or plan outlining area of test
text | c379700a-dcee-5f53-bfcb-67b1171fa66f |  | textbox | OTR Booking Numbers
label | 6f9de3e1-c90c-526b-80d2-748cbe4640a3 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 5570db74-e955-5ac7-bb91-a2f85db02a5c |  | note | Frequency of Test or Inspection - As required
label | b112f133-9dfe-5df2-91aa-b74d2e2740da |  | note | Approvals (as applicable) - Add signature below
boolean | 9e6cb609-173e-546c-ac59-b4f1a1441c66 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 40aafbe6-86a1-5831-8d6a-749e78b75c9d |  | tickbox | S.A Water/OTR - Click to attach signature below
boolean | 8eb9f1f8-f417-52c0-a149-dde1f8bbf674 |  | tickbox | APA - Click to attach signature below
boolean | 35ba1aa3-d8c1-5e2d-bd4b-92d183f0d98c |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Backfill - Pass once completed
label | abc41a5d-b535-54a3-9837-3bab8b4e2ef7 |  | note | Requirements - Blind off pipe with sand to a depth of 300mm above overt of pipe
label | abb70a74-ab95-56cc-a6e1-186c93e3739c |  | note | Sand Type - PM64
label | 48e07d4c-f548-5dfa-b733-4563e9859567 |  | note | Install detectable ID tape at 300mm (or 1 layer) above overt of pipe
label | 538be74b-3832-529b-8f00-879889b4be99 |  | note | Backfill trench to 100mm below finished surface with cleanfill
button | 465bc50a-7b24-5e87-9291-6ed6682aa9f3 |  | button | Compaction tests required | Yes, No
label | e590f19b-d67f-5a0f-a0fd-967a1fc68f52 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500 & For Construction hydraulic drawings
text | 5bc5161d-83a2-59d9-b510-da03a173dbbd |  | textbox | Test or Inspection - All services, external of building in 300mm deep layers
label | 8b6092e0-1bca-5e62-9d1e-971d94cc07ed |  | note | Frequency of Test or Inspection - Per layer, per service
label | 3ee69773-68d2-5141-90f8-d8e2fd5306cd |  | note | Approvals (as applicable) - Add signature below
boolean | 8d5a71f1-d75f-5191-99b5-3631078a0259 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | a7529e3c-34d1-5f5a-9d89-033fc6b29d82 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Record As built Information - Pass once completed
label | 376a10d2-1026-597d-ba62-66fba851173e |  | note | Requirements - Plot & record as installed information on markup shop drawings in site office
label | c2a68dea-5d2b-5366-a368-b223c0ae4946 |  | note | Requirement Reference - For Construction Hydraulic drawings and Specification
label | 7b2c14aa-3533-5331-881e-0339537babdf |  | note | Frequency of Test or Inspection - Prior to backfill
label | ecc7310c-3c76-5a5e-a880-44feb76ac04f |  | note | Approvals (as applicable) - Add signature below
boolean | 53e18c6e-1668-5960-ae7a-2808402278eb |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 24d582d6-e03d-5dc9-8877-1e3c68e7c74a |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Completion - Pass once completed
select | 7995e779-3076-5076-806f-68194729565c |  | dropdown | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | 2e3e63f4-5982-5625-86b0-bb5d99c7ca77 |  | button | Copy to Client | Yes, No
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP-003-Suspended Pressure |  |  |  |  | Yes | ITP-003-Suspended Pressure | bc12433b-57cd-4e00-be91-65996d392957
checkpoint-status |  |  | checkpoint | Identify Route - Pass once completed
text | 5ece21aa-703b-59b9-84a1-aefc1f75d8b3 |  | textbox | Ref HPS shop drawing number
text | eb6ed715-952d-546e-8d9c-f56d53ca17ca |  | textbox | Ref HPS shop drawing number
text | 633d9cd6-45b5-51ff-86a8-96f8d3281e5a |  | textbox | Ref Hydraulic drawing number - where applicable
button | 8d269dd2-4be8-5c0a-a349-a646b9192797 |  | button | Co-ordination required with other trades? Mech, Elec, Fire, Structural | Yes, No
label | 9869636e-4be4-5df7-923f-9e92ade9255b |  | note | Reference Requirement: For Construction drawings
label | 6292ef68-fbca-5a9b-96a3-e0d90b717ab3 |  | note | Test or Inspection - Check drawings are current issue
label | 13845e33-c865-5ca0-8b08-b3b27b7ae9cd |  | note | Frequency of Test or Inspection - Prior to start
label | 8dee2c78-d9b7-5b0f-b567-841d5c49a767 |  | note | Approvals (as applicable) - Add signature below
boolean | 95647033-5ef1-5ead-ba84-ac354f69bfc6 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 21a5d668-de03-5b3b-88e9-8728eeae7530 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Site Set Out - Pass once completed
text | e62d1150-7472-514a-9592-a18e82aff89a |  | textbox | Surveyed Ref points (grids) done by: Engineering Surveys
label | 8624337b-dc1c-5869-9082-6d685151a316 |  | note | Check & confirm route & levels
label | ab707ff7-4ff8-5f6e-a7ee-81bcce5dc659 |  | note | Requirement Reference - Setout drawings
label | a515e868-2651-5629-b435-0df90eae990e |  | note | Frequency of Test or Inspection - Prior to start
label | 633e5ca8-4255-5b1f-a975-6b950afda697 |  | note | Approvals (as applicable) - Add signature below
boolean | f0bfd23a-60f2-5aa8-a667-804b1df880c3 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | ffa50607-89b1-56b7-93ec-6562062cde19 |  | tickbox | Builder - Surveyor / HPS - Click to attach signature below
checkpoint-status |  |  | checkpoint | Install Service - Pass once completed
select | dd672f73-ac77-5131-8b01-cc5a84aa93bc |  | dropdown | Brackets Type | Bi-fix, Two-piece strut, Quickclip, Other
select | 71903f8e-4feb-5a62-9526-9baae25c8637 |  | dropdown | Bracket Spacing (m) | 0.6, 1.5, 2.0, 2.5, 3.0, 4.0
select | a1326a12-9c8d-5ea2-99c2-88ffaced9051 |  | dropdown | Pipe Material | Copper, MDPE, Pe-X
select | 49a3bcaa-e426-5d4f-8c99-1478d52f2122 |  | dropdown | Jointing System | Soldering, Electrofusion, Compression, Other
label | cd58614e-cce5-53ba-83c6-7f89584dd381 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.1
label | 04249620-43bc-5c37-8ef6-990ee72689fe |  | note | Test or Inspection - Carry out visual check of materials for defects or damage
label | cd992060-1a17-5272-8f8c-1516cf424102 |  | note | Test or Inspection - Check for correct jointing of pipe & fittings
label | 99921445-1411-5f3e-985b-1ef6138ed2e7 |  | note | Approvals (as applicable) - Add signature below
boolean | e0eaa661-8916-526a-8428-db97025b5f34 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 369823c6-2945-5aba-b376-3782058eef3e |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Test - Pass once completed
select | 00313929-5c8e-5819-b7ec-97991a8e7237 |  | dropdown | Pressure Test Type | Water, Air, Nitrogen
label | 639432d5-7507-52c7-a857-09d98d6369c5 |  | note | Attach image or plan outlining area of test
text | 3887b12b-fea1-5159-85e1-cf5c10ae8785 |  | textbox | OTR Booking Numbers
text | d0064662-e1f3-5d36-804a-d4d7c0718dfd |  | textbox | Pressure Test to (Kpa)
select | 058d3c93-373d-5304-be5e-a5301a1ec453 |  | dropdown | Test Duration (minutes) | 30, 60, 90+
label | 9405241a-502d-55fe-a9d4-b20f6cdda3a3 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.1
label | 09fda357-8b81-5e7c-beec-b4d0e5de7309 |  | note | Frequency of Test or Inspection - As required (OTR inspector to sign below, if in attendance)
button | 3778fbf9-71b3-59fa-8e18-10ddf6a7a21d |  | button | Inspector attendance | Yes, No
label | 00ffcf2b-08d1-5b55-adc3-a9e9e905a7c2 |  | note | Approvals (as applicable) - Add signature below
boolean | 9610ab4f-cf7b-56d8-a017-d7d9e44de127 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 3862b4a6-5937-5ef5-95bf-bfb674e449a7 |  | tickbox | S.A Water/OTR - Click to attach signature below
boolean | 6a6195de-7965-59d4-8105-302d73494a46 |  | tickbox | APA - Click to attach signature below
boolean | c6425df1-75b2-5d30-99a9-ea63d4b41d75 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Insulation & Identification - Pass once completed
button | fd56ce2f-80e1-5d35-86b4-2b41812e59c2 |  | button | Is Thermal/Acoustic Insulation Required | Yes, No
text | 01ac68ad-004f-5354-99a8-b5c2f5502936 |  | textbox | If Yes - List insulation type/s
label | 1f68e39d-b7c2-5ee1-b54c-e96e07c8bd8d |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500.1
label | f714ca51-136e-5977-814a-610287cb0427 |  | note | Identification & Labelling - Attach photos as applicable
label | 356638c7-5d25-5858-be6b-2b6489473103 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 293b066d-affc-507a-810b-ee9fd3ca0dcf |  | note | Frequency of Identification & Labelling - Every 3m when concealed & 6m where exposed
label | 276f0547-f526-595a-8996-d7c24f5bc9ba |  | note | Test or Inspection - Visually check upon completion
label | c6d10533-44c2-521d-8d44-9dbda00eb898 |  | note | Approvals (as applicable) - Add signature below
boolean | 788c3039-fda5-5796-884e-c815ad511019 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 7741c54f-8a32-5417-855f-04faed4c059b |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Record As built Information - Pass once completed
label | a7e8a4bf-a042-5b54-95e4-92f4cacda668 |  | note | Plot & record as installed information on markup shop drawings in site office
label | 3cc4091d-f56e-5e32-8a98-849a116e0c3d |  | note | Reference Requirement - For Construction Hydraulic drawings and Specification
label | 216526d7-e2b0-5924-8102-dc38e7e4199e |  | note | Frequency of Test or Inspection - Prior to concealment
label | 2358183a-034c-5bde-863f-db5590517a0b |  | note | Approvals (as applicable) - Add signature below
boolean | 49d9162b-7798-5cbb-aea1-411119060c09 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | c1d6bef0-38f1-52bd-a33b-20b313848f40 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Completion - Pass once completed
select | 06cdccf7-15e9-591e-9121-28744ea35bbd |  | dropdown | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | ea56f84b-2863-5cb1-94e8-80cbc04241a2 |  | button | Copy to Client | Yes, No
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | Sanitary & Tapware Commissioning Sheet |  |  |  |  | Yes | Sanitary & Tapware Commissioning Sheet | c2678a06-c877-46b5-9b1c-eda33035e1b8
checkpoint-status |  |  | checkpoint | Basin - Pass once completed
button | f8873476-8653-5fb6-ad0c-b47df5979c7d |  | button | Check for leaks - Basin mixer, trap & waste | Yes, No, N/A
button | ddd57d96-6e44-5928-9873-060b23abdda9 |  | button | Basin mixer & handle is secure | Yes, No, N/A
button | 4686358b-244b-56c1-8287-c02cbc6d4c34 |  | button | Silicone neat and complete | Yes, No, N/A
button | 1f721cf7-dccc-59af-b272-0bc85bb68e72 |  | button | Extended lever for access mixer (if applicable) | Yes, No, N/A
button | cb364a7e-50c0-53c4-9eea-514883b28b12 |  | button | Remove & clean strainer, flush mixer & replace strainer | Yes, No, N/A
button | fea0a798-1de9-5dbe-8726-7c5ca3a85746 |  | button | Check red and blue indications for tempered/cold water | Yes, No, N/A
button | 99d22e30-6e94-591b-b35e-18f43dfdec32 |  | button | Check flexi hoses are tight - no kinks | Yes, No, N/A
select | 422b4b13-e5e9-5dff-ac62-290851b270b7 |  | dropdown | Check completed for multiple basins - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | 2a1e7ea6-ac44-55e5-ba21-05bdba03684a |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | Water Closet/Pan - Pass once completed
button | c907a472-ddbf-51dd-a6b5-b737aa426044 |  | button | Check for leaks - WC/Pan water connection | Yes, No, N/A
button | 12d58ae9-893b-55e5-95d7-5c57c69a7b58 |  | button | Silicone bedding around pan | Yes, No, N/A
button | b0d1ad72-4f4d-533d-9ee0-e1dbd08f6f5f |  | button | Silicone seal pan to wall (neat) | Yes, No, N/A
button | 771861db-fdd3-57f4-b292-2fa261861f3f |  | button | Check proper WC flush (single & dual or Disabled) | Yes, No, N/A
button | f38e6896-8e6b-5100-a475-4f2022070b57 |  | button | Flush toilet paper to test | Yes, No, N/A
button | ad0dbe2a-14c2-52df-a895-2e1bad2c612c |  | button | Check tightness of seat & buttons - and backrest for Access WC | Yes, No, N/A
button | 908e557e-2176-5b9e-b3ec-3450e12f987e |  | button | Check WC is secure | Yes, No, N/A
button | 28c63c26-2da3-52a9-86f8-61a56cf06051 |  | button | Check flexi hoses are tight and cistern cock is open | Yes, No, N/A
select | 46dbaa61-d62c-52a0-9ce6-37bf4f1a6a9f |  | dropdown | Check completed for multiple WC's - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | 228c7249-138f-5f70-9ff6-18506551b516 |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | Urinal - Pass once completed
button | 7f3a24b8-0fbd-523d-af7a-7da4744dbb6b |  | button | Flush water from valve before connection to solenoid | Yes, No, N/A
button | a935c9cb-43a8-5d8c-9bd5-d75be1583f62 |  | button | Check for leaks - water connections & flush pipes | Yes, No, N/A
button | 18f7e8df-ae60-5a25-a7f9-8f0d23b02fff |  | button | Silicone urinal to wall (neat) | Yes, No, N/A
button | 7618e3db-03ee-5c26-8a64-6d9ca550da3c |  | button | Check urinal fixed securely to wall | Yes, No, N/A
button | 25240a37-eac6-5c9f-9a02-7de2167dc1eb |  | button | Check sensor function - water/wave test | Yes, No, N/A
button | 1fb04d41-1a2b-5bdb-8797-ca8b736296e8 |  | button | Set delay and flush time - in valve box | Yes, No, N/A
select | 88632e4a-0f0b-5e5f-8728-508072e73e7f |  | dropdown | Check completed for multiple Urinals - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | c50548c9-8315-5da4-9717-159c0052178a |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | Shower - Pass once completed
button | 47c61403-fdeb-516e-97d5-72a691e49e3e |  | button | Check for leaks - hose connections | Yes, No, N/A
button | 293d827a-e3b9-5807-a159-c44bff3cbc29 |  | button | Check shower mixer trim & handle is secure | Yes, No, N/A
button | 7e5fb1b5-6d0b-50e7-b5c9-7f98def4f997 |  | button | Check shower rail is secure and plumb for Access shower | Yes, No, N/A
button | 1586cdde-67c5-5ea1-8cb4-38a4b52e6777 |  | button | Check operation of hand/wall shower | Yes, No, N/A
button | 861185b1-f3ac-5ff7-b45d-5d3b2484cfb8 |  | button | Remove strainer and flush shower rose | Yes, No, N/A
button | aca7f6af-8e1f-5156-92b0-8720a9a64359 |  | button | Check red and blue indications for tempered/cold water | Yes, No, N/A
select | 5eff00c4-3ee4-5c15-b499-8b0210e2204f |  | dropdown | Check completed for multiple Showers - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | 974f8b4d-be7a-5117-ac77-4b5e5ba084c2 |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | Kitchen or Cleaners Sink - Pass once completed
button | 7a53f424-be33-5ec5-9180-71558cec65eb |  | button | Check for leaks - Sink mixer, trap & waste | Yes, No, N/A
button | ac1f8e91-588f-512d-966d-864cf64ae5e6 |  | button | Sink mixer is secure | Yes, No, N/A
button | 2442747c-d585-506f-b5e2-da63c171afa9 |  | button | Clean silicone from P&W | Yes, No, N/A
button | 3f7e5970-5798-5041-bdf3-d3818a76679d |  | button | Remove & clean strainer, flush mixer & replace strainer | Yes, No, N/A
button | 0e3f610a-ec9a-5686-b18d-02137ae16e8b |  | button | Check red and blue indications for hot/cold water | Yes, No, N/A
button | 1ceda3f2-e781-55e3-a8be-246065771886 |  | button | Check flexi hoses are tight - no kinks | Yes, No, N/A
select | 2cd00801-c26e-52e9-b16a-cd1ecc92663a |  | dropdown | Check completed for multiple Sinks - record quantity | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
text | 4fa3e587-b201-530c-80c9-f8c7398e2add |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | BCWU - Pass once completed
button | 2fe451c6-deac-55f2-a0af-0e207ac99c1c |  | button | Tap is secure | Yes, No, N/A
button | 25bb7b14-10d4-5b79-95af-1c95bf3cd309 |  | button | Check flexi hoses are tight - no kinks | Yes, No, N/A
button | 740ae64a-d954-505c-9b1d-5455784d63bf |  | button | Set & commission BCWU (per manufacturers instructions) | Yes, No, N/A
button | e35e01f0-eb83-5d59-9e94-ef55a5c04e2f |  | button | Remove strainer and flush tap | Yes, No, N/A
button | 0445b332-b10c-51ff-9388-ee8db983ff94 |  | button | Check for leaks - Pipework & tap | Yes, No, N/A
text | e0a39d2b-ae8e-5dc2-9cac-7d9f76186b92 |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | Equipment - Pass once completed
button | 7972a89d-26fe-5bb1-bbaf-25b7fd165b5b |  | button | Check cover/door fixed firmly and open/shut correctly | Yes, No, N/A
button | 27dc24e2-3728-5aa7-b4d8-45fa05322d0e |  | button | TMV commissioning sheet complete (attach, if required) | Yes, No, N/A
button | 23a506e1-cca5-5f43-adfa-b7cea4c71b26 |  | button | Check operation of Auto Trap Primer | Yes, No, N/A
button | 7461faac-9a66-586a-83e8-c5fd0b1c18b3 |  | button | Check TMV/Trap Primer connections for leaks | Yes, No, N/A
text | feb9cdba-1a73-5015-a9ca-d5675eae7a09 |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | Other final checks - Pass once completed
button | 698b4d36-6691-5e06-9e82-f4b9880b67a3 |  | button | Remove tape from floor grates/IP covers and check | Yes, No, N/A
button | 728a115d-c714-5991-bf3f-f00b4f105f5f |  | button | Remove tape from Bolted trap screws | Yes, No, N/A
button | 6746e252-6306-510a-9b0e-b14f4133a441 |  | button | Remove all labels & stickers | Yes, No, N/A
button | 3d51628b-e08b-5ddf-9d34-9b3224770424 |  | button | Check floor waste for debris & clean (if applicable) | Yes, No, N/A
button | 496fda99-4552-518b-ac99-683a245277ee |  | button | Check grates & IP covers are installed and clean | Yes, No, N/A
button | 4280becd-c7bf-541d-84f9-d8aca48d66f1 |  | button | Check tundish cover installed (if applicable) | Yes, No, N/A
button | fff30176-7fdf-5135-8695-ecf83fc6c509 |  | button | Check all fixtures for damage | Yes, No, N/A
button | 559de9d8-c8d0-599a-8db7-1ae9724d68e4 |  | button | Ensure all fixtures are protected | Yes, No, N/A
button | 92a2b892-c6a9-50ad-9dc1-e9711c6ee058 |  | button | Remove all HPS rubbish from room | Yes, No, N/A
text | 9bcd8007-c91f-596a-9908-7dfc4a467639 |  | textbox | Comments:
checkpoint-status |  |  | checkpoint | Compliance Verification - Pass once completed
button | 7201c5f0-55c6-5a22-bd20-71f0821a9d7e |  | button | Complies with criteria | Yes, No, N/A
button | 5a100647-0d74-5bb2-bab0-8261df618b20 |  | button | Corrective actions required | Yes, No, N/A
button | e0982afc-7e00-55d7-be16-1c7ff18d2365 |  | button | All works completed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Completion - Pass once completed
text | ba6748f2-ddcd-5a93-94a9-c7f1c2f3dd2f |  | textbox | Room Completed & Inspected by
select | 97569d6c-27ee-5f22-a12c-a4c7adb45deb |  | dropdown | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | 44dd5c24-e035-5d0a-ad4d-7ae8adc87cc0 |  | button | Copy to Client | Yes, No
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP-001-Sleeving of Penetrations (B) |  |  |  |  | Yes | ITP-001-Sleeving of Penetrations (B) | c4d98045-a644-4a90-89ef-cc9c27442ad6
checkpoint-status |  |  | checkpoint | Identify Route - Pass once completed
text | 4ce11744-aff6-50bd-807d-b39ea743b9a3 |  | textbox | Ref HPS shop drawing number
text | 0b522cba-5a03-5557-9924-dfe5f25f1584 |  | textbox | Ref HPS shop drawing number
button | d68d6685-57f1-52ee-aa92-7602435aabd6 |  | button | Co-ordination required with other trades? Mech, Elec, Fire, Structural | Yes, No
label | 1621edb2-f759-5e32-931c-e15934088086 |  | note | Reference Requirement: For Construction drawings
label | bb861130-2099-556a-8956-a50e4ac95ed8 |  | note | Test or Inspection Type - Check drawings are current issue
label | e602655e-b500-5483-9c2c-1db9768b4a54 |  | note | Frequency of Test or Inspection - Prior to start
label | 8c44ae78-aee0-5bd2-99f8-a1fad558293d |  | note | Approvals (as applicable) - Add signature below
boolean | 6aa63cfe-8b64-56a5-be7f-f1217f8072ce |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | a5506578-2ea9-507c-9b26-000de9541d64 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Site Set Out - Pass once completed
label | e2c78ca4-87c8-573e-849f-c4bc7f513738 |  | note | Surveyed Ref points (grids) done by: Engineering Surveys
label | b32002eb-6841-5a91-9799-0878cbb52618 |  | note | Check & confirm penetration sizes & sleeves/fire collar required
label | a946f14c-13ce-5e33-822f-d6db9c25a9ee |  | note | Reference Requirement: Setout drawings
label | 52ec3d3a-212c-5412-b53f-fbfb1c6242de |  | note | Frequency of Test or Inspection - Prior to commencing installation of Sleeves / Fire collars
label | cd5742df-262a-5e6c-bae1-5521de4dfbbb |  | note | Approvals (as applicable) - Add signature below
boolean | 22f6e26e-d409-5d81-86e4-a3f65598c3d2 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 535f0290-ab8e-511d-89c5-9e08f6d45a2f |  | tickbox | Surveyor / HPS - Click to attach signature below
checkpoint-status |  |  | checkpoint | Install Penetrations - Pass once completed
label | aa5cd946-6ac1-5fc5-a9cc-96519edc8312 |  | note | Requirements - Fire Collars & Materials
label | b3086525-aa09-5951-bfb7-841022a660ab |  | note | Reference Requirement - Spec - 17128-SPEC-CSB
label | 52648838-d279-5aca-9bbe-2915a7f7d3b5 |  | note | Test or Inspection - Carryout visual check of materials for defects or damage.
label | 868c7ed2-3c0a-50f5-bac8-d0ff88f8f63f |  | note | Frequency of Test or Inspection - After install, prior to final sign off
label | 401d6ae1-e0c5-5e4f-b077-5d8990746803 |  | note | Approvals (as applicable)
boolean | 8ddc21db-4f0d-5a0a-83d3-7f373628d03b |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 8ddc3a6a-2d4a-5565-bbdf-1b598ff761a9 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Final Check - Pass once completed
label | dd3192b2-ba42-5c60-96ea-5d1a8d802dcb |  | note | Check all penetrations are installed
label | 3ce7e4f0-cf14-579b-aeb9-bbd70774a64f |  | note | Inspection of penetrations during Concrete pour - where applicable
label | 5fa53b96-23ad-54a2-9281-c11f8bf091a7 |  | note | Reference Requirement - For Construction drawings
label | 47dedbe6-a492-53b5-a85d-7666a047bd68 |  | note | Frequency of Test or Inspection - Prior to concrete pour
label | 2b24ad50-65ff-5d69-8fbe-4aa50215fbde |  | note | Approvals (as applicable):
boolean | 399ad36e-e6f8-579d-8646-f1e6215b6177 |  | tickbox | Hindmarsh Plumbing - Click to add signature below
boolean | 7a7e084a-0fd8-5f13-b56a-0b116140e4cd |  | tickbox | Builder - Built Environs - Click to attach signature below
holdpoint |  |  | signoff | Click to add sign-off Signatures
checkpoint-status |  |  | checkpoint | Completion - Pass once completed
select | d8d2c933-3820-5a96-ae43-15d362a55617 |  | dropdown | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | 385dc59d-7bb2-5887-a2c7-8ac8b2875bd5 |  | button | Copy to Client | Yes, No
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP-004-Inwall Pipe Installation (B) |  |  |  |  | Yes | ITP-004-Inwall Pipe Installation (B) | c99bb70d-d0cc-4c45-baa5-f9898de33921
checkpoint-status |  |  | checkpoint | Room/Site Set Out - Pass once completed
label | a81d820a-e597-55f8-a44c-72f8ca9dce69 |  | note | Identify trimmer, water point, and 1st fix item requirements
label | f98825f9-0327-5acf-a20c-5e564b13ad50 |  | note | Reference Requirement - Setout drawings
label | b783970b-2e8b-5d6f-88d2-9cf2d72bd5b2 |  | note | Install trimmers, water poinst, and 1st fix items
label | 52f57807-1d53-57ad-b4b6-12a45fd17b16 |  | note | Check & confirm pipework route
label | c1351a72-f713-5590-aaac-05b1c6b9fda7 |  | note | Reference Requirement - Setout drawings
label | 10fbe6e1-4d9d-5385-b441-fdd5b76a6b5c |  | note | Approvals (as applicable) - Add signature below
boolean | 02c56d68-6ddb-5db4-ab7a-58662b138f0a |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | ec8dbdf2-2270-591a-9ee5-2340f7657ea5 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Install Inwall Pipework - Pass once completed
select | 96860c4e-4d65-52e0-8470-433613a86783 |  | dropdown | Pipe Material / System | Rehau, Copper
select | c78e838d-2ddc-544d-a90f-eff9bf38147c |  | dropdown | Brackets Type | QuickClip, Saddle Clip
select | a436a2a9-46c6-5e09-a352-dc94dc1fc812 |  | dropdown | Bracket Spacing's (mm) | 600, 1000, 1500
label | f6d06fee-2dbf-5f21-94c0-40ef91137c13 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | ac374c93-5deb-5f1e-9734-b66c4f039280 |  | note | Test or Inspection - Carryout visual check of materials for defects or damage.
label | 2b389fcf-72bb-5850-8560-4388146c858b |  | note | Approvals (as applicable) - Add signature below
boolean | dc949650-3856-5160-9d37-f03b1803cbff |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 3002bbcc-fdcc-5c1d-9808-b9e2862e6fb9 |  | tickbox | Builder - Built Environs - Click to attach signature below
boolean | 214fa086-c88b-5035-9cdb-daa5b5c95314 |  | tickbox | Consultant - Click to attach signature below
checkpoint-status |  |  | checkpoint | Carryout Installation Checks - Pass once completed
label | 788d6fec-8af8-5fb5-b6a7-6745e440cc89 |  | note | Requirements - Install pipework to all fixtures and check the following:
button | b30daa1f-688e-541f-a7f3-b334cd44d674 |  | button | Correct fixtures and fittings installed | Yes, No
button | e8a8c2df-c08c-5790-a01b-8fac49bf7e3e |  | button | Cross connections | Yes, No
button | d5c8db91-5887-5fba-a220-e2795a09866a |  | button | Pipes rubbing against sharp surface | Yes, No
button | fc504280-1183-5e40-bb58-47ead58df59a |  | button | Screws hitting or rubbing on pipes | Yes, No
button | 1818c6db-0c9d-585b-95e6-5b9ad6a075c3 |  | button | Screwed joints in wall are tight | Yes, No
button | e086ad25-7c68-5256-a44c-7165cb4ac770 |  | button | Ensure all joints have been crimped / welded correctly | Yes, No
button | 43b20cb4-7a3a-5ffc-9c08-563939e7dda0 |  | button | Pipes do not stick out beyond studs | Yes, No
button | 6c999cbd-470d-5d71-b979-1826f7da851e |  | button | Pipes are not in a position that will increase the chances of being screwed through by wall contractor | Yes, No
label | 45329dab-257f-567c-a2a4-eebee7d473bc |  | note | Attach images of inwall installation
label | 63ee57ed-9091-5eb0-8e51-429765b2d31d |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & Setout drawings
label | 9d781f5a-f994-5bdc-addc-e78345110ecc |  | note | Frequency of Test or Inspection - Prior to concealment
label | 4c86442d-de58-525b-953d-d9a170574741 |  | note | Approvals (as applicable) - Add signature below
boolean | e20232e7-13b7-56a1-963e-282c6a129ecd |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | a515ad17-205e-5427-bb7a-90a8cb7776a7 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Test - Pass once completed
select | a465191f-c2cc-506b-be19-d38577ff5073 |  | dropdown | Pressure Test Type | Water, Air, Nitrogen
label | cd9faadf-7311-562e-ac21-6e4dc0045ba8 |  | note | Attach image or plan outlining area of test
text | 823c9490-915f-56c6-a77f-31412f73fcab |  | textbox | Pressure Test to (Kpa)
text | ab3cebd6-b215-56c0-beb5-70e8328f4aef |  | textbox | Test Duration
label | a87038d8-5ce9-5639-ab11-0da13365529a |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 540b2a08-618c-538f-9b3a-646b698b7d5b |  | note | Frequency of Test or Inspection - As required (OTR/Inspector to sign below, if in attendance)
button | effafeeb-816b-5ef4-afb6-6e80f0fc700d |  | button | Inspector attendance | Yes, No
label | 1ef42e1e-29de-57fd-afdd-a49e58f342f5 |  | note | Approvals (as applicable) - Add signature below
boolean | 861f186a-2601-547e-b71f-b3e8a7899ded |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 82e647fb-1284-56f0-bff5-129ab6ac8e92 |  | tickbox | Builder - Built Environs - Click to attach signature below
boolean | 8a81f2ad-9337-5a0f-9cd6-5e9cc238515b |  | tickbox | OTR/Inspector - Click to attach signature below
checkpoint-status |  |  | checkpoint | Insulation & Identification - Pass once completed
button | 6acbb105-1a8a-5291-883a-fd9f800bd50e |  | button | Is Insulation Required | Yes, No
select | ec31fedb-f92f-5a32-8c9d-f0f13efb660f |  | dropdown | If yes, Type? (N/A if not required) | Armaflex, Thermobreak, Acoustic, N/A
label | 269de5a9-0aa6-557b-a438-b2476a9ffdad |  | note | Identification & Labelling
label | c96c3e94-0d66-567b-9b96-cc041b1bf3f6 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 0c97e6a7-e932-57a5-b36b-bf06ad8da875 |  | note | Frequency of Test or Inspection - Every 3m when concealed & 6m where exposed
label | a48fff80-52ac-5e40-82b6-cb73d5ffb6ff |  | note | Approvals (as applicable) - Add signature below
boolean | 5188a529-b334-5893-85e1-009a7abbf93d |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | aee90bb3-4999-5f68-a998-1bf100825ec6 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Fill Out Inwall Installation Check Sheet - Pass once completed
label | 59376272-bc06-5f8f-aaf8-097c894133e7 |  | note | Requirements - Refer Inwall Pipework Installation, Process & Check Sheet
button | 6dc00d1d-edf6-56b3-a300-01778b571bcc |  | button | Test or Inspection - Inwall Installation Check Sheet complete? | Yes, No
label | e9c8260d-08d6-5c38-b3d2-3649617848a4 |  | note | Approvals (as applicable) - Add signature below
boolean | 3add9736-e231-57a7-b2de-0d9eb082a93c |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
checkpoint-status |  |  | checkpoint | Sign Room/Wall/Ceiling Sign Off Sheet - Pass once completed
label | 8f7f8371-76c6-52e5-91dc-f21223cdb998 |  | note | Requirements - Once all checks are completed, sign builders room/wall/ceiling sign off sheet (if applicable)
label | 904674f1-0e32-5272-b3e7-4f1712a52a15 |  | note | Frequency of Test or Inspection - Once in wall pipework, test & checks are complete, prior to concealment
label | 8b4ac6e1-688e-51fc-b61c-a5631a67de37 |  | note | Approvals (as applicable) - Add signature below
boolean | 80278b4c-0a45-5207-b86b-0010e27ec2bf |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
checkpoint-status |  |  | checkpoint | Completion - Pass once completed
select | 19ed9846-5cdb-5b69-affb-324e2ef3212c |  | dropdown | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | d47c6a99-3204-54a1-a56c-2bd9e9fe24a8 |  | button | Copy to Client | Yes, No
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | Toolbox Meeting Checklist |  |  |  |  | Yes | Toolbox Meeting Checklist | cfe6bca9-cf09-4af2-a123-7fbe440d8c7c
checkpoint-group |  |  | section | Attendance
checkpoint-status |  |  | checkpoint | Attendance - list of attendees added below
checkpoint-status |  |  | checkpoint | Apologies - list of non-attendees added below
checkpoint-group |  |  | section | Minutes
checkpoint-status |  |  | checkpoint | Actions from last meeting
checkpoint-status |  |  | checkpoint | Administration
checkpoint-status |  |  | checkpoint | HR
label | b0d97cfa-790e-54dd-a808-d32fb2e36e0b |  | note | e.g - Site recognition, any HR issues?
checkpoint-status |  |  | checkpoint | Safety: (including hazards / near misses / controls / site specific)
label | 28165a1f-ad08-5c4e-a40d-f73bb0c1ab7e |  | note | Discussed recent incidents
label | 01189fa4-57b8-5621-b43f-cbe2cd8c038b |  | note | HSE Monthly Reports
label | 1efabcab-bd92-5863-8e7d-9edf5c4a310d |  | note | SDS – Of the week (list which SDS you have reviewed)
checkpoint-status |  |  | checkpoint | Environment: (including hazards / controls / incidents / impacts)
checkpoint-status |  |  | checkpoint | Training
label | cc55897b-c7a2-5000-8097-4b07ffb4f8d4 |  | note | Competency Assessment Guides (Apprentices) if applicable – are they up to date?
checkpoint-status |  |  | checkpoint | Plant & Equipment
checkpoint-status |  |  | checkpoint | Issues & Customer Feedback
checkpoint-status |  |  | checkpoint | Client/Job specific information:
checkpoint-status |  |  | checkpoint | HSE Committee: (key points from minutes / questions / feedback to be raised at next meeting)
label | bfe3615c-f916-5ee1-a849-2cc0171d7c2c |  | note | Discuss recent HSE Committee Minutes
checkpoint-status |  |  | checkpoint | Memo’s and other office correspondence
checkpoint-group |  |  | section | Document Review
checkpoint-status |  |  | checkpoint | Document uploaded below if applicable
checkpoint-group |  |  | section | New Business / Other
checkpoint-status |  |  | checkpoint | Any new business / other comments added below
checkpoint-group |  |  | section | Meeting Closure
checkpoint-status |  |  | checkpoint | Meeting Closed
text | 9e8d0fc0-48cc-5d25-b153-8e8646a91218 |  | textbox | Meeting Closed time
text | e115af19-e13e-5d74-aa88-4c82f64988d0 |  | textbox | Date for next meeting
text | 33b2c92a-2297-5941-97bf-49afeb81c776 |  | textbox | Minutes taken by (Name)
checklist-flat |  |  | checklist | ITP-005 - Inground Pressure Service |  |  |  |  | Yes | ITP-005 - Inground Pressure Service | eb4105c8-1ac6-4279-a4df-f57da05aaa12
checkpoint-status |  |  | checkpoint | Identify Route - Pass once completed
text | 7544cc06-755e-56c7-a8cd-9f350312f8bb |  | textbox | Ref HPS shop drawing number
text | 42444226-f977-5b62-9d47-60eaa637e106 |  | textbox | Ref HPS shop drawing number
text | 5a485d67-75e4-5b1c-a215-f3cdd053bf3c |  | textbox | Ref Hydraulic drawing number - where applicable
button | 05835787-17cb-5a71-a478-ecc951e73f2c |  | button | Co-ordination required with other trades? Footings, Elec, Fire, Structural | Yes, No
label | da1a92f7-bd50-5a0c-aa87-7278da5b9641 |  | note | Reference Requirement: For Construction drawings
label | 18fd4e41-790c-5daf-90ce-75c451c128d6 |  | note | Test or Inspection - Check drawings are current issue
label | 881bc62d-e52a-5bbc-b6de-ffb6566aab09 |  | note | Frequency of Test or Inspection - Prior to start
label | f041e880-631b-5fb6-919a-892814727af4 |  | note | Approvals (as applicable) - Add signature below
boolean | 5b90f45c-5877-5ab2-9642-652afaaa901b |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | df725dd5-ec5b-5201-a762-55dfcd71eacc |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Site Set Out - Pass once completed
label | d3777eda-d537-5a48-8bd5-2462ac4c58d4 |  | note | Surveyed Ref points (grids) done by: Engineering Surveys
button | 7e996f99-f1b2-5777-9733-a4ab35fecb3d |  | button | Check & confirm route levels | Yes, No
button | 5059327b-a9df-5de5-b06e-d6d34c9da636 |  | button | Identify and locate existing services | Yes, No, N/A
label | 0ea9feed-7cd4-5a3c-bf68-e5e9cb00c711 |  | note | Reference Requirement - For Construction drawings & Existing Services drawings
label | 07bd633f-a5a3-5fce-acf2-a07f8e2452a0 |  | note | Frequency of Test or Inspection - Prior to set out of trench and Prior to any excavations beginning
label | d2d8df14-f127-518d-a8ed-b9843f174529 |  | note | Approvals (as applicable) - Add signature below
boolean | 7bf085ad-95d0-5112-a900-9b282d6bd747 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 813f9b43-3f95-502b-b746-ca888b14bc0d |  | tickbox | Builder - Surveyor / HPS - Click to attach signature below
checkpoint-status |  |  | checkpoint | Excavate Trench - Pass once completed
label | 2eb8f260-ec89-5f59-af3c-546ddb6a8bb0 |  | note | Excavate to 50mm (max) below pipe invert
label | 605b1302-a209-55ea-9ebd-456410aab81e |  | note | Separate contaminated fill from clean fill
button | d6fa366c-b56c-5490-a97f-91c549153fc4 |  | button | Spoil to be - Removed | Yes, No
button | 97c7561c-fb45-56ce-b19b-5f7780c8d104 |  | button | Spoil to be - Stockpiled | Yes, No
label | 2d805538-d4d8-5b12-aef0-8cba6a8ce6ae |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | 287ee9fa-cca8-5119-a72e-11f416977e9b |  | note | Test or Inspection - Check spoil for suitability to re-use as backfill or to determine off-site dumping requirements
label | 39fe9a64-bf85-5f93-9f1e-d7c236b70eb0 |  | note | Frequency of Test or Inspection - Prior to backfill
label | 77df7b72-25c1-55f1-b110-3d75eaf7d8fa |  | note | Approvals (as applicable) - Add signature below
boolean | b61e4d8b-1da4-52e3-bdd1-5b4a0c37272f |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | efcacb40-858f-57c0-be42-eb480cbc6dbb |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Place Service Bedding - Pass once completed
button | 5e239b4a-b4db-5212-8ac4-47e34234541f |  | button | Ensure trench base is free from large rocks & debris that may damage the pipe | Yes, No
label | 09ac9eef-1e7a-5faf-a426-c606ecd490ce |  | note | Requirements - Place 50mm Sand bedding for pipe
label | eb0e6d9f-8f4f-5b14-b0b7-33dd65035945 |  | note | Sand Type - PM64
label | 4a2691d1-1d7d-56a5-8cd0-8df516f8d131 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | a6be5368-7412-5b0e-a1c8-29e14bd4c5bf |  | note | Frequency of Test or Inspection - Prior to installation of service
label | bd7b71c7-57b2-55a9-a139-9171054b2a5e |  | note | Approvals (as applicable) - Add signature below
boolean | 6e8d773f-605a-5d3f-961d-6d22e5eda3b9 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 717d620a-e359-55a4-b234-1f113d0dfdd2 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Install Service - Pass once completed
select | d26cf2ac-794f-590d-8610-aa8a73dff9d9 |  | dropdown | Material Type | MDPE, HDPE, Copper, PVC-Pressure
select | 24dc6c2d-282d-5e50-a826-73e1e4b7b8ce |  | dropdown | Corrosion Protection Type (N/A if not required) | Denso & Overwrap, Other, N/A
button | b1faee0c-72cc-562f-9d15-f942cb617fbe |  | button | Thrust Blocks required | Yes, No
label | 23875520-3a27-50d9-a13d-90dec512fc0b |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | ad8a7db2-0cc9-5fbc-bc0c-a003bccbc775 |  | note | Test or Inspection - Carryout visual check of materials for defects or damage
label | f462f3ae-d1cd-5f4b-9763-2560ca564965 |  | note | Approvals (as applicable) - Add signature below
boolean | 9c39d9d5-7915-5785-a327-5e9301f62c0a |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 1a9f1a57-b76a-568f-871f-17db0b610434 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Test - Pass once completed
select | 39275aa0-4a28-5799-992c-2918bd599a25 |  | dropdown | Pressure Test Type | Water, Air, Nitrogen
text | d6335c66-0087-5a49-8f83-c1b20bdc5d9d |  | textbox | Pressure Test Services to (Kpa)
select | 8394e6a7-5e2e-567e-8b11-e56eac876cf5 |  | dropdown | Test Duration (minutes) | 30, 60, 90+
label | 40b0e41e-954c-5417-8a9c-cde1a1cd21b4 |  | note | Attach image or plan outlining area of test
text | 1247505a-9322-5e8e-b8c8-9f3f70207906 |  | textbox | OTR Booking Numbers
label | 11fed094-d493-5d0a-8980-920d4e0d0f31 |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500
label | daa0294d-d0bf-5e22-92a8-3f83caafdf37 |  | note | Frequency of Test or Inspection - As required
label | 60f8299b-a5d0-5f4b-b0d8-f4baa0746636 |  | note | Approvals (as applicable) - Add signature below
boolean | aa8d0e0c-7800-5e6e-a41f-9e1f4e5cec17 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | 123c4a95-9173-57ff-938a-c7379bc77f96 |  | tickbox | S.A Water/OTR - Click to attach signature below
boolean | 89e4f7ce-80e9-512a-bc81-1de7101856d5 |  | tickbox | APA - Click to attach signature below
boolean | 5e8028ce-5460-53c1-bd19-2ba906affef6 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Backfill - Pass once completed
label | c15dd71f-c86f-56ca-89af-cab226eb8836 |  | note | Requirements - Blind off pipe with sand to a depth of 300mm above overt of pipe
label | ce265c78-8aba-5343-8e5b-0999b593c34d |  | note | Sand Type - PM64
label | b4c93557-4072-5d92-9c6c-46c47d173dc6 |  | note | Install detectable ID tape at 300mm (or 1 layer) above overt of pipe
label | 8c2a3715-2038-5660-b77c-2ba4ad827ecd |  | note | Backfill trench to 100mm below finished surface with cleanfill
button | f66ee093-f5de-53b4-b3e3-9dbfedb3add2 |  | button | Compaction tests required | Yes, No
label | 72587371-7bcb-554a-b22f-1ef82660d30c |  | note | Reference Requirement - Spec - 17128-SPEC-CSB & AS/NZS 3500 & For Construction hydraulic drawings
label | ddeed727-5d1f-5e43-a812-f20a13d66bc5 |  | note | Test or Inspection - All services, external of building in 300mm deep layers
label | b4cafdae-f21c-5a53-b072-6ec297f7178b |  | note | Frequency of Test or Inspection - Per layer, per service
label | b91cf50c-2394-5c54-93dc-ba283a216f0d |  | note | Approvals (as applicable) - Add signature below
boolean | 3802d125-82b0-5ddd-bad6-23517d7ad746 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | f8f23528-40ca-56a6-a5be-19afb0c210a9 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Record As built Information - Pass once completed
label | 4ee7090c-1d77-5a9e-826e-3704a31546f5 |  | note | Requirements - Plot & record as installed information on markup shop drawings in site office
label | 0ce81d41-39ad-5b6c-9788-4c94cea9785e |  | note | Reference Requirement - For Construction Hydraulic drawings and Specification
label | 627efdd6-5278-5c49-ab03-c62f9c1ea0f5 |  | note | Frequency of Test or Inspection - Prior to backfill
label | 33d5bfdd-b074-56c4-baec-6e2cdd8105c8 |  | note | Approvals (as applicable) - Add signature below
boolean | 250bf805-7740-5171-af4f-af46ce25f9c6 |  | tickbox | Hindmarsh Plumbing - Click to attach signature below
boolean | ff9aea4e-e9ce-55ca-806b-d86324cd8524 |  | tickbox | Builder - Built Environs - Click to attach signature below
checkpoint-status |  |  | checkpoint | Completion - Pass once completed
select | 7101b670-4f79-545d-a4fa-4b896e0f6715 |  | dropdown | Site Manager | Marc D'Ortenzio, Tariq Eltahir
button | 1843e67e-dc6f-5d0c-878b-e357c0891981 |  | button | Copy to Client | Yes, No
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | In Wall Pipework Installation Checklist |  |  |  |  | Yes | In Wall Pipework Installation Checklist | eb95ba37-cbd1-4631-a3a1-988d4229a3e6
checkpoint-status |  |  | checkpoint | In Wall Pipework Installation - Pass once completed
select | 64fc867d-9764-5ca8-83b4-de0003da3852 |  | dropdown | Confirm Pipe System | Copper, Rehau, MDPE, Other (Specify below)
text | 2ee11592-0b6e-5b4b-9d26-ec88617b9416 |  | textbox | Other (Specify here)
button | 48e08179-6451-5c4e-8b66-81aa3b81e1c1 |  | button | Check trimmers for correct locations & length | Yes, No
checkpoint-status |  |  | checkpoint | Install pipework to all fixtures watching for the following - Pass once ALL completed
button | 477df327-8f1d-5d57-b3ac-20a65040953b |  | button | Cross connections | Yes, No
button | be94df91-4bf2-5258-99bd-09cb2c22849a |  | button | Pipes rubbing against sharp surface | Yes, No
button | 1ea9b3b2-be46-581c-8af9-280a52e54c58 |  | button | Screws hitting or rubbing on pipes | Yes, No
button | 05f2045f-ee47-5fd7-8faa-b1edf506a076 |  | button | Screwed joints in wall are tight | Yes, No
button | 60442289-2b6b-5e04-aab9-3ad59ca45217 |  | button | Ensure all joints have been crimped / welded correctly | Yes, No
button | 4b33433a-9b41-5020-8223-5ded42c68784 |  | button | Pipes do not stick out beyond studs | Yes, No
button | f4101c51-1294-5973-9c77-b35c1a3732e9 |  | button | Pipes are not in a position that will increase the chances of being screwed through by wall contractor | Yes, No
button | 272c8ddc-8347-5d3e-b5f8-27985cd0797c |  | button | Pipes to fixtures come directly down in line with the water outlet | Yes, No
button | 79d9b7db-82d6-5f6b-aff6-bdd8f66f2fd8 |  | button | Ensure second piece of piping is split and fitted over pipe where brackets or grommets can't be installed through metal studs | Yes, N/A
checkpoint-status |  |  | checkpoint | Re-Check in wall water drawings to make sure all items have been installed
checkpoint-status |  |  | checkpoint | Brackets installed as per pipe system manufacturers recommendations
select | c3286169-2adb-52d6-9eaf-f0485f5fb12b |  | dropdown | Type | QuickClip, Saddle Clip, Grommet, Macrofix
select | 5a598a47-3a40-5fe7-a6af-9c70b66ef76d |  | dropdown | Spacing | 600, 1000, 1500
checkpoint-status |  |  | checkpoint | Pipework has been tested, to maximum of 1500 KPA
checkpoint-status |  |  | checkpoint | Check room for following - Pass once completed
button | 1efba8b6-2fb0-5aa8-b460-2c61c2f2daed |  | button | Check all fixture measurements off stud wall are correct | Yes, No
button | fb420cb8-0564-551c-a081-12badb2a9e05 |  | button | Broken pipes (Advise site manager if there are) | Yes, No
button | 551ea917-6be4-5bba-9cbd-3cb63b562425 |  | button | Check all pipes have caps fitted (Drainage and water pipes) | Yes, No
button | 7df7914a-6127-5bf4-ad92-8689aa1cdf69 |  | button | Check for any pipes that aren't connected below(If unsure, advise site manager) | Yes, No
button | 0bae495b-23c6-591e-b881-f7d3a55c4b61 |  | button | Check ID stickers to stormwater & sewer stacks in voids. Fit if required | Yes, No, N/A
button | 6c12b57b-eebb-55a7-99a8-3795ab3f8e1e |  | button | Grey tape or insulate any copper pipes touching steel studs (Check before leaving) | Yes, No, N/A
checkpoint-status |  |  | checkpoint | In-Wall Pipework & First Fix Works completed to specification/drawings
label | 5387167c-543f-5da3-87b9-4696541bd45b |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
boolean | 728d6387-f60d-59b5-af3c-3512634f1eb4 |  | tickbox | Clean up & remove all HPS rubbish from rooms (Straight to bins)
text | 02cd3fbf-3ef5-55d8-969c-1045679db160 |  | textbox | Room Completed & Inspected by
holdpoint |  |  | signoff | Hindmarsh Sign-Off - click to Add signature(s)