## QA Folder Structure
QA Folder Structure | [6 empty] | Checklists
Site QA
Core Walls
Level 05-06
|  |  | Electrical Services |  |  |  | ITP-001 - Conduit Installation (V.100321)
Level 06-07
|  |  | Electrical Services |  |  |  | ITP-001 - Conduit Installation (V.100321)
Level 07-08
|  |  | Electrical Services |  |  |  | ITP-001 - Conduit Installation (V.100321)
**Same up to level 28
eg next - Level 08-09
eg last - Level 27-28
Slabs & Columns
Level 4
East
|  |  |  | Electrical Services |  |  | ITP-001 - Conduit Installation (V.100321)
South
Columns
C9
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C10
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C11
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C12
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C13
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C14
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
Slab
[5 empty] | Electrical Services |  | ITP-001 - Conduit Installation (V.100321)
West
Columns
C7
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C8
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
Slab
[5 empty] | Electrical Services |  | ITP-001 - Conduit Installation (V.100321)
North
Columns
C1
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C2
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C3
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C4
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C5
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C6
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
Slab
[5 empty] | Electrical Services |  | ITP-001 - Conduit Installation (V.100321)
Level 5
East
[5 empty] | Electrical Services |  | ITP-001 - Conduit Installation (V.100321)
South
Columns
C9
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C10
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C11
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C12
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C13
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C14
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
Slab
[5 empty] | Electrical Services |  | ITP-001 - Conduit Installation (V.100321)
West
Columns
C7
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C8
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
Slab
[5 empty] | Electrical Services |  | ITP-001 - Conduit Installation (V.100321)
North
Columns
C1
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C2
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C3
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C4
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C5
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
C6
[6 empty] | Electrical Services | ITP-001 - Conduit Installation (V.100321)
Slab
[5 empty] | Electrical Services |  | ITP-001 - Conduit Installation (V.100321)
**Same up to level 28
Eg next - Level 6
Eg last - Level 28
Stair ST01 & ST02
Level 3-4
|  |  | Electrical Services |  |  |  | ITP-001 - Conduit Installation (V.100321)
Level 4-5
|  |  | Electrical Services |  |  |  | ITP-001 - Conduit Installation (V.100321)
Level 5-6
|  |  | Electrical Services |  |  |  | ITP-001 - Conduit Installation (V.100321)
**Same up to level 28
eg next - Level 6-7
eg last - Level 27-28

## Checklists ITPs
type | name | values | prefix | postfix
checklist | ITP-001 - Conduit Installation (V.100321)
section | Details
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
label | All inspections are to be completed in accordance with the specification and AS/NZS3000:2018
select | Conduit Run type | In Slab Conduit,In Wall Conduit,Underground
text | Conduit route, size & quantity
section | Installation
checkpoint | Check existing services, correct location & permit approval
checkpoint | Correct Depth/Cover
checkpoint | Tied and joins glued
checkpoint | Ends sealed
checkpoint | Area clean and safe
checkpoint | Drawings marked up with changes
checkpoint | Ready for wall sheeting, wall closure or column sleeve
section | Installation Verification
checkpoint | Installation completed to specifications
label | Any issues comment/photo below
text | Name of Installer
text | Date Installed
checklist | ITP-002 - Cable Tray Installation (V.100321)
section | Identification
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
label | All inspections are to be completed in accordance with the specification and AS/NZS3000:2018
checkpoint | Cable Tray Installation
text | Switchboard No
text | Cable Tray Description
text | Tray Location
select | Tray Size | 150mm,300mm,450mm,600mm,900mm
select | No of Tiers | 0,1,2,3,4,5,6,7,8,9,10
button | Fire Rated Tray | Yes,No,N/A
select | Service Tray Supporting | Electrical,Communication,Security,Other,N/A
section | Post Install Checks
checkpoint | Supports installed & correct spacing
text | Clash Detection Completed
button | Trays earthed - Where applicable | Yes,No,N/A
button | Seismic bracing required | Yes,No,N/A
button | Seismic bracing installed & Certified | Yes,No,N/A
button | Cross bracing installed where required | Yes,No,N/A
checkpoint | Trays ready for cable installation
checkpoint | Cables installed
checkpoint | Service penetrations fire or smoke sealed where required
section | Installation Verification
checkpoint | Installation completed to specifications
label | Any issues comment/photo below
text | Name of Installer
text | Date Installed
checklist | ITP-003 - Sub-Mains Installation & Commissioning (V.031121)
section | Circuit Information
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
label | All inspections are to be completed in accordance with the specification and AS/NZS3000:2018
checkpoint | Cable details - Pass once entered
text | Cable No.
select | Protection Device Type | HRC Fuse,MCB,ACB,N/A,Other (Specify Below
text | If other selected above, please specify
select | Protective device rating | 6 amps,10 amps,16 amps,20 amps,25 amps,32 amps,40 amps,50 amps,63 amps,80 amps,100 amps,125 amps,150 amps,160 amps,200 amps,250 amps,315 amps,400 amps,500 amps,630 amps,800 amps,1000 amps,1600 amps,2000 amps,2500 amps,3000 amps,3200 amps
text | Cable Origin
text | Cable Destination
select | No. of conductors per phase | N/A,1,2,3,4,5,6,7,8,9,10
button | Multicore or SDI (Select One) | Multicore,SDI
button | PVC, XLPE, Fire Rated (Select One) | PVC,XLPE,Fire Rated
button | Copper (CU) or Aluminium (AL) | CU,AL
select | Size of active conductors | 1mm,1.5mm,2.5mm,4mm,6mm,10mm,16mm,25mm,35mm,50mm,70mm,95mm,120mm,150mm,185mm,240mm,300mm,400mm,500mm,630mm,Busduct
select | Earth size | 1mm,1.5mm,2.5mm,4mm,6mm,10mm,16mm,25mm,35mm,50mm,70mm,95mm,120mm,150mm,185mm,240mm,300mm,400mm,500mm,630mm
section | Installation Pre-Commissioning checks
checkpoint | Rough-In Complete
label | Attach photos below as applicable
checkpoint | Fit-Off Complete
label | Attach photos below as applicable
checkpoint | Connections Tight
checkpoint | Glands Tight
checkpoint | Cable is Labelled
section | Commissioning Results
checkpoint | Phase rotation correct
button | Earth Resistance test result in ohms | <0.5mΩ,>1mΩ,Fail
label | < 0.5mΩ Clause 8.3.5
checkpoint | Insulation Resistance test result
label | > 1mΩ Clause 8.3.6
button | L1 - L2 | <0.5mΩ,>1mΩ,Fail
button | L2 - L3 | <0.5mΩ,>1mΩ,Fail
button | L3 - L1 | <0.5mΩ,>1mΩ,Fail
button | N - L1, L2, L3 | <0.5mΩ,>1mΩ,Fail
button | E - L1, L2, L3 | <0.5mΩ,>1mΩ,Fail
button | E - N | <0.5mΩ,>1mΩ,Fail
checkpoint | Polarity & Circuit connections
label | Clause 8.3.7 & 8.3.8
button | L1 | Yes,No,N/A
button | L2 | Yes,No,N/A
button | L3 | Yes,No,N/A
button | N | Yes,No,N/A
button | E | Yes,No,N/A
section | Verification
checkpoint | Installation completed to specifications
label | Any issues comment/photo below
text | Electrician Name
text | License No.
text | Date Installed
checklist-flat | Details - ITP (V.030921)
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
label | All inspections are to be completed in accordance with the specification and AS/NZS3000:2018
button | Confirm area of work is accessible & acceptable to commence (If not comment below) | Yes,No
checklist-flat | Single Circuit - ITP-004 - Sub circuit Installation & Commissioning ITP (V.031121)
checkpoint | Circuit details - Pass once entered
text | Circuit Description (Input if known, if not leave till Commissioning)
select | CB / RCD No. | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,64,65,66,67,68,69,70,71,72,73,74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,126,127,128,129,130
select | CB / RCD / Fuse Size in amps | 6 amps, 10 amps, 16 amps, 20 amps, 25 amps, 32 amps, 40 amps, 50 amps, 63 amps, 80 amps, 100 amps, 125 amps, 150 amps, 160 amps, 200 amps, 250 amps, 315 amps, 400 amps, 500 amps, 630 amps, 800 amps, 1000 amps, 1600 amps, 2000 amps, 2500 amps, 3000 amps, 3200 amps
select | Protective Device type | RCD,RCBO,CB,FUSE
select | RCD Rating | 10mA,30mA,100mA
select | Size of active conductors | 1mm Twin,1.5mm Twin,2.5mm Twin,4mm Twin,6mm Twin,1mm Twin & E,1.5mm Twin & E,2.5mm Twin & E,4mm Twin & E,6mm Twin & E,10mm Twin & E,16mm Twin & E,25mm Twin & E,16mm Twin,25mm Twin,1.5mm 4Core & E,2,5mm 4Core & E,4mm 4Core & E,6mm 4Core & E,10mm 4Core & E,16mm 4Core & E,25mm 4Core & E,35mm 4Core & E,50mm 4Core & E,70mm 4Core & E,95mm 4Core & E,1.5mm SDI,2.5mm SDI,4mm SDI
select | Earth size | 1mm, 1.5mm, 2.5mm, 4mm, 6mm, 10mm, 16mm, 25mm, 35mm, 50mm, 70mm, 95mm, 120mm, 150mm, 185mm, 240mm, 300mm, 400mm, 500mm, 630mm
text | Circuit Notes
select | No. of Points | N/A,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40
checkpoint | Rough-In Complete (Feeds)
label | Attach photos below as applicable
checkpoint | Second Rough in (Loops)
label | Attach photos below as applicable
checkpoint | Fit-Off Complete
label | Attach photos below as applicable
checkpoint | Commissioning Results - Pass once entered
select | Earth Resistance test result in ohms | 0.00Ω,0.01Ω,0.02Ω,0.03Ω,0.04Ω,0.05Ω,0.06Ω,0.07Ω,0.08Ω,0.09Ω,0.10Ω,0.11Ω,0.12Ω,0.13Ω,0.14Ω,0.15Ω,0.16Ω,0.17Ω,0.18Ω 0.19Ω,0.20Ω,0.21Ω,0.22Ω,0.23Ω,0.24Ω,0.25Ω,0.26Ω,0.27Ω,0.28Ω,0.29Ω,0.30Ω,0.31Ω,0.32Ω,0.33Ω,0.34Ω,0.35Ω,0.36Ω,0.37Ω,0.38Ω,0.39Ω,0.40Ω,0.41Ω,0.42Ω,0.43Ω,0.44Ω,0.45Ω,0.46Ω,0.47Ω,0.48Ω 0.49Ω,0.50Ω,Fail
label | < 0.5mΩ Clause 8.3.5
button | L-L Insulation Resistance test result | >1mΩ,Fail
label | > 1mΩ Clause 8.3.6
button | L-E Insulation Resistance test result | >1mΩ,Fail
label | > 1mΩ Clause 8.3.6
checkpoint | Polarity & Circuit connections
label | Clause 8.3.7 & 8.3.8
button | L1 (Red) | Yes,No
button | L2 (White) | Yes,No
button | L3 (Blue) | Yes,No
button | N | Yes,No
button | E | Yes,No
checkpoint | Fault Loop Impedance - Clause 8.3.9 (Not required if RCD protected)
text | Earth Resistance Re Ω
text | Earth Resistance Rpe Ω
checkpoint | RCD Acceptance (30mA times checked and correct)
label | X0.5 Trip Time
text | 0.Deg (ms)
text | 180.Deg (ms)
label | .. ..
label | X1 Trip Time
text | 0.Deg (ms)
text | 180.Deg (ms)
label | .. ..
label | X2 Trip Time
text | 0.Deg (ms)
text | 180.Deg (ms)
label | .. ..
label | X5 Trip Time
text | 0.Deg (ms)
text | 180.Deg (ms)
label | .. ..
label | ImA
text | 0.Deg (ms)
text | 180.Deg (ms)
checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | Action taken
checkpoint | Trip test button
checkpoint | Installation & Commissioning completed to specifications
label | Any issues comment/photo below
text | Electrician Name
text | License No.
checklist | ITP-005 - Switchboards Installation & Commissioning (V.031121)
section | Identification
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
label | All inspections are to be completed in accordance with the specification and AS/NZS3000:2018
checkpoint | Switchboard Type - Pass once entered
select | Type | Main Switchboard,Distribution Board,Controls Panel,Meter Panel,Other (Specify Below)
text | If other selected above, please specify
text | Switchboard Name
text | Isolation Device
text | Board Location
button | Generator Back-up Verified | Yes,No,N/A
text | MEN Location
select | Earth size | 1mm,1.5mm,2.5mm,4mm,6mm,10mm,16mm,25mm,35mm,50mm,70mm,95mm,120mm,150mm,185mm,240mm,300mm,400mm,500mm,630mm
checkpoint | Cable details - Pass once entered
text | Cable No.
select | Protection Device Type | HRC Fuse,MCB,ACB,N/A,Other (Specify Below
text | If other selected above, please specify
select | Protective device rating | 6 amps,10 amps,16 amps,20 amps,25 amps,32 amps,40 amps,50 amps,63 amps,80 amps,100 amps,125 amps,150 amps,160 amps,200 amps,250 amps,315 amps,400 amps,500 amps,630 amps,800 amps,1000 amps,1600 amps,2000 amps,2500 amps,3000 amps,3200 amps
text | Cable Origin
text | Cable Destination
select | No. of conductors per phase | N/A,1,2,3,4,5,6,7,8,9,10
button | Multicore or SDI (Select One) | Multicore,SDI
button | PVC, XLPE, Fire Rated (Select One) | PVC,XLPE,Fire Rated
button | Copper (CU) or Aluminium (AL) | CU,AL
select | Size of active conductors | 1mm,1.5mm,2.5mm,4mm,6mm,10mm,16mm,25mm,35mm,50mm,70mm,95mm,120mm,150mm,185mm,240mm,300mm,400mm,500mm,630mm,Busduct
select | Earth size | 1mm,1.5mm,2.5mm,4mm,6mm,10mm,16mm,25mm,35mm,50mm,70mm,95mm,120mm,150mm,185mm,240mm,300mm,400mm,500mm,630mm
section | Completed items checks
checkpoint | Switchboard fixed into place
label | Attach photos below as applicable
checkpoint | Supply cable terminated & checked
checkpoint | Supply Earth cables terminated & checked
checkpoint | All Labels Installed
button | Switchboard Vacuumed and cleaned | Yes,No,N/A
button | Circuit schedules in place | Yes,No,N/A
checkpoint | BMS Interfaces connected
checkpoint | Controls cables connected
checkpoint | Insulation Resistance checks completed. Refer ITPs
label | Attach evidence below as applicable
checkpoint | Earth Continuaity Tests completed. Refer ITPs
label | Attach evidence below as applicable
checkpoint | Polarity and connection checks. Refer ITPs
label | Attach evidence below as applicable
section | Verification
checkpoint | Ready for Energisation
checkpoint | Post Energisation checks completed
label | Attach photos/comments below as applicable
checkpoint | Surge Divertors on after energisation
checkpoint | Installation & Commissioning completed to specifications
label | Any issues comment/photo below
text | Name of Person Completing checks
text | License No.
text | Energisation Date
checklist | ITP-006 - Communications Cabling Installation Installation (V.100321)
section | Details
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
label | All inspections are to be completed in accordance with the specification and AS/NZS3000:2018
checkpoint | Cabling Details - Pass once entered
text | Cable No.
text | Description of cable installation, Destination and origin etc
select | Cable Type, Copper / Fibre, TV | MMOF,SMOF,CAT 6 UTP,CAT 6A UTP,RG6 QS,RG10 QS,CAT 3
select | No. of cables | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24
select | No. of Cores or pairs | 2 Core,4 Core,6 Core,12 Core,24 Core,36 Core,1 Pair,2 Pair,4 Pair,10 Pair,15 Pair,20 Pair,25 Pair,50 Pair,100 Pair,N/A
section | Installation checks
checkpoint | Details of checks - Pass once read & below completed
label | Select - "Y" Completed. "X" not done. "N/A" Not applicable
label | Attach photos/comments below as applicable
button | Bend Radius | Yes,No,N/A
button | Segregation & separation | Yes,No,N/A
button | Correct fixings & supports | Yes,No,N/A
button | Cables labelled at both ends | Yes,No,N/A
button | Correct cable grouping | Yes,No,N/A
button | Comms Racks correctly installed & size | Yes,No,N/A
button | Patch panels or frame labelled | Yes,No,N/A
checkpoint | Test equipment calibrated
checkpoint | Tested to correct standard & passed
checkpoint | Mark Up drawings completed - Attached as applicable
bool | Area clean & safe
section | Verification
checkpoint | Installation completed to specifications
label | Any issues comment/photo below
text | Length
text | Installers Name
text | Date
checklist | ITP-007 - Lighting Control Installation and Commisioning (V.171121)
section | Identification
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
label | All inspections are to be completed in accordance with the specification and AS/NZS3000:2018
text | DALI No / Relay No
text | Circuit Attched
text | Rough-In feed start location
text | Loops/Backbone
text | Finish Location
select | Control Type | Dali,DMX,DSI,Relay,Other (Specify Below)
text | Other (Specify Here)
select | Type of Cable Installed | Twin 1.5,Twin 2.5,CAT5e,CAT6a,Dyna Liite,CBUS,Two Pair Shielded,Other (Specify below)
text | Other (Specify Here)
select | No. of ights per Universe | 0,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65
section | Pre-Commissioning checks
checkpoint | Commissioning checks - Pass once below are completed
label | Attach photos/comments below as applicable
select | CB No. | 0,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60
select | No. of Light Fittings | 0,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60
select | Controller ID number type | 0,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60
button | Is scheduling applicable | Yes,No,N/A
button | DALI, DSI, DMX addressing completed | Yes,No,N/A
button | LCP / Touch Screen programmed | Yes,No,N/A
button | Motion Sensor in place and programmed | Yes,No,N/A
section | Commissioning checks
checkpoint | Switching function as per Functional Description
checkpoint | Dimming function as per Functional Description
checkpoint | Schedule function as per Functional Description
checkpoint | Head end in place and programmed
section | Verification
checkpoint | Installation completed to specifications
label | Any issues comment/photo below
text | ION Electrician Completing Checks
text | System Programmer Company and name
text | Date
checklist | ITP-007A-Lighting Control (Dali) rough-in (V.171121)
checkpoint | Details - Pass once entered
text | DALI No / Relay No
text | Circuit Attched
text | Rough-In feed start location
text | Loops/Backbone
text | Finish Location
select | Control Type | Dali,DMX,DSI,Relay,Other (Specify Below)
text | Other (Specify Here)
select | Type of Cable Installed | Twin 1.5,Twin 2.5,CAT5e,CAT6a,Dyna Liite,CBUS,Two Pair Shielded,Other (Specify below)
text | Other (Specify Here)
select | No. of ights per Universe | 0,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65
checklist | ITP-008 - Emergency Lighting Installation & Test Sheet (V.100321)
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | Drawing & revision number(s) - If applicable
checkpoint | Test Details - Pass once entered
text | Fitting No.
text | Location of Fitting
text | Type of Unit
text | DB Number
text | CCT No.
text | Start Time
text | Finish Time
checkpoint | 6 monthly test Mains Operation
label | Photos/Comments added below as apllicable
text | Test Date
checkpoint | 6 monthly test Emergency Operation
label | Photos/Comments added below as apllicable
text | Test Date
checkpoint | Testing completed to specifications
label | Any issues comment/photo below
text | Name of Person Completing checks
text | License No.
checklist | ITP-009 - Energy Meter Validation Schedule (V.100321)
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | Drawing & revision number(s) - If applicable
checkpoint | Details - Pass once entered
text | Meter Number
text | Energy Meter Reference & Detail
text | Meter Type
text | Model Number
text | Protocol
text | Power Rating
checkpoint | Validation Checks - Pass once entered
label | Photos/Comments added below as apllicable
select | CT Ratio | 50:5,60:5,80:5,100:5,200:5,250:5,300:5,400:5,500:5,600:5,800:5,1000:5,1200:5,1600:5,2000:5,2500:5,3000:5
button | CT Ratio checked & confirmed | Yes,No
button | CT's checked and installed correctly | Yes,No
button | Wiring checked and confirmed correct | Yes,No
button | Energised | Yes,No
button | Meter parameters checked and adjusted | Yes,No
button | Volts checked reading meter to check meter | Yes,No
button | Amps reading red phase energy meter | Yes,No
button | Amps reading red phase check meter | Yes,No
text | Meter Serial Number
checkpoint | Validation completed to specifications
label | Any issues comment/photo below
text | Name of Person Completing checks
text | License No.
text | Date