## IPL - Breakdown
IPL - Henderson
QA
B09
Subfloor
|  |  |  | Unit 27 | pre-populate | Sub Floor QA
|  |  |  | Unit 29 | pre-populate | Sub Floor QA
|  |  |  | Unit 31 | pre-populate | Sub Floor QA
|  |  |  | Unit 33 | pre-populate | Sub Floor QA
|  |  |  | Unit 35 | pre-populate | Sub Floor QA
First Fix
|  |  |  | Unit 27 | pre-populate | First Fix
|  |  |  | Unit 29 | pre-populate | First Fix
|  |  |  | Unit 31 | pre-populate | First Fix
|  |  |  | Unit 33 | pre-populate | First Fix
|  |  |  | Unit 35 | pre-populate | First Fix
Second Fix
|  |  |  | Unit 27 | pre-populate | Second Fix
|  |  |  | Unit 29 | pre-populate | Second Fix
|  |  |  | Unit 31 | pre-populate | Second Fix
|  |  |  | Unit 33 | pre-populate | Second Fix
|  |  |  | Unit 35 | pre-populate | Second Fix
|  |  | Completion documents |  | pre-populate | Completion documents

## Checklists
Checklist | Sub Floor QA
checkpoint | Correct gradiant of the pipework achieved
checkpoint | Pipe wrapped/protected and acceptable
checkpoint | Flood test completed and acceptable
checkpoint | Pipe capped and acceptable
checkpoint | All undefloor plumbing works installed as per specifications
checklist | First Fix
checkpoint | Hot water supply lines run the shortest
checkpoint | Specified Waste pipework is Acoustic lagged and acceptable
checkpoint | Penetrations through fire cells are fire protected
checkpoint | All joist Brackets or Reinforcement installed, if required
checkpoint | Nog's and fixings are installed for water closet, shower, hot water cylinder and etc.
checkpoint | Penetrations through building paper are trade sealed
checkpoint | Hot Water Ring main is thermally lagged
checkpoint | All Pipework clipped neatly and tidy
checkpoint | All pipework secured/ siliconed
checkpoint | Floor Waste Gully Flange is recessed into flooring and installed
checkpoint | Water tested to 1500kpa and loop not effect lining
checkpoint | Checked for drips on water and waste piping
checkpoint | Soil and waste piping hydrostatic test ( Flood test )
checkpoint | Test plug & Gauge removed from pipe system
checkpoint | Fire penetration Schedule is completed
checkpoint | Flange and all through installed pipework flood tested
checkpoint | Plumbing First Fix complete and acceptable and area clean and tidy for next trade
checklist | Second Fix
section | Preinstall QA
checkpoint | Permission to begin work obtained
checkpoint | Drawings correct issue and construction set
Checkpoint | Area is left clean and tidy and work can begin
section | Second fix QA
Checkpoint | Fit-off materials match schedule or drawings
Checkpoint | Setouts/min clearances as per specification
Checkpoint | Water pipework maintained test throughout
Checkpoint | No debris in floor wastes or subs
Checkpoint | Hot water cylinder tempered to required outlet temp
Checkpoint | Flanges installed on all pipework to vermin proof
Checkpoint | All soil pipes are connected to sanitary sewer
Checkpoint | No crossovers, hot on left and cold on right
Checkpoint | All fixtures are siliconed down and splash sealed
Checkpoint | Shower hoses are fitted with non returns
Checkpoint | Area is left clean and tidy
Checkpoint | Work is 100% competed to required specifications
holdpoint | Raise remedial/Request signoff
checklist | Completion documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | LBP Memorandum/ Record of works filled out, signed and attached
button | Any Additional Compliance Documentation - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff