## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | B04 - First Fix |  |  |  |  | Yes | B04 - First Fix | 0a84ea08-bc6c-4126-af40-be42e154253a
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous Substrate Acceptable
checkpoint-group |  |  | section | First Fix QA
checkpoint-status |  |  | checkpoint | Hot water supply lines run the shortest
checkpoint-status |  |  | checkpoint | Specified Waste pipework is Acoustic Lagged
checkpoint-status |  |  | checkpoint | Penetrations through fire cells are fire protected
checkpoint-status |  |  | checkpoint | All joist Brackets or Reinforcement installed if required
checkpoint-status |  |  | checkpoint | Nog's and fixings are installed for WC, WHB, SHW, HWC?
checkpoint-status |  |  | checkpoint | Penetrations through building paper are trade sealed
checkpoint-status |  |  | checkpoint | Hot Water Ring main is thermally lagged
checkpoint-status |  |  | checkpoint | All Pipework clipped neatly and tidy
checkpoint-status |  |  | checkpoint | All pipework secured/ siliconed
checkpoint-status |  |  | checkpoint | FWG Flange is recessed into flooring and installed
checkpoint-status |  |  | checkpoint | Water tested to 1500kpa and loop not effect lining
checkpoint-status |  |  | checkpoint | Checked for drips on water and waste piping
checkpoint-status |  |  | checkpoint | Picked up all left over material and removed from site
checkpoint-status |  |  | checkpoint | Soil and waste piping hydrostatic test ( Flood test )
checkpoint-status |  |  | checkpoint | Test plug & Gauge removed from pipe system
checkpoint-status |  |  | checkpoint | Fire penetration Schedule is completed
checkpoint-status |  |  | checkpoint | Flange and all through installed pipe work flood tested (photo required)
checkpoint-group |  |  | section | First Fix Handover
checkpoint-status |  |  | checkpoint | Area left clean & tidy (Attach Photo)
checkpoint-status |  |  | checkpoint | All work 100% complete to required specifications
checklist-sectioned |  |  | checklist | Toolbox Checklist |  |  |  |  | Yes | H&S Toolbox Talks | 110a8558-8579-4b0b-99cf-120bf00f54e1
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 305f2185-4e3a-4417-ae95-885bb0b1de8a |  | textbox | Office location:
text | b2fd07dc-8f92-4010-8a71-46e71c03ff63 |  | textbox | Who is running this meeting:
text | 1d3d0b15-a56a-498c-b16b-2afa5f8e2573 |  | textbox | Company
text | 88e78785-0eea-4ad8-a896-1622379eacfc |  | textbox | Agenda items:
text | ce0224f5-54b8-47a5-b890-7a5416c69623 |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | 1.
text | 2ec0fc9e-b14f-43a5-bb60-4df5d5ab3ab4 |  | textbox | Issues raised from site safety inspection:
text | 1b5fcc97-f30c-4727-a783-29c22206fa41 |  | textbox | Actions:
text | b5107b7c-d991-4507-a1a9-6180db10057c |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 2.
text | 8978adff-e266-4646-b125-178fba33a0dd |  | textbox | Issues outstanding from previous briefings:
text | 507afe6b-4ee7-4485-bd4b-99698d8e8f47 |  | textbox | Actions:
text | 7d92f59d-ce24-4ec9-8428-a92c87f559e3 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3.
text | 305b3039-3f3d-45b4-8536-fb028ee2010b |  | textbox | Employee-raised issues:
text | c98f50a5-1fb4-45b7-86e0-301132ec8b7c |  | textbox | Actions:
text | c250b53e-5070-459c-b01f-af8fcce5cdb7 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4.
text | 26f6b1aa-3048-4106-a64b-dc4e2cf75ec3 |  | textbox | Positive safe-action observations:
text | dd2ab926-5b94-46f6-a93f-eed5fa00233e |  | textbox | Actions:
text | 464cc30b-c155-4299-b08c-242a1821bd72 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5.
text | ba0166ff-1cef-49fe-a54e-fce60528feea |  | textbox | Incidents or injuries:
text | 8f9035d5-30e5-4ea2-9ec4-4d19df05b3fd |  | textbox | Actions:
text | 1a84fee3-7466-42bd-a3ff-39c2785201a3 |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task & Action/Outcome
text | cb9c1ca7-7b79-4c62-8f74-3a1d70af5886 |  | textbox | 1.
text | d396585a-1ce3-4d1e-b838-375ab4165dd0 |  | textbox | 2.
text | 4657beed-8141-41c2-926d-0d7204a497a2 |  | textbox | 3.
text | 1e162112-08ad-40c3-9d33-6c4bac52a906 |  | textbox | 4.
text | fd629f21-4050-47b3-b236-26daf8c94903 |  | textbox | 5.
text | a08ea05c-aa58-425b-9cb6-e2fa8951a414 |  | textbox | 6.
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Issue & Action
text | 301f9ad4-6682-45c0-aa57-7b074b0e8a13 |  | textbox | 1.
text | 1373bee6-816f-408a-97a0-72f99b461b6e |  | textbox | 2.
text | c487e999-fa82-493c-b540-e056d94778fb |  | textbox | 3.
text | 5341a99d-52f8-4c86-8e11-6e8adfb0627e |  | textbox | 4.
text | 8e55092c-df52-43d0-b019-a8e67550ae09 |  | textbox | 5.
text | b87136a8-71c4-41f7-9cdb-74d4b55b5521 |  | textbox | 6.
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Item & Action
text | 2e63def1-4462-4998-b972-d5125960181e |  | textbox | 1.
text | 044404a1-6065-4d33-8f96-7da9ab2eaf3a |  | textbox | 2.
text | 1e321545-4537-44dd-9443-3ae2c58d572b |  | textbox | 3.
text | e3214f18-5e4b-42bf-856b-435adffda167 |  | textbox | 4.
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Reviewed and signed off
text | 054479d9-523d-4c50-88ce-626d6600059d |  | textbox | 1.
text | e1ea14ce-04e9-4c55-b0e6-131f75ee169d |  | textbox | 2.
checklist-flat |  |  | checklist | Aquatherm |  |  |  |  | Yes | Aquatherm | 14888fc2-e905-4857-9d3a-14ba7342dd23
checkpoint-status |  |  | checkpoint | Aquatherm Check Completed
text | 00330187-83b4-5d69-b644-ba5e103f532e |  | textbox | Installers Name/Number
text | f5f64350-9c7f-5f49-937d-185b2a9dab65 |  | textbox | Other:
text | 35a05a5e-ab90-5b1a-b796-1d5698aed765 |  | textbox | Type of Pipe
text | aaff45f8-a99a-5d8a-824f-a794458fbcb1 |  | textbox | Time test started:
text | fb8684a9-543b-5a53-a1c9-26af49baeaba |  | textbox | Time test finished:
text | 1df04ac1-6780-5ba8-99cb-f8a659e8307b |  | textbox | Test period
checkpoint-status |  |  | checkpoint | I declare that I have installed the above product in accordance with aquatherm specifications with no branding mix
checklist-sectioned |  |  | checklist | First Fix |  |  |  |  | Yes | Add First Fix Checks | 1f4c3650-a094-4133-a560-85f8a33eb0e8
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous Substrate Acceptable
checkpoint-group |  |  | section | First Fix QA
checkpoint-status |  |  | checkpoint | Hot water supply lines run the shortest
checkpoint-status |  |  | checkpoint | Specified Waste pipework is Acoustic Lagged
checkpoint-status |  |  | checkpoint | Penetrations through fire cells are fire protected
checkpoint-status |  |  | checkpoint | All joist Brackets or Reinforcement installed if required
checkpoint-status |  |  | checkpoint | Nog's and fixings are installed for WC, WHB, SHW, HWC?
checkpoint-status |  |  | checkpoint | Penetrations through building paper are trade sealed
checkpoint-status |  |  | checkpoint | Hot Water Ring main is thermally lagged
checkpoint-status |  |  | checkpoint | All Pipework clipped neatly and tidy
checkpoint-status |  |  | checkpoint | All pipework secured/ siliconed
checkpoint-status |  |  | checkpoint | FWG Flange is recessed into flooring and installed
checkpoint-status |  |  | checkpoint | Water tested to 1500kpa and loop not effect lining
checkpoint-status |  |  | checkpoint | Checked for drips on water and waste piping
checkpoint-status |  |  | checkpoint | Picked up all left over material and removed from site
checkpoint-status |  |  | checkpoint | Soil and waste piping hydrostatic test ( Flood test )
checkpoint-status |  |  | checkpoint | Test plug & Gauge removed from pipe system
checkpoint-status |  |  | checkpoint | Fire penetration Schedule is completed
checkpoint-status |  |  | checkpoint | Flange and all through installed pipework flood tested (photo required)
checkpoint-group |  |  | section | First Fix Handover
checkpoint-status |  |  | checkpoint | Area left clean & tidy (Attach Photo)
checkpoint-status |  |  | checkpoint | All work 100% complete to required specifications
checklist-flat |  |  | checklist | Handover checklist |  |  |  |  | Yes | Handover Checklist | 336fc5a9-98b3-4ad3-bbc8-2540bccc383f
checkpoint-status |  |  | checkpoint | PS3s, warranties, user manuals and any other documents attached
checklist-sectioned |  |  | checklist | B04 - Sub Floor QA |  |  |  |  | Yes | B04 - Sub Floor QA | 4829688a-f08b-4516-bf1b-b95ec105a3a4
checkpoint-group |  |  | section | Preinstall Checks
checkpoint-status |  |  | checkpoint | Substrate aceptable
checkpoint-status |  |  | checkpoint | Areas Accessible
checkpoint-group |  |  | section | Subfloor Checks
checkpoint-status |  |  | checkpoint | As per plan
checkpoint-status |  |  | checkpoint | As per code
checkpoint-status |  |  | checkpoint | Correct fall
checkpoint-status |  |  | checkpoint | Sleeves or rap through concrete
checkpoint-status |  |  | checkpoint | Correct bedding
checkpoint-status |  |  | checkpoint | Correct product
checkpoint-status |  |  | checkpoint | Pressure test
checkpoint-group |  |  | section | Handover Checks
checkpoint-status |  |  | checkpoint | Variation plan approved
checkpoint-status |  |  | checkpoint | Site instructions
checkpoint-status |  |  | checkpoint | Site photos
checkpoint-status |  |  | checkpoint | Sign off checked and approved
checkpoint-status |  |  | checkpoint | As built plan recorded
checkpoint-status |  |  | checkpoint | Producer statement complete
checklist-flat |  |  | checklist | FIRE PENETRATION (WRAPS / COLLARS / CAST-in COLLARS) |  |  |  |  | Yes | Add Penetrations | 63f1629b-30e6-4c84-85a2-64001ff06762
checkpoint-status |  |  | checkpoint | Wraps/ Collars/ Cast in installed
checkpoint-status |  |  | checkpoint | Is the penetration seal approved for the wall / floor type
checkpoint-status |  |  | checkpoint | Is the penetration seal approved for the penetration & its application
checkpoint-status |  |  | checkpoint | Are pipes supported as specified by the manufacturer
checkpoint-status |  |  | checkpoint | Sealed is installed as per specification
checkpoint-status |  |  | checkpoint | Penetration Label includes
checklist-sectioned |  |  | checklist | B04 - Second Fix |  |  |  |  | Yes | B04 - Second Fix | 6c6b8a59-0aab-4aea-a81d-0a8681b9863d
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous Substrate Acceptable
checkpoint-group |  |  | section | Second Fix QA
checkpoint-status |  |  | checkpoint | Fit-off Materials match schedule on plans
checkpoint-status |  |  | checkpoint | Setouts/min clearances as per plan
checkpoint-status |  |  | checkpoint | Water pipework maintained test throughout
checkpoint-status |  |  | checkpoint | No debris in floor wastes or stubs
checkpoint-status |  |  | checkpoint | HWC Tempered to required outlet temp
checkpoint-status |  |  | checkpoint | HWC Seismically strapped & braced
checkpoint-status |  |  | checkpoint | Flanges installed on all pipework to vermin proof
checkpoint-status |  |  | checkpoint | All soil pipes are connected to sanitary sewer
checkpoint-status |  |  | checkpoint | No crossovers, Hot on left and Cold on Right
checkpoint-status |  |  | checkpoint | All fixtures are silicon-ed down and splash sealed
checkpoint-status |  |  | checkpoint | Shower Hoses are fitted with non returns
checkpoint-status |  |  | checkpoint | Clamping rings and grates installed (photo required)
checkpoint-group |  |  | section | Second Fix Handover
checkpoint-status |  |  | checkpoint | Area left clean & tidy (Attach Photo)
checkpoint-status |  |  | checkpoint | All work 100% complete to required specifications
checklist-flat |  |  | checklist | Sub Floor QA |  |  |  |  | Yes | Sub Floor QA | 7384a786-efaa-4727-b446-107f1f1b25f9
checkpoint-status |  |  | checkpoint | Correct gradient of the pipework achieved
checkpoint-status |  |  | checkpoint | Pipe wrapped/protected and acceptable
checkpoint-status |  |  | checkpoint | Flood test completed and acceptable
checkpoint-status |  |  | checkpoint | Pipe capped and acceptable
checkpoint-status |  |  | checkpoint | All underfloor plumbing works installed as per specifications
checklist-flat |  |  | checklist | Aquatherm |  |  |  |  | Yes | Add Aquatherm Checks | 7d791072-f64a-470c-834d-5e56848336cc
checkpoint-status |  |  | checkpoint | Aquatherm Check Completed
text | df1f4215-ad3d-400d-9bd9-3f370d9a0a05 |  | textbox | Installers Name/Number
text | 96e29ad0-8109-4c1e-8bc4-120c291eec92 |  | textbox | Other:
text | 93808b05-e4b1-4541-9aca-5f7c5ddae60b |  | textbox | Type of Pipe
text | 3adca44e-039b-43ed-a28f-db288ed69355 |  | textbox | Time test started:
text | c8a2bef9-1639-4b7c-9905-0d39eff7b317 |  | textbox | Time test finished:
text | 110fb267-85ed-4f67-8a37-67009d6695bd |  | textbox | Test period
checkpoint-status |  |  | checkpoint | I declare that I have installed the above product in accordance with aquatherm specifications with no branding mix
checklist-sectioned |  |  | checklist | Sub-Floor QA |  |  |  |  | Yes | Add Sub-Floor checks | 8151276d-9d53-41e0-9e6c-a1ce91cddf06
checkpoint-group |  |  | section | Preinstall checks
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-group |  |  | section | Sub floor checks
checkpoint-status |  |  | checkpoint | As per plan
checkpoint-status |  |  | checkpoint | As per code
checkpoint-status |  |  | checkpoint | Correct fall
checkpoint-status |  |  | checkpoint | Sleeves or rap through concrete
checkpoint-status |  |  | checkpoint | Correct bedding
checkpoint-status |  |  | checkpoint | Correct Product
checkpoint-status |  |  | checkpoint | Pressure Test
checkpoint-group |  |  | section | Handover checks
checkpoint-status |  |  | checkpoint | Variation plan approved
checkpoint-status |  |  | checkpoint | Site instructions
checkpoint-status |  |  | checkpoint | Site photos
checkpoint-status |  |  | checkpoint | Sign off/ checked and approved by head contractor
checkpoint-status |  |  | checkpoint | As Build plan recorded
checkpoint-status |  |  | checkpoint | Producers statement complete
checklist-flat |  |  | checklist | B04 - Pre-Commencement Checklist |  |  |  |  | Yes | B04 - Pre-Commencement Checklist | 83591b5b-db07-4a96-8baf-88769ba080cd
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/Insight Setup (if required)
checklist-flat |  |  | checklist | Pre Commencement Checks |  |  |  |  | Yes | Pre Commencement Checks | 9279fd4d-9814-467c-bbff-e8d9e6730e26
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/Insights Setup (if required)
checkpoint-status |  |  | checkpoint | Subfloor Plumbing / Drainage to be tested prior to being backfilled and covered, pipework is to be filled to floor level for a minimum period of 30 minutes without loss in accordance with NZBC G13.7
checkpoint-status |  |  | checkpoint | First fix testing requirements prior to wall lining being installed. Test potable water within apartments, before linings are installed to 1,500kpa for a minimum period of 15 minutes, in accordance with Building Code NZBC G12.7.5.1a. Use appropriated pressure test equipment.
checkpoint-status |  |  | checkpoint | Test potable PP-R (green pipe) water supplies to a pressure of 2,000kpa in accordance with Building Code NZBC G12, and manufacturers recommendations. Use appropriated pressure test equipment
checkpoint-status |  |  | checkpoint | Soil waste and vent pipes are to be tested to flood level for a minimum period of 30 minutes without loss in accordance with NZBC G13.7
checkpoint-status |  |  | checkpoint | All testing is to be witnessed by local council authority
checkpoint-status |  |  | checkpoint | Hot water cylinders installed in accordance with NZBC G12 reatrained in accordance with figure 14 and thermostat set a minimum of not less than 60°C, Tempering valves to be set to 55°C maximum.
checkpoint-status |  |  | checkpoint | Sanitary fixtures to be installed in accordance with NZBC G13 and tested for leaks and loss of trap seal
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | 9f49cbb4-9472-4efb-8431-1b25375992f1
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | B04 - Completion documents |  |  |  |  | Yes | B04 - Completion documents | a6359c4d-e9e3-4676-a53b-adf6a6aa2154
checkpoint-status |  |  | checkpoint | O&M
checkpoint-status |  |  | checkpoint | Warranty
checkpoint-status |  |  | checkpoint | PS3 - Proprietary Product Installation
checkpoint-status |  |  | checkpoint | PS3 Plumbing
checkpoint-status |  |  | checkpoint | PS3 Wastewater Sump Pump
checkpoint-status |  |  | checkpoint | As-built: Underslab Plumbing
checkpoint-status |  |  | checkpoint | As-built: Blackflow
checklist-flat |  |  | checklist | B04 - Aquatherm |  |  |  |  | Yes | B04 - Aquatherm | e43dfbb6-07bc-4fb7-a3d7-e922fe185204
checkpoint-status |  |  | checkpoint | Aquatherm Check Completed
text | 0e694d87-22e2-57c3-9e4e-e40d5ffd78db |  | textbox | Installers Name/Number
text | 044d16d4-86da-5323-a388-513ad5f228c3 |  | textbox | Other:
text | 4d919921-8582-564e-b9fb-da80c80a1dc1 |  | textbox | Type of Pipe
text | ed8061d8-d1e1-5521-9e70-0843e68fa9ff |  | textbox | Time test started:
text | d486b600-07c5-5ea2-8cfa-c6a429385887 |  | textbox | Time test finished:
text | 98fd8385-8c41-57a3-a169-ae962a028ed0 |  | textbox | Test period
checkpoint-status |  |  | checkpoint | I declare that I have installed the above product in accordance with aquatherm specifications with no branding mix
checklist-sectioned |  |  | checklist | Second Fix |  |  |  |  | Yes | Second Fix | e83930a4-549b-4c44-bb04-d88f8abff85a
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous Substrate Acceptable
checkpoint-group |  |  | section | Second Fix QA
checkpoint-status |  |  | checkpoint | Fit-off Materials match schedule on plans
checkpoint-status |  |  | checkpoint | Setouts/min clearances as per plan
checkpoint-status |  |  | checkpoint | Water pipework maintained test throughout
checkpoint-status |  |  | checkpoint | No debris in floor wastes or stubs
checkpoint-status |  |  | checkpoint | HWC Tempered to required outlet temp
checkpoint-status |  |  | checkpoint | HWC Seismically strapped & braced
checkpoint-status |  |  | checkpoint | Flanges installed on all pipework to vermin proof
checkpoint-status |  |  | checkpoint | All soil pipes are connected to sanitary sewer
checkpoint-status |  |  | checkpoint | No crossovers, Hot on left and Cold on Right
checkpoint-status |  |  | checkpoint | All fixtures are silicon-ed down and splash sealed
checkpoint-status |  |  | checkpoint | Shower Hoses are fitted with non returns
checkpoint-status |  |  | checkpoint | Clamping rings and grates installed (photo required)
checkpoint-group |  |  | section | Second Fix Handover
checkpoint-status |  |  | checkpoint | Area left clean & tidy (Attach Photo)
checkpoint-status |  |  | checkpoint | All work 100% complete to required specifications
checklist-flat |  |  | checklist | Observation Details - |  |  |  |  | Yes | Add Observation | ec35c8fd-6d07-4da5-8efc-6b13c476f675
checkpoint-status |  |  | checkpoint | Observation/s:
checklist-sectioned |  |  | checklist | First Fix |  |  |  |  | Yes | First Fix | f90a1410-d012-446a-91b7-0d0520d6108f
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous Substrate Acceptable
checkpoint-group |  |  | section | First Fix QA
checkpoint-status |  |  | checkpoint | Hot water supply lines run the shortest
checkpoint-status |  |  | checkpoint | Specified Waste pipework is Acoustic Lagged
checkpoint-status |  |  | checkpoint | Penetrations through fire cells are fire protected
checkpoint-status |  |  | checkpoint | All joist Brackets or Reinforcement installed if required
checkpoint-status |  |  | checkpoint | Nog's and fixings are installed for WC, WHB, SHW, HWC?
checkpoint-status |  |  | checkpoint | Penetrations through building paper are trade sealed
checkpoint-status |  |  | checkpoint | Hot Water Ring main is thermally lagged
checkpoint-status |  |  | checkpoint | All Pipework clipped neatly and tidy
checkpoint-status |  |  | checkpoint | All pipework secured/ siliconed
checkpoint-status |  |  | checkpoint | FWG Flange is recessed into flooring and installed
checkpoint-status |  |  | checkpoint | Water tested to 1500kpa and loop not effect lining
checkpoint-status |  |  | checkpoint | Checked for drips on water and waste piping
checkpoint-status |  |  | checkpoint | Picked up all left over material and removed from site
checkpoint-status |  |  | checkpoint | Soil and waste piping hydrostatic test ( Flood test )
checkpoint-status |  |  | checkpoint | Test plug & Gauge removed from pipe system
checkpoint-status |  |  | checkpoint | Fire penetration Schedule is completed
checkpoint-status |  |  | checkpoint | Flange and all through installed pipework flood tested (photo required)
checkpoint-group |  |  | section | First Fix Handover
checkpoint-status |  |  | checkpoint | Area left clean & tidy (Attach Photo)
checkpoint-status |  |  | checkpoint | All work 100% complete to required specifications
checklist-flat |  |  | checklist | Completion documents |  |  |  |  | Yes | Completion documents | fb89c7be-b99b-4138-83c4-e003a6e0fe6f
checkpoint-status |  |  | checkpoint | PS3 Plumbing (BCO10324155-2)
checkpoint-status |  |  | checkpoint | Warranty
checkpoint-status |  |  | checkpoint | O & M
checklist-sectioned |  |  | checklist | Second Fix |  |  |  |  | Yes | Add Second Fix Checks | fd6b3551-b878-401a-933e-6af07374f800
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous Substrate Acceptable
checkpoint-group |  |  | section | Second Fix QA
checkpoint-status |  |  | checkpoint | Fit-off Materials match schedule on plans
checkpoint-status |  |  | checkpoint | Setouts/min clearances as per plan
checkpoint-status |  |  | checkpoint | Water pipework maintained test throughout
checkpoint-status |  |  | checkpoint | No debris in floor wastes or stubs
checkpoint-status |  |  | checkpoint | HWC Tempered to required outlet temp
checkpoint-status |  |  | checkpoint | HWC Seismically strapped & braced
checkpoint-status |  |  | checkpoint | Flanges installed on all pipework to vermin proof
checkpoint-status |  |  | checkpoint | All soil pipes are connected to sanitary sewer
checkpoint-status |  |  | checkpoint | No crossovers, Hot on left and Cold on Right
checkpoint-status |  |  | checkpoint | All fixtures are silicon-ed down and splash sealed
checkpoint-status |  |  | checkpoint | Shower Hoses are fitted with non returns
checkpoint-status |  |  | checkpoint | Clamping rings and grates installed (photo required)
checkpoint-group |  |  | section | Second Fix Handover
checkpoint-status |  |  | checkpoint | Area left clean & tidy (Attach Photo)
checkpoint-status |  |  | checkpoint | All work 100% complete to required specifications