## QA Folder Structure
QA Folder Structure | [5 empty] | Checklists
Site QA
Slabs & Columns
Level 4
South
|  |  |  | Columns |  | Columns - Concrete Pour ITP
Slab
[5 empty] | Hydraulic Services | Slab - Concrete Pour ITP
West
|  |  |  | Columns |  | Columns - Concrete Pour ITP
Slab
[5 empty] | Hydraulic Services | Slab - Concrete Pour ITP
North
|  |  |  | Columns |  | Columns - Concrete Pour ITP
Slab
[5 empty] | Hydraulic Services | Slab - Concrete Pour ITP
Level 5
South
|  |  |  | Columns |  | Columns - Concrete Pour ITP
Slab
[5 empty] | Hydraulic Services | Slab - Concrete Pour ITP
West
|  |  |  | Columns |  | Columns - Concrete Pour ITP
Slab
[5 empty] | Hydraulic Services | Slab - Concrete Pour ITP
North
|  |  |  | Columns |  | Columns - Concrete Pour ITP
Slab
[5 empty] | Hydraulic Services | Slab - Concrete Pour ITP
**Same up to level 28
Eg next - Level 6
Eg last - Level 28

## ITPs Checklists
type | name | values | prefix | postfix | usage count | user addable
checklist-flat | Slab - Concrete Pour ITP
checkpoint | Cast in pipework/sleeves as per approved engineer detail
checkpoint | Penetrations fire collars and pipework in correct locations as per drawings
checkpoint | Tested & Inspected - test results attached as required below
checkpoint | Jordan Plumbing for info Penetration plan/cast in plan marked off
checkpoint | JP supervisor and Builder Rep signature attached below
checklist-flat | Columns - Concrete Pour ITP
checkpoint | HDPE / Raupiano / PVC drainage / penetrations installed as per AS3500
checkpoint | Hydro static test to HDPE / Raupiano / PVC sewer and stormwater stacks
checkpoint | As per AS3500 section 13.2 (No leaks while under test conditions for 15mins)
checkpoint | Cast in pipework/sleeves as per approved engineer detail
checkpoint | Penetrations and pipework in correct locations as per drawings
checkpoint | Book inspection with OTR to undertake visual inspection of each stack as required
checkpoint | Tested & Inspected - test results attached as required below
checkpoint | Ensure all Inspection Openings in columns are capped and flush with external face
checkpoint | Jordan Plumbing for info Penetration plan/cast in plan marked off
checkpoint | JP supervisor and Builder Rep signature attached below
checklist-flat | Suspended Sewer ITP
checkpoint | HDPE / Raupiano / PVC drainage installed as per AS3500
checkpoint | Hydro static test to HDPE / Raupiano / PVC suspended drainage and sewer stack
checkpoint | As per AS3500 section 13.2 (No leaks while under test conditions for 15mins)
checkpoint | Book inspection with OTR to undertake visual inspection of each suspended drain / stack
checkpoint | OTR to sign marked up drawing for each suspended drain / stack - drawing and OTR signatureattached below
checkpoint | Tape to be installed to IP cap on sewer stack once test complete - OTR signature attached below
label | (tape is installed to make sure the IP cap is not removed/loosened by any other trades during construction)
checkpoint | Sign internal walls and ceilings linings handover sheet
checkpoint | Tested & Inspected - test results attached below
checkpoint | JP supervisor and Builder Rep signature attached below