## Project Structure
Folder Structure |  |  | Checklists
Site QA
| Level 1 | Corridor | Plastering & Hebel | Internal wall and ceiling painting
|  | U101 | Plastering & Hebel | Internal wall and ceiling painting
|  | U102 | Plastering & Hebel | Internal wall and ceiling painting
|  | U103 | Plastering & Hebel | Internal wall and ceiling painting
|  | U104 | Plastering & Hebel | Internal wall and ceiling painting
|  | U105 | Plastering & Hebel | Internal wall and ceiling painting
|  | U106 | Plastering & Hebel | Internal wall and ceiling painting
|  | U107 | Plastering & Hebel | Internal wall and ceiling painting
|  | U108 | Plastering & Hebel | Internal wall and ceiling painting
|  | U109 | Plastering & Hebel | Internal wall and ceiling painting
|  | U110 | Plastering & Hebel | Internal wall and ceiling painting
|  | U111 | Plastering & Hebel | Internal wall and ceiling painting
|  | U112 | Plastering & Hebel | Internal wall and ceiling painting
|  | U113 | Plastering & Hebel | Internal wall and ceiling painting
|  | U114 | Plastering & Hebel | Internal wall and ceiling painting
| Level 2 | Corridor | Plastering & Hebel | Internal wall and ceiling painting
|  | U201 | Plastering & Hebel | Internal wall and ceiling painting
|  | U202 | Plastering & Hebel | Internal wall and ceiling painting
|  | U203 | Plastering & Hebel | Internal wall and ceiling painting
|  | U204 | Plastering & Hebel | Internal wall and ceiling painting
|  | U205 | Plastering & Hebel | Internal wall and ceiling painting
|  | U206 | Plastering & Hebel | Internal wall and ceiling painting
|  | U207 | Plastering & Hebel | Internal wall and ceiling painting
|  | U208 | Plastering & Hebel | Internal wall and ceiling painting
|  | U209 | Plastering & Hebel | Internal wall and ceiling painting
|  | U210 | Plastering & Hebel | Internal wall and ceiling painting
|  | U211 | Plastering & Hebel | Internal wall and ceiling painting
|  | U212 | Plastering & Hebel | Internal wall and ceiling painting
|  | U213 | Plastering & Hebel | Internal wall and ceiling painting
|  | U214 | Plastering & Hebel | Internal wall and ceiling painting
| Level 3 | Corridor | Plastering & Hebel | Internal wall and ceiling painting
|  | U301 | Plastering & Hebel | Internal wall and ceiling painting
|  | U302 | Plastering & Hebel | Internal wall and ceiling painting
|  | U303 | Plastering & Hebel | Internal wall and ceiling painting
|  | U304 | Plastering & Hebel | Internal wall and ceiling painting
|  | U305 | Plastering & Hebel | Internal wall and ceiling painting
|  | U306 | Plastering & Hebel | Internal wall and ceiling painting
|  | U307 | Plastering & Hebel | Internal wall and ceiling painting
|  | U308 | Plastering & Hebel | Internal wall and ceiling painting
|  | U309 | Plastering & Hebel | Internal wall and ceiling painting
|  | U310 | Plastering & Hebel | Internal wall and ceiling painting
|  | U311 | Plastering & Hebel | Internal wall and ceiling painting
|  | U312 | Plastering & Hebel | Internal wall and ceiling painting
|  | U313 | Plastering & Hebel | Internal wall and ceiling painting
|  | U314 | Plastering & Hebel | Internal wall and ceiling painting
| Level 4 | Corridor | Plastering & Hebel | Internal wall and ceiling painting
|  | U401 | Plastering & Hebel | Internal wall and ceiling painting
|  | U402 | Plastering & Hebel | Internal wall and ceiling painting
|  | U403 | Plastering & Hebel | Internal wall and ceiling painting
|  | U404 | Plastering & Hebel | Internal wall and ceiling painting
|  | U405 | Plastering & Hebel | Internal wall and ceiling painting
|  | U406 | Plastering & Hebel | Internal wall and ceiling painting
|  | U407 | Plastering & Hebel | Internal wall and ceiling painting
|  | U408 | Plastering & Hebel | Internal wall and ceiling painting
|  | U409 | Plastering & Hebel | Internal wall and ceiling painting
|  | U410 | Plastering & Hebel | Internal wall and ceiling painting
| Level 5 | Corridor | Plastering & Hebel | Internal wall and ceiling painting
|  | U501 | Plastering & Hebel | Internal wall and ceiling painting
|  | U502 | Plastering & Hebel | Internal wall and ceiling painting
|  | U503 | Plastering & Hebel | Internal wall and ceiling painting
|  | U504 | Plastering & Hebel | Internal wall and ceiling painting
|  | U505 | Plastering & Hebel | Internal wall and ceiling painting
|  | U506 | Plastering & Hebel | Internal wall and ceiling painting
|  | U507 | Plastering & Hebel | Internal wall and ceiling painting
|  | U508 | Plastering & Hebel | Internal wall and ceiling painting
|  | U509 | Plastering & Hebel | Internal wall and ceiling painting
|  | U510 | Plastering & Hebel | Internal wall and ceiling painting
| Level 6 | Corridor | Plastering & Hebel | Internal wall and ceiling painting
|  | U601 | Plastering & Hebel | Internal wall and ceiling painting
|  | U602 | Plastering & Hebel | Internal wall and ceiling painting
|  | U603 | Plastering & Hebel | Internal wall and ceiling painting
|  | U604 | Plastering & Hebel | Internal wall and ceiling painting
|  | U605 | Plastering & Hebel | Internal wall and ceiling painting
|  | U606 | Plastering & Hebel | Internal wall and ceiling painting
|  | U607 | Plastering & Hebel | Internal wall and ceiling painting
|  | U608 | Plastering & Hebel | Internal wall and ceiling painting
|  | U609 | Plastering & Hebel | Internal wall and ceiling painting

## Checklists
type | name | values
checklist | Plastering & Internal Hebel
section | Framing
checkpoint | All frames/studs set out correctly
checkpoint | All frames plumb and square
checkpoint | Fix to structural members
checkpoint | All window and sliding door openings are as per plan and line up with above elements.
checkpoint | Nogging all installed correctly
checkpoint | Plywood installed to all wet areas to adaptable units
checkpoint | Door frames fixing
checkpoint | Studco/Rondo Supplier inspection (Provide report to builder)
section | Internal Hebel wall and external hebel wall
checkpoint | Angle/sarking/top hats in place
checkpoint | Hebel panels Alignment
checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
checkpoint | Ensure hebel panels are in full and not cracked
checkpoint | Enure control joints have been installed in accordance with manufacturers specifications and installation guide
checkpoint | Hebel expansion joints have been installed and are consistent including slab junctions
checkpoint | Window seal cuts to be neat & consistent
checkpoint | Ensure hebel panels are in full and not cracked
checkpoint | Weep holes have been installed correctly and at correct heights and spacings
checkpoint | Insulation installed as per AS/BCA (party walls + external)
checkpoint | Panels finish(patches done)
checkpoint | Fire-rated caulking and sealing
checkpoint | Satisfaction and sign off from CSR inspection (Provide report to builder)
section | Plasterboard for Walls
checkpoint | Ply nogging
checkpoint | Rough-in sign off
checkpoint | Insulation installed as per AS/BCA
checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
checkpoint | Villaboard to wet areas ONLY
checkpoint | Plasterboard Lining to be installed as wall set out plan
section | Plasterboard for Ceiling
checkpoint | Confirm Ceiling height
checkpoint | Confirm Access panel location
checkpoint | Ceiling frame work
checkpoint | Ceiling bulkheads where required
checkpoint | Pelmets
checkpoint | Ceiling insulation as per AS/BCA
checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
checkpoint | Ceiling plasterboard Lining
section | Setting & Sanding
checkpoint | Angle /LB/P50 install
checkpoint | First coat setting
checkpoint | Second coat setting
checkpoint | Final coat setting
checkpoint | Sanding
checkpoint | patching
checkpoint | Defects
checkpoint | Final Inspection
check list | Internal wall and ceiling painting
checkpoint | confirm color schedule
section | First coat
checkpoint | Surface Preparation
checkpoint | Clean surface
checkpoint | Protections
checkpoint | Spray/roll
section | Second coat
checkpoint | check first coat
checkpoint | Clean surface
checkpoint | touch up all defects
checkpoint | roll second coat
section | Third coat
checkpoint | check second coat
checkpoint | clean surface
checkpoint | sealing gaps like wall juctions ,skirtings
checkpoint | touch up all defects
checkpoint | Last Coat
checkpoint | Insepections
checkpoint | Final defects