## Breakdown
LJ Brick & Block Limited - 045 Kevin Hickman (Riccarton Park)
Stage - 06 - THB 06-09
THB 06 (TH 29, 31, 32)
|  |  | Brick Installation - Individual letter boxes |  | Pre-populate | FC - S - Brick Works
THB 07 (TH 23, 25, 27)
|  |  | Brick Installation - Individual letter boxes |  | Pre-populate | FC - S - Brick Works
THB 08 (TH 26, 28, 30)
|  |  | Brick Installation - Individual letter boxes |  | Pre-populate | FC - S - Brick Works
THB 09 (TH 21, 22)
|  |  | Brick Installation - Individual letter boxes |  | Pre-populate | FC - S - Brick Works
Compliance Documents
|  | Stage 06 - Individual letter boxes |  | Pre-populate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist | FC - S - Brick Works
section | Preinstall checks
checkpoint | Area accessible, substrate acceptable & approval to start works - Consider services, cavity & waterproofing requirements prior to install
checkpoint | Ground clearance correct to specification
checkpoint | Grids/Wall marked for reference. RL reference/TOW confirmed. Base/Concrete/footing clean, tidy and level ready for first coarse.
section | Brick installation
checkpoint | Base of wall starting correct location - Brick base overhang within tolerances (no more than 20mm)
checkpoint | Control joints installed correctly
checkpoint | Weep holes installed correctly - Consider setout & size
checkpoint | Mortar Joints installed within tolerances (7-13mm)
checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc)
checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checkpoint | All relevant flashings and waterproofing/taping completed as required - If Applicable
checkpoint | Caulking completed (correct colour) and satisfactory finish achieved
checkpoint | Brick cavity is correctly formed and free of obstructions
checkpoint | Brickwork completed to required specification. All brickwork washed/clean & area left clean & tidy - Wall built within tolerance - straight, level and to the correct height and colour
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff