## SOW
Remediation Works
At 3 Ngo Oho Street, Orakei
Date: | 2022-07-06
SCOPE OF WORK
200 | Scaffolding | Type | Amount | Comments
201 | Provide scaffolding, including planks and ladders to the height required to provided access to effect the safe execution of the work items within this scope of works including all provisional sum items. | L/S
300 | Covers
301 | Provide temporary covers and temporary cladding to ensure weather protection and security during the construction process. | P/S
400 | Cladding Removal
401 | Remove all fittings and fixtures attached to the building. Allow for the removal and disposal of all downpipes, gutters and brackets | L/S
402 | Remove & dispose of uv corroded heat pump pipe works and trunking located in the north elevation & replace with new trunking and pipes | P/S
403 | Remove & reinstate heat pump -condenser unit for painting & sub floor repair | P/S
404 | Remove & dispose the sky disk (including coaxle cable) installed in the north elevation | P/S
500 | External wall reinstatement
501 | Remove and dispose of all wet and/or decayed timber framing, and mould affected material including insulation | P/S
600 | External Windows and Doors
605 | Replace rusted /corroded window hardware including hinges, stays and latchets with similar hardware | P/S
700 | Wall Cladding
702 | Water blast exterior surfaces of the property prior to painting | L/S
703 | Thoroughly prepare all exterior faces and exposed edges of the property's soffits, facia and barge boards, for a new paint finish in accordance with the paint manufacturers specification. Apply a three coats of semi gloss acrylic as specified and in accordance with the paint manufacturers recommendations. Paint is to be sourced from Resene. | L/S
705 | Replace rusted window head flashings
706 | Remove and replace damaged soffit, barge and fascia boards | P/S
707 | Rust treat & paint metal gutter where required | L/S
800 | Subfloor Wall and Foundations
801 | Remove any existing vapour barriers installed in the subfloor. Supply and install new 250 micron polythene vapour barrier over the ground within the subfloor spaces in accordance with NZS 4246, taping joints with hold downs. Install 45x20mm timber battens to hold the polythene against the sub floor perimeter wall. | P/S
802 | Supply and install a 4x4m square area of Masons HT Green 300 micron extra thick, super hi-strength Vapour barrier to the subfloor area on the south elevation entry directly accessible from the subfloor door. | L/S
804 | Allow the upgrade of the timber bearer to pile connections and joist to bearer/foundation wall connections where required as per NZS 3604. | P/S
805 | Thoroughly prepare all exterior faces and exposed edges of the property's exterior subfloor wall cladding and entrance way stair and lobby for a new paint finish in accordance with the paint manufacturers specification. Apply a three coats of semi gloss acrylic as specified and in accordance with the paint manufacturers recommendations. Paint is to be sourced from Resene. | L/S
806 | Tidy up the existing sub floor insulation including installing new insulation match to the existing | P/S
900 | Decks, Handrails and Pergolas
902 | Repair external deck -decking, framing & Structural connection where required | P/S
1000 | Roof
1002 | Wire brush, and wash all corroded roof elements including soil vent pipes. Apply Resene GP Metal Primer prior to application of primer and paint. Apply three coats of semi gloss acrylic as specified and in accordance with the paint manufacturers recommendations. Paint is to be sourced from Resene. | L/S
1003 | Remove and dispose of all wet and/or decayed timber framing, and mould affected material including insulation | P/S
1004 | Inspect roof for damages and leaks | P/S
| Description | Type | Amount | Comments
1100 | Building Services
1101 | Remove and reinstate plumbing pipes and fixtures as required or as directed by client | P/S
1102 | Allow to inspect and make necessary repairs to electrical fittings, wiring and other electrical elements in the property | P/S
1500 | Internal Kitchen
1501 | Supply and install new kitchen extract fan through exterior wall | P/S
| Description | Type | Amount | Comments
1800 | External Works
1801 | Allow to break out raised or cracked concrete paved areas and lay new where instructed by the client. Where the area of repair is to a footpath the following repair is to be carried out: Break out existing damaged concrete, install new 100mm 25mpa concrete paths with 500E mesh over well compacted hard fill (GAP40) surface finish to match existing and is to comply with NZBC D1 Slip Resistance tables 1 and 2. Where the area of repair is to a drive way the following repair is to be carried out: Break out existing damaged concrete, lay new 150mm compacted hard fill, install new D12 rods at 400mm centres max into the existing concrete, rods are to be imbedded 200mm into the existing concrete and provide 400mm lap with new SE62 mesh, epoxy with epcon C6. The new SE62 mesh is to be installed centrally to the new concrete with equal cover from the top and bottom. Following the installation of the mesh, install new 25Mpa to a thickness of min 100mm ensuring a smooth finish is achieved. | P/S
1802 | Repair existing retaining wall | P/S
| Description | Type | Amount | Comments
1803 | Repair existing fence in east elevation | P/S
1804 | Remove & reinstall toby box & secure earthling cable. | P/S
TOTAL: |  |  | 0