## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Steel Stud Checklist |  |  |  |  | Yes | Internal Steel Stud Walls Checklist | 0e3ee830-c2d1-4ad7-8d6b-16c4aba4940f
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status |  |  | checkpoint | Area ready for Steel Stud install
checkpoint-status |  |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status |  |  | checkpoint | All frames are square, straight and level
checkpoint-status |  |  | checkpoint | Fixings are correct
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | Fire rating elements installed as per spec
checkpoint-status |  |  | checkpoint | Doors and openings installed as per plan
checkpoint-status |  |  | checkpoint | Nogs / service nogs installed correctly as per plan
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All Steel Stud completed correctly within tolerance in area
checkpoint-status |  |  | checkpoint | Steel Stud report sent through to client
checklist-flat |  |  | checklist | Doors Checklist |  |  |  |  | Yes | Doors Checklist | 151ba8ad-c6dc-4d86-8a5d-d83f77866395
checkpoint-status |  |  | checkpoint | Installer details input
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status |  |  | checkpoint | Door opening checked and correct
checkpoint-status |  |  | checkpoint | Direction of door correct
checkpoint-status |  |  | checkpoint | Number of screws and hardware location correct
checkpoint-status |  |  | checkpoint | Door hinges installed in place with correct screws
checkpoint-status |  |  | checkpoint | Floor clearance correct
checkpoint-status |  |  | checkpoint | Undercoat on door surface
checkpoint-status |  |  | checkpoint | Fireseal around door installed as per spec
checkpoint-status |  |  | checkpoint | Door is fully operational after installation
checkpoint-status |  |  | checkpoint | Door jambs are plumn and level
checkpoint-status |  |  | checkpoint | Door gap around door leaf within tolerance
checkpoint-status |  |  | checkpoint | Door report sent through to client
checklist-flat |  |  | checklist | Stairs Checklist |  |  |  |  | Yes | Stairs Checklist | 1a537231-ee00-437d-9022-49207be4d494
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status |  |  | checkpoint | Stair Units as per Plan
checkpoint-status |  |  | checkpoint | Post / Beam Connections
checkpoint-status |  |  | checkpoint | Bracing Connections
checkpoint-status |  |  | checkpoint | Stringer have enough fixing to framing with solid packer(s)
checkpoint-status |  |  | checkpoint | Verticals Plumb
checkpoint-status |  |  | checkpoint | Aligned and secured
checkpoint-status |  |  | checkpoint | 5mm gap between GIB each side of stairs
checkpoint-status |  |  | checkpoint | Top landing height to RL
checkpoint-status |  |  | checkpoint | Parallel with framing
checkpoint-status |  |  | checkpoint | Stair installation complete
checkpoint-status |  |  | checkpoint | Stair Installation report sent through to client
checklist-sectioned |  |  | checklist | Insulation Checklist |  |  |  |  | Yes | Walls and Ceiling Insulation Checklist | 35658335-2482-4813-9a45-07600a91f37c
checkpoint-group |  |  | section | Walls Insulation
checkpoint-status |  |  | checkpoint | Walls dry and ready for installation?
checkpoint-status |  |  | checkpoint | Correct product and R values installed
checkpoint-status |  |  | checkpoint | Installed correctly - no gaps or bunching
checkpoint-status |  |  | checkpoint | Installed correctly around services
checkpoint-status |  |  | checkpoint | Surplus removed and left tidy
checkpoint-status |  |  | checkpoint | All Wall Insulation completed correctly, checked & reviewed - as per specification
checkpoint-status |  |  | checkpoint | Wall Insulation report sent through to client
checkpoint-group |  |  | section | Ceiling Insulation
checkpoint-status |  |  | checkpoint | Ceiling dry and ready for installation?
checkpoint-status |  |  | checkpoint | Correct product and R values installed
checkpoint-status |  |  | checkpoint | Installed correctly - no gaps or bunching
checkpoint-status |  |  | checkpoint | Installed correctly around services
checkpoint-status |  |  | checkpoint | Surplus removed and left tidy
checkpoint-status |  |  | checkpoint | All Ceiling Insulation completed correctly, checked & reviewed - as per specification
checkpoint-status |  |  | checkpoint | Ceiling Insulation report sent through to client
checklist-flat |  |  | checklist | Ceiling Grid Checklist |  |  |  |  | Yes | Ceiling Grid Checklist | 35c93138-aa9e-4768-b3c7-d36b39444f4f
checkpoint-status |  |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status |  |  | checkpoint | Substrate correct (nogging installed if required)
checkpoint-status |  |  | checkpoint | Ceiling Grid installed level and to correct heights
checkpoint-status |  |  | checkpoint | Correct fixings and number of fixings
checkpoint-status |  |  | checkpoint | Member centres correct
checkpoint-status |  |  | checkpoint | Correct Clips installed
checkpoint-status |  |  | checkpoint | Earth strap installed
checkpoint-status |  |  | checkpoint | Hatches openings trimmed out and installed
checkpoint-status |  |  | checkpoint | Bulkheads installed plumb/level/square
checkpoint-status |  |  | checkpoint | Ceiling Grid completed correctly, checked & reviewed - as per specification
checkpoint-status |  |  | checkpoint | Area left clean & tidy
checkpoint-status |  |  | checkpoint | Ceiling Grid report sent through to client
checklist-sectioned |  |  | checklist | Internal Gutters Checklist |  |  |  |  | Yes | Internal Gutters Checklist | 4d6378db-2619-46d7-b9a5-5dee46c0923d
checkpoint-group |  |  | section | Framing
checkpoint-status |  |  | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
checkpoint-status |  |  | checkpoint | Dimensions / locations of framing checked and correct
checkpoint-status |  |  | checkpoint | DPM installed where required
checkpoint-status |  |  | checkpoint | All frames are square & plumb
checkpoint-status |  |  | checkpoint | External framing is installed at correct centres
text | c9979980-ed11-4272-89e0-1a2f83e3b351 |  | textbox | Input centres
checkpoint-status |  |  | checkpoint | Correct falls achieved
checkpoint-group |  |  | section | RAB
checkpoint-status |  |  | checkpoint | Visual check performed on waterproofing
checkpoint-status |  |  | checkpoint | Waterproofing clean and dry
checkpoint-status |  |  | checkpoint | 20mm gap from flat slab to allow seismic movement
checkpoint-status |  |  | checkpoint | Wall type as specified
text | 47b4cfee-aa00-4ba2-adcc-6ac4ccd5ea76 |  | textbox | Wall type installed
checkpoint-status |  |  | checkpoint | Correct centres for wall type
checkpoint-status |  |  | checkpoint | Gaps are 3mm
checkpoint-status |  |  | checkpoint | Overhang correct as per specification
checkpoint-status |  |  | checkpoint | Sealant installed at steel or concrete connections
checkpoint-group |  |  | section | Vaproshield Installation Checklist
checkpoint-status |  |  | checkpoint | Wrapshield rolls stored upright
checkpoint-status |  |  | checkpoint | RAB clean, free of contaminations and dry to touch
checkpoint-status |  |  | checkpoint | Lower courses lapped under the upper courses with a minimum 80mm lap joints
checkpoint-status |  |  | checkpoint | 150mm lap joint at internal and external corners
checkpoint-status |  |  | checkpoint | All service penetrations covered with liquid flashing
checkpoint-status |  |  | checkpoint | 50mm liquid flashing to all steel and concrete connections
checkpoint-status |  |  | checkpoint | All penetrations and damage to Vaproshield repaired
checkpoint-group |  |  | section | Completion and Handover
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | GIB Lining Checklist |  |  |  |  | Yes | GIB Ceiling Lining Checklist | 4e95cbc8-e5b7-469f-b992-20e659860ef6
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for GIB install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Sealant applied as per spec
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Lining report sent through to client
checklist-flat |  |  | checklist | Head Details |  |  |  |  | Yes | Head Details | 727808e8-4e56-4d8a-9b07-30c3a9bd9fd0
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | Balcony Ceiling (Villaboard) Checklist [A1 L1-6] |  |  |  |  | Yes | Balcony Ceiling (Villaboard) Checklist [A1 L1-6] | 73f9b047-70f5-4ac0-8dc3-0ed3633dacbc
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced.
checkpoint-status |  |  | checkpoint | Ceiling frame installed by others ready for Villaboard installation.
checkpoint-status |  |  | checkpoint | Ceiling frame installed by others is at correct level.
checkpoint-status |  |  | checkpoint | Timber packers installed required level.
checkpoint-status |  |  | checkpoint | Cavity closer installed at ceiling perimeter.
checkpoint-status |  |  | checkpoint | Correct fixing and fixing centres used.
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations.
checkpoint-status |  |  | checkpoint | Villaboard ceiling completed correctly as per specification.
checkpoint-status |  |  | checkpoint | Report sent through to client.
checklist-flat |  |  | checklist | Report number: |  |  |  |  | Yes | Passive Fire Report | 79152609-f572-44dc-bb3b-592d22fb1603
checkpoint-status |  |  | checkpoint | All relevant documents attached/referenced
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-sectioned |  |  | checklist | External Timber Framing Checklist |  |  |  |  | Yes | External Timber Framing Checklist | 813f6bfe-799f-43b3-b5f6-2df48435b8ae
checkpoint-group |  |  | section | Framing
checkpoint-status |  |  | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
checkpoint-status |  |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status |  |  | checkpoint | DPM installed where required
checkpoint-status |  |  | checkpoint | All frames are square & plumb
checkpoint-status |  |  | checkpoint | External framing is installed at correct centres
text | 83b1b4d9-8f74-4afc-98ac-312b53506c2b |  | textbox | Input centres
checkpoint-status |  |  | checkpoint | All openings are in correct location and correct size
text | b5468383-7fd8-4866-80af-bcd3c88fdee4 |  | textbox | Drawing / detail reference
checkpoint-group |  |  | section | RAB Installation Checklist
checkpoint-status |  |  | checkpoint | Visual check performed on waterproofing
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | 20mm gap from flat slab to allow seismic movement
checkpoint-status |  |  | checkpoint | Wall type as specified
text | 7e7e5b9f-3111-43de-97b9-a4c1d02da3e2 |  | textbox | Wall type installed
checkpoint-status |  |  | checkpoint | Correct fixing centres for wall type
checkpoint-status |  |  | checkpoint | Gaps are 3mm
checkpoint-status |  |  | checkpoint | Overhang correct as per specification
checkpoint-status |  |  | checkpoint | Sealant installed at steel or concrete connections
checkpoint-group |  |  | section | Vaproshield Installation Checklist
checkpoint-status |  |  | checkpoint | Wrapshield rolls stored upright
checkpoint-status |  |  | checkpoint | RAB clean, free of contaminations and dry to touch
checkpoint-status |  |  | checkpoint | Lower courses lapped under the upper courses with a minimum 80mm lap joints
checkpoint-status |  |  | checkpoint | 150mm lap joint at internal and external corners
checkpoint-status |  |  | checkpoint | All service penetrations covered with liquid flashing
checkpoint-status |  |  | checkpoint | 25 mm liquid flashing to all steel and concrete connections
checkpoint-status |  |  | checkpoint | All penetrations and damage to Vaproshield repaired
checkpoint-group |  |  | section | Completion and Handover
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | Timber Architraves & Skirtings Checklist |  |  |  |  | Yes | Skirtings Checklist | 9b2847e2-9ce7-40f3-bd3a-ca57966ddc74
checkpoint-status |  |  | checkpoint | Has the plasterer left area cleaned, tidy and removed all plaster dags off wall ready to receive architraves/skirtings?
checkpoint-status |  |  | checkpoint | Are the architraves/skirtings match size and profile as per drawing or contract?
checkpoint-status |  |  | checkpoint | Have the skirting board been properly scribed, sanded, glued and mitred and square at external corners?
checkpoint-status |  |  | checkpoint | Have all the architraves/skirtings been installed with consistent even margin?
checkpoint-status |  |  | checkpoint | Finishing report sent through to client
checklist-flat |  |  | checklist | Additional Details/Photos |  |  |  |  | Yes | Additional Details/Photos | a3912cc6-92e1-49ed-ae0a-84192318c733
checkpoint-status |  |  | checkpoint | All relevant documents attached/referenced
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-sectioned |  |  | checklist | GIB Lining Checklist |  |  |  |  | Yes | GIB Walls and Ceiling Lining Checklist | b32375ab-e77a-41c2-8e12-6e9ae9012025
checkpoint-group |  |  | section | Wall Lining
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for GIB install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Sealant applied as per spec
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | GIB Wall Lining completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Wall Lining report sent through to client
checkpoint-group |  |  | section | Ceiling Lining
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for GIB install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Sealant applied as per spec
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | GIB Ceiling Lining completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Ceiling Lining report sent through to client
checklist-flat |  |  | checklist | GIB Lining Checklist |  |  |  |  | Yes | GIB Walls Lining Checklist | b5596e10-6faf-4e17-b9eb-8130e97c28bb
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for GIB install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Sealant applied as per spec
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Lining report sent through to client
checklist-flat |  | checklist-flat must be display flat but was progress | checklist | Additional Photos |  |  |  |  | Yes | Additional Photos | dfe6cdaa-3b68-481e-93a0-7618365057b9
checkpoint-status |  |  | checkpoint | Photos Attached
attachment | b9337ad9-4fcb-48b4-aea3-15a0501e1302 |  | ???unknown???
checklist-sectioned |  |  | checklist | Area / Grids: |  |  |  |  | Yes | Roof Checklist - Main Roof Section | ee47c0f7-0494-4c59-8582-9620b6423a2c
checkpoint-group |  |  | section | Battens
checkpoint-status |  |  | checkpoint | Timber treatment correct as per spec
checkpoint-status |  |  | checkpoint | Timber spacings are correct
checkpoint-status |  |  | checkpoint | Fixings installed with correct fixing pattern
checkpoint-group |  |  | section | Plywood
checkpoint-status |  |  | checkpoint | Plywood is correct thickness (19mm)
checkpoint-status |  |  | checkpoint | Fixings installed with correct fixing pattern
checkpoint-status |  |  | checkpoint | 65mm 10 gauge stainless steel screws used
checkpoint-status |  |  | checkpoint | Correct adhesive used
checkpoint-status |  |  | checkpoint | Sheets installed in staggered pattern
checkpoint-status |  |  | checkpoint | No gaps between sheets
checkpoint-group |  |  | section | Completion and Handover
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Report sent through to client