## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 1812fc3b-0eab-437a-928a-62297887ba5f |  | checklist | Villaboard |  |  |  |  | Yes | Villaboard Checklist | 0892c27c-06d7-4128-8cde-4301427985c1
checkpoint-status | ade07ef4-27c9-4542-b838-ebc59b4befbb |  | checkpoint | Framing set out (i.e. stud and nog spacing) correct
checkpoint-status | fafa2c26-13b4-433c-a98a-de296aa87855 |  | checkpoint | GIB Lining base are secure and flush with each other with no protruding fixings
checkpoint-status | cb5306c3-a419-48f4-b3cd-d72331fb51c6 |  | checkpoint | Gap between Villaboard edges/joints are at 1-2mm maximum
checkpoint-status | 8257bb2a-2bdb-4dcb-9a39-cf9817ea7228 |  | checkpoint | Villaboard must be installed dry
checkpoint-status | 4e8a2a60-6c6e-4691-989d-7488ae620b64 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 885662a1-974c-43b0-a1af-0aeed83fb01b |  | checkpoint | Villaboard report sent through to client
checklist-flat | d1b8b30b-5ec5-499f-86d7-cf27c91cb80c |  | checklist | Window Detail |  |  |  |  | Yes | External Framing Checklist | 534f7726-d849-490c-a359-9f34dc3a579e
checkpoint-status | cc15a19e-a7f4-4ec5-ab7d-48a7b1851f3b |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | 1d2ea5b7-4fc0-48da-a503-e4f8f56e7989 |  | checkpoint | Area ready for External Framing install
checkpoint-status | 60f7169d-fe81-400d-9916-c0badb628f1d |  | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
checkpoint-status | bbc3fe53-f5b9-434d-8a51-016f1919f9c6 |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status | 4dd5bd80-6d92-4115-951a-e7dc15226221 |  | checkpoint | DPM installed where required
checkpoint-status | 0909a5e2-2ed2-48e3-9fb3-7a5277fbebc2 |  | checkpoint | All frames are square & plumb
checkpoint-status | f661a55b-cdb7-44c1-b06e-49d3fa6c81a6 |  | checkpoint | External framing is installed at correct centres
checkpoint-status | b2e3d9b9-26b2-4463-b31e-efe32dc715b5 |  | checkpoint | All openings are in correct location and correct size
checkpoint-status | f3c2e348-2cf0-42c1-bd1d-085ec0685710 |  | checkpoint | General photos, comments and observations during install
checkpoint-status | 402ae44c-95ed-4b55-b4d1-5438aae1eeb4 |  | checkpoint | External Framing report sent through to client
checklist-sectioned | 1fd54d90-8950-4065-ad88-ea02d49ec0e9 |  | checklist | Parapet |  |  |  |  | Yes | Roof Checklist - Parapet Framing | 770db4db-c46e-42bc-9d72-e61b6996b222
checkpoint-group | 132ba5a9-c3ed-48c8-9f8d-2ea3209db919 |  | section | Timber Parapet Framing
checkpoint-status | 9f37d2b6-6563-4307-932d-57c31c91c8ac |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | 3adf3c52-8a91-43b2-a8fc-31ae4da01a7b |  | checkpoint | Dimensions / locations of parapet checked and correct to grid lines
checkpoint-status | 54095103-dbe4-444e-8502-55227a160bed |  | checkpoint | DPM installed where required
checkpoint-status | ac190a45-8776-4e53-8b3c-55628ee69ca6 |  | checkpoint | H3.2 Infill timber frames are installed square & plumb
checkpoint-status | 6e58b757-4bda-45df-8a7d-3454f9d77b52 |  | checkpoint | Fixings are installed correct
checkpoint-status | 29bfffcd-103f-457a-a183-a4523953d710 |  | checkpoint | Insulation installed
checkpoint-group | 495c6f52-dfaf-4d30-9768-40eb214588af |  | section | RAB & Building Wraps - as per detail
checkpoint-status | 2e2441b5-aacb-431c-b327-a4ce350190a6 |  | checkpoint | Gib Weatherline installed per spec - all screws and joints taped
checkpoint-status | a7857e46-fcde-4b2b-b7b9-9376fac9a805 |  | checkpoint | Tekton Building wrap applied - NO staples through weather line.
checklist-flat | 1772d714-936b-4a8d-8611-9f259ce99777 |  | checklist | Main Section |  |  |  |  | Yes | Roof Checklist - Main Section | 83378981-1626-4b7a-a818-598ac33b2839
checkpoint-status | a3ae7b2f-34be-4f00-baf5-2b0c1c0865ba |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | 22716430-a8e0-4545-9b45-50ce1c34bc92 |  | checkpoint | Timber treatment correct as per spec
checkpoint-status | 8433316c-53c9-4335-8fa8-587ebf34e861 |  | checkpoint | Timber spacings are correct
checkpoint-status | 7c684715-f7fc-4ca4-b467-f13d871adbb9 |  | checkpoint | Fixings installed with correct fixing pattern
checkpoint-status | 30e10419-c5eb-409d-9020-a0ce18a71ea4 |  | checkpoint | Insulation installed
checkpoint-status | 7c4343bf-8c6c-4980-8ff3-27ce708ff4f4 |  | checkpoint | Plywood is correct thickness (19mm)
checkpoint-status | 683828f8-e573-4741-a447-06fb4e83c368 |  | checkpoint | Fixings installed with correct fixing pattern
checkpoint-status | 79846ff0-ae12-4433-94d0-fc3925c06eff |  | checkpoint | 65mm 10 gauge stainless steel screws used
checkpoint-status | baba6814-e7c9-45dc-b2e7-76c626105b64 |  | checkpoint | Correct adhesive used
checkpoint-status | d25f3674-bb93-4334-868f-aac254c1d0b5 |  | checkpoint | Sheets installed in staggered pattern
checkpoint-status | c5b4268f-6f5a-4423-9965-0883fd54b4b3 |  | checkpoint | No gaps between sheets
checkpoint-status | a56f0714-d04a-4aee-a3cf-e7c9ea82f9a9 |  | checkpoint | Installation completed correctly within tolerance in respective area
checkpoint-status | bc787568-b136-4a0c-8c20-9d590ae0dc01 |  | checkpoint | Report sent through to client
checklist-flat | bd2c6a4f-e387-4e77-93ef-0e19cdf46363 |  | checklist | Doors |  |  |  |  | Yes | Doors Checklist | 851722e2-6578-42b1-8b9c-1551cfae6c7e
checkpoint-status | e82604c7-51d3-4d75-8260-ebdfda7f67d1 |  | checkpoint | Installer details input
checkpoint-status | a46c7a0f-b814-4aa7-b691-4ecd3ef80ee3 |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status | 817a0cd8-53b0-4740-a0ae-24ece219a933 |  | checkpoint | Door opening checked and correct
checkpoint-status | 7e76d0d7-6c87-4af0-b252-194592b770d2 |  | checkpoint | Direction of door correct
checkpoint-status | af105858-17d0-424d-834c-51bcc279ab78 |  | checkpoint | Number of screws and hardware location correct
checkpoint-status | b70a7bc9-9003-4f9b-97fd-afa5fedc29eb |  | checkpoint | Door hinges installed in place with correct screws
checkpoint-status | eeaddeb8-8a13-4f3d-98de-c39c90ed0cfd |  | checkpoint | Floor clearance correct
checkpoint-status | 47fec660-9dba-449a-81cc-a9eae362f4bc |  | checkpoint | Undercoat on door surface
checkpoint-status | c79c2bbf-37c3-406c-9405-308181a8a249 |  | checkpoint | Fireseal around door installed as per spec
checkpoint-status | fe9a8af7-30e3-4330-9ad7-2d8ee5fafa20 |  | checkpoint | Door is fully operational after installation
checkpoint-status | e71e5850-202f-4f39-9cbb-8d2504cc01ed |  | checkpoint | Door jambs are plumn and level
checkpoint-status | dbaa0fab-022f-4ed0-a0ed-a7079ad74608 |  | checkpoint | Door gap around door leaf within tolerance
checkpoint-status | a1f58017-b428-4574-b2b5-7e392a3fe884 |  | checkpoint | Door report sent through to client
checklist-sectioned | 35e88f23-e493-4189-af4f-5327e68d1d27 |  | checklist | Steel Stud and GIB Lining |  |  |  |  | Yes | Steel Stud and GIB Lining Checklist | ed5bfca4-850f-475f-9cd5-251e444a841e
checkpoint-group | b61a42d5-f08a-42db-ae0f-0cb7d92ba5f0 |  | section | Steel Stud
checkpoint-status | 8c9985d3-6d11-4ec3-adb5-2457738e2802 |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | ca3169ec-206d-4781-9972-9b729ef25cd4 |  | checkpoint | Area ready for Steel Stud install
checkpoint-status | 72530c8a-26d2-4ed2-8098-44fa592b9c6c |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status | 4ae951fe-bc9d-494c-b3f4-41d2cf2ef6ef |  | checkpoint | All frames are square, straight and level
checkpoint-status | 8e11ce1f-bf34-4011-9eec-b463e2c4a064 |  | checkpoint | Fixings are correct
checkpoint-status | 1a2706e1-88bb-4298-ac7b-f97b92e61015 |  | checkpoint | Any bracing requirements installed
checkpoint-status | 379aab55-c030-4db0-b31e-c6b1c18a772a |  | checkpoint | Fire rating elements installed as per spec
checkpoint-status | c93ccd87-d62a-446b-bcc3-d91990a87d2c |  | checkpoint | Doors and openings installed as per plan
checkpoint-status | 72101359-4485-4b05-b529-465dc2db9244 |  | checkpoint | Nogs / service nogs installed correctly as per plan
checkpoint-status | 4d35dfa5-1403-445b-ba12-be14f92e2d9a |  | checkpoint | Any additional photos, comments and observations
checkpoint-status | ddcbf4f8-deac-4f0c-bb05-5def2b187d8c |  | checkpoint | All Steel Stud completed correctly within tolerance in area
checkpoint-status | 9530d4f1-5422-4e45-9bec-0635056af971 |  | checkpoint | Steel Stud report sent through to client
checkpoint-group | 8f338277-5734-4133-a7b5-bd51f249bd70 |  | section | GIB Lining
checkpoint-status | 08a0394d-ca4d-4262-9a25-0d047c20d08c |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 87aa6c14-60d2-4234-9b33-5fd0c101bdf7 |  | checkpoint | Area ready for GIB install
checkpoint-status | f4e0ecb4-6eeb-40bf-8b20-b407a70eb192 |  | checkpoint | Insulation installed
checkpoint-status | f0e46758-7c36-4826-a139-fc9616f6cbb5 |  | checkpoint | General photos, comments and observations during install
checkpoint-status | ed695f89-9d5d-4a9b-9062-4c3e682c0a7a |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status | 9b562c4f-e6a5-4865-bb73-ebdf348f5981 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | 21561e88-43ee-4f13-a01d-377b53c20deb |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 160107ff-7b2c-4f00-abd5-03c36b48f1c3 |  | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
checkpoint-status | 18c166f8-f24f-4cca-a0c0-479835935bc2 |  | checkpoint | GIB Lining report sent through to client
checklist-sectioned | 008e96da-661a-4a75-8246-84c14eaea126 |  | checklist | Gutter |  |  |  |  | Yes | Roof Checklist - Internal Gutter | f162a3a0-042e-4da8-ac13-ed5365a38155
checkpoint-group | 01cc5f3c-998f-44e9-8226-59d517e089c9 |  | section | Framing
checkpoint-status | 94ac37fb-1123-42ac-918e-853ec5854bad |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | 7e74a467-b3a7-4214-abf8-c11a25f766d3 |  | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
checkpoint-status | 4b8e5ee1-8309-4703-b932-2767923d1bae |  | checkpoint | Dimensions / locations of framing checked and correct
checkpoint-status | dc28820d-1463-42e0-a038-fd8d4e5b5569 |  | checkpoint | DPM installed where required
checkpoint-status | 8e134b44-997b-41e6-9575-6344601b1caf |  | checkpoint | All frames are square & plumb
checkpoint-status | f3654270-5961-428d-9bf8-57dfdc31de81 |  | checkpoint | External framing is installed at correct centres
checkpoint-status | 807f17b7-a2b3-41bf-8d7c-3160c4a891c8 |  | checkpoint | Correct falls achieved
checkpoint-group | b0877735-6bf0-4c86-9009-10887443b0a8 |  | section | RAB
checkpoint-status | 7e3ce4e8-4a6d-43b0-baff-d5f994a36055 |  | checkpoint | Visual check performed on waterproofing
checkpoint-status | 5be468b0-6eb9-4351-b588-c03ebc36ff64 |  | checkpoint | Waterproofing clean and dry
checkpoint-status | a7c02e1b-5589-44e1-9011-2fbaf58f1714 |  | checkpoint | 20mm gap from flat slab to allow seismic movement
checkpoint-status | 359ef5b5-9ec9-41c0-b150-e603771e53fa |  | checkpoint | Wall type as specified
checkpoint-status | e1b225b9-0c92-449d-a338-b90bcd6acf5a |  | checkpoint | Correct centres for wall type
checkpoint-status | b6fe5629-9cd1-41b2-b763-087acaeb6648 |  | checkpoint | Gaps are 3mm
checkpoint-status | ed655212-6dbb-4ef5-a868-2fe642ce1c99 |  | checkpoint | Overhang correct as per specification
checkpoint-status | c128aac7-cfd6-429b-8a42-148edfb19804 |  | checkpoint | Sealant installed at steel or concrete connections
checkpoint-group | 7ff0f17e-b62a-499b-854b-6e0f0142b05f |  | section | Vaproshield Installation Checklist
checkpoint-status | 3484806e-5f90-41e9-89b5-d1d241c9edf2 |  | checkpoint | Wrapshield rolls stored upright
checkpoint-status | c9f5faf5-65bc-4e3f-8988-6eeac589a440 |  | checkpoint | RAB clean, free of contaminations and dry to touch
checkpoint-status | 4c39d321-bfcd-4785-8a88-7e4b82c2724d |  | checkpoint | Lower courses lapped under the upper courses with a minimum 80mm lap joints
checkpoint-status | 6812d1e8-0f44-428f-aa9d-bac402ae7de6 |  | checkpoint | 150mm lap joint at internal and external corners
checkpoint-status | 9237b85b-9e2a-4a17-8ceb-58d5cf98c212 |  | checkpoint | All service penetrations covered with liquid flashing
checkpoint-status | fc08ea66-1266-4431-abd5-4d96f8213392 |  | checkpoint | 50mm liquid flashing to all steel and concrete connections
checkpoint-status | 859e35f7-457d-41e8-ad09-9f48c3f2f2ae |  | checkpoint | All penetrations and damage to Vaproshield repaired
checkpoint-group | b21db042-a154-4905-a80d-a6d5a66b2be5 |  | section | Completion and Handover
checkpoint-status | be990923-f953-4bdc-bec5-79f2b659bc5e |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status | 776fb4e4-fd41-4e0b-a3a5-2d1b5c3087ad |  | checkpoint | Report sent through to client
checklist-flat | 4ee886a5-51b7-4fe9-90ae-dced41d9184f |  | checklist | Wall Strapping |  |  |  |  | Yes | Wall Strapping Checklist | fe5fd872-4195-40f7-a95e-cb2000f3eef7
checkpoint-status | 30d25b2f-c498-4147-984f-112b8c5029fa |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | 38a1f6f5-e6a2-4d2c-9c6e-522a8ee2f8ae |  | checkpoint | Area ready for Wall Strapping install
checkpoint-status | a0fc323c-0488-453c-b0d2-ca34bbb355bb |  | checkpoint | Fixings are correct
checkpoint-status | bf17f733-7047-49cf-9216-f9da6844aade |  | checkpoint | Strapping wall square, straight and level
checkpoint-status | abf547fe-0485-4828-8a2f-5e15418baf15 |  | checkpoint | Nogs / service nogs installed correctly as per plan
checkpoint-status | 5f79b912-b85b-4738-8cb0-97ba92bb8c74 |  | checkpoint | Nogging track where required
checkpoint-status | 5321f717-c1b4-45e3-90a3-2d1a29ede8cb |  | checkpoint | All Wall Strapping completed correctly within tolerance in area
checkpoint-status | 64d3dacb-be2f-4526-bac9-3a734e48b308 |  | checkpoint | Wall Strapping report sent through to client