## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a3bdf1cb-95bc-41f8-bd46-51a546ee402f |  | checklist | Steel Stud |  |  |  |  | Yes | QA - Steel Stud Checklist | 0d090b3d-5a5b-4a8e-99fc-baf36f125ceb
checkpoint-status | d660fff5-b13c-42d6-8893-47d125f31c8e |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | ea235bc8-c08a-4290-98e6-2058eedd9fc0 |  | checkpoint | Area ready for Steel Stud install
checkpoint-status | 299cf8cd-7cc3-4c46-a1d3-d3cace90b62f |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status | 97967caa-9ec6-4398-bde6-1ffc6666ace2 |  | checkpoint | All frames are square, straight and level
checkpoint-status | da3429df-fb7d-41ab-a5bf-ba121b756284 |  | checkpoint | Fixings are correct
checkpoint-status | 4a42c026-bfb2-48cd-8367-40db66011ede |  | checkpoint | Any bracing requirements installed
checkpoint-status | 9a90ee4a-618c-4b9d-be12-8687c5853651 |  | checkpoint | Fire rating elements installed as per spec
checkpoint-status | 23d8fe84-6f36-4d55-bb57-873c4767ff3e |  | checkpoint | Doors and openings installed as per plan
checkpoint-status | 8fadecf9-1017-4a8b-bb47-19ed27dee509 |  | checkpoint | Nogs / service nogs installed correctly as per plan
checkpoint-status | f94952af-4cf5-4812-aa90-c22661244473 |  | checkpoint | Any additional photos, comments and observations
checkpoint-status | ffa31904-2ab9-482b-a0c3-17864a60cff5 |  | checkpoint | All Steel Stud completed correctly within tolerance in area
checkpoint-status | 5a1fc379-7cda-4c05-9be6-447a18c099e0 |  | checkpoint | Steel Stud report sent through to client
checklist-flat | 880947ba-b8e1-43a1-9602-ade4154f3fe5 |  | checklist | In-Situ Framing |  |  |  |  | Yes | QA - In-Situ Framing Checklist for Area: | 1b968627-cdd9-4346-acbc-13566ecdc84b
checkpoint-status | d8fb3b6a-3873-4cc0-a0cf-22f83044158b |  | checkpoint | Structural Steel QA received and correct
checkpoint-status | 17b5b854-ac1e-4511-bb65-569de1eac3c2 |  | checkpoint | General information recorded / referenced
text | 76602e00-2759-4ca5-bf18-17515227c406 |  | textbox | wall type
text | d14082e1-ff44-4896-89b1-789e74c6c754 |  | textbox | thickness type
checkpoint-status | bb113111-4103-4508-844d-b5409dba312d |  | checkpoint | DPC installed, checked and correct as per specification
checkpoint-status | c94d5ed7-aa37-4d72-a9fa-58ad1bf41947 |  | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint-status | 7f6c0321-8a8e-441c-9088-3e3f8f59510f |  | checkpoint | Fixings and hold down bolts checked and correct
checkpoint-status | 3ffea6fa-1932-4edd-b355-483d7f90fe01 |  | checkpoint | All openings (doors / windows etc) checked, correct and approved
boolean | aa775b44-642f-493f-8058-721085d42d10 |  | tickbox | Deflection heads type installed and correct
checkpoint-status | abe01cca-c0cb-4609-92f6-f1af253833b8 |  | checkpoint | Wall checked (straight and plumb) and within tolerance
checkpoint-status | 0d999c1a-453e-4886-9915-032bdb2cd812 |  | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
boolean | 694ddee0-8580-4176-9b66-6a8c6f9b823b |  | tickbox | Service nogs checked and approved
boolean | fcd75488-76c8-4717-a0d5-f642cb0bd8cf |  | tickbox | All other nogs checked and approved
checkpoint-status | bee35581-7ae7-4eb4-90d6-b0fe6e61e3d2 |  | checkpoint | All Wall framing checks completed & Inspections carried out
boolean | adcfdcc4-d884-4a89-bd96-aacf4e0179b2 |  | tickbox | All above QA completed and relevant information attached
boolean | 1ab43d1d-3c38-47b1-8e02-7fc0f71ecc12 |  | tickbox | Relevant inspections completed and attached
checkpoint-status | ba6efaaa-a862-4510-8fa4-4a523929f0d7 |  | checkpoint | Report sent through to client
checklist-flat | f3159b53-ab7c-4698-82e0-66b27670d84c |  | checklist | Roof Framing |  |  |  |  | Yes | QA - Oak Battens | 1d6cf591-a513-47cb-bf84-0a11c3404cf4
checkpoint-status | 2ef35d33-7657-4c00-9e52-a0ed3f9094f3 |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status | 9a56ff5b-2416-4357-8f70-25811379a7d4 |  | checkpoint | Correct spacing between noggins/purlins in its corresponding area
checkpoint-status | 0292f653-a6bb-41e3-bbd5-1b72922e79db |  | checkpoint | Correct number of hardware and specifications according to manufacturer's detail/drawing
checkpoint-status | c6bc939e-81f2-4f0c-91ef-584f457f7df9 |  | checkpoint | Screws are aligned straight, in correct position and all defect free?
checkpoint-status | edc70952-89c6-4ea5-882d-06fc6c321567 |  | checkpoint | General photos and notes
checkpoint-status | 5d960537-cef5-475a-b760-940b33c50b72 |  | checkpoint | Straight, flush, levelled and plumb within an acceptable tolerance.
checkpoint-status | e8af05f3-5c08-41c9-9ac9-ff92c8bb9382 |  | checkpoint | Report sent through to client
checklist-flat | f24ffd0e-367b-4718-be77-880a64ea2283 |  | checklist | Weatherboard Cladding |  |  |  |  | Yes | QA - Weatherboard Cladding Checklist | 2f4c938e-75d0-4598-ba88-eeee08989dc5
checkpoint-status | 241b12a7-0570-4688-b159-db17283c24f4 |  | checkpoint | Weatherboards & all cut edges sealed prior to installation
checkpoint-status | 02e6d2e2-7e97-46a6-90e1-c4eaf5257016 |  | checkpoint | Framing Straight and plumb within tolerance
checkpoint-status | 8c9150d9-ed25-499c-9717-0a5dd0ae0774 |  | checkpoint | All nogs/ special nogs in place.
checkpoint-status | 3d7ed59a-c112-46bd-978f-961898cfa378 |  | checkpoint | Wall underlay and strapping inspected and installed correct.
checkpoint-status | bc2e521e-718b-4cd1-9214-e1e51c46a530 |  | checkpoint | All aluminium joinery Doors/Windows installed
checkpoint-status | 99bcef76-5cda-49d1-b299-61d49766b371 |  | checkpoint | Cavity batten installed at 400 centres
checkpoint-status | 404f0b99-0121-4442-8ed1-2e45412d7629 |  | checkpoint | Cavity closer installed correctly
checkpoint-status | 86c7d9ec-ce0d-413e-bddd-4919a8855a65 |  | checkpoint | Aluminium Flashings to internal/external installed as per manufacturer's drawing.
boolean | 7f4a1875-1540-49c0-819f-60a4353cf522 |  | tickbox | Head Flashings to Doors & windows installed by others
checkpoint-status | 2587a20b-034d-43cb-8a77-26f00e6c835e |  | checkpoint | Fixing Method Checked and correct as per installation manual.
checkpoint-status | 6381298e-57d2-4be2-95de-3a5efcd071b7 |  | checkpoint | All cladding installation checks completed & inspections carried out
checkpoint-status | 271a6078-eaad-43dd-95c5-3aa8a285f305 |  | checkpoint | Report sent through to client
checklist-flat | a1215858-41f9-4718-8787-d68ed562502f |  | checklist | External Timber Framing |  |  |  |  | Yes | QA - External Timber Framing Checklist | 3c784b7f-d970-4145-bdf9-696f4ccd0c22
checkpoint-status | 4f91230d-186b-4337-ba84-0a51e37b2291 |  | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
checkpoint-status | 26959c7d-cc6a-45c6-9a34-72c278e025d5 |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status | 30b8dac3-0c75-456e-af83-63a9ea650f8c |  | checkpoint | DPM installed where required
checkpoint-status | 5931fef5-f6d5-4a93-b864-215c741cc62c |  | checkpoint | All frames are square & plumb
checkpoint-status | e57fcb41-80ef-47cb-a708-582f289faf53 |  | checkpoint | External framing is installed at correct centres
text | f5fd520b-6996-42d3-9282-6d5ed48792c2 |  | textbox | Input centres
checkpoint-status | 4841cd4c-e258-4b56-a5ce-d1406e21162f |  | checkpoint | All openings are in correct location and correct size
text | 37fc134f-f51b-4faf-bb1d-7e8cb0316914 |  | textbox | Drawing / detail reference
checklist-flat | db9d0f94-e84e-49a8-a3f6-bb5213c4b826 |  | checklist | Completion and Handover |  |  |  |  | Yes | QA - Completion and Handover | 5153203f-c78b-4888-ab00-ffb7a6a01389
checkpoint-status | 2e596ecf-ffca-4ccd-ae62-c9964c401dfc |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status | ca731f29-382f-45da-b846-c5b0b3b937db |  | checkpoint | Report sent through to client
checklist-flat | fa8bbb71-7dc8-4b66-863e-a53b54e6ee43 |  | checklist | Door |  |  |  |  | Yes | QA - Doors Checklist | 73ab7460-db9a-4932-ad49-1b6088e13700
checkpoint-status | 50ae36cb-918c-44a5-bbc2-196beec1d209 |  | checkpoint | Installer details input
checkpoint-status | 24f6ba02-a751-4757-aed3-07347777ce68 |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status | 9397bc3d-3d06-4d93-8555-525e8377b9c3 |  | checkpoint | Door opening checked and correct
checkpoint-status | b10cda3e-443b-43c4-90a3-7fe08b4a3969 |  | checkpoint | Direction of door correct
checkpoint-status | 1a3615ae-175c-41f7-a2e7-3c577a391269 |  | checkpoint | Number of screws and hardware location correct
checkpoint-status | 045ad3dd-e5a0-40ac-ae72-e9c2bda6fe50 |  | checkpoint | Door hinges installed in place with correct screws
checkpoint-status | 2f40daae-fa96-48e2-a278-ccda6425a82b |  | checkpoint | Floor clearance correct
checkpoint-status | 9c9d11de-833d-41ef-a428-f220c69a19e9 |  | checkpoint | Undercoat on door surface
checkpoint-status | a0e7e54b-b4fc-4792-a919-910fcce162a1 |  | checkpoint | Fireseal around door installed as per spec
checkpoint-status | 8acefef0-653b-4624-a1c3-02480725f666 |  | checkpoint | Door is fully operational after installation
checkpoint-status | c68675b0-ecb6-407e-9975-fcf6472495de |  | checkpoint | Door jambs are plumn and level
checkpoint-status | 61102063-5bd6-4651-bf0e-9ab8bcaa9d7e |  | checkpoint | Door gap around door leaf within tolerance
checkpoint-status | 80ae7c7f-fd63-41a2-babc-5780cc5a71a8 |  | checkpoint | Door report sent through to client
checklist-flat | 478d895e-4aa9-4f93-a50e-3fe86c5d1a5b |  | checklist | Ecoply Sheet Fixing |  |  |  |  | Yes | QA - Ecoply Sheet Fixing | 74dd0742-bfb4-4936-9e28-7f22bd4aecb3
checkpoint-status | 7fc8495f-f02b-4ac4-8ea3-97fa83acbdcc |  | checkpoint | Ecoply pre cladding/RAB board to be kept dry and under cover
checkpoint-status | 5e306230-e937-4eba-a863-5ad14d8d1cd6 |  | checkpoint | Ecoply Pre-cladding/RAB board installed in accordance with Ecoply barrier installation manual
checkpoint-status | 9d9865e9-2f5f-4862-8de1-b73ee746426a |  | checkpoint | Tape installed over Ecoply pre-cladding/RaB board vertical joints, corners and openings in accordance with Ecoply Barrier installation manual
checkpoint-status | 171c35f2-88b7-4e0c-860d-10475bd698ee |  | checkpoint | uPVC horizontal flashing used at all horizontal joints
checkpoint-status | 81109c96-c7b7-4a30-b302-3a6e67292522 |  | checkpoint | Fixings: Type - Stainless Steel/Galv correct spacing
text | c5fb92df-e74f-5978-8cbd-371ba8986158 |  | textbox | size
checkpoint-status | ad7e68e0-c636-4a02-ad0b-39109c5a5433 |  | checkpoint | The panels overhang the bottom plate on a concrete slab by a maximum of 40mm as per installation manual
checkpoint-status | 9b63bcc8-6237-45a9-b8c0-7b89cc80faee |  | checkpoint | Penetrations through Ecoply pre-cladding/Rab board sealed properly using flexible flashing tape as per E2/AS1
checkpoint-status | 7a67e3b7-ce69-498d-b945-72a11c522759 |  | checkpoint | Fix Watergate Plus underlay with printed side facing the exterior and run horizontally.
checkpoint-status | 949e3b90-c54f-4892-9a02-7f45f9047e25 |  | checkpoint | Fix securely to the frame, with staples at 300 mm centres horizontally and vertically
checkpoint-status | a40527fb-36e9-4aa5-b274-6e646df007c4 |  | checkpoint | Minimum of 150mm lap is required at joins.
checkpoint-status | 56c9f578-86f7-40d1-a980-e06e7f39f926 |  | checkpoint | All vertical laps must be made over studs.
checkpoint-status | 576ce9dd-e57f-4173-9e26-6c3b5875b5f1 |  | checkpoint | Repair small damages, if any.
checkpoint-status | ba076d0e-a06f-441f-bb2b-7ff9f2d90126 |  | checkpoint | Report sent to client
checklist-flat | ed3fbda6-d55a-4498-bc8e-1f00440ebf4b |  | checklist | Soffit Framing |  |  |  |  | Yes | QA - Soffit Framing | 9cadbd7b-78dd-4fd3-a44c-be4abc0ee044
checkpoint-status | aaedba35-c340-48ec-adda-78d695adaeaf |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 88b777b5-87d6-4a96-9526-ef6975a5dc41 |  | checkpoint | Area ready for Soffit Framing and Villaboard install
checkpoint-status | abf279ab-f87a-43ee-a68b-e5698493b24f |  | checkpoint | Correct product & fixings delivered, reviewed and approved as per specification
checkpoint-status | 92cbda72-c19f-42ef-9acf-de0725e687dc |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status | 5662a876-8150-4fdd-92ae-750298346803 |  | checkpoint | DPM installed where required
checkpoint-status | 9a1eef3c-1167-486f-974d-4c4699c6a380 |  | checkpoint | All frames are square & plumb
checkpoint-status | 24294fc8-9489-4ded-8c57-4a6db2d41a4e |  | checkpoint | Soffit framing is installed at correct centres
checkpoint-status | e8da1e3d-7386-4b9c-8a1e-0bc159b5204f |  | checkpoint | Soffit framing report sent through to client
checklist-flat | 966b7476-9eb7-498c-94af-009870c68568 |  | checklist | Villaboard Install |  |  |  |  | Yes | QA - Villaboard Install | b3ea610c-58e5-4c19-95a7-72bc657f94b7
checkpoint-status | 6239867b-4ecc-46dc-bf86-dce511e536d3 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | a870d562-4407-464c-8ec8-beba57cafcbd |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | ff4ea2e0-3f68-4762-b863-d96d47566d6e |  | checkpoint | All lining completed, checked and approved as per specification
checkpoint-status | 7f217a23-5c57-4f79-9c49-76a681a268d7 |  | checkpoint | Correct stopping product and applied correctly to Villaboard walls to L4 finish
checkpoint-status | d2751379-361c-421f-b53e-ae5b2c30d34c |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status | 029c00e2-8739-4487-83f4-0dc6c665125e |  | checkpoint | All sanding completed as required
checkpoint-status | 1e17f728-bfd1-4264-8611-1546701c8b74 |  | checkpoint | Soffit Framing and Villaboard completed correctly within specified tolerance, checked and approved
checkpoint-status | d03a0f5e-1093-4af2-b720-98dab792d1b9 |  | checkpoint | Villaboard report sent through to client
checklist-flat | 45d1bc4d-d35a-4f07-ad26-f1c8c38131c9 |  | checklist | Ceiling Grid |  |  |  |  | Yes | QA - Ceiling Grid Checklist | fafd103a-5057-42e7-8c61-795b415c24e3
checkpoint-status | b2cb5333-4a51-4919-a392-8806cd50440a |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | a53442d5-064b-428b-9e4c-8f5ed9c6b6b5 |  | checkpoint | Substrate correct (nogging installed if required)
checkpoint-status | a527e3ae-cff9-4a9e-abf6-f894ea530aeb |  | checkpoint | Ceiling Grid installed level and to correct heights
checkpoint-status | 041ceb0f-6ee0-4b11-9d63-253bca1604ab |  | checkpoint | Correct fixings and number of fixings
checkpoint-status | e6562bec-2d77-4bd1-8c85-0df79b15e2b3 |  | checkpoint | Member centres correct
checkpoint-status | af8002da-af7a-4f63-9bfe-c15933940849 |  | checkpoint | Correct Clips installed
checkpoint-status | f3f2ede3-2d96-4f02-942b-9cacb0e001b7 |  | checkpoint | Earth strap installed
checkpoint-status | 41e2d170-0717-49e5-b9a9-7cf955754816 |  | checkpoint | Hatches openings trimmed out and installed
checkpoint-status | 966dc7e9-f030-4992-b0c3-b723c82c9a2b |  | checkpoint | Bulkheads installed plumb/level/square
checkpoint-status | c94989d3-dbc1-485f-a708-a632ba1907db |  | checkpoint | Ceiling Grid completed correctly, checked & reviewed - as per specification
checkpoint-status | f3926a30-03b9-41d8-9f28-6be82c6172a1 |  | checkpoint | Area left clean & tidy
checkpoint-status | c4d2ce85-e8fe-4cb7-b6dd-8c40e8dc0afd |  | checkpoint | Ceiling Grid report sent through to client