## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | Stage 03 - CST - S - Completion Documents | 2f7646da-d9f5-4f42-a8aa-c47cccef3486
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | c48e0723-1539-5cac-93d3-bf5be716aba0 |  | button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached | Yes,No
label | 1a10a07a-9814-5646-97d8-bc32979b0091 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 37b69cbc-04be-44fa-ae7b-6c21d53b9ad4
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 924e8201-c7e5-4bcc-bebc-b9615c0a5ffc |  | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes,N/A
button | 74a098fa-1d2c-4f01-bed9-33b1f6f447a4 |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes,N/A
label | ba35ce2f-2ee6-4a10-b0de-d2f804e43d38 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Brick Installation - |  |  |  |  | Yes | SYS - QA - Brick Installation (V1) | 4fedb603-d63c-4ba4-be1c-a689867157fd
checkpoint-status |  |  | checkpoint | Correct drawing revision checked and accurate
text | 5f01c3d7-8918-46c2-a1fe-d95a211ede75 |  | textbox | Drawing number(s) & Revisions
checkpoint-status |  |  | checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
button | 18724b5c-bcb5-4024-a987-a4a965f7cc02 |  | button | Area Accessible | Yes, No
button | 01098b0a-c20c-4b48-b108-54bdc1c5f95e |  | button | Substrate acceptable | Yes, No
button | 2eb543c6-2c30-44e0-bc21-8ca4856237bb |  | button | Permission from Ryman obtained to begin work | Yes, No
checkpoint-status |  |  | checkpoint | Ground clearance correct to specification
checkpoint-status |  |  | checkpoint | Lintel bars installed correctly (2-3 photos uploaded)
checkpoint-status |  |  | checkpoint | Shelf angles (installed by others) installed and flashed correctly (2-3 photos uploaded)
checkpoint-status |  |  | checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc) (2-3 photos uploaded)
checkpoint-status |  |  | checkpoint | Weep holes installed correctly (2-3 Photos uploaded)
checkpoint-status |  |  | checkpoint | Control joints installed correctly (2-3 photos uploaded)
checkpoint-status |  |  | checkpoint | Mortar Joints installed within tolerances (7-13mm) (2-3 photos uploaded)
checkpoint-status |  |  | checkpoint | Cavity is correctly formed and free of obstructions (2-3 Photos uploaded)
checkpoint-status |  |  | checkpoint | Brick overhang foundation within tolerances (no more than 20mm)
checkpoint-status |  |  | checkpoint | All photos uploaded and any additional observations recorded
checkpoint-status |  |  | checkpoint | Area is left clean and tidy (2-3 Photos uploaded)
button | a8407cb1-0695-430a-8c57-0faed8c7f595 |  | button | Any remedial work completed and work completed to satisfactory level | Yes, N/A
checkpoint-status |  |  | checkpoint | Brickwork completed, reviewed and approved for this area
holdpoint |  |  | signoff | Request signoff
checklist-sectioned |  |  | checklist | FC - S - Brick Works |  |  |  |  | Yes | FC - S - Brick Works | 564cb96d-304e-4d04-bba4-54b9ac655dce
checkpoint-group |  |  | section | Preinstall checks
checkpoint-status |  |  | checkpoint | Area accessible, substrate acceptable & approval to start works - Consider services, cavity & waterproofing requirements prior to install
checkpoint-status |  |  | checkpoint | Ground clearance correct to specification
checkpoint-status |  |  | checkpoint | Grids/Wall marked for reference. RL reference/TOW confirmed. Base/Concrete/footing clean, tidy and level ready for first coarse.
checkpoint-group |  |  | section | Brick installation
checkpoint-status |  |  | checkpoint | Base of wall starting correct location - Brick base overhang within tolerances (no more than 20mm)
checkpoint-status |  |  | checkpoint | Control joints installed correctly
checkpoint-status |  |  | checkpoint | Weep holes installed correctly - Consider setout & size
checkpoint-status |  |  | checkpoint | Mortar Joints installed within tolerances (7-13mm)
checkpoint-status |  |  | checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc)
checkpoint-status |  |  | checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checkpoint-status |  |  | checkpoint | All relevant flashings and waterproofing/taping completed as required - If Applicable
checkpoint-status |  |  | checkpoint | Caulking completed (correct colour) and satisfactory finish achieved
checkpoint-status |  |  | checkpoint | Brick cavity is correctly formed and free of obstructions
checkpoint-status |  |  | checkpoint | Brickwork completed to required specification. All brickwork washed/clean & area left clean & tidy - Wall built within tolerance - straight, level and to the correct height and colour
checklist-flat |  |  | checklist | Completion Documents |  |  |  |  | Yes | SYS - Completion Documentation Checklist (V1) | 92af5be5-ca08-4242-8084-a52ac808cf30
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | c9093122-bccf-4892-9d7f-7ee677a3e6fe |  | button | PS3 Completed and attached | YES, N/A
button | ae2870d5-be5a-4b6e-8b2b-c0a17ef8a169 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | YES, N/A
button | 9c1ca3a3-46a1-4b2f-9b9b-68b6b7131400 |  | button | Any Additional Compliance Documentation - Completed and Attached | YES, N/A
label | 315f6226-f67b-4b75-8bac-92233563bdc7 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff