## Breakdown
Lincoln Road
Building B06
Structure
Concrete Pour
|  |  |  | ability to add | Concrete Pour
Building B07
Structure
Concrete Pour
|  |  |  | ability to add | Concrete Pour
Building B08
Structure
Concrete Pour
|  |  |  | ability to add | Concrete Pour
Building B09
Structure
Concrete Pour
|  |  |  | ability to add | Concrete Pour
Building B10
Structure
Concrete Pour
|  |  |  | ability to add | Concrete Pour
Building B11
Structure
Concrete Pour
|  |  |  | ability to add | Concrete Pour
Building B12
Structure
Concrete Pour
|  |  |  | ability to add | Concrete Pour

## Checklist
Type | Name
checklist | Concrete Pour
section | Pour Details
checkpoint | Pour details entered
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Reinforcing
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
bool | Appointment with the engineers confirmed (Enter date & time of the appointment)
bool | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Welding certificates sited and attached
checkpoint | Mill certificate reviewed, attached and approved
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
section | Pre-Pour Completion (Approval to pour)
checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Ryman inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
checkpoint | Concrete Supplier details entered
text | Supplier Name:
text | Specified concrete strength: | mPA
text | Concrete strength ordered: | mPA
text | Concrete quantity ordered: | m3
button | Test blocks booked | Yes, No, N/A
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification | Yes, No, N/A
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
holdpoint | Raise remedial/ Request Signoff
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS