## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV Landscaping - Ground Preparation
ITP Description: |  | Landscaping - Ground Preparation
Document Number (in Teambinder):
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date:
ITP created by: |  | Bunni
ITP approved for use by: |  | Josie Pavlou
Special Notes to ConQA Team :
Inspection & Test Plan - Landscaping - Ground Preparation (Subcontractor)
[9 empty] | Revision: | 0
Date:
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
VicRoads 720 AS 4454 AS 4419 IFC Drawings Sub Contractor ITP
1 | Preliminaries
1.1 | Check for correct documentation | Drawings and drawing registers | Ensure that all employees and subcontractors are: - Using the correct and complete set of IFC drawings - All drawings are the latest revision | Document Review | Prior to Commencement of works | IP | SE | Sign ITP
1.2 | Submission and records | Section 720.03 | Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery. Following information shall be provided to the NA: Samples -Mulch -Imported topsoil Records -Details of suppliers -Soil tests on imported topsoil -Copies/Photos of fertiliser labels | Document Review | Prior to Commencement of works | HP | SE, NA | Issue to TeamBinder Attach: Records & certificates
1.3 | Supply of topsoil | Section 720.04 Table 720.042 IFC Drawings | Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor. Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings . | Verify, Doc. Review if applicable | Prior to Commencement of works | IP | SE | Sign ITP Attach material conformance docs/Test Report
1.4 | Supply of Mulch | Section 720.04 Table 720.044 AS4454 IFC Drawings | Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings. All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings . Imported Wood Mulch shall comply with Table 720.044. | Verify, Doc. Review if applicable | Prior to Commencement of works | IP | SE | Sign ITP Attach material conformance docs (if applicable)
2 | Site Preparation
2.1 | Subcontractor ITP | Subcontractor ITP | Subcontractor ITP to be reviewed and approved by MRPA. | Document Review | Each Lot | WP | SE/PE | Sign ITP Attach completed Subcontractor ITP
2.2 | Soil Additives | Section 720.07 a) AS 4419 | Refer to Subcontractor ITP | Document Review | Each Lot | IP | SE | Sign ITP Attach Test Report Attached Delivery Docket (if applicable)
2.3 | Ripping of subsoil | Section 720.07 Table 720.071 | Refer to Subcontractor ITP. Do not proceed until the NA inspects and acknowledges requirements for ripping have been met. | Verify | Each Applicable Lot | HP | SE, NA | Sign ITP Attach Lot Map/Marked Up Area Inspected
2.4 | Topsoil application | Section 720.07 | Site topsoil shall be used wherever possible, in preference to imported topsoil. Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in table 720.071. Situation • Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum • Planting Areas in disturbed areas steeper than 3h:1v = 100mm Minimum • Grassing in disturbed areas =75 mm, except 100 mm in swales • Individual Tree Planting within grassed areas =150 mm in disturbed grassed areas Topsoil shall be spread on planting areas and grassed areas. Note: Topsoil shall not be compacted. | Verify | Each Applicable Lot | IP | SE/Site Supervisor | Sign ITP Attach Delivery Dockets if applicable
2.6 | Topsoil FSL - Topsoilling and Cultivation | Section 720.07 | Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met | Verify | Each Applicable Lot | HP | SE, NA | Sign ITP Attach Lot Map/Marked Up Area Inspected
2.8 | Mulching | Section 720.08 a) IFC Drawings | Refer to Subcontractor ITP | Verify | Each Applicable Lot | IP | SE, Site Supervisor | Sign ITP Attach Delivery Dockets
2.7 | Weed and Erosion Control Mat | Section 720.04 i) IFC Drawings | Refer to Subcontractor ITP | Verify | Each Applicable Lot | IP | SE, Site Supervisor | Sign ITP Reference TeamBinder Material Approval No. if applicable Attach Delivery Dockets
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /