## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV Landscaping - Planting
ITP Description: |  | Landscaping - Planting
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2022-07-07
ITP created by: |  | Anthony Pearson
ITP approved for use by: |  | Josie Pavlou
Special Notes to ConQA Team : |  | All sites
Inspection & Test Plan - Landscaping - Planting
[9 empty] | Revision: | 0
[9 empty] | Date: | 2022-07-07
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
IFC Drawings
Vic Roads Section 720 (Nov '18)
2 | Preliminaries
2.1 | Check for correct documentation | Drawings and Drawing Register | Ensure that all employees and subcontractors are using: -The correct and complete set of drawings -All drawings are the latest revision | Document Review | Prior to Commencing works | N/A | SE | This ITP
2.2 | Submission and records | VicRoads Spec. - Cl.720.03 | Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery. Following information shall be provided to the superintendent: Inspections of plant stock for all plant species Records: -Evidence of origin of indigenous provenance plant material -Analysis certificates for grass seed -Details of suppliers -Copies/Photos of fertiliser labels | Document Review | Prior to Commencing works | HP | SE,Superintendent | This ITP Attach Records to TeamBinder Approval Form |  |  | Insert Text Box called "Team Binder Approval Number"
2.3 | Supply of Plant Stock | VicRoads Spec. - Cl.720.04 - Table 720.041 | All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans. - Plants are to conform to the supply properties specified in Table 720.041 | Verify | Prior to Commencing works | N/A | SE | This ITP
2.4 | Supply of indigenous plant stock | VicRoads Spec. - Cl.720.04 | A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750). - The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot: - species name - storage code - collection locality - Latitude/longitude or AMG - approximate number of parent plants sampled - approximate number of plants in that local population | Verify | Prior to Commencing works | N/A | SE | This ITP
2.5 | Supply of grass seed | VicRoads Spec. - Cl.720.04 - Table 720.045 | Grass seed shall comply with Table 720.045 | Verify | Prior to Commencing works | N/A | SE | This ITP
3 | Pre-Construction Activities
3.1 | Planting Section Approval | VicRoads Spec. - Cl.720.06 -ECO-LANF-005 | Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works | Verify | Once | HP | SE | This ITP
3.2 | Pest and Weed Control | - Cl.720.05 | The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations. Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. | Verify | Once | HP* | SE | This ITP
3.3 | Setting out planting areas | VicRoads Spec. - Cl.720.06 | Planting areas are to be set out to the location and shape specified in the landscape drawings. - Plant density requiremens and planting offsets established in the plant schedule are to be adhered to. - Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements. | Verify | Each Applicable Lot | N/A | SE | This ITP
4 | Construction
4.1 | Planting | VicRoads Spec. - Cl.720.09 - ECO-LANF-005 | All planting will be undertaken in accordance to Ecodynamics ITP ECO-LANF-005 | Verify | Each Applicable Lot | NA | SE,Foreman | This ITP
5 | Completion
4.1 | Site Final Inspection | ECO-LANF-5 | Ecodynamics ITP signed and completed | Document review & Site Inspection | Following completion of planting works | N/A | SE | Sub-Contractor ITP completed, signed and to be attached
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /