## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 | 90fd026a-4c64-4e08-b179-4e07a69a3cc8
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | e7e4fdfe-a478-5afb-a3a9-729a63fc5473 |  | note | Document Title: ITP-CIV-CAMMS-Type A Fill - Road (Supply and Install)
label | 9e73d38f-9819-5b30-988a-d79299e95025 |  | note | ITP Description: CAMMS-Type A Fill - Road (Supply and Install)
label | 0b3afb1b-393e-5b9b-a3bc-6dd166f314fb |  | note | Discipline (e.g. CIV/STR/RAIL: CIV-CAMMS-
label | f5413fe2-9b93-5989-ad8a-c9bccf6ee2f6 |  | note | Revision Number: 0
label | 92eb597a-497f-5ba7-ba72-feaf482b0e6e |  | note | Revision Date: 17/08/22
label | 33b1437a-fbb2-5e4e-8924-ca677daf4be2 |  | note | ITP created by: Victor Mira
label | 97628c48-0e71-502e-be5f-a7927e48cc03 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | c5650e7c-a5f6-5959-999d-6bc15c6f8df2 |  | note | Reference - IFC Drawings
label | aa556724-809a-5e21-8b5d-ba9d99e0af14 |  | note | VicRoads Standard Section 176 (Sept 2008)
label | 44340d97-29c4-57d6-8d80-42c7fd4520fa |  | note | VicRoads Section
label | e12ab6af-9718-52b5-a274-7fd6324d998c |  | note | 204 (Dec 2015)
label | c9581045-364f-5f57-b07b-c8dc941e9839 |  | note | Code of Practice RC500.20
label | 305c1bd1-f6c3-5178-8119-818ef511053d |  | note | Code of Practice RC500.5
checkpoint-group |  |  | section | 2 - Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | dddf0f28-08b4-5d2e-9802-430d38771541 |  | note | Reference - Section 204.04 b)
label | 87b408bf-836a-55d3-9637-3ee57d6fb3f0 |  | note | Table 204.041
label | 70776731-bc57-5328-adb3-5a099893bf9a |  | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 4e59a56c-c73f-5681-b62e-eea0ba94be01 |  | note | • Assigned CBR≥%8%
label | 29b3aa13-c3b4-5f5d-9357-98393d450674 |  | note | • Swell ≤ 1.5%
label | 09131a96-ddde-5e84-ba3b-e1e067120929 |  | note | • Permeability ≤ 5X10-9 m/s
label | a00738f3-b024-50d4-9980-3ff947b0dc4f |  | note | Grading:
label | 87f16108-3d73-5d86-8a04-1016ca70b4a4 |  | note | • 75.0mm 100%
label | 4768fbd1-9b8b-5a49-a40c-f891abfa52da |  | note | • 4.75mm 40-80%
label | 42543cc8-46e6-5e55-b752-433cafae155f |  | note | • 0.075mm 10-40%
label | 07fd9c59-3eef-54eb-9c1c-586d383749af |  | note | Reference: Material approval in Teambinder:
label | 6946c15c-7584-554e-aeee-dac30e9d0ceb |  | note | Method - Document Review
label | 563815ea-df6d-544e-b38a-7251a84d6cd7 |  | note | Frequency - Once, for each material type
label | 5dc8df66-63e0-5c78-a0aa-dbafffe5d5ba |  | note | Category - HP
label | 726b0f4b-e824-5b7a-b383-4f559fe4ba5f |  | note | Responsibility - SE/Nominated Authority
label | 15989061-9ea3-502a-b52e-89abcd1b9698 |  | note | Verifying Documents - Supplier Material Conformance Certificate
text | 402c925d-d121-5368-94bc-20a02d51aab8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Pre-Commencement of Fill Works
label | 2075881f-ae99-557c-93fc-57c47d98fd0a |  | note | Reference - Section 204.10 (b)
label | 14735cc8-7556-58f5-aced-4f28973b194b |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | c9f89d61-3859-5a63-b040-567eb9c5df4f |  | note | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | 44673574-1bdc-5f5f-abcd-6a32c5759b13 |  | note | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | 0785f514-fbde-5815-b0ad-330f4ba8bbe4 |  | note | Reference: Subgrade Preparation Lot Number:
label | 053c2715-5602-5407-ab07-dd6088289371 |  | note | Method - Visual Inspection
label | 36e8bf8b-0d9b-5fd9-bffd-3ad2fe700240 |  | note | Frequency - Prior to commencement of fill works
label | cdcb542c-4680-545b-841f-35aa18104834 |  | note | Category - HP
text | bef2c1db-6192-5e99-9f1a-b5a4fc9e4d4c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set Out
label | 4fc99d8d-7b0d-50a8-8540-ebf9a97611c8 |  | note | Reference - Design Drawings
label | a1623c43-5598-5ab4-b990-d6ddbe643757 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | bf7b4caf-7cf7-53aa-b575-ca6448fb255d |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | ade72ccb-de6b-5246-a6dd-ccad56db8b54 |  | note | Method - Visual Inspection
label | 50b426ae-d80d-52dd-91ca-2505a5e7db16 |  | note | Frequency - Each lot prior to commencement
label | 967fe583-64d2-5e0d-9af7-7af83d547da1 |  | note | Category - HP*
label | 6ba3d566-2c89-5014-9ee3-53bd5bc41147 |  | note | Responsibility - PE
label | 62915aef-a289-5484-b262-a4a5f5fb6c0b |  | note | Verifying Documents - Signed ITP, Lot Map
text | 3a84f474-626c-5d31-97a2-1c07676c71ea |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 4.1 - Placing of Fill
label | d0001295-d96d-59b9-8e64-30d4542cd3d3 |  | note | Reference - Section 204.10
label | 4d6b9732-89a1-5948-a733-c71aa4ed28b8 |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | a1cecc29-97f5-55dd-b54d-e5aad03fbcb4 |  | note | Method - Visual
label | 697e76ec-c472-5400-92fe-c8503049c351 |  | note | Frequency - Each Lot
label | 4e2236e4-f533-53d1-9145-d636b9912c4b |  | note | Category - WP
label | d302121e-6b66-5378-b652-2f2a46dac28a |  | note | Responsibility - SE/Site Supervisor
label | ddbb7ce5-cebf-5fc7-800c-9b8515e38ff2 |  | note | Verifying Documents - Sign ITP
text | 58cfe9bb-6661-566d-b0d2-5778e66a0681 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Test Roll
label | c0c55aa6-87da-5c9e-8129-b71917c4b44e |  | note | Reference - Section 173.03
label | 5d704c0e-1188-5252-8687-ad82ed96e9db |  | note | Section 204.12
label | 15bfa329-9e55-5178-85d9-db340f00dce1 |  | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 8d72d4a0-ed8a-5c74-be44-0d207be7f018 |  | note | Method - Test Roll as per 173.03
label | 53826049-5b26-5716-8389-4b17bfb98a1b |  | note | Frequency - Each Lot/Layer
label | 32febaef-c8f8-57e7-bdb0-025d8478ef4a |  | note | Category - HP
label | df2d8bdf-c42b-5046-8101-cd3f1dc5caca |  | note | Responsibility - SE/Nominated Authority
label | b0e140e4-54d6-5cec-b733-b324ab07c5e1 |  | note | Verifying Documents - Sign ITP
text | 25de03fe-1f0f-5ced-8194-3a559febf498 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Compaction Testing
label | c566438c-3cd2-59b1-b770-954ac4fc46b7 |  | note | Reference - Table 204.131
label | 1a3d54f0-0b38-54ea-949b-9593a37856dd |  | note | Section 204.14 c)
label | c410df34-f8e1-5cf5-9c73-0f934115549a |  | note | Table 204.142
label | 7cc8fb63-cb4f-544f-905e-0f82446d4203 |  | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | 701b0571-1436-5cd3-bf5c-a8ed0f92d184 |  | note | • Standard Compactive Effort
label | 59b37a54-d3f5-5af6-b4c9-dd0a591de0ac |  | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | 359c569c-886c-5a20-a742-e8d187bef62d |  | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | b635ddd9-8430-559c-a1e8-31e344ae6978 |  | note | • Compaction and Moisture content
label | 88f03fbd-c2d6-5dca-b29e-c3fa1b5e80af |  | note | – Scale A: Characteristic Density Ratio 99%.
label | aeb7ef52-1009-5185-a692-4decff07868f |  | note | – Scale B: Characteristic Density Ratio 98%.
label | 443814b0-0391-5a49-b66f-827756d4b6a3 |  | note | – Scale C: Mean Value of Density Ratio: 100%
label | 5316585c-dfcc-53b5-9be8-b0d9399218c2 |  | note | • Lot size - the leser of one day's production or 5,000sqm
label | 45dec188-07e3-5bf9-b84b-7f2c203225b3 |  | note | ATTACH: COMPACTION TEST RESULTS
label | 144bc1a9-dbe3-57b5-9f75-649257648c7f |  | note | Method - Review Document
label | 6f2b6041-ee55-5c8e-98c4-7a99e2586a14 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 7eec6a9b-a2ae-5111-8f0e-f41c8c33581d |  | note | Category - IP
label | 9b527538-3c23-57b1-93bb-17241ffac15a |  | note | Responsibility - SE/Site Supervisor
label | d8eba684-7ef7-5a0a-82c6-2f1f5605d726 |  | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
text | 66907998-7a0f-531b-aebb-d9bb3ab491cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Preparation of final surface
label | 58977434-ece0-5592-a4fa-3760221e73ce |  | note | Reference - Section 204.15, 204.03 (g)
label | bdb5ee51-dc35-515c-865d-74e610498296 |  | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | a8d54c99-5bdd-5c41-948c-dea686cf2786 |  | note | Method - Measure
label | ba89485c-07c0-5bba-954a-df765c5071c7 |  | note | Frequency - Top layer
label | cb291918-5f37-5da1-a1d1-ae5a14e25d1c |  | note | Category - IP
label | b7c04537-379e-5fe0-9333-61edc20619b0 |  | note | Verifying Documents - Signed ITP
text | f77aae0e-3e41-59f3-9901-18d6b17f2e71 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Post Compaction Material Property Testing
label | 34a7961d-3294-5dec-abc1-ec1c03cb8814 |  | note | Reference - Table 204,041
label | 6c18fc43-064a-5a36-adef-049c2d703a6d |  | note | Table 204.141
label | d786f21c-e22e-59df-87e4-39fda664d597 |  | note | Section 204.14 a) or b)
label | 6fa8f4f8-aad4-50b1-8370-419a31b539c6 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 60e09ea3-91c9-5ec2-9adb-9cd1a02aaaac |  | note | ○ CBR ≥ 3% and Swell ≤ 1.5%
label | 17c4388b-9fcf-5226-bf10-43880ca14fc6 |  | note | ○ Max Permeability = 5X10-9 m/s
label | 947bde13-8b11-5cee-a04e-3f585d0e80f8 |  | note | ○ Grading:
label | 780b08f8-1ae6-5781-aa8b-35ec954f7783 |  | note | – 75.0mm 100%
label | 4aa329d7-0b8e-56d1-9181-d5f33da1903d |  | note | – 4.75mm 40-80%
label | 1c0c92d2-a55a-5080-abae-11a70afc0436 |  | note | – 0.075mm 10-40%
label | 0b9499c5-28d8-532b-8724-7660e44c3e67 |  | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 88efc5ef-586a-52de-8d6b-cc09fe086bc4 |  | note
label | 1fd0d82c-5b2a-52b5-97a0-a31fc71030e4 |  | note | • Scale A:
label | 4a34eb19-3169-5fcc-9093-299a2ee3d91e |  | note | ○ CBR & Swell
label | 36984490-f168-530d-8f3a-745ac01d4b7c |  | note | – Initial - 1 Lot Test to determine Assigned CBR and swell
label | fed783d4-a511-501d-b717-7a5538d7f41d |  | note | – Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | f180c066-ec31-5c33-81e2-0c2cbe8e3235 |  | note | ○ Max Permeability
label | e01a4ccb-f576-59f2-ac58-bea48b7a632e |  | note | – Initial - 1 test per 2 lots
label | c9e282c0-c0f0-5868-af76-c2c749e60557 |  | note | – Reduced - 1 test per 4 lots
label | 0c9179de-1ed8-532e-8298-addcefb557af |  | note | ○ Grading:
label | 60cde34c-a720-5e35-9b9f-9e9fefd3ed5f |  | note | – Initial - 1 test for each lot tested for compaction
label | fc11c122-c287-5568-b283-31ab0f9e771d |  | note | – Reduced - 1 test for every second lot tested for compaction
label | 5e33193b-47ad-5b04-8968-9cb4bff4b8b6 |  | note | ○ Max. PI x%Passing 0.425mm & PI
label | 9ce04ad2-3efd-5dec-a897-0ef5bc40d3f0 |  | note | – Initial - 1 test per 2 lots
label | bd8e5ec4-a545-5f60-9bfa-4fe2766232c1 |  | note | – Reduced - 1 test per 4 lots
label | 814419e6-1b01-56f9-88e8-cb859b90b78c |  | note
label | d59af88d-994c-5920-b445-1c93892d1768 |  | note | • Scale B:
label | 728fb80b-2c0e-5e2f-a18b-54b902b28c0b |  | note | ○ 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 53d88e6a-38ae-5f5f-91d0-91925e0817d9 |  | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 76883f0f-c067-51ec-9bdb-f61fdda2fddf |  | note | Attach: Post compaction test results:
label | 3287eb02-c83d-5639-82a8-6253abbe4bc9 |  | note | Method - Review Document
label | 29ca5a3b-3721-59a9-8b87-3c7f41ed678c |  | note | Frequency - Refer to Section 204
label | 9dc09707-92ce-5d5b-a080-2187870c1b05 |  | note | Category - IP
label | 0d19ad8f-ce63-547a-b518-fd4ff817093e |  | note | Responsibility - SE/Site Supervisor
label | 052df6a8-b797-51e9-b92f-0080359caf69 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | 6f3f0708-7322-53e0-b004-1079eaf55a69 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Survey Conformance
label | 165514d8-f1f7-5394-be35-0e6e251efce0 |  | note | Reference - VicRoads 204.03f,g and h
label | 9f3a512d-e8ff-5931-b3bc-69370c7f7c07 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | e68031a8-3400-57aa-83fa-5e841cd83a8b |  | note | • Level tolerances Scale A:
label | 0ce0af05-2e4d-5f71-a8ae-3801ae5e1b50 |  | note | ○ Range x = +5, -15mm
label | 3c382156-8cf6-5044-80ad-beb7c069372c |  | note | ○ Max S = 12 mm
label | 04133c7b-5892-5a9f-92c7-edcc4e18f963 |  | note | ○ 80 measurements per lot
label | 166f792f-0e7f-5df8-b1e0-57432948e7fd |  | note
label | ec0f0319-c1c6-51b9-94f8-fca642d05330 |  | note | • Level tolerances Scale B:
label | bb6d9daf-64f4-5aea-a824-e4db87c861f1 |  | note | ○ Range x = +5, -25mm
label | 2e3c7899-23fa-5f23-8785-07ec803cf4ab |  | note | ○ Max S = 15 mm
label | fab92276-0a78-5f63-b73f-03f40355a7f9 |  | note | ○ 40 measurements per lot
label | b2e83e56-c09e-5ea7-a3fc-d6efcb3464b5 |  | note
label | 7926e481-264d-5ef8-8f4b-cefe9f116887 |  | note | • Level tolerances Scale C:
label | 7fcf0148-d17f-5662-99b7-d2f9f7e19e24 |  | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 50af3965-12a1-5d7a-a5c5-b78c63a8603e |  | note | Method - Document Review
label | 3d76b1a7-f0a7-527c-88f2-83adee2450bd |  | note | Frequency - Top of Type A/Verge
label | cc501ea0-0db9-57dc-a63b-6cf08fd8988a |  | note | Category - IP
label | a852e29c-fb32-5740-986e-f6edcf4dab4e |  | note | Responsibility - Surveyor, SE/PE/SPE
label | b11b7585-d3d2-50d4-9e8c-24557133f577 |  | note | Verifying Documents - This ITP, Survey Conformance Report
text | 11394e80-218e-5047-a6f9-82ae5b93a5dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Non-conformance Report (NCR) Closure
label | 06185624-6a1c-5515-bcef-38aa1110a7db |  | note | Reference - MRPA Quality Management Plan
label | e57697ef-92e0-5f7d-ad4b-aae3fee3a434 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 417a084c-1920-5316-92ba-fac8526dfac9 |  | note | Method - Document Review
label | e3ce9f02-925e-52e8-9b1c-cccbaacf3fff |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 0352f1d2-8fdf-5b59-afc6-2d2f7cb982f4 |  | note | Category - HP*
label | f82bcc47-b614-5700-9e60-ad623319f333 |  | note | Responsibility - SE/PE/SPE
label | 05a989d8-8d2b-5bdd-8805-61543d247e7b |  | note | Verifying Documents - This ITP
text | ca59115a-2de6-593c-bb4a-4d3d2a5567a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 15261719-c152-530a-8317-155275e31357 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8a525da3-36a7-5a2a-9a8a-b3142adb89ac |  | textbox | Print Name:
text | 4ce3fcb3-c2f4-536c-a16e-320f15350507 |  | textbox | Position:
text | 82ed4162-a996-5510-b9f8-c30bdc103671 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 | ab7ef30d-9104-43f1-81a8-85781b69b393
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1 - Referenced Documentation
label | a26e48ca-b62c-51ca-8723-7ab126cffe3e |  | note | Document Title: Ausnet Conduit Bore
label | 30c8b4d5-4fe9-5295-adc4-47450294b45c |  | note | ITP Description: Ausnet Conduit Bore
label | 9c308e30-e4b0-5a8d-b7af-3b006641a8d9 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 91b37566-1552-5d58-8638-cde75f95933b |  | note | Revision Number: 0
label | e41ffb9f-bd40-5eaf-ba98-7acedefbf593 |  | note | Revision Date: 29/07/22
label | dda31d16-1b1e-5b22-85cc-2f96ce9ce57c |  | note | ITP created by: Michelle Lim
label | 99dbeb7e-3aeb-50ef-90d3-381b7810fa29 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | bc9916e0-20c6-59a2-87b6-1615ffd8efdd |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependant
label | 0b9f5de9-b824-5e8e-9daa-e5f959b24395 |  | note | Reference - AS 4799-2000
checkpoint-group |  |  | section | Preliminary Works/ Materials
checkpoint-status |  |  | checkpoint | 2.1 - Electrical Conduits
label | 2343d2fe-2fbf-58f3-a170-3631321a40fc |  | note | Reference - IFC drawings
label | da2bd1ba-c775-5868-a730-b8caf76a41de |  | note | Acceptance Criteria - Conduit crossing railway to be heavy duty PVC 150mm Id/180mm OD Grade PE100, SDR 13.6
text | 6964125a-a17b-57b2-84af-b8d4d02f7345 |  | textbox | Reference:TeamBinder Material Approval Number:
label | 29590f1f-f2bc-5bde-b12d-3a36f06a6472 |  | note | Method - Document Review
label | e6b2bc50-f99b-5912-8303-16252bef7a44 |  | note | Frequency - Prior to commencement
label | fd5d8759-b47e-5c94-b6f8-58e28e24d3ae |  | note | Category - HP
text | 92bc40ef-ca10-5d7b-b318-4b26bb007cf8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Grout
label | 75c1fa61-6377-5e69-8af8-4659f9163703 |  | note | Reference - IFC drawings
label | 91bc332c-dd2d-5b3d-8967-3b49547074e7 |  | note | Acceptance Criteria - Cement based grout shall be flowable, self leveling and non-shrink
label | 93c779a7-ea85-576e-a5d1-eb8db5984434 |  | note | Grout of the minimum UCS of 2Mpa at 28 days shall be used to fill the abandoned conduits
text | 850d6ace-d689-570b-91f9-ac9d9bd4cc53 |  | textbox | Reference:TeamBinder Material Approval Number:
label | 9b099fd6-ff6f-5cf4-ac7f-3055ee1d302a |  | note | Method - Document Review
label | 9c5d70ed-4d41-5f33-87ae-825287748566 |  | note | Frequency - Prior to commencement
label | 8735742d-2fa8-5080-81a5-f1777e90bbd3 |  | note | Category - HP
text | 05b7f63c-347b-567c-b685-c82a50a43146 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminary Works/ Procedures
checkpoint-status |  |  | checkpoint | 3.1 - Check that current revision drawings are being used
label | 99777746-3b6b-54a3-bdbb-5ad15a4628cd |  | note | Reference - IFC drawings
label | 81a0fcc0-4396-5285-a79b-d6fa80110be2 |  | note | Acceptance Criteria - Drawing revison must be confirmed with the design manager
label | 2defc7ca-d5fc-5ab8-b41b-a9fcc8176091 |  | note | Method - Document review
label | 79e90360-dd08-530d-b5b5-c04977b7b082 |  | note | Frequency - Prior to commencement
label | f29d6c3c-0a33-56f9-9361-350e1492698a |  | note | Category - HP*
label | b2f0579c-60ad-59ca-ae41-4b2db75f9614 |  | note | Responsibility - SE/PE/SPE
label | d6e9d375-5f03-5a22-8960-ca2e2df1acb2 |  | note | Verifying Documents - Design drawings.
text | 3feb5f7a-9a2a-5c70-b6c8-79e073e96022 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Grouting Procedure
label | 9b1e0cd3-546d-596b-92b3-ba8e567ce26c |  | note | Reference - IFC Drawings
label | 05580c18-232e-55aa-9fe8-68ec00e9c65f |  | note | Acceptance Criteria - Volume of abandoned conduit to be calculated to determine amount of grout to be used. This should match the grout delivery volume.
label | 2db1fbcf-be2c-57bb-a754-95c08875e417 |  | note | Method - Measure
label | 211d07da-bd4a-5128-8ffd-82449ca17a82 |  | note | Frequency - Prior to commencement
label | 5056b12d-511a-53d5-a0d3-02a9bc9bbde4 |  | note | Category - HP*
label | 04bc4de1-a3b9-55ea-bd47-96122e0b65fd |  | note | Responsibility - SE
label | 9a1906bb-0cfa-587d-902c-5eb73958eb8b |  | note | Verifying Documents - Calculated grout volume used Grout Volume
text | d3faaeb5-1f84-5558-8a1f-3e8fa4fded80 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - PE Welders Qualifications
label | 6b508fe2-235e-5971-97ab-47d23ec6882b |  | note | Acceptance Criteria - PE welders are to be pre-Qualified
text | ab0b19f9-77e8-539e-8e18-99440450cf9a |  | textbox | Reference:Teambinder Hold point release number:
label | 72bba6b6-e4c5-5670-b070-aaf34aa7ae41 |  | note | Method - Document review
label | c73974b3-ecba-5fa8-84e8-7b573c53de2a |  | note | Frequency - Prior to commencement
label | 9c03e138-3a75-5f29-a298-4095de4a49c0 |  | note | Category - HP
label | 23c5c349-ea8c-521d-9726-da87ebea809d |  | note | Responsibility - SE/PE
label | 8ed28ce6-9254-52a8-a0ba-cf3f32d5c972 |  | note | Verifying Documents - Teambinder approval number
text | b7e8583b-73e1-54a5-9da3-7b52dd9e2ac3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 4d6d00cd-1a01-5b44-9945-0dd8607a6d9f |  | note | Reference - IFC Drawings
label | f249b66e-5d8f-5788-8871-e67414f2d4f4 |  | note | Acceptance Criteria - Set out line and level of drilling works.
label | 02910dca-3067-5f70-82b2-0523a89d3633 |  | note | Survey to mark out existing services.
label | b0c5b90a-4c27-5b3c-9c43-b3d4694a941c |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | 69deff03-f4a2-5285-bb54-5b86de012ee1 |  | note | Method - Measure
label | 91f73fa2-671d-5a44-82b3-485aa0e8f5f9 |  | note | Visual
label | c6f46eeb-67b1-53a0-a4c2-bcee233a7f9b |  | note | Frequency - Each element
label | 02905057-281d-566f-968f-1c7cae60bf66 |  | note | Category - IP
label | 3f05978f-76bb-58ed-95f9-27ac8619ab35 |  | note | Responsibility - Surveyor
label | 126ec3c0-349d-5607-9068-6df1851d725b |  | note | SE/PE/SPE
label | a1e9020e-a5bd-5fe8-966e-f984c6c8c817 |  | note | Verifying Documents - This ITP
text | d2086e41-55f3-534d-9576-c20ca3859822 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Draw ropes
label | 6d3e25d7-025e-560b-8480-0acf9a509a32 |  | note | Reference - IFC Drawings
label | 73bda0f5-5ae9-5693-806c-87416ccc126c |  | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
label | cbd2af81-e826-5ba5-bbd5-3dbd8fcccabf |  | note | Method - Document review/ Visual
label | 26212195-c1d9-5fb1-9766-41f88c2dd09d |  | note | Frequency - Prior to commencement
label | 84b81427-ee06-5a10-8160-08eb8ee9e258 |  | note | Category - IP
label | a832c7b7-007a-5650-a43b-df369ddd79b7 |  | note | Responsibility - PE/SE
label | 49499d03-92e7-5ebb-9ee7-f9a5568bb9c6 |  | note | Verifying Documents - Material compliance certificate
text | bc6c886e-89fe-5bc1-b561-dcf84650d8e7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Conduit welding
label | c3b66b0c-5a24-50d8-8f23-8ebaa0c35d91 |  | note | Reference - IFC Drawings
label | 671ee394-5dc3-5bf9-bfcd-965aca18d7c0 |  | note | Acceptance Criteria - Joints are to be butt welded.
label | fb84f130-03eb-534e-a955-20be59a268ae |  | note | Weld map to be supplied and identify unique joint numbers.
label | e87e08b8-b525-50f5-ada6-a48cd434f201 |  | note | Butt Welding records to be supplied.
label | db525af3-789a-5e09-9fc6-153329a1b2b1 |  | note | Method - Document review
label | e07eaae2-e233-56c0-94dd-fd703e7fb766 |  | note | Frequency - All Joints
label | 6e99f878-ca45-5faf-86f9-38cb9ddc036d |  | note | Category - IP
label | 2fb0f31f-5cc7-5864-81ba-78322019f59a |  | note | Responsibility - SE/Site Supervisor/Survey
label | bd29357b-b484-5b32-9454-870ce5308fb5 |  | note | Verifying Documents - Sign ITP
label | 40b1a6f4-32c8-53e9-a817-ab803ae438f2 |  | note | Butt Welding Records
text | 8dac538c-6b2c-5ba4-8720-d05d1aa50e01 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Drill rig setout
label | 4098c95a-3395-5fcc-a36c-9add0022ab74 |  | note | Reference - IFC Drawings
label | 7d7c5e7e-d616-55bc-84b1-2880e0694fed |  | note | Acceptance Criteria - Location as per current Drill shot plans
label | a64fceae-7330-5ca4-a8d6-953006539b35 |  | note | Method - Measure
label | 10cd76ca-f90f-559c-8ff9-d1449e4a1d18 |  | note | Visual
label | 90920f94-88c3-5b67-b189-480585af60f1 |  | note | Frequency - Prior to commencement
label | 80aeab88-0469-596e-8b7b-80f8b6387cba |  | note | Category - IP
label | 9ad8a52c-8435-5db3-8468-311ab2c10cdf |  | note | Responsibility - SE
label | d322de80-7236-5626-8d09-1e7422253894 |  | note | Verifying Documents - This ITP
text | 28999c4f-5db2-544d-b7f4-aae8207efa5d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Installation of Pipeline (Trenchless method)
label | 11a7b036-bbee-544c-9b00-139e1d0ae2f4 |  | note | Reference - IFC Drawings
label | b31777de-dcf3-56a0-9a19-cc38e40d8c7c |  | note | Acceptance Criteria - Drill to be installed as per the survey setout.
label | ab965dd5-897a-54ef-b784-0411f61a3288 |  | note | Bore longs to be supplied.
label | 72f20a54-b9fa-57b1-b2ac-e21047fc946b |  | note | Method - Document review
label | 7693b7d1-ef10-501c-a9c2-b3d4b3732e23 |  | note | Frequency - During pilot bore
label | 2e3312e3-9d41-5849-a95c-1fea3b9a483a |  | note | Category - WP
label | c6b0fb06-fddc-5358-a26f-d59a948ad16d |  | note | Responsibility - SE/Site Supervisor
label | 73e9d0e3-4f5c-5763-af0e-984a32dbe654 |  | note | Verifying Documents - Bore logs
text | fa82014c-5479-5938-8afa-e3e877e461d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Plug pulling
label | 67f5321e-e58b-521d-8eae-2c9c05f05f90 |  | note | Reference - IFC Drawings
label | 448d2c5c-314a-5475-97d7-1c648eae780a |  | note | Acceptance Criteria - Mandrel with 90% of the pipe diameter to be pulled thrugh each conduit to ensure the conduit hasent been compressed.
label | d10307e6-3b31-5cf0-b366-e5858a6bb272 |  | note | Method - Record and Review
label | 5560ebe8-4de2-5e36-b15b-e252a20519f2 |  | note | Frequency - All Pipe
label | a6fbabd7-bf5e-580b-af0a-a01135cc6b9f |  | note | Category - HP*
label | 7bf43e90-98df-527b-9154-fb601e10256d |  | note | Responsibility - SE/SPE
label | 890a60bf-8cfb-5fb1-87c3-8f9df3b7072b |  | note | Verifying Documents - Sign ITP
label | 53c6dd31-ef14-518d-8464-fdf775628d66 |  | note | Visual of pipe pull pictures.
label | 1640019e-6d9b-5d24-bd9e-a90b077ecb29 |  | note | Subcontractor Test Record
text | 58f5e790-4501-56e2-91cd-31f4a1756074 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Draw rope
label | b60f5da9-c484-5def-b9e9-bd848fc23ff7 |  | note | Reference - IFC Drawings
label | 2db17aed-df56-5901-97d3-0dc4ba4c5b44 |  | note | Acceptance Criteria - All draw ropes must be continious between shafts and have 2m slak in the shaft.
label | f77b750d-6503-5bf3-865f-93b0983ef0c8 |  | note | Method - Visual
label | 4703f643-d2f9-55fd-90ec-b0c366ce3931 |  | note | Frequency - All Pipe
label | 784f2e5a-bb8c-5386-bb57-682cbe52f1de |  | note | Category - IP
label | 4ddb5923-708a-52b8-bfd4-8e53553979be |  | note | Responsibility - SE
label | 2d192fba-4d1f-5c96-83fc-d926e03cb8fd |  | note | Verifying Documents - Sign ITP.
text | 017d9f02-16e0-5095-b649-7944757032b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Mixing of grout
label | 33bca5f9-8c19-548f-9c1e-0843ed57fa40 |  | note | Reference - Grout TDS
label | e3174267-d1d6-50f4-91ec-7ae1fe41da08 |  | note | Acceptance Criteria - Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
label | 7d017c6c-cd41-55ce-afff-3c833e68be01 |  | note | Only whole bags of product shall be used.
label | 3e7838de-f2b5-5102-9f72-a4bc59952aec |  | note | Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
label | c57a6119-8002-5cc5-a4c7-775dedbc23a9 |  | note | Grout mixture should be mixed adequately and free from lumps
label | e0a4d736-3cd9-5744-b7af-61cab2096126 |  | note | Method - Document review/Visual
label | 02bf9f2f-4570-567d-afbe-28e330e303ee |  | note | Frequency - All pipe
label | 5dd592b3-4981-5454-8583-1f19572746b8 |  | note | Category - WP
label | 484bd8b6-481d-5b7c-b187-0b5bbad93164 |  | note | Responsibility - SE
label | c3407150-afe6-5fac-b05f-5a8fc72d052f |  | note | Verifying Documents - Sign ITP.
text | 467f5742-9aab-5f32-9a0d-fa8444800224 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Clean surrounding faces and remove excess grout
label | 7d159a76-5ccb-573b-bcf9-4e1fed385f2f |  | note | Acceptance Criteria - Area free of excess grout and spillage
label | 44756d61-da04-5d1f-a669-e3ccce601413 |  | note | Method - Visual
label | b95396d1-334c-51c4-8c10-58a34f14c510 |  | note | Frequency - Each shaft
label | 5eee597c-182d-519f-a626-f06a1ec9c7c7 |  | note | Category - IP
label | 4b3167c9-cf1d-50d3-879a-e5d03bc233ef |  | note | Responsibility - SE
label | b848cd5f-223a-5d60-bbec-97cb8482ae19 |  | note | Verifying Documents - Sign ITP
text | 1baffb45-d45c-59ae-b08b-ebb98944ec4a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Curing
label | c9e83b02-cda0-5a4f-8eae-22f910b11ffb |  | note | Reference - Grout TDS
label | 4751d2aa-1264-5796-94ae-f4db9f43bea6 |  | note | Acceptance Criteria - Curing in accordance with TDS
label | 8446b435-dca4-5569-b002-4dcc0731e346 |  | note | Method - Document review
label | 39b2d2fe-5f02-560e-a968-af210f08a29b |  | note | Frequency - All pipe
label | a4aca60f-2214-528e-bda0-47fe8d83ac1e |  | note | Category - IP
label | f39f19b0-54b1-574a-86e0-4aa03c6b0860 |  | note | Responsibility - SE
label | ba62e377-a91e-5c52-bbab-14dcdadffbaa |  | note | Verifying Documents - Sign ITP
text | 55a08de3-95ff-5a85-b1ba-0d433d677674 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Auditing
label | be960d36-283c-5a4c-be82-7c453f88155b |  | note | Reference - IFC Drawings
label | 38a2d4c6-15e3-5ab9-968f-ca7fa741f20a |  | note | Acceptance Criteria - Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
label | 594c9a1e-da59-576f-ba81-8d3943958334 |  | note | Method - Record and Review
label | ea463cb6-db40-5926-9b78-5b93ff4a426a |  | note | Frequency - Alll Pipe
label | 224fa96f-e660-5c4e-b6c6-359ce014a9e3 |  | note | Category - HP*
label | e4c878c2-1584-591d-840c-7671f7965be9 |  | note | Responsibility - SE
label | 7b68420c-237e-5107-96d5-0b38fcbe484b |  | note | Verifying Documents - Sign ITP
label | 8c85c847-9d91-5aea-be5c-a1edfc54d0ad |  | note | Auditing Report
text | 70fa33c0-fa63-5290-b98b-e4e5d97d6902 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Reinstatement
label | 986a0bdc-25d6-5888-b53b-a702b80a2957 |  | note | Reference - IFC Drawings
label | e88720c5-dfa4-5968-b168-c01b060d14b0 |  | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 40624830-4c05-5bc6-b15f-7dc3609c2e4f |  | note | Method - Visual
label | 3c18a4f0-5b03-56c6-82a0-a3fe6fc19287 |  | note | Frequency - Each shaft
label | 69948410-d81b-5fe9-85d5-35f6165c513f |  | note | Category - IP
label | 3e2bc950-50d9-567b-807f-ccb1b71b1aff |  | note | Responsibility - SE/Site Supervisor
label | 4b9b6efc-ac94-5535-a08e-1ef5750f70c6 |  | note | Verifying Documents - Sign ITP
text | aa62c1e9-16d8-587c-98f8-14aec683f009 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Subcontractor ITP
label | c1b762ff-1a2e-5df1-b4ec-fd671dd3729d |  | note | Reference - IFC Drawings
label | 564480c5-0d56-5cbe-ad97-ef798bde1201 |  | note | Acceptance Criteria - Acceptance and closeout of subcontractor ITP
label | c0389e95-f04f-55a5-bbc3-f47146a7810b |  | note | Method - Document review
label | 5dfead6d-e45f-5af8-9b3f-183e9ebaf84c |  | note | Frequency - Each element
label | 1146556a-28c6-5c6b-84e2-492fc57c0e6e |  | note | Category - IP
label | a298705d-17be-57ed-b2ef-afb11a8d12ef |  | note | Responsibility - SE/SPE
label | 1b9ec0e2-cac7-5c2b-b1b6-63b865f70fd5 |  | note | Verifying Documents - Sign ITP Completed
text | 96db5df5-7f33-588b-9ea1-e7c7872f41f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 348b2a25-5039-597c-9699-2aa5d2a30ee0 |  | note | Reference - IFC Drawings
label | a9d7fa61-bb74-54fc-8231-537a2d4e9b34 |  | note | Acceptance Criteria - Survey as built report to be compiled.
label | 9a095dbc-ba18-5551-b2cc-0cd949ad2606 |  | note | Borelog obtained from subcontractor
text | cf4e5a54-ec7e-5fc5-a3fe-e1ab49731c18 |  | textbox | Autocad and PDF reports are to be supplied to:
label | 0f2c3fa9-23cc-57a7-b494-75aba86ea02d |  | note | Method - Document Review
label | 81fb97b8-995e-5363-8073-3a52cf383ab7 |  | note | Frequency - Each element
label | 9e9a1be8-4a74-5bad-befe-ee7280db1635 |  | note | Category - IP
label | a6c4ec19-0368-54f0-bbdd-1740c092f052 |  | note | Responsibility - Surveyor
label | 610ee70e-50a0-5857-8aad-8709b47697fb |  | note | SE/PE/SPE
label | 065d12b0-da05-5bfd-b234-981e87aa3ba9 |  | note | Verifying Documents - Survey As Report
text | 12c70a45-bb1f-5047-b37f-1f6748b6e3be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Red-line / As-constructed IFC Drawings
label | c4e1e79c-55f6-56a0-aa00-3bfdd7afc265 |  | note | Reference - MRPA Quality Management Plan
label | 016e02f4-3aba-5a66-b2a6-169febb19de8 |  | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | 65d9017c-bfda-5921-9b43-babf38628b85 |  | note | Method - Document Review
label | f5f691a9-f57d-5d5e-a9a1-5d7d7910b352 |  | note | Frequency - Once, after construction of the design package
label | 444930bf-552f-5370-aa75-2dea667f9582 |  | note | Category - WP
label | 34c105df-0c16-590b-a086-ae04a82ee1bf |  | note | Responsibility - SE/PE/SPE
label | 87844509-bd55-5f80-a132-2fe060fe870e |  | note | Verifying Documents - This ITP
text | fecc2c39-f85f-5f31-ba6d-773102a51b5e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 709657aa-b366-535c-8439-714812c4f713 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | cc5c7067-1a4e-5d4e-878c-c6a4c50777be |  | textbox | Print Name:
text | 2d9c35a5-327f-5d55-8ddf-e84f32b9c8b5 |  | textbox | Position:
text | e29a3a6e-769b-517a-a391-fbd26a88c279 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 | be7abe98-afb2-4482-a028-e494ef40891d
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 8f96228c-d319-5586-a677-037886de0901 |  | note | Document Title: ITP-CIV-CAMMS-Subgrade Preparation - Road
label | 7ff588a7-f7f8-5a3e-a076-b64d2d0c467a |  | note | ITP Description: CAMMS-Subgrade Preparation - Road
label | 973a88d2-9247-56a2-ab8e-aaa9d1700681 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | db1a909e-e121-5302-8e14-7f33c374c30a |  | note | Revision Number: 0
label | 6cba781a-c4a2-571c-9e91-acf90c7069dd |  | note | Revision Date: 17/08/22
label | 4d491cda-d491-5335-beba-845a0318e979 |  | note | ITP created by: Victor Mira
label | fc59655a-309a-5332-b626-2f166eeaffc9 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | e9399691-5b49-53df-9cfb-b3a103bd979f |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | 2233b63d-5916-5db0-8130-001da7d1f2d7 |  | note | Reference - VicRoads Section 173
checkpoint-group |  |  | section | 2 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 2.1 - Survey Set-Out
label | 60a2fd2f-1ae5-57d0-accd-61d0717295b2 |  | note | Reference - IFC Drawings
label | 6a4bdd27-ba01-58ac-9fb1-101039c6164c |  | note | Acceptance Criteria - Area has been set out in accordance with the drawings
label | b94c3360-3b31-48bc-b93d-fad0b82ca888 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 4e924445-91ef-5d85-bb14-f37f86acd9c2 |  | note | Method - Verify
label | 6e42e260-7341-5cac-8d45-ed751439bb6f |  | note | Frequency - Prior to commencement of excavation
label | 766b8a5b-e45c-5ca5-9d7e-e66297bc36b5 |  | note | Category - IP
label | 57d4b966-4e4b-5c64-ab46-a58bee722438 |  | note | Responsibility - SE/Surveyor
label | 9e81873b-c36a-504a-b590-342941419bf3 |  | note | Verifying Documents - This ITP
text | ef892f42-350c-541f-a0f5-6725b5fea365 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | 09886743-379f-5fe9-80c7-b84b0e75ab68 |  | note | Reference - Section 204.06 ( c) Section 204.06 ( e) IFC Drawings
label | 1eb140f2-df02-5535-9f26-e3e66fbf6136 |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | 42377612-41ab-51d6-a9dd-139125f6e8b6 |  | note | In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | eb68d141-3f22-56d7-a3f5-8fb763ee0481 |  | note | Assigned CBR ≥ 2.5%
label | 4d2ae3e7-6660-5701-9c76-9b32aa2b583b |  | note | If parameters are met, rip and recompact to a depth of 150mm.
label | 16d194a7-7ff0-551a-88d4-3df454af0862 |  | note | If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | 16d6e0f9-2e8f-57b9-bbd6-164885896563 |  | note | If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | b3552668-4323-53ba-991d-761fcdbdb4a0 |  | note | Attach: Laboratory testing Verification:
text | a405efca-1691-5658-a252-a97e9e917533 |  | textbox | Enter: Type A fill Lot Number:
label | d319d0e7-70a1-562f-a241-ab5fdf42a939 |  | note | Method - Verify-Document Review
label | 37bbb823-70da-562b-84a2-346c1e19ad8e |  | note | Frequency - Each lot
label | 0560f76b-fcf5-540d-a358-a55e9027372f |  | note | Category - HP
label | 85bcb70b-e02c-50ed-98dd-788e01e0e160 |  | note | Responsibility - PE/Nominated Authority
label | 5a74b024-5392-533e-89ec-10a77ca5ad77 |  | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
text | 8da46770-6485-5614-a6dd-f7ee21bc764a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Material classified as silt
label | f70cae7a-d57e-5a28-b387-1fb239366ec5 |  | note | Reference - Section 204.04 b)
label | b1d4b411-9ef3-5e34-b356-6b22c054691d |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilization to the satisfaction of the Nominated Authority
label | bac3456c-b60c-577a-8e02-b7f328e52d92 |  | note | Method - Document Review
label | 9222b0a0-4cb6-581e-86b7-335698b67844 |  | note | Frequency - Prior to commencing
label | 81a0fdf5-e918-5b3a-ae95-f4272331f686 |  | note | Category - HP
label | 60edc44b-6ddd-5771-b4ab-195eaabc1c07 |  | note | Responsibility - SE/Nominated Authority
label | 93ad2b82-54a2-5a78-a376-e34f59b1bb39 |  | note | Verifying Documents - Superintendent satisfied with Stabilisation
label | 6ec73615-81b3-58ff-b7dd-b6c99a491a6c |  | note | Signed ITP/ records
text | 96fcb126-1b74-54f7-8863-4e8cd9db0201 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Acceptance of Rock Subgrade (where applicable)
label | cc2c2456-3b17-55ff-a1cb-4b61ec26b902 |  | note | Reference - Section 204.06 f)
label | d686c7fe-f4fa-5940-a1d0-950c3b04bf56 |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | f76ad9a5-c361-5c4c-8336-8fbd42a078fa |  | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | fa69819b-4207-53f6-ac28-1f2efada6990 |  | note | Method - Site Inspection/ Document Review
label | 3e6d151e-db6a-5ac8-a1ae-40385bca9e60 |  | note | Frequency - Prior construction of the regulating layer
label | efd7e087-071e-5dc5-8078-485e77ebc1cf |  | note | Category - HP
label | f572d230-d9f3-5828-a3d2-e98658278770 |  | note | Responsibility - SE/Nominated Authority
label | 9e412c9d-a02d-505e-97dc-b83e15f27632 |  | note | Verifying Documents - This ITP
text | 7de3feb2-69a5-5adc-916d-683aac242c7d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Unsuitable Material
label | 86d54d1e-6ad4-5e42-afae-f125547231c2 |  | note | Reference - Section 204.07 d)
label | 9d5ce705-07a3-54b3-a291-b5307e708ed3 |  | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | f94baa85-77d9-54c3-96e0-e8d014d6daff |  | note | Method - Visual inspection
label | e94aa486-89fa-5aa8-90a3-95239004cf3e |  | note | Frequency - Each lot
label | e47ac882-dc41-52b0-8a90-beb39c4da28c |  | note | Category - HP
label | 39d8e355-f7e5-56d5-a4ed-0daef21150cb |  | note | Responsibility - SE/Nominated Authority
label | 4ef9dfa7-10e8-5132-b865-dc6936bbca4a |  | note | Verifying Documents - This ITP
text | 2d337a91-d3fe-5062-b134-34a0d612bf01 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Groundwater
label | 50edeeaf-d04a-5c0e-9687-6bb35f57ba1a |  | note | Reference - Section 204.06 h)
label | aba92a8a-0827-564a-90e2-9420b67b8a6d |  | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | 0eb84394-84a9-5f47-9959-0475fb6ca858 |  | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | d3860bbe-7859-5101-a2f3-87198aaea15e |  | note | Method - Visual inspection
label | dec3471d-6525-5738-ba65-508ab43f50d2 |  | note | Frequency - Each lot
label | c0b99560-9908-511b-b337-709064449739 |  | note | Category - HP
label | f86e83fc-d8a9-50b0-ace6-f87187a2ccf3 |  | note | Responsibility - SE/Nominated Authority
label | 0ade44ef-9102-596f-b4b6-584fee78fe59 |  | note | Verifying Documents - This ITP
text | f3470fbb-0ccd-5e56-839c-606ae6ba8701 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Cut to Fill Zones
label | 88e02adc-c435-5ce9-a5d1-c6c41d6e6e03 |  | note | Reference - Section 204.06 g)
label | ff0fcbee-27ca-52b2-be1c-121e0e3fca0b |  | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | b182177e-2883-5d45-9a02-2aeaa2f0ff8b |  | note | Method - Site Inspection
label | eff4779b-66a0-5f95-94ac-389f0a5c7256 |  | note | Frequency - Each lot
label | 67ade133-79c3-51c9-b384-675f536ff02d |  | note | Category - IP
label | c986cfb5-cf83-50e6-9728-5dff9bb53585 |  | note | Responsibility - SE/Site Supervisor
label | bf22812a-155b-5cc2-a339-cc156aa4e3f6 |  | note | Verifying Documents - Sign ITP
text | 6217bd74-be76-548c-98a8-af8c8bac9879 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 - Proof Roll
label | 802129c0-1bc5-5abd-9376-66941c8a9776 |  | note | Reference - Section 173
label | bc7f0815-069e-5005-ade9-f6332d072b08 |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 62a7441c-6ac6-5ba0-8ad9-fc902b75ffb8 |  | note | Method - Visual inspection
label | dea45c6d-46c4-5ed2-af28-89723d67198c |  | note | Frequency - Each lot
label | 16f8c1c6-bbbb-5e41-846f-bb49430c4526 |  | note | Category - HP
label | 6a7799fe-a3f1-5197-ab82-ac6396a3b75e |  | note | Responsibility - Site Engineer/Superintendent
label | 779117d9-c2e0-53d5-96f0-ddb4497e9784 |  | note | Verifying Documents - This ITP
text | 05edeced-f9ce-5add-8e29-df8cbd8b6568 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Compaction Testing
label | 0d2378f8-59e9-552a-b906-797b7f192bd0 |  | note | Reference - Table 204.131
label | 2ec4c433-cc68-58ad-a8ad-df5a555d4ae6 |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | 87be82ab-180b-5d7d-96d1-af486b906b8a |  | note | Scale A: Characteristic Density Ratio 99%.
label | b5f106b7-0962-5623-a6a2-7295a38b9483 |  | note | Scale B: Characteristic Density Ratio 98%.
label | d3b8f6b7-c21e-5085-a704-d22732baae24 |  | note | Scale C: Mean Value of Density Ratio: 100%
label | a5148e16-02fe-538b-b0bf-20ff08751421 |  | note | Attach: Compaction Test Result:
label | 7a4f1943-e1d1-5e39-845c-322f8d1e4873 |  | note | Method - Document Review
label | 661f1315-fa9e-536c-880f-2584f7d348aa |  | note | Frequency - Each lot
label | 034051d9-a655-5241-8117-017b93b3b94c |  | note | Category - IP
label | 1b75684d-9e75-5559-9b1b-4757c86d632e |  | note | Responsibility - PE/SE
label | 31c405ab-a6d2-5679-8708-81df2d10da7e |  | note | Verifying Documents - Test Records
label | 256104f1-6650-55bf-ad42-0f99d3348536 |  | note | Lot Register
text | 39bb35a2-04e2-5fb1-aca6-d399fa5e1296 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 - Post Compaction Material Property Testing
label | f400ee05-cd8d-51c8-b99e-de129083e6dc |  | note | Reference - Table 204,041
label | ae2964f0-f5ae-5fa6-a9e2-82228f1fec7f |  | note | Table 204.141
label | 4d621d5d-baee-5f62-b444-f9cd5b65ba98 |  | note | Section 204.14 a) or b)
label | ed6ce5a7-e207-5616-8c1d-a8a7019f075a |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 7759e74c-1e62-59e7-9a6f-4e9080080b0b |  | note | CBR ≥ 3% and Swell ≤ 1.5%
label | 1c868bea-e98b-5baf-9b9e-8c4c14e66619 |  | note | Max Permeability = 5X10-9 m/s
label | d79404a9-0395-5289-8e31-14af34de8cf0 |  | note | Grading: 75.0mm 100%
label | 53f83c4e-4188-5741-9567-aaac39e271ab |  | note | 4.75mm 40-80%
label | 436e11b7-b87c-5075-bc7b-ac76267dd44c |  | note | 0.075mm 10-40%
label | 7bdbb1a6-52ea-523c-93d7-8a41f541badb |  | note | Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 31d42ffb-2057-5fa1-95db-a16741171d60 |  | note | Scale A:
label | fbdd37c8-de05-507d-9a35-afd00eabe6e9 |  | note | CBR & Swell
label | 8a199d50-6d53-5dbc-beca-c3f0ec547907 |  | note | Initial - 1 Lot Test to determine Assigned CBR and swell
label | cf66f7c2-be7f-5e8d-8af1-a607b85ca44b |  | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | 3411613b-9a7e-5037-9828-4910c72957e2 |  | note | Max Permeability
label | 9ad40a60-be5f-5567-b3de-60736e9b4003 |  | note | Initial - 1 test per 2 lots
label | 89fa48eb-7446-554e-b50f-8466f36f0241 |  | note | Reduced - 1 test per 4 lots
label | a5a3e594-d4cb-5c8a-987f-40ee7a759e1e |  | note | Grading:
label | e5cdefd0-2c84-5a39-a1c1-63a5c8bc813a |  | note | Initial - 1 test for each lot tested for compaction
label | 95cf2739-2ade-5ec1-b51c-94ae8fa720eb |  | note | Reduced - 1 test for every second lot tested for compaction
label | c0de8a44-e1a4-5724-b7a2-d9cee5060682 |  | note | Max. PI x%Passing 0.425mm & PI
label | ec07aea7-ddc2-5054-9718-1d1c5bae1649 |  | note | Initial - 1 test per 2 lots
label | d28caff2-7593-581b-8cd9-f2ef1d2bc778 |  | note | Reduced - 1 test per 4 lots
label | 7294c4cc-16df-51bc-ada4-8c53b6d1b2f8 |  | note | Scale B:
label | c01fb6c9-4071-51bd-bc25-a12b04ed9848 |  | note | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | a9ca109e-faef-5a71-9ff9-fdb28dc7f094 |  | note | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | f52d893b-e034-5d54-8dfe-ee3303da4fa0 |  | note | Attach: Post compaction test results
label | 7ecf70bb-22a8-5d7f-956e-078ecb189b38 |  | note | Method - Review Document
label | 94cb1796-085c-566e-8ac4-d4c02e1513c6 |  | note | Frequency - Refer to Section 204
label | b8090917-fc52-5d69-ad2f-88aac1b12fd9 |  | note | Category - IP
label | a1da7d61-9299-5bf5-aa71-f969343d8877 |  | note | Responsibility - PE/SE
label | 2cbc9f4c-94df-58f0-93b4-1f12c5c4e387 |  | note | Verifying Documents - Sign ITP
label | 9c360ac1-ff48-5378-a1c6-8900c970802c |  | note | Attach Material Property Test Report
text | 00e6ebbd-f56c-5c67-a293-7f3c3814033e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Post Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Conformance
label | 6d4af626-1c0c-5f39-9f7a-817a473bb5ab |  | note | Reference - VicRoads 204.03f,g and h
label | 65b8d1ea-bfa7-5001-9e4f-d5e5aa660577 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 36fac766-1e49-5239-9f82-586519ab0f96 |  | note | Level tolerances (Scale A):
label | 12cc4599-153f-545c-8214-4457d9cbd6ce |  | note | Range x = +5, -15mm
label | df1c9df4-5bdf-5d27-b152-6553b389d7ae |  | note | Max S = 12 mm
label | c6bf77b5-a684-5e3a-b97d-e677addc3a28 |  | note | 80 measurements per lot
label | 7a1f627a-e805-5227-b419-6862624f975d |  | note | Level tolerances (Scale B):
label | 0a3971db-e34b-5a60-8f18-c59a2abe4185 |  | note | Range x = +5, -25mm
label | 1e6e8111-f86a-5739-8834-1afe11874d63 |  | note | Max S = 15 mm
label | c4dac872-a584-5d93-9095-2e2b2168bcc2 |  | note | 40 measurements per lot
label | efd4a2da-862c-51e2-b7e1-1ec600f58311 |  | note | Level tolerances (Scale C):
label | ee673bb2-c8a2-5bfe-8ea7-0b20235bd905 |  | note | Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | 9a38cabe-3018-5421-9035-78235b39172d |  | note | Method - Review Document
label | 61a4ba2e-1d8b-5bf8-8248-0088736be28c |  | note | Frequency - Each lot
label | e4a99d3c-51c7-56c2-b3e2-9ebd073494fa |  | note | Category - SCP
label | a9c108c7-fc30-5e7b-9b00-7a70b8521574 |  | note | Responsibility - SE/Surveyor
label | 4036fc5c-85eb-50bd-b89a-a4c0d7aaed7c |  | note | Verifying Documents - Sign ITP
label | f1d4e281-c04b-57ad-a0be-dac17ecd5524 |  | note | Attach Survey Report
text | 744dd67d-916b-52ee-a521-a8d0cf28d750 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 04c81412-e6fc-5a23-a127-a6482a95c2ee |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1182a2f4-89e8-511f-94ce-05745706f055 |  | textbox | Print Name:
text | f86afe8a-3097-5505-bcf4-a430016e4756 |  | textbox | Position:
text | 26fbd8d8-a238-582e-85fc-f686493c56ef |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 |  |  |  |  | Yes | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 | eb19a8fa-8442-41b2-b53b-0eeaaa7620ab
checkpoint-group |  |  | section | 1.0 - Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1.1 - Referenced Documentation
label | 4d247935-48ba-533c-b788-7d747238dc19 |  | note | Reference - IFC Drawings, L1-CHE-STD-005, L1-CHE-STD-025
checkpoint-group |  |  | section | 2.0 - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete
label | 11b4965a-6418-5173-ac65-8d47f86fa7ce |  | note | Frequency - Each Mix
label | 56a0906a-1b5f-5336-88c8-f313eef90f58 |  | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
label | 08c0412d-9398-5e4f-a880-1b3143b30d62 |  | note | Reference - IFC Drawings
label | e6544bcc-724f-5955-add4-5463b3072ccf |  | note | Inspection / Test Method - Document Review
label | 419c6f75-9859-5f2f-ae63-64ac626ee2a3 |  | note | HP
label | ea3f7837-5776-5b3a-92c8-562eba3d6f4d |  | note | Responsibility - SE/Site Supervisor
text | 335acc92-a693-5fa4-9a2f-f09419931fbc |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Steel components
label | b3568d07-909e-5c25-b376-94a10a9d8b62 |  | note | Frequency - All elements
label | ef9aabb0-56d2-5578-af9f-3378d521b819 |  | note | Acceptance Criteria - All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250
label | 17f60f8e-32b6-5566-a31c-9ae4d9b5217c |  | note | Reference - IFC Drawings, AS41000, AS1163
label | 2f17a07a-cafe-54a5-8b69-426d3cfd0a50 |  | note | Inspection / Test Method - Document review, Visual and Measure
label | 46d74043-2362-5d7d-8122-0256abfd68ef |  | note | IP
label | c80d8ab1-335e-5532-8e1e-d6d17d62fbd7 |  | note | Responsibility - SE/Site Supervisor
text | 139bf227-8a03-5708-b5ea-67589477db35 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3.0 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - Survey Set-out
label | 9f70c6a0-e0f2-521d-b97f-aad133a101d6 |  | note | Frequency - Each element
label | 37e2ab1b-108b-544e-acbe-86b23b1bdfa6 |  | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | eeae2cf5-04db-5cf0-a07e-e62b304ff6be |  | note | Offset checked against the running edge prior to installation of posts.
label | e725ec05-46f1-526e-8e9f-3d8233c41658 |  | note | Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | dca4462a-61d8-5311-9210-3b618fbccde1 |  | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | d9b9d42f-994a-566e-ab97-3698c5144bbe |  | note | Reference - IFC Drawings
label | 4a7b50ad-a302-5772-a1b4-830eb55c2edf |  | note | Inspection / Test Method - Measure,Visual inspect
label | 395beb16-210b-5646-b3ba-237117865c16 |  | note | IP
label | 9bceb032-1c5c-5a66-a972-7fb09a234cfa |  | note | Responsibility - Surveyor, SE/PE/SPE
text | a747adb6-cbbf-5fa0-aab4-79726cad202e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4.0 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Excavation works
label | 1d53b8cd-0b0c-535e-a8c8-cfaaaf96455b |  | note | Frequency -
label | ab580a53-ba35-5f69-88e7-037732f5ed2b |  | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements.
label | 83d58eac-ec60-59d3-a667-461cc8813cb7 |  | note | Follow asset owners guidelines for work around their service.
label | 725ff805-7f98-5fa9-8fe9-08fb0c4f8e96 |  | note | Excavation must use Non Distructive Digging in the rail corridor
label | d6e5291c-c1ee-5027-ad33-35c0c04cd5b9 |  | note | Reference - IFC Drawings, L1-CHE-STD-005
label | 71226d9a-dbe4-545d-aaa2-aca9681d96b3 |  | note | Inspection / Test Method - Visual
label | a5a04ca5-aee8-5413-93b0-d793916ddb17 |  | note | IP
label | 7cc8fbed-0d14-5a68-908c-0bd61476526b |  | note | Responsibility - SE/Site Supervisor
text | 1d5f4c50-336b-5f6c-bf4c-87d49c45b5fe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Ground Conditions
label | 48f523f5-8981-52aa-903f-1eeb4baaf48f |  | note | Frequency - Each post
label | 54d4ab6c-9b56-503e-b947-99e9fcc9c8bd |  | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | e8ecac4b-69af-5096-907f-e052ad7d031f |  | note | Reference - IFC Drawings
label | c2c09b12-6084-51f9-8e6d-3a5da104844b |  | note | Inspection / Test Method - Visual
label | 997dee6c-7155-574f-8d82-0747f59ef06d |  | note | IP
label | 978532e5-7ce0-50ad-bed3-02ecb1fbcc3d |  | note | Responsibility - SE/Site Supervisor
text | 56033256-f943-55a8-b556-c64f930b3cd8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Post Foundation
label | 45b1590e-465c-5058-a2e3-260257ce88b9 |  | note | Frequency - Each footing
label | 48e18afd-1c0b-570c-9e57-0908cd3f6848 |  | note | Acceptance Criteria - Up track (Alongside central pier): - 300mm Dia, - 2000mm Depth, - 2700mm Typical Spacing
label | ddee2c10-6af2-5160-91ac-5bf6a4854e55 |  | note | Up track (Outside central pier): - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
label | 2d09376d-f77c-510a-b4dc-abf851a4b2c1 |  | note | Down track: - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
label | 97539f69-b3c9-5ca3-b9c7-492d7f2c5a05 |  | note | Gates: - 350mm Dia, - 1400mm Depth, - 1350mm & 4000mm Spacing
label | 1e4d99c5-6261-53e0-9743-cd0d77c1d1bb |  | note | Reference - IFC Drawings
label | 77d6fd66-bce5-563b-a3af-4e4b03e81494 |  | note | Inspection / Test Method - Measure
label | 6f416c82-674f-5426-8101-63cee10006ea |  | note | IP
label | 223cf01a-dd37-59a0-bfbe-f37d8c1ff0c6 |  | note | Responsibility - SE/Site Supervisor
text | 681455ab-229d-5f50-9a75-73be8816c44a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Post Installation
label | 7a57e7e7-3e8f-5334-8a23-529ef3a6d440 |  | note | Frequency - Each post
label | 63340f6a-8a82-503e-8e54-62819bb60d47 |  | note | Acceptance Criteria - Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | c0da548b-4edb-5feb-90a0-01ced39dd1fe |  | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | 0a989d61-bb6d-56be-8d54-8811e10cda01 |  | note | Maximum post spacing to be 3.1m
label | 7b875fc6-6aee-5a2d-977e-f682b7cfc22a |  | note | Two spans at 1350CTRS at the end and at Refuge bays.
label | 710ccab2-bf83-5522-98fd-28a4017fec85 |  | note | Max. post height 1800mm above ground level.
label | fbae2b5b-2b82-5e33-975e-d3445da0a653 |  | note | Vertical Tolerance: ±20mm from the design line.
label | 0e8ff680-384f-51a9-8d1c-ce9b3a7b39d9 |  | note | Reference - IFC Drawings, L1-CHE-STD-005
label | c2076ff6-7fee-5a9b-b828-b1d7ec86b229 |  | note | Inspection / Test Method - Measure
label | b0d25201-57a8-5480-b90c-6b01a503237f |  | note | IP
label | 4a9bdc29-75a3-53a0-9d65-805adbf90436 |  | note | Responsibility - SE/Site Supervisor
text | fc5390b5-525f-5155-8fc9-a6bb1b8e1f07 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 - Chain Wire Mesh Installation
label | 1d66618a-70c4-51f6-9607-e61366c17661 |  | note | Frequency - Each element
label | e30cb1f0-416e-57fd-9981-2393aa243961 |  | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
label | 5949f35f-b09c-581b-bcff-fe04c3e614c4 |  | note | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | 3dc05141-96b1-5312-9530-eb17eb35f549 |  | note | Reference - IFC Drawings
label | 114eb368-79d3-545a-8afa-651fc58c785b |  | note | Inspection / Test Method - Visual
label | bc98188b-739a-5acd-9d06-fdecfe2d245f |  | note | IP
label | 32c953f3-d01c-5e41-a30c-12250225807b |  | note | Responsibility - SE/Site Supervisor
text | 25f23cf0-6e5f-5e67-8aa1-61823c303e5f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 - Bracing
label | ecc05b2a-006f-510b-a897-cf4fe8ce3a73 |  | note | Frequency - Each element
label | a0520f2f-b0dd-5aee-b069-2c16977a38a8 |  | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 1a9f073d-4df0-56e3-bc95-2c14fb6aa6cc |  | note | Bracing to be installed on both sides of the fence at the fence corners
label | c594120e-57ee-5d51-9b7c-30db72f5a939 |  | note | Reference - IFC Drawings
label | 492d1735-46ab-586b-8275-e0f05991e1fe |  | note | Inspection / Test Method - Visual
label | e9f8ee03-a73c-5b11-b7d6-a9ab2577dfb5 |  | note | IP
label | 87aa72c3-cc9c-533c-9bb8-edc6e3baf5e5 |  | note | Responsibility - SE/Site Supervisor
text | 6cf3ce7a-efd4-5d21-9558-250e1fa16816 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 - Refuge Installation
label | b39ca321-e5ce-57b6-92b8-8cd41394e3b9 |  | note | Frequency - Each element
label | 59a50098-0a67-5909-9b81-47659e4edc4b |  | note | Acceptance Criteria - Refuge Access to only open from track side.
label | 3db4913f-dc2f-5d65-9e03-14e94f9b396a |  | note | No chain wire mesh to be installed at refuge access.
label | 1d3a3435-636f-55eb-9749-6eaa0bd438a8 |  | note | Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
label | 4c3a542d-fbea-5ab8-9905-c6a0cbc5fb5a |  | note | 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | e3547d8d-9b9d-501c-9b1b-8d25821e80f8 |  | note | Reference - IFC Drawings
label | ddc09f81-c022-5e55-b877-7c4d466c69a1 |  | note | Inspection / Test Method - Visual
label | 42add704-531e-5999-8724-b1bebc2ee682 |  | note | IP
label | 62797a6d-60ed-5f43-bdf0-8de753c14de5 |  | note | Responsibility - SE/Site Supervisor
text | 893c7be1-a1e2-5b75-929e-21d3603923e5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 - Refuge Signage
label | 42edfd48-aa05-5e26-ad39-3cf184d41627 |  | note | Frequency - Each element
label | 5c365182-f6ca-52dc-8363-12c782100dc1 |  | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
label | 9ad54944-13bc-529d-9687-30b12002ac1e |  | note | Reference - IFC Drawings
label | faa33523-6900-53f1-a3ba-922b262b078a |  | note | Inspection / Test Method - Visual
label | d3aacea0-881c-5cd7-8cfc-f38e5610af2f |  | note | IP
label | 7079ce95-dd5f-5eab-b39d-f094fdbe7619 |  | note | Responsibility - SE/Site Supervisor
text | 0e09b4f1-a564-56e7-bdd1-f3e77804dc55 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5.0 - Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Fence Height and Track Clearance
label | 25acb272-1e12-5d84-b6cd-ab8ce464c384 |  | note | Frequency - Each lot
label | 23a2d6b9-d634-5f96-b55f-7d5e98e710e1 |  | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | bc309458-6c59-577c-9897-9665043b0c32 |  | note | Reference - IFC Drawings
label | fd2df783-dbb4-512f-82f1-a8fa142efd60 |  | note | Inspection / Test Method - Measure
label | 698421fe-24bb-5a95-a166-3c8fd8cfd18c |  | note | IP
label | 4094a60c-fbfa-5902-a59c-cee5d15dac09 |  | note | Responsibility - SE/Site Supervisor
text | f45683a8-91cd-5fc5-b87e-4b106b4a2c77 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 67a4ba8e-e22f-5f4d-9aca-54c0b3924856 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 3d809b9a-3404-5249-be50-d7789edc50f1 |  | textbox | Print Name:
text | aa4fca8f-3ecc-5856-b9fe-0901864b2edf |  | textbox | Position:
text | 0cbf9109-4a71-5f1e-9cdd-3456421886b0 |  | textbox | Work Completed On:
text | 88c350c0-ff62-5344-83c4-5c7e9d2369d0 |  | textbox | Date: