## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV Delineation Fencing
ITP Description: |  | Delineation Fencing
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 1
Revision Date: |  | 2022-08-19
ITP created by: |  | Ethan CARUANA-SMITH
ITP approved for use by: |  | Pradeep TALASILA
Special Notes to ConQA Team : |  | ITP for Robinsons Rd
Inspection & Test Plan - Rail Delineation Fencing
[9 empty] | Revision: | 1
[9 empty] | Date: | 2022-08-19
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | AS1657 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete | IFC Drawings | 25 MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor
2.2 | Steel components including posts, mesh and fittings | IFC Drawings AS1657 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 Black PVC finish | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, and fence start and end points. Offset checked against the running edge prior to installation of posts. | Visual and Measure | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings | Excavation completed by auger outside of service working limits. Follow asset owners guidelines for work around their service. | Visual | Each fence footing | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.3 | Fence Footing | IFC Drawings | Footing dimensions 600mm deep x 300mm diameter. Every second footing to have dimensions 1200mm deep x 300mm diameter. 25 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per VicRoads Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample. | Measure | Each footing | IP | SE/Site Supervisor | This ITP Concrete Dockets
4.4 | Fence Post Installation - Non-sleeved | IFC Drawings | DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover. | Measure | Each post | IP | SE/Site Supervisor | This ITP
4.5 | Chain Wire Mesh Installation | IFC Drawings | Chain-wire mesh 1200x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips. | Visual | Each element | IP | SE/Site Supervisor | This ITP
5 | Post-construction / Post-installation Activities
5.1 | As-Built Survey | IFC Drawings | Posts are to be checked for verticality and ensure spacings do not exceed standards. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /