## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV Rail Delineation Fencing
ITP Description: |  | Rail Delineation Fencing
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 5
Revision Date: |  | 2022-08-19
ITP created by: |  | Ethan CARUANA-SMITH
ITP approved for use by: |  | Pradeep TALASILA
Special Notes to ConQA Team : |  | ITP for Robinsons Rd
Inspection & Test Plan - Rail Delineation Fencing
[9 empty] | Revision: | 5
[9 empty] | Date: | 2022-08-19
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | NIST-0001(2) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | NIST-2617(3) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | NIST-2662(1) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Non Dependent | SAST-3281(1) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete | IFC Drawings Section 610.07 Table 610.071 | Unless otherwise stated the following will apply: Concrete Mix is to be 25 MPa concrete per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor | Supplier Certificate of Compliance
2.2 | Steel components including posts, mesh and fittings | IFC Drawings AS4100 AS1163 AS1101 Part 3 AS1554 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, refuge bays and fence start and end points. Offset checked against the running edge prior to installation of posts. | Visual and Measure | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings | Excavation completed by NDD Follow asset owners guidelines for work around their service. | Visual | Each fence footing | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.3 | Fence Footing | IFC Drawings | Footing dimensions 500mm deep x 300mm diameter. 32 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample. | Measure | Each footing | IP | SE/Site Supervisor | This ITP Concrete Dockets
4.4 | Fence Post Installation | IFC Drawings | DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover. | Measure | Each post | IP | SE/Site Supervisor | This ITP
4.5 | Chain Wire Mesh Installation | IFC Drawings | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips. | Visual | Each element | IP | SE/Site Supervisor | This ITP
4.6 | Welded Mesh Installation | IFC Drawings | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with cable ties in accordance with manufacturers specifications. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips. | Visual | Each element | IP | SE/Site Supervisor | This ITP
4.7 | Refuge Installation | IFC Drawings | No chain wire mesh to be installed at refuge access. Refuge Access to be located at max. 20m intervals along the fence. Install additional refuge bays or reduced spacing to allow access to rail assets 50mm dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. Refuge access to be 1200mm wide | Visual/Measure | Every 20m Max. | IP | SE/Site Supervisor | This ITP
4.8 | Gate Installation - Gate | IFC Drawings | Foundations and posts installed as above with 2400mm spacing. 2 no. 1800mm (H) x 2400mm (W) gate panels per gate. Centre post of gate to be sleeved and positioned on the side external to the construction site to ensure gate only opens into construction site and gates that are parallel to track when closed open away from track. | Visual/Measure | Each Gate | IP | SE/Site Supervisor | This ITP
4.9 | Limited Clearance Sign | IFC Drawings NIST-2617 Appendix A3 | Limited clearance signs to be erected at all refuge locations and at each end of Delineation Fence where fence is offset at 2.4m from the centreline of track. Sign to read "DANGER LIMITED CLEARANCE DO NOT OCCUPY DURING PASSAGE OF TRAINS" | Visual | As required | IP | SE/Site Supervisor | This ITP
5 | Post-construction / Post-installation Activities
5.1 | Fence Height and Track Clearance | IFC Drawings | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to nearest rail. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
5.2 | As-Built Survey | IFC Drawings | Posts are to be checked for verticality and ensure spacings do not exceed standards. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /