## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-CAMMS- Unbound Flexible Pavement
ITP Description: |  | Unbound Flexible Pavement
Discipline (e.g. CIV/STR/RAIL: |  | CIV-CAMMS-
Revision Number: |  | 0
Revision Date: |  | 2022-09-06
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Aldrin Guinchoma
Special Notes to ConQA Team : |  | ITP for Camms Road
Inspection & Test Plan - insert description here
[9 empty] | Revision: | 0
[9 empty] | Date: | 44810
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | Reference Documents: IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 |  | VicRoads Section 173 (10/9/2008) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 |  | VicRoads Section 304 (13/8/13) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 |  | VicRoads Section 801 (19/07/18) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 |  | VicRoads Section 812 (13/07/16) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Crushed Rock Mix Design | Section 304.03 Section 304.05 Section 812.04 Table 812.121 IFC Drawings | All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product. Enter: Teambinder Material Approval number [free text box] | Document Review | Material conformance as per Table 812.121 | HP | NA | TeamBinder Material Approval Number
3 | Preliminaries-Documentation
3.1 | Subgrade Preparation | 304.04 | Prior to placing subbase material, the subgrade shall meet the requirements of Section 204. Reference: Subgrade Preparation/Type fill Lot Number: | Document Review | Each Lot | HP* | PE | Underlying layer Lot number
3.2 | Select Scale | Project Requirement Specifications IFC Drawings | Specify site specific scale: Enter: Site Specific Scale (A, B or C) [free text box] | Document Review | Prior to Commencement Each lot | HP* | PE | Sign ITP
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-out and Lot size | IFC Drawings Section 304.06 | Lot size shall be the lesser of 4000sqm or a days production. Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06. ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP) | Survey Document Review Measure | Each lot | IP | Surveyor SE | Sign ITP
5 | Construction / Installation Activities
5.1 | Crushed Rock Delivery Dockets | 304.04 | A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1) ATTACH: Delivery Docket(s) | Document Review | Each Lot | IP | SE | Attached Docket Sign ITP
5.2 | Placement of Material | Section 304.03 Section 304.06 Section 304.08 | Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas. Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material. Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances. At no location shall water pond on the surface of any pavement layer. | Visual and Measure | Each lot | IP | SE/Site Supervisor | Sign ITP
5.3 | Construction - Jointing | Section 304.07 | The layout of joints shall conform to the following requirements: (a)material shall be spread in such a manner as to minimize the number of joints; (b)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m; (c)transverse joints shall be offset from one layer to the next by not less than 2 m; (d)longitudinal joints shall be offset from one layer to the next by not less than 150 mm; (e)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane. | Visual and Measure | Each lot | IP | SE/Site Supervisor | Sign ITP
5.4 | Compaction test (Frequency) | 304 .11 (b) | The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots). Scales A and B: 6 samples Scale C: 3 Samples Pass: Tested NA: Not Tested | Visual | Each Lot Where applicxable | IP | SE | Sign ITP
5.5 | Post Compaction Materials Testing (Frequency) | 304.11 (c ) | SCALE A: The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency: Compaction: Lower Subbase: none Upper Subbase: 1 in 4 Base: 1 in 2 PI: Upper Subbase and Lower Base: 1 (two samples) in 8 Upper Base: 1 (two samples) in 4 SCALE B: the first lot of each pavement course shall be tested for post-compaction grading and PI. SCALE C: Post compaction grading and PI testing is not required (CHOOSE NA) | Visual | Each Lot Where applicxable | IP | SE | Sign ITP
5.6 | Proof Roll | Section 304.08 | All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer. | Visual | Each lot | HP | Nominated Authority | Sign ITP
5.7 | Protection of compacted layer | Section 304.09 | The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence. | Visual | Each lot | IP | SE/Site Supervisor | Sign ITP
6 | Post-construction / Post-installation Activities
6.1 | Compaction Testing (results) | Section 173 Section 304.08 Table 304.081 | During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed. Density Ratio to be based on tests performed with Modified Comp active Effort. Scale A: Subbase Layer Characteristic Density Ratio (CDR) ≥ 98% Base Layer CDR ≥ 100% Scale B: Subbase Layer CDR ≥ 97% Base Layer CDR ≥ 98% 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot. Scale C: Mean Value of Density Ratio (3 tests): Subbase Layers >98% Base Layers >100% ATTACHL: Compaction Test Results | Document Review | Each Lot Where applicxable | IP | PE | Compaction Test Rersults
6.2 | Post Compaction Materials Testing (Results) | Section 304.10 Section 304.11 RC 500.02 | Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type. 20mm Class 3: Grading 26.5mm 100% 19.0mm 95-100% 13.2mm 75-95% 9.5mm 60-90% 4.75mm 42-76% 2.36mm 28-61% 0.425mm 14-29% 0.075mm 6-14% PI between 0 to 10 20mm Class 4: Grading 26.5mm 100% 4.75mm 42-76% 0.425mm 10-28% 0.075mm 2-14% PI between 0 to 20 PI x % passing 0.425 mm sieve (max) 450 Scale C: Post compaction material testing is not required (Choose NA) | Document Review | Each Lot Where applicable | IP | PE | Compaction Test Rersults
6.3 | Survey As-Built - Surface Level | IFC Drawings Section 304.06 Table 304.061 Table 304.062 | No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction. Subbase course shall be not < the specified thickness by more than 15 mm. Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness. The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm. Scale A: A minimum of 80 measurements per lot Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm Base: mean range ±5mm, maximum Standard Deviation of 8mm Scale B: A minimum of 40 measurements per lot Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm Base: mean range ±8mm, maximum Standard Deviation of 10mm Scale C: Lower Subbase (mm) +15/ -25 Upper Subbase (mm) +10/ -25 Base (mm) +/-15 | Document Review | Each lot | IP | PE/Surveyor | Survey Conformance Report
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /