## MTM Stormwater
ConQA Team Notes:
Document Title: |  | ITP-RAIL-CAMMS-MTM StormWater Drainage
ITP Description: |  | CAMMS MTM Stormwater Drainage
Discipline (e.g. CIV/STR/RAIL): |  | RAIL
Revision Number: |  | 0
Revision Date: |  | 2022-08-12
ITP created by: |  | Justin Kreinberg
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Camms Road Project
Inspection & Test Plan - Subsurface Drainage (Supply and Install)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2022-08-12
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 701 (May 2020) | N/A | N/A | N/A | N/A | N/A | N/A
1.2 |  | VicRoads Section 705 (June 2021) | N/A | N/A | N/A | N/A | N/A | N/A
1.3 |  | MTM Track Drainage L1-CHE-STD-030 (July 2018) | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries-Materials
2.1 | Drainage Pit - Supply | Section 705.07 | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with 705.07. Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | SE | Teambinder Material Approval
2.2 | Drainage Pit - Step Irons | Section 705.04 | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | SE | Teambinder Material Approval
2.3 | Drainage RCP Pipes - Supply | Section 701.05 | Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with 701.05. Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | SE | Teambinder Material Approval
2.4 | Drainage Flexible Pipes - Supply | Section 701.07 | Flexible pipes shall be supplied in accordance with 701.07 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | SE | Teambinder Material Approval
2.5 | Drainage Slotted Pipes - Supply | Section 701.07 | Subsurface drainage shall be supplied in accordance with 702.04 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | SE | Teambinder Material Approval
2.6 | Drainage Bedding Material - Supply | Section 701.09 | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | SE | Teambinder Material Approval
2.7 | Drainage Backfill Material - Supply | Section 701.09 | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | SE | Teambinder Material Approval
3 | Preliminaries-Procedures
4 | Pre Construction
4.1 | Survey Set Out-Pits | IFC Drawings Section 701.10 | Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10 ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP): | Visual inspection | Each Lot | IP | SE | This ITP
5 | Construction - Pit Installation
5.1 | Pits-Pit Excavation | IFC Drawings Section 705.05 | Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit. | Visual inspection | Each Lot | IP | SE | This ITP
5.2 | Pits-Excavation Foundation | IFC Drawings Section 705.05 | Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness: > 80mm for clay foundations > 150mm for rock foundations | Visual inspection | Each Lot | IP | SE | This ITP
5.3 | Pits-Placement of Pit | IFC Drawings Section 701.10 | Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm | Visual inspection | Each Lot | IP | SE | This ITP
5.4 | Pits-Jointing | Section 705.11 | All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter. Exposed reinforcement shall be coated with an approved epoxy treatment | Visual inspection | Each Lot | IP | SE | This ITP
5.5 | Pits-Shaping of Floor | Section 705.13 | Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe. | Visual inspection | Each Lot | IP | SE | This ITP
5.6 | Pits-Step Irons | IFC Drawings Section 705.12 L1-CHE-STD-030 | Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser | Visual inspection | Each Lot | IP | SE | This ITP
5.7 | Pits-Fitting of Covers | IFC Drawings Section 705.17 | Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement. Height shall be within 10mm of the design level | Visual inspection | Each Lot | IP | SE | This ITP
5.8 | Pits-Pit Lids | IFC Drawings L1-CHE-STD-030 | All stormwater pits shall be provided with a locakable minimum Class D piit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030 | Visual inspection | Each Lot | IP | SE | This ITP
5.9 | Pits-Backfilling Around Drainage Pits | Section 705.18 | Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal | Visual inspection | Each Lot | IP | SE | This ITP
5.10 | Pipes-Trench Excavation | IFC Drawings Section 701.15 | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of: > 300mm, < 600mm for RCP > 150mm for Flexible Pipe The base of the trench shall be compacted to refusal using mechanical plant. | Visual inspection | Each Lot | IP | SE | This ITP
5.11 | Pipes-Bedding Placement | IFC Drawings Section 701.16 | Bedding material shall be provided and placed in the full width of the trench to the below minimum: > 100mm where D<1500mm > 200mmwhwere D≥1500mm Bedding material shall be placed and compacted in layers <150mm loose thickness | Visual inspection | Each Lot | IP | SE | This ITP
5.12 | Pipes-Placement of Pipe - RCP | IFC Drawings Section 701.17 Section 701.20 | Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered. Gaps between spigot and socket are in accordance with the manufacturers specifications The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length | Visual inspection | Each Lot | IP | SE | This ITP
5.13 | Pipes-Placement of Pipe - Flexible Pipe | IFC Drawings Section 701.17 Section 701.22 | All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications | Visual inspection | Each Lot | IP | SE | This ITP
5.14 | Pipes-Lifting Holes | Section 701.18 | Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed. | Visual inspection | Each Lot | IP | SE | This ITP
5.15 | Pipes-Survey Conformance | Section 710.10 | Location of drainage shall be verified by a surveyor prior to backfilling | Visual inspection | Each Lot | IP | SE | This ITP
5.16 | Pipes-Backfill Placement | IFC Drawings Section 701.16 | Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness. Filling shall not be placed within 2.0m of the open end of the pipe. | Visual inspection | Each Lot | IP | SE | This ITP
5.17 | Pipes-Backfill Testing | IFC Drawings Section 701.20 Section 701.29 | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill) Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer | Visual inspection | Each Lot | HP* | Nominated Authority | This ITP Attach record of test report Attach material delivery docket
5.18 | Slotted Pipes-Trench Excavation | IFC Drawings Section 702.08 | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of > 150mm for Flexible Pipe The base of the trench shall be compacted to refusal using mechanical plant and be <50mm below the specified level of the invert | Visual inspection | Each Lot | HP | SE | This ITP
5.19 | Slotted Pipes-Geotextile placement | IFC Drawings | Trench to be wrapped with geotextile in accordance with the manufacturers specifications. All laps are to have 150mm lapped at the top of the trench | Visual inspection | Each Lot | IP | SE | This ITP
5.20 | Slotted Pipes-Bedding Placement | IFC Drawings Section 702.09 | Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level | Visual inspection | Each Lot | IP | SE | This ITP
5.21 | Slotted Pipes- Placement | Section 702.03 Section 702.09 | Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe. | Visual inspection | Each lot | IP | SE/Site Supervisor | Sign ITP
5.22 | Slotted Pipes-Backfill Installation (Granular Filter Material) | Section 702.09 | Material shall be placed moist and compacted in layers not exceeding 300mm. The method of compaction shall be in accordance with the procedures and reviewed by the NA. | Visual, Doc. Review | Each lot | HP | SE, NA | Sign ITP Attach Backfill Delivery Dockets
5.23 | Slotted Pipes-Backfill Installation (No Fines) | Section 702.09 | All subsurface drainage shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing | Visual | Each lot | HP | SE, NA | Sign ITP Attach Backfill Delivery Dockets
6 | Post-construction / Post-installation Activities
6.1 | Flushing & CCTV | Section 701.28 Section 701.30 | All pipes shall be flushed clean from end to end on completion All drainage lines shall be inspected after completion of earthworks to subgrade level and prior to construction of the pavement layer by an independent testing organisation using CCTV | Record Review | Each lot | HP* | Nominated Authority | This ITP Attach Inspection record
6.2 | As Built Information | Section 701.10 | Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10 | Document Review | Each lot | IP | SE | Attach Survey Conformance Report
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /