## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0 | itp |  |  |  |  | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-RAIL-CAMMS-MTM-Stormwater Drainage
note | ITP Description: Stormwater Drainage
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): RAIL
note | Revision Number: 0
note | Revision Date: 12/08/2022
note | ITP created by: Justin Kreinberg
note | ITP approved for use by: Victor Mira
note | 1.1 - Non Dependent
note | Reference Documents: VicRoads Section 701 (May 2020)
note | 1.2 -
note | Reference Documents: VicRoads Section 705 (June 2021)
note | 1.3 -
note | Reference Documents: MTM Track Drainage L1-CHE-STD-030 (July 2018)
section | Preliminaries-Materials
checkpoint | 2.1 Drainage Pit - Supply
note | REFERENCE: Section 705.07
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with 705.07.
textbox | Enter: Teambinder Material Approval number
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Teambinder Material Approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Drainage Pit - Step Irons
note | REFERENCE: Section 705.04
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
textbox | Enter: Teambinder Material Approval number
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Teambinder Material Approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Drainage RCP Pipes - Supply
note | REFERENCE: Section 701.05
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with 701.05.
textbox | Enter: Teambinder Material Approval number
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Teambinder Material Approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Drainage Flexible Pipes - Supply
note | REFERENCE: Section 701.07
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Flexible pipes shall be supplied in accordance with 701.07
textbox | Enter: Teambinder Material Approval number
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Teambinder Material Approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.5 Drainage Slotted Pipes - Supply
note | REFERENCE: Section 701.07
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Subsurface drainage shall be supplied in accordance with 702.04
textbox | Enter: Teambinder Material Approval number
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Teambinder Material Approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.6 Drainage Bedding Material - Supply
note | REFERENCE: Section 701.09
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
textbox | Enter: Teambinder Material Approval number
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Teambinder Material Approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.7 Drainage Backfill Material - Supply
note | REFERENCE: Section 701.09
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
textbox | Enter: Teambinder Material Approval number
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Teambinder Material Approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries-Procedures
section | Pre Construction
checkpoint | 4.1 Survey Set Out-Pits
note | REFERENCE:
note | IFC Drawings
note | Section 701.10
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction - Pit Installation
checkpoint | 5.1 Pits-Pit Excavation
note | REFERENCE:
note | IFC Drawings
note | Section 705.05
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Pits-Excavation Foundation
note | REFERENCE:
note | IFC Drawings
note | Section 705.05
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
note | > 80mm for clay foundations
note | > 150mm for rock foundations
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.3 Pits-Placement of Pit
note | REFERENCE:
note | IFC Drawings
note | Section 701.10
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.4 Pits-Jointing
note | REFERENCE: Section 705.11
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
note | Exposed reinforcement shall be coated with an approved epoxy treatment
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.5 Pits-Shaping of Floor
note | REFERENCE: Section 705.13
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.6 Pits-Step Irons
note | REFERENCE:
note | IFC Drawings
note | Section 705.12
note | L1-CHE-STD-030
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them.
note | Step rungs do not come within 50mm of the top of the riser
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.7 Pits-Fitting of Covers
note | REFERENCE:
note | IFC Drawings
note | Section 705.17
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
note | Height shall be within 10mm of the design level
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.8 Pits-Pit Lids
note | REFERENCE:
note | IFC Drawings
note | L1-CHE-STD-030
note | ---------------------------------
note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable minimum Class D piit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.9 Pits-Backfilling Around Drainage Pits
note | REFERENCE: Section 705.18
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.10 Pipes-Trench Excavation
note | REFERENCE:
note | IFC Drawings
note | Section 701.15
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
note | > 300mm, < 600mm for RCP
note | > 150mm for Flexible Pipe
note | The base of the trench shall be compacted to refusal using mechanical plant.
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.11 Pipes-Bedding Placement
note | REFERENCE:
note | IFC Drawings
note | Section 701.16
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Bedding material shall be provided and placed in the full width of the trench to the below minimum:
note | > 100mm where D<1500mm
note | > 200mmwhwere D≥1500mm
note | Bedding material shall be placed and compacted in layers <150mm loose thickness
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.12 Pipes-Placement of Pipe - RCP
note | REFERENCE:
note | IFC Drawings
note | Section 701.17
note | Section 701.20
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
note | Gaps between spigot and socket are in accordance with the manufacturers specifications
note | The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.13 Pipes-Placement of Pipe - Flexible Pipe
note | REFERENCE:
note | IFC Drawings
note | Section 701.17
note | Section 701.22
note | ---------------------------------
note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.14 Pipes-Lifting Holes
note | REFERENCE: Section 701.18
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.15 Pipes-Survey Conformance
note | REFERENCE: Section 710.10
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Location of drainage shall be verified by a surveyor prior to backfilling
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.16 Pipes-Backfill Placement
note | REFERENCE:
note | IFC Drawings
note | Section 701.16
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
note | Filling shall not be placed within 2.0m of the open end of the pipe.
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.17 Pipes-Backfill Testing
note | REFERENCE:
note | IFC Drawings
note | Section 701.20
note | Section 701.29
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
note | Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: HP*
note | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
note | ---------------------------------
note | VERIFYING DOCUMENTS:
note | This ITP
note | Attach record of test report
note | Attach material delivery docket
textbox | Date Completed:
checkpoint | 5.18 Slotted Pipes-Trench Excavation
note | REFERENCE:
note | IFC Drawings
note | Section 702.08
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of > 150mm for Flexible Pipe
note | The base of the trench shall be compacted to refusal using mechanical plant and be <50mm below the specified level of the invert
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.19 Slotted Pipes-Geotextile placement
note | REFERENCE: IFC Drawings
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Trench to be wrapped with geotextile in accordance with the manufacturers specifications.
note | All laps are to have 150mm lapped at the top of the trench
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.20 Slotted Pipes-Bedding Placement
note | REFERENCE:
note | IFC Drawings
note | Section 702.09
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each Lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.21 Slotted Pipes- Placement
note | REFERENCE:
note | Section 702.03
note | Section 702.09
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe.
note | ---------------------------------
note | METHOD: Visual inspection
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE/Site Supervisor
note | ---------------------------------
note | VERIFYING DOCUMENTS: Sign ITP
textbox | Date Completed:
checkpoint | 5.22 Slotted Pipes-Backfill Installation (Granular Filter Material)
note | REFERENCE: Section 702.09
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | Material shall be placed moist and compacted in layers not exceeding 300mm.
note | The method of compaction shall be in accordance with the procedures and reviewed by the NA.
note | ---------------------------------
note | METHOD: Visual, Doc. Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE, NA
note | ---------------------------------
note | VERIFYING DOCUMENTS:
note | Sign ITP
note | Attach Backfill Delivery Dockets
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.23 Slotted Pipes-Backfill Installation (No Fines)
note | REFERENCE: Section 702.09
note | ---------------------------------
note | ACCEPTANCE CRITERIA: All subsurface drainage shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
note | ---------------------------------
note | METHOD: Visual
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP
note | ---------------------------------
note | RESPONSIBILITY: SE, NA
note | ---------------------------------
note | VERIFYING DOCUMENTS:
note | Sign ITP
note | Attach Backfill Delivery Dockets
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Flushing & CCTV
note | REFERENCE:
note | Section 701.28
note | Section 701.30
note | ---------------------------------
note | ACCEPTANCE CRITERIA:
note | All pipes shall be flushed clean from end to end on completion
note | All drainage lines shall be inspected after completion of earthworks to subgrade level and prior to construction of the pavement layer by an independent testing organisation using CCTV
note | ---------------------------------
note | METHOD: Record Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: HP*
note | ---------------------------------
note | RESPONSIBILITY: Nominated Authority
note | ---------------------------------
note | VERIFYING DOCUMENTS:
note | This ITP
note | Attach Inspection record
textbox | Date Completed:
checkpoint | 6.2 As Built Information
note | REFERENCE: Section 701.10
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Each lot
note | ---------------------------------
note | CATEGORY: IP
note | ---------------------------------
note | RESPONSIBILITY: SE
note | ---------------------------------
note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
textbox | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | ---------------------------------
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder
note | ---------------------------------
note | METHOD: Document Review
note | ---------------------------------
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | ---------------------------------
note | CATEGORY: HP*
note | ---------------------------------
note | RESPONSIBILITY: SE/PE/SPE
note | ---------------------------------
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Metropolitan Roads Program Alliance Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP