## Pipes Installation Checklist
ConQA Team Notes:
Document Title: |  | CHK-001-CIV-Stormwater Drainage Pipes Installation
Check list Description: |  | Stormwater Drainage Pipes Installation
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | [Date of Approval]
ITP created by: |  | Jon De Castro
ITP approved for use by: |  | Aldrin Guinchoma
Special Notes to ConQA Team : |  | This Checklist is only to be used in Camms Rd Project
Item | Task/Activity Description | Reference / ITP Reference | Acceptance Criteria | Pass | Fail | N/A | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
[7 empty] | Method | Frequency | Category
1 | Pipes - Survey Set-out | Section 701.10 IFC Drawings ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 4.1 | 1. Pipes are set-out in accordance to IFC Drawings and Section 701.10 with the following tolerances below. (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250 |  |  |  | Survey | Each Lot | HP* | SE | This Checklist Survey Report
2 | Pipes - Trench Excavation | IFC Drawings Section 701.15 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.12 | 1. Excavation for pipe have a horizontal clearance between the pipe and the excavation wall as per below. > 300mm, < 600mm for RCP > 150mm for Flexible Pipe 2. The base of the trench have been compacted to refusal using mechanical plant. Trench depth : ___________ Drawing Reference No: _____________________________________ |  |  |  | Visual inspection Measure | Each Lot | IP | SE | This Checklist
3 | Pipes - Bedding Placement | IFC Drawings Section 701.16 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.13 | 1. Bedding material provided and placed in the full width of the trench to the below minimum: > 100mm where D<1500mm > 200mmwhwere D≥1500mm 2. Bedding material placed and compacted in layers <150mm loose thickness @Jesse - please check bedding requirements as per design (use sand bedding?) |  |  |  | Visual inspection Measure | Each Lot | IP | SE | This Checklist Material Delivery Docket
4 | Pipes - Bedding Testting | IFC Drawings Section 701.20 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.14 | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). 2. Three (3) tests done per lot. 2. Bedding compacted to refusal by hand held mechanical equipment & material (Swell ≥ 2.5%) mean moisture ratio of 92% between the completion of rolling and the placement of overlaying laye. Responsible Engineer to confirm if the bedding testing is required for this lot. |  |  |  | Compaction Test | Each Lot | IP | SE | This Checklist Test Reports
5 | Pipes - Placement of Pipe - RCP | IFC Drawings Section 701.17 Section 701.20 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.15 | 1. Correct size of pipe installed Pipe Dia ________; Drawing Reference No. ___________________________________ 2. Pipes phycially checked and confirmed No Damage prior to install 3. Rebate and socket ends of pipe segments placed facing upstream and be fully engaged 4. Gaps between spigot and socket are in accordance with the manufacturers specifications 5. Lower portion of pipe in contact with the bedding layer and shaped to accomodate the joint collar 6. Correct type and size of rubber rings used and properly installed at pipe joints |  |  |  | Visual inspection Measure | Each Lot | IP | SE | This Checklist Material Delivery Docket
6 | Pipes - Placement of Pipe - Flexible Pipe | IFC Drawings Section 701.17 Section 701.22 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.16 | 1. Correct size of pipe installed Pipe Dia ________; Drawing Reference No. ___________________________________ 2. Pipes phycially checked and confirmed No Damage prior to install 3. Rebate and socket ends of pipe segments placed facing upstream and be fully engaged 4. Gaps between spigot and socket are in accordance with the manufacturers specifications 5. Lower portion of pipe in contact with the bedding layer and shaped to accomodate the joint collar 6. Correct type and size of rubber rings used and properly installed at pipe joints |  |  |  | Visual inspection Measure | Each Lot | IP | SE | This Checklist Material Delivery Docket
7 | Pipes - Lifting Holes | Section 701.18 ITP-008-CIV-Stormwater Drainage - Item 5.17 | 1. Lifting holes plugged off in accordance with the manufacturers specifications after the pipe is installed. |  |  |  | Visual inspection | Each Lot | IP | SE | This Checklist
8 | Pipes - Survey Conformance | Section 710.10 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.18 | Each run of underground drainage shall be Survey verified prior to backfilling. - Offset pits to kerb +/- 20mm Drawing Ref No._________________________________ - Plan location pits not adjacent to kerb +/- 100mm Drawing Ref No._________________________________ - Invert level of pipes at pits +/- 50mm Drawing Ref No._________________________________ - Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250 Drawing Ref No._________________________________ |  |  |  | Visual inspection Measure | Each Lot | IP | SE | This Checklist Survey Report
9 | Pipes - Backfill Placement | IFC Drawings Section 701.16 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.19 | 1. Correct type of Backfill material used. 2. Backfill material placed full width of bedding material and compacted in layers <150mm loose thickness. 3. Filling not placed within 2.0m of the open end of the pipe. |  |  |  | Visual inspection Measure | Each Lot | IP | SE | This Checklist
10 | Pipes - Backfill Testing | IFC Drawings Section 701.20 Section 701.29 ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.20 | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill). 2. Backfill material compacted to a density ratio > 97%. 3. Material with ≥ 2.5% have been maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer. |  |  |  | Compaction Test | Each Lot | HP* | SE | This Checklist Test Results
11 | Flushing & CCTV | ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.1 | In accordance with Section 701.28, Section 701.30 |  |  |  | Record Review | Each lot | HP | Nominated Authority | ITP-008-CIV-Stormwater Drainage Supply & Installation
12 | As Built Survey | ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.2 | In accordance with Section 701.10 |  |  |  | Document Review | Each lot | IP | SE | ITP-008-CIV-Stormwater Drainage Supply & Installation
13 | Repairs to Damaged Pipes | ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.3 | In accordance with Section 701.31 |  |  |  | Document Review for Repair Procedure CCTV Report Review Visual Inspection | Each lot | HP | Nominated Authority | ITP-008-CIV-Stormwater Drainage Supply & Installation
14 | Non-conformance Report (NCR) Closure | ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.4 | In accordance with MRPA Quality Management Plan |  |  |  | Document Review | Once, prior to closure of this lot / element / Work area | HP* | PE | ITP-008-CIV-Stormwater Drainage Supply & Installation