## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-CIV Landscaping - Planting Rev 0 | itp |  |  |  | Yes | ITP-CIV Landscaping - Planting Rev 0 | 05fc42bb-442f-4ebf-8923-70f7f2ecba29
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | ededcba4-123d-5ba3-98a7-f35785142093 |  | note | Document Title: ITP-CIV Landscaping - Planting
label | 77429000-cf62-5f9a-945d-98ed4eab2cef |  | note | ITP Description: Landscaping - Planting
label | 7b03aa0b-ebc3-55fc-bf4a-b6fd88153607 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 45cff9c8-249a-56bb-9927-b4571f7d8853 |  | note | Revision Number: 0
label | 7a3264c9-0802-511d-88a8-bc576d67f0a4 |  | note | Revision Date: 07/07/2022
label | cab4eabe-50ad-5c5a-b8b7-1dd64d281618 |  | note | ITP created by: Anthony Pearson
label | e58e726d-d6e8-5b67-9e84-d8f671cdecae |  | note | ITP approved for use by: Josie Pavlou
label | 91df0bc8-c464-51b8-9b8d-f308325a5f66 |  | note | Reference: IFC Drawings
label | edf6cd7d-ea3a-592c-83f7-42648228f5e8 |  | note | Vic Roads Section 720 (Nov '18)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Check for correct documentation
label | d7333de6-9847-5dc8-8e80-7e560877bdde |  | note | REFERENCE: Drawings and Drawing Register
label | 8b1b2a19-cd5c-52b7-91e6-86c3d2b3aaea |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using:
label | ad368125-5091-5f7d-a183-57cfd9111166 |  | note | –The correct and complete set of drawings
label | d8a037c3-1db8-599b-8bf2-a357f5d35687 |  | note | –All drawings are the latest revision
label | 3cd10063-b172-587b-a4a3-d5ec8d365635 |  | note | METHOD: Document Review
label | c9c91341-535f-5f27-8970-bd65441d8212 |  | note | FREQUENCY: Prior to Commencing works
label | 7822429b-c856-5578-aa5f-9ae579051599 |  | note | CATEGORY: N/A
label | 27ecc188-98a8-529a-9d83-c01fb25880e3 |  | note | RESPONSIBILITY: SE
label | c973bd2a-e4b1-560f-9e52-4ec8542fd3ce |  | note | VERIFYING DOCUMENTS: This ITP
text | 0674044c-277f-55be-81bd-acd7741d99fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Submission and records
label | 6e4c2045-b67d-5c84-8aa4-4846225c373c |  | note | REFERENCE: VicRoads Spec.
label | adf94b04-f019-5d32-bc8e-fd911de157bb |  | note | – Cl.720.03
label | 518a6587-0233-5516-a092-8367ffb4cc13 |  | note | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
label | 688ea0e0-b62e-5e53-93ba-1fcc0d0e8586 |  | note | Following information shall be provided to the superintendent:
label | 78e23197-8b2a-514a-9d87-452e25226313 |  | note | Inspections of plant stock for all plant species
label | 76eec676-daa8-5346-a444-b833c0306b0c |  | note | Records:
label | 378c54f5-fb5f-5200-9a13-96d329e2e61c |  | note | –Evidence of origin of indigenous provenance plant material
label | c082b68d-17a3-5014-87c8-9ad8aeecddac |  | note | –Analysis certificates for grass seed
label | d5a88fa3-891b-55bd-8ae7-03558f8aebca |  | note | –Details of suppliers
label | bdeeb4d9-8820-5038-8dfe-db6cfcd47080 |  | note | –Copies/Photos of fertiliser labels
label | 9b400fe4-66fa-5a49-a64b-633854b24c4b |  | note | METHOD: Document Review
label | 344141f0-8245-53ed-a5e6-cf0f11ee5508 |  | note | FREQUENCY: Prior to Commencing works
label | 707ee908-86e8-5076-8e6e-70cfd62e3600 |  | note | CATEGORY: HP
label | a27aaa9b-5d92-558c-a65a-eae68db7b6b2 |  | note | RESPONSIBILITY: SE, Superintendent
label | 9b337fc7-a3f3-5824-ac62-142f7e9e9a85 |  | note | VERIFYING DOCUMENTS: This ITP
label | e7237599-5e70-599e-85f2-4db325a587a8 |  | note | Attach Records to TeamBinder Approval Form
text | bd869664-6c01-5985-a7c4-a086c99f8d3f |  | textbox | Teambinder Approval number
text | b3a77750-1940-5d83-bb8b-7a8ee1274dc9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.3 Supply of Plant Stock
label | 1d60967e-a966-5546-8080-60bfbe71a231 |  | note | REFERENCE: VicRoads Spec.
label | 430da420-478b-5509-923b-b3a72655f574 |  | note | – Cl.720.04
label | b6870227-8428-5927-869d-2505005628bb |  | note | – Table 720.041
label | ebed25c5-2366-5ea8-9e2f-35c68f5067b6 |  | note | ACCEPTANCE CRITERIA: All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
label | 73b48c93-6172-5009-881a-0ec5def7d195 |  | note | – Plants are to conform to the supply properties specified in Table 720.041
label | 83b89061-c8b9-51d7-b60e-033840956361 |  | note | METHOD: Verify
label | 000ff965-bbf1-54b5-b4ab-31433a28ab75 |  | note | FREQUENCY: Prior to Commencing works
label | 63e39f93-8e13-57a7-b00f-d1987045cf40 |  | note | CATEGORY: N/A
label | 7d8269a6-3112-5641-bcde-a92a641c2270 |  | note | RESPONSIBILITY: SE
label | c00e8223-5152-5a83-9168-298cd80c55f0 |  | note | VERIFYING DOCUMENTS: This ITP
text | de212611-9193-56ed-8683-803a0ed4239b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Supply of indigenous plant stock
label | 4c4f1325-c550-5321-b491-72f696ff49f5 |  | note | REFERENCE: VicRoads Spec.
label | 96dcd7f1-ddb7-5355-985a-8381f2f7256c |  | note | – Cl.720.04
label | 535f60ba-74b9-5a31-a42a-5d220242b88f |  | note | ACCEPTANCE CRITERIA: A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
label | 6935b185-78d8-5065-8091-160effeba4c4 |  | note | – The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
label | a6b34593-2517-5958-992a-a4f36c1f2c39 |  | note | – species name
label | eb5abac7-0830-5290-aeeb-56d9c2721fe8 |  | note | – storage code
label | da0f404c-6fb3-58e4-b511-628a63cebfb2 |  | note | – collection locality – Latitude/longitude or AMG
label | e584f7de-6a69-5101-be95-603af823ce60 |  | note | – approximate number of parent plants sampled
label | 694f7c1b-224c-508a-8ab0-a5508e45e9d0 |  | note | – approximate number of plants in that local population
label | 9ba87d4e-f6ae-5912-b96d-1d40b92cee10 |  | note | METHOD: Verify
label | 3cbf455e-ea3b-5a5a-98dd-9ddd36f81509 |  | note | FREQUENCY: Prior to Commencing works
label | 61511258-c6c2-58a7-af27-267e2a7a9453 |  | note | CATEGORY: N/A
label | ad37ade0-4bfc-5283-8a03-32d1032fd5ed |  | note | RESPONSIBILITY: SE
label | d45b0ca6-e65e-5802-9c48-ac54d2aa0e62 |  | note | VERIFYING DOCUMENTS: This ITP
text | 34e487d3-5dc6-5351-a44b-ef4eb708ab85 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Supply of grass seed
label | 8992e108-9990-5cf0-b522-4813c5e7ff20 |  | note | REFERENCE: VicRoads Spec.
label | 5604c809-ef02-53c8-9da3-4b05aa26cc2b |  | note | – Cl.720.04
label | e90a3101-d980-5621-8878-2d3e250579f5 |  | note | – Table 720.045
label | 1a38e20f-10a1-56c9-8d3e-22abb2a5acd1 |  | note | ACCEPTANCE CRITERIA: Grass seed shall comply with Table 720.045
label | da079a83-9d59-5f27-ae73-08851aa21f8e |  | note | METHOD: Verify
label | 1ecfb537-721f-5b73-a47d-a43056e6b667 |  | note | FREQUENCY: Prior to Commencing works
label | 21e9d6ec-87b9-56a0-9274-dd3c5bc4c1c2 |  | note | CATEGORY: N/A
label | 444551d7-d821-5d6b-800a-5f2690685c60 |  | note | RESPONSIBILITY: SE
label | 84a44efd-f6a9-5552-8a53-4cf13b4b9280 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4891b334-303d-505d-b8dd-24992708b4b8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 3.1 Planting Section Approval
label | 31abddf6-0292-5779-b7fa-a9ce851e7920 |  | note | REFERENCE: VicRoads Spec.
label | 5365f746-6f51-5804-83e6-67fd08ef328b |  | note | – Cl.720.06
label | 26896c34-f64d-504a-a7fd-8c398b1d559c |  | note | –ECO-LANF-005
label | 1e9bfa12-c82a-5ac8-9b4b-b636594e2f97 |  | note | ACCEPTANCE CRITERIA: Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
label | 95aac2cf-dcfb-516f-8498-0525bc4e74de |  | note | METHOD: Verify
label | 89e8e522-9d00-5d50-b201-71a64030a3a8 |  | note | FREQUENCY: Once
label | b9c6d056-e184-5914-8bf1-0493fbe2117f |  | note | CATEGORY: HP
label | 84370671-cb28-5949-9d4f-a2d2ccf94aa3 |  | note | RESPONSIBILITY: SE
label | 4eb9072c-0441-555d-bfe7-b5487a7810de |  | note | VERIFYING DOCUMENTS: This ITP
text | a735db1d-9868-5d38-8e29-da7bb221d491 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.2 Pest and Weed Control
label | ba6b1540-a0c9-5839-94d9-268059c9e739 |  | note | REFERENCE: – Cl.720.05
label | 929ae378-f101-5c87-8db6-35a0cdb4e53d |  | note | ACCEPTANCE CRITERIA: The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
label | e2bf77fa-dc96-5f8f-90aa-2784ccb9891c |  | note | Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
label | 878aa50f-c93c-5b6d-b06f-8c2bcb0f6cca |  | note | METHOD: Verify
label | 46591df2-db04-599e-8a0e-eb3b087071c6 |  | note | FREQUENCY: Once
label | e223a018-e2fc-5b7b-9a44-3be83ce5db1c |  | note | CATEGORY: HP*
label | beb392ab-d295-5ee9-95fe-dfede0b99581 |  | note | RESPONSIBILITY: SE
label | cb54675a-4cb1-5045-835a-ec0a5acf3715 |  | note | VERIFYING DOCUMENTS: This ITP
text | 64b65e91-2eef-5f5f-85b9-f9ef80aecbee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Setting out planting areas
label | 38a38118-0473-5e8e-9554-db7b1f6960eb |  | note | REFERENCE: VicRoads Spec.
label | 7dd14a35-9f93-58f5-a095-bd60b891b5c5 |  | note | – Cl.720.06
label | df8a2e07-626a-5f1a-be43-9e94ea4819b9 |  | note | ACCEPTANCE CRITERIA: Planting areas are to be set out to the location and shape specified in the landscape drawings.
label | 2b1e070a-4125-50d0-a0b7-63f4380a0ce8 |  | note | – Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
label | 3535728c-81a1-5d88-a07f-a77d185d8772 |  | note | – Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
label | 0e36b26e-b43e-555a-96e1-c28010570278 |  | note | METHOD: Verify
label | f5125479-83af-5947-902f-d5bbd0884c47 |  | note | FREQUENCY: Each Applicable Lot
label | e047076c-7a4c-5d02-86b5-e7a37859b435 |  | note | CATEGORY: N/A
label | 8a296442-72a4-5f24-bee0-2d7eacc937e8 |  | note | RESPONSIBILITY: SE
label | 8794d097-37af-5c3f-8d58-3382788782af |  | note | VERIFYING DOCUMENTS: This ITP
text | 24c6febe-1434-5780-b3c7-ac5341876af8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 4.1 Planting
label | 085f2f9b-d91f-5d60-930a-f8eceeb55c53 |  | note | REFERENCE: VicRoads Spec.
label | f4c25964-7c1d-5fbe-ba9a-d46d62ddf8aa |  | note | – Cl.720.09
label | 343b98eb-8462-580a-8cc4-9a191f75fb47 |  | note | – ECO-LANF-005
label | dbe5670c-3523-5ab2-9d5c-84be23488a7e |  | note | ACCEPTANCE CRITERIA: All planting will be undertaken in accordance to Ecodynamics ITP ECO-LANF-005
label | 2bb2c125-acee-5bfa-b09d-9e37b48dbc36 |  | note | METHOD: Verify
label | 650b77b6-e8c4-585a-9a55-e2289dbc66c6 |  | note | FREQUENCY: Each Applicable Lot
label | c36279ac-b7ec-53db-9e2f-a4a6f9b5f159 |  | note | CATEGORY: N/A
label | 271e9984-1d54-5948-b5be-2b29b2bea7bc |  | note | RESPONSIBILITY: SE, Foreman
label | 434fcda8-e92e-5988-9841-e13bc4b43022 |  | note | VERIFYING DOCUMENTS: This ITP
text | d1d54974-c9e2-5641-8004-4292c170cdd3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | 4.1 Site Final Inspection
label | 11d45b9a-6993-53e0-bbdc-63a1a3c7b605 |  | note | REFERENCE: ECO-LANF-5
label | b99f1f7d-7181-5312-8aec-1312378697c2 |  | note | ACCEPTANCE CRITERIA: Ecodynamics ITP signed and completed
label | 5f75dc36-c40b-5e1e-9596-2c819ae5bdf8 |  | note | METHOD: Document review & Site Inspection
label | 14ee9675-f42b-531c-8a87-e47a401f1065 |  | note | FREQUENCY: Following completion of planting works
label | 0eb6d142-d1bb-5d8f-9ce0-187e5092356c |  | note | CATEGORY: N/A
label | 70c81b3f-7abe-577d-b0db-55f35b91ece4 |  | note | RESPONSIBILITY: SE
label | 9929b1f9-e9d4-54f9-92c5-c54b2ea268a2 |  | note | VERIFYING DOCUMENTS: Sub-Contractor ITP completed, signed and to be attached
text | cb5b5030-7b7b-5684-832b-28f872968ad9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | d46276a3-30db-5d97-a59e-262490e0a773 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d211defb-309b-5313-9243-e4afb54d12d3 |  | textbox | Name:
text | fc993cca-f9f2-5502-8496-319f434c9edc |  | textbox | Position:
text | f23776f9-9882-5c31-b0cc-94c42cf00df4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-Rail-Track Removal & Construction Rev 1 | itp |  |  |  | Yes | ITP-Rail-Track Removal & Construction Rev 1 | 060a6c16-0208-4ac0-bb36-af4c30631585
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | db7edd85-e0a4-4ee5-8b07-d374592de747 |  | note | Document Title: ITP-Rail-Track Removal & Construction
label | 9fc5de94-2973-474a-88f0-34c94ed9b9cd |  | note | ITP Description: Track Removal & Construction
label | 668fe582-9574-4c6a-b678-af1b7f851cfa |  | note | Document Number (in Teambinder): n/a
label | 395cd2e4-c18e-4a74-a093-52952a0c1a67 |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | f552de8b-221b-4a97-87c4-7edb819aa359 |  | note | Revision Number: 1
label | ac77438f-b5ed-412c-b9e2-d2297f646d46 |  | note | Revision Date: 7/12/21
label | 9c5e4327-0cd1-4992-b440-0fabdce793b5 |  | note | ITP created by: Ty Qiu
label | 08e2d604-3d77-454e-8c8f-276dce2e12af |  | note | ITP approved for use by: Aldrin Guinchoma
label | e6895917-dd33-403a-bf04-be57b206e60e |  | note | 1.01 - Clyde Rd Rail Civil IFC Drawing Set, MRP-ACD-TRANS-000358-MRP-DPK-016-00-CPW-0003-0, Design Change Notice MRP-016-C-ACD-FRM-03-NWA-CPW-0001"
label | 9b6fa20c-bb7b-49bc-95cf-15270e74e8e8 |  | note | 1.02 - L1-CHE-STD-025 Transit Space and Clearances Standard
label | a46d1e17-8c66-4632-a4f3-98bfaf2152b9 |  | note | 1.03 - L1-CHE-STD-039 Track Design and Construction
label | 9b4b3307-d99e-448a-9136-89abd2dcdda3 |  | note | 1.04 - L1-CHE-SPE-316 Concrete Sleepers
label | dd10edc9-d457-4ef5-9cf5-22a9a0544db5 |  | note | 1.05 - L1-CHE-SPE-064 Ballast Supply Specification
label | 0824bc36-28a7-4baa-b394-35d09bdb8918 |  | note | 1.06 - L1-CHE-SPE-315 Resilient Rail Fastening Assemblies
label | efe4a1bc-ff4c-4420-abc4-508e9b888b1a |  | note | 1.07 - L1-CHE-SPE-003 Track Geometry Tolerances
label | 2d0be18b-f9c0-44dc-bf0b-0694d2f28da0 |  | note | 1.08 - L2-TRK-PRO-028 Requirements for Welding Track
label | b5e6bc6d-3c5b-43dd-bb2c-31894556e5e5 |  | note | 1.09 - L2-TRK-PRO-029 Laying Rail - Bolted, Welded and LWR
label | c16f5d95-5959-45c8-b007-8349bbcd4599 |  | note | 1.10 - L2-TRK-PRO-015 Stress Control of Continuously Welded Rail
label | 3b205932-5e79-4ad5-94e9-398df765172d |  | note | 1.11 - L2-TRK-PRO-016 Closure Rails
label | 7667b4e8-d592-4373-afed-f9e8a7d098e2 |  | note | 1.12 - L2-TRK-PRO-014 Rail Welding Process
label | 6824f2d6-03e9-44e8-8587-04855877ce30 |  | note | 1.13 - L4-TRK-FOR-128 Track Geometry Conformance Certificate
label | 16194134-f908-43f1-8775-2157b577aaa8 |  | note | 1.14 - L4-TRK-FOR-129 Track System and Component Conformance Certificate
label | 3e402eeb-76f4-4935-ab69-4a4b4b86714a |  | note | 1.15 - PTC Heavy Rail Track Construction Standards Drawing F598
label | b2941b5f-3a82-4d8d-9a6b-cbc3ce66f907 |  | note | 1.16 - L1-CHE-STD-029 Earthworks and Formation Standard
label | 966fc2db-d217-4ac1-b2d7-da2bec853cd5 |  | note | 1.17 - L1-CHE-SPE-178 Earthworks & Formation Specification
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.01 Obtain and submit Material Certificate of Compliance for Track Materials: Rail Strings, Concrete Sleepers, Track Jewellery, Geofabric, Ballast Matting, Ballast 60mm Aggregate, Welding Kits, Welding Crucibles
label | 94441d13-f94c-4c3c-9878-333f5fc84d9a |  | note | REFERENCE: IFC Drawing(s)
label | 05d47519-0d90-4582-898e-a15e42d221ed |  | note | Bill of Materials
label | 2eb8e790-f400-4b5a-9593-6b71777c0961 |  | note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | 42319622-1322-4937-83bf-72b37cd0dc89 |  | note | Attach: Manufactuer Cetificates of Compliance
label | 91cf926c-09d2-40f7-aa34-59081a4e6cb0 |  | note | METHOD: Review Document
label | 4efb2814-b1a1-4d7c-a33f-d3349ea1baee |  | note | FREQUENCY: Once
label | f173a0da-67ed-4e70-acd6-8054e760a90e |  | note | CATEGORY: HP
label | 41dbd476-0eac-498c-b2b7-6b23b7f22c8f |  | note | RESPONSIBILITY: Site/Project Engineer
label | f0feafb9-20fc-44b4-8a4f-5dd65ea24392 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4e6537b9-d56a-4893-b8e2-12dff7fc38a5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 Submit Welding Procedure/welding qualification welders Record
label | be582768-7ead-4d4e-8171-e35ca8a5e28a |  | note | REFERENCE: AS 1085.20 Welding Rail Steels
label | 3bc583d7-da07-415b-a6c3-41347143b348 |  | note | ACCEPTANCE CRITERIA: Qualified personnel & welding accordance with manufacturers specs.
label | df7faa11-6843-4a27-8624-5f1b6ab8d7b1 |  | note | METHOD: Review Document
label | 0a83e01e-1e31-4c80-b617-3e8936accfa2 |  | note | FREQUENCY: Once
label | 5254f80f-9605-4e08-ad42-e37d90d17ea3 |  | note | CATEGORY: HP
label | 8130ccd4-cd8e-4fb7-bdf3-f1a836167c41 |  | note | RESPONSIBILITY: Site/Project Engineer
label | bbeab88c-8d9c-4076-bdcd-0e67d7cd78b1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 2fd5fe58-c257-440f-b6a2-68d0c3679eb2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03 Inspect supplied items upon delivery
label | 6a3c93b4-60a8-4628-85f0-1e8370347f3f |  | note | REFERENCE: Bill of Materials
label | 262d2092-764e-4dd8-b095-c3c2ad84d67b |  | note | ACCEPTANCE CRITERIA: No damage or debris on components
label | dbdafd86-a110-4110-850c-96f855ec1e75 |  | note | Validate total number and type of components matches drawing
label | 2d2f4904-e2d2-4ad7-bb4b-8becf42d4fb0 |  | note | Attach: Photos on site:
label | ba67b5c7-3008-4cf2-aa2c-00b9398ae928 |  | note | Track Rail
label | c077cdb9-d0e8-40ce-add2-91df1bbca8c3 |  | note | Track Sleepers
label | 11e568e3-ad2e-4931-9392-d1725994eac2 |  | note | Track Jewellery
label | 4f68d94f-399c-46ac-84f9-1197191ea5fb |  | note | Geofabric
label | 626d5973-2d82-4ff1-b269-7bed02c77203 |  | note | Ballast Matting
label | 66cdcb6b-f66a-4a9a-92e1-b552ab5b3267 |  | note | Ballast 60mm Aggregate
label | b0d5753d-9ab5-4e1d-91b9-5655bc3b3846 |  | note | Welding Kits
label | bb843a23-4134-461a-beea-3f39edb0b0af |  | note | Welding Crucibles
label | cf87c022-f216-4916-95a7-8766a1de5639 |  | note | METHOD: Visual, Measure
label | f0e342f2-44fc-4178-a67b-7b003d0e615d |  | note | FREQUENCY: Per delivery
label | cf08593d-cea7-47de-9f37-59c70e5c0a0c |  | note | CATEGORY: IP
label | c1cf8eb9-c25d-4571-8c82-ad2339049626 |  | note | RESPONSIBILITY: Site/Project Engineer
label | 691f12fa-508f-472c-a9dd-5847bf4a2550 |  | note | VERIFYING DOCUMENTS: Material Inspection Report
text | 9041ff19-8ee9-43a1-b7d2-a63ec841ce5e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.04 Confirm extent of track removal required for civil works
label | 129967bb-f1b8-4d86-b4f3-85a989bf98ee |  | note | REFERENCE: IFC Drawing(s)
label | 51a592a3-fc87-4f92-a482-6381bed6f392 |  | note | Track Construction Site Mudmap
label | 2a821c0c-d534-4d72-9f2d-2b7af3788474 |  | note | ACCEPTANCE CRITERIA: Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site
label | 624c9f0d-1ec7-4920-95ad-987a663b8e40 |  | note | Pre-removal survey of existing track alignment
label | bdba907d-dda8-404c-9aa9-4b360acab5cf |  | note | METHOD: Visual, Measure
label | dbfdc8bb-cfe0-4945-b717-7aad819cb472 |  | note | FREQUENCY: Once
label | 36c3936d-f5d0-4845-a0db-1cb5dedba6b4 |  | note | CATEGORY: IP
label | 90c48a65-4f22-4faa-9969-5b92711ab9b8 |  | note | RESPONSIBILITY: Site/Project Engineer
label | 1c34e832-35e7-4cb6-84f6-e8869b120cb6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0f4d26db-f2d2-4b2c-9001-44c5f5b911e4 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.01 Deconstruct and remove track components, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
label | a7e22fa4-cda1-47a1-95e6-a8b480f54842 |  | note | REFERENCE: IFC Drawing(s)
label | 2b484d30-33b6-45a8-b62a-a7c94d1cbea0 |  | note | Track Construction Site Mudmap
label | 4bdc90dd-9d8b-43a6-9592-f9ebbbb26425 |  | note | ACCEPTANCE CRITERIA: Track structure to be removed to the designated limits as identified.
label | 0eb9d513-3b2d-430e-aafb-ce2f62b20a1d |  | note | Visual confirmation of removal on site
label | 0b066747-81e3-48f8-b1ab-424c6c41156b |  | note | METHOD: Visual, Measure
label | 27772082-c87d-4343-adf4-6e4ceb0f6819 |  | note | FREQUENCY: Once
label | 6ee33d29-0e5c-4361-8c18-fee48d238e20 |  | note | CATEGORY: IP
label | 1a352544-6fef-4bc7-9d34-6f5c56fb7456 |  | note | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
label | 9e4453fe-7ce6-4451-83cd-ff29caa006af |  | note | VERIFYING DOCUMENTS: This ITP
text | 88a9ec2b-454b-415e-b915-7be21db05634 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 Earthworks completed and site handed over from Civil Contractor
label | bf0882f7-3cc3-46c4-a31e-6b337e01e308 |  | note | REFERENCE: L1-CHE-SPE-178 Earthworks & Formation Specification
label | 232d2f68-d215-4ad1-a10f-d76cfd6c3f8b |  | note | ACCEPTANCE CRITERIA: Confirmation of completion of underlying ITP(s)
text | ee1bc114-540b-44f7-a3f5-f8f3049a28cf |  | textbox | Underlying ITP reference:
label | db7df987-4d15-4891-a491-9584edb259c1 |  | note | METHOD: Visual, Measure
label | b05f0288-b54e-4b8c-93b8-0e63c0c5d989 |  | note | FREQUENCY: Once
label | 2db37856-35ab-4020-bd67-e51ee76894e8 |  | note | CATEGORY: IP
label | 704888f4-319b-4cc7-9521-b9515f234c09 |  | note | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
label | f1f7b2f8-ea26-4a80-8cb8-0e2f45671b8f |  | note | VERIFYING DOCUMENTS: This ITP
text | 2af81042-ac03-420e-9b37-cb769575dcc5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.03 Installation of Bottom Ballast
label | bdedd4ea-094f-468a-bc38-c3d4da60d8e7 |  | note | REFERENCE: PTC Heavy Rail Track Construction Standards Drawing F598
label | f45db2f9-b427-4d32-9db4-33c12f8f502b |  | note | ACCEPTANCE CRITERIA: Overall Minimum 300mm bottom ballast depth
label | 42d8480c-cc2c-43e4-bb5c-0661e5227e64 |  | note | Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compacted using a vibratory compaction plate
label | cfa69e44-f8ed-4f86-8527-3e873106601a |  | note | Bottom Ballast to be left 20-40mm below final design level
label | 2ee65c7d-a11a-473b-82ec-c16bb1b68512 |  | note | Tolerance:
label | 31b4aeab-46b5-47d9-93e7-d6a7a4b0510e |  | note | Under sleeper -0mm/+25mm.
label | fc6e54eb-382e-4f68-9817-b26648eeb6f1 |  | note | Attach Site Photo:
label | c2e2acd3-02bb-46e9-be56-f0a9e466a7ce |  | note | Installed Bottom Ballast Layer
label | 10b2f9e3-4f6c-4a04-870d-67de4703896f |  | note | METHOD: Visual, Measure
label | 47e21be1-908c-4bc8-b506-345fbd93aac0 |  | note | FREQUENCY: Once
label | 0e4de03d-2c27-4f4e-8e12-7ae535ee3a12 |  | note | CATEGORY: IP
label | 72a33a6d-9a41-4571-b6b8-616edc9b41ad |  | note | RESPONSIBILITY: Track Surveyor , Track Supervisor , Site/Project Engineer
label | 64ba8f21-ef41-4cb7-89a2-158e887a17a6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 80eda710-c38d-472f-9c4d-493e61c19566 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.04 Laying of Sleepers
label | 5babd9d1-b86b-4c4a-b3a8-caa911130bff |  | note | REFERENCE: L1-CHE-SPE-003(1) Heavy Rail Construction Tolerances
label | 853fb610-8f68-457b-9dbe-3ae41daf02b3 |  | note | L2-TRK-PRO-028 Requirements for Welding Track
label | 818dd035-fec8-4933-9519-cc7f1dfa5d43 |  | note | ACCEPTANCE CRITERIA: Sleepers square at nominal 685mm +/-25mm for open track
label | de7197af-2ee2-4879-9568-b955fd8ceda3 |  | note | Sleepers square at nominal 600mm +/-25mm through RRV Pad and CH44317.057 - 44407.057
label | c54004d2-004c-4354-a2ca-b43f8a8d739e |  | note | Attach Site Photo:
label | fc9b4697-bcef-4fec-94fd-783867f8bc02 |  | note | Laid Sleepers
label | 9a47755c-dee7-4916-9e56-49013ebeb85e |  | note | Sleeper Spacing Measurement
label | 4f313f8a-a8e2-428c-a71c-ff0e5e052777 |  | note | METHOD: Visual, Measure
label | 1cefdc90-fea0-439c-91d1-60894b8a3948 |  | note | FREQUENCY: Once
label | f46a0b87-9451-4d7f-998c-8fa84946b358 |  | note | CATEGORY: IP
label | d6a5aad2-c863-4761-ad69-dcb83395a136 |  | note | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
label | 941579e1-689e-4a3b-9ad0-f8c7ebbd594f |  | note | VERIFYING DOCUMENTS: This ITP
text | ef70a2aa-729b-46cc-b45c-8b328024a870 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.05 Rail & Fastening Installation
label | f79b13ce-92c8-4306-944d-b7309064f550 |  | note | REFERENCE: L2-TRK-PRO-016 Closure Rails
label | 3e51234e-c823-4902-95e3-f2f1ab5a1d8f |  | note | PTC Heavy Rail Track Construction Standards Drawing F598
label | 7c844a21-9d82-4fae-bf04-dd7b17a9a649 |  | note | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
label | efcdfa4e-1ab7-403f-8307-190c068f96f8 |  | note | New Rail lengths installed to be as per the approved Clyde Road Stressing Plan
label | c9d1298a-e6b2-43cf-a930-8ef26734f0df |  | note | Gauge of track to be checked upon installation of fastenings
label | 76c0c1b6-a27b-4aae-8e9b-1264abb4d01e |  | note | Gauge +4mm/-3mm
label | d5571ae5-158a-407e-8f05-774a0b763ece |  | note | Gauge Variation over 2m 4mm
label | 7595f7f4-8a6b-45e0-8962-3937e43f03d0 |  | note | Attach Site Photo:
label | 2473f139-7809-49c9-b284-b2b619cd3795 |  | note | Laid rail
label | 430d6c06-74da-4ea1-b1ea-826cfc9973e6 |  | note | Rail joint to existing weld measurement
label | 44afcd46-1dfe-416e-b6e4-f499a8dc5b6d |  | note | Rail joint between sleeper bay measurements
label | faf074e3-d237-4ca6-aab7-0bad5e5cc214 |  | note | METHOD: Visual, Measure
label | 014c24c2-2627-499d-84ec-05b21ca99be8 |  | note | FREQUENCY: Once
label | a4958a4b-88f8-4a7d-8fda-9597ddd8a6e8 |  | note | CATEGORY: IP
label | 7c6657e9-a465-4184-b4f2-e11738ade23f |  | note | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
label | e97311f9-8094-43e5-93e5-61135a10096a |  | note | VERIFYING DOCUMENTS: This ITP
text | 93a50127-4adf-49e3-ad21-e97817ad2da9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.06 Track Tamping
label | c17e1bc3-8070-44b5-9a09-6efb84237583 |  | note | REFERENCE: L1-CHE-SPE-003(1) Heavy Rail Construction Tolerances
label | 70fa150f-23f3-4341-8c2d-0554cae9b7ac |  | note | ACCEPTANCE CRITERIA: New Track (mm)
label | 11cc0880-fb85-40e6-9ef4-e4373e505008 |  | note | Gauge: +3 / -3
label | 14d0a0bf-7985-4b31-a3c0-e2ee2c84f973 |  | note | Gauge Variation in 2m: 4
label | ee5c857a-17b2-4676-8a32-d2daba7adc0a |  | note | Line (10m Chord): +4 / -4
label | 12949649-6e2d-4451-831f-96aee0d2a103 |  | note | Twist (3.5m Chord): +2 / -2
label | 67474440-90db-4e3a-a1a2-67d3423be1b4 |  | note | Top (10m Chord): +5 / -5
label | 17bf539c-aa9c-4d7b-bdd3-e62dd4c21faf |  | note | Cant: +5 / -5
label | 392b56a0-86da-41dc-a05f-4a70aac09466 |  | note | General Alignment: +15/ -15
label | f69aea9a-8dc6-4bfb-a2eb-d8d962283abd |  | note | Upgraded Track (mm)
label | f9517aa0-ad4f-444f-b840-d1e7aa6010b5 |  | note | Gauge: +4 / -3
label | 65beb737-bc5e-446b-b270-73907e54c2fb |  | note | Gauge Curves with Wear: +12 / -3
label | b76e7f46-8b91-473e-b566-8769ea80c5fb |  | note | Line (10m Chord): +15 / -15
label | 72158b80-e929-41f3-870e-d82f4de63977 |  | note | Twist (3.5m Chord): +5 / -5
label | f53aac20-8d8f-4c0c-8374-7c46826ac1bf |  | note | Top (10m Chord): +5 / -5
label | c8933e5b-69ec-4c7d-964a-68646db9364e |  | note | Cant: +5 / -5
label | ab77e2ab-c779-410f-be97-c152c9d63f63 |  | note | General Alignment: +15/ -15
label | 51ad99cf-4513-434e-8d44-7b360a5bf02e |  | note | Attach;
label | 53f5562b-877e-4596-807e-f11dd74d2b92 |  | note | Tamping Geometry Recording
label | 7c59c57a-d343-43b6-9e75-affc09d362b6 |  | note | Survey RL measuring sheet
label | c4065429-9a60-44d0-9c9d-b0560391db4a |  | note | Attach Site Photos:
label | 78ce3450-11d3-48ec-8aa1-ec0bf0b7b7ba |  | note | Tamping Activity
label | 6e348fce-986a-44ae-9e9e-c5594eaf6918 |  | note | Structural Offset Measurement
label | 949d7627-8184-4259-8a01-1dcab9ca7752 |  | note | METHOD: Visual, Measure
label | cc8cb4bc-58eb-4f04-af23-a1b8a91d436d |  | note | FREQUENCY: Once
label | 39faa4f9-ee7f-42d6-94b2-11d2fe1b3a6b |  | note | CATEGORY: HP
label | e7134902-d3d8-4c13-93e9-cc15883c91f6 |  | note | RESPONSIBILITY: Track Surveyor , Track Supervisor , Site/Project Engineer
label | d415a623-397b-4516-bb23-3c358ee82ee0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 635ad92e-aebf-4d84-96d9-13f77d0af801 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.07 Regulating and Ballast Profile
label | 6d4d2765-419d-4a68-80c4-56589c2f8980 |  | note | REFERENCE: L1-CHE-STD-029 Earthworks and Formation Standard
label | 9f60da1d-20b7-4d25-843d-df0cc48051bf |  | note | PTC Heavy Rail Track Construction Standards Drawing F598
label | ca11ee48-c176-4c9a-a39c-c6aa51835f68 |  | note | ACCEPTANCE CRITERIA: Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter
label | 09d41348-4992-42c3-9980-510631e768cb |  | note | No Ballast to be on top surface of sleepers or around rail Fastenings
label | f4c058a8-9b93-4108-a73f-38b9c50032cc |  | note | Attach Site Photos:
label | 788325ce-cece-4e38-b987-d0b7c60e0632 |  | note | Ballast Shoulder Measurement
label | 5fbf326f-5067-464e-8c3a-a1cf4dc88f5f |  | note | Rubber Panels free of ballast materials
label | 552ac6f7-6636-4a46-b780-5cfa9869c71e |  | note | METHOD: Visual, Measure
label | c11b114e-b5c5-4a5e-8e7a-df4d78edf1a1 |  | note | FREQUENCY: Once
label | ed1a7269-ed6c-4e26-b0b6-5331bca2dec8 |  | note | CATEGORY: HP
label | 8565b10b-3aa6-4f08-a274-d7d05ab9548f |  | note | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
label | 4b83e84f-7b83-437e-b2cb-b56a9734a2dd |  | note | VERIFYING DOCUMENTS: This ITP
text | f5db9997-c6f4-4ff9-b586-968bf30d93e9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.08 Aluminothermic Welding
label | 3e442533-d98c-4764-9965-268de59214b8 |  | note | REFERENCE: L2-TRK-PRO-028 Requirements for Welding Track
label | 91404724-ad8c-44fc-aeed-3efe6f701f50 |  | note | L2-TRK-PRO-029 Laying Rail - Bolted, Welded and LWR
label | 4c65a5e3-5d04-4638-91cc-799295f26f0d |  | note | L2-TRK-PRO-015 Stress Control of Continuously Welded Rail
label | 5b9154c8-d34e-4170-9be5-a1f541f57553 |  | note | L2-TRK-PRO-016 Closure Rails
label | 7260cd9e-e5bc-416f-9f69-3ca690fd6eab |  | note | L2-TRK-PRO-014 Rail Welding Process
label | 1d731509-c045-4759-a17a-7de3529b4530 |  | note | ACCEPTANCE CRITERIA: Welds to be lined and finished to alignment standard
label | 6b457c50-e048-4288-99e2-7b464850d32a |  | note | Tolerance:
label | 27b30831-d68d-4fc7-a347-aa5ab88fafa6 |  | note | Gauge Face +1.0/-0.5mm
label | f88155f8-f000-4d41-8e35-2a355933b9d7 |  | note | Running Face +0.6/-0.0mm
label | f7e922bd-156b-4366-afd8-2f7f78c8f483 |  | note | Verify Aluminothermic welding carried out in accordance with AS1085.20
label | 7884078f-6948-41ca-a18d-a423cb311792 |  | note | Aluminothermic Weld Return Form to be completed
label | fc7ebb31-318d-4dac-9b9b-b3460caa5ab8 |  | note | Attach
label | 6906cb6f-fbc7-477b-8951-d5dc6fcfef02 |  | note | Aluminothermic Weld Return Form
label | 19b47bdf-5bb3-4fe8-bae1-2aade6c72ec2 |  | note | Attach Site Photos:
label | 735740de-b3e1-4131-a906-0b67cd61e341 |  | note | Welding Aligning
label | d4a1d379-c8f4-46d7-98f2-49319a2c5aba |  | note | Welding Process
label | c7a92713-18c1-4756-9617-a4dea0f10b1f |  | note | METHOD: Visual, Measure
label | 77a9c7ca-05d4-4f07-9329-742c11b5e46b |  | note | FREQUENCY: Each Weld
label | 0249979c-7e63-431a-a077-1b8a4408f719 |  | note | CATEGORY: HP
label | 58b4e2e5-6b71-42b8-988a-f438efce9fae |  | note | RESPONSIBILITY: Track Welder , Track Supervisor , Site/Project Engineer
label | 70a86060-34bc-47a9-ae77-658e59162927 |  | note | VERIFYING DOCUMENTS: This ITP
text | a55db373-aa8d-48b7-88da-618322ce7454 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.09 Track Stressing
label | d752cd6a-ee35-4976-9081-f3c8e28537af |  | note | REFERENCE: L2-TRK-PRO-028 Requirements for Welding Track
label | daf8f270-2988-46f5-9773-0c4244f866b9 |  | note | L2-TRK-PRO-029 Laying Rail - Bolted, Welded and LWR
label | 6f409c12-3c94-417b-9986-9624db81565e |  | note | L2-TRK-PRO-015 Stress Control of Continuously Welded Rail
label | d06df499-29e8-4b76-9251-33c99ff40f16 |  | note | L2-TRK-PRO-016 Closure Rails
label | 8af80116-d567-4b45-acfa-62d9ea3c71ce |  | note | L2-TRK-PRO-014 Rail Welding Process
label | 1c0c2158-f4e0-4aa8-b92a-287acccc754f |  | note | ACCEPTANCE CRITERIA: Stressing Rail in line with V/Line Rail Welding Process
label | 12ab7b97-0855-4245-9538-dc47a8b3c075 |  | note | Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
label | c4020ba5-b8ec-44e8-b09b-30d397e79fbc |  | note | Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
label | d36d7e8f-c3f6-4b23-9725-ed1f3c431221 |  | note | Reference Marks recorded pre and post tensing of rail
label | 2057039a-0f31-468a-9992-d656fafc27f7 |  | note | Aluminothermic Weld Return Form to be completed
label | dd90d02e-a926-45a7-a04b-7be02dde672a |  | note | Attach
label | a16940fc-aeed-493e-857e-bd0aed137fa9 |  | note | Aluminothermic Weld Return Form
label | f6eece24-4d12-482b-b65a-c5928b1b0906 |  | note | Attach Site Photos:
label | 90ce63a4-0c60-4099-9a11-70576aa00618 |  | note | Stressing Activity
label | 16009136-9db8-41b6-83e1-cf8b9145710c |  | note | Under Rail Roller Spacing
label | e5bae0d5-f478-4057-82ca-ae84ce61fc79 |  | note | Before/After Reference Mark Measurements
label | e35cc45c-41ae-4887-a73b-acbb963146b1 |  | note | METHOD: Visual, Measure
label | 3fd2c331-e0a2-4ed8-b66a-a2c1ba99f898 |  | note | FREQUENCY: Each Restress module
label | 47f2fa18-1991-472b-a4f9-dbd7f01d19c9 |  | note | CATEGORY: IP
label | 66d9abd1-4ce5-4de8-8f36-9e38e306cbe9 |  | note | RESPONSIBILITY: Track Welder , Track Supervisor , Site/Project Engineer
label | 5dcdde2b-90a2-47e2-9445-f7081a86c3be |  | note | VERIFYING DOCUMENTS: This ITP
text | e6849833-f84a-443e-82ba-f7e7ac7bcd95 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Weld Ultrasonic Testing
label | c6e52775-aaf9-4e94-be1f-86c10b2587cb |  | note | REFERENCE: L2-TRK-PRO-015 Stress Control of Continuously Welded Rail
label | a77e8aa8-0973-4afe-ab82-80ec9fd6bbd4 |  | note | ACCEPTANCE CRITERIA: All welds shall be ultrasonically tested;
label | 5f5b8211-603d-47a9-af17-25283ff9512f |  | note | The cross section of the area of the head and web shall be completely scanned;
label | 059edc6a-68b8-4bcf-b3ef-40eec6b04fe9 |  | note | The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
label | dd1fa13f-af47-4c3c-9e66-3e141be90fac |  | note | Welds shall be scanned to both directions.
label | a644bf69-7ff5-4cd3-9c8d-3afe99cb1edb |  | note | No classified internal defects found
label | 3619143f-006f-4ad9-b240-d7462fafbdd4 |  | note | Final weld geometry to be assessed
label | abf279ba-8a01-4273-abc7-e38a5bd4c18f |  | note | Tolerance:
label | db760583-0f50-49ff-b393-332f39b74005 |  | note | Gauge Face +1.0/-0.5mm
label | 94198d52-65f5-4b08-a8d3-ffd5f6ab8104 |  | note | Running Face +0.6/-0.0mm
label | 25fcf028-a1d2-4dad-a2a7-264655651397 |  | note | Aluminothermic Weld Return Form to be completed
label | c6f3d8e9-15f2-4bb1-a8ea-9ddd50b6adc8 |  | note | Attach
label | 61c2fd70-351c-4e05-a77d-9517322831cd |  | note | Aluminothermic Weld Return Form
label | 30ce6492-2850-41c7-9a3e-61d6501d55fe |  | note | Aluminothermic Weld Test Report
label | 4459c0d0-4b58-44a0-a911-da5f458c9d94 |  | note | Attach Site Photos:
label | e021ef10-83e4-49ae-bbcf-5fe715065cac |  | note | Welding Aligning
label | df98b5e7-6049-46e1-8e73-e8d6ce7ca4a4 |  | note | Welding Process
label | 41f22406-d07d-4b05-9c4c-bca1b4cfddc7 |  | note | METHOD: Visual, Measure, Test
label | 839462f0-b84d-4ded-a5a1-af29131eec94 |  | note | FREQUENCY: Each Weld
label | 2fe7320c-d0e1-4c67-9190-33ea4e7f305c |  | note | CATEGORY: HP
label | 4cd45ff1-b13d-4a62-bd0a-bef46a050c66 |  | note | RESPONSIBILITY: Weld Tester , Track Supervisor , Site/Project Engineer
label | af24bde9-3189-48c8-84cf-f3267ffd170e |  | note | VERIFYING DOCUMENTS: This ITP
text | 79f12c7d-0f62-469b-8b0d-f024f3594acf |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.01 Track Certification
label | 7630f928-b170-4606-bac1-c439e70986d6 |  | note | REFERENCE: L4-TRK-FOR-128 Form A: Track Geometry Conformance Certificate
label | 6730da69-068c-4cf5-8931-033cf9691cb6 |  | note | ACCEPTANCE CRITERIA: Attach: Track Geometry Conformance Certificate
label | e48a3f2c-46f0-4eaf-b602-92fe1657b753 |  | note | METHOD: Visual, Measure, Document Reivew
label | 9c49698e-1b75-4895-9f27-3bd095611f41 |  | note | FREQUENCY: Once when all occupation works complete
label | 73d5da0d-3204-47a4-a05e-86cbdaa22920 |  | note | CATEGORY: HP
label | e896aabf-3f54-43fb-84d1-02e058be3549 |  | note | RESPONSIBILITY: Track Certifier , Site/Project Engineer
label | 84ece96a-e2a4-424f-aa49-34de244eb7c8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | eee6718f-78d1-4c4e-ac6b-383d94f7cfc2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.02 As-built Survey
label | e236b007-431b-4eaa-8dd1-f14e9a96e89a |  | note | REFERENCE: IFC Drawing(s)
label | 58bebd6b-bd08-4eeb-adbd-934a40673f33 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | 93463f5a-2e64-4db8-9417-e4385c9a1684 |  | note | Attach: Survey Report, Engineering Asset From
label | b0ed905d-1478-4321-8c4e-dd8509f96ba4 |  | note | METHOD: Survey, Document Review
label | ffda0631-4f0d-4de8-b8c2-971ac76957d1 |  | note | FREQUENCY: Once
label | 8b6905b9-36fc-474b-be14-35d17d7b12d2 |  | note | CATEGORY: IP
label | 5d2cbfa8-3a1f-44b1-9317-68f440b8c98e |  | note | RESPONSIBILITY: Track Surveyor , Site/Project Engineer
label | 77cf4c52-061c-4ec1-8697-0ff26e2bfa9a |  | note | VERIFYING DOCUMENTS: This ITP
text | 014482bf-7466-4527-ae42-25d3942b1e92 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6b7552af-db19-4aa8-a921-f920edd1ad66 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | f9476d4b-4e5d-4523-908e-a8f56efbb8e7 |  | textbox | Name:
text | b7d2d932-8699-46d7-acd3-7f5a4f90f49e |  | textbox | Position:
text | ed0442a5-94ba-4873-83e9-fbed498c4917 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Clyde Road Installation of ACO Drainage & Subsurface Drainage Rev 0 | itp |  |  |  | Yes | ITP-CIV-Clyde Road Installation of ACO Drainage & Subsurface Drainage Rev 0 | 087a42f7-8e2d-4677-9c8e-24d607b59fc6
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | d20ca1b8-50d7-5ff2-832f-a8956f09c891 |  | note | Document Title: ITP-CIV-Installation of ACO Drainage & Subsurface Drainage - Clyde Road
label | 30ab5d8e-9b42-54e0-a359-450944cee786 |  | note | ITP Description: Installation of ACO Drainage & Subsurface Drainage - Clyde Road
label | 97f01bf1-8dca-56a7-b567-effe56b182ae |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 0c35da10-b075-5eca-9f5c-1b1ab0b02320 |  | note | Revision Number: 0
label | 1fa978ac-b060-5b18-9b38-0e7c7929981c |  | note | Revision Date: 30/08/21
label | 6a3e2831-134d-5ae9-8ccf-935330651042 |  | note | ITP created by: Justin Kreinberg
checkpoint-status |  |  | checkpoint | 1.2 VicRoads Section 610
checkpoint-status |  |  | checkpoint | 1.6 VicRoads Section 702
checkpoint-status |  |  | checkpoint | 1.8 VicRoads Section 703
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete Mix (Min 25MPa) - No testing Req.
label | e1c92e37-be38-5562-9d3c-88dc9bb10c3b |  | note | Reference - IFC Drawings 610.07 Table 610.071
label | 10a81bdc-32af-5d4a-897b-6a0f7c02d1a9 |  | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 55b7694c-5a22-5864-9c48-bbcb7948a69e |  | textbox | Teambinder Material Approval number:
label | 72786f7a-9031-5e46-845c-14626f420f37 |  | note | Method - Document Review
label | 6268a795-ab1d-5898-985c-7b0093116bb6 |  | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | 3fec5071-ece1-547b-aef6-7f687450fcfb |  | note | Category - HP*
label | e5a3e07d-9b33-53da-b4a5-d29cb29028a3 |  | note | Responsibility - Nominated Authority
label | 7cc28562-38d2-5416-a402-adb22f0d241f |  | note | Verifying Documents - ConQA Hold Point Release
text | 3843f87e-9641-524f-aa8d-911757dfefae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - ACO Drain and Lid Supply
label | d63c6c7b-170f-53ab-9d5c-75b0a8d974d0 |  | note | Reference - IFC Drawings
label | 9a9a8f36-ba4a-543f-871e-78f93eb85ffd |  | note | Acceptance Criteria - Aco Drain Type: Power Drain S300K - Sloped Drain - Depth 300mm (300x325mm) Grate Type: Heelsafe Anti-slip ductile iron grate - Class D, 240 kN
text | e728dc92-9ce5-5218-8e1b-3e2d001dcf06 |  | textbox | Teambinder Material Approval number:
label | f0efc5c1-4959-57dd-b52e-f30f05993bbc |  | note | Method - Document review
label | b43038cb-4b78-5333-8504-d2a87ac1b4d3 |  | note | Frequency - Once, for each product, prior to placement of product
label | 3d520e58-3998-511b-8f90-01e146bc77d7 |  | note | Category - HP*
label | b3db03c0-55f0-527d-9024-e65043e7b071 |  | note | Responsibility - Nominated Authority
label | bd9dde6f-fd72-544e-bb6c-6439a5836fe9 |  | note | Verifying Documents - ConQA Hold Point Release
text | 48b13484-ddee-5e43-9a6f-a02457096b52 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Subsurface Drainage Supply
label | e07f3eb3-402a-5f54-8b04-6d7fdcc7b96c |  | note | Reference -
label | 0f61cd41-b8b4-54dd-bee1-040357ed0e95 |  | note | Acceptance Criteria - Subsurface drainage pipes 100 Dia ADS N-12 Dual Wall HDPE Pipe wrapped in geotextile Geotextiles Sleeve Shall comply with 702.06.
label | 0fcd8650-55e1-5194-b158-c5b784061f14 |  | note | Method - Document Review
label | d6d692bc-bcdd-57ea-b91f-03525f953b7a |  | note | Frequency - Once, for each product, prior to placement of product
label | 450b5a04-a8f5-5827-8b38-686ab60c04eb |  | note | Category - WP
label | 76b32e10-fb4b-5117-971d-16d1d28da1e0 |  | note | Responsibility - SE
label | c6cff767-6328-5e18-84ff-5e6f3a3d8269 |  | note | Verifying Documents - This ITP
text | 4025b3be-59cb-5048-a6a2-5099590df2c4 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 - IFC Drawings
label | 057be727-a8fc-5c2f-916e-c9499cf78b93 |  | note | Reference - MRPA Quality Management Plan
label | 003867db-42b2-5184-bbc6-9805f1bcdbbe |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 8f574a65-3480-5c24-a88e-1650abfe7944 |  | note | Method - Document Review
label | 9030416a-ae00-515b-86c5-a988ecb30fa4 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 186b4ad1-2567-51d3-9644-12f51f61bc26 |  | note | Category - HP*
label | 06178a68-74f9-5d27-b048-4aed5139e874 |  | note | Responsibility - All
label | 775ee77a-5db5-5f1d-a56d-bea5285ded52 |  | note | Verifying Documents - This ITP
text | dc9cf1d9-040d-5aca-a2dd-bac1be4e95e7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Survey Set-out
label | 1c76ece2-0228-5ad4-a609-8aa399a48295 |  | note | Reference - IFC Drawings
label | bca9b00e-eeca-5f93-acde-25a4e9439016 |  | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to element
label | ba752d01-5d11-5cfa-93d1-2186bbdaa8a1 |  | note | Method - Measure Visual
label | 9354fcfa-574b-5774-90f9-2071a7e764d5 |  | note | Frequency - Prior to Commencing
label | 6d7acbe1-2d74-5d10-8a4c-f5f47d8f7bcb |  | note | Category - IP
label | 69993a52-defe-56cb-9232-3455c75898e4 |  | note | Responsibility - Surveyor SE/PE/SPE
label | 0945a0df-0fba-5588-b563-adab9b8100c6 |  | note | Verifying Documents - This ITP
text | fe1e1a5c-69d7-5a44-bc06-8f0946c87766 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Trench Excavation
label | 622aa526-1019-5bfe-a740-e212d956df41 |  | note | Reference - IFC Drawings Section 702.08
label | 0b432e0f-b0bd-5cda-9c5c-c844f8edb1e0 |  | note | Acceptance Criteria - Trench shall be excavated to allow for a min of 150mm between each side of the ACO drain The depth of the excavation shall be a min of 225mm below the base of the ACO drain The bottom of the trench shall be compacted There shall be no departures from the grade of the base of the trench that would allow ponding of water. Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | 018c36d0-8bd3-55fb-ac3c-15c45d3096d2 |  | note | Method - Visual
label | 85821579-74fd-53bc-8571-001ccf8e44a6 |  | note | Frequency - Each Lot
label | a42209df-e3cf-58a7-8ff9-0d8a55beff63 |  | note | Category - HP
label | 857bc328-315d-56dc-a6f6-d89083606aa8 |  | note | Responsibility - SE, NA (Nominated Authority)
label | f5674edf-cd80-555a-b3cb-b49bbb006526 |  | note | Verifying Documents - This ITP
text | 093e1186-d6a4-5ad4-9fbd-5e8c8ee3b009 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Placement of bedding
label | 18dcd225-5bba-5d78-afe8-ef1215b2eafb |  | note | Reference - 702.09 c)
label | 18d7951e-3909-524a-916c-868d63ab3842 |  | note | Acceptance Criteria - Bedding of granular filter material of thickness between 75 mm and 200mm placed across bottom of trench and screeded & compacted to level Place 150mm of bedding under pits
label | 5edced82-6d0c-504f-9aea-648c3f69b228 |  | note | Method - Visual inspection
label | d7cf213e-4942-520b-8bfd-6436fad52d2f |  | note | Frequency - Each lot
label | ab09cd65-1ed6-5141-86fd-520250c4bed4 |  | note | Category - IP
label | 6f3cfc78-2a81-5c68-aa71-c12ccd495ab6 |  | note | Responsibility - SE/Site Supervisor
label | 35e5323e-ef20-5456-a155-4a9f4ae26eb5 |  | note | Verifying Documents - This ITP
text | 52344634-e3e4-54eb-b78c-a35130ef1f6d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Place ACO Drain
label | 910aa410-0fb6-58d9-b709-440b4590ba74 |  | note | Reference - IFC Drawings Installation Methodology
label | 4968a5ab-6aa0-59cb-a7b2-cc72c1c3ae8d |  | note | Acceptance Criteria - Place ACO as per IFC drawing in center of trench ACO units to be placed flush with adjacent precast units with slope facing correctly as nominated on drawings. Polystyrene to be installed between ACO drains and precast bridge components
label | 77df95d5-fdf5-522f-9c62-44397733a708 |  | note | Method - Site Inspection
label | 65d5295f-12c3-53f1-b683-e00a2c17d7be |  | note | Frequency - Each Lot
label | 8d7c47c4-b907-558d-b150-36d5334aa105 |  | note | Category - IP
label | 8ff4db9a-2909-5282-b602-922a950a5656 |  | note | Responsibility - SE
label | 6aa8c3ed-fc92-5bc4-965a-904597adac5a |  | note | Verifying Documents - This ITP
text | 1925cc2c-e7bf-5c5a-a6be-15610d483f61 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Sealant
label | 69961694-4f8a-546a-8145-cef2456adb02 |  | note | Reference - IFC Drawings Installation Methodology
label | b047510c-0a0e-5c57-8c75-97dbf05835f9 |  | note | Acceptance Criteria - All pipe connections to be sealed as per installation methodology
label | ae648477-bbfc-5587-acf5-8b9265391c5c |  | note | Method - Visual
label | 1648e583-fe10-5e41-96cb-21b6130ff4b8 |  | note | Frequency - Each element
label | 830980bb-aa69-539c-95f7-6b9ef160b75f |  | note | Category - IP
label | e6214499-9d94-5180-9692-727ba7ad3087 |  | note | Responsibility - SE
label | 6d34cdae-af9e-54da-97ce-80c49669c0df |  | note | Verifying Documents - This ITP
text | 702ff0d2-8302-5457-852c-70142aca1b33 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Connection to Pits
label | f94d4d36-eef6-531b-8417-4b438ecc76fb |  | note | Reference - IFC Drawings Installation Methodology
label | caee6edf-9987-5e07-ac06-bed002c187d2 |  | note | Acceptance Criteria - Connection between ACO drain and drainage pit to be established with via core drilling and sealed as per installation methodology
label | 53ae0e20-1791-5b2b-ba57-c73372e0575a |  | note | Method - Site Inspection
label | 26538777-7014-5692-acdb-71fc321e265c |  | note | Frequency - Each Lot
label | 52be19f5-f992-5f2c-971a-a156f32ca5d2 |  | note | Category - IP
label | 5399a8ab-8f33-5901-b799-6a8a8c29dd53 |  | note | Responsibility - SE
label | dece5f9a-d060-5299-8915-dab95eadecc6 |  | note | Verifying Documents - This ITP
text | e268d5c1-c1e7-5a59-92ac-946ade9d9028 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 - Pre-concrete check
label | f4b7b479-71ad-5e6d-afaf-7ae05005bf34 |  | note | Reference - VicRoads Spec Cl.703.09 Cl.610.17 (a)(b) (c)(d)
label | 4f879f5c-c9fc-5ca7-9c22-81f4c6fe1998 |  | note | Acceptance Criteria - Concrete shall not be placed when the air temperature measured at the point of placement is >35 C or < 5 C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10 C or greater than 32 C. Unless otherwise specified concrete shall be N32 standard strength.
label | 609dee00-ad4b-5dfd-80b6-f4a2d834232c |  | note | Method - Site Inspection Temp Verification
label | 38f6c139-115a-5407-847b-2e005363778a |  | note | Frequency - Each Lot
label | 7798018a-073e-5b1d-a4b5-9a9167f379a7 |  | note | Category - IP
label | e93aed91-35b2-544f-ae4d-cd3222d89e2d |  | note | Responsibility - SE
label | ac0997f6-0b2b-5fc2-aa35-98cdcaf4d74a |  | note | Verifying Documents - This ITP
text | 0cef9a5c-3cde-5a8e-9aca-fc1c3097a183 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 - Concrete Placement
label | 2bd3905c-7cf7-5f05-9c6b-30a6ea5ed77f |  | note | Reference - IFC Drawings VicRoads Spec. Cl.610.13(f)
label | f7df87a3-f4ec-52e8-ad07-683aa386d072 |  | note | Acceptance Criteria - Concrete Strength to be 32MPA as nominated on Drawings; Concrete placed within 60-90 minutes of the commencement of mixing;
label | 618c988c-148c-5067-aa44-391b2197a942 |  | note | Method - Site Inspection
label | bdc668c8-cfb7-525a-bea9-d9862dcfd6d1 |  | note | Frequency - Each Lot
label | 8a459984-521c-57f3-8a54-82720df2c178 |  | note | Category - IP
label | 18fb7f07-6a65-54d6-8d09-30cbd34d45fe |  | note | Responsibility - SE
label | 5513010e-4cc9-5e03-aeb6-cb16fe3dc9a3 |  | note | Verifying Documents - This ITP
text | fdd57a16-3332-5c07-80ab-b0aabc4fa9f4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 - Concrete Finish
label | a078ffe1-7eac-5585-9ac8-6e1fcef07001 |  | note | Reference - VicRoads Spec. Cl 703.25
label | aa157f22-0a05-51d7-8e4b-b0411b405b00 |  | note | Acceptance Criteria - Use a wooden float for a lightly textured non-skid finish. Concrete to have a neat appearance and uniform colour
label | 1f3a138e-987c-502b-a624-d5afd9fe7fad |  | note | Method - Site Inspection
label | 2e67e646-065d-53db-b6a7-b82343325e78 |  | note | Frequency - Each Lot
label | c2fa98b2-5d6f-5b2b-b501-9aea886ad15b |  | note | Category - IP
label | 4c13a36e-a515-5815-8ff8-1230ddf9a5e8 |  | note | Responsibility - SE
label | d77c8d08-1ad5-5eb6-90ea-174f16111ee9 |  | note | Verifying Documents - This ITP
text | 5ea67b7d-a0ab-5fa2-9c9d-ac1b416c5e68 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 - Pipe and Geotextile Installation
label | a8be94e7-9a65-5348-9e2d-175d9df29f38 |  | note | Reference - VicRoads Spec. Cl702.03
label | 6a417e2c-ffda-5e95-aca0-7f3473de8e43 |  | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | eabf7a5f-5f02-543c-b08c-f65307e3a0b5 |  | note | Method - Site Inspection
label | 182d3ce5-8e55-55aa-a281-e964e3e40485 |  | note | Frequency - Each Lot
label | 52385b03-7d5c-5a68-87e1-b12f1002acb2 |  | note | Category - IP
label | c18fe2e5-0350-591c-8a0b-930fbc6b9d00 |  | note | Responsibility - SE
label | 8cbe14f7-f182-5701-a660-e254dcc9fbd8 |  | note | Verifying Documents - This ITP
text | 7bbfc73d-068d-5099-a4e5-3994dc1a8d92 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - As-built Survey
label | 04dd9cc7-9512-52e6-b51b-d64d6c1aabe4 |  | note | Reference - IFC Drawings 610.32
label | c09c9636-ef8c-5074-90cc-3d5472134507 |  | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate Vertical and horizontal alignment between adjacent segments shall not exceed 5mm Attach: Survey As-builts / Survey Report
label | a542dbeb-9a76-5b78-9523-020178a78ac5 |  | note | Method - Document Review
label | 5399b1ea-917b-56fb-ad14-eada29732a9a |  | note | Frequency - Each element
label | 0ff625fd-1c49-565d-924f-8920dbeee402 |  | note | Category - IP
label | 52083766-edff-519b-9fe8-7677b0b10d38 |  | note | Responsibility - Surveyor SE/PE/SPE
label | 836ff6bc-c302-5c13-a4bd-e811d0b68c8e |  | note | Verifying Documents - This ITP
text | 2a862ad2-9802-5369-be3c-18f4c41e0940 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | f1a9a8df-e05b-5478-b018-5918c7747440 |  | note | Reference - MRPA Quality Management Plan
label | 1ea12204-0414-53f0-870d-bf37ccd7f695 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 6f969f54-5045-5b8f-bf30-31f6c2781200 |  | note | Method - Document Review
label | 5dabb68a-d779-5b7b-a966-d533bc859545 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | b4753a17-6ce0-5ebe-abcd-fa2fa958472a |  | note | Category - HP*
label | 01925c1d-c853-5641-9543-4c93733d9816 |  | note | Responsibility - SE/PE/SPE
label | 0cd014b7-d566-573a-8e36-79bcf2837675 |  | note | Verifying Documents - This ITP
text | 4558d90a-968a-5ba4-9786-019130dc4b6a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 00397a23-7f0b-5b40-9cd9-b73bc4f981b7 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | e30c6b5e-5737-5819-8554-db5bc5640336 |  | textbox | Print Name:
text | 95116e46-a573-5fb9-afcb-c1427bd72889 |  | textbox | Position:
text | 853de026-9b29-504b-b17b-fc64ab48a1b0 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-STR-Structural Concrete Rev 3 | itp |  |  |  | Yes | ITP-STR-Structural Concrete Rev 3 | 0928b9b5-8857-4683-be81-582c6162942d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | a97551af-246b-531e-823c-c8dcdae78d9e |  | note | Document Title: ITP-STR-Structural Concrete
label | 51e33dc4-63e1-5930-9dba-d1fcbec51f25 |  | note | ITP Description: Structural Concrete
label | e263d61f-eb57-5d49-9993-6d16ce8c3b9b |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 7172c690-a39a-598a-bbdd-be21f23f8881 |  | note | Revision Number: 3
label | 5b4cf925-1704-58c8-adae-6c533efcb016 |  | note | Revision Date: 12/05/2021
label | 8c6d92d8-5ee1-5729-ae5a-7c824eabceb3 |  | note | ITP created by: Mike Freeman
label | 53ffbe9f-34d9-551c-ad2b-8d318c79b029 |  | note | ITP approved for use by: Mike Freeman
label | e4bcbefe-6e85-57cc-8cf3-f04cccb319ce |  | note | 1.1 VicRoads Section 602 October 2007
label | f7b48ea9-64d4-5389-b602-dc55240cd259 |  | note | 1.2 VicRoads Section 610 June 2019
label | 65361b6d-d3ce-5d06-ab9b-69c0545fd2ad |  | note | 1.3 VicRoads Section 611 November 2018
label | 428c8458-f13f-5a7c-9b6e-684e4af022fa |  | note | 1.4 VicRoads Section 614 June 2017
label | 1849c6aa-3610-56ec-a34b-12b6a9d30109 |  | note | 1.5 AS3810.1 2018
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 8698801f-ce7c-5292-879c-ff60909e5188 |  | note | REFERENCE: 610.07
label | 02bada9a-9dd3-50b3-8b9a-185e4ab105b1 |  | note | Table 610.071
label | 7c2e280a-485e-54ba-bf50-50c57323151e |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | a00d1248-4e46-5156-9a5e-04ccbbd62595 |  | textbox | Enter: Teambinder Material Approval number
label | e0ff5bf7-2816-5219-bcfb-04e47850fe66 |  | note | METHOD: Document Review
label | 9316ca91-d0fa-5e68-8f5c-36a9aaddee34 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 7cd7b0f8-8f57-5392-b890-54d5d81acb83 |  | note | CATEGORY: HP
label | 479e33a4-7321-598c-86bf-4fc4d887ff28 |  | note | RESPONSIBILITY: Nominated Authority
label | 6b942077-743f-5f46-9ead-c8a7994be726 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 2d3f74c5-7f6a-5c46-a522-d032a1837530 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 69ae1d11-b68d-5905-9531-c3d1e5623bd4 |  | note | REFERENCE: 611.05 (a)
label | 9f7193d8-f927-5cc5-9894-6f3fd0258ed6 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing
label | ba3cd733-46a9-56ed-b2d8-033665b3e1cd |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | caea1ed3-46c0-59a9-9340-013152d9c360 |  | textbox | Enter: Teambinder Material Approval number
label | f6ec7599-c150-5224-976e-920e348fdef0 |  | note | METHOD: Document Review
label | 7a90f6ff-9ef4-5531-bc06-2a8633351c41 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 9b4d1289-2392-55db-a7b5-e2862d9f7494 |  | note | CATEGORY: WP
label | 1d04a40c-477c-5ca9-9773-f7ca226c4e9e |  | note | RESPONSIBILITY: Nominated Authority
label | 31805df8-618a-5634-a7a4-985d19625e6f |  | note | VERIFYING DOCUMENTS: This ITP
text | 92206434-6065-5c39-8a72-b110d5df3dee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | f302dfbe-05c5-57fb-83ee-97e37468c7e9 |  | note | REFERENCE: 610.26 (a)
label | c5b0d796-ba8e-5edb-b50a-db53cac7ecdc |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | cf28e848-9beb-5cf1-8f3b-5145ff050f63 |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | f40464dd-f0b7-5e42-ab08-475f156591c2 |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 86e3b9c4-e475-56d2-9a22-ad4f8e358bc7 |  | textbox | Enter: Teambinder Material Approval number
label | eb3375ed-b2ca-53f9-aac7-5e730fea9e34 |  | note | METHOD: Document Review
label | 525be135-0dfb-5c1b-913a-f9db8bd96103 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | ca4934dc-9e11-5f37-b34d-317adf1bdd43 |  | note | CATEGORY: WP
label | 8d998068-43c3-5b4c-8cbe-73ba0b49275b |  | note | RESPONSIBILITY: Nominated Authority
label | c53dcbfa-53f1-5b44-9615-26b73ab0df5f |  | note | VERIFYING DOCUMENTS: This ITP
text | 739eaa1b-b973-5a35-aa3d-7d2815ed5f6b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 905299f5-cbc7-5bcf-b1e0-bc4e400cb305 |  | note | REFERENCE: 610.17 (f)
label | aebe19c6-e71f-5404-ac2c-e9c34cccf79f |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority
text | 161543ae-f4b3-51c3-a738-7c5dd0446789 |  | textbox | Enter: Teambinder Material Approval number
label | 59b1113c-fd7f-5702-8053-4df5cb688586 |  | note | METHOD: Document Review
label | 53b7d05a-3109-528d-b0be-afe94a9dabca |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 72ea244e-58b3-5f64-be36-a367ffb42c5a |  | note | CATEGORY: WP
label | 622e1594-4bf2-5b8c-aedb-10b6a8f54a2e |  | note | RESPONSIBILITY: Nominated Authority
label | 8d7524f7-81c2-518d-b0ac-fa3bf2c027ec |  | note | VERIFYING DOCUMENTS: This ITP
text | 40a5aae7-624a-51e7-a8a4-a2f9fe10d129 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | c7d02a25-10ea-5c14-9057-671d4363451d |  | note | REFERENCE: 610.23 (d)
label | 7952b45b-936c-555c-bb71-1c279a06defe |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 20f99057-1961-5752-9f17-874a2463341f |  | textbox | Enter: Teambinder Material Approval number
label | 688269bf-f66c-5d8c-8ea3-ba8ce879df00 |  | note | METHOD: Document Review
label | 3554e020-0769-5f40-9559-97a2f1cd5576 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 218ec411-2f19-5488-ba99-257f1891ce8c |  | note | CATEGORY: WP
label | 657128b0-4f3f-5c8a-9f87-81bfa94599aa |  | note | RESPONSIBILITY: Nominated Authority
label | 4bf03dfc-7909-5790-a805-5711dae19774 |  | note | VERIFYING DOCUMENTS: This ITP
text | ad99c461-e6ff-5c37-91c7-dd6b2cfa7624 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | 9c44602d-bfd2-5137-a7ee-6721c8007520 |  | note | REFERENCE: 610.18 (a) (i)
label | f431e020-841f-5d89-9e87-978004583f94 |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | d332400a-c9f6-5a41-9de1-13f2c469080e |  | textbox | Enter: Teambinder Approval number
label | db639a3e-7185-5db5-a4c9-3d9a981ca08c |  | note | METHOD: Document Review
label | 130938f8-025e-5605-aaa1-2c208ce24600 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 403c7190-67f7-59e0-95be-f0cec254639b |  | note | CATEGORY: HP
label | 62f2a3dd-3a71-5953-8a0c-71de055b32f8 |  | note | RESPONSIBILITY: Nominated Authority
label | dd03b114-be7d-5f44-9a15-6080bdf63779 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 48d7770a-65b5-5b10-89fa-f1e5e8a62879 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | 6d43ade9-e384-552b-8802-9b5dc499a5db |  | note | REFERENCE: 610.18 (a) (v)
label | 442d36e6-6cad-5ab1-b141-af2745769629 |  | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | 5aa5b33b-82d7-5ad3-81c7-f5b51a96ec1a |  | textbox | Enter: Teambinder Material Approval number
label | 87ccca23-df4f-511e-99d9-ae3a03f9e0cf |  | note | METHOD: Document Review
label | 6d5da1ec-e5a6-59ae-9531-f67f8cdfcae3 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 87ccb3cb-d959-5ef4-b0d5-81586547b870 |  | note | CATEGORY: HP
label | 20bc30c3-fcd5-5c12-8877-6c201fae5364 |  | note | RESPONSIBILITY: Nominated Authority
label | 10bacfc7-50a2-5da0-b9c6-8b30f3083b6f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | d6c032c0-ea95-54d3-a56f-44d9b5552c79 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | 3857bf62-0fdb-57f0-9d94-f2d017c76960 |  | note | REFERENCE: 610.18 (a) (iv)
label | 91c3c61f-241d-58b6-af93-aff37f68cd0f |  | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | dd39b3d0-939b-58ff-b7bf-07b756c0b33c |  | note | Minutes of this meeting to be submitted to the Nominated Authority.
text | 32196e34-d8cc-52d2-a365-3d66a47f16c3 |  | textbox | Enter: Teambinder Material Approval number
label | ff520d0f-8f41-5fd8-a056-47c3f60a0f0a |  | note | METHOD: Document Review
label | 36aeff07-3c77-5f28-812a-9b849cd93ae9 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | c4de079f-d503-5d8a-aa65-0c61df31acf8 |  | note | CATEGORY: HP
label | 754b29bf-b131-5a6b-a460-b076608f20c8 |  | note | RESPONSIBILITY: Nominated Authority
label | 3b39db89-f823-5867-b7e3-3ef148a5f6df |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 82bb5f0d-f79e-550c-8fcd-02ef05c70469 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | 5f37b3c0-c198-566b-bd03-40aa0503a4be |  | note | REFERENCE: 610.17 (a)
label | e244a8c1-da80-51fa-857d-4ef502a25ab5 |  | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | 14be1544-b88c-5c27-a8a5-ce5a202c6989 |  | textbox | Enter: Teambinder Material Approval number
label | 49a80c2b-a9d8-5129-a08d-07abe8d53714 |  | note | METHOD: Document Review
label | 4d1fdc0a-6048-515b-a81d-12bef45f23fb |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 9b613af8-c0b9-59e3-a79b-4a5f68e4978f |  | note | CATEGORY: HP
label | 631de9f7-cc98-5b54-b2f4-5998589bda17 |  | note | RESPONSIBILITY: Nominated Authority
label | 4c0637a0-e98c-5d5d-8d63-3aee43a4ddaf |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c7860018-b2d7-5d30-8c26-af599197ccb3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Early Loading and Trafficking of Decks and Approach Slab Procedure
label | dea787ee-803a-5608-8e65-a9cfcbcf645a |  | note | REFERENCE: 610.36
label | 07ce7625-3ba8-58d8-bb3c-06115b899fa3 |  | note | ACCEPTANCE CRITERIA: Early loading shall not proceed until:
label | 1bd81d5d-9f10-5665-b9ab-2f90ae8ee553 |  | note | the early loading and trafficking quality procedures and ITPs have been reviewed by the Nominated Authority; and
label | dcbc7dcd-c904-5f80-b472-7d21b09ba4e6 |  | note | evidence of the minimum curing periods, compressive strength results and temperature monitoring have been provided.
text | 7734cc37-854d-58c2-a687-28fcda279c4c |  | textbox | Enter: Teambinder Material Approval number
label | 8520e42f-d2f0-54b9-be90-c186d5e1a61a |  | note | METHOD: Document Review
label | 1a457512-21bb-5c3e-9733-9efa774ac7ca |  | note | FREQUENCY: Where applicable, once, prior to application of load
label | 5687ea9f-08a2-5314-b0cc-66a6431759d7 |  | note | CATEGORY: HP
label | b61255e3-4bd5-5075-ba26-eb54a386ba83 |  | note | RESPONSIBILITY: Nominated Authority
label | b88c1a1b-0bb5-578e-be9d-70219bb91801 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 5063f9de-78e6-533e-9d17-376c443b355d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Concrete Drilling Procedure
label | d901e42d-b112-5f3a-8256-53d1e7311ce5 |  | note | REFERENCE: 610.46
label | aefad9f7-35af-5aaf-bcc1-82d9ac267e27 |  | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | f998b361-5ea7-5af1-8ee7-a4a6f03d5f6e |  | note | The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | 3a790745-62c3-5caf-9704-e91ca72d0280 |  | textbox | Enter: Teambinder Material Approval number
label | d45d7670-a215-584b-ab26-3d1335d037b6 |  | note | METHOD: Document Review
label | fef0677a-c4bf-5e05-a73e-cad36a58b166 |  | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | 2864cc67-5d11-52bc-909f-e8b869840587 |  | note | CATEGORY: HP
label | 69b60fa9-edab-5f96-854b-443d4444a42e |  | note | RESPONSIBILITY: Nominated Authority
label | 2a7dbef8-95f9-551f-bcd7-d2c47e9bb638 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c9e5dbfb-c4ac-5c63-a45b-e9188e1c3552 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | a1598e41-9470-55ef-864a-4cd947331d4a |  | note | REFERENCE: MRPA Quality Management Plan
label | 479e75fa-dfb6-552f-a8db-329656e6a175 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
text | 1275eaee-7449-504c-85d3-7cfc85ead278 |  | textbox | Enter: Teambinder Material Approval number
label | 969ee766-8391-5d73-b704-f9bdee033c80 |  | note | METHOD: Document Review
label | 55ebe0a6-672e-5862-be15-6699b515e859 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 99b59b1f-ceba-5062-b5ad-b7ff2db0f33c |  | note | CATEGORY: HP*
label | 2172d2cc-dfaa-5322-b0a0-d1cb97eb9801 |  | note | RESPONSIBILITY: All
label | 0b2520da-4982-5a36-ab71-ddce1ad39a24 |  | note | VERIFYING DOCUMENTS: This ITP
text | a413f3c6-318b-5ec7-a08f-03fc0b504c23 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | f04c90d2-90f1-5081-8e65-661be26066bd |  | note | REFERENCE: IFC Drawings, 610.47 (a), Table 610.472
label | b9af0e36-0893-5c28-9255-1e84d42706d0 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | c8b395d4-ce5d-507a-aa51-462dd8a0b36f |  | note | METHOD: Measure, Visual
label | 821c450a-c5f2-518b-96bc-08fb3e972fb5 |  | note | FREQUENCY: Each element
label | b550a5cd-682d-5fa4-8005-987ce10f0932 |  | note | CATEGORY: IP
label | 28c0c74f-f9d2-5ad4-8686-edf2598e6561 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 5802d3ae-807c-52b0-85ab-ac3266e6876d |  | note | VERIFYING DOCUMENTS: This ITP
text | 20d1d337-3c0d-5b15-aea4-18abbe95c18b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Excavation Drawings
label | a779e083-402d-5bfa-b175-37270f93ea30 |  | note | REFERENCE: 602.02
label | a8ea0931-cc01-5c14-8b5d-81712a1da615 |  | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | 639bed5e-5d1b-5070-9cdd-506f3e101eb7 |  | textbox | Enter: Teambinder Approval number
label | f2dde708-9a40-5685-8d28-a93a78c0e299 |  | note | METHOD: Document Review
label | ae55ca9f-ea0a-502d-813f-c65e7beb1b12 |  | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | bd6fa580-664f-56ae-9826-cd9d128104ca |  | note | CATEGORY: WP
label | 95f60467-f2df-562b-a504-efdea65d4865 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6e9e41c4-b5c9-5921-afb7-421765ff8bbe |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 52b236c9-bded-5dd1-94e0-b3f620b762b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Excavation Inspection
label | c826fd17-1bf9-56d8-b6f3-c2b11b39bdc1 |  | note | REFERENCE: 602.03
label | 511a3024-1ecf-5fda-9304-86e12d13c4d4 |  | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | 2709c9d6-96a0-544e-89ca-f9df7285cdb3 |  | note | METHOD: Visual
label | 4985d820-5620-5476-8006-b389ab0d4184 |  | note | FREQUENCY: Where applicable, prior to placing blinding concrete
label | 66422e9a-83d8-5b1a-b553-0bc1b235cb05 |  | note | CATEGORY: HP
label | b55c50ee-8a7e-5374-be83-d4e64be7e640 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c9844646-a916-5608-aeee-dd8b56f28c4c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 2df2f842-e992-59ef-8296-57e7bf4c5245 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Design and Construction
label | 9a23f521-021b-5911-88ca-93afd868bec3 |  | note | REFERENCE: IFC Drawings, 614.04, 614.05, 614.06
label | d19aedbb-be0f-534c-a80d-55e6093cac9a |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 96eccdcf-6fcd-5889-b709-521b384908c0 |  | note | Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | 918dce0f-6ee3-5d01-943b-9a6c2ae79a2b |  | note | Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 8bf3355f-89c5-5280-a2fd-18f6d326c214 |  | note | METHOD: Document Review, Visual, Measure
label | da3ca8e1-385f-5099-9bd2-f3965d72f59b |  | note | FREQUENCY: Each type of element
label | 42138e6d-82b1-5ac9-9846-b46ed9398c6f |  | note | CATEGORY: IP
label | f62fc1d4-decc-5e27-93b5-fcf595858bd5 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | b1e49d10-f72c-5c17-af63-10fea11186f6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2a94157f-cd0b-51f2-b525-31e4903c4fa7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | d2ca25e4-6391-57cd-9666-c88cbe852cb8 |  | note | REFERENCE: 614.08
label | ee0e7767-802b-5483-8480-4397ad3dc1b3 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | fce4cc5a-a2d8-5d71-8bfb-0547bfa22f8c |  | note | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres
label | 5314e331-702c-524a-863f-eac45deace96 |  | note | All other concrete members
label | 078b632c-9b0b-5207-8938-c1ed2f1e4b3f |  | note | Any member for which self-compacting concrete is proposed.
label | bd87daa7-fa1c-5912-8b2b-c601f4afd8b4 |  | note | Attach: Attachment A
label | 9e56ef48-dd01-5e3b-b96b-b8d0a37d27b4 |  | note | Attach: Attachment B
label | 9e42cc5c-71ce-594b-929f-35c432546524 |  | note | METHOD: Document Review, Visual, Measure
label | de459b5f-1618-5e52-9e45-e5d4dc70c8fe |  | note | FREQUENCY: Each element (where greater than 2m)
label | 2a03c0b5-7410-568c-81fb-9868fcd5276d |  | note | CATEGORY: HP
label | ea6d2707-3331-5703-898c-18bc8be0fc06 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | d4a9a3a0-6a6a-575f-b5c1-94bf81798a7b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 18130d1c-b874-58e2-b598-efa6289507eb |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | ded0d797-4804-5edb-875b-b4ee74bde37d |  | note | REFERENCE: 614.08
label | 121560c9-e000-5e0c-882f-6b41624c78b3 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 6d41e56e-681e-59bb-bbfb-ef51e65d4adc |  | note | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
label | acc1a199-f43b-51c8-a854-cfb1bb1bff3e |  | note | Attach: Attachment C
label | b3331828-4416-5b11-a543-41b42c970a2b |  | note | METHOD: Document Review, Visual, Measure
label | 19f9b1d0-0747-5d3f-b16c-aa912e6edc2d |  | note | FREQUENCY: Each element (where 2m or less)
label | a0988c05-0879-5f52-937c-29816e002851 |  | note | CATEGORY: HP
label | 3ec1eee6-78f5-59bf-8e77-6543f544b328 |  | note | RESPONSIBILITY: PE/SPE
label | b38ddcbc-0db1-5002-bc00-7c4ab47ec5a5 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | d48ee42a-8a63-5066-ace0-c51bd9afff81 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Pre-pour Survey
label | afce64f5-868a-55d1-9b79-b7f8dd4444ae |  | note | REFERENCE: 610.47 (a), Table 610.472
label | 74905cd6-3aad-53ec-9155-60bec61a4e6a |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | e786be97-2795-5d7e-931f-ca7dc47cf1c1 |  | note | METHOD: Measure, Visual
label | 20dabba4-eb3a-5187-8331-39c67bf024f7 |  | note | FREQUENCY: Each element
label | 71dd6ce1-1d87-587d-bc3f-4d951a414c52 |  | note | CATEGORY: IP
label | 98926faf-9c0a-501e-8d47-c4a52ea86299 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | e972f242-4fbc-588c-9eaa-de3491119c8f |  | note | VERIFYING DOCUMENTS: This ITP
text | ea5462cd-f621-552e-a588-fa265d06a21a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement
label | 6adf5e32-d7c5-51d7-8871-397990c0d443 |  | note | REFERENCE: IFC Drawings, 611.06, 611.09, 611.10, 611.11, 611.12
label | e2df325f-ab3c-5941-b4b7-9be193f0883c |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 6fc11ebe-ed84-5f4c-9f32-8456a28db44d |  | note | Projecting reinforcement is the correct length and location.
label | 9a9ed214-790e-5c0e-8b36-4db4102e889e |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | d976746b-87b6-55f1-80de-30df5f23f3e0 |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 6bf9f6d1-1895-595f-b483-ad5dbb7cf452 |  | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 3568a405-a6f1-51f0-931e-bd22ef6367d6 |  | note | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | 302efedd-4053-5b39-8ca5-6ce97b78871c |  | note | METHOD: Measure, Visual
label | c55eb57d-076c-5648-931f-320db376c093 |  | note | FREQUENCY: Each element
label | a1932b86-b0a5-566b-8cc4-6af44007ed35 |  | note | CATEGORY: IP
label | a3b09e0f-0ea7-5129-bc61-d555432c0712 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 9fc4705a-a379-57b0-8ae2-3d3a93303096 |  | note | VERIFYING DOCUMENTS: This ITP
text | 09a14c6f-67d8-5234-9b7d-4fc9658f9ecd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Reinforcement - Electrical Continuity
label | e3570d05-3812-5a5c-ab0b-1920b3e9ff0f |  | note | REFERENCE: IFC Drawings, 610.29 (d), 610.43
label | 8220c961-e01f-50d2-a294-f0311c0ba8bf |  | note | ACCEPTANCE CRITERIA: Element reinforcement cage to be made electrically continuous by:
label | 78c490d3-8af7-5ddd-a2f7-695e05bf6a79 |  | note | i. tack welding 4 no. min. selected main / longitudinal bars to all intersections of every ligature / lateral bar at 1.5m centres
label | b36572cf-e326-5784-bab8-763f1b6212cb |  | note | ii. tack welding the selected main / longitudinal bars at all splices (2 tacks minimum per bar)
label | b54f3cc5-1ed8-50bd-8615-f40e75946bfe |  | note | iii. tack welding or fastening the grounding clamps to the main reinforcement
label | 7dc1e0bc-b45c-5af1-aede-4c498fd54cfd |  | note | Evidence that the resistance across the cage has a maximum value of 0.01� / 10,000�� is required.
label | 032b36c7-0295-57da-912c-d7542cbb0f32 |  | note | Photograph or attach: Ohmmeter reading from end to end or corner to corner of the reinforcement cage
label | 7d06cb4f-6453-5abb-b5c5-f9464036dce4 |  | note | METHOD: Measure, Visual
label | 1ce93031-45d5-5799-8936-411c1e7367dd |  | note | FREQUENCY: Where applicable, each element
label | c3ea8399-6b2b-573a-be4c-850bdb31bf3e |  | note | CATEGORY: IP
label | 527d26ae-6f29-5020-8b6e-a6150286f8f3 |  | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
label | 36feb8ce-b043-5f9c-8e50-2930c9fdd6f2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3823f81e-d5d8-52bc-a382-f91c3725d41f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 Cast-in Items
label | a3573f3b-3903-542f-afe5-698aa60ee413 |  | note | REFERENCE: IFC Drawings, 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
label | 3c90d2e6-b6a4-58ea-a50c-56ec5c33ce19 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | b9d95a1c-e00b-5138-9d82-2572af1bb283 |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 34253a31-56bf-5b05-9a38-f6de69d51b20 |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | fb519ad5-f894-5f55-9ddf-c86ee94f9a62 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 02127fe7-81ea-5ad1-ba59-8884c2924393 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | c470172e-e323-5486-86bb-d1cf519b7e46 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 965ac793-ebd5-55fa-a56c-4c55602c1789 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | a6a1d764-4d16-55c6-80bb-7dcffd9827f4 |  | note | iii. Ducts and conduit location = ±12mm
label | b2588c59-2bd4-5809-aba5-1a588183d017 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | acb60aff-a7f7-573e-8a63-403718a05241 |  | note | METHOD: Measure, Visual
label | b2635f7d-1f1d-5433-a3a4-e17c28e63fa2 |  | note | FREQUENCY: Where applicable, each element
label | 7c34a8eb-8418-5afb-918f-325d0b6424be |  | note | CATEGORY: IP
label | 5d4e500c-0b03-5496-a041-2f3cbb6513a1 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 53f88de5-f899-58cd-a602-a24d6d5a90c4 |  | note | VERIFYING DOCUMENTS: This ITP
text | a0970411-3b1e-502b-a1cd-8a6e154d0393 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Thermal Differential Monitoring
label | e9939065-a6fe-5cdb-88e5-32d813cf0e9b |  | note | REFERENCE: 610.22
label | 48f03dca-5d1c-54bf-8da1-d2f7f655ce80 |  | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
label | 7fdf83a4-eb7f-5d21-ae1b-a17b8672cf45 |  | note | Only applicable if the element has:
label | d0ede7f7-5186-564c-8fec-4b86b00011da |  | note | i. the smallest sectional dimension exceeding 500mm
label | ae17e2c6-4635-57f2-aa2a-d0a73a3bf836 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 9911cc62-226f-5689-b5b7-9caa1fc8e206 |  | note | METHOD: Measure
label | 26acb5a0-8826-56f9-8bf0-e26b370a484f |  | note | FREQUENCY: Where applicable, each element
label | c2dec2b8-9abf-5da3-838f-bacdcd8c7c2c |  | note | CATEGORY: IP
label | d989de34-f955-545e-af34-3a9db6c44b60 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 18189fbe-2ca9-529c-a13e-4eb183e9262f |  | note | VERIFYING DOCUMENTS: This ITP
text | 9f0abe11-82f8-5009-a930-353f9bbfdc81 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pre-pour Inspection
label | 567a261a-109a-524b-bcd4-ebb78350bf11 |  | note | REFERENCE: IFC Drawings, 610.18 (a) (ii) & (iii)
label | 9f44c230-3f39-5282-92ae-f13eaf490854 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority. All foreign material has been completely removed from the forms.
label | a89dd1ae-ff4b-51b2-92d5-9e19c2d60bae |  | note | METHOD: Measure, Visual
label | 3347c57f-d182-5fa4-bfa4-2c8993bcd732 |  | note | FREQUENCY: Each element
label | 0b0b0cea-c781-5ca4-84ba-686a872e1e28 |  | note | CATEGORY: HP
label | 8f6b2445-2c98-552d-9f84-746a77006bc2 |  | note | RESPONSIBILITY: Nominated Authority
label | 857a5456-2104-5cc9-9e8c-28f492fa0394 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3087fdde-b0c1-58a0-90f5-545a7283faca |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.10 Weather Conditions & Evaporation Limits
label | e52c382e-3fe8-55a8-9990-92ba9e41dca6 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure, 610.17, 610.17 (a) & (e), Table 610.171
label | 9583b5ce-e6fa-56db-a841-d7cea45dc7bf |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 9fd79ca8-b645-5a94-a5a1-943662b7e9ab |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | c95ba554-1f08-56d1-8b44-1f353fa8c466 |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | bbe54aba-4a58-5e17-8fb9-9c5151044ff6 |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | ca421dec-60f1-537c-8030-95fd33b8a392 |  | note | Record: Required information on the Concrete Pour Record.
label | 356b3bac-a7a1-5a19-b2a2-4945ae34de07 |  | note | METHOD: Measure, Visual
label | 294441f5-8dcf-5017-9150-a87d4e09a342 |  | note | FREQUENCY: Each element
label | 6b426494-c966-53ff-8ded-771f19a66917 |  | note | CATEGORY: IP
label | 81fc1b10-b1cb-5fc1-b096-7a730ff6a159 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 22a8c5d7-1afe-52db-a6f3-4c4c30ea32a7 |  | note | VERIFYING DOCUMENTS: This ITP
text | bb253476-3174-565a-9342-42f69ef08bff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Sampling Frequency
label | 5dd9dcb7-ff4e-53e2-ad64-47e3da5e19fd |  | note | REFERENCE: Site Sampling & Testing Procedure, 610.16 (b)
label | 50d9c7ee-c65d-5127-9f9e-deddaf4040f2 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 92d9ed22-c608-5d09-abd3-473e6d3c9156 |  | note | 0m³ to 10m³ = 1 sample
label | 33055125-b3c2-5264-b550-686b7d687e35 |  | note | 10m³ to 25m³ = 2 samples
label | 0f3cb237-61a3-5140-8b24-31ddcecf3a2b |  | note | 25m³ to 50m³ = 3 samples
label | 36638a0e-1b25-5d3c-80b2-d796b8e7e652 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 6ada4062-3b2b-5096-b9f8-41d5a0e7ace3 |  | note | For each additional 50m³ and additional sample shall be taken.
label | 5cc2a359-8919-5ab6-bba4-bef4eea247f0 |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | abab45c4-20bd-5cba-b645-773e564ef900 |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | adc7a43d-0bc5-5085-89ca-31c5eca66d68 |  | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 82169a08-4c02-5079-a66c-606236f99c96 |  | note | Record: Required information on the Concrete Pour Record.
label | 894f00ee-2bc9-5e3e-aafb-a25ddbb05e6f |  | note | METHOD: Test
label | 63f171c9-4628-5fd9-abb8-8b41db2520c3 |  | note | FREQUENCY: Each element
label | e835c03c-4cdc-52f8-b332-dd02a405d876 |  | note | CATEGORY: IP
label | aceee362-01c9-5421-861c-b7e899e42c8b |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | cb4ddb8f-858f-5ed4-acf3-c62e63680006 |  | note | VERIFYING DOCUMENTS: This ITP
text | b06fea77-bfd7-522b-a33a-3c8fbee4ac52 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Concrete Testing - Slump
label | c3b8d4ce-4ff7-5b65-803c-d2d3c4f2332e |  | note | REFERENCE: 610.16 (c)
label | f62efb4d-ddd6-5528-827c-b5dc893d61c0 |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances = <60mm = ±10mm
label | 6b7ea989-2fce-5099-a33d-3a80922e0bae |  | note | ≥60mm to ≤80mm = ±15mm
label | 33e87f2c-a646-5735-bce8-0034076e98f4 |  | note | >80mm to ≤110mm = ±20mm
label | eeffb729-9419-5a3c-bb1e-faeccc7aae8f |  | note | >110mm to ≤150mm = ±30mm
label | 18364d0d-bd95-55b5-b4fc-c092394cb3df |  | note | >150mm = ±40mm
label | aa3a3158-2f13-5c1f-8cf6-9f5113fc6947 |  | note | Record: Required information on the Concrete Pour Record.
label | a8310a5c-394c-5b72-bcb2-f113380b3f34 |  | note | METHOD: Test
label | fe4fe253-141d-5955-b709-4936741c165e |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | e8013985-da01-5e43-9bea-cc0d9f5f456e |  | note | CATEGORY: IP
label | 716fc965-de76-5b38-afff-a119ae106d52 |  | note | RESPONSIBILITY: Concrete Tester
label | ac258b4b-4a57-55b3-895e-0e530a4b6c44 |  | note | VERIFYING DOCUMENTS: This ITP
text | d90e1498-423a-5d42-ae9a-02bec1d20e8f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Spread, Passability & Viscosity
label | 0e209274-a42a-594c-9dbc-097b50a13e55 |  | note | REFERENCE: 610.13 (b)
label | 0f324b11-f3db-5edb-ae8c-ad8b15f02a6b |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | 48d0eec4-f1af-59f6-b1f5-ebc0a14f4680 |  | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 1c3f76f4-00d8-5432-969e-a9020982c2da |  | note | Passability = d10mm (aggregate height differential)
label | 9ce65bc9-7a11-550c-9185-57fa5cb22258 |  | note | Record: Required information on the Concrete Pour Record.
label | 6db0ec2d-a259-5f1b-b258-7834a2fe5ffc |  | note | METHOD: Test
label | af927c48-d48c-5ea8-88ab-42456495d94b |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 61369700-59b0-5542-ab6a-a1467256a32e |  | note | CATEGORY: IP
label | 474d296c-7a17-5f7c-b99d-3f4e81db3c8d |  | note | RESPONSIBILITY: Concrete Tester
label | 51f1604e-7456-59d4-9376-3d0a4d6baae1 |  | note | VERIFYING DOCUMENTS: This ITP
text | a83a82a4-138c-5600-84f3-6ce6dd98b905 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Concrete Testing - Compressive Strength Cylinders
label | 83c23a3a-cdeb-5210-8fcd-5b01700bd6e3 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | da8016c1-537f-5a2d-a1a5-875e604896f1 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
label | a6427173-2b07-5d02-943e-dda9409afe8f |  | note | METHOD: Test
label | d06208af-daad-53be-b3b3-9095552a3cc1 |  | note | FREQUENCY: Each sample
label | ca432a50-3897-5c91-9801-bc57599df91d |  | note | CATEGORY: IP
label | caf32316-8192-597c-b284-7338722e52e6 |  | note | RESPONSIBILITY: Concrete Tester
label | 58914674-7536-53b9-b185-3e3ac1cdea77 |  | note | VERIFYING DOCUMENTS: This ITP
text | b65cc4ec-3ace-52ec-a03e-e8755f8a8dd7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Supply & Discharge Rates
label | eae180da-2e3c-5291-908a-e7da0138cd17 |  | note | REFERENCE: 610.13 (a) & (f)
label | b9496a50-500e-566a-a917-e6842d66d00b |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 70103e6f-7762-55c4-980b-281a4f7fc2a8 |  | note | No water is to be added once discharge commences.
label | 073ad2ce-5541-578a-9cc5-7117b505a6a4 |  | note | Maximum time between batching trucks is 25 minutes.
label | 71acc7d5-4a0c-5f33-ab34-dddbdaed7127 |  | note | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | c7b369fa-20fc-54f1-82c1-9d137d331dc3 |  | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | ad2173e2-94ac-5bb1-be26-0d7aff885cb0 |  | note | Record: Required information on the Concrete Pour Record.
label | 68ea08ce-5be0-5edc-adfd-4b17916ca805 |  | note | METHOD: Measure, Visual
label | cd2d6080-d991-58a1-9e5b-62e4c9af3d9e |  | note | FREQUENCY: Each load
label | a9986e47-5434-5957-bb9f-af1fc42d5b44 |  | note | CATEGORY: IP
label | 22fc7447-ba44-58c9-984b-2a9bcec7eaeb |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 84ff7875-8f20-59d1-9cdd-6bab9065a5fb |  | note | VERIFYING DOCUMENTS: This ITP
text | e78e0edb-0622-5e0b-9751-b3f85c5c28b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Placement & Compaction
label | 6d7f247f-3f6b-5009-b039-d442c513d96b |  | note | REFERENCE: Placement & Compaction Work Procedure, 610.18 (a) & (b), 610.18 (d) (i)
label | 191453e5-d324-5b7d-a4ae-0b1af83c67ee |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | dd6cf09d-c99b-5aaa-9972-39aac22174f9 |  | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 36152fe0-2781-50ea-b33b-bccee6d534c8 |  | note | Concrete is not dropped freely from a height exceeding 2m.
label | 701bb17f-9862-5c91-8e40-4c9a96550419 |  | note | Concrete is not moved horizontally by use of vibrators.
label | f8477a9f-5285-51a4-9162-0c04e982d1a4 |  | note | Adequate compaction is ensured
label | 1270cd50-5b2c-5417-9cb9-1df3e0652064 |  | note | Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 919281a2-bfbc-5a48-b6fb-9726d3f25ac0 |  | note | Concrete layers are not more than 350mm
label | 27c5df7f-682f-5547-a511-6df5d06d6681 |  | note | Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 172d88d9-d7df-5a27-b662-9f20a57a7065 |  | note | Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 74525bd0-5c9b-548b-8f46-0e2436945919 |  | note | Record: Required information on the Concrete Pour Record.
label | 571774a3-60dd-53bc-bbd6-da6c12533a66 |  | note | Attach: Concrete Pour Record
label | 01848f16-1c8f-5c15-a6aa-58e1ed77994b |  | note | Attach: Concrete Dockets
label | b0d7eb18-5960-53d5-a621-5db06989187e |  | note | METHOD: Visual
label | 3cfbde8b-e621-5fbf-951c-c4ba1ebf1a77 |  | note | FREQUENCY: Each load
label | 0224202e-5b07-5fce-b3ee-013dd1942647 |  | note | CATEGORY: SP
label | 2b76c4c4-b681-5335-aadd-d394fdf93a37 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 50e9ec22-f508-5043-8c08-e4a4eef94a64 |  | note | VERIFYING DOCUMENTS: This ITP
text | 673923a6-923a-5a6f-b6dc-bad08c0766da |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Surface Finishes
label | 24a60cfa-c364-54d6-a759-9ad827b20e94 |  | note | REFERENCE: IFC Drawings, 610.31, 610.20
label | 480cb9ee-89d6-5ce0-8971-ed35a0129086 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 4080561b-3138-59a9-9572-af1a6316c004 |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 95830b48-18ab-5a74-adbd-9a7f50e20096 |  | note | METHOD: Visual
label | e824c501-c684-5b72-9a87-a9efdb4b80cf |  | note | FREQUENCY: Each element
label | d6661d00-60e9-5976-8132-0316df0ad50d |  | note | CATEGORY: IP
label | 634aca69-6e9a-57e4-b887-61a7eaf90d2b |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 4fb98b99-d25c-54e0-9ae6-a1262cf678d8 |  | note | VERIFYING DOCUMENTS: This ITP
text | f1847edc-084a-50a6-a357-92c4ca3dc8a3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Curing
label | 3ab421ac-ccc7-5511-a65f-db9118537f3e |  | note | REFERENCE: Curing Methodology, 610.23, Table 610.231
label | cee89d35-d188-5520-9186-921af58fa2fc |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 6f0ec38a-1bd2-5121-b9a5-85abbaf54cb9 |  | note | METHOD: Visual
label | 93037677-aeab-5367-974f-e119c8c93711 |  | note | FREQUENCY: Each element
label | 7e27490d-cf2f-5b08-9c1f-243a6fc3d5b2 |  | note | CATEGORY: SP
label | 42e9c3ed-76f7-5c9d-b0be-0f28ec73fcaa |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | feeca18c-dd92-59d3-a428-856fe941e65f |  | note | VERIFYING DOCUMENTS: This ITP
text | 416e28a5-9eb0-5a12-8694-4e37b82a050d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Thermal Differential Monitoring
label | 989c7c48-ee80-5ace-b72e-5ddc545dd00e |  | note | REFERENCE: 610.22
label | 8d71874e-ba29-577a-961b-f4521f33dcb6 |  | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20�C.
label | d558525e-f5b1-5d6d-a313-5bd267015fde |  | note | Only applicable if the element has:
label | 421e2c00-f307-5458-bc87-2d76fe7b90a1 |  | note | i. the smallest sectional dimension exceeding 500mm
label | 9220be94-290a-5155-8471-42412beb653d |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | c9ed6813-abfe-5741-ba73-9b9a0276d9de |  | note | Attach: Thermal Monitoring Report
label | 35aa3f41-9177-5291-a77e-f81a069a2a92 |  | note | METHOD: Document Review
label | f20105f6-6ae3-57f3-93f1-56fd89cd3bdc |  | note | FREQUENCY: Where applicable, each element
label | 69ba4aad-4b7e-586b-89df-25a76aefdd28 |  | note | CATEGORY: IP
label | 2a767854-67ca-5da9-9289-eaec9c129077 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 633a882a-5a40-5507-a35d-7a72db0440e2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 303f17c9-912f-563e-805d-bce50944e131 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
label | 9166fd51-2afa-5479-8a8b-fec2c2856e5e |  | note | REFERENCE: IFC Drawings, Table 610.251
label | d3876480-6daf-5434-bf33-0fcef41967d3 |  | note | ACCEPTANCE CRITERIA: Where IFC drawings do not nominate minimum strength development for removal of formwork, refer to table 610.251. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | 5f4652ac-df70-556d-8c05-f01eda0dfe2f |  | note | Only applicable if the element has:
label | 58490e52-7d2b-5083-b4b2-34c81465c9d8 |  | note | i. the smallest sectional dimension exceeding 500mm
label | 61aeeed5-203b-5276-9c15-2a804c4b2854 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | eb3205e7-7a8b-5c8b-b152-1054d273e97e |  | note | Attach: Thermal Monitoring Report
label | 14b654ae-5a0c-51c5-809c-3aa98798ef6b |  | note | METHOD: Document Review
label | 4537df01-1977-55c3-91f8-c93ddeda4451 |  | note | FREQUENCY: Where applicable, each element
label | 25a3869c-1dc6-53e6-b205-36f78e89a662 |  | note | CATEGORY: IP
label | 65c42148-8d18-5c4a-ab1a-751f360e03ee |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | c38d6e72-73b0-515f-b59b-8e7ed5a1dc2f |  | note | VERIFYING DOCUMENTS: This ITP
text | 6087176f-a41f-5f7f-b660-05f9b36de381 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection - Cracks
label | 61668ca5-f3d7-5db5-9cdc-30d88f828efd |  | note | REFERENCE: 610.24
label | f75f1ab1-42ff-5db5-bd18-a6581d3accd0 |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1). If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 71ccff73-4b9c-548d-aaf2-e40d064097aa |  | note | Only applicable if the element has:
label | 0f813708-4f3f-5124-9d44-9957a9aafe4f |  | note | i. the smallest sectional dimension exceeding 500mm
label | d1544ccf-93a1-5314-97c1-a809da2e73fc |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | e2037724-967a-5ad5-82d1-63bb28d8e8bc |  | note | Attach: Thermal Monitoring Report
label | c5880c9c-129e-502a-b92a-6469ae150167 |  | note | METHOD: Visual, Measure
label | c19914ff-4495-59dd-a8d4-cb717e566f3e |  | note | FREQUENCY: Each element
label | 78e8b984-4516-57c6-879a-08a5befdd822 |  | note | CATEGORY: IP
label | 421e6a27-5329-5822-80e1-637471e463ed |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0aa51f90-a2d1-53f0-ba44-bedd31328dcd |  | note | VERIFYING DOCUMENTS: This ITP
text | 5fdb6057-5356-5aa6-b5df-aad0c8798df7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Surface Finish
label | 102aac8b-b2ce-513b-8d44-f409927425bc |  | note | REFERENCE: IFC Drawings, 610.31 (a) - (n), 610.32
label | d8a6bb47-294c-5289-b857-b58a1cd5c1e6 |  | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
label | 22f0cfff-77c8-5849-b56d-752736540fb4 |  | note | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 38026483-c5e1-5dd7-8962-245d7d9307f6 |  | note | METHOD: Visual
label | 5c271ca1-8876-5dc1-9b32-9c2954b062f5 |  | note | FREQUENCY: Each element
label | a9f4e186-9634-5f89-95ef-d090d03e4a49 |  | note | CATEGORY: IP
label | d151cc4d-4067-57f3-a045-68ed3d12a62e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3a793a23-44e9-54eb-b11b-26265eec66ca |  | note | VERIFYING DOCUMENTS: This ITP
text | 89381728-375e-53bd-9010-511eeadd1734 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Measurement of Concrete Cover
label | 54c2379c-5ef8-5301-8395-1d1baa9e8a0a |  | note | REFERENCE: 610.34
label | a8893124-17ad-5085-abd0-d9af2e2f00fe |  | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
label | 717e22de-c1c5-58af-b42c-3a31fd36bfb2 |  | note | Minimum 10 no. measurements recorded in each area.
label | 99fbda9b-5bb5-5c71-8711-b261abb196b0 |  | note | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 883af887-c789-53d1-a79f-0febcdcb422b |  | note | Attach: Covermeter Check Record
label | 4ac7b100-0e8c-5687-9575-eeaaf01d2acf |  | note | METHOD: Measure
label | 4e91c4a5-6c8e-558f-a2af-de2eb6b848b0 |  | note | FREQUENCY: Each element
label | 2ee5009e-69e3-513f-92a0-2b35ee99df33 |  | note | CATEGORY: IP
label | 3296eb25-c672-52ce-a3e7-9d962a6a1908 |  | note | RESPONSIBILITY: SE/PE/SPE
label | ef6febc3-5243-502d-a1a4-ca20e682a731 |  | note | VERIFYING DOCUMENTS: This ITP
text | 37a0a671-a709-5e18-b3dd-02518facfa29 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 2849aa3e-e78b-54cf-87f2-44333e39f066 |  | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure, 610.35
label | bc52587b-6914-5adc-8160-a728e7e02b7f |  | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
label | 56d96c5d-10ac-5ad3-bd24-816c9bd334fe |  | note | Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | c7d8a2b1-f517-5e9a-8d4e-2e3e48bada99 |  | note | Attach: Concrete Test Results or Maturity Test Results
label | 4b5dad0d-a75e-5088-87f5-4c6d90275c74 |  | note | METHOD: Document Review
label | 3415a757-b91f-586e-aea7-2ece1ee7c308 |  | note | FREQUENCY: Where applicable, each substructure element
label | 03ce317b-d0d4-5880-9890-55919a13fdb6 |  | note | CATEGORY: SP
label | 52a61b11-f8f6-5a35-829d-75d2b3bcd6ca |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | abd6c29c-c24a-5610-a598-58601ee3f824 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0ebd1570-7b9e-5270-ab74-299ff4bcabf7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Early Age Compressive Strength Results - Early Loading and Trafficking of Decks and Approach Slabs
label | 2b03442f-3ec6-5ab8-8178-540d5cb3f460 |  | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure, 610.36
label | 8cdc218c-c2e8-5a6b-b54d-7e586d88dfb6 |  | note | ACCEPTANCE CRITERIA: Minimum compressive strength requirement of 32MPa.
label | 02a4c84d-609d-59c0-9523-4ca0e0cc9fcc |  | note | Minimum duration before plant and equipment may access = 3 1/2 days.
label | 7631c18e-aead-5dcf-a34a-db3576d62b60 |  | note | Minimum duration before traffic open or element loaded = 4 days.
label | 595d396d-c9f0-566d-9b53-16c703b806c1 |  | note | Attach: Concrete Test Results or Maturity Test Results
label | a0a4ee62-3af6-59a6-a36d-654069828881 |  | note | METHOD: Document Review, Visual
label | 07ffd956-75b8-5977-8da1-51d66d150ab6 |  | note | FREQUENCY: Where applicable, each superstructure element
label | d0e53ee5-541a-5c33-8da0-4538f0096f15 |  | note | CATEGORY: HP
label | 7efee2ec-f168-5962-9529-da8b6c7c0f8c |  | note | RESPONSIBILITY: Nominated Authority
label | 28ab6997-d1f7-5ff5-9792-3c151d57e3f8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 881ee687-c797-560f-8c8a-dbd00c278540 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.8 Compressive Strength Test Results
label | ef78adb0-40b5-5777-8d4b-f374732f1289 |  | note | REFERENCE: IFC Drawings, Table 610.05.051, 610.16 (g)
label | 1e801315-d911-5a8c-88c6-310d3032ec03 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | d147f6d0-bfc3-5d21-848c-291b5f8d16be |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 3f7091bd-beb1-51a9-96dd-db497c4eafc1 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 86dc321c-1266-582d-b4e5-54f07d483d1d |  | note | Attach: Compressive Strength Test Results
label | b384b51f-57c9-51f4-b54e-829929f5c3ec |  | note | METHOD: Document Review
label | e8e3fd20-5870-5a7d-a031-9d02b7fa22a6 |  | note | FREQUENCY: Each cylinder
label | f1db15cb-b19c-5ab1-a84c-4887ba0ddff6 |  | note | CATEGORY: IP
label | 76136e02-6ab1-57bf-82cb-465f29b45cdb |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4fe9d1bc-5370-50d2-bd14-5af4a618fe70 |  | note | VERIFYING DOCUMENTS: This ITP
text | fa1bb77f-6645-5b75-a81b-64843a31d207 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 As-built Survey
label | e4ad722f-2d6a-5192-bbbf-844599bf9955 |  | note | REFERENCE: IFC Drawings, 610.47, Table 610.472
label | 401f53da-7a11-5a39-bf26-bb874dc08938 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | 4c427359-d841-5c7b-84fc-a81eb1003585 |  | note | Attach: Survey As-builts / Survey Report
label | ea3f7491-98e5-5257-bb55-445ab1e327bd |  | note | METHOD: Document Review
label | bb21eb56-b9e3-570e-a99c-f4255715ffa9 |  | note | FREQUENCY: Each element
label | eedfb6da-caa5-586f-9096-c51dc0ff7737 |  | note | CATEGORY: IP
label | dd43c740-7a05-5bb4-b58d-781905e074e6 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | be88abf9-34d7-5c9c-adc6-a17bf610879f |  | note | VERIFYING DOCUMENTS: This ITP
text | 1189029f-43e4-50ff-a31a-a3d818a7814d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 Non-conformance Report (NCR) Closure
label | 518b46e8-8653-53c9-805d-197e5602c859 |  | note | REFERENCE: MRPA Quality Management Plan
label | 10bad0ba-1d14-5a26-ae3d-06ad38d36b3d |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 9a3dc134-04da-5d0b-872d-6eac0d61916e |  | note | METHOD: Document Review
label | df5c05e9-1552-517d-9af4-7ec3b7f62304 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 09d4b7f4-e5d1-549d-9c8b-c4764463ece1 |  | note | CATEGORY: HP*
label | 02c964a2-1e9a-5ae1-866d-be48f78a20ff |  | note | RESPONSIBILITY: SE/PE/SPE
label | 19fb8275-f8f8-5195-a413-3a6176dafb46 |  | note | VERIFYING DOCUMENTS: This ITP
text | 80583f97-4b84-56a2-b72f-e9428455659b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | dabc7d55-447e-5fda-9330-12c72bcc9d1e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 84be6865-dbd1-58b2-bcf8-e9a76fa70f46 |  | textbox | Name:
text | 2aece164-b5d3-55a5-83be-2a20c72e429a |  | textbox | Position:
text | 25335f4b-a02f-5124-ad2c-80632627e3f6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | Conduit and Pit (Roads)- Products and Materials Rev0.0 | itp |  |  |  | Yes | ITP-CIV Conduit and Pit (Roads) - Products and Materials | 0a5d970c-6bb8-4726-a4d5-fde70af3388a
checkpoint-no-status |  |  | checkpoint | Reference Documents:
label | 31c0adfd-b46b-436c-a484-41327cb1a02a |  | note | VicRoads Standard Section 733 (April 2019)
label | 335c7ae9-5198-4c9f-9a54-40554b2df324 |  | note | VicRoads Standard Drawing TC-1220
label | f7e2c50f-ac88-423a-9958-c39256f3efb6 |  | note | VicRoads Standard Drawing TC-2204
label | 74c917a5-0cc7-4c0b-82db-21382d263149 |  | note | ITP Revision: Conduit and Pit (Roads) _00
label | b85f012e-087c-4c1f-9c8a-1fab81ecc614 |  | note | ITP template approved by: Romualdo Magpantay(October 2019)
checkpoint-status |  |  | checkpoint | 1.1 - Electrical Conduit
label | cb9f7266-7be9-431c-a29b-a26c86bb376c |  | note | All conduits installed underground for electrical wiring, traffic signals and traffic services shall be heavy duty grade , rigid orange, UPVC conduit to AS/NZS 2053.2 or Profile wall-smooth bore HD UPVC conduit to AS/NZS 2053.6
label | d8329fe9-2c7b-4ede-8eae-d3274bde5e74 |  | note | NOTE: Profile wall smooth bore and sandwich wall type conduits shall not be used for VR works.
label | 7158ed3d-6f8f-4bc8-9743-61f5eb2a6ff3 |  | note | - - - - - - - - -
label | c3fbdb56-3086-4858-b08d-580232e8c76d |  | note | References - 733.02(a)
label | 18b31c0d-31ed-4148-a721-dd654cf1d0c1 |  | note | - - - - - - - - -
label | a7b41f09-1c5b-4fac-9dec-d321399e52cc |  | note | Verification Record - Certificate of compliance from supplier
label | 6538f6d2-38c8-49ca-963e-9fa71fb14d9c |  | note | Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.2 - Communications Conduit
label | 89fe4e9e-1e48-4e97-bac7-70aa20b8150f |  | note | Rigid white UPVC communication conduit complying with AS/NZS 2053.2 or Profile Wall-smooth bore HD UPVC conduit to AS/NZS 2053.6
label | 86a0e00b-a84b-44d3-b0ee-d3ad559f0b4b |  | note | - - - - - - - - -
label | 0bc627ab-f716-47a9-a7c6-214409d4eda4 |  | note | References - 733.02(a)
label | 7d3cb3a0-6e72-4d7c-a022-ca563bc6ee45 |  | note | - - - - - - - - -
label | 21135147-33fa-48e7-aa7c-7efc6896013d |  | note | Verification Record - Certificate of compliance from supplier
label | 160db65c-715a-43d8-93f6-c65f9550ffa9 |  | note | Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.3 - Conduit for bored road crossing
label | 8539ddbc-5994-4d60-95ac-462246ed41e9 |  | note | HDPE continuous conduit is permitted. Ensure internal diameter is not less than specified.
label | e6bce093-cbdc-40a1-9a9b-e4eab2df1048 |  | note | NOTE: Profile wall smooth bore and sandwich wall type conduits shall not be used for VR works.
label | 546995fc-79cc-4884-90fc-746b31773ebc |  | note | - - - - - - - - -
label | d8a3e4b7-17cf-47c4-a708-8b4211d80515 |  | note | References - Table 733.021
label | 1435e07b-a7a8-4397-a9b5-adec5139e187 |  | note | - - - - - - - - -
label | 09d5e5a4-45ee-41d6-ab87-c28816a2640f |  | note | Verification Record - Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.4 - Bedding Material
label | 0d20e9e6-aa53-453f-8404-812951586b88 |  | note | Sieve size AS
label | dc7e25b7-bbdc-4398-a8b2-f30c9af98df8 |  | note | 19mm - 100% passing
label | 250e1911-6b34-45d6-abed-86bd8ab22860 |  | note | 0.075mm - 10-40 % passing
label | 8ed713b9-f7d6-4588-8cdc-0c1efd406a9a |  | note | Plasticity index 2 - 10
label | 5131f99d-7c46-4e79-bd10-7538f046df3f |  | note | - - - - - - - - -
label | c338b3df-4e84-414a-b16f-e3e9bfbf223b |  | note | References - 733.06 Table 733.061
label | f5a725bf-a348-460e-b35f-f8f07cfb64a5 |  | note | - - - - - - - - -
label | 528c8679-41e2-4fc5-9a58-147e390431b1 |  | note | Verification Record - Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.5 - Select Backfill
label | 82e3241b-6097-4d86-8a11-5fe13608ff31 |  | note | Sieve size AS
label | f5033e96-c0dc-47c6-bbc4-1e1b0e1d63bf |  | note | 75.0mm - 100% passing
label | cb9ee98a-558a-4570-a427-737731bc706a |  | note | 2.36mm - 40-100 % passing
label | 78707078-2c2c-4722-95b7-d6b510bf1239 |  | note | - - - - - - - - -
label | e889a50a-fd51-4fd1-9a8e-52e65e84f27f |  | note | References - Table 733.061
label | fc657cec-2df1-4b5d-91cd-5a034f346b6f |  | note | - - - - - - - - -
label | 17f0cdbd-ea1b-4bde-981f-f7176b23a7a3 |  | note | Verification Record - Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.6 - Common Backfill
label | 3c4a2424-b798-4090-b407-cc9deb4d23cc |  | note | Sieve size AS
label | 1ee9820c-b8af-4f9d-81a2-0799c65821e9 |  | note | 19mm - 100% passing
label | 46b81afc-fa97-498a-bbe9-e28475b69cb9 |  | note | 0.075mm - 10-40 % passing
label | 8483f602-a5f5-490a-9092-29b8a8228c27 |  | note | Plasticity index 2 - 10
label | 23ebab57-ba52-4e0c-93c8-74bd06f3d4f9 |  | note | - - - - - - - - -
label | 48d10dad-201f-49f2-af2e-f2f60868d285 |  | note | References - Table 733.061
label | 8e577ce9-8de7-435a-a0b5-8ce3d1d0f32e |  | note | - - - - - - - - -
label | c10e235d-bf7a-47fd-bace-165845bcefde |  | note | Verification Record - Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.7 - Pit Lids
label | 3b29f051-9750-471b-a24a-cd40371439e2 |  | note | Cable pit lids shall be VicRoads type approved, impressed with 'VicRoads' and 'Electrical', 'Communication', 'Traffic signals" as appropriate as per VicRoads Standard Drawing TC-1220
label | f2a07b22-3c34-496a-936e-716f99316425 |  | note | - - - - - - - - -
label | cabe61f8-4ac2-4afc-ba01-4b1e4a2681d0 |  | note | References - TC-1220
label | bb626869-f648-4f7e-954b-1f90ba585af0 |  | note | - - - - - - - - -
label | b731ae9a-b28c-4545-bbf5-519968b7f024 |  | note | Verification Record - Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.8 - Pits and surrounds
label | c8ae6d12-b82d-402b-b537-fea451d3222a |  | note | All Pits and surrounds shall be VicRoads type approved. Pit, surround and lid are compatible together.
label | 5fa176c0-014c-458a-a66d-f59c4b745a29 |  | note | - - - - - - - - -
label | cf6e1338-1414-4cad-93b2-b0ac09e80e99 |  | note | References - 733.07,
label | 9e77349c-ae38-4f70-82b5-a3e5b4d0633f |  | note | - - - - - - - - -
label | f9da7832-2631-431e-bd9f-f1a59817452c |  | note | Verification Record - Record teambinder material approval number
checkpoint-status |  |  | checkpoint | 1.9 - Details of boring
label | ce4ce283-801d-41a6-9127-00cc21009a41 |  | note | Detailed proposals for boring under carriageways shall be submitted to the Nominated Authority for review prior to commencement of work.
label | 6303e1ba-95f6-4b85-ba89-ad4e06ef21f5 |  | note | - - - - - - - - -
label | 75a30c50-d21a-4860-8771-ed8f8244fca1 |  | note | References - 733.03
label | 78f0d3b8-5efb-4617-b866-55cca2ff7de7 |  | note | - - - - - - - - -
label | db74f9f4-8d33-4912-8bff-c6344812e1a0 |  | note | Verification Record - Refer to teambinder reference
checklist-sectioned |  |  | checklist | ITP-CIV-Clyde Rd Street Lighting (Supply and Install) - VESI Rev 0 | itp |  |  |  | Yes | ITP-CIV-Clyde Rd Street Lighting (Supply and Install) - VESI Rev 0 | 0b86a3e6-dc1f-42ea-8132-e1035a284c19
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | f8831f76-8e5a-5922-a36d-3a1f090a49d4 |  | note | ITP Description: Street Lighting (Supply and Install) - VESI
label | b3e3d694-41f1-55ce-86d0-6ff0ea6505ff |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 5793df7e-2d62-54ac-9969-8baf5e98620e |  | note | Revision Number: 0
label | 4c0291dc-85d1-5dee-9dbe-e28c3d58bbc8 |  | note | Revision Date: 05/08/20
label | 775b2455-fc67-5a9b-acc3-e4f44fbd08a7 |  | note | ITP created by: Christofer Cappelleri
label | 457fff2c-3313-5864-b58a-9a1e6e4f49bb |  | note | ITP approved for use by: Josie Pavlou
checkpoint-status |  |  | checkpoint | 1.1 Non Dependent
label | c3187918-4d27-5a51-b0e2-878f86aac392 |  | note | Reference: IFC Drawings
label | 6d99a435-5bd2-5e9c-942a-8b4717e9369b |  | note | AusNet Services
label | 3a1d6ddb-b2f8-5806-baeb-331b302b2283 |  | note | Technical Specification
label | aeb26a94-dc89-5f14-8641-3d70c104330f |  | note | Project No. 75065539
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 - ACCC Form
label | 3b8fe0d1-e6da-5e10-a6c5-0e637e83232b |  | note | Reference - IFC Drawings
label | 277d8f69-1ba5-569f-a0d5-91d75664c7f8 |  | note | Acceptance Criteria - Before any works commence, the accredited contractor shall obtain an "ACCC Form" from AusNet Services representative for permission to commence works.
label | a017d1b2-0a80-5ddf-9ead-6565171ceb97 |  | note | Method - Document Review
label | fe879d0f-a37d-5ca9-8f92-3263ac1bc03c |  | note | Frequency - Once prior to works commencing
label | aacd9866-5a73-5ceb-88bb-ede675b3a3b9 |  | note | Category - WP
label | 09dcf2d9-1ec4-53b3-80d3-5ab6860d203f |  | note | Responsibility - SE/PE/SPE
label | 8fcf289c-2aa0-54bb-b21a-05c1c2a6613a |  | note | Verifying Documents - This ITP
text | 20a5ef81-a3f7-5840-b1cc-f1ec9c5cd8dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Prequalification
label | bec8631c-7dbc-5d89-8816-4a6c38ff7816 |  | note | Reference - IFC Drawings
label | cd918865-91fb-57ea-88c5-c251767fadfc |  | note | Acceptance Criteria - Subcontractor to be a VEDN accredited contractor.
label | 1802be77-7a33-5019-902d-5156f5738b4b |  | note | Method - Document Review
label | 4a309767-8a54-595a-b4a8-9183c5bbbc2b |  | note | Frequency - Once prior to works commencing
label | 1644adb1-8cc1-53fe-b7c7-716eef1c7490 |  | note | Category - WP
label | 406cba61-7252-570e-a572-eb06fe19cef8 |  | note | Responsibility - SE/PE/SPE
label | faf85941-481b-5014-a8db-089d7d8a85a3 |  | note | Verifying Documents - Reference TeamBinder Approval No.
text | 1df2ea1a-3115-5a53-9112-9b92903125e7 |  | textbox | TeamBinder Approval No:
text | 91e772a6-a106-56bc-9d34-1d9056a69785 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Auditor
label | 6bc489b8-d38c-5ee1-a630-078be9bd22cf |  | note | Reference - IFC Drawings
label | 674f8423-38e6-5df9-8ae4-eebd4a20b920 |  | note | Acceptance Criteria - VEDN approved civil auditor
label | dc6aeb37-8599-5e4d-a61f-564abe2cffda |  | note | Method - Document Review
label | 67665a51-f28d-5502-8507-23e51155917b |  | note | Frequency - Once prior to works commencing
label | 5064caf9-0469-5ada-882f-5514d06883bf |  | note | Category - WP
label | a73152c4-ac78-5510-8fd9-f9be7d78f6a9 |  | note | Responsibility - SE/PE/SPE
label | 774ab012-8a2e-5e76-9a82-ad2d7861a42b |  | note | Verifying Documents - Reference TeamBinder Approval No.
text | 57f2e850-d947-5d9b-afe4-3b47826fd8b9 |  | textbox | TeamBinder Approval No:
text | c05af450-50c5-5e6f-a68e-24df8369dc62 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.1 - Material Compliance
label | 0344d532-d449-574d-9f9e-2f2c2b40f61f |  | note | Reference - IFC Drawings
label | 090ad1d9-3270-5da2-8025-cdd29ca38497 |  | note | Acceptance Criteria - Materials to comply with VESI Standards
label | 1c2b1354-a7c7-5c3c-ab07-ded00a78bf11 |  | note | Method - Document Review
label | 01dec8eb-2601-5223-bb19-63173cc6c2ef |  | note | Frequency - Per Source
label | f75f461a-774a-5e23-9e2c-1d1a4b32b69c |  | note | Category - IP
label | 921319a9-a4d9-5ac7-92aa-af3cfbb9964c |  | note | Responsibility - SE/PE/SPE
label | af17ae9c-2023-594a-aa0c-f8d834b62c85 |  | note | Verifying Documents - This ITP
text | 1da4de08-9f28-50eb-8061-822c12152d59 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Inspect supplied items upon delivery
label | cba80fd3-74bc-5072-b606-27585d6cab58 |  | note | Reference - Vic Road Standard Drawing TC1064, TC1065
label | 8e88654a-2982-5491-843a-8781d0207538 |  | note | Acceptance Criteria - Supplied items are to correct spec, class, size, undamaged and brand new.
label | 4f33185b-103a-55c7-a22c-78a229ad92b0 |  | note | Method - Visual /Site Inspection & Document Review
label | 7feaeef4-f6cc-53f5-8a81-f90a40f6d964 |  | note | Frequency - Per Delivery
label | 3c19763f-9f6b-581e-b265-bcb1bb590035 |  | note | Category - IP
label | 1267f1c8-abfa-596b-81ce-90d3168fe17c |  | note | Responsibility - SE/PE/SPE
label | c43dab7b-b679-54f6-9e03-0d172c4fa631 |  | note | Verifying Documents - This ITP
text | 3b0112f3-398c-5310-87cb-648d3d9a3aea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Survey set out
label | 9e6a27bf-57ee-5cb2-be7a-57979eaf5dde |  | note | Reference - AusNet Services Technical Specification Project No. 75065539
label | 553677a5-a934-5e41-9e1a-b0ba4257da04 |  | note | Acceptance Criteria - Set-out survey carried out by a surveyor and within the tolerances as per AusNet drawings/specs.
label | 9ea93e53-4879-5df2-952f-9bca9ff8498f |  | note | Method - GPS/Visual
label | 840a8d6b-d025-56fa-8935-7514028a7d92 |  | note | Frequency - Each Element
label | f1edb31b-f4d2-5ec0-9074-270e30ae55ab |  | note | Category - IP
label | 95dd7acf-9aca-53e5-bf4e-1de1fb50870e |  | note | Responsibility - SE/PE/SPE
label | 1068e613-7940-586a-bcc7-15a5f42bde08 |  | note | Verifying Documents - This ITP
text | 217041dc-97ef-56e5-a6b9-cf9a7397d5cd |  | textbox | Date Completed:
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 3.1 - Pit and Conduit Installation
label | b066f6dd-45c8-5417-9ec9-96144923b867 |  | note | Reference - IFC Drawings
label | 53efb8fc-6deb-5f5e-b1b9-c02b11f8443d |  | note | Acceptance Criteria - Conduits and pits to be installed as per IFC Drawings
label | aee2c625-1ce7-5d1d-8408-470b3150c173 |  | note | Method - Review Document
label | afaa2c62-6561-52fd-9bb8-4b7a2a440aa8 |  | note | Frequency - Prior to commencement
label | 64cc34f6-526b-5432-ac2b-e19d4ae0f5df |  | note | Category - WP
label | 5994aed0-e037-5462-8353-7ab40e2c5415 |  | note | Responsibility - SE, PE
label | a4d04278-ceed-5bd6-a40f-d0b892fb1106 |  | note | Verifying Documents - This ITP
text | 076c214b-ac44-539e-912f-0762b5875efc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Conduit and Cable Detailing
label | 90976136-210d-5a4d-869a-d79c21732176 |  | note | Reference - AusNet Services Technical Specification Project No. 75065539
label | ee614be4-073b-57d2-b218-56a9df3dc64c |  | note | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer Verification document: As-Builts
label | 37616ad8-b9f7-5f33-85b9-20b0d0d72420 |  | note | Method - Site Inspection
label | 6be48188-9f82-52be-85bc-b2ae89972e14 |  | note | Frequency - Upon completion of each section
label | 4b2bcf3f-e7b6-5192-8611-bf0703886847 |  | note | Category - IP
label | e1302bff-6b59-5da8-b16b-d3a1abe0b9d7 |  | note | Responsibility - SE/PE/SPE Services Engineer
label | 26985af0-0fbc-5d89-8f0d-db1895462386 |  | note | Verifying Documents - This ITP
text | 64993559-8d83-5ee6-bb8e-f808ae96c1aa |  | textbox | Date Completed:
checkpoint-group |  |  | section | Light Pole Works
checkpoint-status |  |  | checkpoint | 4.1 - Installation of Light poles
label | 01c3f191-f792-53d1-a16f-bf7befd1b496 |  | note | Reference - IFC Drawings
label | dbdc1220-1987-52c3-8f41-dd50e94d5dc3 |  | note | Acceptance Criteria - Light Poles to be installed as per IFC drawings in accordance with VESI requirements.
label | 3200923f-0b25-5de8-9024-00a324358067 |  | note | Method - Visual /Site Inspection & Document Review
label | 9eb27818-269b-5115-972d-ab3d871df9a2 |  | note | Frequency - Per Lot
label | fa909c74-ad81-5324-8e04-9f0f6bf13bc3 |  | note | Category - IP
label | 42c8f6d5-8036-582e-923d-56a29f16285a |  | note | Responsibility - SE/PE/SPE
label | a12a000a-e888-53e5-bb20-d021984faf6d |  | note | Verifying Documents - This ITP
text | 004ae347-9c21-58c6-8352-a28e0fea15fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Asset Labelling
label | af872a21-553c-58ac-8c61-60e5c0d246a5 |  | note | Reference - IFC Drawings
label | 75b6e46d-9ca1-5f0a-a3e5-19f9eb0a6142 |  | note | Acceptance Criteria - Pole Labelling to be as per IFC Drawings.
label | 742675c3-c604-55f2-a008-69ff3abd9e19 |  | note | Method - Visual Inspection
label | 526d8761-d4f1-555c-82b1-51665bb1dcf6 |  | note | Frequency - Per Lot
label | 3e14a71a-73a0-548d-a1cc-9596bd8d042d |  | note | Category - IP
label | e441fb14-4251-51d4-84ad-4a8e0e71bf36 |  | note | Responsibility - SE/PE/SPE
label | 14458229-1dda-59be-9b40-23af1eab7163 |  | note | Verifying Documents - This ITP
text | 22ff91ca-26ca-5cfe-b8e7-d5c08ef5d941 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | 5.1 - Commissioning & testing (Civil Audit)
label | fd25d143-d1df-544f-a031-2cd1682d7486 |  | note | Reference - AusNet Services Technical Specification Project No. 75065539
label | 65c3cfba-366b-57a5-83ee-2a54dfe3f5b0 |  | note | Acceptance Criteria - Upon completion of all trenching and conduit install, a Civil audit by a VEDN approved Civil auditor will be completed and approved before proceeding.
label | 8d514088-1457-5ed0-af49-a1c4a051a6db |  | note | Method - Commissioning & testing
label | c10c27eb-5882-594d-a0b4-49d025f0ec5c |  | note | Frequency - Upon completion of each section
label | ed0a4d4a-57c7-5961-aadf-b464dc841bcc |  | note | Category - IP
label | 8d28eec0-81e7-5626-b31e-ada482fc9f4c |  | note | Responsibility - SE/PE/SPE Services Engineer
label | 19b9552c-e6ae-56e7-85c0-65cd7e893856 |  | note | Verifying Documents - This ITP
text | 243311cf-1764-513c-af5f-b3c093b753c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Commissioning & testing (Trench Inspection)
label | 78d2037a-8920-5f06-93a6-fb7bece86215 |  | note | Reference - AusNet Services Technical Specification Project No. 75065539
label | d6475072-be13-5226-bd81-b7dff76918f4 |  | note | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer Verification document: As-Builts
label | 5c206f44-bbc2-5133-97d6-747df52bfa50 |  | note | Method - Commissioning & testing
label | 63e525e7-9a81-5ae9-8e75-44be6f0615ef |  | note | Frequency - Upon completion of each section
label | 7db5bd6b-a5c0-5621-9b10-01513700a183 |  | note | Category - IP
label | 5f741658-119b-5814-9b48-a160256c4a63 |  | note | Responsibility - SE/PE/SPE Services Engineer
label | 6045f98c-b384-5d66-8246-02b4d1d24988 |  | note | Verifying Documents - This ITP
text | 3c42f8a2-1e03-55bd-8ecf-d52bda0b6dfc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Commissioning & testing (Pre-commissioning)
label | 3d9d4322-861c-5b1d-be21-74141670a49e |  | note | Reference - AusNet Services Technical Specification Project No. 75065539
label | da1f9566-8806-5d20-a9a5-2382b483c53f |  | note | Acceptance Criteria - Passing of the pre-commissioning audit with all non-conformances rectified.
label | 87f6593c-e5db-5b2f-8b3c-41a682954a5c |  | note | Method - Commissioning & testing
label | 2ff77401-52d1-5fde-91ae-47b5999e9daa |  | note | Frequency - Upon completion of each section
label | 2c155cbc-8b75-5419-8ddb-a6676d1546b0 |  | note | Category - IP
label | 8c0191a3-6056-5a19-afb9-b3a0416f5f91 |  | note | Responsibility - SE/PE/SPE Services Engineer
label | 37491e1d-5577-51a1-89e2-b967f6c3865e |  | note | Verifying Documents - This ITP
text | c7a65340-2770-510f-b475-6b1b03fc3407 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Commissioning & testing (Final Audit)
label | 2adef817-a0a8-57ab-ad53-b3ea1a623972 |  | note | Reference - AusNet Services Technical Specification Project No. 75065539
label | cce74f60-dd56-5584-9f76-b2c67c95ad86 |  | note | Acceptance Criteria - Passing of the final audit will be completed by AusNet Services to inspect the completed works with all non-conformances rectified.
label | 32543f9d-007e-5294-8205-7559fc4fb26b |  | note | Method - Commissioning & testing
label | 96500039-2de2-5dbe-8e18-fa192376533d |  | note | Frequency - Upon completion of each section
label | 75ae8a05-d0b0-5841-84bd-80166de13d77 |  | note | Category - IP
label | ecbb5241-e192-5371-a241-9534364c6659 |  | note | Responsibility - SE/PE/SPE Services Engineer
label | 4ff5a67a-569c-559b-8173-6247488407c5 |  | note | Verifying Documents - This ITP
text | 58ab0f6b-ee84-540e-ae0b-8e0c122ef018 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Testing and Certificate of Electrical Safety
label | 1debf6d8-fe13-5e19-9b4c-e5407702f88c |  | note | Reference - IFC Drawings
label | cfe55858-d46d-5bb7-bd3c-6576ac929ede |  | note | Acceptance Criteria - Prior to final acceptance, the contractor shall test all distribution cabinets, circuits, switches, PE Cells, luminaires, and all other electrical and electronic components for correct installation and operation Attach Documentation: Certificate of Electrical Safety for electrical installation
label | 2bf1cfb3-51d4-55f7-8324-a2ce68070260 |  | note | Method - Document Review
label | 9351a03d-d949-5731-8f98-ac4f8d64e946 |  | note | Frequency - Upon completion/ Work area
label | 501c5338-5d5f-54f0-9732-72ce2e929869 |  | note | Category - IP
label | b7f72b88-59bd-536d-9d11-938697ff15bb |  | note | Responsibility - SE/PE/SPE
label | 232ec94d-ab8c-5bb6-9aee-48d590d584a8 |  | note | Verifying Documents - This ITP
text | cabb0475-1d8d-5479-8837-0cf9e439f7b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - PC Cert of AusNet Agreement
label | 7eb3e5ad-84aa-59cb-b1b0-1f316b665089 |  | note | Reference - IFC Drawings
label | 0601856c-6703-5b05-adbb-301b9d0a170b |  | note | Acceptance Criteria - To be signed off by FH and AusNet
label | 8515d9b1-96f9-5576-95d9-3b1281c38fb4 |  | note | Method - Document Review
label | 9d1ae9bf-4622-52a1-9965-66d3faf4db0f |  | note | Frequency - Upon completion/ Work area
label | 544a2bf0-7758-5e2c-830c-d94741b658ca |  | note | Category - IP
label | be1c59db-754e-59b8-b6e0-3a7ee848722d |  | note | Responsibility - SE/PE/SPE
label | bdd63665-aee3-57e0-a23b-8135a40c2f39 |  | note | Verifying Documents - This ITP
text | d219b67e-fa8e-57c0-a861-95df6daba150 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Non-conformance Report (NCR) Closure
label | 0a8d8f5e-3023-5344-95e9-b6840788951f |  | note | Reference - MRPA Quality Management Plan
label | 1c073271-a69d-5a14-bafa-b572e17f6358 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in TeamBinder.
label | d004e653-ddc9-5d8a-9b1c-0dcd69263013 |  | note | Method - Document Review
label | 206060d4-3508-58d4-a5d1-1262c803da38 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 57459297-dbf1-5584-b9b6-14fab0e430cb |  | note | Category - WP
label | 3e02c191-f6e2-54ae-bb6b-ae74f0c17878 |  | note | Responsibility - SE/PE/SPE
label | 22ab8b46-8570-585a-9734-a16cd0cc80ec |  | note | Verifying Documents - This ITP
text | ce6e016a-3a0c-5064-914e-e600d7741f8f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1c630ab8-fcf0-5edd-9f26-0bda86157c78 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2e66b56d-ad28-5428-9dc6-6ea49794ffd2 |  | textbox | Print Name:
text | e341228e-c8dd-5c0c-ae48-89b08098e6f9 |  | textbox | Position:
text | bee606f1-3895-50fa-8469-611b7b151325 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-CIV Conduit and Pit (Supply and Install) – MTM Car Park Lighting Rev 0 | itp |  |  |  | Yes | ITP-CIV Conduit and Pit (Supply and Install) – MTM Car Park Lighting Rev 0 | 0fd106e9-a8a6-4c0d-832c-29f795cc69f3
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 8245882c-6d26-4074-845e-f768edfe5621 |  | note | Document Title: Inspection Test Record – Supply & Installation-Conduit & Pit (Electrical & Communication)
label | ff1863f7-d941-493c-997c-f2b55c1f869a |  | note | ITP Description: ITP Checklist -Supply & Installation-Conduit & Pit (Electrical & Communication)
label | 7491555e-17e6-436e-8f60-de995fde207b |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 7d23be5c-3fde-4209-80b4-fdcbf966b6c1 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | ba93151b-5e55-4236-8370-b74b3a34739d |  | note | Revision Number: 0
label | 38fd57a3-e18f-45f6-9431-05ba6ad0c7d6 |  | note | Revision Date: 3/11/20
label | bdb4abe4-5ba9-4ef0-8128-c0ae2f78a6b9 |  | note | ITP created by: Romualdo Magpantay
label | 9d83dd7f-3579-4b85-ba08-a06b9abe2877 |  | note | ITP approved for use by: Romualdo Magpantay
label | 68f7a394-43fe-47cf-8624-770b1ed82da3 |  | note | 1.1 L1-CHE-STD-035
label | f8b93d03-af6c-4739-be9c-b5ace0199606 |  | note | 1.3 AS /NZS 3000
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain and review manufacturer documentations for the supply of materials
label | d80e24b7-5c33-4b23-82f0-1e4e7d8857fe |  | note | LV + HV Conduits
label | faa4d201-07da-4bc3-9f1d-af8dc3bb2a88 |  | note | Communication Conduits
label | e8f10562-01cf-4961-89af-05ebc767d605 |  | note | Fixing and Supporting Materials
label | f835262a-df9c-4de1-b70b-c5712bb8895d |  | note | Pits
label | ef98ad83-fa24-4220-950e-333097a852d4 |  | note | REFERENCE: IFC Drawing
label | 3e9a7f77-87fd-41cb-9d9d-97df37b160e8 |  | note | Supplier Specification
label | 8e9833bf-f8f6-48c1-b55a-40ebcffb7254 |  | note | AS /NZS 3000
label | a8f77e3b-80d7-4ee5-a89c-29b06b392175 |  | note | ACCEPTANCE CRITERIA: Materials comply with relevant specifications.
label | f93bc3fc-c050-4109-b2eb-e6cad1b35c06 |  | note | Obtain conformance certificates and submit to the Nominated Authority prior inclusion into the works.
label | 8bf0dad9-aeee-45ef-a730-dddf18f7b777 |  | note | METHOD: Visual
label | 333bde63-47bb-4203-9d45-28d9a4800432 |  | note | FREQUENCY: Once
label | f1f666d7-1669-4a4c-ac87-7d7cb45c6b4a |  | note | CATEGORY: HP
label | 498cca1d-015d-4bfa-a1ea-f32cf984d2d9 |  | note | RESPONSIBILITY: Nominated Authority
label | bdeb03b5-1c59-4866-8f2c-fab3b7e8a570 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 0110244c-04d1-4ed2-b36a-c97d5c04b569 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Inspect supplied items upon delivery
label | c214d01f-9eb6-46a8-ae7a-fb25701516b0 |  | note | REFERENCE: IFC Drawing
label | ee42be96-0ecf-47be-b041-078d10662faf |  | note | Supplier Specification
label | 90dd6f31-2c25-40db-be12-128de9c17ece |  | note | AS /NZS 3000
label | fb65ab46-6c81-4db5-8f8c-42a602a2558c |  | note | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
label | 70a2581e-8679-4e7d-8e06-43736c2d966d |  | note | METHOD: Testing
label | bf3f5936-0995-41d8-95f2-6a07c2239ae8 |  | note | FREQUENCY: Once
label | 840fe781-9582-44e2-8a83-df0feacd8d2d |  | note | CATEGORY: IP
label | e1a15270-5aaa-45a1-8423-656678f2a97e |  | note | RESPONSIBILITY: Electricians Site /Project Engineer
label | 1f2b5673-ea8b-4973-b859-5585420b98ed |  | note | VERIFYING DOCUMENTS: This ITP
text | fa8d9bfb-fa5a-463b-94e9-5315e44a755f |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Excavation of Conduit Trenches & Pits
label | e82e907d-1b28-414f-aea1-dca25be897b6 |  | note | REFERENCE: AS/NZS 3000 clause 3.9
label | f8caafba-ae59-4472-bd24-d9a13c6869ea |  | note | IFC
label | a63a89ea-1859-483b-9c29-9b44d4cf403a |  | note | Drawings
label | a4542eea-bf61-4f84-9d0d-1bbff8a0dddf |  | note | ACCEPTANCE CRITERIA: Install the conduits after earthworks have been completed to subgrade level.
label | 7067ab04-d1df-481a-9b59-15b723a57110 |  | note | Installation of the conduits must be in accordance in the design dwgs.
label | ebec8b2e-ad68-4530-8a1b-a32596a13a86 |  | note | Where the conduits run beneath a road, provide a minimum cover of 500 mm from the top of the conduits to the underside of the pavement; in all other areas, provide a cover of 500 mm to finished surface level.
label | dc074582-b1af-44e1-b601-b7f61c80b88b |  | note | METHOD: Inspection
label | 95ea92c3-60a1-4b09-b97c-3a16fbc4d28c |  | note | FREQUENCY: Once
label | 08db74f1-1771-4519-ad03-6427bda3c28d |  | note | CATEGORY: IP
label | 3b082fb0-ad2f-46ea-8144-a01c30649c87 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | f808622a-62e0-4985-9e66-303ef85dc942 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4f9b9550-d4a5-48d4-95c9-ad7313a5bc15 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Sand bedding, laying and backfilling
label | 4f7e5dc3-8b11-4bd9-ba7e-470f9fbad9a0 |  | note | REFERENCE: AS/NZS 3000 clause 3.11.4.5
label | d68045dc-b75b-450e-a0e1-5b95d3798a05 |  | note | IFC
label | 0e31d6a5-678f-42cd-87a1-282d8c1f1e80 |  | note | Drawings
label | d18544e8-76a0-42f0-9c3f-8118d1b22b94 |  | note | ACCEPTANCE CRITERIA: Use a min. 50mm compacted sand for bedding if not shown on the design drawings.
label | 36a9ed5b-085d-421c-8df1-5e42c71910d6 |  | note | Lay the conduit on a straight grade and line
label | 860ed9b2-6dc4-4434-ada9-3a6e3557c23c |  | note | Compact backfill over the conduits to 100% relative compaction or depend on IFC drawing & pavement design requirements.
label | 26235877-62fa-490e-87f0-8a9e73df98de |  | note | METHOD: Inspection
label | 6d8205b5-2387-49aa-85b4-7fb0fb81fab4 |  | note | FREQUENCY: Once
label | 6a2e997d-56e0-45de-8449-58e986df1d68 |  | note | CATEGORY: IP
label | d95d95b9-bde1-4625-88ab-f0233cbca46d |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | 4ab243f0-cd8b-4027-9bda-bf640533c275 |  | note | VERIFYING DOCUMENTS: This ITP
text | dd156848-2743-4ca4-839e-8615001e8799 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Install conduits according to manufacturer’s instructions, relevant drawings and Standards
label | 753c60fe-a185-4a5a-beae-dee3f64f3c55 |  | note | REFERENCE: AS/NZS 3000 clause 3.9
label | 2602771e-64dc-4984-a503-045684ecf84d |  | note | IFC
label | 548d5fb0-6bd4-4e8f-af1b-a4b9cb20d6e8 |  | note | Drawings
label | 6cb055de-b76b-4d9c-a2cb-cc40481d33ae |  | note | ACCEPTANCE CRITERIA: The works are constructed in accordance with AS/NZS 3000 Wiring Rules and Services and the installation Rules of AS 2067.
label | e91b4b35-5b72-4a57-985d-dd426a2d483a |  | note | Conduits are joined together with solvent cement, generally in accordance with clause 4.2 of AS/NZS 2032 and all joints are water tight and free of foreign matter
label | 87c5c293-3a99-40b2-84f3-b16fbb826137 |  | note | Conduits are inline & positioned evenly
label | 228530df-c765-475e-8cdb-db01f7817830 |  | note | Location of each conduit is as per Design Drawings
label | 3b6fc993-8339-43c7-a55a-9407e28daa13 |  | note | METHOD: Inspection
label | cb00a945-4369-4974-acb8-00cb4d9445db |  | note | FREQUENCY: Once
label | 9f8cb281-e76d-4ff6-af59-38d613a3f803 |  | note | CATEGORY: IP
label | 2ae9781f-82a6-4415-916d-6c9193ffa139 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | 938236cc-d1c9-4dce-a3e0-f1956e72c8fe |  | note | VERIFYING DOCUMENTS: This ITP
text | de31940e-5363-4faa-83f9-0441b37f3258 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 IFC
label | 6409e8f2-e4dc-4d4c-ba15-9330016ea0d8 |  | note | REFERENCE: Drawings
label | 64def37a-c907-4c62-8da6-c14fb7a47632 |  | note | L1-CHE-STD-035 section 12.6
label | 92d50df1-9c5b-4a86-a0fa-6918963eef92 |  | note | Drawings
label | 052369c2-a24e-4756-a50e-eab9d8b7c697 |  | note | ACCEPTANCE CRITERIA: Compliance to IFC Drawings, Schedules & relevant specification:
label | ef0a7655-f412-4216-b39d-513b365aa4fe |  | note | Correct pit as per the IFC drawings
label | d75ac377-b088-4526-9f0a-84d726c273c2 |  | note | Soil underneath pit bedding is to be firmly packed prior to install
label | 6a95867a-1fa4-4848-a304-24222cbc3064 |  | note | Bedding according to IFC drawings to be placed
label | 76fa3220-df21-474d-bc1e-b592d14a55e8 |  | note | Pit orientation is correct
label | 2fce79f1-f678-46a8-9449-54d66bfaf916 |  | note | Lids & covers to comply with technical specification
label | f2de72c6-8bf7-4cae-af13-b03aaf060762 |  | note | METHOD: Inspection
label | da40489e-01dd-4ab2-b570-5139f4d973b5 |  | note | FREQUENCY: Once
label | d32e2cf5-b57e-4f2b-8ec7-8d1826798d05 |  | note | CATEGORY: IP
label | a658ab8d-c871-466c-ab66-c29eeaafe47e |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | e86988e0-2c3e-42b4-8d53-2fffe9fd606f |  | note | VERIFYING DOCUMENTS: This ITP
text | 4c76103c-409a-4fac-9511-012ccedab68a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Marker Tapes
label | 8b432eaf-5bbc-417b-9a2f-9e294ed9f2e7 |  | note | REFERENCE: AS/NZS 3000 clause 3.11.4.5
label | 5844e2e8-526c-4bea-99be-2b7bdb916c96 |  | note | IFC
label | 8f1751af-f64e-409f-b072-ce745b149681 |  | note | Drawings
label | 0e029b47-59e7-42fd-9a83-994a663af29e |  | note | ACCEPTANCE CRITERIA: Wiring systems installed underground shall be identified by an orange marker tape complying AS/NZS 2648.1. Positioned at approximately 50% of depth cover above wiring system or any additional mechanical protection provided that system.
label | 135b77ca-468d-4f4a-b657-e5cb27b2f1ec |  | note | METHOD: Inspection
label | 5cc4316e-6d9b-4c1d-a87e-a2662d15dd61 |  | note | FREQUENCY: Once
label | a5a41336-e05b-4ed9-9035-dd953be6d5d8 |  | note | CATEGORY: IP
label | bbeb602a-0ad4-4c22-80c3-075c7bc2850e |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | be6cf2ec-81e1-438d-8a40-a7978ce6b24e |  | note | VERIFYING DOCUMENTS: This ITP
text | 5af0fd20-5d9e-4837-8091-fd391332c640 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Install draw-in rope to all electrical conduits(if applicable)
label | 6ad1f72b-778b-41f9-9778-6dfe41891fa4 |  | note | REFERENCE: IFC
label | ad2a437c-1792-471f-ab64-142f726297f6 |  | note | Drawings
label | 5d290f58-baba-495b-b778-c129d521c809 |  | note | QA & Work method of statement
label | b31965e9-8e6a-462a-9e91-659dd3d5e20b |  | note | ACCEPTANCE CRITERIA: Polypropylene draw-in rope consisting of one continuous length of not less than 4mm dia. in all electrical conduits or specify in methodology
label | 012499f7-c1a1-493f-857a-18df2a4feb54 |  | note | METHOD: Inspection
label | 29e0d044-932f-4c71-86f5-658ee133c4ac |  | note | FREQUENCY: Once,
label | f8f08a6d-8ab9-49fd-80cc-7722d41c9310 |  | note | CATEGORY: IP
label | 6afaf2f5-6782-4b8d-aacc-e87731b014a4 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | cb26452d-cbce-4f8c-b45a-6e1ac45a9132 |  | note | VERIFYING DOCUMENTS: This ITP
text | c1a75ab7-bd45-4cf6-9355-a4ea1e67d967 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 As-built Survey (if required)
label | 11753015-98b9-48af-847c-5e5d821206c0 |  | note | REFERENCE: As Built Drawings
label | 739e919c-4d1c-43ee-a572-da890030b41a |  | note | Asset Change form
label | cb3d7507-f400-4ce7-b4a5-f553fc6cef4f |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | f230dc59-d5d3-48f2-b6eb-8b8739b4147f |  | note | Attach: Survey Report, Engineering Asset From
label | 3956d74c-799a-49ca-8547-5f6e843de6a7 |  | note | METHOD: Survey Document Review
label | 6841ba25-a15e-4b0c-a87c-4ba9f9761e0c |  | note | FREQUENCY: Per lot
label | bc1ca013-6576-44cc-8219-f96bd2a1213a |  | note | CATEGORY: IP
label | dd36f1f2-bc88-4048-8710-7bcd37fa4e93 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | d1141aa3-13a8-4198-ab6d-cf0bad25c9f8 |  | note | VERIFYING DOCUMENTS: This ITP
text | b5652f1e-8627-4d83-adf3-7dd5b5333bf9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | bc12a867-8b67-47d3-8838-0cd2b5d05a19 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a8e6f442-fc32-4e38-a629-79c5fac9dd52 |  | textbox | Name:
text | 9050063a-f40e-4d41-9150-93ed06959e81 |  | textbox | Position:
text | 6f356b89-a459-48e4-81a1-08fed03ca05e |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Supply & Installation of Guard Rail Rev 0 | itp |  |  |  | Yes | ITP-CIV-Supply & Installation of Guard Rail Rev 0 | 1642102d-9e3d-40eb-b107-6b551d277e34
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | cb93b6bb-a08a-4dd0-b28e-ac0ff6803414 |  | note | Document Title: ITP-CIV-Supply & Installation of Guard Rail
label | bef6c0de-bdca-4e80-8797-6f0e848e43ab |  | note | ITP Description: Supply & Installation of Guard Rail
label | 25a5283e-eca1-4498-aea3-f371ef0376ca |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 3469950e-33ee-4c10-bf0a-d4b0305358f0 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 8239104f-702b-4c99-8627-d2d9aaf6f45e |  | note | Revision Number: 0
label | 88cbf0f2-ded1-4d9c-bbcd-abbd2a3a686e |  | note | Revision Date: 09/062020
label | 405db14c-bb79-42d9-acc5-cf07768522ac |  | note | ITP created by: Romualdo Magpantay
label | b18f4089-b7ff-4109-bc78-f653d4546e41 |  | note | ITP approved for use by: Michelle Edgar
label | f58af8a1-5712-443b-a92d-28c359839c5d |  | note | 1.1 VicRoads Section 708 November 2018
label | c22bfd4b-2dae-4b20-9a83-8428e69edc13 |  | note | 1.2 VicRoads Section 703 April 2019
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | 2.1 Accepted Products and material confirmation
label | 664f09df-7e38-4cfc-b452-df8ccff8e0c2 |  | note | REFERENCE: VicRoads Spec.
label | 35ac2b19-b1c8-4993-b779-2a4dd9ad1c2f |  | note | Cl.708.04
label | e7677f7c-82d3-461b-baad-8f56ce87140b |  | note | ---------------------------------
label | bd135d6f-4e73-482c-a033-0a4969cd9a1d |  | note | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | 66f2393a-d2f5-469b-b997-fc8bd9284010 |  | note | Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
label | af18778b-a827-4c94-a6dc-fb8e6e88d0a5 |  | note | ---------------------------------
label | 1eb57a5f-ac7d-4c17-ac66-8893842d48b6 |  | note | METHOD: Document Review
label | 0e33f39c-b252-4222-9f91-b4f957241889 |  | note | ---------------------------------
label | 8c920a66-33bc-4aa7-98a8-1ebf043bb30b |  | note | FREQUENCY: Each member material component
label | 0b4b3006-4b39-4395-a456-f33caf849ada |  | note | ---------------------------------
label | 34f5dc88-da1f-44a7-adcc-76d53fb0d290 |  | note | CATEGORY: HP*
label | 9eb29a49-ca7e-4867-b235-28a12ec1637e |  | note | ---------------------------------
label | f070b85a-f78a-4059-a8ad-06996201d82b |  | note | RESPONSIBILITY: Nominated Authority
label | f1f5e403-6177-4a4d-9a5e-ea5f30ce6d47 |  | note | ---------------------------------
label | 75d34057-1362-42e5-b123-dc213b39b16e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4240b1df-f730-4eb0-a309-fd8a576438f8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Identification of guard fence components
label | 1ab94afa-3ca9-45d9-a414-582274b64359 |  | note | REFERENCE: VicRoads Spec.
label | 52366cbd-8b23-417b-a9be-dc091e677fa9 |  | note | Cl.708.05 (a)
label | 7a719430-a704-475d-b38a-d2995e1d4180 |  | note | ---------------------------------
label | 8d3d948a-2cc2-4a19-a384-2d9e4f8200f9 |  | note | ACCEPTANCE CRITERIA: w-beam sections, both ends of posts and all plastic components of proprietary end treatments unotrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
label | 824e06a5-5065-44c9-acc5-10dd3ff6f277 |  | note | ---------------------------------
label | f14efbff-28ff-473e-98c7-37f7bfcedc34 |  | note | METHOD: Visual
label | 2d8f193c-9937-4ee5-83c0-7c6cd0c5e69f |  | note | ---------------------------------
label | 0727e723-d985-42ab-95e9-c08d8d0a1990 |  | note | FREQUENCY: Each member material component
label | 90fe285e-91aa-48e6-bb57-79690e6f900e |  | note | ---------------------------------
label | f0af6cac-aa86-48fd-8e79-8548769ee745 |  | note | CATEGORY: IP
label | ab09f33c-e042-4d8e-b903-103d933c643b |  | note | ---------------------------------
label | 8b40806d-add1-4038-9fe7-b0d257e675f6 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e7f17db4-5f4b-4182-a09d-a014edd810d7 |  | note | ---------------------------------
label | dde2df8b-29cc-4b8f-946d-8f806b9f3477 |  | note | VERIFYING DOCUMENTS: This ITP
text | 54c84473-0753-40e4-8f0b-7bf12af354fd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Obtain and submit Material Test Certificate of Compliance for the barrier systems
label | d429e854-4910-4b41-8c16-85ca3fab710a |  | note | REFERENCE: VicRoads Spec.
label | ef0fa972-bb72-485d-a0aa-6097759a0acd |  | note | Cl.708.05(b & c)
label | 072a8690-4f1e-48f7-b3d2-0795359291f5 |  | note | AS/NZS 1594, AS1627, AS 4680
label | 6c1b0b2f-60c9-4a05-8091-a2669bf881ff |  | note | ISO/IEC 17025 a
label | 79737947-dacc-47a0-83a7-ae00de403fde |  | note | ---------------------------------
label | f3f9891b-7e0c-433b-ba11-8d264bcd7544 |  | note | ACCEPTANCE CRITERIA: W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
label | f85a2a5f-4625-4b8a-8077-38bf67bc220f |  | note | ---------------------------------
label | e85359ba-4717-466b-9ec1-aaf347d4cacd |  | note | METHOD: Document Review
label | 4ba0a63a-ac41-4a41-b6ca-349d83b7b649 |  | note | ---------------------------------
label | 71d4698e-7910-4406-9b21-590e25446960 |  | note | FREQUENCY: Min 14 days prior to commencing, 1 per 1000m of material
label | 2d678d41-d18a-4a8f-9d0e-922156164d85 |  | note | ---------------------------------
label | 7e02c901-92d5-427f-a8cf-850f62913289 |  | note | CATEGORY: HP*
label | 0963bc39-ca10-4ee2-b72b-aa524e225e86 |  | note | ---------------------------------
label | a2243320-f5ac-43bf-826c-1d85fbf55301 |  | note | RESPONSIBILITY: Nominated Authority
label | d9afb97f-4190-4b55-b46c-61fa91f2298f |  | note | ---------------------------------
label | b6a12eda-19d6-431d-aad5-22815dd0fb93 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 885703ac-3a39-47a0-b2a7-a9b48262cfa2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Verification of Protective treament/ galvanisation records
label | fd2338a2-2168-43e8-b9d3-e54426414f6e |  | note | REFERENCE: VicRoads Spec.
label | ed430ae3-3c03-48a1-a606-b7d26f9bf2e0 |  | note | Cl.708.05(d)
label | 835dec1d-c57c-4342-88e6-92231b0b61f3 |  | note | ---------------------------------
label | a2bdfd5c-3c32-4c5d-9de4-4c0069f6765d |  | note | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214
label | 6f132675-5228-44ed-b05c-8e88c2465c19 |  | note | ---------------------------------
label | 0ff9879d-e528-4f4a-bdf0-bd94dfedff29 |  | note | METHOD: Document Review
label | 0e6560ec-76f4-46b6-a533-3f5871627201 |  | note | ---------------------------------
label | eb492865-05a9-40d8-a1bb-959bf6e8119a |  | note | FREQUENCY: Min 14 days prior to commencing, 1 per 1000m of material
label | fbc114d8-927c-4581-bc49-0bf2370245e2 |  | note | ---------------------------------
label | 37c42ba0-2788-4dab-a24c-f4797a4d179d |  | note | CATEGORY: HP*
label | 4723774f-aa8f-4969-9c62-6178d69b56ea |  | note | ---------------------------------
label | a594026f-9ba9-4443-8394-6e7766314f42 |  | note | RESPONSIBILITY: Nominated Authority
label | 86567967-d7b0-4ee7-9406-3b707ef5fd4a |  | note | ---------------------------------
label | 7775fa34-f348-4171-9dc5-b5e44e61874f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | db05669d-de3c-4da8-8b6c-b24daacb7eda |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Concrete mix design
label | 2f54a3e3-9027-4015-8a26-e829b364f135 |  | note | REFERENCE: VicRoads Spec.
label | 3e95d0a6-f54d-4aff-ba75-68a6e82729d9 |  | note | Cl.703
label | ebd1643b-e284-499b-851b-005f80556daf |  | note | Cl.708.05(g)
label | ae488979-05c6-49d0-822b-12ea373015e4 |  | note | AS1379
label | ea0bf1a1-5dbb-4ce4-8ffc-effe9b4440fd |  | note | ---------------------------------
label | 2041dad9-2211-41c2-bfa9-0672297c05d4 |  | note | ACCEPTANCE CRITERIA: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
label | 9afbf3ac-0e79-4bbc-be72-8173dd95ef39 |  | note | (i) Portland cement-based concrete, N20 strength grade, or
label | 23e90b89-1973-41f8-8442-1970079b3139 |  | note | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
label | 8c279a43-7b25-4e06-a6ea-86c9f98f9ce5 |  | note | ---------------------------------
label | 5b5e568b-47a4-44f8-b7c1-39cdd61a1b7f |  | note | METHOD: Document Review
label | d746fecd-4e33-413f-b3aa-21efa94ed13a |  | note | ---------------------------------
label | d70c5037-ec0d-4eeb-b514-20df7eb90f3a |  | note | FREQUENCY: Prior to Commencing
label | ad533048-7300-47d1-9293-b13eb7270ad8 |  | note | ---------------------------------
label | 3fc8555f-a699-4557-ad87-77c3ef4172d0 |  | note | CATEGORY: IP
label | 22ff322e-a0bc-45b4-b920-2d38f56ebe8c |  | note | ---------------------------------
label | 7e113bcf-664b-4474-92ab-f672fd87eed9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1e1fdeb6-f49d-4e36-a5d3-6db77a1d2cad |  | note | ---------------------------------
label | 7e508892-c33e-46e4-8adf-bd21f51aa060 |  | note | VERIFYING DOCUMENTS: This ITP
text | 97d6cd91-0eda-4960-815a-a16a5300e755 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 8539b7fb-b808-4bcd-bdd7-94e596c4a084 |  | note | REFERENCE: Project Spec.
label | 4020a7be-6a5a-430f-a258-4a7f0e6cea3a |  | note | Cl.1190.07
label | 2ff47e26-8e4a-4923-b907-085884bd87bb |  | note | IFC Drawings
label | 84ebce4b-06d9-4706-9f07-33fc5c44049a |  | note | ---------------------------------
label | f458756d-584e-4e01-b3ed-0062235d71ab |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element.
label | 91579024-473e-4b2c-b399-d8879c49165e |  | note | Attach: Survey As-builts / Survey Report
label | 61b4b284-5cfa-4ea6-b518-db01f1188ed4 |  | note | ---------------------------------
label | 6fefa7ae-56d4-4528-9cfb-095b01c899dd |  | note | METHOD: Measure, Visual
label | 3edb77f2-61e2-4d82-8086-32df24b83625 |  | note | ---------------------------------
label | bf72a6cb-68f4-481e-8d65-60950b23a9e0 |  | note | FREQUENCY: Prior to Commencing Excavation
label | 04caceab-98aa-4cb6-9b39-10d78fea8969 |  | note | ---------------------------------
label | 3710e4a2-bd87-4823-82e5-050b1af944f8 |  | note | CATEGORY: IP
label | 9a2b3e88-56ff-4b98-b664-eb2ed1f8d48b |  | note | ---------------------------------
label | 013baa1c-8fa0-477e-bcba-c60d5030ccef |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 95bc68fa-794f-4b38-972d-6adda833684b |  | note | ---------------------------------
label | 2c85ff03-ec49-49c1-9b3f-eaf6c821fbb9 |  | note | VERIFYING DOCUMENTS: This ITP
text | e8e76f6d-294e-48fc-ae71-81198965756e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Obtain approval of location and length
label | 36d99d49-5408-4065-8d3c-105a3b9f8427 |  | note | REFERENCE: VicRoads Spec.
label | 1942d9a0-3a39-448f-9495-81184fcc9931 |  | note | Cl.708.08
label | 751832c5-e91f-4ee4-af75-22634b9e80d7 |  | note | IFC Drawings
label | 682176f8-a837-4888-9100-6c8293289381 |  | note | ---------------------------------
label | 6a984d38-381e-4514-8069-68bc60e0234d |  | note | ACCEPTANCE CRITERIA: The required location and length of all guard fence shall be confirmed with the Superintendent.
label | c4f16e82-f478-4671-87e7-d8350f81eac8 |  | note | ---------------------------------
label | 59e44ff2-8def-4e9c-a973-dd358edddc73 |  | note | METHOD: Measure, Visual
label | 9139d000-28ed-4589-806d-e977affb2944 |  | note | ---------------------------------
label | 6a1426a7-e198-4f51-a26b-902532110020 |  | note | FREQUENCY: Prior to Installation
label | 370fb5d4-8b07-4f8e-b18a-4aee92bec5ce |  | note | ---------------------------------
label | 1b517da4-04fd-4ed3-8114-3011608b2deb |  | note | CATEGORY: HP*
label | 7799a854-7ea4-4a03-8cce-910297197a4e |  | note | ---------------------------------
label | a27687fc-104e-4453-aa5f-ccf0374ea660 |  | note | RESPONSIBILITY: Nominated Authority
label | f3fbe496-acde-4ccb-b665-8d2c363df275 |  | note | ---------------------------------
label | 6c9b63a7-1cd8-4784-8eab-0eb85970d9c9 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 8f34667c-00ba-4c67-981a-885a5b5e1371 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Install posts, rails and terminations
label | 43d266f5-e073-4492-b551-45a997ea0cb2 |  | note | REFERENCE: IFC Drawings
label | 586ac785-bc75-4290-8828-63e8556c621b |  | note | VicRoads Spec.
label | a93e097b-d0db-4a6d-9a02-af579e18f808 |  | note | Cl.708 .07(a & d )
label | ce868c1f-e62d-4047-8c23-e35121aea5cf |  | note | IFC Drawings
label | edef8674-4d95-4f57-aa59-7c27cb4bc888 |  | note | ---------------------------------
label | 10d7f799-44d9-4315-8c35-b613be2ffad7 |  | note | ACCEPTANCE CRITERIA: Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | 97d4a350-e3bb-4c75-801a-afb0e1287e76 |  | note | ---------------------------------
label | 0b334649-d320-482f-9ac8-83f8cf5ad308 |  | note | METHOD: Measure, Visual
label | 78260b58-149c-45f1-aa8e-3154f417cab0 |  | note | ---------------------------------
label | 5b55f462-b1fc-449a-90ef-86e3c27d64b3 |  | note | FREQUENCY: During construction.
label | a9eacf13-4fa2-401d-9c18-ede45651cfc2 |  | note | ---------------------------------
label | 1af7e840-24ba-4eb3-85bb-424f8b78ee2b |  | note | CATEGORY: IP
label | d4d29876-4cad-4edb-bbd5-682ad286b03d |  | note | ---------------------------------
label | 4ec40d54-1f89-4475-af3d-f3bd700026c1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a95d8656-32ce-4fde-90db-8c37ac9e2fdc |  | note | ---------------------------------
label | 191ef6ed-5854-4473-aea2-79b67e61eb48 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7ebd9c01-aba3-4e58-967b-69aab861a39f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Construct crushed rock base for maintenance strip
label | ae042442-cf58-4691-99e8-48e50e892290 |  | note | REFERENCE: VicRoads Spec.
label | 27331a3e-b864-48ab-9212-2950b322aff3 |  | note | Cl.708 .11
label | 6ad3479c-9ac3-428f-a744-d03b36c1b7c5 |  | note | Cl.812
label | 1e0ad0a1-1a5d-4052-82df-1827360d9da0 |  | note | ---------------------------------
label | 97017a5b-7e0b-42f0-b67f-df9ab03c9fa4 |  | note | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
label | 519e4a2c-81cb-4b01-bade-87c61af60cda |  | note | ---------------------------------
label | 7922151f-1d36-4074-8993-98e4a51a36ca |  | note | METHOD: Measure, Visual
label | 9b8b8f5a-c288-4653-b941-a50aa317420c |  | note | ---------------------------------
label | dcbcea35-d5c7-42a9-b8f6-0981f024e2dd |  | note | FREQUENCY: During construction.
label | 14217e29-2d2e-4a29-a9d9-e6c795bdb956 |  | note | ---------------------------------
label | beed8879-8dc8-465f-8b7f-b6bccfe45334 |  | note | CATEGORY: IP
label | a6825c83-1997-4566-930c-2cf2d4d71c13 |  | note | ---------------------------------
label | 9ddc610c-bc50-4a40-b0d7-304026ab9c75 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a37ca4ad-d378-4c8c-9115-61ba1c144c16 |  | note | ---------------------------------
label | 4a6cb9c8-6294-4d7f-9962-eb6d45c946d6 |  | note | VERIFYING DOCUMENTS: This ITP
text | e0653313-473a-4fa5-a64e-e5456d3346e1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Construct concrete maintenance strip
label | a56daa7a-8912-4301-9497-d072169e29d3 |  | note | REFERENCE: VicRoads Spec.
label | 66eb0bf3-be38-4bde-9844-d8fba916def2 |  | note | Cl.708.12a
label | 83c7f96a-aeb9-4d03-a27a-cce347b3df86 |  | note | Cl.708.5g
label | 7e447915-c62c-4fcd-9cc9-2cb907fa1fce |  | note | Cl.703.11
label | 08e97734-6a88-40a2-a1ec-c73f495b743d |  | note | ---------------------------------
label | 486f7b54-39ca-499e-99d1-65b1ac5a234a |  | note | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
label | b5ff2491-c574-4062-be2d-d707085280f0 |  | note | ---------------------------------
label | d47c9b9a-cfab-4c8f-b3c4-bca0ba91bac2 |  | note | METHOD: Measure, Visual
label | 659dc0a0-9291-4915-a417-a330d0ee8797 |  | note | ---------------------------------
label | 3e430a14-95b3-4b0b-9c50-223c4f660708 |  | note | FREQUENCY: During construction.
label | aaf2411d-f6e8-402c-84da-43a9eec94c98 |  | note | ---------------------------------
label | 04bc1cf0-6c60-406d-a9d7-c05805574b11 |  | note | CATEGORY: IP
label | 04932370-7568-4c60-b64c-27071d563bab |  | note | ---------------------------------
label | 23cfb672-c506-4e6b-b1af-8370669cf566 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4453ff58-6d93-4022-8cc0-b2561442dc44 |  | note | ---------------------------------
label | 1def0acc-5e52-4d73-85da-ff1190b7dded |  | note | VERIFYING DOCUMENTS: This ITP
text | 40ef8667-5603-4df4-ae84-6a1c67dbf2fe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Curing of concrete maintenance strip
label | a7ad03cf-ab05-4188-85c7-06d356c72826 |  | note | REFERENCE: VicRoads Spec.
label | 2a74bb66-b736-4b96-9621-68d2bcea3692 |  | note | Cl.708.16
label | 5ca7fd45-2896-40d4-832c-1364537a2066 |  | note | Cl.703
label | df024125-29c9-44df-8386-d80a88fd2e17 |  | note | ---------------------------------
label | 570a9279-39b8-42fd-8b9f-c78f96906353 |  | note | ACCEPTANCE CRITERIA: Concrete shall be cured either by water curing,wet hessian,polyethlyene sheeting adequately sealed against moisture losses, curing compound or combination thereof.
label | b4574bb4-4fad-4b25-89bd-79c868db93f1 |  | note | Curing compounds to be in accordance with AS3799.
label | 620b18b9-6946-42e4-9384-d3efbba354e8 |  | note | ---------------------------------
label | 5be7850a-8d0e-4f46-bc47-ca32aa20cd95 |  | note | METHOD: Measure, Visual
label | 89b1b4f7-8caa-437b-8583-67be14ec6fdd |  | note | ---------------------------------
label | 3842fc5d-774a-4708-970c-67494d0978cc |  | note | FREQUENCY: No less than 7 days after concrete placement
label | edb04e63-5fa2-452f-b62e-e6366c30ae11 |  | note | ---------------------------------
label | efcae276-faa6-48f8-9fef-32ec503d48c8 |  | note | CATEGORY: IP
label | 8ca60abc-fa99-456a-a035-584bb28edfa0 |  | note | ---------------------------------
label | db5a1b5a-cfba-41a9-a383-da6ca7897cac |  | note | RESPONSIBILITY: SE/PE/SPE
label | 94b09d66-455b-41e2-85fc-2c1190f0e26e |  | note | ---------------------------------
label | 1bafdba8-82f2-47b5-9c26-3b3119777c21 |  | note | VERIFYING DOCUMENTS: This ITP
text | 33b6306f-9950-4c72-9840-900642335059 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | 4.1 Delineators
label | 1d8087cc-53a3-4b2d-80dd-f147eb3b361a |  | note | REFERENCE: VicRoads Spec.
label | 06cb5d0b-fb49-4c8c-ae91-8c90908f1ba0 |  | note | Cl.708.11
label | 521be77e-6e90-416b-aed7-589ddc1cf908 |  | note | Cl.703.12
label | dce5d562-3528-4be1-bf37-56ab7f520be4 |  | note | ---------------------------------
label | c19a9bf3-c59d-4a38-bf7c-1858e34981e5 |  | note | ACCEPTANCE CRITERIA: Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
label | be158b69-2c72-4ca5-b65b-73f6b2250a24 |  | note | ---------------------------------
label | 607a3834-6e64-4e89-af8e-0f99a0b97311 |  | note | METHOD: Visual, Document Review
label | a68c25ec-5cc2-41a7-9755-0b8a20d7e0f9 |  | note | ---------------------------------
label | 2330059c-1ff6-4e8d-9299-163dddc09301 |  | note | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
label | 56669472-9783-4f51-8f16-c0d392524328 |  | note | ---------------------------------
label | 25bfaf31-630e-4aad-bf74-24cd658555c6 |  | note | CATEGORY: IP
label | eb9652ee-ee72-42ab-ba3d-61820c2a3dfe |  | note | ---------------------------------
label | f5b045f7-9bdc-44dc-8642-703d9b11c860 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 11bc717c-af40-437f-be10-9202008dba61 |  | note | ---------------------------------
label | 93c07f7c-dbd8-41ad-9b02-58645c23f5bc |  | note | VERIFYING DOCUMENTS: This ITP
text | 0360fdcb-6a08-433a-b892-26ee1e07ed39 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Existing Sign & markings Reinstatement
label | e9bc1187-58ad-4d9e-93fc-cc292b5b1be6 |  | note | REFERENCE: VicRoads Spec.
label | 1aaefa20-1511-468b-a9dd-0def640929db |  | note | Cl.708.17
label | 54e37862-6eb3-435a-8cdb-cd3b7cd2d894 |  | note | IFC Drawings
label | e20e217e-043a-4981-8977-9af47a2b14a0 |  | note | ---------------------------------
label | 4f6e03a3-06c6-43e5-a246-377a73ac2ccc |  | note | ACCEPTANCE CRITERIA: The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
label | bec21cc4-026d-4331-a6f1-8a56a362d42b |  | note | ---------------------------------
label | 4348306f-b58e-4741-acc7-fe57bac9f7ec |  | note | METHOD: Document Review
label | 94bdeed4-2694-4ddb-8d40-f398b3348657 |  | note | ---------------------------------
label | 3d9e6100-4ea8-4c49-ad2f-ce67dd1b0e80 |  | note | FREQUENCY: Each element
label | dc79cca7-12e8-4581-9577-aff31c187f31 |  | note | ---------------------------------
label | eff9a4d5-fdd8-4b0e-9bb3-1877fc0d75a3 |  | note | CATEGORY: HP*
label | b324685a-14d8-49b5-9c37-78851c43d920 |  | note | ---------------------------------
label | 789ba0d5-5f11-4faf-9f9c-a6a6d16fdfe1 |  | note | RESPONSIBILITY: Nominated Authority
label | 1a3f4e50-78a0-4c67-beaf-6d79f4ce4e8c |  | note | ---------------------------------
label | b907131c-eb90-43eb-918b-9eaced909722 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b18a30f1-9ddb-454d-9868-ef1e28cece00 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Compliance Audit of Safety Barrier System Installation
label | 3b134e76-cbf1-4a3d-834f-b8ed92930890 |  | note | REFERENCE: VicRoads Spec.
label | 9a592707-1884-4a77-8e5f-7fe3257363f9 |  | note | Cl.708.10
label | b7320eb8-242e-486f-9bc4-684886a924f3 |  | note | ---------------------------------
label | 870113d2-7e79-4a90-954c-fc22b3e914c0 |  | note | ACCEPTANCE CRITERIA: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufactures installation Manual and specifiction for each end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
label | 8b1e0b98-79c6-4221-8518-cc833336fe6b |  | note | ---------------------------------
label | 84a03148-4071-4ab4-830e-e3fbaeae78f2 |  | note | METHOD: Visual, Document Review
label | 14c32c6e-37a9-40c0-9c75-671d786ba58d |  | note | ---------------------------------
label | 592d6329-e60a-4fa6-9484-e3774fe72ec8 |  | note | FREQUENCY: Each bridge beam
label | eda9abd1-28d5-4b68-b28c-fdda1b01b072 |  | note | ---------------------------------
label | 901cf460-a087-497c-a4c9-d1ece0df957c |  | note | CATEGORY: HP*
label | eeb1b6f6-a119-4a5c-9712-5ca0da7b56db |  | note | ---------------------------------
label | 57233f9a-9fa5-4c8e-a21a-4b3e64aa5500 |  | note | RESPONSIBILITY: Nominated Authority
label | 7a59c018-da00-457a-9f9c-59d14efe1264 |  | note | ---------------------------------
label | 24b61409-82fb-400d-a238-a6b285de1ae2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | bb8a0aa8-c8bf-46f3-bc67-17793e51cf74 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Survey data captured for as-built purposes
label | 11ae5bcc-bd97-49ae-8bfb-ec1945e1dcf6 |  | note | REFERENCE: IFC Drawings
label | 8bf85656-af68-4cb3-b852-de4b1eb01d80 |  | note | VicRoads Spec.
label | ad0029d8-e719-4d88-8b94-baf496cbcd45 |  | note | Cl.708
label | 7d8e8746-b124-484a-9679-785fcda7d5c6 |  | note | ---------------------------------
label | 941ea664-065a-425e-96cd-2fb69f330416 |  | note | ACCEPTANCE CRITERIA: As-built Drawings
label | c48609b5-f01e-4f87-86f0-7fba42457c64 |  | note | Tolerances as per VicRoads Specifications, Clause 708.
label | 33f25985-46ba-4ca1-9391-379c651cef2c |  | note | ---------------------------------
label | 23360799-7e9e-4443-affd-3f936c9b80a4 |  | note | METHOD: Visual Document Review
label | 037f72d4-365b-4eed-ada2-fe3663b78090 |  | note | ---------------------------------
label | ab8abde7-e67d-4673-9ecf-9fece2268ff3 |  | note | FREQUENCY: Where applicable
label | 41f3e896-6c11-4566-9eda-e1d894f9601f |  | note | ---------------------------------
label | 7fc96454-4466-4705-9d53-8d6971391aaf |  | note | CATEGORY: IP
label | f3c97c71-d75d-41b8-bc6a-7bdf253092f6 |  | note | ---------------------------------
label | 6a9cf5b1-dc50-4bbb-9073-57b40cbc2366 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 2b960e37-eec5-4301-a85e-3a20d2ba08b7 |  | note | ---------------------------------
label | 19d3635d-ff9e-446c-9c9f-d481ab664b59 |  | note | VERIFYING DOCUMENTS: This ITP
text | cc6ac47a-14b5-4a57-b3da-52253f3bf46b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Non-conformance Report (NCR) Closure
label | 2427dcf7-8488-4f69-9d01-857c4a9f7fa4 |  | note | REFERENCE: MRPA Quality Management Plan
label | 261fd618-724b-477a-81b8-f3aa84978a53 |  | note | ---------------------------------
label | 63e14932-c9dc-4a62-9d71-cd4db7ba0b92 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 907a9998-ef8a-47bf-8e72-2530a002507b |  | note | ---------------------------------
label | 5cc19204-3d64-4833-8f85-bf8c38cf4d4f |  | note | METHOD: Document Review
label | 12a3e8d0-0668-4727-959f-b2ce77cfd2e5 |  | note | ---------------------------------
label | 262a7701-c5c3-4cba-8311-33a8a7b0b8c1 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 7abc72c6-d478-49aa-bf04-0b60837aa8eb |  | note | ---------------------------------
label | 5532773a-aa3b-48e1-961a-b9fb26018675 |  | note | CATEGORY: HP*
label | b8ca3f91-11e3-41ed-96c3-b2158b082646 |  | note | ---------------------------------
label | 6539e55b-97c0-4302-9f38-88d3badecd85 |  | note | RESPONSIBILITY: Nominated Authority
label | 019de8b2-a9e9-41d7-80e4-ab67512b956f |  | note | ---------------------------------
label | 70ff4f2b-e31b-4b74-aacb-215d8bf028ff |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c28e342e-3898-4dc5-b552-f62d26fcef63 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 03814465-bf05-437c-b507-5491df3a32a3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 890db5ed-1cec-4229-81b9-68eb503e9c23 |  | textbox | Name:
text | d17be69e-d562-426d-bf9d-deaef9078385 |  | textbox | Position:
text | 62f1f9f7-9c45-495a-96e2-0f830d811521 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-Clyde Road Precast Elements (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-Clyde Road Precast Elements (Supply & Installation) Rev 0 | 230c4fe5-d744-413a-8e9b-44b80c8d0cea
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | db49b6a0-de21-4320-a257-568c98195f66 |  | note | Document Title: ITP-Clyde Road Precast elements (Supply & Installation)
label | a6a1db31-bc99-40cf-afc9-732c528a0e9a |  | note | ITP Description: Clyde Road Precast elements (Supply & Installation)
label | 8a4b5f17-5896-4061-a72b-2a408f03dcab |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | dbc964a0-9186-43fa-a633-8cdc8d36dc1d |  | note | Revision Number: 0
label | 1904802e-c356-47ad-b265-d1a572c5a098 |  | note | Revision Date: 6/01/22
label | 267d66d3-38c4-497c-86cf-105e1638eb29 |  | note | ITP created by: Justin Kreinberg
label | fd2e1bc9-bc49-486c-b373-9dc94319e9b4 |  | note | ITP approved for use by: Victor Mira
label | 0167de48-b387-424c-b298-d3195630178f |  | note | 1.1 VicRoads Section 169 July 1993
label | c19e5a51-741b-44ac-8383-ebf410e0ae99 |  | note | 1.2 VicRoads Section 610 March 2019
label | 83137f96-4f68-4b09-9586-f622c5bd5f65 |  | note | 1.3 VicRoads Section 611 November 2018
label | 9a92c5d9-8be3-4ca2-9caa-d66f01b28acf |  | note | 1.4 VicRoads Section 613 June 2017
label | 9503f445-27ae-4933-a6e8-fd846be01d31 |  | note | 1.5 VicRoads Section 620 May 2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Grout - Product Selection - Cementitious Grout
label | 07eafa26-f265-4c65-b1b4-b78e1d70b351 |  | note | REFERENCE: IFC Drawings
label | fd43b790-47a4-49b5-8587-07a938a6f9c8 |  | note | 610.28
label | 72a27215-7f26-4031-9f91-babfb3063df7 |  | note | 610.33
label | d5c3f7f9-d581-4a3b-a919-d23f87ef383f |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | b5bc9a3a-bf1b-4912-a86b-9b9d53b77349 |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | f9089db0-6ce0-4dc0-a194-58cd81bfabe5 |  | note | ii. have the required strength at 28 days as noted on the IFC drawings.
label | 1d42e1e2-ddca-43ca-ab28-688cf5952acf |  | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
text | 86d5cde7-538a-49dc-b96a-4cb7380a7037 |  | textbox | Enter: Teambinder Material Approval number
label | c6fbc19b-72b5-4327-8ea7-d2595143a911 |  | note | METHOD: Document Review
label | 8fbe27b3-cd98-43b5-a52d-a3ce57b01504 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 59dbdd7b-5aa1-4d81-869c-048f9456d5f9 |  | note | CATEGORY: IP
label | 4c6edb78-add5-4100-b75f-dd000f09e394 |  | note | RESPONSIBILITY: Nominated Authority
label | 8bccad07-1edd-4a21-b21c-c8cbcc6d0dc8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1c2227fe-d5ce-4a8b-ab9e-8770d39fa303 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Grout - Product Selection - Epoxy Grout
label | ac39fc7b-0e00-4adc-821d-8671a69dff75 |  | note | REFERENCE: IFC Drawings
label | 0f781e7a-2a99-4719-9c71-2d4d5045e056 |  | note | ACCEPTANCE CRITERIA: Details of the materials and the proportions of grout mixture shall be submitted for review. Product to be selected based on the following criteria:
label | 2fb68360-3af2-4caa-8d61-f913bde2d920 |  | note | i. have the required strength at 28 days as noted on the IFC drawings.
label | 24dbb0c2-81c3-45ea-8b9b-30a886d7e6e9 |  | note | ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
text | 096f7485-cc73-4ff8-a073-60e4b177e431 |  | textbox | Enter: Teambinder Material Approval number
label | 665eabe8-8860-48a3-ba4b-a3e7add08fe4 |  | note | METHOD: Document Review
label | 73322a7f-c9b5-4502-aab9-ae8324032280 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 28b121e8-2613-41bd-bcae-ff8c8b8f7eca |  | note | CATEGORY: IP
label | 14e9b324-7355-40c6-94bc-6502f97a8392 |  | note | RESPONSIBILITY: Nominated Authority
label | 69a03b29-f428-4010-896b-c391fdf490b6 |  | note | VERIFYING DOCUMENTS: This ITP
text | dcb51e1a-202d-48dc-a82f-3dfe0e318436 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | 3c541d17-6c6e-443c-b876-1720aa076ab3 |  | note | REFERENCE: 610.23 (d)
label | 3f9028fb-ee64-4ebf-838f-6df60904159d |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 9a80fd94-11a9-4ecc-b33e-a147fc977894 |  | note | Note: This may be the same product used for the concrete curing
text | 82dce37c-ce26-456c-ae6e-cc32d5f5120b |  | textbox | Enter: Teambinder Material Approval number
label | 7ea1d570-3397-4365-b919-ea7bbd428966 |  | note | METHOD: Document Review
label | 8802e9a0-4cd2-47e0-92c9-22ea4223319c |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 9dc63dd6-ca63-436b-9293-e78f6c8c20a5 |  | note | CATEGORY: IP
label | 488aadc7-86ca-4dd6-952e-13d2341595f8 |  | note | RESPONSIBILITY: Nominated Authority
label | 061bd454-0f51-4b9f-b911-ac26d1dec0f5 |  | note | VERIFYING DOCUMENTS: This ITP
text | d293669d-d7ff-4e48-bceb-68dae07c3cc3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | 7251fc6d-7315-4304-9a3e-96f39354253c |  | note | REFERENCE: IFC Drawings
label | 3437fed6-d697-4387-9c54-42da39a3c66e |  | note | 610.47 (a)
label | 69ac7ed0-46c3-41ae-8310-051667870edf |  | note | Table 610.474
label | a767e97e-e56e-48d5-a922-1aad5b770aee |  | note | 620.09
label | 0d40f9c1-2bdb-4cc9-a258-ec976b826f7f |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | fe1f3e58-2d02-4857-a0f2-2e721b2f8c83 |  | note | i. Certificate of Compliance / Birth Certificate
label | 0188715f-908d-40be-9be3-9491faf85248 |  | note | ii. Compressive strength test results
label | 1af26d99-a062-4b24-8537-6644291ca453 |  | note | iii. Precast Lifting Design
label | 0fbc5082-7f51-44f4-a3a5-61d73f603888 |  | note | iv. Pre-pour check sheet / ITP
label | 150809d7-674d-49ee-9240-5443903072f3 |  | note | v. Pre-stressing check sheet / ITP
label | ee0f2555-ed2b-4b11-a214-0f01fd30d525 |  | note | vi. Post-pour check sheet / ITP
label | 6ca2dadf-c832-43db-a5a6-9d4bfae5f1a4 |  | note | vii. Covermeter check record
label | 42f3744c-35dd-43fc-bbf4-902074cf1c24 |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.473
label | bac29dd8-0413-4be2-9fdd-21fcbaef80e7 |  | note | Note: Different revisions of 610 have different clause numbers
label | 9bd04afc-de3a-421f-a09f-8a50da8d944e |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
text | a2e70852-98e7-40dc-92e4-3bb10cd9792a |  | textbox | Enter: Teambinder Approval number
label | f4bb769d-1728-4071-9b4b-ada7ad2ce25f |  | note | METHOD: Document Review
label | 7b7916e1-1a95-47a9-99bd-db1e9f2d4e53 |  | note | FREQUENCY: Each element
label | 5d27fa7c-f73e-4e2b-889c-365697c4403b |  | note | CATEGORY: IP
label | 83fccdde-96e2-4709-845c-f6b177d9d359 |  | note | RESPONSIBILITY: PE/SPE
label | afdfc5bf-b53d-48e8-90ce-2ff162b69b0e |  | note | VERIFYING DOCUMENTS: This ITP
text | fea0d726-3188-4b03-8bc1-9965df4130d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Temporary Works Designs
label | e89a8228-cbbf-4b03-ade4-a581a44824fd |  | note | REFERENCE: 610.27
label | 18691156-729a-4ac4-9a89-26071b8da024 |  | note | 613.04
label | 53410085-8faf-4b88-aaff-66636e08a0b0 |  | note | 613.05
label | fdb0be2e-f977-4035-9255-6dfc29229216 |  | note | 613.16
label | bcd61939-44b1-4d58-9785-98bdfee8f4ad |  | note | ACCEPTANCE CRITERIA: All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design.
label | ee510e1a-74f0-4344-b281-260016295085 |  | note | Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority.
label | 7eb5c265-9d0e-4bf9-b97a-76a6a6e886ed |  | note | Attach: Temporary Works Design
label | 21d0d392-8fd2-47ca-be03-9a063ade2005 |  | note | Attach: Attachment A
label | 281ac242-457e-46a8-896f-2702f40a893c |  | note | Attach: Attachment B
label | ea87609e-54f7-4ca1-987e-0dd56eb854ce |  | note | METHOD: Document Review
label | 7c758d54-1bb5-484b-9698-2515b2124e5a |  | note | FREQUENCY: Where applicable, once, 5 days prior to installation
label | 58c6ad47-b5bd-4007-904a-122b88ceed54 |  | note | CATEGORY: HP
label | 72fc12b8-ea22-4db2-a571-096c11617ffe |  | note | RESPONSIBILITY: Nominated Authority
label | 5a1131d3-ec63-4656-8f71-acd38f541900 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 6dc2a3df-0699-4522-a5c9-61e8b3aa8a8b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Curing and sampling procedure (for Concrete, Grout and Mortar)
label | ba7acbb2-b76a-469b-b990-61a321aae2d4 |  | note | REFERENCE: 610.23 (a)
label | f64e446e-700f-44f9-ba47-18491358b8c8 |  | note | ACCEPTANCE CRITERIA: Curing and sampling procedure to be submitted for review to the Nominated Authority.
text | b82d1233-5d11-41e1-9387-830be82b5c5f |  | textbox | Enter: Teambinder Correspondence Approval number
label | 65b7def1-84ef-4a5c-b1e4-89d84de4fee2 |  | note | METHOD: Document Review
label | 0a0f0c9d-ef3f-4eed-87a4-b638792694c2 |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | 4aa0496e-460f-4b53-9604-aeef0b1eb5bd |  | note | CATEGORY: HP
label | c9f24980-1c3a-48f6-aaaf-96ecd3fbe1d1 |  | note | RESPONSIBILITY: Nominated Authority
label | 55d9efd6-1ec5-40e6-9d24-c210845c2a72 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 26b12d9a-2e80-45fa-8540-1497946205da |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | b373d183-cb15-4c0c-be5e-7dfc89b4def4 |  | note | REFERENCE: MRPA Quality Management Plan
label | 0f40569a-5e30-4021-a129-aa1296ceb86f |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | a625206c-6892-4b45-8d45-6724f574c89a |  | note | METHOD: Document Review
label | 8d2c9eed-7e71-46a8-b7e3-7cd2d5db1159 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 9475e38f-25dc-47fe-81ce-66fe1f7e7858 |  | note | CATEGORY: HP*
label | 5caa18e9-0eee-47d7-9885-962a45b11991 |  | note | RESPONSIBILITY: All
label | 4d94c688-8274-413b-8290-f9da59638a65 |  | note | VERIFYING DOCUMENTS: This ITP
text | 07e453ab-5c98-4e69-928e-26dedfebc922 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pre-Cast Compressive Strength
label | 3f5695e9-dab7-4013-bfe9-e88c60027099 |  | note | REFERENCE: IFC Drawings
label | 7a823ad7-c023-4233-a412-cf1689c1a00a |  | note | Compressive Strength Results
label | aff6704a-0fef-4b84-a5b1-80b791e3ed48 |  | note | ACCEPTANCE CRITERIA: Minimum required compressive strength has been achieved.
label | 39bd8345-8fd1-40ba-95c2-3a24e2a7688e |  | note | Attach: Compressive test results
label | 1cda871e-b3de-45f4-bf96-138eeca6f6ec |  | note | METHOD: Document Review
label | bd4d63b6-8bd6-46bc-9a06-c1cc25c0e65b |  | note | FREQUENCY: Each element
label | e4a83a8a-76dd-4e0b-abc7-f0138478b88d |  | note | CATEGORY: IP
label | 3d74dd36-df97-42a7-904e-f66beb554622 |  | note | RESPONSIBILITY: PE/SPE
label | b8f677e7-8607-4389-ac6a-63dd5a0b8da0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 25f5070e-84a9-4356-abfd-f16fbba122dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Survey Set-out of Precast Elements
label | a48136c5-78e8-4d97-bca6-041bc93ff255 |  | note | REFERENCE: IFC Drawings
label | 1eeee259-85c2-49da-9da5-1557fbcedc87 |  | note | 610.47 (a)
label | 9e72c520-0271-4001-b0c9-10c71b566308 |  | note | Table 610.472
label | cb76e0e5-fbeb-4cb2-89bc-47f44eb904fd |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the Table 610.473 as applicable to the element.
label | 5773ca37-2493-4bc9-b888-82915d8cbdb3 |  | note | METHOD: Measure , Visual
label | b19fa0d8-a76a-4b03-8832-ac77d4759a6f |  | note | FREQUENCY: Each element
label | 61f405c7-8c0e-4a6c-8b4d-06f10a7f4518 |  | note | CATEGORY: IP
label | a113b19d-652c-4546-a90f-e682d8105bd0 |  | note | RESPONSIBILITY: Surveyor , PE/SPE
label | e1f8a2ba-d903-409f-808a-860f8c9b1b71 |  | note | VERIFYING DOCUMENTS: This ITP
text | e6faf0f0-e55e-40ab-902d-6b4a1620660a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Galvanized Dowel
label | 19449685-ab91-4d91-a62c-b0906a0d315c |  | note | REFERENCE: IFC Drawings
label | 34a6a185-dfcf-4530-aa2f-04dcc9e0e711 |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1647
label | fb6a4e02-3d6c-4e87-8545-83f8ba1b6e63 |  | note | ACCEPTANCE CRITERIA: Rubber rings and 40mm DIA PVC conduits to be installed.
label | 0f49802a-f2a6-4896-bb67-45e4eb6f817f |  | note | Top of PVC conduit to be sealed
label | 9abc8893-ade9-4ce1-8279-dd9864050587 |  | note | METHOD: Visual
label | 9431ff5a-a156-4e9e-9edd-855b074cb805 |  | note | FREQUENCY: Each Pier Crosshead
label | addb879f-1643-431e-9fc1-0ff6fc94c483 |  | note | CATEGORY: IP
label | 0d34ae68-c6d8-4f95-9b19-9641f52a7b07 |  | note | RESPONSIBILITY: PE/SPE
label | 28980461-5a8c-45bb-aab0-bfb5884b3942 |  | note | VERIFYING DOCUMENTS: This ITP
text | 225d2a5b-29b2-4d9a-8c79-2c3edeb4cede |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Precast Handling
label | 81829621-b742-4a66-85b7-19b2854f467e |  | note | REFERENCE: 620.07
label | 36c4d272-d0e0-4cd4-a8ae-1c971b81a6c5 |  | note | Crane Lift Study
label | e04642b7-8951-4708-8a0b-9c8e406904e2 |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 7f2295e0-5709-4117-9d91-0c5dc4855143 |  | note | METHOD: Visual
label | 8310526c-d5fe-435e-a06d-bcc5f037fad3 |  | note | FREQUENCY: Each element
label | 50fb4cb0-5d27-45c9-9118-ffb72e5a662f |  | note | CATEGORY: IP
label | d6a5af53-da59-4a01-8c97-fb22e184ac16 |  | note | RESPONSIBILITY: PE/SPE
label | a62be63e-3fa2-4508-95a7-cf9990d5792c |  | note | VERIFYING DOCUMENTS: This ITP
text | 6d8b7eac-d066-4d95-b7d4-8831418cb378 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Precast Placement
label | ed449d59-f860-4f19-845f-cbe37ae355d3 |  | note | REFERENCE: IFC Drawings
label | cbc3a817-96b1-4bed-8211-78b10878b00c |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1687
label | 4f71cbae-3609-426b-bdaa-175d4e96f467 |  | note | 610.27
label | 17eeb0bc-1c1b-421e-895d-1388429c767e |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | 92b8d3d5-67df-439f-a69c-f1d416db12a7 |  | note | The nominal gap between elements is as per the IFC Drawings.
label | 056fb3f6-8989-43ca-a7af-4aafb4894092 |  | note | Longitudinal gaps: 20mm
label | 8e4288c8-5e16-40c3-8e6a-cd918cb60c6a |  | note | Transversal Gaps: 50mm
label | 2baa7219-03d9-4f5c-94c8-e530b2289df2 |  | note | METHOD: Measure , Visual
label | 20b0c1cb-5f97-4eab-ac7b-ad8fa1c1d56a |  | note | FREQUENCY: Each element
label | b25ff908-e4d5-4244-b2b8-3fa10bec0811 |  | note | CATEGORY: IP
label | 8e348cae-5c0a-4730-8ca5-8f95f247eb6d |  | note | RESPONSIBILITY: Surveyor , PE/SPE
label | dd929bb4-dc1c-468f-8fb6-f1fa41234ab2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5ab11841-d768-4b26-9988-75103e481aec |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Grout mixing and placement
label | e2924360-0d43-4773-a92b-faf28c0e5e07 |  | note | REFERENCE: IFC Drawings
label | 148f3708-b703-4006-ad28-d2b8328ec4fc |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1647
label | 265af49f-e6ec-4fad-9d75-5818c6c35e96 |  | note | Manufacturer Instruction
label | f8528059-8289-4e9d-9add-d691ea588593 |  | note | 612.18
label | d569b7b1-7246-4e09-bae1-6655bf5608eb |  | note | ACCEPTANCE CRITERIA: Grout mixed as per the manufacturer instruction. Full container to be used.
label | 7ecfc0c6-c067-4108-859f-71bce00bbf7d |  | note | Attach: Contractor Grout checklist
label | 5ba31ba5-e011-4189-92ec-d3db45628c5c |  | note | METHOD: Visual
label | 311cffb9-8bef-4107-8627-ce48bfd9e1fc |  | note | FREQUENCY: Each element
label | a9e047bb-8d9e-4b57-8758-21a939832d83 |  | note | CATEGORY: HP
label | 3cc648f7-0868-4cde-8641-e662d90349f1 |  | note | RESPONSIBILITY: Nominated Authority
label | f4a83af9-5710-4736-950d-0e24e3c227d7 |  | note | VERIFYING DOCUMENTS: This ITP
text | bb611c57-a37a-4cdc-85e6-8ade84a19915 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Falsework Certification
label | 41402681-8ae5-4c40-b599-6cfa6a064e2c |  | note | REFERENCE: 613.12
label | 679be41a-958a-4195-9048-3db8eb8c7348 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above)
label | d24bf1bd-bd49-4e77-a821-89dd906e68dd |  | note | Attach: Attachment B
label | c5337c5a-0027-486c-89f9-87173bb88455 |  | note | METHOD: Visual , Document Review
label | a68c9a12-1c54-4ad2-bee9-3ca2e3e00441 |  | note | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
label | 87b08863-9e6a-4ca7-949e-aabebb435107 |  | note | CATEGORY: HP
label | d34224e3-cef8-4c71-bee1-e93857964ce7 |  | note | RESPONSIBILITY: Nominated Authority
label | 12908f37-f92d-41c0-a12c-224e79dbb5bf |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | a743bbbb-0815-4691-a4f5-0e49b413498e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 Flowable Epoxy Grout Compressive test (Precast element slab penetrations)
label | be19ba95-405a-46d5-afa4-735a598d6501 |  | note | REFERENCE: IFC Drawings
label | d6344807-0669-4da5-9d98-b5d59e68bf43 |  | note | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2
label | c5d6217e-194f-452a-92c8-98bb821b6db7 |  | note | Complete: Grout Pour Checklist
label | 56728fc8-3760-41d6-be89-312d27b5072f |  | note | Complete: Grout Pour Record
label | a8a068d4-9b93-4045-bdbf-d7b0caf3b592 |  | note | Complete Test Results
label | 0242bd4c-1fdd-435c-a9de-04fe3228e9b0 |  | note | METHOD: Visual
label | e2417912-2a3c-4078-8795-b9b77d3904b3 |  | note | FREQUENCY: Where applicable
label | 28a2f7f7-1993-4317-b469-8592e13f1bfb |  | note | CATEGORY: HP*
label | 684d148c-e7e1-4aef-976f-68fa13067714 |  | note | RESPONSIBILITY: SE
label | dcadb480-5239-4b76-8092-bd35321ba705 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8793b743-32ae-4d4b-a941-779f9e043e9a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | 1bc23994-41fb-4483-aaad-9f2379687b08 |  | note | REFERENCE: IFC Drawings
label | 11057868-ba45-4560-853f-a37f86b07383 |  | note | 610.46 (a),
label | 34d11d79-d008-4750-8985-eeeb3c18c4ab |  | note | Table 610.462 (November 2018)
label | b81e9f26-9e0d-4abd-8780-9a044efecd49 |  | note | 610.47 (a)
label | 78a3affe-85c5-4db1-8d75-1f965903ab13 |  | note | Table 610.472 (March/June 2019)
label | 37c16dd8-fce0-4dcc-83f4-813af745de3a |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | 06ec21a8-87c9-438a-9d41-b7d7d1156f6a |  | note | Attach: Survey As-built / Survey Report
label | 23fbf208-a225-40ae-b095-85208c36c1a0 |  | note | METHOD: Document Review
label | 61a75d1f-a0a1-4c2e-8a9a-d34bf4ebcac3 |  | note | FREQUENCY: Each element
label | 0a549120-99e1-4eae-9766-c47ca5378005 |  | note | CATEGORY: IP
label | 1326679f-9284-491f-a856-e1c3cfbe2680 |  | note | RESPONSIBILITY: Surveyor , PE/SPE
label | 2b2a4e8b-183f-4394-8cc7-714812bd84de |  | note | VERIFYING DOCUMENTS: This ITP
text | 47928e7c-7243-48f5-a563-629dfafe80f5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Removal of Falsework
label | a7db2543-071d-4776-857b-68ed2611930a |  | note | REFERENCE: Temporary Works Design
label | d50f75ed-6609-48cd-83f4-c55f89b66524 |  | note | 613.16
label | accbe8b0-ea86-4538-85d8-0cd06554243c |  | note | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
label | 1fd861bb-1010-4745-b639-88c9c2a112a9 |  | note | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for and repair.
label | 1bc5cbcc-4daf-41c0-80a0-fa137a51998f |  | note | METHOD: Visual , Document Review
label | 877aa4cf-a3e8-41a6-9c50-b17c0bd0724e |  | note | FREQUENCY: Where applicable, each element
label | 2fa0f4ff-63a8-4db9-8c05-724f3d249145 |  | note | CATEGORY: IP
label | d8abd82c-8e90-4641-93a6-36dd581d9aae |  | note | RESPONSIBILITY: PE/SPE
label | fa945da6-aaca-46d6-8794-a70df5d92bba |  | note | VERIFYING DOCUMENTS: This ITP
text | 6d192ead-10e2-4019-8958-62f211df79db |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Patching works
label | dd4f89b7-5356-44a3-9edb-0199df44f794 |  | note | REFERENCE: Temporary Works Design
label | 6cb67890-5687-43d5-adb8-56c26ddbd168 |  | note | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
label | f2c3cd97-0570-4ae9-8637-7044ee481368 |  | note | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for any repair.
label | 888cb34e-2ebc-4cce-9eed-c813500182b9 |  | note | METHOD: Visual , Document Review
label | e7361b6e-dfde-4963-9964-33ca135cecdb |  | note | FREQUENCY: Where applicable, each element
label | 72179b9e-f82d-41c0-890c-db54811a60d0 |  | note | CATEGORY: IP
label | e887ec4e-6d6f-4c90-8bf6-6c99be37e53c |  | note | RESPONSIBILITY: PE/SPE
label | 2deef56a-a59b-432b-895e-6daa3df6663f |  | note | VERIFYING DOCUMENTS: This ITP
text | b8cf347e-c570-4726-b6d8-07bbc5340cf0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | 031e5506-3b28-458c-bf4e-632df14099c1 |  | note | REFERENCE: MRPA Quality Management Plan
label | d2cc1244-fd82-40ed-9564-d5e1a2442b14 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 8d2682a0-2f34-4639-b778-9b070382f777 |  | note | METHOD: Document Review
label | bf2976d5-c2dd-4be9-9a51-8a8f424a6280 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 36f6bdba-bd24-4a1d-bb0f-0ab5fd36bbd1 |  | note | CATEGORY: HP*
label | bfb95600-a058-4275-a11c-7656a63e83c8 |  | note | RESPONSIBILITY: PE/SPE
label | cf1342cd-d107-4f3c-8f9f-0dba37f44360 |  | note | VERIFYING DOCUMENTS: This ITP
text | 09d535ce-10fe-4333-be21-501e40d08058 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 5844f92f-a8a5-480a-85ac-e0441c8ea1fb |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d39d4c67-fc3b-42dc-aed1-b82556acbd8a |  | textbox | Name:
text | 0ba42a77-9d54-46bd-a373-82a7bb506606 |  | textbox | Position:
text | 348c9c43-8a50-4721-91d1-6dc8b39a93e5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-RAIL-Formation Subgrade (Supply & Install) MTM Rev 0 | itp |  |  |  | Yes | ITP-RAIL-Formation Subgrade (Supply & Install) MTM Rev 0 | 289d33d9-a4e2-48ed-86ce-91c72f97990a
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Referenced Documentation
label | 60d4ef6b-3ca1-5cfb-9e3c-4eceeebcb28e |  | note | Document Title: ITP-Rail-Formation- Subgrade(Supply and Install) MTM
label | 71a2e435-4b89-5e19-97b6-bfe4a95a499b |  | note | ITP Description: Formation- Subgrade(Supply and Install) MTM
label | 4582c24b-6bc9-59b8-958b-31e73eeb1fab |  | note | Discipline (e.g. CIV/STR/RAIL:Rail
label | 77688411-102f-5652-9dd1-ee60a518f298 |  | note | Revision Number:0
label | 4a2193b5-bde2-5fce-adea-6c8e891a3142 |  | note | Revision Date:29/06/21
label | 87bde367-14ef-5b0e-8c3b-9bfe71ce46f2 |  | note | ITP created by: Yasna Naicker
label | f768b0b1-2430-562e-9fd2-cc1f88ae2d31 |  | note | ITP approved for use by: Romualdo Magpantay
label | 97680d09-377c-5d1d-9d7e-f8bce7481baa |  | note | Reference - 1.1 Drawing Pack - Rail Track and Civil - MRP-016-C-ACD-REP-03-NWACPW-0001
label | 05f1c4d3-fb38-58d0-a34c-60cb29330c7d |  | note | Reference - 1.2 Metro Engineering Specifications - Earthworks & Formation Specification - L1-CHE-SPE-178 (VERSION 2)
label | 3ca0609e-9f05-5f4a-b3dc-149684d071fc |  | note | Reference - 1.3 Metro Engineering Specifications - Earthworks & Formation Standard - L1-CHE-STD-029 (VERSION 3)
label | 903be132-f6bb-5740-8a90-493be35afd46 |  | note | Reference - 1.4 Australian Standard - Methods of testing soils for engineering purposes - AS 1289
checkpoint-group |  |  | section | Preliminary/Material
checkpoint-status |  |  | checkpoint | 2.1 - Verification of Subgrade supply Material
label | 7359c896-9153-57ac-8848-62548b6daf35 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9.5 Table 1 AS1289 Tests 5.1.1 & 5.3.1
label | 76f7ccb4-646f-516e-811d-7c782a5db215 |  | note | ACCEPTANCE CRITERIA: Subgrade shall comply with the following criteria: Soaked CBR - 3% min nominal Plasticity Index 9-20% Dispersion (pin hole dispersity) - ND1/ND2 Dispersion (Emerson class number of soil) - not to be class 1 or 2 Collapse strain - to be agreed by MTM geotechnical engineerFree swell index - 2.5% max. Soil soluble salt content - 3% Organic content (dry weight) - 2% max. Refer to AS 1289 for Tests
label | f8e56c59-d3fd-59c3-b714-847f65205e30 |  | note | METHOD: Visual/Review Test
label | 57fbbe2a-33be-5fc3-a3d6-131ce5b47e29 |  | note | FREQUENCY: One test per 1000m³ Volume < 1000m³ at least one set of tests shall be carried out
label | 4bd2bda9-604a-55f8-8b19-43cd35ec9010 |  | note | RESPONSIBILITY: SE/PE
label | e995f09d-eef4-542e-aba0-287338ffcffa |  | note | VERIFYING DOCUMENTS: NATA Material test results Sign ITP
text | 012b8b15-8da9-522a-9ec1-ae8469ae2aa6 |  | textbox | Team Binder Approval Number
text | 0b36d68c-2471-5076-9bf6-7f2a1dd733c1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Subgrade Preparation and Installation
checkpoint-status |  |  | checkpoint | 3.1 - Survey set out
label | fa2e7a62-d477-5a43-b695-3f7674acff25 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 8.2.1a
label | d64501a3-2ee5-52ff-9271-9cf6e775d3a6 |  | note | ACCEPTANCE CRITERIA: Survey control requirements for setting out and validation of foot prints, level & slope angles
label | 43d7073f-657b-5056-a89a-3d38b32c83e6 |  | note | METHOD: Visual and Measure
label | a0844ba1-94e8-52da-878a-710dfd6f9ea7 |  | note | FREQUENCY: Prior to Commencement Each lot
label | 68968343-4546-5554-8881-3a0bb568fb18 |  | note | CATEGORY: IP/SP
label | 89d1fbc5-b40c-5805-995c-97cba0703a29 |  | note | RESPONSIBILITY: Surveyor and SE
label | 53425e3a-ec15-5fa6-897c-1f687332714b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | fd42c6d5-aece-5228-8e51-9473a92e7e95 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.2 - Place and spread the Subgrade Material For track constructed on embankment
label | 31d6fb7a-9791-5a6c-ad77-ad6695efc06f |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9 L1-CHE-STD-029 - Clause 12
label | 45dab005-db80-5969-bffd-6b7f7e0aa8cb |  | note | ACCEPTANCE CRITERIA: Assessment of underlying layer If min CBR < 3%: Install min 1m structural fill If general fill is to be placed directly over subgrade: Subgrade to be compacted to 98% If structural fill is to be placed directly over subgrade: Subgrade shall be scarified to 200mm and re-compacted to 100%
label | b3c195d0-533d-592b-8f7c-25e03c037992 |  | note | METHOD: Visual and Review Test
label | 695a8877-d54e-5107-a44d-3200b3c05572 |  | note | FREQUENCY: Each Lot
label | 884912ce-cde1-5423-8f21-60294f3bc711 |  | note | RESPONSIBILITY: SE
label | d4f40253-0aa0-53e7-a502-984fc3c08ff3 |  | note | VERIFYING DOCUMENTS: Sign ITP Compaction test
text | 1e16b39b-2922-5bc8-ad3b-f538a08ba7c6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.3 - Place and spread the Subgrade Material For track constructed on embankment
label | fa7c0f98-04aa-518b-ad44-de7f259c000a |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9 L1-CHE-STD-029 - Clause 12
label | 832bd9d8-3608-545b-9440-1a1cbaad3240 |  | note | ACCEPTANCE CRITERIA: CBR Assessment of underlaying layer If min 3%< CBR < 8%: If general fill is to be placed directly over subgrade Subgrade to be compacted to 98% (Standard Compaction Test) If structural fill is to be placed directly over subgrade Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
label | df88b440-bef9-5a5c-ae27-ee3dc2a74f40 |  | note | METHOD: Visual and Review Test
label | 3095e2c6-4e06-5d63-8193-cca23150a99f |  | note | FREQUENCY: Each Lot
label | 2714b087-c555-53cb-8477-2b72ec13adea |  | note | RESPONSIBILITY: SE/Nominated Authority
label | a2e98a18-5be8-5ae8-b9f8-ab43b40a46d9 |  | note | VERIFYING DOCUMENTS: Sign ITP and Compaction test
text | 85b6b0a1-082f-54d5-8b34-50579b0600cc |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.4 - Place and spread the Subgrade Material For track constructed on embankment
label | ffa7d348-f26e-575b-990e-41297a33f1ec |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9 L1-CHE-STD-029 - Clause 12
label | 7021f854-7c95-55e7-902b-848af4edc034 |  | note | ACCEPTANCE CRITERIA: Assessment of underlaying layer If min CBR > 8% Excavation can be stopped to suit capping layer or at top of section with CBR > 8% Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
label | c8c59799-7c18-58e3-8e8a-ee900406017c |  | note | METHOD: Visual and Review Test
label | 51613412-cbf9-54ee-9f5d-b30055c11fd6 |  | note | FREQUENCY: Each Lot
label | 8e2ec758-357b-54fd-8bbc-b6038d0950e9 |  | note | RESPONSIBILITY: SE
label | 2b9d3d7a-a66b-52a4-acd7-8fbfce491043 |  | note | VERIFYING DOCUMENTS: Sign ITP Compaction test
text | 21d44b26-ead1-5b0b-a5e9-b9a84175043d |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | 3.5 - Confirmation of material compaction & strength by Proof rolling
label | 95fdcb2d-17f4-5c5f-8cf1-1e46bae83e81 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9.4.1.a and Clause 8.6
label | 20f7776a-09ba-5db0-8689-798e17dbd3cf |  | note | ACCEPTANCE CRITERIA: Proof roll as per L1-CHE-SPE-178 - Clause 8.6 To confirm the material compaction and strength have been achieved. Earth works layers shall be compacted so they are capable of withstanding proof rolling. Unstable areas detected shall be remove, reworked and and or /improved as agreed by approved representative.
label | f0175259-6f7d-541b-8d82-f6775c5cdc24 |  | note | METHOD: Proof roll
label | dea0621b-6f5a-5f99-adae-98df97323a88 |  | note | FREQUENCY: Each Lot
label | 36fd7ff6-de7d-5ab8-8be5-809d0a8bd61f |  | note | RESPONSIBILITY: SE
label | 5bc52ed5-8d6d-59f3-bca6-dfeb4533484c |  | note | VERIFYING DOCUMENTS: MTM / NA representative signoff
text | ad644b08-dbea-51a1-8e30-2315b182250d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 - Onsite Compaction Testing to specified densities
label | 70fcf7ed-0678-537a-a834-98ea9cd26b8b |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.2.5 AS 1289
label | fe428000-c689-510a-a98c-4076a2bf51d8 |  | note | ACCEPTANCE CRITERIA: Minimum Characteristic Value of Density Ratio of 98% when assessed using a Standard Compactive effort.
label | 42c1927d-6bf9-593e-96ea-71746df98726 |  | note | METHOD: Review Test
label | c90748a5-6de8-5526-a927-97d6a3d64de0 |  | note | FREQUENCY: Each Lot
label | 5a93f9c4-fbd8-5e81-901b-b98672f181a1 |  | note | RESPONSIBILITY: SE
label | 1f0369c1-1a55-5a74-aa86-756d410885cf |  | note | VERIFYING DOCUMENTS: Sign ITP/Compaction test
text | ff0db8c9-2626-52ff-8c1a-370ee62a8e86 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Subgrade Finishing and Tolerances
checkpoint-status |  |  | checkpoint | 4.1 - Survey Conformance report/As-built Survey
label | 612d5769-fab2-502f-ac6b-46b09524c322 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9
label | d798749e-b9ab-59f2-bf6e-809d224bcfa2 |  | note | ACCEPTANCE CRITERIA: Subgrade on embankments shall be installed within +/- 40mm of approved design surface level The width and slopes shall be no less than the dimensions specified in the approved design( negative tolerances ar not permitted)
label | a87dcfe3-a98c-575c-b939-52f9a0342ee1 |  | note | METHOD: Document Review
label | 2016e0b6-2b05-544c-b232-d0843fc75f23 |  | note | FREQUENCY: Each Lot
label | c6667196-8766-5540-a6c7-9bed126e8b84 |  | note | CATEGORY: IP
label | d839cc42-9f61-5143-ad74-d6977d0de086 |  | note | RESPONSIBILITY: SE/Surveyor
label | 795184d2-64bf-5195-a52f-95265ad84e24 |  | note | VERIFYING DOCUMENTS: Survey conformance report
text | 75a9ecfd-b3bc-56a1-9e5d-c4ce4d89885a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Non-conformance Report (NCR) Closure
label | 1899ac05-35e7-5595-932d-c201a5e8c1c6 |  | note | REFERENCE: MRPA Quality Management Plan
label | 4ac1cc2c-350c-5b7f-9720-d1a8db520ad7 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 2a912c4b-1354-56d2-ab0d-2543a77fcc27 |  | note | METHOD: Document Review
label | d0ed11fd-f3aa-59bd-b247-e4faca8f329f |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 559ef034-dad5-5da5-b261-1dc615875ff5 |  | note | CATEGORY: HP*
label | 1f837d64-3492-5662-b62c-1d915727107b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 80b30f52-6198-56d7-8cc4-0d94ca50b4cb |  | note | VERIFYING DOCUMENTS: This ITP
text | 3ada8968-de60-5742-a804-770188f7cdb5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLD POINT SIGN OFF
checkpoint-status |  |  | checkpoint | Final Inspection
label | 11e76939-ba1f-5f0c-8dba-07f868241599 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | cab697f6-2a45-534b-a7b0-c7cfec8667f6 |  | textbox | Print Name:
text | 76d7778f-73be-5fc8-b093-055b58a0c040 |  | textbox | Position:
text | 77d7d9b3-ee0a-508b-bd24-902e44005a21 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-CIV-Pit and Conduit - CSR (Supply and Install) Rev 1 | itp |  |  |  | Yes | ITP-CIV-Pit and Conduit - CSR (Supply and Install) Rev 1 | 2a3904ac-4bf9-4292-b249-047404f86cd1
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 590cd48c-a00f-4685-8a15-8d6a5022dfc6 |  | note | Document Title: ITP-CIV Pit and Conduit - CSR (Supply and Install)
label | 2911c05a-41fa-417e-b391-36e2146fb622 |  | note | ITP Description:
label | edcb649c-c284-472c-87e4-849cf6e70f82 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 7af6884b-d8f2-442b-ac60-3073807e416c |  | note | Revision Number: 1
label | dc39d991-fd63-482b-a3ac-207c374f7f0b |  | note | Revision Date: 7/04/2020
label | 509c6cec-965c-47d7-b397-8328b82b9825 |  | note | ITP created by: Thomas Hudson
label | fa3ab906-db4a-414c-80a5-2962ab3a5852 |  | note | ITP approved for use by: Josie Pavlou
label | a70579b8-f6a6-48cf-b7f1-753339692487 |  | note | 1.1 IFC Drawings
label | f0bc1367-d9b0-4172-8bac-b5871f6ca1d8 |  | note | L1-CHE-STD-043 (VRIOGS 012.2.1)
label | f995cd70-2d09-4515-be40-6ac28028ef04 |  | note | L1-CHE-SPE-070
label | 66081945-7ffd-4f0a-b3f9-7924d36e0181 |  | note | Australian Standards
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Conduits
label | 66a6e93f-b058-49e7-99be-884bd154da1f |  | note | REFERENCE: HV Conduit: AS 2053
label | 5fb4c8e4-3886-4ef6-9497-3fa27a1ad23d |  | note | HV Conduit (boring): AS 4130
label | b0d5ef88-8b33-4331-899f-4aaf3368d44e |  | note | Comms Conduit: AS/ACIF S008:2006
label | ecd15509-56d7-4ff9-a862-1167214c9329 |  | note | LV Conduit: AS/
label | 4ebfe7ec-3a91-4658-a459-05d83633893c |  | note | NZS 3000 - 2000.
label | 7a4da787-a0a5-40a6-92a6-aa54d85aa0ca |  | note | L1-CHE-STD-043
label | 76fb15bd-b2b7-43a7-a1f3-ac91d22ce104 |  | note | L1-CHE-SPE-070
label | d074e907-6062-4be6-8cf0-b3947e8560b1 |  | note | ---------------------------------
label | d996d005-fad7-414a-923b-299b6bc69be6 |  | note | ACCEPTANCE CRITERIA: 22kV Conduits: 150Ø (160mm OD), orange electrical heavy duty 8.8mm wall thickness, greater than 1.65x cable diameter for single cable
label | ad595808-433f-48b5-9d24-d2878d146f22 |  | note | Comms Conduits: 100Ø (114mm OD), PVC White comms conduit 4.6mm wall thickness
label | 19cba730-d9f3-424b-997e-c56db1ac95be |  | note | LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | be1ac960-0402-4250-98e1-6c15c5242968 |  | note | LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
label | dac0603f-d048-42c1-b885-ff1fedefef42 |  | note | HV CONDUITS TO HAVE A MIN 2000mm BENDING RADIUS
label | 143866b0-f917-4406-acfa-4d891379cf35 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 5a6c3c69-5ea9-4a20-ad5b-b764f033f1df |  | note | ---------------------------------
label | 00282289-2e3e-4fec-aeb1-7a1acb7bc710 |  | note | METHOD: Document Review
label | 48896eb2-1334-4e05-9d06-954ad6e75b73 |  | note | ---------------------------------
label | 58a21c0d-9892-456f-9789-1c9f8a8d0beb |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 7c1a7458-e78a-4979-be6f-e60b57e974b8 |  | note | ---------------------------------
label | cf3fc0f4-eb3a-4a6c-bd85-b0cdb27618ab |  | note | CATEGORY: IP
label | 48ab0f31-e101-44c3-92aa-84cdaa2701ac |  | note | ---------------------------------
label | df5c6212-a38c-4928-8cbb-629090ab5ee8 |  | note | RESPONSIBILITY: SE/PE
label | d150939d-d76d-4057-9112-e45767b0326b |  | note | ---------------------------------
label | a2c61d32-452c-435f-bcf5-f5fdc1b430a8 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets
text | 089f2ce2-16a1-41a7-8a1b-9676f15ee37e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Pits and Pit Lids
label | 4e1c9bee-0009-4c10-8ff7-52ccef34b8ba |  | note | REFERENCE: IFC Drawings
label | fc6e7793-7dcd-4fa7-8c25-910941ede0fb |  | note | VRIOGS
label | b5ac22a2-013b-4dff-8459-90bcd6b26f01 |  | note | 012.2.1 Section
label | f0fbe51c-1f5c-484d-9c30-0f14061a4254 |  | note | 6.15-16
label | 71afcfd9-7fc8-4eae-8887-43759f90a1d9 |  | note | VRIOGS 012.2.1 Section 6.9
label | 4228d24a-c024-40b5-ae6f-d1d96f64e6da |  | note | VRIOGS 012.2.1 Cl.
label | 9d42e41a-2044-4945-b82e-d501ab12c3ac |  | note | 6.7 (c)
label | e9ff849e-cef5-4ab9-b19e-20d93f39dae4 |  | note | L1-CHE-SPE-070 Cl.
label | e51c5b13-bc89-4ba3-b8cf-119492d7de2c |  | note | 10
label | 74ce22f4-9727-456b-b9d0-7af9ebfc30c8 |  | note | ---------------------------------
label | f358ed21-73e7-402b-9ba7-cf599009b29f |  | note | ACCEPTANCE CRITERIA: Pits:
label | 5ea1ead3-83fb-42ff-b885-28e5606b08cc |  | note | LV & COMMS CONCRETE PITS SHALL BE 600 x 600 x 1000D WITH CLASS D TRAFFICABLE LIDS
label | dc1f9c9c-03a4-48ad-81b9-d4507245211e |  | note | Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
label | 34c64439-a4ae-4092-bf4d-3ae136ead67c |  | note | Pits 900x900mm or greater, multipart pits lids to be used.
label | e4e95848-5865-41a3-9ecb-4aecb8d345d9 |  | note | Concrete Pits to be made as per AS 3600
label | aa2590dd-1411-4665-ac68-c458771f1986 |  | note | Pit Lids:
label | 9c595dcb-ffe3-4a73-9a45-a7cf2b9393fd |  | note | Pit Covers shall comply with AS3996-2006
label | e9177b0b-3b38-4700-9eff-cc4e86f5629c |  | note | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | e71dc6d2-6bd2-4e7b-9dc1-5124f576c4d5 |  | note | HV Pit Cover: pit covers shall be labelled with the words “DANGER - Railway High Voltage” (L1-CHE-SPE-070 13.4)
label | 1a10838f-66cb-497a-bd5a-273583a58ee6 |  | note | LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | 0ddf805b-8bc7-454d-8f33-9e69f4f88afe |  | note | Inspect materials upon delivery and attached delivery dockets.
label | a7e19aa5-d654-40d8-bdac-97adbf6f2485 |  | note | ---------------------------------
label | 8183dd12-fb59-436c-a087-bb78e4a0fcb1 |  | note | METHOD: Document Review
label | c54082a5-cb0f-47a1-a104-7504cfada21f |  | note | ---------------------------------
label | c29aebd7-6f9b-4dbb-96e5-35093cf663cd |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 46759666-1f6d-4586-acf3-21c62057a6e7 |  | note | ---------------------------------
label | 5f16cb87-aec5-49cb-9cf8-a4470083f4d3 |  | note | CATEGORY: IP
label | 15a088e1-8359-45e3-b1cd-714cabf84172 |  | note | ---------------------------------
label | c618373d-9ef1-4c76-9cc3-81e9ab9b5533 |  | note | RESPONSIBILITY: SE/PE
label | 77719181-d769-4f12-a373-ba31cbd6aaba |  | note | ---------------------------------
label | da06faf3-1875-4a9f-8004-1039c9785fb0 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets Attach Precast Birth Cert
text | e3993774-5f8e-4488-9fae-d69b3af46673 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Warning/Marker Tape
label | 018bea9a-2689-4205-8b0d-f8923e40c243 |  | note | REFERENCE: IFC Drawings
label | 025963b1-7ffd-402e-abec-710da5ea96df |  | note | AS/NZ 2648.1
label | cf14ce56-078b-4123-befc-a72d50a652c1 |  | note | TS-SP-013
label | a73908bf-c093-4a82-b904-41ef956a6642 |  | note | L1-CHE-STD-043 6.4
label | b2fe80bc-e4b0-4640-b53e-7790b52d6f6b |  | note | ---------------------------------
label | 95f3deea-fe6b-4e1a-8046-afacf6c18b37 |  | note | ACCEPTANCE CRITERIA: Warning/Marker Tape:
label | 111ab35b-80d3-4a41-ad76-f5f51eec223f |  | note | Above LV:
label | e7e118ef-376c-4d36-b38c-c99d00ca69ca |  | note | 150mm minimum wide orange coloured PVC
label | 0ca9a63f-1096-4b75-842f-b088f4eeacf7 |  | note | ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 7016b444-bf0f-4466-968a-1200dfb980a4 |  | note | Above Comms:
label | f1e8b25a-e413-4af3-b424-277b95ac482c |  | note | 75mm minimum wide white coloured PVC
label | 9939a14c-bcfd-4835-b9e3-7fb28370a219 |  | note | ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
label | 47b25941-4468-4b2e-93dc-34ea22f97c8a |  | note | Above HV:
label | 30fe123a-609f-4ac1-9130-4cc6ffe47118 |  | note | 300mm minimum width orange coloured PVC 'Danger - Electrical Cable Below'
label | a3774f79-932d-4b9a-b0d5-e6431eef53de |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 98b90b86-b5c7-44db-8289-e9c9b3926c3b |  | note | ---------------------------------
label | f9ed3d6a-0fa3-4727-a977-f8a6802e4118 |  | note | METHOD: Document Review
label | a613b317-d25d-4d13-9f34-d629e7980db6 |  | note | ---------------------------------
label | c036989f-6b03-4632-b7dc-995018576526 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | bb229ebe-6cc1-407a-afce-c16fbf54f5ac |  | note | ---------------------------------
label | 037376b4-b83c-4ddc-bed4-3324334315be |  | note | CATEGORY: IP
label | eb6f4c3c-7e2b-4ec5-8b44-28438f2cfa08 |  | note | ---------------------------------
label | 0315e6c0-419f-4197-8811-032e68a59856 |  | note | RESPONSIBILITY: SE/PE
label | 5f6480a6-5a65-4a37-ac74-787cffc27f57 |  | note | ---------------------------------
label | 5627adc5-f531-44c5-bffe-0a7313d9facd |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets
text | 4eb0712a-2814-4e85-b055-58a72b4417fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Protection Barriers
label | 0a6d413f-59e1-4ba0-8bd3-70df6289c8c5 |  | note | REFERENCE: IFC Drawings
label | 6ce75b0f-de17-442f-af5d-09d10ac01c24 |  | note | L1-CHE-STD-070 10.3.3
label | 79b21828-7974-40b5-9b8d-d88a3b78cd46 |  | note | AS4702
label | 80d5f19e-04c8-4b81-893e-13505ff91a60 |  | note | ---------------------------------
label | 541fbc4f-088d-4e8d-9fc3-8d5ada248629 |  | note | ACCEPTANCE CRITERIA: Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
label | 16644ab5-0137-4d34-8475-e35553d3347b |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 75f2cbe7-a98e-4abc-885b-aea4e36f5c3e |  | note | ---------------------------------
label | f61b59c3-9041-4f6f-b609-f752973b4f2e |  | note | METHOD: Document Review
label | 23547675-a18b-4c9c-a1c5-21f1d018bbd9 |  | note | ---------------------------------
label | f5f63737-1a40-46f4-a31c-f26dd9e3c94c |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 9416e636-91e4-4b2b-9b62-c7e86ffc191f |  | note | ---------------------------------
label | 3a039ec7-3e2e-4d7b-96ab-00297d6f86f2 |  | note | CATEGORY: IP
label | ae4aadd8-ed7a-4069-be14-754dfc191b5e |  | note | ---------------------------------
label | e5bf5472-4084-454c-9a50-b4faabd9433d |  | note | RESPONSIBILITY: SE/PE
label | 8c868196-edb5-405e-9440-fed1461ea167 |  | note | ---------------------------------
label | 9f8dd984-9d4e-45ec-b052-0c74906e50e0 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets
text | e0d8a857-16a3-46c6-bbd5-efa2b032090e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Backfill Material
label | 14158f9f-2d97-436f-95ab-c9a576f1a103 |  | note | REFERENCE: IFC Drawings
label | b2f63eb4-2189-460d-9d66-3f4e646776a8 |  | note | L1-CHE-STD-043 Section 2 Table 1
label | c67b3172-8195-4796-b460-f511e7d5a40d |  | note | ---------------------------------
label | a7ad3fd4-b93a-4169-893f-b95762205fad |  | note | ACCEPTANCE CRITERIA: Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could damage the conduits.
label | 174453b3-0340-4c62-a6f2-1cc24a2d7880 |  | note | Inspect backfill material.
label | 4eca26b3-a2a6-497c-a4c8-182301a17609 |  | note | Attached delivery dockets (if applicable).
label | 65b9de2b-3544-4778-a8cb-6af05a2d0490 |  | note | ---------------------------------
label | 76a48565-ea1a-4634-b7af-485d947a08a8 |  | note | METHOD: Document Review
label | d35ad7d7-15dc-4547-a20d-6c7df4a65cbd |  | note | ---------------------------------
label | b9e6ca80-1627-42f8-9a78-5ea7f98cb90c |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 3fd77db0-bd8f-4e73-9550-5f0d49d21d4c |  | note | ---------------------------------
label | 6b0357dc-f468-493d-b35d-56252cdf3e48 |  | note | CATEGORY: IP
label | 9b85436e-e508-4e29-bc53-78e4a4f6d1f4 |  | note | ---------------------------------
label | d3216d52-b39b-40ec-a1dd-a06921e1d589 |  | note | RESPONSIBILITY: SE/PE
label | f437f086-1de8-4cf9-b362-997456d18da6 |  | note | ---------------------------------
label | be3a5190-314c-4668-aefb-b313854fc768 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets (if applicable)
text | f882a09f-64c2-48a8-866a-2938a8340409 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Bedding Sand
label | adda4aa3-2534-4a2f-af61-b83487a2c552 |  | note | REFERENCE: IFC Drawings
label | 1b7f3845-ac73-4d3e-8154-33445dee1051 |  | note | AS2758.1
label | b951ed34-fe25-4916-bdd4-af64cc3bd091 |  | note | ---------------------------------
label | 943f5855-9f9c-4cb7-8be9-dfa67d1c1353 |  | note | ACCEPTANCE CRITERIA: Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
label | ec3fcb02-7dc6-49ee-ad31-ea8fb60e7987 |  | note | ---------------------------------
label | 41e2e1c2-1750-44b2-b015-c94529aab553 |  | note | METHOD: Document Review
label | 03340c42-97d9-4a6a-a02a-e9f4aa43bb5e |  | note | ---------------------------------
label | 095a9f14-371e-47ab-ac59-5de1781a7a3e |  | note | FREQUENCY: Each Material Type, Each Delivery
label | a062548c-cc88-412f-8a63-21b82737a590 |  | note | ---------------------------------
label | 26a4b5d1-b45d-4a29-9f99-261cc131aa47 |  | note | CATEGORY: IP
label | 9bc2d096-51a0-4d41-9d37-68d714902491 |  | note | ---------------------------------
label | 9efce7d3-2ce4-4cb8-994c-378133675aae |  | note | RESPONSIBILITY: SE/PE
label | 8914faa8-66fe-4a9f-89e0-2d59538639a8 |  | note | ---------------------------------
label | ce9e698b-1282-4f48-a4e0-b1293f808c11 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets
text | f2d956c0-3591-4fa7-9028-a8263de431c2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Draw Wirer
label | 96ed9692-2c69-4e98-bf91-09e82ac8698c |  | note | REFERENCE: TS-SP-013
label | c5578ee8-8a3a-40df-83f7-7d129784714b |  | note | AS 4142
label | f3055e3e-3a31-46a9-bddb-63f5773217a2 |  | note | ---------------------------------
label | 0138524c-f1e4-4d2d-9e69-972e6f5c8fe3 |  | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
label | 04ee3a20-3a31-40aa-b837-fb5da681c306 |  | note | ---------------------------------
label | f9e6f8ab-dde9-4a12-a81b-fe705a5832aa |  | note | METHOD: Document Review
label | 487e53ef-ccf7-44fe-9873-3a2cf26cce56 |  | note | ---------------------------------
label | 33b51fad-9caf-48a8-9874-ee7bd4372db3 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 00555cb3-a8a9-461f-a3c2-9fba7f1bc3fd |  | note | ---------------------------------
label | 1c46f497-b6c0-4b40-ad5d-197af48ae63a |  | note | CATEGORY: IP
label | 183cfd8a-50f4-42d4-b0c5-6e238f46e61b |  | note | ---------------------------------
label | fa2ba814-6c4a-4805-bac7-99917ae60018 |  | note | RESPONSIBILITY: SE/PE
label | 562edd8b-30ec-42d6-95d7-7a195871c434 |  | note | ---------------------------------
label | e935d59d-63a5-45f3-918f-31ff8227fef7 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets
text | 0b78defd-e000-4430-86e3-f13eb18b064e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Concrete Mix - Trench
label | 2dd77bd1-4dea-4599-aa3c-8018cf9a9631 |  | note | REFERENCE: L1-CHE-STD-043
label | c3617e83-57fa-468a-9837-f23ee9c60362 |  | note | ---------------------------------
label | 8305ca08-7929-42f1-bed0-8272b7427fe7 |  | note | ACCEPTANCE CRITERIA: Concrete strength at 28 days shall be not less than 25MPa.
label | 1f6efa4f-8a2a-483f-ba75-739a1aa46fec |  | note | Chemical admixtures or fly ash shall not be used
label | 86faa0e7-8e60-4b6f-9b7d-1ae414b7dea3 |  | note | ---------------------------------
label | 0bfad4ef-5418-478f-8435-121d7f00d13c |  | note | METHOD: Document Review
label | bcbc2f31-4b5c-4b94-ac3a-6e5f03464b62 |  | note | ---------------------------------
label | 957c8472-1df9-43be-9177-1dfd42b62fda |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 8dbcce21-5a4b-4177-986c-1715fe884d5b |  | note | ---------------------------------
label | 5147a8b6-d28d-4314-a894-3174d41fd6a1 |  | note | CATEGORY: IP
label | 82352740-ec04-43ee-918f-d49eb073054e |  | note | ---------------------------------
label | e74b7c9b-df3c-4a57-8150-4549ea5a91c3 |  | note | RESPONSIBILITY: SE/PE
label | 1b8fbb5a-5cdd-49f2-8067-6f0107dec0dd |  | note | ---------------------------------
label | e0eb4c0d-d0b8-4b49-ac97-ad99bdeffb44 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets
text | 67b3fd9e-c4b2-407e-b83f-5c248ed101ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Markers and Marker Posts
label | 606f4f6f-a548-4ae1-afe5-22ece4336792 |  | note | REFERENCE: L1-CHE-STD-043 13.2
label | 7aee7f0e-da65-4849-86b4-82b047410761 |  | note | AS 4799
label | 8222116a-890f-4fb0-8fc2-535c6a13443d |  | note | ---------------------------------
label | 0b2eefe8-0dc3-4176-97b9-291d21f9c810 |  | note | ACCEPTANCE CRITERIA: Markers and Marker Posts are to be manufactured in accordance with AS4799.
label | 9083affd-c66f-4377-a705-108772fdff00 |  | note | ---------------------------------
label | 938ba215-d449-414e-8057-24011f0f4594 |  | note | METHOD: Document Review
label | 9ed6525f-e325-419f-b5e1-4865465d1581 |  | note | ---------------------------------
label | e83b39c6-bed0-4529-926d-4345b4c249a1 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | e501e50d-e3c6-45b9-ab41-4d3b6f43729b |  | note | ---------------------------------
label | 8c25388a-56a6-40c1-9617-5613e761a401 |  | note | CATEGORY: IP
label | 6c2ebfd3-198c-4259-ba00-c7a13dfcb378 |  | note | ---------------------------------
label | 6b1f93cc-ff0a-4c6e-87db-4e42c24cf7dd |  | note | RESPONSIBILITY: SE/PE
label | 3bcf046f-5de8-41af-8236-8f18a03e85b4 |  | note | ---------------------------------
label | d4ed6e14-8e7b-490a-9695-93a173e6cad8 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets
text | a1af4068-53e6-427b-9168-9790ac99329c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 740c6a72-461a-4cd2-9019-79b00cff3904 |  | note | REFERENCE: IFC Drawings
label | 3eb9db23-5bb0-4cac-9616-9f6474d3fb1d |  | note | ---------------------------------
label | a838291c-be2d-47dc-9148-71c02159c2cb |  | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | b8fcfbf5-3b0f-4d7b-ace2-da8035a0e335 |  | note | ---------------------------------
label | a9ad05b9-9642-4ae4-b59c-6955ad1f1d9d |  | note | METHOD: Measure Visual
label | cd433f54-8c74-465e-b023-78aff3ff201e |  | note | ---------------------------------
label | bc575fba-c1c3-4465-b84a-e240f5ac9767 |  | note | FREQUENCY: Each element
label | f4fa0d01-e5cd-4f43-a7a4-0397bea9cef4 |  | note | ---------------------------------
label | 8781ce18-b910-406a-8175-bd328190e7bb |  | note | CATEGORY: IP
label | 622a1efc-cb3e-4d26-b084-7e69c0d24cc6 |  | note | ---------------------------------
label | 624b7fd2-043f-46d8-9159-d488087e2c54 |  | note | RESPONSIBILITY: Surveyor SE/Site Supervisor
label | 7709342b-1c49-4b7d-ac72-7d9da2f94a39 |  | note | ---------------------------------
label | 9df9f901-4a82-4b52-9a46-3a55f339a2eb |  | note | VERIFYING DOCUMENTS: This ITP
text | a0626667-0b25-4c74-9c0f-0f2cdcf63e07 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Permits
checkpoint-status |  |  | checkpoint | 4.1 Services
label | 7b8d7396-b1b0-4b12-acf0-666ecbe38ff1 |  | note | REFERENCE: Services CAD file
label | 489e7e4d-ba35-424b-b6a5-4d12bb7192a3 |  | note | ---------------------------------
label | b6c71e70-ff2a-4dad-9bed-7c5e842ca7ed |  | note | ACCEPTANCE CRITERIA: All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
label | efe8b5ab-0665-43a3-884f-91105446e636 |  | note | Survey to mark out existing services.
label | 121db1ee-3d40-4a38-a0d6-fee62418706e |  | note | ---------------------------------
label | febfb505-c17f-40eb-b785-a1ada002c560 |  | note | METHOD: Visual
label | c57ccfe0-5e61-4ed5-b753-0c09cec8ecd3 |  | note | ---------------------------------
label | bb4ff98d-e73e-4abe-bd8e-40e006b27b61 |  | note | FREQUENCY: Prior to commencement of works
label | e15687fb-b426-4698-8e47-10f92bde4071 |  | note | ---------------------------------
label | f1a2fa9f-0614-43e2-993c-27cea1aa7b43 |  | note | CATEGORY: IP
label | d2d772b2-f0ea-4061-8814-b538933ee654 |  | note | ---------------------------------
label | f6b150fc-a5c4-4f15-9976-8b894d4651a9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2f733e77-774c-4037-9520-fb429ca86eb2 |  | note | ---------------------------------
label | 293dbb3d-5cff-4dda-ac06-429c16be5f0d |  | note | VERIFYING DOCUMENTS: Sign ITP
text | b71e2b9c-b417-4358-96fc-de4711b4d6db |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Excavation Permit
label | 53ccc94e-a453-4a84-a25a-b3a2643acade |  | note | REFERENCE: MRPA Excavation Permit
label | 8f41ccbd-c1fc-47b5-bf04-217099a6bb32 |  | note | Ground Penetration Permit
label | 6eeacaf0-3e8e-4315-9407-85bc678ebe66 |  | note | Metro NAE
label | 72962808-3441-4efa-bf43-7c3560784a23 |  | note | ---------------------------------
label | 1c902815-4af7-409b-b590-afef74dd1736 |  | note | ACCEPTANCE CRITERIA: Insert Permit No.
label | 8733a66e-d5e2-4e31-84aa-17102d89ad49 |  | note | ---------------------------------
label | d807b39e-028a-4380-ac65-5627b0e6ee17 |  | note | METHOD: Document Review
label | d99290d8-731a-40d0-ab00-eb2274c9fa94 |  | note | ---------------------------------
label | eb6009ff-daaa-48c5-ab34-a67826b40ff0 |  | note | FREQUENCY: Prior to commencement of works
label | 06d45b80-6928-4ef1-9076-19bb155833f6 |  | note | ---------------------------------
label | 0bf48e6d-b37c-49a9-9eca-72b80de9f503 |  | note | CATEGORY: IP
label | a03b53ee-b9fe-44bf-b568-6d06255cdecd |  | note | ---------------------------------
label | 5a5f5957-01d6-4de4-ae7c-5d9ea505b43c |  | note | RESPONSIBILITY: SE/PE
label | 5f562655-e880-4022-a3e5-3e3d6e07bb52 |  | note | ---------------------------------
label | 34b8bbc0-6e57-4549-b4a8-1e7f780d9421 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c78370d7-469f-4f13-b116-323596265edc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 VicTrack PTW (if applicable)
label | 6c484e86-4ae8-4ffd-aafd-1be223ff76e1 |  | note | REFERENCE: MRPA Excavation Permit
label | 67ac82d7-f98f-4c60-9090-ad309df70015 |  | note | VicTrack PTW
label | 79b37fff-49bc-4617-9d5e-21ce85790193 |  | note | ---------------------------------
label | b190730d-3acb-48ad-a29c-1dea8cfb8d3c |  | note | ACCEPTANCE CRITERIA: Insert Permit No.
label | bb748ee7-e148-4372-8910-f70f45d55d12 |  | note | ---------------------------------
label | fca82ad0-61d8-483f-86b5-e939cc7d34f9 |  | note | METHOD: Document Review
label | 5e2ed80b-1d9f-495d-901c-f116a01a5d77 |  | note | ---------------------------------
label | 1ef8269c-c5d5-448f-8743-ddf904c3a50c |  | note | FREQUENCY: Prior to commencement of works
label | 3fe8fd1f-3565-4ce2-91a1-4e4d04aee720 |  | note | ---------------------------------
label | c78a7b6e-4d6b-47fc-baf2-046e4d54daaf |  | note | CATEGORY: IP
label | f7e2b328-1f0e-4ebe-b85d-dbac722e0bae |  | note | ---------------------------------
label | c3f65e8e-39ea-4a0d-ba47-5fa0e4e61f51 |  | note | RESPONSIBILITY: SE/PE
label | 8c798d55-219e-4311-ab71-c5cd56900a82 |  | note | ---------------------------------
label | e86cb0fc-5818-4ee4-b693-739c5630abd2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 3c838035-0d6a-4f0d-a0f4-d35e1e6fb26f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 PTDT (if applicable)
label | cc91e82c-703c-4b09-abb8-63336c41cd68 |  | note | REFERENCE: MRPA Excavation Permit
label | 8965714f-ae4c-40d6-a52a-023be6504764 |  | note | Ground Penetration Permit
label | a1118362-6b8b-4319-b35d-9a9361c08e15 |  | note | Metro NAE
label | d5b3f66b-0955-4c11-85cd-106c4e8b00aa |  | note | VicTrack PTW
label | 4abe1df0-beb6-4067-9121-f17f83e73952 |  | note | ---------------------------------
label | 9977eb3b-4420-46c9-9edd-8fab67b98400 |  | note | ACCEPTANCE CRITERIA: Insert Permit No. or Notification Email
label | 257bc7f2-fe81-410e-b519-01a4c1396ca8 |  | note | ---------------------------------
label | 576f3d8a-3fef-4964-96d4-587d4de80a70 |  | note | METHOD: Document Review
label | 7881cccd-ff17-4ec7-afc1-fc8e858a9272 |  | note | ---------------------------------
label | a8db66bf-d5ee-47be-ba8d-592a79fbb619 |  | note | FREQUENCY: Prior to commencement of works
label | 7ab3c051-c0b1-4ea2-a105-dca598ec9814 |  | note | ---------------------------------
label | d5279a97-b102-4bb6-90b1-85eafad5239e |  | note | CATEGORY: IP
label | 4025f1c0-d00e-4aa0-9dc2-64496d6a180c |  | note | ---------------------------------
label | 74c725f0-61c7-4751-9beb-ee44d11e124f |  | note | RESPONSIBILITY: SE/PE
label | 7bcea1d9-f766-4a2b-a3bd-e0f3a54c235b |  | note | ---------------------------------
label | b6ad3dbe-2de5-4fc3-9229-840f2c1fd7fe |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 925f5314-21b3-4c10-9d48-b8692db3b5bd |  | textbox | Date Completed:
checkpoint-group |  |  | section | Excavation Activities
checkpoint-status |  |  | checkpoint | 5.1 Trench Excavation
label | 784d9fdd-b41e-4257-9c51-1980ad0f3ebb |  | note | REFERENCE: IFC Drawings
label | c5df8650-8b45-4f8d-baca-0e17628b39bd |  | note | L1-CHE-SPE-070 7.3 Table 2
label | 240f5097-3fb7-48c0-9fb3-8455651bef90 |  | note | L1-CHE-STD-043
label | b593dade-7787-428f-9322-034369412543 |  | note | L1-CHE-STD-070 7.1c
label | 88aeb87e-5e06-41d1-8d9d-5d9fae4e5f2a |  | note | ---------------------------------
label | af8bf63d-b634-4473-bd4b-0401f6ba06ea |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | bfeb26a8-d372-4ac8-9caa-7c7e95c467d5 |  | note | Edge of trenching to be a min. 2m from structures/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
label | 6ac776f7-d0de-45c7-ac17-0a5e78033f41 |  | note | The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
label | eaa1dc38-651e-4230-ac33-84a5e161f516 |  | note | The width of the trench shall be not less than 200 mm (chain or bucket excavation)
label | d3a25ad1-5957-416f-9c25-1517c377dd1f |  | note | or 300 mm (backhoe and other).
label | b1438685-d8a4-4805-9f13-54d4802477c3 |  | note | ---------------------------------
label | 3ed5294c-c514-4240-9dee-91f20238401c |  | note | METHOD: Measure, Visual
label | b1c5135a-1b9a-4bd1-a260-a08c3581e2de |  | note | ---------------------------------
label | fbaf511c-d4d8-42fb-ad8d-94daa4ce33dc |  | note | FREQUENCY: Each lot
label | 55659777-2a46-466b-953f-7b5feabdafed |  | note | ---------------------------------
label | 3102c20b-0ad9-438f-80fb-ebcbd65f7d57 |  | note | CATEGORY: IP
label | fec255f6-f3b6-4867-99bb-09caa8026f7b |  | note | ---------------------------------
label | 11de2c40-b7b1-46f9-a95f-f6b2512ca05d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | dc7598f0-c24e-412d-9468-c9e38cff0a1f |  | note | ---------------------------------
label | 388de4b6-bca4-46b4-a01e-84b42b7fef02 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9ff39d60-497e-4336-91b2-87297f1f95b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Trench Stability
label | 674ccb52-439c-427f-9b7e-4cf56fea5206 |  | note | REFERENCE: L1-CHE-SPE-070
label | 8dbbd3a0-4993-444e-ac81-a076dd544c05 |  | note | L1-CHE-STD-043
label | 42e47b86-8746-41ad-804f-b5bee5e4a115 |  | note | L1-CHE-STD-070
label | 1d55fca3-05a3-4a7c-a170-4ac0ae9faef4 |  | note | IFC Drawings
label | 01f09271-bc76-4f59-ac0c-2b9675983209 |  | note | MRPA standards
label | a5720035-81d6-4ed8-806c-ae1ee90e2f18 |  | note | ---------------------------------
label | 53e81d45-7f3e-46f0-85f7-0018edcc670e |  | note | ACCEPTANCE CRITERIA: Trench stability check:
label | ee911d15-d2a8-42b8-bf02-5278842a14db |  | note | - Shoring,
label | 4c8b922b-ea81-4e8e-8ba1-35956f4b2707 |  | note | - benching
label | 945592c5-6e43-4e8d-8b54-a3a972001985 |  | note | - geotech signoff
label | 6b6b7956-da9f-4684-810e-0baf55879116 |  | note | ---------------------------------
label | 8980112b-0060-4479-97d9-c11118d269b9 |  | note | METHOD: Visual, Document Review
label | 6184c6c3-8bf9-4a02-83a6-cef939125d75 |  | note | ---------------------------------
label | 6a81ffb1-3347-4a18-b3b9-d4c6b754caad |  | note | FREQUENCY: Each lot
label | 675f1d66-34d5-4e6d-b661-169db6a3b7f5 |  | note | ---------------------------------
label | 87b44f2c-2b2b-44af-b56a-452ad021bdbc |  | note | CATEGORY: IP
label | 85a79434-7687-4dfa-92b1-2f62ef49f096 |  | note | ---------------------------------
label | a08559a9-6b0c-4cd9-ac42-cfbe669f14b7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | bd4b23ec-864b-4f69-884d-e5dea183fa62 |  | note | ---------------------------------
label | 11852a5f-6630-4d38-84eb-147fa9f5d923 |  | note | VERIFYING DOCUMENTS: Sign ITP Attached Geotech Report
text | 8f1707e9-4883-49c0-b788-f7fd0a85c2ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 ULX Trench Excavation
label | 2c53e89f-84d6-481a-b63a-b90f84d0f98f |  | note | REFERENCE: L1-CHE-SPE-070
label | 8cee4a78-6a81-4793-9a4d-5daaca687f29 |  | note | L1-CHE-STD-043
label | 249040c0-6bce-4090-8249-e2b1c5fa653b |  | note | L1-CHE-STD-070
label | 77e29cad-772d-4d91-ba55-5e70840222ef |  | note | IFC Drawings
label | 9a613734-7714-4f0b-bd80-c9e30983dc66 |  | note | ---------------------------------
label | 968c8741-0051-4408-8d99-b1dec6417e57 |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | 1baefded-a013-4bce-baff-2ebb8a9cb7cb |  | note | Trench alignment to be perpendicular to the tracks and extend 3m past the edge of rail on both sides of track.
label | 9ef388a1-60a3-43de-900d-d18bf80cbaaa |  | note | Top of conduits to be 1.2m below top of rail.
label | 06cf6483-1947-4a4a-b46f-b0bba6a293f7 |  | note | ---------------------------------
label | d39b7909-4e1b-48d7-a3c9-f783d62d716d |  | note | METHOD: Measure, Visual
label | 69c7e75d-7f29-4ba3-b1c2-167fa0f6a205 |  | note | ---------------------------------
label | 406e207c-b4bc-4f2f-b284-e8ea314bcda1 |  | note | FREQUENCY: Each lot
label | e766820a-8d1d-4114-848b-8bef257b621a |  | note | ---------------------------------
label | f3517940-3f62-44f0-a826-32d75b648c8e |  | note | CATEGORY: IP
label | 48e913da-b833-47e6-a9fe-be8b6aca1c4f |  | note | ---------------------------------
label | 8dd4ec82-5316-4b76-99bb-69f7a105eace |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e166e999-651b-464c-ad3d-d9cbbd2f47f6 |  | note | ---------------------------------
label | e4bddf48-98c3-4111-9d77-8010ec9d897e |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ab661f05-a17e-4910-97fb-f36395f2e4cf |  | textbox | Date Completed:
checkpoint-group |  |  | section | Conduit Placement
checkpoint-status |  |  | checkpoint | 6.1 Bedding Sand
label | 0c95ce2b-c2b7-4e9b-b8e5-122a13644710 |  | note | REFERENCE: IFC Drawings
label | 3b188b7d-8f4d-4e9d-a4c1-82f4379fbf54 |  | note | L1-CHE-SPE-070
label | 9c5792e1-08ff-4df5-8197-ecda292d6b13 |  | note | L1-CHE-STD-043
label | 378089c2-b94c-43dd-9d28-902ebcc72137 |  | note | L1-CHE-STD-070
label | 131cd202-0713-4c20-ab00-30d2a03ab028 |  | note | ---------------------------------
label | a289f87b-3fe5-4faf-99f6-df1a91625058 |  | note | ACCEPTANCE CRITERIA: 100mm of bedding sand/crusher dust to be places at the base of trench.
label | e217e4df-d2a7-415a-bbd9-d2b0d5b7b4a1 |  | note | ---------------------------------
label | 77859f30-dc60-42fd-94b2-d1fa505d4d28 |  | note | METHOD: Measure, Visual
label | c1f3ae52-065f-403b-927d-e3badbaaf27b |  | note | ---------------------------------
label | a56080df-8d0a-4a2f-ac6e-10756f71fded |  | note | FREQUENCY: Each lot
label | 28391a53-bd2f-4714-aab7-5b254ed80de9 |  | note | ---------------------------------
label | de69014f-5ff6-401b-9cef-8d1c477860b3 |  | note | CATEGORY: IP
label | b373d049-30e0-4a7e-8ef7-d37b4a36d52d |  | note | ---------------------------------
label | ed56484e-c6fb-4a54-8277-f57a901fa1c4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4a5b17c5-366c-4f77-be0c-bf8081b676b4 |  | note | ---------------------------------
label | a1eb3257-7592-4513-b612-e113296801bc |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 0617b192-84ab-49e9-8d19-1a9cfd5dc361 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Conduit Configuration
label | f90bd2d0-05a3-484f-b015-58bf7a8ef760 |  | note | REFERENCE: IFC Drawings
label | d37bb076-f620-4450-8f64-fc359874fa6c |  | note | L1-CHE-SPE-070
label | 05233b0e-8e7b-46a5-84bb-55e214c02128 |  | note | L1-CHE-STD-043
label | 5dd3f8da-fec7-4d8a-b29d-5ffbd6821e48 |  | note | L1-CHE-STD-070
label | 732f00d8-229a-46f7-91c9-a1ae4cf7561b |  | note | L1-CHE-STD-077
label | a5293a46-acf3-4d16-9c0c-50c219cacb27 |  | note | ---------------------------------
label | 7621e73d-3a52-4a5c-bc27-0f8ef75bb66b |  | note | ACCEPTANCE CRITERIA: Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | cb914204-51c2-4591-981d-663581942cd3 |  | note | Min Cover
label | bc178762-8625-4bff-a3e2-6ee5fe696211 |  | note | - HV: 1000mm
label | 1040170a-9212-4bb4-b834-31a7acc4a839 |  | note | - VicTrack: 650mm
label | c19e12aa-7b9e-4349-b90f-f4fa368f0f83 |  | note | - Signalling: 800mm
label | 6b428cfa-e104-4c03-a7c6-e77b539b643f |  | note | - LV: 800mm
label | ee5ad726-3f44-4ac6-84e2-eec1b5f17952 |  | note | - Electrolysis: 800mm
label | 6772a826-c508-44c1-a109-96f8c4fde39f |  | note | - SCADA: 800mm
label | 40c92f6a-cc29-47ea-98cb-658c7cd7bcb0 |  | note | - MTM Comms: 600mm
label | 2998654f-beed-44ee-a1a3-46cf32b3df38 |  | note | - 800mm below water coarses (stab sand encasement)
label | fc6ed32e-f5c2-4e79-aa2a-0077d5371759 |  | note | - 1200mm Under VicRoads Roads & top of Rail
label | 01754d02-be40-4d21-a4ba-e874f19652eb |  | note | - 900mm below council roads
label | b13caa58-7c0a-4495-ae47-5e861d0cd9c2 |  | note | ---------------------------------
label | 8119754c-6629-48eb-b9ef-913f16ff8c54 |  | note | METHOD: Measure, Visual
label | b7c6539e-add6-4ce6-9bfd-97252608856a |  | note | ---------------------------------
label | abfae9a8-797e-4fdf-aa21-541ca29fe0a6 |  | note | FREQUENCY: Each lot
label | e51fc357-9d87-4766-9e4f-759601260664 |  | note | ---------------------------------
label | 2c5eb0f2-676b-4cf3-9d57-6069001bb8d3 |  | note | CATEGORY: IP
label | 35873aeb-0280-4b2a-a872-1e13c4dbbf43 |  | note | ---------------------------------
label | f523b6ca-6aed-46eb-8222-e4b2bb52adbb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9fcb3530-0927-4adc-91bb-0c3ee68d4001 |  | note | ---------------------------------
label | 9c73d659-7429-426c-b94d-ae13d7a3fb2d |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 98bb2d30-b2ce-4a53-ba61-09804ed0f1d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Separation of Services
label | 755594b9-ce4d-4cbe-b2ed-ee48a0fe30c7 |  | note | REFERENCE: L1-CHE-SPE-070
label | 1d2934d9-97c2-4ff1-a404-ecf2f9452e46 |  | note | L1-CHE-STD-043
label | 3de53a4a-5423-4a45-907d-ba94845d886c |  | note | L1-CHE-STD-070
label | f1c71579-a85f-471f-a9ad-806f8421caa0 |  | note | L1-CHE-STD-077
label | 0dcdeae8-48af-43e3-8df5-779ff5d52d2c |  | note | IFC Drawings
label | d3986b8a-876d-4af5-ac32-65be16f3b6f6 |  | note | ---------------------------------
label | 26707277-a01c-41d4-bfe8-7ce8572775c0 |  | note | ACCEPTANCE CRITERIA: Separation of services
label | 4f4ddcd7-fdb6-4592-8004-ee9cd67f4239 |  | note | - HV: Min. separation distance between HV conduits at least 50mm
label | 2832c049-f82e-4a26-aae8-ae7272aca38b |  | note | - VicTrack: fiber 300mm from HV
label | fc67d247-0175-4fb2-bca8-3d24167b51de |  | note | - Utility: 300mm to utilities
label | bc54afc2-a0da-4942-bb30-6cc4d329fb94 |  | note | - Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 0becbc99-0940-4c6f-835a-42bea05383a5 |  | note | ---------------------------------
label | e19cc918-8513-4254-b6d0-8cd622507289 |  | note | METHOD: Measure, Visual
label | 2c642233-94a1-4907-8954-52cac23cb5ff |  | note | ---------------------------------
label | f518b9f0-1550-4259-ad45-f485a72a5f46 |  | note | FREQUENCY: Each lot
label | 1479247a-2143-494b-a9c7-9edcfeee9b60 |  | note | ---------------------------------
label | 412f13ae-5482-4abe-bb89-91a9fbc56c40 |  | note | CATEGORY: IP
label | accd8f9d-4de5-4278-b2bf-344e8f0afedc |  | note | ---------------------------------
label | 2d327ba5-ebe4-4260-94fe-d0486a7591a0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e9b1e5e5-eb92-4eb1-815c-044961827eaf |  | note | ---------------------------------
label | 4b63e5a5-bfe6-4e33-80cf-c086445dd337 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | aefeea95-64c6-4633-a0d1-41b4ba05b17b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Joints
label | 01d07210-4f04-48d6-8e85-b91a923e7041 |  | note | REFERENCE: L1-CHE-SPE-070
label | 32d41f63-32be-4dd3-a874-22d2917cdd69 |  | note | L1-CHE-STD-043
label | 3d762541-cab9-4f31-987b-995d3ca10273 |  | note | L1-CHE-STD-070
label | d7d510e8-e4a4-4b83-a0c0-ab54045ccfd9 |  | note | IFC Drawings
label | 10c4d6aa-eb2d-4f00-9f1d-43b7cfd693f8 |  | note | ---------------------------------
label | 9f06def4-2a7b-483e-8771-05e30ecb6839 |  | note | ACCEPTANCE CRITERIA: All conduit joints shall be made by utilising the spigot and socket ends.
label | 2afbf290-c85e-451a-858b-4eba7478fd5d |  | note | Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
label | 571d5432-39e5-4a18-b721-a70c7d7882a3 |  | note | The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
label | 20785c67-27c2-4ee6-ac4f-03b36c1058ed |  | note | Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | ee274cc7-8b02-4216-9359-0802add7f0a6 |  | note | ---------------------------------
label | 643ccb47-cedc-4272-8369-8a795a82e23c |  | note | METHOD: Visual
label | 6195468d-6a58-469f-b785-7f97b0aca2c9 |  | note | ---------------------------------
label | cb30a2e1-5587-4877-a01c-7db2cdf97385 |  | note | FREQUENCY: Each Joint in each trench
label | 835dae3c-4fe0-4558-a7e6-435482072fd1 |  | note | ---------------------------------
label | 574c07c5-eace-4adc-b728-d763d185069f |  | note | CATEGORY: IP
label | a2d1448c-d92d-47f0-a9ac-e4d9bb5ea67e |  | note | ---------------------------------
label | 827a0de6-0d56-41fb-b8e6-b3b4670b6ba0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | bd6ed2de-2d0f-4d24-8bd3-e18a3b530a17 |  | note | ---------------------------------
label | 4c616b14-f793-4a0f-a82e-e407c0c4dedd |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a1fd77b4-2578-4661-9f30-2fc5a9876a0c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Conduit Inspection
label | 56d60006-5a57-4d26-9dfa-30a27f57df90 |  | note | REFERENCE: L1-CHE-STD-070 16
label | f0ef96b9-0a3a-47af-8744-be9b73085ed9 |  | note | ---------------------------------
label | c03455fb-43fa-499f-bb63-e6682592b5a2 |  | note | ACCEPTANCE CRITERIA: Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
label | 39e1b5ea-6402-4ffe-8a32-88f5af7688aa |  | note | ---------------------------------
label | adb4e41c-739b-405e-93d5-7f0e6b9b771f |  | note | METHOD: Visual
label | 749cb004-a65e-49d6-88ba-bac4c7e76b8a |  | note | ---------------------------------
label | 8f8dfd5a-57f8-4763-8b3d-6242cf544666 |  | note | FREQUENCY: Each lot
label | 45f362ea-efcf-4194-9d3a-5fd061ff86f1 |  | note | ---------------------------------
label | 6d954932-2548-4765-b49b-aaef647062eb |  | note | CATEGORY: HP
label | 107df051-9f37-41d3-b103-6a16537b0af4 |  | note | ---------------------------------
label | 9fd616bc-6740-4a66-9fe8-fee3828cfcc8 |  | note | RESPONSIBILITY: SE, NA, MTM/VicTrack Rep.
label | 2a0afe69-3abb-4dd2-956d-e81f8e617c24 |  | note | ---------------------------------
label | e59d837f-83f6-4834-b62b-f1446a07a69c |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a289c2e3-0007-40fd-9d04-0fdff1e4a046 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Survey As Built
label | 22038614-0c21-4f99-b676-aaff286a07fd |  | note | REFERENCE: L1-CHE-SPE-070
label | 8dcadabe-f309-4a7e-a8cf-fa9896cdf9d7 |  | note | L1-CHE-STD-043
label | e66eee66-abbe-482f-8faa-ba639f384e4a |  | note | L1-CHE-STD-070 CL13.1
label | 2e0ed3a1-8b77-4b99-ac67-909134d441ab |  | note | IFC Drawings
label | ef5cf45c-8f28-4e19-86c8-f99a35f770f9 |  | note | ---------------------------------
label | 524b3600-b649-4b23-9a2d-4c2aee986315 |  | note | ACCEPTANCE CRITERIA: As-Built survey to be completed and recorded before backfill
label | 954c79ea-6238-4608-a295-579280aebb44 |  | note | - Cable joint locations.
label | 53193552-216a-4fb8-989e-1e9427ed90c8 |  | note | - Cable pit locations (Corners)
label | 640e4cf1-5683-4564-83ab-f65bdffc2437 |  | note | - Pit dimensions & pit lid type
label | b82ed1b5-625a-4940-95dc-8137599da6b5 |  | note | - Under line crossings
label | f2e5a44b-2158-42b8-8a4a-15b43c5e06a3 |  | note | - Under road crossings
label | d09e54c0-6516-4466-bc47-3fd31fdcee2d |  | note | - Changes of direction
label | 0db5acc1-8567-445b-a08b-e3d431f282f3 |  | note | - Spare Conduits
label | 8081be2b-3b58-45ad-bba1-7c25c098a62a |  | note | - Conduits labelled as per trench profile
label | a00ce5e4-e7d3-499e-99ae-0af70de22e10 |  | note | - every 10m
label | fe1880a0-b7cd-469b-b413-c284e2ca5d18 |  | note | - Other significant points of the cable route
label | 4fceb2fd-aa22-4ed1-b58b-b81e9f7bf509 |  | note | ---------------------------------
label | e7441a9a-1099-454e-b4b2-f9c922c94516 |  | note | METHOD: Measure
label | d17de0ce-bbee-4238-8c18-54085b646ac6 |  | note | ---------------------------------
label | b477db45-e027-4291-9f87-62faa3ff7257 |  | note | FREQUENCY: Each lot
label | 09110377-348c-4a20-925f-c84eeb2a91bb |  | note | ---------------------------------
label | 43bf1093-d6e8-4e92-81ac-8a4d6239e788 |  | note | CATEGORY: WP
label | 0c04e9f3-afec-4e56-8404-72d178fa14a8 |  | note | ---------------------------------
label | b625e359-6414-4d3d-91d1-5da73b007ffb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 35695341-3121-407f-9ae0-00e77ed385b4 |  | note | ---------------------------------
label | df3e9587-2f11-40d3-8433-65edad5aeecc |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 70fec08b-6d0b-47a1-801a-cb714a03ad1d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Bedding Sand Installation
label | 2bf5377c-91e3-4c86-9409-4a3228529400 |  | note | REFERENCE: L1-CHE-SPE-070
label | 088a5fab-28fd-4f5c-9996-80a7d5c32143 |  | note | L1-CHE-STD-043
label | 29a93db0-0ad7-460e-9036-6d0948c3dbe5 |  | note | L1-CHE-STD-070 CL13.1
label | f8522341-3f5a-4ce8-aff9-b706121468dd |  | note | IFC Drawings
label | 3f31b61d-269d-4c08-b04d-520b2fb44aec |  | note | ---------------------------------
label | 29d7557d-d10a-4a1b-84f0-25b9a2a56063 |  | note | ACCEPTANCE CRITERIA: Bedding sand/crusher dust extends 50mm past edge of conduits.
label | 96c2637f-43bc-4b13-8f2f-c308fcfe222a |  | note | Bedding sand/crusher dust extends 100mm above conduits.
label | 5633bea2-246c-4626-8408-371625e4e750 |  | note | ---------------------------------
label | a3c4bd5b-c635-430b-9fac-84be906d7e88 |  | note | METHOD: Visual
label | 03da609d-ec00-4d57-9b94-cbad094418c8 |  | note | ---------------------------------
label | 3996319b-76d4-4a50-bc15-b054dfe17441 |  | note | FREQUENCY: Each lot
label | 758e62ef-b81d-42da-8a5d-24489af668d9 |  | note | ---------------------------------
label | 671797a7-6eef-453d-86d4-347fead2cb13 |  | note | CATEGORY: IP
label | ba9d69e9-c686-4a49-9d95-6cc71dcf85d8 |  | note | ---------------------------------
label | e67f14eb-01c7-4068-92f1-514408692c31 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c11522f6-f8c7-43c3-aacf-5476f6722848 |  | note | ---------------------------------
label | dc3ceab9-bac1-4a69-8ff0-b162148a7e6b |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Delivery Dockets
text | d7a27170-4490-453e-82d6-54e2bd7a400c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 HV Protection Barriers
label | 6c59db80-026e-45e5-abed-4b6d1a0d8a37 |  | note | REFERENCE: L1-CHE-SPE-070 Cl10.3.3
label | e6d30b86-31c5-4967-b842-dcc33674d627 |  | note | ---------------------------------
label | a49ab333-9d89-4803-8d84-02989c236a46 |  | note | ACCEPTANCE CRITERIA: Top of HV Protection barriers installed 150mm above and 50mm beyond vertical line of any HV conduits
label | 0e60cc88-bccb-4a3c-85bd-0136259347f8 |  | note | ---------------------------------
label | 77a0a015-b807-457e-ba03-cc0261e3cb01 |  | note | METHOD: Visual
label | bb09466d-5165-4259-b0b7-ebad6d463d31 |  | note | ---------------------------------
label | f9dc125a-1e58-4e53-be42-9f7dfaef418f |  | note | FREQUENCY: Each lot
label | 974465ba-29c2-4952-903d-9e2abe89009a |  | note | ---------------------------------
label | 29bee25d-bc8e-437c-95e9-35abec36d056 |  | note | CATEGORY: IP
label | 3973b53d-cc64-4cce-921e-ff893a5dba92 |  | note | ---------------------------------
label | 9c70809e-ca82-4c46-a70a-dc2bd1e2764e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8bf21024-022a-4807-b585-a3954f235edd |  | note | ---------------------------------
label | 02255c52-8683-46b1-8484-6b979dc02d3c |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 12c1db4c-1e9a-4be1-9304-4ec61c10f06d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Marker Tape
label | d558be7a-6c53-4e3f-94c8-bc8fd8e7dc46 |  | note | REFERENCE: L1-CHE-SPE-070
label | 6d7b51ff-06e7-4cd8-8622-43cc89775b36 |  | note | L1-CHE-STD-043
label | 9b63fbd1-bc9f-4a25-b754-00c376536f13 |  | note | L1-CHE-SPE-070 Cl10.3.3
label | 3d24971b-5227-41bb-b4a4-e5ecc3323359 |  | note | ---------------------------------
label | 8531327e-1e07-4f9b-904d-a342823a858f |  | note | ACCEPTANCE CRITERIA: Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barriers.
label | cb37d647-5776-4454-a791-128c45203ec3 |  | note | Tape to be one continuous length.
label | ff08ef43-668f-48f0-ab49-97f5359b8042 |  | note | VicTrack to inspect the Marker Tape placement..
label | dad185ba-f1f0-4f7a-b2e9-851420df303e |  | note | ---------------------------------
label | 479561b6-fd14-4a9f-a135-8c1aa71f45fb |  | note | METHOD: Visual
label | 98d686f3-276d-442b-9a1e-1870a04b1d8f |  | note | ---------------------------------
label | 04a943d1-9511-4257-a442-a35df11facc1 |  | note | FREQUENCY: Each lot
label | 18f35982-977b-44ca-90fc-98c4778bf2b9 |  | note | ---------------------------------
label | df509e29-f8bc-4e46-beed-3f1440832c5b |  | note | CATEGORY: HP
label | 03faea93-9a04-42e8-8b4d-10428107ee98 |  | note | ---------------------------------
label | 8838ed1e-9410-4c7d-83a6-230dcc56a578 |  | note | RESPONSIBILITY: SE, NA, VicTrack Rep.
label | 987fd01d-c106-414f-8746-a544217ad1f2 |  | note | ---------------------------------
label | e844e673-9c2b-4272-bd1a-0fe2846138c3 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | cf460c3d-e23f-4df9-8b9d-5d32bc0a94cf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 Backfill Installation
label | 5fd044ef-cfec-4a35-8871-366b646409d8 |  | note | REFERENCE: IFC Drawings
label | 9e689752-d5fe-4136-8aa7-980fa3db296f |  | note | L1-CHE-STD-043 clauses 6.15 and 6.16
label | dabb3fc0-3ee0-4750-8de4-69eb8b2541d1 |  | note | ---------------------------------
label | 42f23343-8e5d-4951-9c5b-d8442fe93132 |  | note | ACCEPTANCE CRITERIA: Backfill per trench profile
label | cf18ef75-c035-442d-9ad3-cca47b3b4edc |  | note | - 150mm layers
label | 1a6bad27-3c71-4571-b81e-5772963c6388 |  | note | - CBR >3% for existing material to be used
label | ea5a32aa-7d74-4730-80cc-d3abc27bab71 |  | note | - 95% compaction
label | 2f5e7188-b029-4b34-86f1-b3b7ad433f85 |  | note | - conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
label | 5789911c-911e-4278-a402-308afc528290 |  | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | 7adca1ee-6870-4c42-8160-27fb6495edce |  | note | Trenches under road pavement - backfill to be same material as the road formation material.
label | 3838a126-9039-4434-9416-b1792f05dd1c |  | note | Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
label | 54ed27ac-423f-4b91-aa2a-a49b708f944d |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 506cb447-dfc9-4ede-99a0-9a61ea53813a |  | note | VicTrack to be notified and witness the first layer of backfilling.
label | f759a993-2ca1-48e6-8acb-f25513668176 |  | note | ---------------------------------
label | 84c3f060-0a48-4ced-a231-abafa89419b4 |  | note | METHOD: Visual
label | bc1bf6f9-cc47-4d0a-9ff5-b2bd3b50c698 |  | note | ---------------------------------
label | 34e09c31-bf3e-4340-b8f4-4b6f599f314d |  | note | FREQUENCY: Each lot
label | ceac9311-f571-4bcc-994a-55b8f14fc5f9 |  | note | ---------------------------------
label | 76e5914e-9365-41a5-9f16-d13e768d10ff |  | note | CATEGORY: HP for first layer only, IP for the rest.
label | ab04e49e-7a27-48a4-9b64-91f3939df26e |  | note | ---------------------------------
label | daffab16-0bc2-46a3-a9d7-a32ca23253a1 |  | note | RESPONSIBILITY: SE/Site Supervisor/NA/VicTrack Rep
label | fc0c07c3-7b2a-46b9-84af-a7b643f7c466 |  | note | ---------------------------------
label | a1877764-8e70-48a5-96a6-12488f5fa7a7 |  | note | VERIFYING DOCUMENTS: Sign ITP Attached Delivery Dockets
text | 8652a74f-bba4-4c57-b0cc-13ff6555a3d1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.11 Compaction Testing
label | d235bd55-b12f-4083-aa22-386121575e90 |  | note | REFERENCE: L1-CHE-STD-043 clauses 6.16
label | 5878df24-5a44-4ee1-9f18-36af94a39c84 |  | note | ---------------------------------
label | 0bbbbea9-b62c-47cb-8445-8fd64aabf680 |  | note | ACCEPTANCE CRITERIA: Compaction to achieve 95% Standard Compaction.
label | f5bb8d66-0f45-4122-8716-9da80f2f5d15 |  | note | The tests shall be taken on a frequency of one (1) test per 200 linear metres per layer or one (1) test per area per layer where any area of excavation is less than 200 metres long.
label | 7dc9da6b-87cc-4dd8-b664-1dabee9d1079 |  | note | ---------------------------------
label | 7818b98f-ac17-4071-9cb0-5b66da2ef2e1 |  | note | METHOD: Document Review, Visual
label | 507fe1f8-69ee-4539-a326-7e3853b52d71 |  | note | ---------------------------------
label | 96a7b720-468c-4abf-abf7-d140d6e365c5 |  | note | FREQUENCY: As Per L1-CHE-STD-043 6.16
label | 4978d891-4c60-4e14-93bb-5afb4f2ccf0c |  | note | ---------------------------------
label | 22cd116f-b96a-412b-98f5-a5a90e31b001 |  | note | CATEGORY: IP
label | f0e3e878-7494-416d-85b5-fc364786ab99 |  | note | ---------------------------------
label | a3566e5a-4385-4fc9-a519-0c55a17745d6 |  | note | RESPONSIBILITY: SE/PE
label | df7f21a1-e9a0-4b56-b009-33dd9fd0916e |  | note | ---------------------------------
label | e1dbbb24-e049-45dc-8cd8-857d4d24c409 |  | note | VERIFYING DOCUMENTS: Sign ITP Attached Test Report
text | 89d3cee6-ab07-40e6-b6ce-5f1def8c2d48 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Location
checkpoint-status |  |  | checkpoint | 7.1 HV Pits
label | 05336ee6-1bc5-4177-a9b4-4d8b85084e65 |  | note | REFERENCE: L1-CHE-SPE-070 (Cl 7.21c) CL9.2,9.3
label | 1c103ec9-d47b-4dd6-b0f8-dfde004f2636 |  | note | ---------------------------------
label | 5ed4c725-93bf-479b-828a-739b1d5ccb45 |  | note | ACCEPTANCE CRITERIA: HV Pits
label | 6c8a5b39-5a09-412f-802c-d297cdb7db6d |  | note | - intervals no greater than 400m
label | 6978f70f-814d-4b88-823a-59d445ac550c |  | note | - 3m from rail
label | 9e5b0c51-eb6f-440a-a5b7-8a2b30250fa4 |  | note | - Access Roads, Class D lids
label | a77d316a-b9d8-4fe2-a0bc-8a706921d7d8 |  | note | - Footpaths and non traffic areas, Class C Lids
label | 3ed20171-47da-4787-8739-d688137a1e5b |  | note | - Alignment of square pits parallel to property line
label | 4019c718-7c59-4092-9335-67d1afdd86c8 |  | note | - Pit size as per L1-CHE-SPE-070_9.3.2
label | e4851ab9-1e2b-49eb-b9a3-59ae1751fb3b |  | note | ---------------------------------
label | b7ace729-6d3e-44e5-8892-6fd19b48cce5 |  | note | METHOD: Visual
label | 6c048e39-7aeb-45d9-a631-27f44eee4333 |  | note | ---------------------------------
label | 5fb73c4e-41e5-47bd-b4d8-29efac91f7fb |  | note | FREQUENCY: Each Pit
label | bb9e9263-466b-41b7-b727-ce704400b46a |  | note | ---------------------------------
label | 48720b91-2c25-40b5-9188-d3a544741964 |  | note | CATEGORY: IP
label | 3c822620-d4bc-40a9-9200-6165936c600a |  | note | ---------------------------------
label | 2d9863a6-b3bc-4971-95ae-4cf38cd2cfd5 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ce9d1aec-4a37-4a6b-883b-2dc946a633d7 |  | note | ---------------------------------
label | ebbced02-c19d-490e-80d1-6d8e517dfcba |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a564378c-9412-4d5c-9c5b-1b186c72bc6b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.2 Sand Pits
label | e5860015-fb5a-4751-acaf-f3aa343b1638 |  | note | REFERENCE: L1-CHE-SPE-070 9.4
label | 27e3097a-5fad-48a6-9dd0-3f0bd2f72aa1 |  | note | ---------------------------------
label | 728f934b-953e-4d1b-874f-170e77a9b283 |  | note | ACCEPTANCE CRITERIA: Min. clearances from:
label | 84261bbe-b8e3-4af5-9b3f-71a0e819ea12 |  | note | 5000mm CLEAR OF VICTRACK ASSETS
label | 9c378792-5dbb-4fe2-b815-8c8afe6b8fe6 |  | note | 2000mm CLEAR OF MTM SERVICES
label | 866bc9d2-c4e2-478c-8c60-1d78a1a1329c |  | note | 3500mm FROM NEAREST RUNNING RAIL
label | e5eb4193-db56-4b3a-ad9d-18b68329481a |  | note | Sand pits shall not be used within paved areas and access ways
label | 0cc27e36-dbed-4d67-afa3-cd74a306933d |  | note | Not to be deeper than 1500mm
label | 2b6f8702-a6df-4fd5-8ffa-63d66edcb901 |  | note | ---------------------------------
label | f9d7f5d5-cabf-4c60-9605-de6677e55eb8 |  | note | METHOD: Visual
label | 147b3958-0d09-4eaf-8910-d5e5b3705332 |  | note | ---------------------------------
label | 8dac0eb3-c8fe-4009-9e44-66e28dfc3b01 |  | note | FREQUENCY: Each Pit
label | 48f74379-7e2f-46d1-98be-0552ecb9837d |  | note | ---------------------------------
label | 6feaaac5-9370-4711-a7a6-c1719adb4592 |  | note | CATEGORY: IP
label | bccf799b-df8a-43dc-ba84-14deb5396428 |  | note | ---------------------------------
label | cb3a9b42-8df3-44e3-b69e-5635175ffaab |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0b9f379c-4aa7-447d-b58d-0ff09ce78703 |  | note | ---------------------------------
label | 5fb650bc-4945-4301-9222-f8a9defa9aea |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 04c02834-ab69-4cab-a71a-ab57ab595741 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.3 Vic Track Pits
label | 8479e302-4b30-4f01-ac0b-baa52319d96f |  | note | REFERENCE: L1-CHE-SPE-070
label | d559b9dd-0294-45f8-959a-63b86d36609c |  | note | L1-CHE-STD-043
label | ddd64b21-24a0-4e62-b547-f3aa7a68ff68 |  | note | TS-SP-013 7.2.2.vi & 7.3.7
label | 3939804f-9452-4822-b0d3-bc1c1e4ee6e4 |  | note | ---------------------------------
label | bc705d32-f359-43b4-b833-9105bd36e3a3 |  | note | ACCEPTANCE CRITERIA: VicTrack Pits:
label | d4e6dddf-8b50-48b1-8a7c-0138fe5f724b |  | note | - intervals no greater than 380m
label | 8227881f-295a-495e-b3d6-fa5877dd057f |  | note | - no lateral deviations of conduit from the straight line between pits greater than 2 metres over the nominal 380 metre pit spacing not all at a single or several distinct points. If this cannot be achieved, then the pits need to be at a closer spacing;
label | 5c941045-ac00-4d7a-9185-fa9cd3b5ac4c |  | note | - 4m from rail (if within 4m a physical barrier at 3m is required)
label | 7f216b40-21a9-4241-aaf1-f574632f0b4a |  | note | - Access Roads, Class D lids
label | 1f4d2ca6-e2f3-4dd8-ad2b-a398e7575696 |  | note | - Footpaths Class C Lids
label | 90e4caae-8f60-4608-a8d6-e9becda8da09 |  | note | - non trafficable areas Class A with bollards
label | 3fd52d24-ba90-4a47-b59e-9fb7ffe583ce |  | note | ---------------------------------
label | b8b2c2f2-ee7b-4be7-9909-20691447f5a4 |  | note | METHOD: Visual
label | 44d68686-30e2-466c-a5b8-859514bb19a4 |  | note | ---------------------------------
label | a38a91a7-eb55-49c2-903d-3b74fa377caf |  | note | FREQUENCY: Each Pit
label | d95886e5-00a5-4346-97b5-8426e9e3a50d |  | note | ---------------------------------
label | 691dac2d-039c-4bec-b315-4839de05533c |  | note | CATEGORY: IP
label | a0a5c97a-573a-46aa-90dd-63c9397397d5 |  | note | ---------------------------------
label | e9044d70-a701-4b4e-acc8-7697bfc96351 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 321a0591-3d0e-4de5-8430-c4a4ef61dba5 |  | note | ---------------------------------
label | aeda0c30-bb09-4bf8-8ba0-4c6c0abc3a75 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 15edc3a6-addc-4f9e-90d8-272edd8d09f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.4 Signalling Pits; LV Pits; Electrolysis Pits; SCADA Pits; MTM Comms Pits
label | ca619e11-33ec-4f37-bc9c-b48d323d956c |  | note | REFERENCE: L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
label | 00dbf13e-2050-4896-b240-d3a8182c22f0 |  | note | ---------------------------------
label | e20aab42-a2d5-4175-8998-a238d3764586 |  | note | ACCEPTANCE CRITERIA: - intervals no greater than 400m (electrolysis 190m)
label | 147ef081-e444-4c12-92ae-f15796b8607f |  | note | - 3m from rail
label | 01b67701-eb2b-4c90-a09a-636fe41e1259 |  | note | - Access Roads, Class D lids
label | f7e22d9e-e59e-4167-aaad-246384d5e7ee |  | note | - Footpaths and non traffic areas, Class C Lids
label | c26f418a-1c49-42a2-9bf0-0df367597995 |  | note | ---------------------------------
label | 7f603370-6049-44ec-b71a-5c062506c7c6 |  | note | METHOD: Visual
label | 2cc963fe-6988-4ce7-a25a-278c658fc0d7 |  | note | ---------------------------------
label | 55a08844-2047-4351-807d-49b27b0add4d |  | note | FREQUENCY: Each Pit
label | 500a98d1-93ea-4ed6-bb17-5dea8d809a07 |  | note | ---------------------------------
label | 4106ce6f-45f0-49a9-a77a-bce001726636 |  | note | CATEGORY: IP
label | 77afef6c-1813-4cb3-98f1-c215b7c8ef85 |  | note | ---------------------------------
label | e592ae5f-9344-495c-95b8-53a6765a6769 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 5b419daf-1073-417b-8144-de340456f215 |  | note | ---------------------------------
label | bc866435-792f-46b9-b1e0-65a7891836ab |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9548c5e9-4cc9-4df2-a446-785d344517a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.5 Additional Considerations
label | 380b49a1-9826-4b2c-a0d6-fce21014cd0b |  | note | REFERENCE: IFC Drawings
label | 3c062e0f-a5a2-4ec0-9b36-c46a30167233 |  | note | ---------------------------------
label | 7b75d285-0b01-4987-a9dc-2ded45ed77da |  | note | ACCEPTANCE CRITERIA: Access tracks to pits
label | 9ce6e6d8-6f1c-44e3-8513-ab0aa8a65d2f |  | note | Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
label | f4cc81c2-7688-4aa0-8390-0edfe4d0c996 |  | note | Hand rail & retaining wall installed as required
label | 4ea11498-0d24-4c98-af06-96063da638ed |  | note | ---------------------------------
label | 49e6d377-0361-4cf9-9f10-7c3deea7405f |  | note | METHOD: Visual
label | 218a9580-5326-4441-a344-0b6be2b4abd5 |  | note | ---------------------------------
label | 00022a1a-3bb9-4f64-97c2-716886259989 |  | note | FREQUENCY: Each Pit
label | 9ee4b4db-f0af-4ba2-a67a-fac9e215faee |  | note | ---------------------------------
label | ffa0fcd9-8105-4411-8c98-0d2004fd74ff |  | note | CATEGORY: IP
label | c3ce4282-48fc-478f-94c9-13ee0c4f2ec8 |  | note | ---------------------------------
label | d166873a-6628-4bd2-a669-9fa525810946 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2be2129d-af55-4453-ae56-be2f132ef42c |  | note | ---------------------------------
label | cded60fc-0dae-4157-9c89-2108d2f7dc50 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 0800c955-1103-467b-bbbe-b99c80e47d7b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Installation
checkpoint-status |  |  | checkpoint | 8.1 Bedding
label | 57789f91-6dd4-4365-9c95-a65740db1896 |  | note | REFERENCE: L1-CHE-STD-070 Cl 7.21.u
label | 4e04b6d5-18bd-47b3-a69e-d7e55f3274e3 |  | note | L1-CHE-STD-043
label | 547bf226-7491-4fb3-980e-f57a445b7ad9 |  | note | ---------------------------------
label | 0219c4f2-0b6e-42ca-bcfc-38ba42861487 |  | note | ACCEPTANCE CRITERIA: 150mm of crushed rock under pit extending 500mm past the pit
label | 01a90f95-0305-4fd9-be25-a2a4e91fa18b |  | note | Drainage arrangements shall be provided at the base of each pit.
label | 9ed5d82b-1916-4cc5-82d3-3c524a34b95b |  | note | ---------------------------------
label | 8f1a2da7-d71c-4b8a-be9e-1f40dce19688 |  | note | METHOD: Visual
label | 96781123-e468-46dc-9f24-7f26ebbd077f |  | note | ---------------------------------
label | 2f004c3a-a5ef-4b49-88aa-fa4679db321e |  | note | FREQUENCY: Each Pit
label | 0d00d8b8-0ac0-4e6c-82cf-8da8b3449208 |  | note | ---------------------------------
label | e0a5ff00-bdf9-4e91-b821-1ba76feacdd2 |  | note | CATEGORY: IP
label | 4ba97126-b478-4e5e-b69d-d2fb6fe7afa6 |  | note | ---------------------------------
label | db7efd08-2041-4b2b-8eab-ed8196434c21 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | eb4ba9e3-4076-4a53-824e-e775d876ffe2 |  | note | ---------------------------------
label | 54374133-0842-447c-82f9-c775b4df3c52 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Delivery Dockets
text | f8789f81-c98b-4a98-baff-d66710fce590 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.2 Pit Orientation
label | 0fb18bdb-757a-4b50-92dc-8c7db05db878 |  | note | REFERENCE: IFC Drawings
label | 87f22d3a-40f4-478a-b108-c60209287817 |  | note | ---------------------------------
label | c1787536-0f06-452c-9ec0-f729070cdefd |  | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
label | 150a6dca-107a-4a9e-9b90-f4cc746ac62e |  | note | ---------------------------------
label | 6e642cda-641a-4683-92fb-3bba1f81e394 |  | note | METHOD: Visual
label | 632c2ab9-a36f-499f-9380-e944e08194a2 |  | note | ---------------------------------
label | 3f30d3d6-d60e-485f-99d2-212ebe24679e |  | note | FREQUENCY: Each Pit
label | 34c6ff2c-fdb2-4f32-969d-2281e546dcc5 |  | note | ---------------------------------
label | c75d3d3b-3025-4ad2-a8b0-6952340c8bc7 |  | note | CATEGORY: IP
label | 54d66628-6dfb-4218-a3e3-3858ecb351b0 |  | note | ---------------------------------
label | e88f47a5-1903-4289-bb29-0706c461ccef |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b26d9b27-7f1f-43f4-bb82-fb889115f60e |  | note | ---------------------------------
label | 77a50c49-c991-4928-9b8a-0b11559f5971 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 1fab800f-523f-45dd-9f3c-2140672e0bff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.3 Pit Installation
label | 8ee03eb3-80ed-4f81-b9e5-41428a2517f3 |  | note | REFERENCE: IFC Drawings
label | fe26ab96-4759-46e8-908b-1391f9e2909c |  | note | ---------------------------------
label | a54c9241-13f4-4472-9f97-8ac726d90589 |  | note | ACCEPTANCE CRITERIA: Pit installed to design specifications
label | d9d77dd8-3cec-470f-965b-90e381adc7be |  | note | Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
label | 77054a43-2be6-40e4-ac52-ad9b94c1612b |  | note | ---------------------------------
label | 64f54cd0-a7b8-4f3a-8ae4-0089e9453917 |  | note | METHOD: Visual
label | 370c8fbb-02e4-4ec1-9dbc-fbd8c2dcdf00 |  | note | ---------------------------------
label | 3eb752dc-2b20-47cb-9d29-06b8a7f0d631 |  | note | FREQUENCY: Each Pit
label | d34e9a42-eadf-4ce3-bc14-7292e92675b2 |  | note | ---------------------------------
label | c4ed792d-49d4-466e-8b23-c059dfd4bd59 |  | note | CATEGORY: IP
label | 4ee20c1b-ba44-4047-926e-7a868900de8e |  | note | ---------------------------------
label | a5890b95-25fe-4590-98df-cf7b72fe262e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c25a431a-5829-4e92-9d72-05a1ce37490f |  | note | ---------------------------------
label | 0cce8ed4-d2b7-4ad2-99f5-3be596de2627 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 23a9a057-aba8-4b76-86fa-1a589a5ef889 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.4 Pit Greater than 10ft
label | 76101749-e44c-43f6-9d09-fe32d98a0ba3 |  | note | REFERENCE: MRPA Procedure
label | 2cc8bcab-fe68-4a3b-80e1-0a6d6b1392af |  | note | ---------------------------------
label | 558e27ad-0f8a-4672-b87e-fcbb927c9d8b |  | note | ACCEPTANCE CRITERIA: Each pit if non standard lift (greater than 10t) the following is required:
label | c71d88da-4f4f-412a-9646-c44610da636d |  | note | - Certified Working Platform
label | b25c68aa-2499-4190-b165-06290bad7d4a |  | note | - Certified Lifting Anchors
label | d18686f3-9809-4ce3-9cee-9887d781a296 |  | note | - Approved Lift Study
label | 84d167d4-10cd-443f-8ff9-df05e4b4d875 |  | note | - Check Birth Certificate
label | c94e57e0-b665-4216-8424-97d2ced4a1fc |  | note | ---------------------------------
label | b19e4ff4-0928-411b-ae50-e3203e02d7e2 |  | note | METHOD: Visual
label | 2ba1df41-46d5-49e1-b3db-35fbbf9e6848 |  | note | ---------------------------------
label | e5078b5d-1f32-4dbe-8422-a232708364d4 |  | note | FREQUENCY: Each Pit
label | 44b5545f-47fa-45b3-b9c3-e06a87e73459 |  | note | ---------------------------------
label | 0af1a356-43ed-4bf0-9824-82c779a8448d |  | note | CATEGORY: IP
label | 4c51a6b8-94e6-4556-a683-3e0f025b8f4e |  | note | ---------------------------------
label | dd4ef742-68e9-4345-aa7a-d53d03c2f32d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | d9b53baf-06fe-4ee5-95a8-daca1a6d4248 |  | note | ---------------------------------
label | 9b0ce562-106b-4178-b437-f8bf450e343e |  | note | VERIFYING DOCUMENTS: Sign ITP Attach: Geotech report, lift procedure, shop drawings
text | a7a5f916-7bda-4726-9070-0127ab01572a |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Fit Off
checkpoint-status |  |  | checkpoint | 9.1 Conduit Entry
label | 25751da0-f388-45ce-b219-7d80559bb8ca |  | note | REFERENCE: L1-CHE-SPE-070
label | 75e41688-dae1-4fce-ae61-35740a4a87ae |  | note | L1-CHE-STD-043
label | 1f095378-090b-42cc-90b8-342bf7ca82eb |  | note | L1-CHE-STD-070
label | 91569700-1151-4238-8736-75cb554af237 |  | note | IFC Drawings
label | c61ae337-7078-4456-ad73-e9ca6f23cb0e |  | note | ---------------------------------
label | 32161b26-e20b-442c-b97c-13eec845f76b |  | note | ACCEPTANCE CRITERIA: Lowest conduit 100mm from the pit chamber floor.
label | da35002d-fea7-4753-9b96-066900f224b2 |  | note | ---------------------------------
label | 4fa1a25f-1d59-451f-8675-0259215c2aed |  | note | METHOD: Visual
label | f067ab7d-4219-45a8-a73c-9096e1bf0ed8 |  | note | ---------------------------------
label | 37f1864c-11be-46ff-83f5-c1a01239635e |  | note | FREQUENCY: Each Pit
label | 5b3c3772-e347-475c-a5ee-82e1ed4b03b0 |  | note | ---------------------------------
label | a4dcf576-44eb-41e4-a46b-9426ffe94d50 |  | note | CATEGORY: IP
label | 7d9bc312-b99d-44ce-855f-07f0136346e8 |  | note | ---------------------------------
label | 315fdd79-f26c-4d02-ba30-d85fa9da7edc |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fb35aaad-e171-421d-8509-995ebb7e7bdd |  | note | ---------------------------------
label | cf0ee6b2-ec49-4d7c-8f0e-7d53ae502864 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6da53050-3330-44ff-a07c-b664b7388fd5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.2 Tracer Wire
label | e3419bf8-35ef-444c-913d-45ecc5608308 |  | note | REFERENCE: L1-CHE-SPE-070
label | 1e1b0a39-007d-4ee7-8d5a-fa57265ed03b |  | note | L1-CHE-STD-043
label | 815e9ca4-b8d7-4bd4-9d36-988b95d0255c |  | note | L1-CHE-STD-070
label | 882c04e5-85f1-4dad-bf8e-9850e641cbbd |  | note | IFC Drawings
label | 0fc6dfb2-edbd-4414-8df6-638ac4f2870c |  | note | ---------------------------------
label | 9f9b5389-589b-46a6-b4e8-c5eaf1e948c9 |  | note | ACCEPTANCE CRITERIA: Warning tracer wire for Vic Track routes to be drilled into pits and crimped off.
label | aa838c57-ea29-4618-9f2a-415ded911838 |  | note | If tracer wire broken needs to Crimped
label | c336dc4d-13ed-490a-a3c0-325f9b162f23 |  | note | ---------------------------------
label | 50f55b86-2a49-4576-9b14-07bb99dc6e54 |  | note | METHOD: Visual
label | 2a51b1b5-b79c-49ee-92e3-e44d34cf1437 |  | note | ---------------------------------
label | 3bd08a7b-1d06-4ed9-968d-99f76a25c7c5 |  | note | FREQUENCY: Each VicTrack Pit
label | a6d45a00-7af4-4490-a603-5f1dbe9e673e |  | note | ---------------------------------
label | 66e46243-8268-476e-bf60-2da67591ecd7 |  | note | CATEGORY: HP
label | 09f29bcb-7c01-430c-a262-eb05b6277ec6 |  | note | ---------------------------------
label | 9787e1b7-4efa-457f-8493-cd35612216d6 |  | note | RESPONSIBILITY: SE, NA, Vic Track
label | a93fce33-4066-4c9c-998e-0319ec2a9236 |  | note | ---------------------------------
label | aa84064f-7669-49ca-9e6a-e6be9d59ad1c |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 235e1099-6b2d-4217-98f9-5063114e6ecb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.3 Spigots and Bell Mouths
label | 737177a0-0f58-42cb-bafe-055aef52a48f |  | note | REFERENCE: L1-CHE-SPE-070_9.3.4
label | 55821f5a-5bd8-448e-a2a0-08ccc319003c |  | note | ---------------------------------
label | 6b3b67b3-992d-4193-8012-347b76d2cb00 |  | note | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
label | f6a9d130-0457-4dc4-aa9a-fc8f1b9a6df0 |  | note | HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
label | 343991da-c494-40b7-a180-af11b30fd8da |  | note | ---------------------------------
label | 5924c504-0d01-49e0-8515-541da3c52797 |  | note | METHOD: Visual
label | a242a03f-f9a0-4406-922d-ada84307828b |  | note | ---------------------------------
label | c2935f6b-4da2-4cd3-9966-890f342ce634 |  | note | FREQUENCY: Each Pit
label | cde3c90b-6e16-4d47-a770-d4f006afe741 |  | note | ---------------------------------
label | 19ac3f1c-b9f1-4f37-b70f-d05c700192ec |  | note | CATEGORY: IP
label | 8aa1ca34-5df5-45e9-be04-6c379d29c9f9 |  | note | ---------------------------------
label | e523ed2b-3383-4b0e-888a-9071d79868d0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 52454c89-e38c-4714-a5c6-3abef55ad21f |  | note | ---------------------------------
label | 8aa081d3-fbc9-4c4a-9837-dc78bcc32ee3 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 2507d887-8977-4b53-9ad0-0a593a03ed9d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.4 Draw Ropes
label | bf7b080c-86df-40b1-bdff-f5b41f5b2a20 |  | note | REFERENCE: VRIOGS 012.2.1
label | 866029c4-b312-4722-87fd-bdf240ffa7d8 |  | note | ---------------------------------
label | 6c327a67-2c35-4b3f-b0cf-e3d8a5ac3ac1 |  | note | ACCEPTANCE CRITERIA: The draw wire shall be continuous for the complete length of the conduit run.
label | d18cfc98-285c-4b4b-ac0d-22810c7654d5 |  | note | The draw wire shall have a minimum of 2 metres of slack within every pit.
label | 6363cbb9-94ac-41ea-ac8b-b2fb81909b53 |  | note | ---------------------------------
label | 6e41578a-d343-41a6-addc-13f2faa41a80 |  | note | METHOD: Visual
label | 2e8e1210-2036-4bfe-8d94-46a281f3ab13 |  | note | ---------------------------------
label | f3c4438a-2088-4e93-8675-40c54f3c7886 |  | note | FREQUENCY: Each Pit
label | cb8bbfda-65f9-4549-bbef-a8514f903e33 |  | note | ---------------------------------
label | 7fd6e24e-5131-43ce-a9af-ba70557e4a52 |  | note | CATEGORY: IP
label | ee34a976-792e-45b2-8fcb-34675f8e97d2 |  | note | ---------------------------------
label | fabb40e4-01ad-4022-9fc8-d24eb053c53f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | a73aa9e4-3528-4444-a8cf-fe1cf27bb16d |  | note | ---------------------------------
label | 276201d0-5eb0-4e5c-9959-040017a43ad1 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 7b186ddd-076b-4e83-a3f4-3e5c083103af |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.5 Backfill and Compaction Testing (if applicable)
label | dfc0122c-2f43-460d-ad0c-ddf5d5092314 |  | note | REFERENCE: L1-CHE-SPE-070
label | 9747c1de-4f45-47d4-ad1d-910b7ae7e69d |  | note | L1-CHE-STD-043
label | 18636d9d-300a-4b7d-ada8-f1e261a83ef8 |  | note | L1-CHE-STD-070
label | 24ea81bc-e8cc-4700-9f64-f5a4dc08ca5b |  | note | IFC Drawings
label | 1dfe85f9-8bec-4e3c-a399-905bdf3a6e8e |  | note | ---------------------------------
label | cb7e38df-6526-42c7-b6f7-d94721caaf95 |  | note | ACCEPTANCE CRITERIA: Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
label | 3786d3f9-c17e-43ff-9434-a02b53c758de |  | note | Sand within sand pits to be compacted in layers no more than 250mm layers
label | d11dc1ef-a470-4fe2-850c-00347a09c57a |  | note | Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
label | 26300b42-a4cc-4efb-bdaa-cc3c74000047 |  | note | ---------------------------------
label | 9f5f8497-f123-4b8c-bee7-c59d030dffcc |  | note | METHOD: Document Review, Visual
label | 952d940d-af51-4783-9ede-ca64312cf53b |  | note | ---------------------------------
label | 8a76a045-1e12-4230-90b4-6611e4d0e764 |  | note | FREQUENCY: Each Pit
label | 4383dfcc-a8db-4f59-98db-ad91b4b9889f |  | note | ---------------------------------
label | 55bc59c4-cbda-4715-bb57-507a0a22e742 |  | note | CATEGORY: IP
label | acad4d50-ac8d-4ba8-8aff-e27f8553fb72 |  | note | ---------------------------------
label | b16516de-66a1-42ad-9530-52bcb1c51a8b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e6ecf461-e381-4dd6-8fc2-0c0f0772381a |  | note | ---------------------------------
label | 63b291d7-f9a5-4a09-a41d-ca79891f7532 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Test Report
text | 7feebb85-d67d-4086-a6a5-6bd196462e77 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.6 Step Irons
label | 9ef94af7-8616-4869-87e4-85fc28651f04 |  | note | REFERENCE: L1-CHE-SPE-070_9.3.7
label | 59a39793-1ebe-4029-b746-7042da0ed338 |  | note | AS1657
label | e1a4af1e-88c5-4023-9f24-43f4f334a60b |  | note | ---------------------------------
label | 0a9eedd5-06e9-4c13-ba84-019ed09564d0 |  | note | ACCEPTANCE CRITERIA: Step irons/rungs to be installed if pit is greater than 1m in depth (including lid thickness)
label | 1324f0cf-bac2-45e7-aa13-4e5ca47fd5a5 |  | note | ---------------------------------
label | f1c35d03-a8b5-4bc7-a2bd-82ee08580214 |  | note | METHOD: Visual
label | e16996c9-2755-45b3-89c3-aa17ef801a1e |  | note | ---------------------------------
label | 716a6f22-a7f5-4993-ab62-74a1b0720216 |  | note | FREQUENCY: Each Pit
label | d0bc0f25-6e1b-43bf-b8aa-a98b658d09d0 |  | note | ---------------------------------
label | 86234b16-9f41-4811-8a3d-b7b2be56a605 |  | note | CATEGORY: IP
label | 1fed9edc-89cf-415f-a56d-2a58a3982982 |  | note | ---------------------------------
label | ca386e05-cd00-40e0-80b9-aec46f09e9d5 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c58b137e-bbf2-4dcf-9b1b-9a40b3e0bf9d |  | note | ---------------------------------
label | 311152d8-1729-4472-904c-9182ebae3df8 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 47711660-c9d4-4990-984d-4e3fdb7ddbe6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.7 Spare Conduits
label | 338ee08c-f9bf-45f6-876b-8e3bd067fbc4 |  | note | REFERENCE: L1-CHE-SPE-070
label | 7f1cc0f6-90ba-4b17-b335-e1c532c53a55 |  | note | L1-CHE-STD-043
label | a8059fce-d4c8-4e46-92db-2f9d06b62388 |  | note | L1-CHE-STD-070
label | d8448db1-d9cc-4b1d-ba38-6ae7d88a30d9 |  | note | IFC Drawings
label | 7e4736d5-10e6-4e46-b138-cfacc3e31e05 |  | note | ---------------------------------
label | 073b77fe-111d-4fb9-a7db-7dfe90c744d9 |  | note | ACCEPTANCE CRITERIA: Spare conduits to be sealed and to be included on survey report.
label | 5965bc58-f888-4acb-8ff8-eac58ea198af |  | note | ---------------------------------
label | 6dcf6cfb-0f77-49b1-84bc-901b030362f1 |  | note | METHOD: Visual
label | 91387028-9562-4720-8fb9-15aad675d072 |  | note | ---------------------------------
label | a8c99527-ed9f-4059-81e8-31e6ee681c53 |  | note | FREQUENCY: Each Pit
label | 0cfaf79b-440c-408b-9247-1f98e0b3a001 |  | note | ---------------------------------
label | 8bd29a55-c92f-4de4-b33e-9866e0dcb825 |  | note | CATEGORY: IP
label | 33e33927-b931-4d78-a415-8389b728432e |  | note | ---------------------------------
label | 0fe6f5f5-16a3-4dd9-8103-c30f2dd2f614 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 636fa8c2-349b-4ed1-85a0-c243885ad8a2 |  | note | ---------------------------------
label | 7d83700d-29f6-4ced-802d-88b29aa4175a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 034a5d94-2599-41f8-ab05-9c7e03de1c3e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.8 Pit Labels
label | 23506dc5-a465-4346-bfb6-1cf04711b7b8 |  | note | REFERENCE: L1-CHE-SPE-070
label | 759fdb97-78cf-4333-9394-1876e80b0bc1 |  | note | L1-CHE-STD-043
label | 185f8e77-0b19-418c-a4bd-4820cb04c2a4 |  | note | L1-CHE-STD-070
label | 9466eaa0-c51a-442d-ab09-ec079407aa6a |  | note | IFC Drawings
label | 835a6cae-6f18-4154-b2f6-8966698597d1 |  | note | ---------------------------------
label | 0a79cda6-13fd-4066-ab35-eb0a390f7df7 |  | note | ACCEPTANCE CRITERIA: Pit labels Brass Label (30mm x 150mm)
label | a12062e4-dc77-404e-b0b4-5cb136cd5734 |  | note | - HV: DANGER - Railway High Voltage
label | 5a5a6e4f-4f6e-4a0f-bb83-34b6772a9525 |  | note | - VicTrack: Victrack Comms
label | be64c675-1fe5-4ab8-ba7d-3f9e218654df |  | note | - Signalling: Rail Sign Comms
label | dee34e5a-c911-491c-8682-ec8451b2db15 |  | note | - LV Pits: Electrical
label | bbdc6a15-f8b8-4c46-8090-d27891030b06 |  | note | - Electrolysis: Electrolysis
label | f991db30-f9c5-4831-95a7-a45138c24307 |  | note | - SCADA: Rail Sign Comms
label | 7283b5e9-ce8b-4665-9b8e-6f05e634c3a0 |  | note | - MTM Comms: Rail Sign Comms
label | c8b205f8-ce20-4523-b778-40f73e5c8947 |  | note | ---------------------------------
label | 1550a349-8110-4c8e-a998-f02a4a83c5ea |  | note | METHOD: Visual
label | 5c21da2d-f91a-4c28-9737-7a10cdfe03b4 |  | note | ---------------------------------
label | 2d07ba18-e91a-4a22-8160-661c38d261d1 |  | note | FREQUENCY: Each Pit Lid
label | 0396ee8d-a781-495a-8807-9330f453930d |  | note | ---------------------------------
label | 77592f69-62e9-4718-ba61-e69388423572 |  | note | CATEGORY: IP
label | 05f2ff90-243d-46a3-8dea-b0e3045463b3 |  | note | ---------------------------------
label | 127a3d07-7955-45e7-819e-9dbbefa362b9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 48a6b121-21af-4abc-9b05-1e04c466400f |  | note | ---------------------------------
label | 4f8e4597-3a2a-4756-86c2-de7a55b133fa |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 4121b90f-b6f5-47a8-8868-c2d757d11539 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.9 Pit Numbers
label | 12d184e0-eed4-4bdc-b2e3-2bbd128df7e6 |  | note | REFERENCE: L1-CHE-SPE-070
label | d2850cc6-70aa-4c39-ac23-5bc8157a74a1 |  | note | L1-CHE-STD-043
label | 1cad8793-fc62-4812-abdf-942ee1c850af |  | note | L1-CHE-STD-070
label | 10607520-4447-443a-a543-a6f5674d87af |  | note | IFC Drawings
label | cbda36fa-2263-4dc2-96dd-a4b897c1a15a |  | note | ---------------------------------
label | e8a98be2-f73b-4ce8-a32e-14d6fc058d15 |  | note | ACCEPTANCE CRITERIA: Pit Number Brass Label (30mm x 150mm)
label | 49193567-086e-4330-9816-3ebd2d473aa7 |  | note | - HV (22kVV Feeders): ###HV
label | 728f1991-5ad4-420e-afa9-979b29c63133 |  | note | - DC (HV Feeders for OHLE): ###DC
label | 360f6450-7ab9-46a3-a783-f6dabbf899cc |  | note | - VicTrack: ###C
label | 7679106c-f94d-468f-abbc-8d39bb9b515b |  | note | - Signalling LV: ###SL
label | ec6e35d5-de68-4778-9055-82efe496ae06 |  | note | - Signalling HV (2.2 or 3.3kv): ###SH
label | 297bb9c1-12f6-42a5-b089-328c1f6815f3 |  | note | - LV Pits: ###L
label | fb35fa92-9c8a-46c6-a35a-8c53f29f58cb |  | note | - Electrolysis: ###E
label | d72ef8ed-1e9c-4170-b0ef-447aa0c46d2c |  | note | - SCADA: ###MS
label | 1ae04313-de21-4550-aa1f-1dccd85b3404 |  | note | - MTM Comms: ###M
label | 1ef51810-d77f-4c91-8926-6657c4e64694 |  | note | ---------------------------------
label | 184434a7-29c7-45c5-b9c7-1a86b239b007 |  | note | METHOD: Visual
label | 14fbb6b0-1c89-45c2-83ea-a7e2b97fd8c5 |  | note | ---------------------------------
label | 248f0bf7-2d5f-446f-8c06-21f11a52e796 |  | note | FREQUENCY: Each Pit Lid
label | 30562f97-b08f-4137-a3a9-f64168c3eefa |  | note | ---------------------------------
label | f4fb5b54-2551-4346-9989-0e56ade290d0 |  | note | CATEGORY: IP
label | 20e9cce0-2482-4109-aaf4-24fca962c4da |  | note | ---------------------------------
label | 81727477-b68b-429b-90fa-055e92b1b5dd |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cb68978f-91e5-4c1b-a2e8-69734cca920d |  | note | ---------------------------------
label | c65907a1-588b-4104-bc31-0028d2b2f120 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 603206e0-a656-462e-898f-aba98582288c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.10 Mandrelling
label | d6861122-caab-42ec-946f-58403fc852d9 |  | note | REFERENCE: L1-CHE-STD-070 Section 16.1
label | 8b4b6411-a135-48f9-bb21-0e6f5e1b5d8e |  | note | ---------------------------------
label | 24fc386f-51d4-4e7c-8d23-a09cf81ee0fb |  | note | ACCEPTANCE CRITERIA: The mandrel shall be solid, have diameter not more than 12mm smaller than the internal diameter of the conduit and be a minimum 230mm in total length and 130mm in flat length. It shall be pulled through every conduit in both directions by hand or with a machine to ensure their integrity.
label | 62615d48-531d-4375-a372-d2dc2ab3e9a4 |  | note | MTM/Victrack Witness
label | 1b139952-c392-482a-b2a6-eb03e5ac1d59 |  | note | ---------------------------------
label | ae223d45-7ed2-4623-a50d-8be75de250de |  | note | METHOD: Visual
label | 51685669-8b1a-4a19-bc38-36bd578f4981 |  | note | ---------------------------------
label | 6d89b383-25f4-46bb-9fcc-4a1536c40e89 |  | note | FREQUENCY: Each Conduit
label | ce18949c-30bb-4a49-ae86-ee68a9f23b5f |  | note | ---------------------------------
label | 18bcad4c-0fc4-40e7-9f1f-bd26a5117b71 |  | note | CATEGORY: HP
label | 4d977ad1-fb83-4d2b-a690-2ed2f034d6ce |  | note | ---------------------------------
label | a087dd93-2b10-4836-8556-31bced097253 |  | note | RESPONSIBILITY: SE, NA, MTM/VicTrack Rep.
label | 460cdf80-de5e-49a5-83a5-8562c1115105 |  | note | ---------------------------------
label | 05c99c01-712b-4184-9cd1-49485fdcd814 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 39f77d32-0acf-42a0-ab43-f3a09fa5f715 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Protection and Labelling
checkpoint-status |  |  | checkpoint | 10.1 Non Trafficable Pits
label | 6d80a3d8-4dff-40b0-ba13-da9a6ad9b1ad |  | note | REFERENCE: L1-CHE-SPE-070
label | ef362c14-d71f-4376-8722-bdfbbbcde231 |  | note | L1-CHE-STD-043
label | 60af9f18-52b8-458b-8f94-522871151af4 |  | note | L1-CHE-STD-070
label | 302acd0b-d3ca-4e09-b3d3-96270b91dc7d |  | note | IFC Drawings
label | 51125c7d-66c3-4c3f-a5e4-a7031cee7ab8 |  | note | ---------------------------------
label | 355b717c-7fe5-490f-b1b1-586c07228147 |  | note | ACCEPTANCE CRITERIA: Non trafficable pit lids to be 50mm above FSL and to have 2 x white bollards installed at the corners of the pit.
label | 03f36c52-4e0f-4452-b588-4ca346db60a0 |  | note | ---------------------------------
label | d5ff21f0-f490-41d9-aa97-37df00ed535e |  | note | METHOD: Visual
label | 3bfa13d1-f813-4c58-b43d-982056be2a23 |  | note | ---------------------------------
label | 4289404e-ff17-4678-b7b5-c7c393e31ae7 |  | note | FREQUENCY: Each Pit
label | 2cebc6ea-6b02-4818-beca-35a2fad7dd2c |  | note | ---------------------------------
label | 35ae7428-1e72-41ce-a799-6439d4a65590 |  | note | CATEGORY: IP
label | da81333f-d5c8-4538-9751-1aaca286b83a |  | note | ---------------------------------
label | 93872ec6-19d9-4ce5-b678-a5a2e66e7565 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 92acb53b-4881-4bcc-8e1c-96e509a0fdc0 |  | note | ---------------------------------
label | 7fe677a8-e0b8-4186-b70a-82897f018b42 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | fdff33e7-37df-4ad1-948d-de87c44cfe9c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.2 Sand Pits
label | adab6666-c5dd-4a74-b605-1bd7a81e6eed |  | note | REFERENCE: L1-CHE-SPE-070 Cl 9.4.3
label | 0742d1d2-85fd-45f9-810d-449ffd56511a |  | note | IFC Drawings
label | 8bc53ac1-710c-49e9-b05f-938de54df173 |  | note | ---------------------------------
label | 1ba44b2b-6129-4a1b-9f2d-2b0812649457 |  | note | ACCEPTANCE CRITERIA: Sand Pits (HV)
label | 1c974c1f-e5b9-4a3c-9d5d-92d6598c6788 |  | note | - 4x yellow posts installed at the corners of the pit and 2 of which shall have cable route markers attached
label | b06a765e-b239-4bdb-9e52-27e890b38e19 |  | note | - If posts are impractical, 4x monuments with cable route marker plates affixed and a cable route marker nearby indicating position of the pit
label | 640f1510-a16a-4a14-9336-1cf4c0ec96e3 |  | note | ---------------------------------
label | ba9a0361-ea0f-4c31-9646-648640768467 |  | note | METHOD: Visual
label | 69e82eda-fdae-4d3a-931d-b76c03410bdd |  | note | ---------------------------------
label | ad1ad12b-8691-4eaf-9a67-a40b6d152050 |  | note | FREQUENCY: Each Pit
label | 50d8387f-ff97-4aef-91a2-5680b604d335 |  | note | ---------------------------------
label | 8dcb7d48-7358-41c3-b405-65b667c56f03 |  | note | CATEGORY: IP
label | 5ece1615-1d7a-4a6b-8d8c-d10b045ebd60 |  | note | ---------------------------------
label | ebb3c73e-055b-4217-a363-2de09b24aac1 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4832c30b-72ff-42f7-ae5e-0c2378026f62 |  | note | ---------------------------------
label | 8590c546-f9f2-4f6d-902a-f93f0c7fbf10 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a3168b8a-574c-4c0b-94da-f499aa9776dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.3 Cable Route Markers
label | 50075fdc-a20d-46b0-8406-09a5b1e59678 |  | note | REFERENCE: L1-CHE-SPE-070_13.2
label | ca7e6470-b114-4020-bf75-7aa90ce5ed66 |  | note | STD_E0169 and STD_E0170
label | 02b31740-0274-4a62-9ffd-d65780a2b6af |  | note | AS 4799
label | d4d72b23-293f-445d-b234-2179dfdfe978 |  | note | STD G0003 and STD G0004
label | 52b8c719-450f-41e5-8045-838814b7f4fe |  | note | ---------------------------------
label | 912ab35b-291f-4fba-b6f4-da133ed1c8d4 |  | note | ACCEPTANCE CRITERIA: Cable Route Markers
label | 3bc4fbff-658e-4b65-8946-a0701fe72a3b |  | note | - points entering & leaving the rail corridor
label | c685444a-220b-4296-b250-996c7ce98f12 |  | note | - no greater than 100m spacing
label | 6bc2bfa9-a188-49d6-a509-d17914a391a2 |  | note | - Change of direction (more than 5 degrees)
label | 5426902e-ddeb-4950-ab99-8cea2c25b548 |  | note | - White posts with marker plates for conduit runs
label | ba7737cb-9299-4972-9a42-633dd89ddfab |  | note | ---------------------------------
label | f0813531-46cd-47d1-b9d8-1fc122a0da59 |  | note | METHOD: Visual
label | 8ed46a1f-943f-4081-97a1-c968ff3f064a |  | note | ---------------------------------
label | 16f95de2-2bcf-42ca-befb-16805f7871c5 |  | note | FREQUENCY: Per Cable Route
label | cd378a41-87d1-4474-b4d8-9fbd1eba786a |  | note | ---------------------------------
label | c0387de9-c402-4444-8ab6-69b586541f12 |  | note | CATEGORY: IP
label | 5f34e964-fe13-4d01-b142-bfebcaa3065d |  | note | ---------------------------------
label | f8a97d94-415b-4a30-a75d-38b4e487c7af |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8a829844-ddbe-40b0-b151-71479257e04d |  | note | ---------------------------------
label | 22e555ea-751f-4f93-92ad-68fc074c379a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e7c34a9d-7132-4551-a118-1d5744ce1cb9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Cable Route Handover
checkpoint-status |  |  | checkpoint | 11.1 As-built Survey file
label | 6d1a39ef-6efa-479f-87d3-9f2d8d69b383 |  | note | REFERENCE: L1-CHE-SPE-070 Section 13.1
label | 953de29e-ea2a-4cb1-9b54-a2d9ba4dbcc1 |  | note | ---------------------------------
label | 456e66ad-78ae-4593-9a70-2e959558accc |  | note | ACCEPTANCE CRITERIA: Survey report to include but not limited to:
label | 1a66d9e8-8f8d-4306-888d-08b6d6236f7a |  | note | - Cable joint locations.
label | 20d789e6-42e7-4dee-b1b0-cadc94055284 |  | note | - Cable pit locations (Corners)
label | f9992b55-acec-48f8-bcec-60b42633a35c |  | note | - Pit dimensions & pit lid type
label | aed6e1b6-f836-4ae7-a1c5-c93ab6bdc97f |  | note | - Under line crossings
label | 8d55dc8a-0f6f-43ea-9c08-020f361c41c8 |  | note | - Under road crossings
label | 2a67846b-6443-44f7-9768-81335c540e8c |  | note | - Changes of direction
label | d66f7a0a-e136-46d5-8d29-7d0358977495 |  | note | - Spare Conduits
label | 88dbe8a4-e969-44d6-892a-04f32a686ac7 |  | note | - Conduits labelled as per trench profile every 10m
label | f4a33658-0d15-4fe7-9ee4-067964a904d2 |  | note | - Other significant points of the cable route
label | 889db008-2cbb-4e18-b73a-4db298447226 |  | note | ---------------------------------
label | 1a78d49a-7b39-47c3-8ece-321b8d9a31ef |  | note | METHOD: Document Review
label | 31f95367-13bc-4d06-bfcc-93cc11c01275 |  | note | ---------------------------------
label | 0cc264dc-ab5a-41dc-8140-bf74dc1dd4c6 |  | note | FREQUENCY: Each Design Pack
label | bbfed3c2-324d-451d-9545-64415fc9b838 |  | note | ---------------------------------
label | 96518fa1-1fc6-4c69-97b2-aa43c8cfe175 |  | note | CATEGORY: IP
label | 17c8cb51-4639-4faa-9e44-d91bf55d1299 |  | note | ---------------------------------
label | a25ce71d-7988-4025-b95c-16a851b642f8 |  | note | RESPONSIBILITY: SE/PE
label | f4849e74-8c2a-4cf4-bdee-6bf9107d8cbb |  | note | ---------------------------------
label | b7ab2161-cb0d-46af-9396-7b506653807a |  | note | VERIFYING DOCUMENTS: Sign ITP Attached Survey Report
text | 201a84fa-2db4-49e3-8a8c-ac06a769644b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11.2 Engineering Redline mark-up
label | 9c0d7c80-c7c8-4645-8f7d-51d0dfa7c876 |  | note | REFERENCE: IFC Drawings
label | cf468cf1-57e1-419b-ac7f-edc847a7fd09 |  | note | ---------------------------------
label | 28b8fcfd-a17e-4118-a634-925293983d51 |  | note | ACCEPTANCE CRITERIA: As constructed cable plans shall be provided for the entire cable installation and in accordance with AS 4799 and the PTV Infrastructure Drafting Standard.
label | c13b2675-6dc7-4a34-92d7-aec8d9593d73 |  | note | ---------------------------------
label | cf3931b9-6a4e-416b-8b10-86bd0d5549d1 |  | note | METHOD: Document Review
label | 6859dba0-f516-4962-a717-c449fc6d4063 |  | note | ---------------------------------
label | 4e462861-7940-49b2-8c4e-3388919612b0 |  | note | FREQUENCY: Each Design Pack
label | a6ffcc0d-c9fd-40dd-a122-b42ba23db8b4 |  | note | ---------------------------------
label | 933383ed-c029-4463-8987-6ebe675af473 |  | note | CATEGORY: IP
label | 79613198-1773-4d07-8eba-9577e4873b00 |  | note | ---------------------------------
label | 98dad112-85dc-4299-99e9-ab0ccebe8330 |  | note | RESPONSIBILITY: SE/PE
label | efc099f5-1a31-46d6-9006-fce216535268 |  | note | ---------------------------------
label | 76f425ea-3413-49b0-8832-4f784f3f6162 |  | note | VERIFYING DOCUMENTS: Sign ITP Attached RLMU
text | 581b5be2-0a25-4086-9a54-b0a68b7c16b1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Cable Pulling and Terminations
checkpoint-status |  |  | checkpoint | 12.1 Cable Pulling
label | 01d2289b-51b6-4a4b-b395-b7b25a860f82 |  | note | REFERENCE: L1-CHE-SPE-070
label | fdf9d9a6-e5bb-42b5-91c2-6a0ac69ef670 |  | note | L1-CHE-STD-043
label | 86b2c6be-0241-4d60-b801-17ac1a153131 |  | note | L1-CHE-STD-070
label | 3dbad0ff-cbd6-4900-826a-cc6e353f9f60 |  | note | IFC Drawings
label | c5b7eec0-e1a5-4968-804f-3b9faf58cb7f |  | note | ---------------------------------
label | fe5f3d6f-7621-4779-a415-af6f0c5404c9 |  | note | ACCEPTANCE CRITERIA: Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
label | 7256527a-a35a-41eb-9746-d5979638f955 |  | note | ---------------------------------
label | 3ac5ecc1-f5b2-4d48-a215-630647cddaaf |  | note | METHOD: Visual
label | 6dc2c94e-d722-48a2-b7b7-a618b1600349 |  | note | ---------------------------------
label | 2f77914a-5b48-41df-8ae4-fac1d31ac869 |  | note | FREQUENCY: Per Cable
label | b63d77bf-2fb3-4ef2-ae9a-3ea77233d669 |  | note | ---------------------------------
label | 64dc3b1d-879b-4656-b86a-2ef75a640700 |  | note | CATEGORY: HP
label | 625ba395-e77b-4d12-8cd3-64b5966ceedf |  | note | ---------------------------------
label | e4cbe09b-e8e7-45e4-a48e-dfd34c3d1a38 |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | ed725d88-0ff7-4042-99d9-a60311880c01 |  | note | ---------------------------------
label | cf967afb-4a33-4b7b-a4ce-1b5368b42af3 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c6c37bf5-7768-48fd-9f25-dbf50597b947 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.2 Cable Labels
label | 89221f50-6d0d-4460-a98a-bfac64dedd6c |  | note | REFERENCE: L1-CHE-SPE-070 Section 13.3
label | d4735b98-0b3e-4cff-9b5f-6f105bf23f06 |  | note | ---------------------------------
label | 3df40d57-919f-4789-9366-5d2dcf252db8 |  | note | ACCEPTANCE CRITERIA: All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
label | f9822f74-70f3-49c5-8157-1875d5ccff8e |  | note | The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
label | ea962610-0bed-4506-a22d-6377683b95fd |  | note | ---------------------------------
label | 7f832110-57d1-4a11-b44c-7a1945e22d12 |  | note | METHOD: Visual
label | e073472b-a247-4997-9ceb-deede2934b50 |  | note | ---------------------------------
label | c132f06e-3546-4883-a84d-35edd822a279 |  | note | FREQUENCY: Per Cable
label | 5705d779-3e27-4f60-8d91-6da2be4e296d |  | note | ---------------------------------
label | b066c9cc-8da9-436f-a9b5-acd1890ca635 |  | note | CATEGORY: HP
label | dbc626fb-6352-49c9-8fd4-2be79d7b996b |  | note | ---------------------------------
label | 13a3c712-1510-4205-90b7-3dbff3ad6360 |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | d37de3cb-0a4c-4b1e-b58a-365449aad7e9 |  | note | ---------------------------------
label | 454e741f-90f1-4d0c-952c-62113838e187 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 79c33282-99a2-431e-9d66-e603c873a6b0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.3 Cable Joints
label | 660eb9e0-66ff-4c82-8ef0-06806b05c0c0 |  | note | ACCEPTANCE CRITERIA: Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
label | 14310201-9a8f-44a8-880f-118fcd8419b1 |  | note | ---------------------------------
label | b908e835-d092-4fbe-8037-4991e7ef956f |  | note | METHOD: Visual
label | 2925be6a-ffec-4c80-b177-6ef1eb64dc69 |  | note | ---------------------------------
label | 23089e94-cdd7-4f8f-be1f-1df276642aca |  | note | FREQUENCY: Per Joint / Termination
label | cf91141a-1725-4b43-8d86-4bc47a34d02b |  | note | ---------------------------------
label | 72b621bb-ef63-4bff-9793-793119be4a07 |  | note | CATEGORY: HP
label | a5d54e5a-45b2-468e-9567-95826259629b |  | note | ---------------------------------
label | 7c556c98-c1fe-4b8c-b93d-ba1811a3d3fc |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | ce79a753-9869-41c8-9531-b887066f2be8 |  | note | ---------------------------------
label | 74d398a2-0c65-45d7-8eb7-08c69a9dd809 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 1982c784-c759-4a4f-90cc-35a390aff2b2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 13.1 Handover Check
label | c8fa2569-2373-4e3d-8f9c-0e667f90d096 |  | note | REFERENCE: IFC Drawings
label | e629715e-6995-486a-af81-0a91cac7e419 |  | note | ---------------------------------
label | d62c0bba-6fbf-4c89-8336-88823f4b40bc |  | note | ACCEPTANCE CRITERIA: Handover check completed for Testing and Commissioning.
label | f7bf747b-230c-460e-a331-22798733da0f |  | note | ---------------------------------
label | 3d49927f-e877-458c-ba13-a771670f582d |  | note | METHOD: Document Review
label | 8043bdd8-7c40-4410-8812-f14846e23a2d |  | note | ---------------------------------
label | 6fab8930-6618-46bb-a8b3-98c92cd4b79a |  | note | FREQUENCY: Per Lot
label | 8a5d2f6f-3dcc-42a0-aab5-304034fbcfd6 |  | note | ---------------------------------
label | a0bffdfe-171e-4c07-b72b-6b11c188092c |  | note | CATEGORY: HP
label | 6ce9c339-722a-49a5-aa16-6697075f5efc |  | note | ---------------------------------
label | 80485dfd-f9e3-4962-80f6-d8b05e31c570 |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | b3608c6d-e372-47a4-886d-839f7e7b94d6 |  | note | ---------------------------------
label | 5c4b7ed0-0d41-47b2-8b09-ac6bc543ac6f |  | note | VERIFYING DOCUMENTS: Sign ITP Attach MTM/Vic Track Check Sheet
text | a5ca3c65-f630-419a-bcc0-cda3afc34496 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 Testing and Commissioning
label | c6b05eaf-520f-4645-ab67-a7b372972d1c |  | note | REFERENCE: IFC Drawings
label | fd8cdcde-42a9-421b-9840-041e62fa16fa |  | note | ---------------------------------
label | 503082ff-c3df-4871-b8ff-83693916aa48 |  | note | ACCEPTANCE CRITERIA: Testing and Commissioning to be completed
label | a621c263-3768-4297-ba5e-f9532bfb98f4 |  | note | ---------------------------------
label | 2f97eea2-1f73-412a-9461-d88e9d2a27a4 |  | note | METHOD: Document Review
label | 6fa3ebe5-dcbd-48a9-a96c-10e88af233c2 |  | note | ---------------------------------
label | 88b3eb45-113d-43d4-acc2-0e142e9c4160 |  | note | FREQUENCY: Per Lot
label | 66b6502d-e3ed-4141-a824-5c97fba28e36 |  | note | ---------------------------------
label | 83c7fdfe-2658-4ad8-b0b5-6269182a468d |  | note | CATEGORY: HP
label | 5f5a39bd-2f23-4433-8c3c-2090ee4f8b05 |  | note | ---------------------------------
label | f7d98061-aed2-4b94-90f4-abc6b7f76ddf |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | c3f7535d-a454-4157-91c9-5396eec10c3c |  | note | ---------------------------------
label | 0e545e45-38f1-4d5f-805e-f2fd80479aeb |  | note | VERIFYING DOCUMENTS: Sign ITP Attach T&C Report
text | f5f7ffb0-062e-461d-97d4-ab331c1360ed |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | a7faa9e2-710e-42c0-88aa-c898386335aa |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0dc426dd-66c8-455f-85be-3dd4d809fa2c |  | textbox | Name:
text | c96a5e19-35fc-4cd5-98b6-a762e6df64a2 |  | textbox | Position:
text | 2a856638-b687-46e6-a6d4-b0fed316bbd9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | itp |  |  |  | Yes | ITP-CIV-Subsurface Drainage (Supply and Install) Rev 1 | 2c8c9acc-b847-4f53-b68c-a6562637d306
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 3c018061-82c0-496e-a4b9-eac70bc371e7 |  | note | Document Title: ITP-CIV-Subsurface Drainage (Supply and Install)
label | 790eb939-670c-489e-8f76-33e2c3e6cdb1 |  | note | ITP Description: Subsurface Drainage (Supply and Install)
label | 01dfa365-a4eb-4c45-9613-61eb72bb0785 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | cdf5c38e-9ed3-4f50-85ac-159c273d369c |  | note | Revision Number: 1
label | 2d797de5-d9bf-4053-a06f-38a97cfae59d |  | note | Revision Date: 11/09/2020
label | 95e5f4ef-4f9c-4c6a-8cb7-ec45198ba919 |  | note | ITP created by: Josie Pavlou
label | 226dffb7-5de3-4157-a37e-71507081fe5f |  | note | ITP approved for use by: Michelle Edgar
label | 30c9ee35-d942-4c3f-a212-a2cca301882b |  | note | 1.1 VicRoads Section 702 (May '19)
label | 7a28a3d1-8b15-4be5-b685-e498410cc801 |  | note | 1.2 VicRoads Section 204 (Dec '15)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Check for correct documentation
label | e3711645-7a16-4d08-8086-8fd7bd1f9226 |  | note | REFERENCE: Drawing and Drawing Register
label | c528f783-dd00-44c2-bd61-6621462f18a6 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | a56d7f9a-335b-4555-bf1c-c6ede7a59c8a |  | note | Using the correct and complete set of drawings
label | e03d2af9-0982-42a2-8bf3-bb1ee6b7373d |  | note | All drawings are the latest revision
label | 720c764b-da12-4d6e-95b4-9f09e8b04f3b |  | note | METHOD: Visual inspection
label | 4d338e51-dca3-4c42-8848-81d179258ecc |  | note | FREQUENCY: Prior to commencing any activity
label | c577e0d8-4f9e-4631-8b5d-9902d14a784b |  | note | CATEGORY: WP
label | b203c1a3-1eb9-40f2-95a2-e5cabca8394c |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1da2d96d-6016-413e-aec2-9119008de44b |  | note | VERIFYING DOCUMENTS: This ITP signed off
text | e09fcebb-b0d2-46f7-bf7d-52624dfb8904 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2
label | 49096da3-d20b-4a37-a50b-e2b5c98435c8 |  | note | REFERENCE: IFC Drawings
label | 0e65f153-3a1b-49a3-a57f-cc3d3975af7c |  | note | Section 702.04, 702.05 & 702.06
label | 3fba28d2-7f02-45f5-9e7f-eae41c4f1fca |  | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes:
label | 8510277b-cf65-446a-8cd3-9e3a33ffb162 |  | note | Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | 6b0435fb-9e03-4432-9e98-887b621baa49 |  | note | Granular filter material:
label | 8ea57a68-da9a-427b-b1cb-d1ed609f96ac |  | note | Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
label | ec8ac6ec-85c0-49c9-9bd6-a4e58f828db9 |  | note | No Fines Concrete:
label | c094cd3c-252e-481c-a5f1-659ef4583669 |  | note | Shall comply with 702.05 e)
label | 8b9b790e-b749-4038-bac8-c161587bc138 |  | note | Geotextiles:
label | 86359956-7766-4851-a722-3bb10bc2378d |  | note | Shall comply with 702.06.
label | e50193b8-8385-406d-848e-d3906f02516e |  | note | Subsurface drain pits:
label | 85c80531-d8d0-4896-a6bd-5d6c98a6eb5e |  | note | All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | 72755cc8-154f-4b66-8719-2d2e685ae9a9 |  | note | Pit Lids:
label | c7057345-118b-4cad-ac6b-fb049d8ff6de |  | note | Type M3 circular lid (as per SD 1051) for Type S1 pit
label | 2a3f0792-c4ce-4120-88b8-605f8565bbbe |  | note | Flushout risers:
label | eff94199-f337-49ea-9cd9-fb731dc3347a |  | note | As per SD 1631
label | 952c8f0f-d120-4e85-90c5-a1b0d7dda2d6 |  | note | METHOD: Verify, Document Review
label | 514ffe78-b512-4555-b673-4c25bf019244 |  | note | FREQUENCY: Each Lot
label | 4f61fe75-97cf-46df-a882-99e1e8eeee96 |  | note | CATEGORY: WP
label | 5ada8afe-c77a-4c53-b203-42c4112dee23 |  | note | RESPONSIBILITY: SE
label | 558d97a3-33d2-447d-bbd8-16a8d4a5f28b |  | note | VERIFYING DOCUMENTS: This ITP, Material Conformance Certificates, Team Binder Material Approval No.
text | e08e55bc-8222-4ff0-8856-4dcdad4c688a |  | textbox | Text Box: Insert Team Binder Approval No.
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set Out
label | 82784c1a-46d9-4b1b-a2c9-bd36d7ebb82c |  | note | REFERENCE: Section 702.03
label | 8e780fa7-055d-4e1c-8428-5c9330df6355 |  | note | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
label | 9f0b3422-4922-425f-85fd-25cca33dd421 |  | note | METHOD: Visual inspection
label | d913c571-163a-40f5-997a-e8253702a106 |  | note | FREQUENCY: Each Lot
label | 74992344-fb7f-4a51-a75f-98199338a7da |  | note | CATEGORY: IP
label | e1159c2b-0ade-46f6-9094-9f3723503d1e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 62111314-8a97-4d14-94e4-06298a21bfb6 |  | note | VERIFYING DOCUMENTS: This ITP
text | abb483a7-4f26-4006-aec5-ff163d073c54 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Trench Excavation
label | c7799003-87c5-40b6-9558-cf0ce816729c |  | note | REFERENCE: Section 702.08
label | 414d04b5-2f80-4c28-b3ec-1b160332030a |  | note | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | 084532ab-68f0-4fa5-b74d-a82035dd44f7 |  | note | There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | 62dd2dc0-573a-4ab2-affc-e1690a5225d9 |  | note | Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | 07440c3b-153d-48b6-90f5-252defe765a1 |  | note | METHOD: Visual Inspection
label | 5c3137e9-3689-454e-a005-917a266ab3b7 |  | note | FREQUENCY: Each lot
label | fe30ad11-bfa5-44fc-b8c5-88d0ef253087 |  | note | CATEGORY: HP
label | 0c9221dc-eec1-41ee-b594-6ef1c5dc4934 |  | note | RESPONSIBILITY: SE, NA (Nominated Authority)
label | c0c3d684-8e90-48a2-93b9-360707981fd6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 401b40df-e7c3-48f2-9ed3-a5778eef28aa |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Placement of bedding
label | 4a7fc11f-cd24-492c-8fba-4da35d0a8a6f |  | note | REFERENCE: Section 702.09 c)
label | be151651-4981-4c2d-a9c3-f3893d7b1836 |  | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | 60d0442a-fdff-493c-b48a-f1582dd1980e |  | note | METHOD: Visual inspection
label | 9503dab2-841e-4201-9084-b70d34b974a6 |  | note | FREQUENCY: Each lot
label | efef9d1d-40ec-4471-8e33-1c2a39add401 |  | note | CATEGORY: IP
label | 80dfb8aa-7ff2-4b72-adb9-e655608ecae9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 78bd541b-e752-4916-9940-4ee6bdc3b053 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach bedding material delivery dockets
text | d21f3b8c-fad0-4bbf-9041-1394d7c2e060 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Pipe and Geotextile Installation (if required)
label | 46ee0f14-d251-411e-a278-b3e8ed913806 |  | note | REFERENCE: Section 702.03, 702.09
label | b4af9681-ed9d-4a0f-a965-5559d8be6cdc |  | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
label | b1e33b4c-c057-4153-b7c5-83b09be8a96c |  | note | METHOD: Visual inspection
label | a0b00ca2-cad4-453a-b03b-d657c3f877e2 |  | note | FREQUENCY: Each lot
label | daad278b-d924-4fc5-99f3-55cd95861ae2 |  | note | CATEGORY: IP
label | 30d77a0e-2f21-4b66-bacb-afdfc860499e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7d3580c5-ed56-4c23-8c36-95603a47c818 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Subsurface pipe and geotextile delivery dockets (if applicable)
text | 9f49f297-b231-4eaf-a56a-6f4bfb5478a3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Backfill Installation (Granular Filter Material)
label | 4132a64e-dd82-401f-a309-f8dfb055c515 |  | note | REFERENCE: Section 702.09 (g)
label | 7c2112c7-b4de-464a-972f-04f5220b0882 |  | note | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm.
label | 232695b0-c924-497b-b8ae-3d444950c745 |  | note | The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | 7c01cd5e-d0ba-412f-8ed1-d1e8d697db76 |  | note | METHOD: Visual, Doc. Review
label | 8bf2e6fe-4bc6-4d20-9a06-f0c7c0b9e447 |  | note | FREQUENCY: Each lot
label | 5ed347ed-389c-47e1-a3ea-f828ea97d21c |  | note | CATEGORY: HP
label | 8c45dcda-47ca-45a2-ba93-ff8afef8ea76 |  | note | RESPONSIBILITY: SE, NA
label | 644d1afc-634d-40e4-9733-797c8128905c |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Backfill Delivery Dockets
text | 4699dec7-1d0e-4316-9499-b9964dd1e785 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 Backfill Installation (No Fines)
label | 52f2bbe4-0099-4976-88e1-b9a6b6f78c7c |  | note | REFERENCE: Section 702.09 (g)
label | c1c46323-975f-402d-8d73-fb0a262ef2c4 |  | note | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
label | ea1ed365-28c6-4a0a-9f81-1e09bbbce181 |  | note | METHOD: Visual
label | d6fd22c4-d73e-4f37-abd2-d2bc165b54c1 |  | note | FREQUENCY: Each lot
label | 201813bd-4f5e-4a26-8865-5322f4c5768d |  | note | CATEGORY: HP
label | 90617d8d-17ab-4532-a812-026d7101a7c1 |  | note | RESPONSIBILITY: SE, NA
label | 9a33067b-cba8-46a4-852b-c142b83bfc16 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Backfill Delivery Dockets
text | 78e78252-a885-40fe-9ad0-31b5a2cab956 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 Install Pits and Flushouts
label | 58b9ed6c-4492-49e8-b3e4-8b55286ba2f0 |  | note | REFERENCE: Section 702.10
label | 26d25e37-aa64-4374-80de-13fc94996be3 |  | note | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | b04667ff-81b1-4456-946d-30e142c3b1c8 |  | note | METHOD: Visual
label | c3d2eaea-c68f-4c39-89c9-4481617a5196 |  | note | FREQUENCY: Each lot
label | 8040a17d-fdff-4d06-9d2b-732db222555c |  | note | CATEGORY: WP
label | 1fe20e55-5238-4c9c-919b-2f7a85e2131f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 55d45292-df86-4714-953e-71d69f8c78b7 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Pit and Flushout Delivery Dockets
text | b4c92aac-de0b-4962-90af-16bde2d8be08 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Marker Points
label | 74ad540b-6c04-4f17-bd95-1e484d948942 |  | note | REFERENCE: Section 702.11
label | 2eeecf2c-5b98-4eb8-9543-7eb564a5ab51 |  | note | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | bb2410fc-28ce-46f9-95ca-117261c02517 |  | note | METHOD: Visual
label | 198b393b-9b76-4b9e-92ff-0c8373a8d6b8 |  | note | FREQUENCY: Each outlet
label | fe98e145-6c94-496d-9c9d-a3debc1834b9 |  | note | CATEGORY: IP
label | bbe168dd-d7ea-478f-9710-88b47cfc4319 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8723738b-931c-40d1-a43e-201a786e046b |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Marker Post Delivery Dockets
text | ac46c735-cda0-49c2-8f55-c8b5c68119fd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Flushing
label | 99ba903e-2d68-4333-b9a1-fc157a112f04 |  | note | REFERENCE: Section 702.09 (h)
label | 064ae60f-f2fd-481a-b5d2-eecd53fc1197 |  | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | 85347770-0afd-4e9d-b5a8-4405b6705a96 |  | note | METHOD: Record Review
label | 19729922-5218-4774-9ba4-e62309a073da |  | note | FREQUENCY: Each lot
label | b85f98d2-2414-4a1b-b265-7a9f5e944809 |  | note | CATEGORY: HP
label | 1b2cc03c-e535-4298-a6f7-eba074781b71 |  | note | RESPONSIBILITY: SE, NA
label | 43f7a915-6d17-4082-8ffd-975ab73f2483 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Inspection record
text | 4fd8e163-6b25-45fc-8c47-0d2362bcff55 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.9 CCTV
label | d773cb29-e080-4c01-8d95-4b4fc5806b78 |  | note | REFERENCE: Section 702.09 (g)
label | 1464d8fb-30ac-40b3-a24d-528a94aa4458 |  | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
label | edcf9cbd-0333-42ae-84c7-ad488334d8ad |  | note | METHOD: Record Review
label | 2e7a0168-0648-47e7-a5c1-784a047b9dee |  | note | FREQUENCY: Each lot
label | 51cd2fdb-1720-4869-a4c3-4f9310a694c6 |  | note | CATEGORY: HP
label | 702da0a7-0767-4de6-adb1-4a560fbafb91 |  | note | RESPONSIBILITY: SE, NA
label | 9f7b44b7-97ac-4a18-9593-c90e974e7494 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Inspection record
text | 063f4e90-cc21-48b3-8304-85d3cee4d079 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 As Built Information
label | 19d23dd2-9000-4fdd-b90c-dc392b1652da |  | note | REFERENCE: Section 702.03
label | 98884de2-49e9-4ebc-acf8-62663e2c110b |  | note | ACCEPTANCE CRITERIA: The invert of the subsurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | 1408f082-52c0-41e5-aa80-2d31285f77da |  | note | Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
label | 31223f3e-1d6f-41e8-b494-08075468e442 |  | note | METHOD: Document Review
label | 06015a87-3fc6-45f3-a4f8-36a285a235d6 |  | note | FREQUENCY: Each lot
label | 7e92c9ee-e892-470e-9769-a56c6c2abce8 |  | note | CATEGORY: IP
label | 343beeb3-63cb-437d-bbe6-b638851554b2 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | a12e5d6c-247e-4101-a3f5-6b46058ac881 |  | note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
text | c8189d4e-c6de-4a5d-aad6-388ef17ab8f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 58dda066-6f1f-4d5f-9966-210a0263d01d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d7992670-75dc-41de-81c2-0ac5f0b72acb |  | textbox | Name:
text | 4c946b09-e726-45cb-aa6e-45ed2cb4801c |  | textbox | Position:
text | cd0a8f67-42ac-48cb-871e-de80511ee663 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-Rail-Sleeper Replacement Rev 0 | itp |  |  |  | Yes | ITP-RAIL-Sleeper Replacement Rev 0 | 33586639-a59c-42b9-8d9b-1349188c6cd3
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | f85afb82-2c77-48a3-80ad-1385df535475 |  | note | Document Title: ITP-Rail-Sleeper Replacement
label | bf14dcf4-1770-46d5-b8b8-5a8b15e664b5 |  | note | ITP Description: Sleeper Replacement
label | 4701075f-78e1-41bb-9bcc-cb27a515379c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
label | 683bef8f-8ed1-4eb7-8470-95d48dc75901 |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | 1eb4b477-ec59-434d-ad29-506c85b57a1b |  | note | Revision Number: 0
label | 5b780ed2-7adb-46e4-ac12-ea958880fc0f |  | note | Revision Date: 30/07/2020
label | 77ad4e3c-5f55-49a8-902c-46057b3d6c35 |  | note | ITP created by: Mathew Holm
label | 5051adcf-2e3a-46a1-ab58-761b55823e79 |  | note | ITP approved for use by: Romualdo Magpantay
label | 9ea629ae-b9fe-4b3a-a94f-705c56478b27 |  | note | 1.1 L2-TRK-SPE-003
label | dbdefe78-851d-49cc-9148-c8cc045caf7b |  | note | 1.2 L2-TRK-SPE-004
label | 7a00c3be-d6d6-45ec-8f5e-822fe09e1ecc |  | note | 1.3 L1-CHE-SPE-003
label | 2c2e91c4-70f3-4142-ac26-8d1bad1d7021 |  | note | 1.4 MTSP 030100-01
label | babac4e2-a185-47bc-84a2-5756de0cc0a7 |  | note | 1.5 L1-CHE-SPE-316
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain and submit Material Certificate of Compliance for sleepers & ballast
label | dfdb0fe4-0ad9-415d-bc32-a50897f41e09 |  | note | REFERENCE: L2-TRK-SPE-003
label | 6ed5a74c-a39d-49d5-95d7-8071805ff900 |  | note | Material Design Drawing
label | aed3c449-e876-4d7e-b089-2445fd4f72c3 |  | note | L1-CHE-SPE-316 9.4.6
label | 1cec4e69-3d5e-4332-8e0b-a97e167a33e3 |  | note | L1-CHE-SPE-064 Ballast Supply Specification
label | 203c2256-b442-4dc4-9031-1c28308d88e4 |  | note | AS 2758.7
label | 024637f3-80ab-4a5a-aab1-44aebc86429a |  | note | ---------------------------------
label | c110b071-8202-4a0d-a3ce-fcfdffc312a4 |  | note | ACCEPTANCE CRITERIA: Verify Sleepers to be in accordance with MTM standard.
label | bb791ae4-2c55-44d4-aad1-fd558e84e322 |  | note | Sleepers with defects not be to be used for tracK construction(free from any damage).
label | fc2f72d9-675b-4b01-904b-191484462c46 |  | note | Concrete sleepers supplied shall conform to the testing requirements as specified in AS
label | 88217b20-3c90-4df3-a42f-20c84933ee22 |  | note | 1085.14 Prestressed Concrete Sleepers.
label | 9542fef2-5fc8-4e62-9b98-bbf8acd7a816 |  | note | Verify supply ballast material (if applicable)
label | 596849e8-b9d0-495a-9a8f-96baef84f1c5 |  | note | Attatch: Photo Sleeper & Ballast
label | 7847d7ce-6964-421f-a28b-26f3efd2fcd3 |  | note | ---------------------------------
label | 64b4dc9a-ffa4-4963-8df9-aaad1a63a8e6 |  | note | METHOD: Review
label | 06dc142b-1959-4fc9-a9c3-2c632631b859 |  | note | ---------------------------------
label | e3e8bd2f-d432-4ccb-a5d9-6023435b769a |  | note | FREQUENCY: Once
label | 7b9ed2ac-2a2d-4151-ab30-e95f2e1f1e46 |  | note | ---------------------------------
label | 28f06742-e235-479b-a5b5-df3e1ed0bdc2 |  | note | CATEGORY: HP
label | 2ec987b6-db1f-4b91-be82-e5913de89283 |  | note | ---------------------------------
label | 014db9d7-687c-46e4-be48-f4812982e0ce |  | note | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
label | 17cfa5bb-4ba9-41d0-acfd-257827355a5f |  | note | ---------------------------------
label | 3bda576a-7162-4293-ac0a-09b35949b7fb |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c4411409-2591-40ce-8e4a-ccbf8bc5dc41 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Obtain and submit Material Certificate of Compliance of new (Rail Jewellery) fastening assemblies
label | 594b5d86-9a8e-46e3-9553-1cc0e4c82bdd |  | note | REFERENCE: L2-TRK-SPE-004
label | 688162d0-79c0-483c-b832-024bcb1c338b |  | note | IFC Drawing
label | 8a3c6e1e-4fe1-4253-94e7-8e6b30279be1 |  | note | ---------------------------------
label | 31d9b01f-4940-4304-9e79-c3a0d460b994 |  | note | ACCEPTANCE CRITERIA: Free from damage and supplied in accordance with MTM specification
label | e130c636-31a6-4287-8f97-fa0ce04ff377 |  | note | All fastening assemblies may be subject to inspection by MTM, or their nominated
label | c97ede34-de00-4587-aaca-4f6794278a8f |  | note | representatives. This may be undertaken at the manufacturers, suppliers, and/or
label | 3b800b9e-753c-41d3-8d27-b0b5448be328 |  | note | sub-contractor’s works facility or point of delivery to ensure conformity with this
label | 4cdb3bee-482f-4a89-a19f-dd1eba02c73d |  | note | Attatch: Photo Fastening assembly(Rail Jewellery)
label | 8fc9ec93-264d-4fa9-9157-739df5775e12 |  | note | ---------------------------------
label | 50fcd5d3-17ec-4371-b6e3-4254c11d0816 |  | note | METHOD: Review
label | e9d1a335-1e28-4b34-9a3c-a798448dc62b |  | note | ---------------------------------
label | c5bdc7c5-6370-401e-af8f-522654cf594d |  | note | FREQUENCY: Once
label | ea6a1c06-6ad5-4b98-80eb-3972ec192779 |  | note | ---------------------------------
label | 383a41fd-8b0a-4d40-bce2-e73ce6a11096 |  | note | CATEGORY: HP
label | c75d8bf6-36ce-42fd-be01-4f770b2977a6 |  | note | ---------------------------------
label | e4af9669-eb56-4fa4-8c3b-278f5d41784c |  | note | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
label | 99f0f000-525c-45c7-bd96-eac04ff21365 |  | note | ---------------------------------
label | 806b097a-161a-4a40-b7b0-4160c2618663 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 242ef9bf-3415-48cd-848a-9a3a0684a93f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Inspect supplied items upon delivery
label | f4a04fff-c2e3-40c6-b5d7-a25fe54b0799 |  | note | REFERENCE: IFC Drawing
label | e4c5eb27-4fa3-49e4-b73e-c5267350f58c |  | note | ---------------------------------
label | 05dea1d1-b685-453d-848e-1f1a51718be8 |  | note | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
label | 8e0af55b-1917-4cd0-898f-83986ecde787 |  | note | ---------------------------------
label | 754ab233-a6f4-4fef-beef-e084c49c46df |  | note | METHOD: Visual Dimensional
label | 6ef33f28-3aab-4035-a3fa-c545b09eb582 |  | note | ---------------------------------
label | de1b3e06-37aa-4aa9-9a48-4e14f786c6d3 |  | note | FREQUENCY: Per delivery
label | afb95445-3196-4646-873b-22b860263fa1 |  | note | ---------------------------------
label | 8afbcc3a-46de-4d16-b3dd-e64e26d040e7 |  | note | CATEGORY: IP
label | 7f2a0f93-d632-41cb-aaf0-b3faccfdbf87 |  | note | ---------------------------------
label | b0abf8c7-dfb3-45d5-aeda-3d6d1c6a5978 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 0b726337-c01a-4ef6-8552-1a186591ff0d |  | note | ---------------------------------
label | cb9b19e3-5ab8-41d7-b73b-9799bb603584 |  | note | VERIFYING DOCUMENTS: Material Inspection Report
text | 7c6aa2ed-b27d-475c-bbb3-1e85c3d5ad39 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Removal of Existing Sleeper(s)
label | 9201b5b9-cd13-42f5-98dd-dbc28a97d9bc |  | note | REFERENCE: IFC Drawing
label | d2db3333-e0d9-4d49-8321-224f7c7c89e7 |  | note | ---------------------------------
label | 1e88e527-f1ab-440d-852b-3f9134c3e902 |  | note | ACCEPTANCE CRITERIA: All Jewellery is removed from rail/sleeper by use of approved rail tool
label | fdb6e221-952d-474e-a104-428945ba4066 |  | note | Machine operaotr performs "side removal" technique to remove from track
label | c8d506de-0aa5-48fd-91b8-4e807bc1ffbe |  | note | No contact with adjacent sleepers
label | 4944eb54-8e46-48c2-be4e-9033d390294e |  | note | ---------------------------------
label | 5a0ef7f7-82e0-42c0-bdc9-5f5c6917859e |  | note | METHOD: Test Visual
label | ff77780b-1bb7-4609-8c6c-77716781c678 |  | note | ---------------------------------
label | 77cf53dd-f0ed-4fde-86d3-6692d658622a |  | note | FREQUENCY: Per lot
label | fdd1ee54-953c-40a5-aeb9-5df158286340 |  | note | ---------------------------------
label | 33a099f3-0b62-4db9-9914-fb12795ca807 |  | note | CATEGORY: IP
label | 54b1bde0-aae2-4f1a-a58d-c50f182d3f06 |  | note | ---------------------------------
label | c8a21175-74d3-44f2-85b3-6a57f942de61 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | f4f63edf-7bfb-442c-8f07-df1703ddda04 |  | note | ---------------------------------
label | c5d2f487-8331-4e62-b6dd-9a4e7d2a6e25 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1b6454c5-f066-48ad-ae32-bdafc5dd6f46 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Ensure existing formation is suitable for new sleeper laying(if required)
label | 30f2791b-2e73-4f50-bacf-533ffe1d33d7 |  | note | REFERENCE: L1-CHE-SPE-178
label | 3f6462bd-efcf-47c0-8f28-a56e739c8880 |  | note | ---------------------------------
label | b2d1550d-10cb-4009-a461-de18cadac0c0 |  | note | ACCEPTANCE CRITERIA: Compacted, even fall, no ponding and certer binding with sufficient width
label | e70ef7da-332a-4304-bc8a-7673c8ac44ea |  | note | ---------------------------------
label | a87af164-f68d-48cb-a443-bbbf96a7ed47 |  | note | METHOD: Visual
label | 90241609-22dc-4cbe-8a56-5b07ab413f8a |  | note | ---------------------------------
label | 0f5884f8-7277-4aaa-b55d-e2e441ea629e |  | note | FREQUENCY: Per lot
label | e65fbd23-edfb-4290-adb0-ec1e69e69ae6 |  | note | ---------------------------------
label | af17f285-5303-4f08-b114-e3f6760cc1c9 |  | note | CATEGORY: IP
label | e78d3818-3ab1-4638-b066-16062da00de3 |  | note | ---------------------------------
label | 5cb5e393-8d4d-4094-8449-b7bc296c2490 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 988953c8-ef33-477f-8ea2-ee70c91f4593 |  | note | ---------------------------------
label | 5611a745-d1b5-43b5-bc3d-04c817b0d448 |  | note | VERIFYING DOCUMENTS: This ITP
text | f23f9a08-48c9-4a67-993b-36954d324d65 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Off-set centerline peg established to control alignment of track construction(if required)
label | c0b023ca-47e8-42ea-b9b3-16d3f87d9d70 |  | note | REFERENCE: L1-CHE-SPE-003
label | fcb1d201-1a9a-4ef5-a179-06d273f7c7fe |  | note | ---------------------------------
label | 4a39393f-fae8-40ef-a49d-d60a50038598 |  | note | ACCEPTANCE CRITERIA: chainage reference for each peg
label | bda9baae-1984-46a3-8a23-47f1f7b7fe2b |  | note | 20m interval on tangent track
label | 42886ecb-65e2-42bf-8a0e-4375c5856b6a |  | note | 10m intervas on vertical & horizontal curves
label | 79bb37fa-472c-4ead-a9ca-08d08c712b1a |  | note | ---------------------------------
label | e253b99b-aaa3-4a51-a812-e4e0fc863ad2 |  | note | METHOD: Dimensional Survey
label | 7be73f8d-cfea-4532-a06e-0d8362d84a13 |  | note | ---------------------------------
label | f777e04d-ee02-4268-82f9-f11a36024c8d |  | note | FREQUENCY: Per lot
label | 10dd1dd3-97a6-4f2c-b9bf-54a81e2f7e01 |  | note | ---------------------------------
label | 1c1f3a3c-ef7e-46d8-94eb-42023ebc3d2f |  | note | CATEGORY: IP
label | 02a363ca-ba93-49ab-80ce-afa73aa9d85d |  | note | ---------------------------------
label | b517214c-7d5f-4d67-883d-62b910c24f40 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | ca41d757-eb00-4ae4-92eb-618a0cfa0340 |  | note | ---------------------------------
label | c0e090d7-696e-4aca-bd93-c68ed9a1eb6f |  | note | VERIFYING DOCUMENTS: This ITP
text | 61cfcce4-7e87-434c-9d63-c73cd30ea1ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Installation and verification of new concrete sleepers laid at correct spacing,square & pads are installed
label | d573f0c7-a46b-4062-a830-b8299138811a |  | note | REFERENCE: L1-CHE-SPE-003
label | f8e384af-1b0e-4bb9-b0d9-9e41c5ae1a49 |  | note | ---------------------------------
label | df42b79c-8d9b-4975-94e0-5c5abc3c56ca |  | note | ACCEPTANCE CRITERIA: Machine operator performs "side insertion" technique to get sleeper into postion
label | 04a387e5-a256-4c8b-9090-9855b8dd1ed1 |  | note | Sleeper pads present
label | c93566d1-028c-444d-ad1a-6abe0c6bf4b7 |  | note | Rail insulation biscuits installed in lugs
label | d872d57d-4add-4d49-9f81-1a729476c857 |  | note | Rail E-Clips installed by use of approved rail tool
label | f38bb454-5ef2-4271-8e11-f3b0367b6d33 |  | note | Sleeper spacing installed at Plain Line Track: standard of 685mm ± 25mm
label | 2a665612-6d4e-48f5-b439-8c37f1578d03 |  | note | ---------------------------------
label | 3000874a-85e1-4003-a23b-dfa34a042105 |  | note | METHOD: Measure Visual
label | 408badfa-d89b-48a6-bdb4-236a02ba7795 |  | note | ---------------------------------
label | 0fcbaa7e-766b-49b7-9293-12f8ae40b185 |  | note | FREQUENCY: Per lot
label | 0d7eda8d-182f-4a0c-8ebd-31b47e08cd31 |  | note | ---------------------------------
label | 9b87ef97-6a5a-4d2c-a799-8560937b42c8 |  | note | CATEGORY: IP
label | 4aa2717f-0421-4e8b-ae15-1697a4a36685 |  | note | ---------------------------------
label | d809d2c2-50fd-40e8-a62e-007a8be11d62 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | f37bd4e7-da29-42ca-9474-f4b0cb447844 |  | note | ---------------------------------
label | c5acddb0-2ba9-4cdc-bd01-60efd8a97e25 |  | note | VERIFYING DOCUMENTS: This ITP
text | d648892c-da68-4a89-adb7-5aeb51260aeb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Installation and verification of all fastening applied in accordance with the manufacturers instruction. Ensure that the Rail is 100% fully clipped up.
label | c2735567-bfb8-464a-b3db-746839b5f126 |  | note | REFERENCE: As per specification
label | bc3cdde7-cd92-420c-b885-f745b9137f8d |  | note | ---------------------------------
label | 3b21cba1-1150-42ce-a0ec-bee654eaeb33 |  | note | ACCEPTANCE CRITERIA: Insulatora on field & guage side of each rail(if applicable)
label | 928c4b83-8aa5-48c7-b1dd-0d20c55df4af |  | note | ---------------------------------
label | 41e31387-36e8-46d6-bc62-f0cab0b7d4cd |  | note | METHOD: Visual Measure Doument Reivew
label | 0af952e8-2bf8-43ab-aed3-cb8e2bb5e3c2 |  | note | ---------------------------------
label | 23b9bcb9-bdbb-435a-b005-317e3cf7d230 |  | note | FREQUENCY: Per lot
label | e558602d-1c01-4e09-9196-53bb7f6bf408 |  | note | ---------------------------------
label | b1dfcf46-a80d-4aef-9319-7732c457a163 |  | note | CATEGORY: IP
label | 8a370c58-ad35-4541-9b43-253eb046042f |  | note | ---------------------------------
label | c13fb90f-6172-46e4-8f37-879ffb8d5e2b |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 264fb52f-8752-4e66-90a1-a29caaaef9ed |  | note | ---------------------------------
label | 7897e06e-2f75-4995-b2a6-0181c3dc6535 |  | note | VERIFYING DOCUMENTS: This ITP
text | 47e3a07c-47b6-4eb2-b791-e98f5ef36d21 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Tamping /Boxing Works (Verify ballast profile complies with specification)
label | 844c8e9b-ff4a-4ced-a8d8-2f779da4096a |  | note | REFERENCE: MTSP 030100-01
label | ce0732a8-7296-4a74-a8f6-326e6237b138 |  | note | Appendix 1 Table
label | 50821aed-f21e-4f3d-852b-f3345c5cba53 |  | note | MTST 000002-01
label | 108fb67e-85fe-411f-b733-2106fcee6b0e |  | note | ---------------------------------
label | 210414e9-a736-4b7d-b30c-7b3249069904 |  | note | ACCEPTANCE CRITERIA: Track Geometry
label | 5d114891-b39f-4960-932d-1f23a0d98ef8 |  | note | Wide gauge < 12mm from design
label | 9977514f-879d-4819-980e-0353bc479fb6 |  | note | Tight gauge <-8mm from design
label | 2a04a52b-70b7-4b4f-9710-7b7db67a5ee5 |  | note | Cant <25mm from design
label | fe3881b6-0247-4070-a8e8-259c6097a9f8 |  | note | Twist (3.5m) < 15mm from design
label | dd2ca902-c076-4cc4-9a85-d78cfad3c0ff |  | note | Twist (10m) < 30mm from design
label | 3306d1a6-7957-48db-a45f-7b9d53a08064 |  | note | Top <20mm from design
label | 4b569b5a-6014-40ce-acf3-f3623d839552 |  | note | Line <18mm from design
label | 5bd378b1-144c-4a54-992f-fc87d02130aa |  | note | Ballast shoulder 450mm wide 1:4 fall
label | 68601537-39e8-42a2-9ba9-636bd157a867 |  | note | Top of sleeper free from ballast
label | d48cd9f4-ded4-4954-94a9-5dd36338a557 |  | note | Attatch: Track Measurement Sheet
label | d684af16-7ed5-4b6c-8ce7-4b86e5932e7d |  | note | ---------------------------------
label | 66f30d2b-a4fd-46e1-a4bf-dd1adeeabc53 |  | note | METHOD: Measure Visual
label | 61076292-9ffa-4e52-b749-b122acb7f590 |  | note | ---------------------------------
label | cb17167a-c515-484f-96d5-c0a034072939 |  | note | FREQUENCY: Per lot
label | 1c677a03-230f-4470-a2c3-dd707882da11 |  | note | ---------------------------------
label | 3075dc9e-6e8c-4403-ad31-5064ad3e2ea3 |  | note | CATEGORY: IP
label | e7ebd008-a978-4d52-af24-2c4a06a02dad |  | note | ---------------------------------
label | 9f2af1f4-6af1-4ce7-8e61-ffc9d9235466 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 2f8ead7b-686a-48b7-8599-780c42e4c8cb |  | note | ---------------------------------
label | 24bb0e93-5d92-42be-ae60-9be6ce5bcda2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 83e66edd-0927-4884-918f-9bd2e55cb57d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 As-built Survey
label | e71da790-0ba7-4227-b2c9-dff3dc76d443 |  | note | REFERENCE: IFC Drawings
label | 95e5e61a-2abf-4a17-8d23-23029fd1e387 |  | note | L1-CHE-SPE-003 Section 11
label | a56eb409-ff8e-4a38-8bb6-e153766af45d |  | note | ---------------------------------
label | f120a1db-86bb-4ac3-a998-46715d78a772 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate rectification works
label | aa510acd-ea12-4383-b3b1-45dcd9ada316 |  | note | Attach: Surevy Report
label | 951cf1e7-8358-4e6e-bfc7-b120488d7bf0 |  | note | ---------------------------------
label | 638c0dc9-1921-46a2-93ab-391b811b8334 |  | note | METHOD: Document Review
label | 99b046f0-3a43-41d8-a6e4-8f7dd75d8e17 |  | note | ---------------------------------
label | de8d2954-b62c-4c09-b27f-c24aa61d3c9f |  | note | FREQUENCY: Per lot
label | 0692f01f-b4ec-4b70-8201-6b3051148ce9 |  | note | ---------------------------------
label | 135d7566-01a8-423b-a76d-5a205ae8771f |  | note | CATEGORY: IP
label | 3568c95d-bd2a-46a3-a949-fd31484fdc70 |  | note | ---------------------------------
label | 22ece7f3-0bf9-436a-82e9-b271ff8a157c |  | note | RESPONSIBILITY: Surveyor
label | 591df421-12a6-4d1c-bd95-8d9280127f11 |  | note | ---------------------------------
label | a793807b-c4db-4ca2-b53c-81ab5bd7855d |  | note | VERIFYING DOCUMENTS: This ITP
text | 74b08283-debd-4666-b263-03bbaf8d1eb4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Track Certification
label | be7e42d7-e1f5-4cbb-a37e-cc6f79dc024e |  | note | REFERENCE: MTMF020000-1 – Track Form A T
label | 03500a0e-5fda-411d-a6b6-fc901500abff |  | note | MTMF020000-2 – Track Form B
label | 847ac3e9-da7f-4bec-89de-5b658ca05b37 |  | note | ---------------------------------
label | 22b312af-1abb-4a97-ab08-396447f4e1f2 |  | note | ACCEPTANCE CRITERIA: Attach : Track Geometry Conformance Certificate
label | 5b8a1269-e2bd-494a-8bbf-5d39b16fa03f |  | note | Attatch: Track System and Component Conformance Certificate
label | bbdafd9e-371d-470e-869d-09bf834b7507 |  | note | Attatch: Before/After Photo of worksite
label | 62bd2c01-4b70-48e3-8f2e-786c9a88cadc |  | note | ---------------------------------
label | 7eb137d1-048c-4c9f-87bd-c520e6e515bc |  | note | METHOD: Visual Measure Doument Reivew
label | 6b74709b-af4b-4491-be80-a43933e9cabb |  | note | ---------------------------------
label | 89b5721c-2cff-42d0-8e93-e72ecdac77b5 |  | note | FREQUENCY: Once when all occupation works complete
label | 90a3587e-624f-4acb-ad72-666fa4229691 |  | note | ---------------------------------
label | 273b692b-2444-426f-8b5f-74dd9c095ff5 |  | note | CATEGORY: HP
label | 3831f3c6-b410-4f40-be3c-17bfa6376fec |  | note | ---------------------------------
label | 8844fe01-231b-45f8-9e87-827dd6a87157 |  | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | 1410197b-233b-4deb-a2cd-c6533367c3e9 |  | note | ---------------------------------
label | c95f85cc-e852-4cb3-8221-b9e125d230f1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1a608cc2-b909-4e3d-999e-aa224ed29ca2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 69e91e5a-c2c5-4b01-a0b3-f948d138e42f |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | ba185c2a-421c-4b02-a08d-f84b69cfc6b7 |  | textbox | Name:
text | e6403de7-a7fd-4184-b95d-092fd671bdc6 |  | textbox | Position:
text | 87fd2829-8428-4043-adee-8bd5357347ba |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV Conduit and Pit - Rail (Supply and Install) Rev 2 | itp |  |  |  | Yes | ITP-CIV-Conduit and Pit - Rail (Supply and Install) Rev 2 | 35a8e7d2-e52e-4b97-b61e-ceeaa69201a1
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | b7d6ff07-ee14-4a1b-b822-e3cdb53d22cc |  | note | Document Title: ITP-CIV Pit and Conduit - Rail (Supply and Install)
label | f97dc404-a431-4f0c-9dc4-59e4d6adcb74 |  | note | ITP Description: Pit and Conduit - Rail (Supply and Install)
label | 2e06c637-183f-4ffd-82be-43181d49d1d5 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 7c22c600-c886-47cd-b4d2-cf93777ae3d1 |  | note | Revision Number: 2
label | f4fb4f94-c0be-4763-a7fa-3a211a140c81 |  | note | Revision Date: 7/04/20
label | f2512571-c10f-4af3-ab8c-2f8412d5733e |  | note | ITP created by: Thilan
label | d4530402-01a3-495d-8d0c-ca885b169c03 |  | note | ITP approved for use by: Josie Pavlou
label | 9ed1ef83-9d06-4c20-8aed-97d6d56dee80 |  | note | 1.1 IFC Drawings
label | 9e15c136-eb7e-4f30-8227-716c0d651965 |  | note | 1.1 L1-CHE-STD-043 (VRIOGS 012.2.1)
label | 1095ca82-63e3-41bf-8959-37ba2ba4b24e |  | note | 1.1 L1-CHE-SPE-070
label | 11fed343-6309-4bac-9e0f-995916a87cf6 |  | note | 1.1 Australian Standards
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Conduits
label | c762e001-cafb-4007-a695-b05e4bf54a0e |  | note | REFERENCE: HV Conduit: AS 2053
label | f81cde9e-7629-406b-987f-c5eb1df46052 |  | note | HV Conduit (boring): AS 4130
label | f95f589e-88fd-4c18-b528-75ec152b29a3 |  | note | Comms Conduit: AS/ACIF S008:2006
label | 66811519-4a0e-45a8-b62c-1adf3b1e6819 |  | note | LV Conduit: AS/NZS 3000 - 2000.
label | 91a80372-d7b8-4800-b86e-13b346eb60ac |  | note | L1-CHE-STD-043
label | 74148bc1-b68a-48b4-ad7f-5696b3babccd |  | note | L1-CHE-SPE-070
label | 977dfa53-986f-44c1-b22a-16b0d03e4cf0 |  | note | ACCEPTANCE CRITERIA: 22kV Conduits: 150Ø (160mm OD), orange electrical heavy duty 8.8mm wall thickness, greater than 1.65x cable diameter for single cable
label | 5aac8c37-5a35-49d6-b81b-55e659549d9d |  | note | Comms Conduits: 100Ø (114mm OD), PVC White comms conduit 4.6mm wall thickness
label | 2d0ea55d-e8c0-4f50-8c37-be9d84eeddfe |  | note | LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | 168a00e0-2114-4f49-b709-79b0538cf272 |  | note | LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
label | 1a57cbae-cd55-45be-aba1-6d16be6b84b1 |  | note | HV CONDUITS TO HAVE A MIN 2000mm BENDING RADIUS
label | 19e4beb8-3c89-402e-93b9-220d94220a0e |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 074099d8-d947-4179-8d1d-1132b52a33d8 |  | note | METHOD: Document Review
label | 85259b93-acd5-4312-88b5-5a6d02149e77 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | a1bde12a-2373-4b35-bb9c-500f9e88bd29 |  | note | CATEGORY: IP
label | bd36b0bb-db33-4cf9-8668-3e99238ce12a |  | note | RESPONSIBILITY: SE/PE
label | 2129dd7c-4317-43e0-81f3-323ce875f7b2 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No.
label | 63be034a-f49e-4912-96c3-a1707c23d996 |  | note | Attach delivery dockets
text | 2578b562-56f8-4844-9e1f-4ae0f9c06a01 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Pits and Pit Lids
label | 98f5af53-4173-4056-855e-234441822a8a |  | note | REFERENCE: IFC Drawings
label | 4a792fe4-8e43-4876-abd2-cad7472105d8 |  | note | VRIOGS
label | 271e0f90-dcb3-44d5-9770-ca95981dc874 |  | note | 012.2.1 Section
label | d591a34b-5927-4111-8da5-5d246a7e163d |  | note | 6.15-16
label | 74b0c708-0855-47f2-8379-66157d0e5aef |  | note | VRIOGS 012.2.1 Section 6.9
label | a6fe5c76-4bc7-4438-b581-dfbd5938650c |  | note | VRIOGS 012.2.1 Cl.
label | e1c75c9c-6e91-4da6-acbc-53c6b387312f |  | note | 6.7 (c)
label | 218ac4c6-b607-43af-804b-3e0d8c902384 |  | note | L1-CHE-SPE-070 Cl.
label | 48ec70dd-d473-41ef-8e21-28a97efd7bfa |  | note | AS1289
label | 0b5aaa7a-11eb-4724-ba5f-6b4218022b17 |  | note | ACCEPTANCE CRITERIA: Pits:
label | 53f5ac6e-001b-4109-aab0-5352fcbceb38 |  | note | Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
label | fe6a6da4-dbd9-49a2-9ae1-59a45db972bf |  | note | Pits 900x900mm or greater, multipart pits lids to be used.
label | 14eaf7a4-d3f6-4ec6-b255-0fcd88aec2ea |  | note | Concrete Pits to be made as per AS 3600
label | 9b98b049-0fec-4add-aaf4-75734630ba4f |  | note | Pit Lids:
label | 1403d809-283e-4136-a5b5-4054b5dc2163 |  | note | Pit Covers shall comply with AS3996-2006
label | 555b92af-55af-465d-bfd8-1d1e5e027876 |  | note | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | b5daf436-09bc-42df-a0a8-73032396f199 |  | note | HV Pit Cover: pit covers shall be labelled with the words “DANGER - Railway High Voltage” (L1-CHE-SPE-070 13.4)
label | 0583f0fb-b838-4875-a9ad-568b865ad48a |  | note | LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | da706568-42e1-40bf-be0d-77f952627f39 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | a15f0d65-b843-46a4-9958-002daa3825dd |  | note | METHOD: Document Review
label | d1faf293-44dd-4881-bfbc-df86618d4fae |  | note | FREQUENCY: Each Material Type, Each Delivery
label | cc453854-b476-4e5f-9b0b-fac2a9f2bb6a |  | note | CATEGORY: IP
label | c0ebc259-c075-4d75-9a74-65b75c437ded |  | note | RESPONSIBILITY: SE/PE
label | 2352e0ab-19a7-4cf4-8005-267bef950a1a |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. Attach delivery dockets Attach Precast Birth Cert
text | feb13b9e-3d8c-4b35-b485-3a2afda3f9ea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Protection Barriers
label | df137959-1328-40b0-9313-dd02f0c41adc |  | note | REFERENCE: IFC Drawings
label | 8bf4de41-99d6-4185-b6b9-1769e46a4614 |  | note | L1-CHE-STD-070 10.3.3
label | 056ac4c7-a1ed-42ac-865d-64667bcbcce3 |  | note | AS4702
label | 90676bc1-a9ac-44e3-a84a-95c2c179fdcc |  | note | ACCEPTANCE CRITERIA: Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
label | c26899f5-1cef-4ea6-814b-77ff0f5e0b21 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 78531998-1612-4ddc-adea-01df1234b8f5 |  | note | METHOD: Document Review
label | 96b48240-d522-48fe-9b2c-a32336d594da |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 6fc0a5d9-fd3e-4ab8-b168-6a3f7e799a96 |  | note | CATEGORY: IP
label | c4c90e7d-745f-4548-bf91-23106f98fdb7 |  | note | RESPONSIBILITY: SE/PE
label | cad2e387-662c-4577-bcd8-f2ffca1a40dc |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. and Attach delivery dockets
text | adc2712b-671f-46e8-bb75-5fb0a1b3d344 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Backfill Material
label | 03fca773-703f-4adb-9757-f64c924d3444 |  | note | REFERENCE: IFC Drawings
label | 08951731-f76e-4d7a-a36f-d9a20c1bc6cc |  | note | L1-CHE-STD-043 Section 2 Table 1
label | 6d789094-cbb5-4dd1-ac4d-81ec1d07cfae |  | note | ACCEPTANCE CRITERIA: Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could manage the conduits.
label | b75549da-ab79-43d9-8a49-e28f550a8c17 |  | note | Inspect backfill material.
label | 1650e505-8449-4eb4-9a0f-cd1bba03bce3 |  | note | Attached delivery dockets (if applicable).
label | 585f8e8c-7105-4029-939d-149598c8c292 |  | note | METHOD: Document Review
label | c378baef-cbcb-422c-ac76-fef31d81c01e |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 4f800446-5a31-4231-b93f-1e2ef98f1c05 |  | note | CATEGORY: IP
label | c137ca40-0ba8-4de8-b2b0-0a6f5c8e6f68 |  | note | RESPONSIBILITY: SE/PE
label | 8508954b-142c-4e5f-bd83-8f0de1856938 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. and Attach delivery dockets (if applicable)
text | 65e6e011-efbe-4b2f-8f45-5fa2170ba944 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Bedding Sand
label | 91ee4543-8134-4971-ace5-b829d854cd14 |  | note | REFERENCE: IFC Drawings
label | 12413bb1-0840-4f6b-b694-faaac094025c |  | note | AS2758.1
label | ab08c713-d561-4fc9-92a0-0330f664c47e |  | note | ACCEPTANCE CRITERIA: Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
label | 0fb735a7-40a1-4c79-9f98-8dc81d2cb5f2 |  | note | METHOD: Document Review
label | e14c1eb2-6579-4e68-ae89-9ede852013a8 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 17a7ab6f-e8c3-451b-8783-f72b057d6a4f |  | note | CATEGORY: IP
label | 11869094-bc7b-49ed-a34a-d1489db73b7f |  | note | RESPONSIBILITY: SE/PE
label | b4c36a5f-f604-403b-99a8-a352090b6f10 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. and Attach delivery dockets
text | ac491cf0-846f-4fac-8216-ae551b17ca27 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Draw Wirer
label | 99a5919e-9315-4a1a-b06c-d6fbd689d856 |  | note | REFERENCE: TS-SP-013
label | c634786b-c9ea-434d-a9be-f75ae8b50503 |  | note | AS 4142
label | 89699581-6340-45ad-a34d-5a1cddfa3f80 |  | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
label | b0b9969c-9f7b-42f5-ae71-c71eb510d652 |  | note | METHOD: Document Review
label | f966b245-07c6-448b-878e-20a8f3dabe38 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 05c6afc4-3b09-4984-bfa6-0ad82b934949 |  | note | CATEGORY: IP
label | 3cee8eb0-8d75-49ac-bf2a-ee78ec1d802b |  | note | RESPONSIBILITY: SE/PE
label | 36576ef3-2538-4e3c-a789-7bf223b6bd4b |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. and Attach delivery dockets
text | e63a6897-6722-47ea-9687-858bee32ab52 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Concrete Mix - Trench
label | 68a52004-26ee-4407-97be-a2c340a36556 |  | note | REFERENCE: L1-CHE-STD-043
label | 52f7db67-6ccf-4f86-a564-c4ed6651913f |  | note | ACCEPTANCE CRITERIA: Concrete strength at 28 days shall be not less than 25MPa.
label | 76d4c518-0e30-4d84-8893-847f253d12f9 |  | note | Chemical admixtures or fly ash shall not be used
label | 85cf2add-e051-4377-9742-ce626c8c64e7 |  | note | METHOD: Document Review
label | 61ab892e-60af-4f51-8dfb-70e3c61ef64d |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 687399c7-d199-4b5e-bd40-0f4b4617daae |  | note | CATEGORY: IP
label | 558d2b77-af3f-4dfe-a76c-bf860d94a920 |  | note | RESPONSIBILITY: SE/PE
label | 510f1a6d-e455-4765-8a76-3d66652dbd4a |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. and Attach delivery dockets
text | c7c3836d-e555-4fb3-8467-eecb4417c147 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Markers and Marker Posts
label | 793a918a-1c48-49a6-9ca2-fdfe4564cec6 |  | note | REFERENCE: L1-CHE-STD-043 13.2
label | 1d766547-491b-4fcb-bd10-448eda58814a |  | note | AS 4799
label | 5f4f47ff-6334-4ec8-929d-972132f7fdeb |  | note | ACCEPTANCE CRITERIA: Markers and Marker Posts are to be manufactured in accordance with AS4799.
label | 7928aa91-cac8-4510-89ae-e33402f4cbc0 |  | note | METHOD: Document Review
label | 22b72af5-950b-4401-846b-d318d7e92c00 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 73ea4d5a-c78d-4b87-a886-55d057723027 |  | note | CATEGORY: IP
label | daeaf8cd-1b7c-4270-82a5-254c87572da8 |  | note | RESPONSIBILITY: SE/PE
label | 115552c3-c5d5-4ec6-a0ac-66809be00a3d |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. and Attach delivery dockets
text | 8efb6611-0aa9-4534-b145-cefd643ebbf2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 8822186f-94ad-4e95-aa33-d3c522624e28 |  | note | REFERENCE: IFC Drawings
label | 8a5ae4d9-e14c-4280-b4ee-3fd505d6f26a |  | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | 6e1519b0-a83a-4dce-b77e-4207175e9b94 |  | note | METHOD: Measure and Visual
label | 27cbfe08-8ac3-4d92-84e7-bdbeed7ddf7c |  | note | FREQUENCY: Each element
label | c9ac9ad9-3183-4b3d-b771-f63c1e706860 |  | note | CATEGORY: IP
label | 71bab649-0967-4244-8e38-b039951929ab |  | note | RESPONSIBILITY: Surveyor and SE/Site Supervisor
label | 89d86609-05ec-4e13-899c-008d3405d5b3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 48f01373-0e24-4f33-abc2-c7fcd7ee1b27 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Permits
checkpoint-status |  |  | checkpoint | 4.1 Services
label | d525a9ba-aad6-4fa3-9b6c-3460e5ba4be5 |  | note | REFERENCE: Services CAD file
label | aa7ffd89-df46-4e4d-9d42-b279e6069758 |  | note | ACCEPTANCE CRITERIA: All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
label | c46dd5bb-f21b-4c0e-a9f7-3ff642045f40 |  | note | Survey to mark out existing services.
label | 8768d1ef-d05f-4f81-a9d6-de188c06773c |  | note | METHOD: Visual
label | ccc4aa9d-2a51-4a71-bc27-fcc120c66ea7 |  | note | FREQUENCY: Prior to commencement of works
label | 2ae6409f-9a5b-40c0-a706-158e755f037d |  | note | CATEGORY: IP
label | 96e37306-32d7-4a9e-8bdb-ab5a27453394 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | aaa49860-43ad-496e-b41b-4098d8e4ff4c |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 833816ba-7364-49e0-8bc9-1d6d8c7cda65 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Excavation Permit
label | f705b8c8-a7be-4905-9455-fae9841d4b9a |  | note | REFERENCE: MRPA Excavation Permit
label | 14ce239e-76f0-4332-902f-fdfb3dd7d29a |  | note | Ground Penetration Permit
label | 11ffb899-0e07-4b90-a511-53f8bd8bccaa |  | note | Metro NAE
label | ed6bf57e-e01c-4a25-aa5a-bd7b5a700887 |  | note | ACCEPTANCE CRITERIA: Insert Permit No.
label | ef9d6062-fe3a-403a-8f53-a0c09478b2c3 |  | note | METHOD: Document Review
label | 11a848b7-2685-482d-b001-2b25c85de55e |  | note | FREQUENCY: Prior to commencement of works
label | 8dff5c3a-7312-4d32-b626-9c4be46e1ea9 |  | note | CATEGORY: IP
label | 077a9b59-3e57-424f-b3af-fd7c365b8b8b |  | note | RESPONSIBILITY: SE/PE
label | 5f6e3628-a6e0-4735-89c7-47630f819650 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c1c1b9f5-4817-4588-b70c-7cfd95421706 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 VicTrack PTW (if applicable)
label | c8a3b05a-a26e-40ef-878d-a146b661628f |  | note | REFERENCE: MRPA Excavation Permit
label | 22caf517-eda0-4eef-880a-4145dc1c7a60 |  | note | VicTrack PTW
label | 25e79882-9a6a-4c90-94df-55a76f3dcb8e |  | note | ACCEPTANCE CRITERIA: Insert Permit No.
label | d09d5ff1-4a28-46ff-8bb8-662279123da4 |  | note | METHOD: Document Review
label | baf51798-c4a4-4912-8c7a-79b70f6dcbbd |  | note | FREQUENCY: Prior to commencement of works
label | 55ae3f14-1dfb-40a8-9e14-cebbddd6ab81 |  | note | CATEGORY: IP
label | 755a6c21-4624-47b1-9bd4-e173c3731189 |  | note | RESPONSIBILITY: SE/PE
label | 31b403aa-b65d-4536-adcb-06178de51ec1 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 7faba2e5-1bad-4868-a3db-cd413da65b02 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 PTDT (if applicable)
label | 18f1e550-47f9-4c8f-b9cc-07b804d3060f |  | note | REFERENCE: MRPA Excavation Permit
label | 8d8092e8-0e49-4a7d-b4c7-dd52f55869dc |  | note | Ground Penetration Permit
label | be3e4018-e196-42b6-9a49-4badbd0b11a0 |  | note | Metro NAE
label | c5c41e4c-99ba-48b5-8bcb-c2c91c77bc98 |  | note | VicTrack PTW
label | 11306f99-7bf5-4c78-ae0e-b7367ebe9f3b |  | note | ACCEPTANCE CRITERIA: Insert Permit No. or Notification Email
label | e707737a-f2ad-4715-a8c9-2d5b22637b82 |  | note | METHOD: Document Review
label | 2b1bc44b-7415-4c16-8d08-333f7ae2e2ab |  | note | FREQUENCY: Prior to commencement of works
label | 818f13b0-c6f9-457f-9358-a0301bed01cc |  | note | CATEGORY: IP
label | aff0816a-c49a-4b1b-8433-61c4be5acca8 |  | note | RESPONSIBILITY: SE/PE
label | fe31b934-671b-41dd-8159-dc86f0829a76 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9a45e409-37e3-4197-99f6-424763a367a9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Excavation Activities
checkpoint-status |  |  | checkpoint | 5.1 Trench Excavation
label | 29025e6b-0fc4-42a8-8699-b34a8f9df527 |  | note | REFERENCE: IFC Drawings
label | 91e5a6ae-c712-4248-8dc4-2f0ec30efe4d |  | note | L1-CHE-SPE-070 7.3 Table 2
label | b227b051-cf54-4db1-a769-174c006cba76 |  | note | L1-CHE-STD-043
label | 2bd7a3e1-4603-4c13-b731-c1d61965256d |  | note | L1-CHE-STD-070 7.1c
label | 47f91323-86e1-4dfe-ac1b-226aa73b99b7 |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | 7d402057-f331-4e33-987c-c48b45c33371 |  | note | Edge of trenching to be a min. 2m from structures/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
label | 70a94672-987f-4838-882c-202068826b86 |  | note | The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
label | b831d697-b6ce-406f-8111-f6552efabfd3 |  | note | The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 650e3300-715c-417d-915a-298649f3fbb9 |  | note | METHOD: Measure, Visual
label | d5be0519-37cf-4fcd-84b9-9a3a7b549bdf |  | note | FREQUENCY: Each lot
label | 2cfdae6e-df60-4db0-99c5-d4385592975f |  | note | CATEGORY: IP
label | d8cabcd5-9198-42d3-bd4d-b316aac31b89 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 66ce684a-54d5-416d-b7b8-0ce12db5444f |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 4f66cd35-8bc6-4d2c-9f26-b855a8ddb725 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Trench Excavation
label | 20404829-9ad3-4f9d-adc2-ff69183a16c9 |  | note | REFERENCE: L1-CHE-SPE-070
label | aa587a59-8819-4e6a-958b-768439d285a8 |  | note | L1-CHE-STD-043
label | 3be23b78-0da6-4b66-9358-6ea09f499e20 |  | note | L1-CHE-STD-070
label | d9f606e9-d972-4f60-93fd-c4858a978fa8 |  | note | IFC Drawings
label | 68742551-62e9-4134-8d47-6c7331714c13 |  | note | MRPA standards
label | 6caf6ff2-da93-415b-aa58-361d83cc0572 |  | note | ACCEPTANCE CRITERIA: Trench stability check:
label | 80730a80-09b2-4340-beff-ad9ed9419079 |  | note | - Shoring,
label | aba815da-1c74-4075-86fb-ca44f843f21c |  | note | - benching
label | b3dce9b1-66ce-4234-9e62-377e9d9274f9 |  | note | - Geotech signoff
label | bb12efa6-76b3-4feb-8f8d-70a3244e30ed |  | note | METHOD: Visual, Document Review
label | e6959b3b-e992-4c32-94dd-62adf2ec8dee |  | note | FREQUENCY: Each lot
label | 36fb5624-29e6-4b53-98f2-ec8ce5bced29 |  | note | CATEGORY: IP
label | abacdc2e-3070-4aca-8d37-667240de57c0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | eb02a84a-f333-4f56-91ee-2293061e40d0 |  | note | VERIFYING DOCUMENTS: Sign ITP and Attached Geotech Report
text | c38cf7a6-0842-4736-8912-411ec9642ec2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 ULX Trench Excavation
label | d8c689c0-ca74-4995-8577-3d084025ccdb |  | note | REFERENCE: L1-CHE-SPE-070
label | 87e88b25-d555-4308-a7c6-d44d14d6991e |  | note | L1-CHE-STD-043
label | 3393f19c-2a64-481f-aa1a-27711ebc0c44 |  | note | L1-CHE-STD-070
label | 26af780c-e1e6-4483-bb35-526ccec1e857 |  | note | IFC Drawings
label | e4c674c1-8721-4cf0-802f-1e50241c6986 |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | 8cb429df-b0ff-4370-b47d-8ea03d844bd4 |  | note | Trench alignment to be perpendicular to the tracks and extend 3m past the edge of rail on both sides of track.
label | 005b37e7-5e91-4b85-9036-2b25b5549d9c |  | note | Top of conduits to be 1.2m below top of rail.
label | b0609084-6998-45ea-b9e8-dc4563f94f95 |  | note | METHOD: Measure, Visual
label | a076e636-edd1-4c6b-ab56-0f3d05886176 |  | note | FREQUENCY: Each lot
label | d75e9a92-e7cb-4f9d-930c-22799ea68e9e |  | note | CATEGORY: IP
label | fbb1e435-5651-455f-833d-40efe81e910b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3956f16c-5cb1-4f3f-b344-63319a80d065 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 5bb70317-97de-4a2e-ae61-26a0c1194861 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Conduit Placement
checkpoint-status |  |  | checkpoint | 6.1 Bedding Sand
label | 98705b91-1769-4565-8fdd-f860f838cb80 |  | note | REFERENCE: IFC Drawings
label | 81a3fa7c-a434-42b7-b899-5f186509653a |  | note | L1-CHE-SPE-070
label | 5aa5b947-dc18-428f-870f-c9cd8d43b1f6 |  | note | L1-CHE-STD-043
label | feb6b8e9-a943-48ba-a7c2-f6e85c1fc623 |  | note | L1-CHE-STD-070
label | 6065b095-5666-4ad0-97af-618ef6bab07f |  | note | ACCEPTANCE CRITERIA: 100mm of bedding sand/crusher dust to be places at the base of trench.
label | 499e8856-ae37-48df-a276-1bea75812329 |  | note | METHOD: Measure, Visual
label | 14bd295c-b484-4dc7-9f31-5bf80c21c57f |  | note | FREQUENCY: Each lot
label | af41cd49-3994-44b4-863d-09264b5e9bfb |  | note | CATEGORY: IP
label | f00c6099-064b-4809-9a27-4b93a70b1f11 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9f2d6f82-3949-4acf-8189-fea9033cbb5c |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 721c8684-5e73-4ee5-9df8-0ea698585a17 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Conduit Configuration
label | c9bac7a9-23b6-4a2f-b029-4933a002888c |  | note | REFERENCE: IFC Drawings
label | b336146c-91f1-4715-b175-01821d10a3c4 |  | note | L1-CHE-SPE-070
label | 49c72de1-0762-4891-af79-6f28b1a1e931 |  | note | L1-CHE-STD-043
label | dcc31644-f560-4007-b81f-37082d62fe07 |  | note | L1-CHE-STD-070
label | 1d066463-d799-4203-8114-96c4cbf636fa |  | note | L1-CHE-STD-077
label | 30c1c83e-076d-4ac1-850d-5eca7bf9c470 |  | note | ACCEPTANCE CRITERIA: Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | 0b296b21-da7b-4b35-8065-20999ffb400f |  | note | Min Cover
label | 76f34cd8-ee0a-47b4-b61f-67b60ee781f7 |  | note | - HV: 1000mm
label | e29ba66b-5684-42d7-b9f2-953560b6f6f9 |  | note | - VicTrack: 650mm
label | 93f0e095-a260-4b17-a64e-77d95680ea13 |  | note | - Signalling: 800mm
label | 1a1865f8-1f35-447a-88e4-ab2839337304 |  | note | - LV: 800mm
label | 48d37547-1d30-47dc-b3e1-1051a210ac5d |  | note | - Electrolysis: 800mm
label | ec81ef23-5002-4e06-a59d-58e4e5ce61ec |  | note | - SCADA: 800mm
label | 30f59c44-49b0-45af-b5c9-c5810d335793 |  | note | - MTM Comms: 600mm
label | de4aa337-79a5-442e-b15c-10f738b21054 |  | note | - 800mm below water coarses (stab sand encasement)
label | ae780c55-3175-48a9-b789-f725b7e438ed |  | note | - 1200mm Under VicRoads Roads & top of Rail
label | aae4aabf-d4a7-48ff-b6f8-20b5d17227aa |  | note | - 900mm below council roads
label | a5bb9d1c-3ea8-4f92-9e77-fbeae8be4b1f |  | note | METHOD: Measure, Visual
label | e6b03980-6495-47ad-ad2b-7a51ce4313f3 |  | note | FREQUENCY: Each lot
label | 8a2a70bd-0ce0-469a-a014-fda1c4d88952 |  | note | CATEGORY: IP
label | 05aa9b07-0ec3-45ef-b517-9b6b9f3d9768 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ce17414b-cd9d-44ad-9865-6c6cb8dbaec8 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6ea43e15-7e87-40ea-bab2-11cd28d1334d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Separation of Services
label | b5b119ad-97f3-4df0-9dc6-9bdec27843d2 |  | note | REFERENCE: L1-CHE-SPE-070
label | da079561-8a0f-4e54-873f-584d91f3a0e5 |  | note | L1-CHE-STD-043
label | df404217-1bb1-45dc-a0ba-a422767ef87e |  | note | L1-CHE-STD-070
label | d3f17061-6038-4709-8925-09c7c8618342 |  | note | L1-CHE-STD-077
label | 1f78dddb-ff30-4cf4-aa54-b29c92081a0b |  | note | IFC Drawings
label | 4709e790-53ea-45e0-9945-d7bfedfa6411 |  | note | ACCEPTANCE CRITERIA: Separation of services
label | 8bc19d13-e2c8-4349-aa01-9d2323bfc352 |  | note | - HV: Min. separation distance between HV conduits at least 50mm
label | 2eeb54b2-bfb9-4e8b-adec-a4f1aa543222 |  | note | - VicTrack: fiber 300mm from HV
label | a426cfa8-4a84-4996-bc94-cdaabfc5fc97 |  | note | - Utility: 300mm to utilities
label | fc904f36-359c-4616-8656-56c1bb7ae682 |  | note | - Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | a6710ec0-22ff-4d7c-982b-ac47c192e3fd |  | note | METHOD: Measure, Visual
label | de58ee9b-f55e-4a02-8a08-26190e3f8b3e |  | note | FREQUENCY: Each lot
label | d553c7b4-76c8-43a5-990d-62a081397c64 |  | note | CATEGORY: IP
label | ba6f92ae-27c2-4e2c-acc2-8a434914a268 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f30d2b4f-29bf-4fa9-a639-446b149bcd92 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e5b07975-9ba6-4a9a-afb6-7a821cdf80c3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Joints
label | 49361e48-3077-4015-9f32-ca7e00561f78 |  | note | REFERENCE: L1-CHE-SPE-070
label | d2bd57dd-c19d-40b2-9b1a-3ed8bdf16178 |  | note | L1-CHE-STD-043
label | 7ab7a873-1085-427e-872a-5d7a079596d7 |  | note | L1-CHE-STD-070
label | b2af8412-8021-4a43-8efd-ee9ff86162c3 |  | note | IFC Drawings
label | d0e54b65-7bef-4a0e-bcf2-a2e64a3bcf2b |  | note | ACCEPTANCE CRITERIA: All conduit joints shall be made by utilising the spigot and socket ends.
label | 47cf32d5-a2aa-400a-b2ce-e278a08d6bcd |  | note | Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
label | 06b39f78-5e6e-407a-a558-c179a76f190f |  | note | The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
label | c20e1369-f971-480b-90eb-6fb52dfaae86 |  | note | Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | 1fd97bad-f7f2-410e-8951-d93beedede36 |  | note | METHOD: Visual
label | 0a8bf95a-f65e-4a13-bd62-e1d3673055c3 |  | note | FREQUENCY: Each Joint in each trench
label | 257da79b-d855-4473-9dbf-c80fc0e10cb0 |  | note | CATEGORY: IP
label | 4da35460-57d7-4aa8-b043-827e81c5ad41 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8cf38ff2-8b47-4087-9286-1ca904b31b12 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 539455bc-d651-4929-b91b-640e52783934 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Conduit Inspection
label | 57786bd9-07e3-4526-ba53-c1e01ba3e515 |  | note | REFERENCE: L1-CHE-STD-070 16
label | 81b93d27-9d9e-419b-9a84-34a3e4dd83eb |  | note | ACCEPTANCE CRITERIA: Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
label | 9659287e-4b3b-47f9-a89e-341042bb6e76 |  | note | METHOD: Visual
label | ad224157-ea82-4cb9-9a6a-bf14cec6198c |  | note | FREQUENCY: Each lot
label | 082831da-6e35-4510-b62a-0592df8c5aca |  | note | CATEGORY: HP
label | 2dc4e2b9-c1cf-446f-9964-ee96f09c2973 |  | note | RESPONSIBILITY: SE, NA, MTM/VicTrack Rep.
label | 5ac9f3d7-8f92-432b-a456-3caf8db5a2c4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 0bb022fa-adb7-4858-9e29-32afb4eba542 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Survey As Built
label | bcaf2c96-73ef-4ee1-9e47-3444c94daa31 |  | note | REFERENCE: L1-CHE-SPE-070
label | 7cf0c768-7cca-4a17-9438-f89f39521b98 |  | note | L1-CHE-STD-043
label | d715ddc7-d3f7-4a05-b532-6e5ec5124b27 |  | note | L1-CHE-STD-070 CL13.1
label | 0a6852c8-cf14-4b47-a87f-07a010a8d1f5 |  | note | IFC Drawings
label | 8a993d79-ec32-4401-8e5c-59c224306f67 |  | note | ACCEPTANCE CRITERIA: As-Built survey to be completed and recorded before backfill
label | 6e3560eb-2dfc-4ca2-b051-330bcdd392f6 |  | note | - Cable joint locations.
label | 85caa304-06a8-4d45-a80b-cf6ba210e5d8 |  | note | - Cable pit locations (Corners)
label | 7a27781d-a23f-4eb4-968a-b9554bf698e5 |  | note | - Pit dimensions & pit lid type
label | 7e3f1f91-3a09-4f4f-82ef-ba8d140ff65a |  | note | - Under line crossings
label | b2fd1979-bc32-4b87-8861-cb192b3c8d54 |  | note | - Under road crossings
label | 697bcd73-ded4-4fc9-8be6-7ef3a624456d |  | note | - Changes of direction
label | 8954cd13-379f-4677-af51-d655a24247d8 |  | note | - Spare Conduits
label | 4aea1517-82a2-428e-837c-850564f06b3f |  | note | - Conduits labelled as per trench profile
label | a67cd7c7-a34d-4a74-a5a6-5295fa856c18 |  | note | - every 10m
label | e5e8cb0e-b60b-4d4f-ae33-2cfe958420dd |  | note | - Other significant points of the cable route
label | a7d334ad-3828-4dff-a2b9-de76591411e7 |  | note | METHOD: Visual
label | eabde393-38d9-426f-a852-be3d6695c43e |  | note | FREQUENCY: Each lot
label | 647ce11d-37d3-4838-8a28-0ab798ec96ae |  | note | CATEGORY: HP
label | 38115ec4-af09-4990-921d-424421ca9e5c |  | note | RESPONSIBILITY: SE, NA, MTM/VicTrack Rep.
label | 5549a19b-fddc-4b51-b3c7-f4e4218e3f7b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e3c38544-bf69-4f22-8437-7e648c3110e1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Bedding Sand Installation
label | cec6d6b8-ef88-4f93-9821-765a32e98b31 |  | note | REFERENCE: L1-CHE-SPE-070
label | e41490fb-9fbd-4332-871c-12a69c0425ee |  | note | L1-CHE-STD-043
label | b363a49c-f92e-46fe-a2b7-b7d7ec118809 |  | note | L1-CHE-STD-070 CL13.1
label | e7442292-13bf-46f0-ab75-12ed686ea566 |  | note | IFC Drawings
label | 9e1432ff-77ae-43a5-bb68-b1cf4cb859ff |  | note | ACCEPTANCE CRITERIA: Bedding sand/crusher dust extends 50mm past edge of conduits.
label | 1a509775-e504-49e4-b42f-8cf3fd547ba2 |  | note | Bedding sand/crusher dust extends 100mm above conduits.
label | a2fba646-5cf9-4737-8f65-85f33e4dfc1a |  | note | METHOD: Visual
label | fedef3fe-2d39-4579-a7b3-69664a52b2ed |  | note | FREQUENCY: Each lot
label | a461d2bd-9438-45d3-91db-466f771fe4c9 |  | note | CATEGORY: IP
label | 57a6d835-790d-40f9-8226-bc164bef2495 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | dde6c9a1-11e6-41a6-bb88-e8f019b9b228 |  | note | VERIFYING DOCUMENTS: Sign ITP and Attach Delivery Dockets
text | 201e0dda-70cc-42cf-9e8a-aca156953591 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 HV Protection Barriers
label | cd1c18e7-f1f7-4f1d-8ee0-4545eaf1308e |  | note | REFERENCE: L1-CHE-SPE-070 Cl10.3.3
label | 2a3f1fbd-0b9f-41d7-97c1-089f19dd6c60 |  | note | ACCEPTANCE CRITERIA: Top of HV Protection barriers installed 150mm above and 50mm beyond vertical line of any HV conduits
label | b5d93d7a-fab8-4210-952d-c1078a8b1536 |  | note | METHOD: Visual
label | 606d643b-a36e-4700-8ee0-ed31d4143714 |  | note | FREQUENCY: Each lot
label | 21f3a5e8-6b84-4de3-9b55-9acc9ad7ce69 |  | note | CATEGORY: IP
label | 8ccdc0b3-1ee1-42ca-9cbd-21bf590c6f1e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b5411149-03a4-4c35-b707-94e6eaa37f58 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a57dc98e-d62f-4cc6-9b9b-5fbe335dda5d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Marker Tape
label | 6bb2cffd-70ca-4140-abbe-0e457a0db4ea |  | note | REFERENCE: L1-CHE-SPE-070
label | d9b7b2df-8071-4880-8675-1b0012116b40 |  | note | L1-CHE-STD-043
label | 47cc2b22-9a88-478a-b242-4a53ec7fb585 |  | note | L1-CHE-SPE-070 Cl10.3.3
label | 8f6b6dac-3093-4179-a49d-20a58d501067 |  | note | ACCEPTANCE CRITERIA: Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers.
label | 147a6212-964d-42db-b2a6-0e90dc3609b6 |  | note | Tape to be one continuous length.
label | b89300a3-1647-43ff-8a53-58dd53467bd3 |  | note | VicTrack to inspect the Marker Tape placement..
label | c6b37ad7-ebe4-4ffc-a30e-f4319c3d7621 |  | note | METHOD: Visual
label | d61794ed-29ce-46ca-af90-182183257cdd |  | note | FREQUENCY: Each lot
label | 758ec25f-a811-494e-92ee-0c849ebcca91 |  | note | CATEGORY: HP
label | 06b40a2a-a85d-4cde-85ae-f7938453b33e |  | note | RESPONSIBILITY: SE, NA, VicTrack Rep.
label | 91725e4a-7b49-492a-9e75-c2d2540c8de6 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a3a59e89-c71d-4ab6-a023-658bb14fe81f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 Backfill Installation
label | 8e286050-a3de-4f5e-968c-b3b5b8eb9193 |  | note | REFERENCE: IFC Drawings
label | 797d0d04-1cf1-4361-8e85-c045e9936147 |  | note | L1-CHE-STD-043 clauses 6.15 and 6.16
label | 1cb1f761-dc43-43b3-995a-cac17608893b |  | note | ACCEPTANCE CRITERIA: Backfill per trench profile
label | 73bc13e3-89ff-4933-aba1-42e2fc42b6e4 |  | note | - 150mm layers
label | 02d06cd2-c316-490a-bee3-1792c47affea |  | note | - CBR >3% for existing material to be used
label | 7424449c-c689-4954-9d0b-48635d6ccd8b |  | note | - 95% compaction
label | 4cac22d1-e19f-4cf7-9e02-e3918b5a73f4 |  | note | - conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
label | 02a16102-66a9-4b8b-8fc0-6602bebe3b98 |  | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | 882612b5-1b76-477d-9ecd-5237a63392e2 |  | note | Trenches under road pavement - backfill to be same material as the road formation material.
label | 87916cca-36e9-4e49-9e96-e96d9cfa670b |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 9249cbe7-1487-4390-8b7a-247302dd9e70 |  | note | VicTrack to be notified and witness the first layer of backfilling.
label | 2e1222b5-cd60-4261-abd4-406887a7bca6 |  | note | METHOD: Visual
label | b697d41d-e633-4ade-8ae8-189b735c06a5 |  | note | FREQUENCY: Each lot
label | 4f597e57-50cf-4d2f-8b7f-e0cb3262823f |  | note | CATEGORY: HP for first layer only, IP for the rest.
label | dbbe107e-0e13-4902-b2fe-2c6305a0567d |  | note | RESPONSIBILITY: SE/Site Supervisor/NA/VicTrack Rep
label | c6b18bf3-7310-4af2-a247-2544ecb346bf |  | note | VERIFYING DOCUMENTS: Sign ITP and Attached Delivery Dockets
text | 955b3ba8-58f0-4fe8-9bc4-f7983c5a0bfd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.11 Compaction Testing
label | e27d5afd-6f67-4c79-93af-fb7988c52ec7 |  | note | REFERENCE: L1-CHE-STD-043 clauses 6.16
label | 5f1cb97b-4e9a-4ae8-ab9a-9a22a11b3b8b |  | note | ACCEPTANCE CRITERIA: Compaction to achieve 95% Standard Compaction
label | ae4f39cd-42e4-400e-909d-d8e5e05f2f4e |  | note | The tests shall be taken on a frequency of one (1) test per 200 linear metres per layer or one (1) test per area per layer where any area of excavation is less than 200 metres long.
label | 0bf99103-d3a6-40bc-a63b-9b8f0a77e6c8 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | da1f47e9-331e-444b-9533-c184e5415f22 |  | note | METHOD: Document Review, Visual
label | aecb0ea8-8574-461c-93fc-1ee7e2de36c2 |  | note | FREQUENCY: As Per L1-CHE-STD-043 6.16
label | fdf23ae2-5344-4f15-8aa7-a608b4aade5f |  | note | CATEGORY: IP
label | b5a48481-7a77-417e-8fcd-fc826b3268eb |  | note | RESPONSIBILITY: SE/PE
label | 0815fb2c-c21f-4211-a17b-1f88458e5dba |  | note | VERIFYING DOCUMENTS: Sign ITP and Attached Test Report
text | 402bbd76-3b65-42ad-a606-e8094274f129 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Location
checkpoint-status |  |  | checkpoint | 7.1 HV Pits
label | 7435718d-c180-4a48-9ced-e05c4f4fbf7c |  | note | REFERENCE: L1-CHE-SPE-070 (Cl 7.21c) CL9.2,9.3
label | dc9dbd85-8d93-465c-b002-3f62fda6b7d1 |  | note | ACCEPTANCE CRITERIA: HV Pits
label | efd87ac7-c4a6-4440-84f8-33b3bb6c60d0 |  | note | - intervals no greater than 400m
label | 3812d03f-4ae9-4fac-be8a-1f5464eb683b |  | note | - 3m from rail
label | 94b36406-9c03-475c-bc7e-7d2c330e4376 |  | note | - Access Roads, Class D lids
label | dd95af08-13f1-42ce-99a5-01be345730d3 |  | note | - Footpaths and non traffic areas, Class C Lids
label | 89835a39-91c9-45ce-85f4-a06ea3976ff6 |  | note | - Alignment of square pits parallel to property line
label | e688830f-ac5f-4729-aa79-34d977fbe360 |  | note | - Pit size as per L1-CHE-SPE-070_9.3.2
label | f5a869ba-b3cd-4a17-b492-e95410377a53 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 4f9b951a-f620-4b26-9a04-9e1363618c1f |  | note | METHOD: Visual
label | a0e51f7a-16f8-4330-aab3-194b5e509903 |  | note | FREQUENCY: Each Pit
label | 96e2bb4f-9c52-4d7f-b586-c2239601b4e8 |  | note | CATEGORY: IP
label | 990a87b0-f8dd-4989-a5b5-9ac0a0449d8e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 5197e16c-65d7-4b78-8822-0b7ddccabc56 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 1bd742ce-568b-4a61-a359-888a5cd5c1be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.2 Sand Pits
label | 90ae8712-15f7-4599-a4db-19c5709e6d58 |  | note | REFERENCE: L1-CHE-SPE-070 9.4
label | 5527b30d-f0cb-46b3-8c2e-fb7603c5225f |  | note | ACCEPTANCE CRITERIA: Min. clearances from:
label | 1055eda2-e203-45a1-88cc-1bda49c597bc |  | note | 5000mm CLEAR OF VICTRACK ASSETS
label | 8f962e87-5225-48f1-8735-05f2d578a610 |  | note | 2000mm CLEAR OF MTM SERVICES
label | ede0074c-99fe-4df4-a45b-32c1b2501a62 |  | note | 3500mm FROM NEAREST RUNNING RAIL
label | 9cb9f8fa-ba04-471b-9406-58863d1d2e30 |  | note | Sand pits shall not be used within paved areas and access ways
label | 8ecddf09-254a-41bb-a7e0-9d2d0a22475d |  | note | Not to be deeper than 1500mm
label | ce4221e5-2ca6-4956-81c9-3b2fcb7f9e37 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 8c838edb-7516-41dc-b7ef-3d4a29af2c1b |  | note | METHOD: Visual
label | cc3a7f80-c69b-4bf8-b30a-c21ce354e806 |  | note | FREQUENCY: Each Pit
label | f6b67d55-5637-457d-b82d-eec3edd30b65 |  | note | CATEGORY: IP
label | 97f00217-0fc8-43e2-b639-59d1e3d64bd5 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1364425a-114e-4d96-be9c-ff3dc16af70d |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 87c67b5d-cb85-4455-93f3-bf30ce7e4b09 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.3 Vic Track Pits
label | d9a763db-b2ca-4e56-bd1c-affaf50992d7 |  | note | REFERENCE: L1-CHE-SPE-070
label | 9ea4d317-1765-4d1e-b889-c91211114080 |  | note | L1-CHE-STD-043
label | 5b145268-a096-45f6-b63f-3c4e9c0393b2 |  | note | TS-SP-013 7.2.2.vi & 7.3.7
label | 2cc04287-38fc-4605-911d-6f9119cad548 |  | note | ACCEPTANCE CRITERIA: VicTrack Pits:
label | dfe03678-cea4-4d91-b4b8-b7f8afaa66a5 |  | note | - intervals no greater than 380m
label | 3251c9a5-cf80-4fea-9da2-9a9705b904c9 |  | note | - no lateral deviations of conduit from the straight line between pits greater than 2 metres over the nominal 380 metre pit spacing not all at a single or several distinct points. If this cannot be achieved, then the pits need to be at a closer spacing;
label | 072607ee-ab09-45b1-b2d0-949b6f3f6f11 |  | note | - 4m from rail (if within 4m a physical barrier at 3m is required)
label | 64ba1dec-db2d-486b-8262-21eb25f51e69 |  | note | - Access Roads, Class D lids
label | 0e2fde0c-6c04-4e98-9feb-8e7288c00d8b |  | note | - Footpaths Class C Lids
label | 6803052b-4115-4844-959c-b8b0055f6780 |  | note | - non trafficable areas Class A with bollards
label | 387d6c38-0f8f-4489-b7d0-4e08c904a0f4 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 42361803-22b7-43a9-88cb-5b5117203ecf |  | note | METHOD: Visual
label | 3bb5eef9-3add-4fc9-bc60-7a70ce2ee8a8 |  | note | FREQUENCY: Each Pit
label | 7751d073-207b-4838-b1a0-3e7fd994cf17 |  | note | CATEGORY: IP
label | cc9420bb-7097-40ea-a5f7-9922f2b3a6a9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4d11720d-e4e5-4a7a-82eb-3bd34cf29da6 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ecfcfcf7-b943-46f5-8045-09f21226cf0a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.4 Signalling Pits ,LV Pits, Electrolysis Pits, SCADA Pits, MTM Comms Pits
label | 3e8e77e2-2651-4631-93fc-a142304707b3 |  | note | REFERENCE: L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
label | feff5b06-20eb-420b-8b20-9db46bc2f913 |  | note | ACCEPTANCE CRITERIA: - intervals no greater than 400m (electrolysis 190m)
label | 3332ac39-9c55-4138-8eb0-a13b353cf15d |  | note | - 3m from rail
label | 25837a31-2b85-4d83-a6c7-20e8dd29b896 |  | note | - Access Roads, Class D lids
label | 7878a961-5f9e-4e3c-8f6b-2a0ef879a92b |  | note | - Footpaths and non traffic areas, Class C Lids
label | 32e77685-291a-405f-9f82-e1f347a325c0 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | a21a74a2-f28a-4ce1-9b94-24bbb2c93229 |  | note | METHOD: Visual
label | f975e4de-9e23-4f38-b38c-5c8ef37e3793 |  | note | FREQUENCY: Each Pit
label | c49ea61c-add4-45b1-b83f-99677e3893eb |  | note | CATEGORY: IP
label | 02ca3c76-ca24-4940-a4bd-6e9bb55a5e3b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f7fdb1bd-611b-426a-b043-f55b4f690eab |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6a049397-f7a9-4319-81cd-78f4573dc5c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.5 Additional Considerations
label | 3ce2a761-c73b-4396-8572-516f3fa2c472 |  | note | REFERENCE: IFC Drawings
label | f05a5b87-f356-41a6-b799-9bbe5e6c7b82 |  | note | ACCEPTANCE CRITERIA: Access tracks to pits
label | 65e68171-28c0-4af3-9b7f-6b18202f181b |  | note | Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
label | 1fc193b1-99be-4bd5-b350-acd1b20cadd8 |  | note | Hand rail & retaining wall installed as required
label | e3c6a160-9145-40d2-8cb3-dce838d7a719 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | f38c6916-612b-438b-9aa5-ca202a11d5e1 |  | note | METHOD: Visual
label | ecc73d49-2c6c-447d-8276-826e2566f70c |  | note | FREQUENCY: Each Pit
label | 0921efd5-558e-4f76-a556-973461cd30f8 |  | note | CATEGORY: IP
label | c8aabb07-1211-4bdb-801c-d59d74823cca |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 97cb518c-cc03-48fb-afaf-bf4ea6a7295f |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 5ce7c873-44a7-4296-9dc7-255ba6ff26fa |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Installation
checkpoint-status |  |  | checkpoint | 8.1 Bedding
label | 8280f5be-f32b-470a-b31e-dbd3352974f5 |  | note | REFERENCE: L1-CHE-STD-070 Cl 7.21.u
label | ee6ee37d-1ff5-4ee1-862d-3b967d327991 |  | note | L1-CHE-STD-043
label | 38b2ddd3-cd76-42d1-a87d-bbc455d21b34 |  | note | ACCEPTANCE CRITERIA: 150mm of crushed rock under pit extending 500mm past the pit
label | 897dfe60-65df-4e06-8d32-bbcebede0add |  | note | Drainage arrangements shall be provided at the base of each pit.
label | 8303105c-71bd-4249-a2cf-4344f9d8e193 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 51eeec1d-d570-408c-b588-cd576fb67dda |  | note | METHOD: Visual
label | 2bb3eef7-da03-4ae1-a852-83a63fc04d2e |  | note | FREQUENCY: Each Pit
label | 70af5611-480b-4b3a-8b46-81456568a823 |  | note | CATEGORY: IP
label | 6e0f9db2-e880-414e-ad4e-83cf30284ec8 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2a51283a-1a7c-44ef-8129-e94bfcd44c9d |  | note | VERIFYING DOCUMENTS: Sign ITP and Attach Delivery Dockets
text | 23932592-4547-4850-9a8d-b32e76149fac |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.2 Pit Orientation
label | 808ed407-744b-4ca0-86d4-378ee6d4df35 |  | note | REFERENCE: IFC Drawings
label | 975960ac-0900-489c-8c3e-cc7b8614af78 |  | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
label | c28ae9f1-7d6e-4ef4-a295-15608cf32dd5 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | da956230-e742-478d-a0be-95c8ec3951b5 |  | note | METHOD: Visual
label | 7e4d9d81-1cb5-4f57-9865-ae24c25cf547 |  | note | FREQUENCY: Each Pit
label | 53f7076b-940f-4c5b-a99d-4c0e29a456b8 |  | note | CATEGORY: IP
label | a3c48b35-c09c-4ec8-b79c-bb9e38adcaa8 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9ed83006-4de1-4b7d-b97f-eb4803f018b4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 06ba42b3-018b-4060-afd4-f5ff2727b73a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.3 Pit Installation
label | d04ee5d3-23e1-4e27-a474-96fb1e432114 |  | note | REFERENCE: IFC Drawings
label | a3ce7367-53d1-464b-9754-7d135a9a57ba |  | note | ACCEPTANCE CRITERIA: Pit installed to design specifications
label | 32e42038-0b22-48f6-8110-57ba3c869d78 |  | note | Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
label | 625cc3e1-636b-4120-a99d-0203c1a1b156 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | a259a608-5848-4141-9993-0f7990f27254 |  | note | METHOD: Visual
label | 2414e3b1-2451-4326-b32a-5eb820945ea0 |  | note | FREQUENCY: Each Pit
label | b4adf293-6f67-4387-b435-7068f7a4a59c |  | note | CATEGORY: IP
label | ef970011-46be-442c-9db7-592aabdede03 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 31d0d84f-c946-4062-8b36-f1f227571cae |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 4e9b5c45-8ff6-4f7e-a31d-cd5a10e77c2a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.4 Pit Greater than 10ft
label | 2a0f554c-6593-4b9e-9f00-5d3fb6009788 |  | note | REFERENCE: MRPA Procedure
label | d74ac2ea-ff18-4e05-8d28-ad12f054ce1d |  | note | ACCEPTANCE CRITERIA: Each pit if non standard lift (greater than 10t) the following is required:
label | 77684674-5172-4f70-817e-816603d9800e |  | note | Certified Working Platform
label | 71d41fa3-2c1b-4a88-8095-ce2ece2dadc6 |  | note | Certified Lifting Anchors
label | 30e91272-b763-437a-94d0-340951653687 |  | note | Approved Lift Study
label | 71c4c4a8-0103-4a2a-842e-b2133ea7ab9a |  | note | Check Birth Certificate
label | 60f7ee56-7dd9-4eaa-af71-bfca81eba3df |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | f2dae682-d8ed-45c4-9bd6-404edadc90b0 |  | note | METHOD: Visual
label | ae7f23d3-e6e3-4e0f-b518-9e168636557f |  | note | FREQUENCY: Each Pit
label | a5e99368-745c-4be8-9d68-221237e7792e |  | note | CATEGORY: IP
label | 78fe235b-c6ae-4ff3-bc48-9d1086f67e75 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 603aaa26-aece-4035-a01d-cfa189aef05f |  | note | VERIFYING DOCUMENTS: Sign ITP and Attach: Geotech report, lift procedure, shop drawings
text | 5a87b589-5fe9-46e2-b75b-c54c4982bfe2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Fit Off
checkpoint-status |  |  | checkpoint | 9.1 Conduit Entry
label | 0dbaa054-ce78-42ce-87a1-2b3b1ca7c04d |  | note | REFERENCE: L1-CHE-SPE-070
label | 73733c3b-b076-4687-8138-9313f1544527 |  | note | L1-CHE-STD-043
label | a41de2bb-d0a3-4df6-bd64-0ae2d7789735 |  | note | L1-CHE-STD-070
label | c83fd0d5-6a7b-4165-9e9c-5a165bfad9cc |  | note | IFC Drawings
label | f925c1b7-d08b-4dc0-8d1a-7d350515e26a |  | note | ACCEPTANCE CRITERIA: Lowest conduit 100mm from the pit chamber floor.
label | a5160531-24bf-4441-ae61-5e0efc81d9a0 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 23d84b05-52b4-4ee4-a8cf-e327b3473ba7 |  | note | METHOD: Visual
label | e3ffe38d-8008-4ed8-a7f9-0a86b462234a |  | note | FREQUENCY: Each Pit
label | 3aef916d-3c92-45fc-88f8-ce98a2723477 |  | note | CATEGORY: IP
label | e7c7d2d9-c63f-4519-8e1c-bb47f6164615 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 418bd85e-6320-43c0-abc8-4b096de1aa9a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9d592fa3-6c54-4c69-a3e5-16d1738825db |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.2 Tracer Wire
label | 2d9e6672-2abc-470c-8f32-ee9a5975a317 |  | note | REFERENCE: L1-CHE-SPE-070
label | 0793866b-d71d-4652-87a8-7b24a7b67a27 |  | note | L1-CHE-STD-043
label | 0b09e06e-1f26-4e9b-8217-47df361e24e7 |  | note | L1-CHE-STD-070
label | 3e7fc1f9-4da6-47f0-b1bc-e0fff3796b79 |  | note | IFC Drawings
label | 668903bf-dc1b-4cca-acb4-1fada94670aa |  | note | ACCEPTANCE CRITERIA: Warning tracer wire for Vic Track routes to be drilled into pits and crimped off.
label | 439b344b-df74-4018-b8ff-8edc706f1a89 |  | note | If tracer wire broken needs to Crimped
label | 70f5dc56-7399-42cf-bb29-88f8aeae51a2 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 77e3fe01-6ff0-46f7-8101-6a4b10720886 |  | note | METHOD: Visual
label | cc9a1ec1-cd68-445a-97aa-ab5242daca85 |  | note | FREQUENCY: Each Pit
label | 3b4a6457-8eb4-40bc-ad0a-b14f258e4ac8 |  | note | CATEGORY: IP
label | e85eee52-de99-44cc-82b2-422b05183239 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2992f531-6c5c-4200-9403-cedb92a0e476 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9570c396-1c28-4360-bab6-628bddfef7d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.3 Spigots and Bell Mouths
label | 3d8ecba8-55b1-42c4-8cb6-ab538a32709a |  | note | REFERENCE: L1-CHE-SPE-070_9.3.4
label | 33d46f82-4849-40e2-bcbf-6af974e25075 |  | note | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
label | 8667d82c-8cba-4fc3-b2f0-e86cd2ee913f |  | note | HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
label | af7cf2bd-f6e4-4804-b74c-f94254f41e58 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 2cbd5aed-269f-4726-977e-da6d0582f1eb |  | note | METHOD: Visual
label | f89deea6-c356-48bc-a6d5-3050c62915c1 |  | note | FREQUENCY: Each Pit
label | d2078d8a-670a-4040-9c60-814b265fcb86 |  | note | CATEGORY: IP
label | 9c6784d6-e160-40d7-a4ab-f4df5b80402d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c33c3e63-89ce-4a38-b1a0-7793d0b173b9 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 92bed7f8-2fbe-4cef-9df2-f207f30a1593 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.4 Draw Ropes
label | dd4bc9ce-07e8-4e54-a36a-5da09a868d76 |  | note | REFERENCE: VRIOGS 012.2.1
label | 464c0921-8d6a-45a8-8d6c-600cc6965a98 |  | note | ACCEPTANCE CRITERIA: The draw wire shall be continuous for the complete length of the conduit run.
label | d2f52111-af0d-405e-8214-62cbd571ca13 |  | note | The draw wire shall have a minimum of 2 metres of slack within every pit.
label | 89d55617-6222-4c76-89c0-ca696e5b636b |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | fa20c302-60a0-48e0-88ab-9e2518046c45 |  | note | METHOD: Visual
label | 5a8bdf94-8174-444c-a66e-43eaaddc04ae |  | note | FREQUENCY: Each Pit
label | 194588cc-eee6-461f-97d2-d5ce0f638049 |  | note | CATEGORY: IP
label | 42af5e6c-9bca-439b-9d64-8391ce77e251 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c8feb82b-980f-4acc-a50b-447e4aa516ee |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c5aa6eef-aa7d-4e17-af2c-7d9ce1917984 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.5 Backfill and Compaction Testing (if applicable)
label | bdda359d-f9a0-45dc-b6d2-4a71f84a937c |  | note | REFERENCE: L1-CHE-SPE-070
label | 25304c42-a512-496a-af14-8ec9c49a48af |  | note | L1-CHE-STD-043
label | ef20747e-f4ba-4ca3-8566-3f08f211931a |  | note | L1-CHE-STD-070
label | 94d4956d-49ca-42af-8bab-f6e710a5fb01 |  | note | IFC Drawings
label | 2283d90a-fae8-4230-b113-ae98591d56fb |  | note | ACCEPTANCE CRITERIA: Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
label | 24e8285b-a02c-41a0-b98a-a7b28d46f80e |  | note | Sand within sand pits to be compacted in layers no more than 250mm layers
label | 16606a91-a160-4348-b46e-46de45d6dd22 |  | note | Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
label | 55e198d5-ed72-4fbc-ae77-d1862cb16b38 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 2a738038-5093-4ab4-83e4-357393bbe70a |  | note | METHOD: Document Review, Visual
label | cfeba53d-408d-4d90-953a-512cd5109532 |  | note | FREQUENCY: Each Pit
label | a83d7535-c7e0-4c80-9a1e-54039f8c3402 |  | note | CATEGORY: IP
label | 1141e9fc-a10c-4841-863f-f3dfc80d8736 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2e3c71b9-03f5-4099-9dec-5bdeab4c4035 |  | note | VERIFYING DOCUMENTS: Sign ITP and Attach Test Report
text | d3e6504c-d598-4f02-9735-ade8aa75cf33 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.6 Step Irons
label | 5295e0b5-ed77-479c-bdd2-72b1e60dad5d |  | note | REFERENCE: IFC Drawings
label | a7386756-cfa7-4d0e-8b78-4d15559677ed |  | note | L1-CHE-SPE-070_9.3.7
label | eee3af14-cdbe-454f-a764-5d1a35e27fe4 |  | note | L1-CHE-STD-043_14.2
label | 21e3517e-41c4-4718-8698-8dc4f0007807 |  | note | AS1657
label | 2ea95bee-c2c6-4694-9cdf-cf8ecf035744 |  | note | ACCEPTANCE CRITERIA: Unless otherwise noted on IFC drawings, the below is required:
label | 354f8e62-d431-41b2-be1f-7aad5e14ab3a |  | note | High Voltage Pits: Step irons/rungs to be installed if pit is greater than 1.0m in depth (including lid thickness)
label | 37952c79-0b6f-4afb-b542-552162169883 |  | note | All other Pits: Step irons/rungs to be installed if pit is greater than 1.2m in depth (including lid thickness)
label | 91871b32-e8e9-4ac3-8726-95f21e2ecd58 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 759f3d09-9535-47de-ba86-d86fae2e2bef |  | note | METHOD: Visual
label | 46d94e6e-9b67-482e-9313-a2ab34791c08 |  | note | FREQUENCY: Each Pit
label | b6f179a7-f19e-41ef-9bfc-25789315e0b3 |  | note | CATEGORY: IP
label | b60a12cb-9d51-456b-9fae-7f2911657977 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cebc8478-a1b9-4778-80ae-86374ac79a96 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ea2597a9-950e-4c6e-893d-2be44312669b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.7 Spare Conduits
label | aaa6bc3b-10e2-4794-8745-20b4f26cf9e2 |  | note | REFERENCE: L1-CHE-SPE-070
label | 2b8e261c-652d-4838-a6cf-62144a6826a7 |  | note | L1-CHE-STD-043
label | 3884a487-60ac-4c8c-a1cc-d77730ff1355 |  | note | L1-CHE-STD-070
label | 22707b0d-c774-403c-a452-5757a33d16e5 |  | note | IFC Drawings
label | 634b2488-ad1f-4281-8269-68b8fbb82a8e |  | note | ACCEPTANCE CRITERIA: Spare conduits to be sealed and to be included on survey report.
label | 61797612-863f-4f91-a14a-d19cb817a7a9 |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 1c560560-3216-4535-bbd6-c4429323e326 |  | note | METHOD: Visual
label | 9a73bf4b-3536-43a6-8300-4c77f56251c8 |  | note | FREQUENCY: Each Pit
label | 4e290878-f61b-44a9-9548-98c5ba70c844 |  | note | CATEGORY: IP
label | 5c228011-e014-4cf1-bfdc-9ee1f2f29d27 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | a8aeb13b-5ba6-494d-aa00-af0cae7270aa |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 42bc4f96-2618-4d53-b324-7a3e8946a969 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.8 Pit Labels
label | 94af5d61-8fb1-4d2a-9e2b-2a164121ee87 |  | note | REFERENCE: L1-CHE-SPE-070
label | d74ae488-3eea-4ce2-9a3f-06cb63fd7482 |  | note | L1-CHE-STD-043
label | ef317cfa-2879-47cc-9660-69807e13fd7d |  | note | L1-CHE-STD-070
label | 7d152893-ac12-46ab-85d8-db96f346888a |  | note | IFC Drawings
label | f3c72aea-f510-45f2-8352-481cab621bb5 |  | note | ACCEPTANCE CRITERIA: Pit labels Brass Label (30mm x 150mm)
label | 61140515-5fde-4cb3-99fb-f26836c0bf8d |  | note | - HV: DANGER - Railway High Voltage
label | 10fa611d-70bc-407a-955b-239a493b6226 |  | note | - VicTrack: Victrack Comms
label | e79c1639-705e-4cd8-b98e-cfdbcc5a27c0 |  | note | - Signalling: Rail Sign Comms
label | 0ab149e5-7072-46a7-93a7-fc7997035939 |  | note | - LV Pits: Electrical
label | 00c6162a-0499-4602-943c-ff7d12e680f9 |  | note | - Electrolysis: Electrolysis
label | b755ed29-4934-448d-a09c-07a6dea54c4c |  | note | - SCADA: Rail Sign Comms
label | e4a05ef2-df71-4183-b891-6c7ff2d2db0d |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | b71194e0-008a-4352-bee4-f5cc718dff1d |  | note | METHOD: Visual
label | 8d78270d-5ac2-460e-8876-fd9046172ade |  | note | FREQUENCY: Each Pit Lid
label | fc7293c8-2f6d-417e-8785-b6c12d0bb1c5 |  | note | CATEGORY: IP
label | 168eed5e-bab8-49a0-b71d-46ecef9adb97 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | eccf9650-1cf4-4aa6-9182-d1e9aaa2485b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 10838d2d-822b-4df1-9475-7f206762db7a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.9 Pit Numbers
label | 5f2554e2-1502-4390-a039-2b1ea2b5673d |  | note | REFERENCE: L1-CHE-SPE-070
label | 875df38d-275b-470e-87b1-9bdc8b2fce9f |  | note | L1-CHE-STD-043
label | cae90b6c-7711-464c-92ed-a9933883489e |  | note | L1-CHE-STD-070
label | fad2b63b-bfba-4062-9ecb-c270235a5b19 |  | note | IFC Drawings
label | a94a716a-a245-4f90-8edc-d2ba2fbd20a7 |  | note | ACCEPTANCE CRITERIA:
label | 1ab33e56-aff0-4ebd-8189-2f4685f3ba8b |  | note | Pit Number Brass Label (30mm x 150mm)
label | 735fcc10-2cfd-47db-b98b-991c08bac045 |  | note | - HV (22kVV Feeders): ###HV
label | 2d1c92f7-5776-4420-91da-4a9722f99a4f |  | note | - DC (HV Feeders for OHLE): ###DC
label | ca87e779-81a2-446a-8372-32d7a710f4aa |  | note | - VicTrack: ###C
label | 61b4deb7-f76a-4510-8f35-e0c492cc96d2 |  | note | - Signalling LV: ###SL
label | f9400996-de14-4642-9951-3b332c9eb17d |  | note | - Signalling HV (2.2 or 3.3kv): ###SH
label | bebdb258-de65-43d8-b4ec-89130900896e |  | note | - LV Pits: ###L
label | 4a9fc22f-270e-4080-959f-fe373c4314fc |  | note | - Electrolysis: ###E
label | ad79ab64-ec1b-47b1-af30-813b22215d2d |  | note | - SCADA: ###MS
label | e3eff17f-c186-41a2-afb8-796ea25e0169 |  | note | - MTM Comms: ###M
label | 4a15654d-af01-4ab6-84a2-4f76f3733900 |  | note | METHOD: Visual
label | e495613e-5bf7-4785-8e44-9576014d1aef |  | note | FREQUENCY: Each Pit Lid
label | 57824ef4-2a7f-4e14-90f0-7b258d33e040 |  | note | CATEGORY: IP
label | 7d694c16-28a3-464a-b3c9-076f083a1b9d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3bb3c695-f098-49c0-9e4b-a4cb37d4916e |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 670d50f1-ea26-4ce1-8eab-ef7ec4015ee4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.10 Mandrelling
label | e799ef98-84eb-4a45-843d-022f1026be3a |  | note | REFERENCE: L1-CHE-STD-070 Section 16.1
label | 8f55d906-8959-48e8-9e67-c713d1ac1803 |  | note | The mandrel shall be solid, have diameter not more than 12mm smaller than the internal diameter of the conduit and be a minimum 230mm in total length and 130mm in flat length. It shall be pulled through every conduit in both directions by hand or with a machine to ensure their integrity.
label | 06edac78-59db-4e95-b540-8c360f112e81 |  | note | MTM/Victrack Witness
label | c0b33a1a-e435-4688-9b29-f8b54a5d2f75 |  | note | METHOD: Visual
label | 373d712d-76a3-469f-ad70-b4a687ee674b |  | note | FREQUENCY: Each Conduit
label | 6862688f-8310-4f41-8565-9083af2db49d |  | note | CATEGORY: HP
label | dae77ff2-d772-47d6-93ff-bc3a8653cd00 |  | note | RESPONSIBILITY: SE, NA, MTM/VicTrack Rep.
label | 8640b1df-997f-4fcc-a691-1777504a3aa7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | aa77c315-8845-46de-8d06-31cd53a4aaba |  | textbox | Date Completed:
checkpoint-group |  |  | section | Protection and Labelling
checkpoint-status |  |  | checkpoint | 10.1 Non Trafficable Pits
label | e0676b87-2134-4fbc-9b00-7c0bc1beec53 |  | note | REFERENCE: L1-CHE-SPE-070
label | e9155a0e-3f92-43be-aa8d-d0637617ea02 |  | note | L1-CHE-STD-043
label | 1c0fba99-a55a-4586-9a66-1988f8eedef9 |  | note | L1-CHE-STD-070
label | 44395b10-ba95-4271-a40f-9c67688cb45b |  | note | IFC Drawings
label | 3d2a1670-7a2c-44cf-a606-f0cf5baa8675 |  | note | Non trafficable pit lids to be 50mm above FSL and to have 2 x white bollardes installed at the corners of the pit.
label | cd565c61-960d-44d6-b41c-88c47e2f103f |  | note | METHOD: Visual
label | c462d61b-ac0b-412b-9a28-422706c45ce7 |  | note | FREQUENCY: Each Pit
label | 30f1708d-1d0a-4777-9ca1-4fe7ae525fe8 |  | note | CATEGORY: IP
label | 2e5dd140-3078-4195-8580-969cdf7e8fec |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 449ffd3d-17c2-4820-9a3c-5d9515520ff3 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 8532b98f-9060-4901-977e-f8969527d03d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.2 Sand Pits
label | e93329d6-fd45-4a1a-9959-7914acf80978 |  | note | REFERENCE: L1-CHE-SPE-070 Cl 9.4.3
label | b4161d2f-a9c9-4ea0-af93-ec69a098e1d8 |  | note | IFC Drawings
label | 0bac8839-870d-4bdd-83b1-1397f254f597 |  | note | ACCEPTANCE CRITERIA: Sand Pits (HV)
label | 81d50ab5-046e-480c-9bbc-cda0d4052925 |  | note | - 4x yellow posts installed at the corners of the pit and 2 of which shall have cable route markers attached
label | db03b7ea-c3f1-4035-9411-e83c2807eba1 |  | note | - If posts are impractical, 4x monuments with cable route marker plates affixed and a cable route marker nearby indicating position of the pit
label | 448863da-cf34-4987-a7da-31f088bd0944 |  | note | METHOD: Visual
label | 9ad661f0-f0cd-47c4-9de1-688fd7ae940f |  | note | FREQUENCY: Each Pit
label | 763b9640-9951-4348-87e4-a23871b52ada |  | note | CATEGORY: IP
label | eaa65c51-5742-47ef-9825-60c07fb0e5d8 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3e87899d-a833-4f64-a2af-13f688eaa72c |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 4ed03c86-11f9-4c82-8efb-eeba00d4dfd2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.3 Cable Route Markers
label | 1abec983-5420-4799-8928-cbd5d10a5502 |  | note | REFERENCE: L1-CHE-SPE-070_13.2
label | 5f59c202-0c14-476b-a079-6d147d25b634 |  | note | STD_E0169 and STD_E0170
label | 761532ea-6598-464d-a2a2-e4325b51ea32 |  | note | AS 4799
label | ffdeb2a4-dc1c-486b-b91d-99d9b6f54379 |  | note | STD G0003 and STD G0004
label | ef20ef0e-269b-4369-a1d4-d3c84130c9f7 |  | note | ACCEPTANCE CRITERIA: Cable Route Markers
label | 35cfeb08-52b0-4da6-99b0-a0f96f9ee9ae |  | note | - points entering & leaving the rail corridor
label | 33f4852c-6b6a-4fd6-b0a4-1379b495139c |  | note | - no greater than 100m spacing
label | 3ad9e259-f6df-40dc-89d5-dbb00c28089a |  | note | - Change of direction (more than 5 degrees)
label | f268ed91-b2ab-43fb-8e38-1840461252c0 |  | note | - White posts with marker plates for conduit runs
label | 13cf052a-3c36-4f74-811e-e5303124f2c3 |  | note | METHOD: Visual
label | 68dc5199-c3bd-4395-9a3a-0560933556f4 |  | note | FREQUENCY: Per Cable Route
label | aeb6d0ad-080f-4bf6-a64f-223e8221b557 |  | note | CATEGORY: IP
label | a072135d-b1d5-4739-afd0-0a9ed3cea35a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e1beabb5-5f21-496a-b2a4-a2e38bbeb7c1 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c1efbd47-d1b2-4650-a81e-bf1507acfcf2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Cable Route Handover
checkpoint-status |  |  | checkpoint | 11.1 As-built Survey file
label | 65f1b423-a21e-41c7-8ea4-965f836fe34e |  | note | REFERENCE: L1-CHE-SPE-070 Section 13.1
label | dc4ab8bd-c214-4db0-9329-feca9d7de059 |  | note | ACCEPTANCE CRITERIA: Survey report to include but not limited to:
label | c734d7cc-9675-4511-ac14-29942b42952a |  | note | - Cable joint locations.
label | 5b80515f-64c7-4d50-9f32-6217e6701c58 |  | note | - Cable pit locations (Corners)
label | e5adc0bd-c518-463a-b42a-8abe99e76455 |  | note | - Pit dimensions & pit lid type
label | 120c5319-2cf6-4b51-a69e-72f56bee5cbe |  | note | - Under line crossings
label | 3604be7c-9b95-4777-89ed-936a7613d3b8 |  | note | - Under road crossings
label | 6dc6b3ed-6151-4926-a939-0fe74e589aa8 |  | note | - Changes of direction
label | c515d506-d95d-4b52-b690-87bb504ea3f3 |  | note | - Spare Conduits
label | bc27c38b-cf6b-4ebf-b0b5-6601de4e15ae |  | note | - Conduits labelled as per trench profile
label | 415e03ad-4fba-44bb-aa76-1c1967d775a6 |  | note | - every 10m
label | bcf98ab8-5587-4dbf-b120-e9cf85e14dec |  | note | - Other significant points of the cable route
label | 155bf22f-46cd-403a-90a5-0a3e904205a5 |  | note | METHOD: Visual
label | 4275a477-df24-4c39-8c1d-92b89c326f77 |  | note | FREQUENCY: Per Cable Route
label | a13492b1-3a3d-474f-85e3-c7cb29b47bac |  | note | CATEGORY: IP
label | 0680a0a8-0a6e-4d70-b23e-71019f315631 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ac335dd6-b9ef-4e42-94c6-08bc30350ba2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 90b4147b-441d-4e4d-9373-fd0a41f5a05e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11.2 Engineering Redline mark-up
label | bc0d2049-b5dc-40ea-99a5-28019b81f087 |  | note | REFERENCE: IFC Drawings
label | 9e6e6b88-8a8c-4d40-a364-5db5ed0266a6 |  | note | ACCEPTANCE CRITERIA: As constructed cable plans shall be provided for the entire cable installation and in accordance with AS 4799 and the PTV Infrastructure Drafting Standard.
label | f927fc5e-7c5e-41e2-b8a2-94a56354cc86 |  | note | METHOD: Document Review
label | cf89ca87-d174-4c89-a674-65a5dfdf494d |  | note | FREQUENCY: Each Design Pack
label | a95bec2b-2771-4090-9ac3-a7c9e69e4d11 |  | note | CATEGORY: IP
label | 78e155f1-e606-4090-ad75-ef2a38e16e61 |  | note | RESPONSIBILITY: SE/PE
label | 851e25c4-8a74-4937-af10-0b8123662173 |  | note | VERIFYING DOCUMENTS: Sign ITP and Attached RLMU
text | aea3a1e5-772a-48ad-8a02-5cb9f98f35cb |  | textbox | Date Completed:
checkpoint-group |  |  | section | Cable Pulling and Terminations
checkpoint-status |  |  | checkpoint | 12.1 Cable Pulling
label | cf10c9ab-0d56-4956-af58-74960a92036a |  | note | REFERENCE: L1-CHE-SPE-070
label | 08128dc5-4b7d-4155-a2ad-fe75e98cb80a |  | note | L1-CHE-STD-043
label | d952a606-4623-4bbb-b523-ba55d4c5f772 |  | note | L1-CHE-STD-070
label | 0a9e7564-7a25-464e-b642-6d6300707d29 |  | note | IFC Drawings
label | e66ef8e6-83d5-4222-a2df-6558015e1e37 |  | note | ACCEPTANCE CRITERIA: Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
label | b4656f7c-964f-4efa-962b-3d5d89fc8108 |  | note | METHOD: Visual
label | fdc99f57-2e0e-48c0-8c9d-584367681b79 |  | note | FREQUENCY: Per Cable
label | 9bf4be57-fc33-4eb4-8533-a92d3c78fffb |  | note | CATEGORY: HP
label | 41c4bf4c-3691-4a94-87d0-ae391a702242 |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | c0460eea-6040-45e4-abc9-3b64e3cbba4f |  | note | VERIFYING DOCUMENTS: Sign ITP
text | b972c04b-679e-423c-a293-ffcfa46d70dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.2 Cable Labels
label | f2ec1cfa-5dcc-4406-85c9-2ee45d441ccc |  | note | REFERENCE: L1-CHE-SPE-070 Section 13.3
label | 396fb2be-e505-4cdc-bc47-804b5314a87c |  | note | ACCEPTANCE CRITERIA: All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints
label | 8df7d6bf-3697-4df6-84eb-bdab4bd80a3e |  | note | The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
label | b2140ee1-8228-4be5-a428-e6796a96ec46 |  | note | METHOD: Visual
label | 86b90db1-5690-4f18-89d2-076704da30f4 |  | note | FREQUENCY: Per Cable
label | c2208897-bde2-4a0d-8cd2-3e51ff878205 |  | note | CATEGORY: HP
label | 24b79dc1-f903-4158-a4a2-a29280a49441 |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | eb1e92a7-461d-4c36-93ff-38b87dce30a6 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 84167c14-0953-41f3-940a-31dfc55ee6b6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.3 Cable Labels
label | 0089965f-59c3-4e27-85de-f19e44be7e6c |  | note | ACCEPTANCE CRITERIA: Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
label | 5ca7975d-88d4-4f1d-ad7f-b4f24bde0c09 |  | note | METHOD: Visual
label | 37915173-8d79-40c4-9645-53b30acfb4ed |  | note | FREQUENCY: Per Joint / Termination
label | 8489172f-2f5e-4fd8-9580-ceff00b92218 |  | note | CATEGORY: HP
label | 42833d69-0814-4d64-92f3-68afb6dd5f0b |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | caa039d1-c881-41ad-8fdb-9ac663b766b7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 1944cdaa-85a4-4a84-a70c-6339a0000604 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 13.1 Handover Check
label | cb51c90a-fba2-471b-b34c-ba3820a31505 |  | note | REFERENCE: IFC Drawings
label | 5402d154-e9e9-4af5-9961-b7061418e399 |  | note | ACCEPTANCE CRITERIA: Handover check completed for Testing and Commissioning.
label | e9023818-b59c-4724-96b9-7e8ec1e631eb |  | note | METHOD: Document Review
label | 8010122a-72ae-42c8-89da-844ae14f1c60 |  | note | FREQUENCY: Per Lot
label | baa09f1a-faa3-4bfd-aae3-006c36b4ede7 |  | note | CATEGORY: HP
label | ed5d2d08-448d-4443-b402-e5ae36fcd808 |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | 5bc9ec8b-e2bf-4c22-a770-faa658466929 |  | note | VERIFYING DOCUMENTS: Sign ITP and Attach MTM/Vic Track Check Sheet
text | fa2f4222-2c50-47dd-93f7-0342f0e15de5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 Testing and Commissioning
label | f3bb71d1-d4b1-454d-85d0-b5088881d7e4 |  | note | REFERENCE: IFC Drawings
label | 21e61d6d-09bd-46ad-86a6-320929e7bd08 |  | note | ACCEPTANCE CRITERIA: Testing and Commissioning to be completed
label | 94040a93-143e-4360-bda6-4a84670f86be |  | note | METHOD: Document Review
label | e4c460ac-0d60-4c1e-950b-dd6f2b19ce8b |  | note | FREQUENCY: Per Lot
label | e57761cb-3b90-4268-a45d-4651e67b0077 |  | note | CATEGORY: HP
label | e531b66c-b1e7-4560-bfe4-88bb74c19422 |  | note | RESPONSIBILITY: PE, MTM/VicTrack
label | 7792b1b3-78eb-4385-8640-9185b62a5e56 |  | note | VERIFYING DOCUMENTS: Sign ITP and Attach T&C Report
text | 2e715e59-d579-43eb-b3da-a77ad2a13465 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 273e8ce9-918c-4d7c-98b4-869dd4559353 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 4d08cf7d-8f4f-42b2-a649-16d426ff0662 |  | textbox | Name:
text | ba1484cd-9dd0-4482-887f-5ffe3ff21178 |  | textbox | Position:
text | 17b31d9a-7c3b-4ec2-93ce-fcc757854141 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-Rail-Formation Structural Fill (Supply & Installation) MTM Rev 0 | itp |  |  |  | Yes | ITP-Rail-Formation Structural Fill (Supply & Installation) MTM Rev 0 | 39f36880-e53f-4197-9145-bcaf6b704e29
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 4a1210d7-e4e0-4353-97ee-13107a3d1017 |  | note | Document Title: ITP-Rail-Formation Structural Fill (Supply & Installation) MTM
label | e6239645-68e5-43cf-940d-c7a3b296187a |  | note | ITP Description: Formation Structural Fill (Supply & Installation) MTM
label | a333bd64-1152-44f1-b31d-eec21462a3a0 |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | a1f71fcc-d7ac-44df-a703-b1c6124faa96 |  | note | Revision Number: 0
label | 41237337-92d6-477d-ae22-1a3a156422a6 |  | note | Revision Date: 30/06/2021
label | 0bb29374-c6ea-4abb-8266-9b6c80f2aeea |  | note | ITP created by: Yasna Naicker
label | dd9c17b2-6196-4089-9aa2-6dbb4a9a7739 |  | note | ITP approved for use by: Romualdo Magpantay
label | 93844edf-93f8-449a-a58e-72026c81c6f9 |  | note | 1.1 - Drawing Pack - Rail Track and Civil - MRP-016-C-ACD-REP-03-NWACPW-0001
label | 7079844a-fcf4-45c0-9e7e-6436d5ced612 |  | note | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification - L1-CHE-SPE-178 (VERSION 2)
label | beb8a8d6-6681-4611-a2e3-8e34c0c680cd |  | note | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard - L1-CHE-STD-029 (VERSION 3)
label | 9ffcacab-08b4-496e-96e4-21c550d9ab49 |  | note | 1.4 - Australian Standard - Methods of testing soils for engineering purposes - AS 1289
checkpoint-group |  |  | section | Material
checkpoint-status |  |  | checkpoint | 2.1 Structural Fill Material
label | 5424d49c-7b6a-4cf0-8ffe-55dcfc9c9e6a |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.3
label | 33446691-04b6-4493-af58-7d3997229312 |  | note | Table 4
label | 73746ef6-aa2d-4c27-9ab4-3a78d8eb7708 |  | note | ACCEPTANCE CRITERIA: Structural fill materials shall have the following properties:
label | d707450c-d181-4fe4-a333-a1e520b13871 |  | note | % passing 53.0mm sieve 80-100%
label | cd6b80ec-cd53-47c6-83c6-4c56bcd5d110 |  | note | % passing 2.36mm sieve 15-100%
label | 68563efb-fddf-4d2f-9ac2-f34478558a00 |  | note | % passing 0.425mm sieve 0-70%
label | 5a0e957b-80ac-4c0a-9a70-189de1abe850 |  | note | % passing0.075mm sieve 0-30%
label | e3794e17-6691-40d5-861b-2f1deea493b4 |  | note | Soaked CBR 8% min compacted to 100% standard dry density
label | bd377406-ba87-4e90-b738-e6d4a7635de1 |  | note | Liquid Limit 40% Max.
label | 6dc89c22-433a-4701-b204-65d59d5ffb50 |  | note | Plasticity Index 20% Max.
label | 2d82218d-7ddf-4314-a9e3-ff33e9ac8873 |  | note | Dry Density 1.8t/m³ Min.
label | e6ebed39-6856-4c27-80a5-3edc8f45afbe |  | note | Refer to AS 1289 for Tests
text | b83e0e5c-30d2-4177-aed0-ef54dcfb4071 |  | textbox | Team Binder Approval Number
label | d0ef87ba-8f09-4ec0-a07a-98fc25afe7f0 |  | note | METHOD: Test
label | 08d585b7-5c07-4b09-a26b-45777183ca5a |  | note | FREQUENCY: 3 tests per 1000m³ , 3 tests if 500-1000m³ , At least 2 tests if < 500m³
label | 5b2c0fe1-df5e-4472-9128-43572d2c2ae6 |  | note | CATEGORY: HP
label | 791c0069-a9f1-48e3-9dad-0d401f6192b0 |  | note | RESPONSIBILITY: SE/PE
label | 9c0b889d-735f-45bf-81fa-6f4b34eeb2c3 |  | note | VERIFYING DOCUMENTS: Supplier NATA Material Conformance Certificate
text | 8b67d664-92e4-4a6f-a72b-62c57e2adcbf |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Structural Fill Preparation and Installation
checkpoint-status |  |  | checkpoint | 3.1 Survey set out
label | 4d5fd110-dfe0-4b18-862f-623bb07c65d7 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 8.2.1a
label | baf6ea48-681e-4a75-aed8-746c497e60ab |  | note | ACCEPTANCE CRITERIA: Survey control requirements for setting out and validation of foot prints, level & slope angles
label | 035080a0-5da3-4af2-a453-f2e07b375918 |  | note | METHOD: Visual and Measure
label | 44f95ae1-4a0a-42b7-aa76-37e7aebe76c2 |  | note | FREQUENCY: Prior to Commencement Each lot
label | 7e75b943-7487-4b20-8d4e-fabcc6e01f36 |  | note | CATEGORY: IP/SP
label | 1cc546c9-00f0-47ac-a94f-21070eb74e6a |  | note | RESPONSIBILITY: Surveyor , SE
label | 757044f6-bcab-43d5-a7be-4c931a47fd68 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 68433734-87ca-4b30-9e84-b7f3fbe95fcf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Structural Fill Preparation and Installation - Undersubgrade Assessment
label | 300e96c9-6824-4822-87dc-bf0d229ac7a0 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.3
label | a93923c0-77db-483f-8f7f-7c0ad398d5a9 |  | note | L1-CHE-STD-029 - Clause 12.0
label | 22b98285-b36a-4ca5-a870-494502a797e4 |  | note | ACCEPTANCE CRITERIA: Where Rail Subgrade CBR < 3%:
label | cd64e51e-5eb8-4e53-bf8e-cbfa4347ee9d |  | note | Required minimum depth of structural fill is 1000mm
label | 27385ed7-2b0f-49a0-af09-ab621fe90e08 |  | note | 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | b3d6a734-4979-42e9-ab5b-e07bb69e1d1e |  | note | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | 3dabfbdb-9d8e-4ced-b611-8803c1eab224 |  | note | METHOD: Standard Compaction Test
label | 643b8edc-2d9b-4740-b138-2dfcd6b82718 |  | note | FREQUENCY: each lot
label | 58f2ecc6-c069-4754-b8d1-3d9635f61c4d |  | note | CATEGORY: HP
label | ebaeaa50-a6fa-4369-ad61-6922f6e2600f |  | note | RESPONSIBILITY: SE/
label | 00a17bac-e860-4aaa-b0dc-1e7ac0665692 |  | note | VERIFYING DOCUMENTS: Sign ITP Compaction test result
text | 018748f7-738d-43b1-8e50-70d1ac78c8d7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Structural Fill Preparation and Installation -
label | 0fb5fb7e-94ae-4e8d-b6b3-f610285f3158 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.3
label | cf872205-54f1-45f8-a227-ce1435dc30e6 |  | note | L1-CHE-STD-029 - Clause 12.0
label | 9c732cb9-0b13-492e-89fa-1c51c5979013 |  | note | ACCEPTANCE CRITERIA: Where Rail Subgrade 3% < CBR < 8%:
label | 66879711-3690-45d6-90a0-c872acf188d9 |  | note | Required minimum depth of structural fill is 500mm
label | 9333e946-4fce-4a9b-8909-1ee3dce9f602 |  | note | 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | 5d52d480-7fbc-4b19-84b2-557ff314c5d5 |  | note | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | 1f99eede-6d16-49f9-9ecf-8e86e4279f3c |  | note | METHOD: Standard Compaction Test
label | 598597dd-65b9-43ca-8f88-90df62a4de42 |  | note | FREQUENCY: Each Lot
label | 013b7cfd-343e-412c-b282-0944e6f3b256 |  | note | CATEGORY: HP
label | 38212650-a2a1-40ad-8e6d-9490f9c716a2 |  | note | RESPONSIBILITY: SE/
label | a355641c-bf23-4a2d-a491-c9642fad7303 |  | note | VERIFYING DOCUMENTS: Sign ITP Compaction test result
text | 7dcbc244-83d6-4168-bccd-4a31b2d99b48 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Structural Fill Preparation and Installation -
label | 9b8dbd6f-f838-429b-b2e9-5ee4d03884f3 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.3
label | 4a57f7a1-7536-41f6-b6c3-92c0e4b345c5 |  | note | L1-CHE-STD-029 - Clause 12.0
label | 42ac8784-f9b3-40d5-81df-f62789b4cb0e |  | note | ACCEPTANCE CRITERIA: Where Rail Subgrade CBR > 8%:
label | 5ee167a0-b14f-43be-b85a-3a762dfcfbf4 |  | note | Structural fill can directly be placed onto subgrade and compacted to 100%
label | 7c80ce86-bc8d-407a-a4e8-08ee98300b64 |  | note | 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | e1033052-7652-41af-8948-baabd9fddd0e |  | note | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | 25c52278-2f3c-4082-937e-93f945308801 |  | note | METHOD: Standard Compaction Test
label | 6720ceb2-fdda-4056-b440-059ae814bb49 |  | note | FREQUENCY: Each Lot
label | 3604ebd2-ae67-4c7e-9dfd-db8636c4bfa9 |  | note | CATEGORY: HP
label | 8fb22633-54aa-46c4-9fd9-be010f217b50 |  | note | RESPONSIBILITY: SE
label | b19b0851-a548-46c7-8dbd-337bb20b586d |  | note | VERIFYING DOCUMENTS: Sign ITP Compaction test result
text | 5a0176f2-0a07-4bd6-907a-c9ca0f5e55a3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Confirmation of material compaction & strength by Proof rolling
label | 12435828-8464-4791-b054-f95e019e8ee1 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9.4.1.a and Clause 8.6
label | 303dc2db-1701-4bdc-ab9e-2d5fefd64162 |  | note | ACCEPTANCE CRITERIA: To confirm the material compaction and strength have been achieved. Earth works layers shall be compacted so they are capable of withstanding proof rolling.
label | d3f2501b-47d8-47b3-832a-ab7d969d748e |  | note | Unstable areas detected shall be remove, reworked and/or improved as agreed by approved representative.
label | eb3b8452-2f46-4777-a7f2-207eaac0976d |  | note | METHOD: Proof roll
label | 5db4554e-89d4-4fbb-9dcb-3ab570e74cbc |  | note | FREQUENCY: Each Lot
label | 754f1066-694e-4644-8440-d213763a764d |  | note | CATEGORY: HP
label | 62740628-380e-4475-94b0-cd20fb69086d |  | note | RESPONSIBILITY: SE
label | 9bb01783-3102-4d8d-b66d-8584cf90cec5 |  | note | VERIFYING DOCUMENTS: MTM /NA representative signoff
text | c7d32f14-c3a2-4860-bf57-3e1dc548719c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Onsite Compaction Testing to specified densities
label | 6b1b1d18-cfad-494f-be3f-454ea54332d3 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.2.5
label | e622a4f9-b496-4f16-98da-c6bea98c69a8 |  | note | AS 1289
label | fef99bcc-ec0b-40a3-8f80-5c65513beb44 |  | note | ACCEPTANCE CRITERIA: For cohesive soils:
label | 74377a40-8f50-4643-bdfe-75e177bb5976 |  | note | Minimum Characteristic Value of Density Ratio of 100% when assessed using a Standard Compactive effort.
label | 47c99456-6e21-4c1a-a0e1-9bb794a05317 |  | note | For Rock fill: No visible deflection of surface under 10 tonne vibratory rollers after eight passes
label | 94ec0772-7c1a-456e-bb69-4546e0cede1b |  | note | METHOD: Review Test
label | 4b75217d-f214-4d01-b3fa-0448db61ea49 |  | note | FREQUENCY: Each Lot
label | 46ccffb3-367b-4e55-aac1-a5c794699eda |  | note | CATEGORY: HP
label | 9ffea1aa-511e-43f8-a826-97f07d841bf0 |  | note | RESPONSIBILITY: SE
label | d11a1450-2263-451d-bab2-505d06882e68 |  | note | VERIFYING DOCUMENTS: Sign ITP, Compaction test
text | 249c7ab3-fc2d-4492-9cb1-0c9735f4e035 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Structural Fill Finishing and Tolerances
checkpoint-status |  |  | checkpoint | 4.1 Survey Conformance report/As-built Survey
label | 7550deab-7f7b-4324-bd9b-c4fd3e96eb32 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10
label | 6b26d3a7-1d0a-4ceb-8c9a-f138930ba503 |  | note | ACCEPTANCE CRITERIA: Structural fill shall be within +0 to -35mm of approved design surface level
label | 4ad1a081-806a-4c29-8bc4-582975e52e80 |  | note | Structural fill shall be within +0 to +50mm of 3m straightedge laid on final structural surface parallel and perpendicular to centreline
label | e6135db2-9ca0-4dfb-8a36-eb1be7140bfc |  | note | METHOD: Document Review
label | d359a07b-2c0f-4e04-b246-17828043a9ed |  | note | FREQUENCY: Each Lot
label | 52fd4775-ba15-44ee-8c14-04f001338ea8 |  | note | CATEGORY: IP
label | bd379f29-968e-4393-9414-56310476bd55 |  | note | RESPONSIBILITY: SE/Surveyor
label | 23ab7af2-83f9-4fe0-ab80-2bad0dfc7e9f |  | note | VERIFYING DOCUMENTS: Survey conformance report
text | f0cf20fe-ed10-40bf-9dbf-a757cbe25995 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Non-conformance Report (NCR) Closure
label | 85ca784c-b12d-49b0-a1af-bc56ec4366ea |  | note | REFERENCE: MRPA Quality Management Plan
label | 66cb5c32-7a74-491b-94ac-2dc8cf3f0069 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 31ea2194-1c76-4b08-9891-4754f31a5127 |  | note | METHOD: Document Review
label | b74bb88d-a064-4917-880e-0c9ac8fe9efa |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 14bcef87-2352-483b-a15d-0e7908f3dbd8 |  | note | CATEGORY: HP*
label | 77496156-2577-4012-a2bc-491372132280 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 12324f9b-8e8c-4831-a969-3b0c0f3163a6 |  | note | VERIFYING DOCUMENTS: This ITP
text | ca0901f9-c15c-4cbb-ad59-054f3256a40a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | a40f1a78-6fef-4553-b130-f8928791a01e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8bfffbe1-b714-44c5-96ba-f3ba134a2ab0 |  | textbox | Name:
text | e413dd9a-a0d9-4f53-b8db-92c74d1962d7 |  | textbox | Position:
text | 7ed356fe-f394-46fb-9b98-f844dfac96cb |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Clyde Rd-Precast Crosshead (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Clyde Rd-Precast Crosshead (Supply & Installation) Rev 0 | 3be24293-1593-412d-a9b9-e79ce6847138
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | aa78fd6a-4ae3-410f-a16c-72174e94c498 |  | note | Document Title: ITP-STR-Clyde Rd-Precast Crosshead (Supply & Installation)
label | 37708d27-ea70-408c-a1cd-a2350e96104e |  | note | ITP Description: Clyde Rd-Precast Crosshead (Supply & Installation)
label | 09393010-054a-40e0-a42c-b9937e486801 |  | note | Discipline (e.g. CIV/STR/RAIL: STR
label | dee1865d-51d0-45e4-9606-9d71e9f1a90c |  | note | Revision Number: 0
label | a82c0297-5d70-4383-9034-1f14a1fb1373 |  | note | Revision Date: 6/01/2022
label | 5529d425-f0a7-4367-ba8b-41b91823990c |  | note | ITP created by: Justin Kreinberg
label | 9fec7139-b8c8-435a-badf-242ea2f49730 |  | note | ITP approved for use by: Victor Mira
label | 187ba73d-a8d9-4c62-9397-7332af89e1fa |  | note | 1.1 VicRoads Section 169 July 1993
label | 4846f0a0-b39e-4a25-9e47-b9053e1864b1 |  | note | 1.2 VicRoads Section 610 March 2019
label | e8830aae-eb3f-448a-b7eb-fceb26bd1879 |  | note | 1.3 VicRoads Section 611 November 2018
label | 933acb11-3e7f-4da3-8d24-03bda3d7db6d |  | note | 1.4 VicRoads Section 613 June 2017
label | 62986700-5684-4e65-91cf-fb6b1537263a |  | note | 1.5 VicRoads Section 620 May 2009
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Grout - Product Selection - Cementitious Grout
label | b39c6e42-911c-4105-aa67-0a0829681225 |  | note | REFERENCE: IFC Drawings
label | 50f37fc5-119d-46c2-8577-0e5b1563cd4e |  | note | 610.33
label | bf962cdc-e67e-4b49-bb13-b7def40c9817 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | c1107b77-b9b9-4f2f-84ae-8e4efa6589a1 |  | note | i. Either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | e75b786b-1eae-48d1-90fd-b6604dee4446 |  | note | ii. have the required strength at 28 days as noted on the IFC drawings.
label | 6cd78335-bed2-4155-8fef-519fa1e47864 |  | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
text | 8570a5ef-c930-4cbc-99a6-53712087e1cc |  | textbox | Enter: Teambinder Material Approval number
label | d165cceb-c943-4a97-8071-0f7489d57c9e |  | note | METHOD: Document Review
label | 0fdabfe3-3954-4d3d-8c27-23cf59fbd261 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 303ea9f3-5f0c-43c6-8441-15e0b5c62d18 |  | note | CATEGORY: IP
label | ffe56afe-1cbc-49d8-8f85-6505ec677021 |  | note | RESPONSIBILITY: Nominated Authority
label | 6b9a174c-5a83-4dca-9471-32fbdc76d563 |  | note | VERIFYING DOCUMENTS: This ITP
text | d1e6df6f-ff4f-4929-aa56-2c7904a88baa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Grout - Product Selection - Epoxy Grout
label | 32092dde-fd47-4d97-ae40-a669944f5e7d |  | note | REFERENCE: IFC Drawings
label | 8fb5bf85-b2cd-4ea6-a684-85d8bc16246f |  | note | ACCEPTANCE CRITERIA: Details of the materials and the proportions of grout mixture shall be submitted for review. Product to be selected based on the following criteria:
label | 66243fec-a687-473d-afbd-4f5d017ffe0f |  | note | i. have the required strength at 28 days as noted on the IFC drawings.
label | d4a8f672-259a-4522-882d-f5dc9a9502ed |  | note | ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
text | 1b5973b1-cdb0-406d-9820-82dc8dcc83a2 |  | textbox | Enter: Teambinder Material Approval number
label | 63858b8f-2844-4125-962b-e6978dd778bc |  | note | METHOD: Document Review
label | 15b17512-af30-4dc1-87b1-13318e5b8e36 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | b8648cc0-638d-4f13-95f5-47f67e788313 |  | note | CATEGORY: IP
label | 17dd4261-afd2-45cb-b107-8a7b54223bb3 |  | note | RESPONSIBILITY: Nominated Authority
label | fb118de2-1b07-40d5-93b9-381983f9d987 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1cfab689-6b3f-4ed0-8b7e-2715095511b2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | 75129406-a2ec-4047-8c86-995827565c3a |  | note | REFERENCE: 610.23 (d)
label | 784f52bd-ce29-4ded-953a-a5ecd5ddec89 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 59c33131-6489-4f6b-bfcb-81a69ace4ab2 |  | note | Note: This may be the same product used for the concrete curing
text | 009b8db8-4055-4831-a042-4071b796d4e6 |  | textbox | Enter: Teambinder Material Approval number
label | db79aede-f1bd-40d6-a80e-1e821cb6c1cf |  | note | METHOD: Document Review
label | b4af7882-652d-40ea-bc6a-ae8236b25eb4 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | d3dd840d-0238-4e23-b7cd-5bf0014e4656 |  | note | CATEGORY: IP
label | 7b2477ff-1681-4d96-b0b2-9ce2eb440abd |  | note | RESPONSIBILITY: Nominated Authority
label | 1b8c2f29-09e5-42ac-8000-6f4290a1f461 |  | note | VERIFYING DOCUMENTS: This ITP
text | e44ffbc7-3010-46fc-9f69-9f097da157bd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 ACRS Certification (for Starter bars)
label | 64007a59-e7f3-4c79-b219-6d6b58d0bdda |  | note | REFERENCE: 611.05 (a)
label | 7bb3f6ce-eec2-4f8d-a3eb-d33507e8ea4d |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | 3578e3c5-f86f-427d-b43e-92bbbb05e40e |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | aa53deef-e9e5-4fb9-98a1-6679000ced02 |  | textbox | Enter: Teambinder Material Approval number
label | 29b63b23-ba9c-4ff8-966e-8af3cb7d18b2 |  | note | METHOD: Document Review
label | 6f4d7225-bd65-4184-8e54-ffa5c34ff939 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | e0b1e67c-3a3a-4a2a-b07f-506bfe920f5d |  | note | CATEGORY: WP
label | 2f6a1cff-4bc3-4cb0-b19d-2e5a42a36a00 |  | note | RESPONSIBILITY: Nominated Authority
label | ba6023ee-c325-4497-8faa-1612f83d8cc7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 908debd3-24f6-4dfb-8462-52cb1fd7afa7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Precast Elements
label | 4fa2768c-e6e1-4dcd-a522-634c5a53a633 |  | note | REFERENCE: IFC Drawings
label | 8e3186f1-b84d-4b71-8a46-971293a04400 |  | note | 610.47 (a)
label | 96f0fa78-3b2d-430e-a9d4-abc0c19c3146 |  | note | Table 610.474
label | 03e835a9-50a2-4c8c-8425-1b3ae4f310a5 |  | note | 620.09
label | dbe76301-6336-41de-b756-7a4283ea947b |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 399c2fef-76ea-4110-b2d8-ba46f46229d5 |  | note | i. Certificate of Compliance / Birth Certificate
label | f8eb6e0a-ac4c-4c1b-954b-05dbb5159361 |  | note | ii. Compressive strength test results
label | 88d150b0-4d7c-4344-b05a-41a99386e1db |  | note | iii. Precast Lifting Design
label | e749b73f-e97d-4029-be38-30fd98e92cf2 |  | note | iv. Pre-pour check sheet / ITP
label | 95135610-e623-4107-b0a1-c8dd3a92e131 |  | note | v. Pre-stressing check sheet / ITP
label | c42a5055-e9da-4925-bb8f-353c4364ee16 |  | note | vi. Post-pour check sheet / ITP
label | bce01d04-0cee-4a95-afac-06e6e60de547 |  | note | vii. Covermeter check record
label | fbd03981-bcad-46d4-9dda-0b2954387392 |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.473
label | fd095459-3daa-4bdc-b4e7-5fd7fe544dcf |  | note | Note: Different revisions of 610 have different clause numbers
label | 4e665618-97c8-49bd-a3e2-177c9f028ef3 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
text | 8157d5a7-7370-423f-93cb-ca63b90fd627 |  | textbox | Enter: Teambinder Approval number
label | 3175f78b-4aab-42ec-a535-15a1f760d186 |  | note | METHOD: Document Review
label | 56fe54ec-4591-4500-9df1-a3013b05e889 |  | note | FREQUENCY: Each element
label | 00554eaf-4049-46d0-8e48-ffb0eb6de927 |  | note | CATEGORY: IP
label | ad95552d-aee3-42cc-8142-4162dff01f5c |  | note | RESPONSIBILITY: PE/SPE
label | bdaa121d-ea8f-48c7-8ab3-6ff9ed0e4b6c |  | note | VERIFYING DOCUMENTS: This ITP
text | 199472ee-acce-42d5-91dc-9fb44ca835f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Temporary Works Designs
label | 4ed742b9-5f7c-4bfd-8158-ea5a00769327 |  | note | REFERENCE: 610.27
label | 0d405eea-4180-4555-b510-695b5a1be08f |  | note | 613.04
label | 5e67501e-f123-488c-9dd4-d365aa3151eb |  | note | 613.05
label | e1f44289-a69e-4eec-88a7-f52ccc2c0919 |  | note | 613.16
label | 933988ff-ab06-4647-b760-ea4bbb175b49 |  | note | ACCEPTANCE CRITERIA: All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design.
label | 7650b1da-adfd-4d88-9d85-64de24abe911 |  | note | Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority.
label | a2191a7e-72b8-4d89-8d58-eb366b4a627f |  | note | Attach: Temporary Works Design
label | 4f36db80-007b-4bc8-bd88-eaf0310aca6d |  | note | Attach: Attachment A
label | 99778bfc-392f-427c-9acf-8d7ca29cfd90 |  | note | Attach: Attachment B
label | c685a61e-4b5e-4c67-916c-6585f8ce071a |  | note | METHOD: Document Review
label | 4c9aa44a-523b-44eb-8cca-03766b0c4168 |  | note | FREQUENCY: Where applicable, once, 5 days prior to installation
label | 3578254f-ad55-4103-9234-f89c144e60ae |  | note | CATEGORY: HP
label | 2a9669b7-f154-4ff6-9ce6-90c939359b8f |  | note | RESPONSIBILITY: Nominated Authority
label | 921a8588-aaed-40ab-a511-c8bac9ca0a4e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 72474ebf-d61e-438e-be9d-11b736d145e9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Curing and sampling procedure (for Concrete, Grout and Mortar)
label | a3cef31a-871a-415c-af67-29c2fcf41d31 |  | note | REFERENCE: 610.23 (a)
label | e86daad5-2bfc-4832-8735-c5f40b91a8b1 |  | note | ACCEPTANCE CRITERIA: Curing and sampling procedure to be submitted for review to the Nominated Authority.
text | 79a73a79-bafc-42ba-b311-a81b4673ec0a |  | textbox | Enter: Teambinder Correspondence Approval number
label | 8578afeb-f11e-43f8-adb7-59422810239f |  | note | METHOD: Document Review
label | b91f566e-6e2d-4f02-bdd0-4797a75b0a70 |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | 3d08b25f-4db3-4ead-9bab-9d4f9367770c |  | note | CATEGORY: HP
label | 31a8273c-7137-4a5b-9812-7bcf24df36c4 |  | note | RESPONSIBILITY: Nominated Authority
label | 3f21c91d-b9ab-42fd-b8b8-fa7132a462ef |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | cd8816d0-4b41-4979-812b-9924ab0f5a5a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 0185b947-ac1f-4155-b3c4-5ed3820d17e4 |  | note | REFERENCE: MRPA Quality Management Plan
label | 8b61f348-eb73-4246-b65f-80ecb944e621 |  | note | ACCEPTANCE CRITERIA: Revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | f4de0381-4a3b-4976-91af-04938b276c8d |  | note | METHOD: Document Review
label | a3cfba4c-e6eb-471c-a4cd-9b313785027b |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 88c3badc-eb2a-4af6-a2f1-42596a499311 |  | note | CATEGORY: HP*
label | 29459876-cb72-487d-9da7-d097f29e6987 |  | note | RESPONSIBILITY: All
label | f592ffa2-16c1-4758-88aa-627bfcd700f5 |  | note | VERIFYING DOCUMENTS: This ITP
text | b6f9e36c-9265-4ef8-90b0-1287635727e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Crosshead Compressive Strength
label | c6f44ac6-78ca-406a-8f8f-cdb83f071732 |  | note | REFERENCE: IFC Drawings
label | e148b539-644f-4eae-978b-6bb7eae1b091 |  | note | ACCEPTANCE CRITERIA: Minimum required compressive strength as (50 Mpa) has been achieved.
label | d8dd5b12-cfc2-47ee-9dbd-1b238645bcf0 |  | note | Attach: Compressive test results
label | 7aa9b49b-8400-4ce5-aa06-d2eb649b1402 |  | note | METHOD: Document Review
label | d84b5675-68a1-4840-b64c-1e5511b1add9 |  | note | FREQUENCY: Each element
label | 4a49d9d8-70b3-4c81-88c2-3a9c39def4e0 |  | note | CATEGORY: IP
label | 02392a21-3c37-4d75-bfe1-daeb3d400cd5 |  | note | RESPONSIBILITY: PE/SPE
label | cacb707f-25dc-416a-9517-902781f096e9 |  | note | VERIFYING DOCUMENTS: This ITP- Compressive test results
text | 07420ff1-1698-43d6-8c47-73cc844792b2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Survey Set-out of Precast Elements
label | 6c09ad51-12c0-4498-9286-86860d7b8989 |  | note | REFERENCE: IFC Drawings
label | 152c562e-8048-44e6-9ea3-f0fd1ce227f8 |  | note | 610.47 (a)
label | 13d210d2-e7a1-479f-8fcb-82cd6d4c1abf |  | note | Table 610.472
label | 36dc6455-aac8-4079-82ed-7116cad83d97 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the Table 610.473 as applicable to the element.
label | d30f3856-e254-4a6f-8240-cb6267e025c4 |  | note | METHOD: Measure
label | ad03a05a-9718-4433-b247-96f555237fda |  | note | FREQUENCY: Each element
label | addd1aae-c19a-486e-b95c-45d57da89952 |  | note | CATEGORY: IP
label | 296c41c8-fe7d-40e4-8e26-f6f2629d6234 |  | note | RESPONSIBILITY: Surveyor , PE/SPE
label | 41d524cb-0a79-45ff-9d04-6cc1ab84f4eb |  | note | VERIFYING DOCUMENTS: This ITP
text | 2056c39c-8edc-4d20-9e6d-0c0da831b413 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Starter Bar Installation
label | f90aaa67-3778-4b56-ab60-d00d7bc39e89 |  | note | REFERENCE: IFC Drawings
label | 8b529220-6f5a-4847-8236-101e967bbd9e |  | note | MRP-016-C-ACD-DRG-16-NWA-1622
label | d52c4f4c-d2cf-4d61-8639-7da90b894f40 |  | note | ACCEPTANCE CRITERIA: Starter bar assemblies to be connected to piles in accordance with the Design Drawings. Ensure the level and location is accurate to the starter bar ducts cast in the crossheads
label | 9139b6bd-d41b-4eeb-a33a-c6676af007e3 |  | note | 1130mm PROJECTION IS SPECIFIED FOR STARTER BARS
label | a526ef6a-44d8-4458-b042-552c617fe48d |  | note | METHOD: Measure , Visual
label | 00c33d05-bad1-48d7-9af5-d497d3ebda5c |  | note | FREQUENCY: Each element
label | cb3d6976-710e-407a-a72b-b719a762e40b |  | note | CATEGORY: IP
label | b9488202-3b54-4289-9635-91e7b21206e4 |  | note | RESPONSIBILITY: Surveyor , PE/SPE
label | b6738bb6-3f5e-4b14-b0a6-bde0add31367 |  | note | VERIFYING DOCUMENTS: This ITP
text | 41507e01-5e4f-4bfc-af59-281dc5877487 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Precast Handling
label | 9bdfe280-7075-493f-a179-014a19dd6c17 |  | note | REFERENCE: 620.07
label | 3d31fb4d-47cf-48fd-83fa-68a2fe92fc4d |  | note | Crane Lift Study
label | 12b87f8c-8634-451e-b705-55155846e8ff |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 4de1d293-a6f2-4a57-9438-05e272a14c97 |  | note | METHOD: Visual
label | 5dd86f53-c520-46a8-a57d-26f94296f9d6 |  | note | FREQUENCY: Each element
label | d6f5e035-3d93-482f-a3f5-512574766d88 |  | note | CATEGORY: IP
label | 3b72c679-8f1c-4abf-a595-ec5a3d74d776 |  | note | RESPONSIBILITY: PE/SPE
label | 341f8051-f9c9-46ee-a983-f8642df378de |  | note | VERIFYING DOCUMENTS: This ITP
text | 7d90d5e4-03d0-403e-93ee-00c74d827ddb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Crosshead line and level / HDPE Shim Placement
label | 184ec472-4e23-4cca-bf75-fa4c08501fa2 |  | note | REFERENCE: IFC Drawings
label | bd8f9025-878a-46f4-b424-1e7a43455238 |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1628
label | e46ac3ff-bbba-4ce8-928b-f2c67b85f868 |  | note | ACCEPTANCE CRITERIA: Place the HDPE shims (or variety of shims) to the survey marks and to the required thickness to ensure correct line and level according to the IFC Drawings and tolerances. HDPE to be nominal 20mm for the grouting activities.
label | 8c81788e-3737-471a-8ae2-f37da3737336 |  | note | METHOD: Measure , Visual
label | 2f55787e-fee7-4de4-a8ca-b7f6d3d0d6b2 |  | note | FREQUENCY: Each pile
label | 6074e91e-064b-4a3c-99c9-ba6fdd332f51 |  | note | CATEGORY: IP
label | 85f32527-124f-4a67-9a58-43399a2478ea |  | note | RESPONSIBILITY: Surveyor , PE/SPE
label | cfd804a8-80a1-417d-8a70-cfdd35c79010 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1f46894c-c243-4359-a3a7-31411fbd2d9c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Precast Placement
label | 5f05c737-f077-4cd8-b5a5-3e52ed5b2df0 |  | note | REFERENCE: IFC Drawings
label | 06e9e37e-629d-4dea-893e-4ddc68965cb9 |  | note | 610.27
label | 56dbbbda-5bc9-4126-90df-6a474614b4de |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | 7be3aeb1-e5e9-4dcf-8329-0f7d4877a88a |  | note | The nominal gap between elements is as per the IFC Drawings.
label | 8c356319-3f4d-42c2-b4a1-a0390aa086ac |  | note | METHOD: Measure , Visual
label | 759f6e4d-4b80-4261-b307-cd29bde35858 |  | note | FREQUENCY: Each element
label | 37dc702a-e5a2-41bc-a9af-04d83b8a96f5 |  | note | CATEGORY: IP
label | 2e0da991-8beb-445f-b438-38f5cb2c1265 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 396a9ca3-fa03-48ee-8742-ed0d68e2c441 |  | note | VERIFYING DOCUMENTS: This ITP
text | ac9f676a-0b5a-4476-8919-e4b3d4e142dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Reinforcement - Electrical Continuity
label | 47c3934e-7e14-4e1c-8b32-51c050b853d3 |  | note | REFERENCE: IFC Drawings
label | bf19b915-9f93-443c-9f14-09dcd996c35b |  | note | 610.29 (d)
label | 3aa12b5d-d7ff-4170-8e5f-434eab9ab158 |  | note | 610.43
label | 78b5f71b-2b31-49f9-b6e1-40ffee199447 |  | note | ACCEPTANCE CRITERIA: Element reinforcement cage to be made electrically continuous after placement of crosshead and prior to grouting starter bar ducts, site tack weld electrical continuity bar to starter bars and longitudinal reinforcement.
label | d22b031c-50ec-4798-8b4e-2e99fe809560 |  | note | Evidence that the resistance across the cage has a maximum value of 0.01O / 10,000µO is required.
label | 1c504b52-9392-4b3d-b22f-6376bf3b1c98 |  | note | Photograph or attach: Ohmmeter reading from end to end or corner to corner of the reinforcement cage
label | 923fcca2-ccb7-42bb-a308-62ff4d358f92 |  | note | METHOD: Measure , Visual
label | ac1e7e46-b94e-42de-9c91-6c0670ae5072 |  | note | FREQUENCY: Where applicable, each element
label | e4d623a2-7268-45aa-a454-13dd87f44773 |  | note | CATEGORY: IP
label | 1f6d4a2d-6704-439e-98b6-dd190d8f1244 |  | note | RESPONSIBILITY: Earthing Engineer , SE/PE/SPE
label | 75cc63c2-71df-4382-8c46-5aeb85de4722 |  | note | VERIFYING DOCUMENTS: This ITP
text | 982f2f24-ba64-46dc-b4da-9f18979f9d1c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Foam Seal and Bleed tube
label | 25e5d67b-7fab-41be-9bbe-cb5cf95e3f9a |  | note | REFERENCE: IFC Drawings
label | 4ba2e666-c90f-4e17-96ef-de45623d389e |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1628
label | 5a2c3f1c-0322-4fb2-b721-291634665d8b |  | note | ACCEPTANCE CRITERIA: Foam seals and formatube are to be placed around pile head and fixed into position
label | 68a2d350-f373-448b-834f-14d99cbe8dc3 |  | note | Bleed tube is in position
label | e63e05c9-ac5b-4894-83b7-771fa773b40a |  | note | METHOD: Visual
label | 049e2161-92a0-418c-8724-6866915e4bde |  | note | FREQUENCY: Each element
label | dff9976f-2765-49f3-a8f5-b54ae29193ba |  | note | CATEGORY: IP
label | 420cc4d8-475a-4a41-97ae-ef6591ce067e |  | note | RESPONSIBILITY: PE/SPE
label | 3c0436b5-6479-44f8-81e3-2acc9db8c23b |  | note | VERIFYING DOCUMENTS: This ITP
text | 77fee25d-65a6-4a99-992b-33bf30a69560 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Grout tubes
label | 03add9e9-a2d5-43d5-a8e2-b5ab1b8865c4 |  | note | REFERENCE: IFC Drawings
label | 029400c6-f993-4248-9b1c-e6a6c2d76df1 |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1628
label | c805114f-4320-4fec-bbe5-3a84d1a9229c |  | note | ACCEPTANCE CRITERIA: Grout tubes are inserted to 20mm above the bottom of the duct
label | 47ad5ea4-9750-40c0-980c-5fe4f05569e1 |  | note | METHOD: Visual, Measure
label | cafaed31-8f9e-4abc-bf6f-7d1e95c52109 |  | note | FREQUENCY: Each element
label | 5177f9e8-6433-4d6f-a183-811b3c538c07 |  | note | CATEGORY: IP
label | 3ae23961-e4f5-436a-9844-a0c2d9b0995a |  | note | RESPONSIBILITY: PE/SPE
label | 42ed12e1-0303-4973-bba9-32b28faed3d4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 37c34921-b852-44fe-bd04-1e7853c09e3e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Grout mixing (Epoxy)
label | fb496a71-b444-4e92-a748-572594cfd591 |  | note | REFERENCE: Manufacturer Instruction
label | edb64570-a7c2-4495-90b0-a946ac9db301 |  | note | 612.18
label | 6ba5bd6f-f6a8-455b-a198-088c85a621c2 |  | note | ACCEPTANCE CRITERIA: Grout mixed as per the manufacturer instruction. Full container used.
label | 43b893af-e144-48da-8610-fb110f3f1046 |  | note | Attach: Contractor Grout checklist
label | 294bb3d7-a8fd-4b84-add5-52d5240085fa |  | note | METHOD: Visual
label | 97ff1c7b-963a-4b2d-a3d3-93a884a2ac12 |  | note | FREQUENCY: Each element
label | dc11b414-c8f5-4c38-a358-e96de3969e4b |  | note | CATEGORY: HP
label | 180e4282-5520-4532-8a4e-4aae495fa8ad |  | note | RESPONSIBILITY: Nominated Authority
label | f5adff44-42d4-4408-a3fa-fd0e413618ec |  | note | VERIFYING DOCUMENTS: This ITP
text | 1377619e-283a-4128-8fcd-2ba957ddfcf0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Bleed tube
label | 51fd04ba-fa3f-4f42-b593-e8e393d78996 |  | note | REFERENCE: IFC Drawings
label | eac84611-191f-4aa3-ab1a-f522f46f1407 |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1628
label | 170b5084-a223-456f-accf-9f57f42628f1 |  | note | 612.18
label | d46361c8-023c-492b-86ea-8eeda4285981 |  | note | ACCEPTANCE CRITERIA: Grout allowed to flow until grout flows freely from each bleed tube.
label | 165c3ceb-b41c-4276-9faa-5ddf3cefe4d4 |  | note | METHOD: Visual
label | f25752aa-4695-46df-97fa-eab7ec0ac8e9 |  | note | FREQUENCY: Each element
label | fc5ce6ae-1c0e-4d27-bce8-993798bc5d13 |  | note | CATEGORY: HP
label | af386c2b-1f5b-4bd0-976c-d068e385bc22 |  | note | RESPONSIBILITY: Nominated Authority
label | f0c679cf-0a9d-4788-aad3-2d8faebcc722 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7a9a1a22-11f4-4073-826b-4559603ec68f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 Grout injection (Epoxy)
label | 4a1f5297-029f-4204-bf05-f46059e3b4bf |  | note | REFERENCE: IFC Drawings
label | 2cb9e20b-9ad3-4c18-9fce-4fe5fa054beb |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1628
label | e29a326e-3325-4964-b372-b7bbb3bcf070 |  | note | MRPA-RFI-001247
label | f8360e8a-9a37-46f2-a20c-29c9409f66f1 |  | note | 612.18
label | 550da94b-66c0-45e9-b461-a3dc820f3f63 |  | note | ACCEPTANCE CRITERIA: Grout injected in a continuous pour until 100mm Level from top of the pile is achieved
label | 69129149-94de-4107-a28f-03d5f8748081 |  | note | Attach: Completed Grout Pour Checklist
label | fdfcf5ea-bd68-4125-9434-5d1d42ef315a |  | note | Attach: Completed Grout Pour Record
label | 4798f6f5-8f8b-40f7-9a88-6508829b84cc |  | note | METHOD: Visual
label | 9827943a-9429-4b26-8657-d54b2cf7c10f |  | note | FREQUENCY: Each element
label | 6d9bdce8-b3b9-4f9e-acd4-9aceec1c3984 |  | note | CATEGORY: HP
label | a225b4d7-145f-4389-b916-5cf4085da2df |  | note | RESPONSIBILITY: Nominated Authority
label | 7124c3fe-c343-4c5b-b9b4-776b2470030d |  | note | VERIFYING DOCUMENTS: This ITP -Grout Pour Checklist
text | 9d2093c0-3b2f-44ba-81c5-31c5ff724e1e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Grout mixing (Cementitious)
label | 25fb14b6-554b-4fe6-a476-10ab4f9bf4d8 |  | note | REFERENCE: Manufacturer Instruction
label | ddea718e-0be5-4798-a6c5-6c9a247653e8 |  | note | MRPA-RFI-001247
label | faa8cf55-14c7-4f81-9f63-ffc22def189c |  | note | 612.18
label | 1f617da1-aa4f-4ccb-b680-2aaf39d9610d |  | note | ACCEPTANCE CRITERIA: Grout mixed as per the manufacturer instruction. Full container used.
label | b7e14900-6836-4ed4-8746-80647c8a7083 |  | note | Attach: Contractor Grout checklist
label | 4bead7fb-9ecb-4c27-9976-f2ea371e840d |  | note | METHOD: Visual
label | 7f8e3d84-d36f-4e60-948f-ccee05050a52 |  | note | FREQUENCY: Each element
label | 44e2d503-f868-41c2-8bad-63316b5d5503 |  | note | CATEGORY: HP
label | 3b493949-8cbc-4cea-9b4f-6127e759389f |  | note | RESPONSIBILITY: Nominated Authority
label | e6c12697-4916-4038-8a0a-2db362f54e3a |  | note | VERIFYING DOCUMENTS: This ITP
text | 7dc65ca6-cb1d-42c7-bf6d-28717c6584e2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 Grout injection (Cementitious)
label | 221b1c87-6a68-445c-8569-bdc5dd159143 |  | note | REFERENCE: IFC Drawings
label | 829c2702-9401-4b87-bef5-ab90530156d1 |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1628
label | 05d97a3c-1442-4f43-9540-2f420e80f221 |  | note | MRPA-RFI-001247
label | 1e88da9b-e4d9-4348-ab72-e8fd7fb8707d |  | note | 612.18
label | 32d5edae-62f0-4915-9d40-2906c1ffe035 |  | note | ACCEPTANCE CRITERIA: Grout injected in a continuous pour until grout emerges from the top of all ducts
label | cdbfb431-b48b-4178-ae3f-892d1db254ba |  | note | Attach: Completed Grout Pour Checklist
label | 3296426b-faab-4f32-a964-50dbd77e839b |  | note | Attach: Completed Grout Pour Record
label | 90c0cc04-fa39-408b-802a-fe36db8af170 |  | note | METHOD: Visual
label | 349f04b6-f605-469e-b93e-d492600df982 |  | note | FREQUENCY: Each element
label | a4c22714-4333-45fa-8695-4d91e79e1dc6 |  | note | CATEGORY: HP
label | 1c890955-4c03-4d0c-8f82-93be497e52a2 |  | note | RESPONSIBILITY: Nominated Authority
label | aa3df98f-2085-4264-b5e9-083f06040de0 |  | note | VERIFYING DOCUMENTS: This ITP -Grout Pour Checklist
text | ea9d044b-e1f6-42fc-a609-803bdeb3bb67 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Falsework Certification
label | d9173708-e9c3-4ef2-8efd-d01f6b1793c1 |  | note | REFERENCE: 613.12
label | 1f7a876e-b825-431d-8244-85b8c8c0337a |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above)
label | 02998a7d-37f6-431f-9101-f86610c6a07b |  | note | Attach: Attachment B
label | 2ec5758e-cbe1-4772-a82c-94397e55337e |  | note | METHOD: Visual, Document Review
label | 3b036382-fc01-408c-b3a4-94ee772ac055 |  | note | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
label | d1d8dbca-9414-4b0b-84f7-318f520a8a1f |  | note | CATEGORY: HP
label | eb7da048-f135-48ca-8833-8077f58311b8 |  | note | RESPONSIBILITY: Nominated Authority
label | 42bb19f3-3a3b-4187-a57c-b34621ae6d28 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | d4459e75-84ae-49e4-8c96-56f6e33e1574 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 Flowable Epoxy Grout Placement (Pile to crosshead connection - Soffit)
label | ed32d515-798d-4de2-aaaa-8d3f4e4f6698 |  | note | REFERENCE: IFC Drawings
label | fe02ea0d-7be7-4f9a-ba4c-cd19732d99cc |  | note | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2
label | 131e1e2b-421e-4cec-b1a1-806426b092df |  | note | Attach: Compressive Test Results
label | e2a5981b-38ea-42d5-a500-c14f2e0d5cf7 |  | note | METHOD: Document Review
label | 3b42d38c-f1b7-43ca-885d-bf43257e3b14 |  | note | FREQUENCY: Where applicable
label | 32d44214-00af-42e8-a5c3-516e925a5076 |  | note | CATEGORY: HP*
label | d692dfc8-4d1d-430f-9d2d-e0fc48f6ed1f |  | note | RESPONSIBILITY: PE/SPE
label | d90e632b-78b5-443d-bcd4-593a486a2507 |  | note | VERIFYING DOCUMENTS: This ITP- Compressive test results
text | 50be4e2b-ab14-41de-ba58-69b3c45a711b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Flowable Grout Pour (Pile to crosshead connection - Starter Bar Ducts)
label | 9356dee6-1ce8-4a9a-8d51-eb30fa9544d0 |  | note | REFERENCE: IFC Drawings
label | 29f866ab-7219-46d8-947f-33d17de60f2c |  | note | ACCEPTANCE CRITERIA: The minimum compressive strength of test cubes made, cured and tested in accordance with AS 1478.2
label | 894c09c7-ce74-453f-beee-dc52b3d2d245 |  | note | Attach: Compressive Test Results
label | 47084996-f2d3-42ea-821a-27e8d30d05fa |  | note | METHOD: Document Review
label | c8268d10-5454-46af-9382-b27f4bde7eb8 |  | note | FREQUENCY: Where applicable
label | 7ef95fd4-f0fa-4e9c-b004-d4859c37c919 |  | note | CATEGORY: HP*
label | cc785f45-7c67-41d6-9d97-8cf8ce6eca11 |  | note | RESPONSIBILITY: PE/SPE
label | 8ed7cc9f-38a3-4799-ad0d-a369c19917b2 |  | note | VERIFYING DOCUMENTS: This ITP- Compressive test results
text | 381be953-046a-4278-be92-47f0510041bd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 As-built Survey
label | 81919015-8ffb-4b6a-aeb0-bc65198000e5 |  | note | REFERENCE: IFC Drawings
label | 32354c71-86e4-4150-8565-355c8d111c7a |  | note | 610.46 (a),
label | e6479d8e-3382-4148-b579-55ac57a8d72a |  | note | Table 610.462
label | e3003489-3ed8-4c13-9b0f-c9953cd0e103 |  | note | (November 2018)
label | 90d49c3e-6d49-4216-98d6-e7c995aaec68 |  | note | 610.47 (a)
label | 2d8b8bdf-fe40-4e19-8b30-5f1f7028d57c |  | note | Table 610.472
label | 82d6ee95-68fc-4aba-8dfe-b0d513053e26 |  | note | (March/June 2019)
label | 0e15464a-d67c-4fb6-a80e-008cbc33456a |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | bb326d51-10a6-4097-8b39-c9ebbbc74761 |  | note | Attach: Survey As-builts / Survey Report
label | eb1451a3-9ffd-41d3-9134-a45884347898 |  | note | METHOD: Document Review
label | 08d2b669-8a3d-49bc-958d-da714927821b |  | note | FREQUENCY: Each element
label | 2accbc32-caf1-4423-9058-bc5328bcd138 |  | note | CATEGORY: IP
label | 82b3825f-318d-4b4b-967b-826496b556f3 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | f374a262-4d3a-4750-9bae-f39614ae46fb |  | note | VERIFYING DOCUMENTS: This ITP
text | c3ae6dd4-ed3f-4e57-8797-dbe28218fb70 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Removal of Falsework
label | 3ed486f5-448d-4f72-991f-a70510a9b2f9 |  | note | REFERENCE: Temporary Works Design
label | b27f874d-b674-4d2a-a88d-772f41cdd6f3 |  | note | 613.16
label | 8dd2f583-612f-4fab-a814-71905c1fb9ed |  | note | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
label | d92d734f-2c09-4529-8af0-b523771be85e |  | note | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for and repair.
label | 2a16d70d-0645-48d2-bb54-e7c99d101b87 |  | note | METHOD: Visual , Document Review
label | 1b3f36c3-b237-4cf3-b5c3-c70ab9f25762 |  | note | FREQUENCY: Where applicable, each element
label | 4e0d2b08-22ed-4ab5-a0a9-4a1cb226ccbf |  | note | CATEGORY: IP
label | 527425b8-0264-4c73-a6b6-7e40eb4f5f2d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8c709c03-bf7c-45bd-af65-b30bea88d030 |  | note | VERIFYING DOCUMENTS: This ITP
text | be179804-4418-483e-bc81-e4e20ecd96dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Patching works
label | b869232e-49ae-4fd8-abbf-6b47c467ae00 |  | note | REFERENCE: Temporary Works Design
label | 7ec493c5-6be1-433d-97d8-e48bcbdd9e40 |  | note | 613.16
label | b01163fb-e992-4017-8aef-f0793e69c9e2 |  | note | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
label | 92d37788-7036-49f3-afe8-f323402782e8 |  | note | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for any repair.
label | 2b1b0a99-7737-4607-9445-690701f0af7c |  | note | METHOD: Visual , Document Review
label | 6dc93497-9df0-4a2c-b9d4-f6be3d699158 |  | note | FREQUENCY: Where applicable, each element
label | 5ec0b5bd-a4b9-4367-b1cb-56fd361433fb |  | note | CATEGORY: IP
label | 673aa7e4-e99c-40d8-b198-6978232430a9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f055f0fb-8316-4e5a-b522-1a2afbdbd377 |  | note | VERIFYING DOCUMENTS: This ITP
text | 706a1b54-2d86-4bb3-b6e5-1ef5b2cabf5c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | f97c01df-1ead-4292-908d-a31f9ba55f3d |  | note | REFERENCE: MRPA Quality Management Plan
label | 63a80331-adaa-48c6-91a0-5bd12df4bdfb |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 8436d4ed-2354-4d76-aa96-f5fd98a7779d |  | note | METHOD: Document Review
label | 4b79b5b5-7d33-4507-94f2-e1329ef9b72d |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 0ed1b3ed-7df3-4181-af8e-d28b36757b97 |  | note | CATEGORY: HP*
label | d0bae94b-032f-46f9-9948-c0a1717329fc |  | note | RESPONSIBILITY: SE/PE/SPE
label | e786805f-bb86-4a4c-bda8-79be045e958e |  | note | VERIFYING DOCUMENTS: This ITP
text | b31ff805-7d7a-4d2e-a1ce-ac310885506f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6a0cfb3f-2758-47f2-b9d1-47432b909b4b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c68aaf10-19dd-4b30-af9c-7b17ffd92ad9 |  | textbox | Name:
text | 4ad059dc-5174-417d-90df-aedf999480d1 |  | textbox | Position:
text | fde43c1c-3b38-4b3d-9484-1aa1121b9687 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Steel Bridge Girders - On Site Bolting - Clyde Road (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Steel Bridge Girders - On Site Bolting - Clyde Road (Supply & Installation) Rev 0 | 3f45686d-425f-41bf-89cc-311a0d75789f
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 0bb6799e-4b35-417e-9975-fdf8d1bc27b8 |  | note | Document Title: ITP-STR-Steel Bridge Girders - On Site Bolting - Clyde Road (Supply & Installation)
label | ac275b50-f467-4a8b-8426-115a3ce5dcc4 |  | note | ITP Description: Steel Bridge Girders - On Site Bolting - Clyde Road (Supply & Installation)
label | d9494cf3-7ac6-4039-a644-503110e89f9e |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 3bd2f741-5f9b-484e-bdea-0bf8c95ff3cf |  | note | Revision Number: 0
label | 6a45f7ac-ef68-4e15-a63f-01a5f5c6b143 |  | note | Revision Date: 31/08/21
label | 54a0f7ff-8083-4c8c-87f0-5b52e3c23c9f |  | note | ITP created by: Justin Kreinberg
label | d02ec31a-d9e1-42e9-bbd4-80fac1c7883d |  | note | ITP approved for use by: Aldrin Guinchoma
label | d94906ed-bef0-4ef5-bc6d-1a2cbecff1ae |  | note | 1.1 VicRoads Section 630 October 2013
label | 987d1890-03f5-4072-b67e-3327e463295d |  | note | 1.2 VicRoads Section 631 February 2009
label | 5e196146-7de7-45bc-b87b-293555c9625d |  | note | 1.3 AS4100-1998
label | d07d2130-2942-4001-b2bb-f8bb566a4ff8 |  | note | 1.4 AS5131-2016
label | 1a7f0aef-128d-417c-b6d3-8a4a84a79bbd |  | note | 1.5 AS4680-2006
label | fdba7be2-6229-49bf-9467-c95c019f3eae |  | note | 1.6 AS2312.1-2014
label | 3d75f488-75b0-4fa8-8055-7fc64a36402b |  | note | 1.7 AS4506-2005
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | fbc46e0b-e5ae-4ef7-82c4-486c9d4dc6f0 |  | note | REFERENCE: IFC Drawings
label | b86b80a8-8d16-4ed3-a406-e25d21153c71 |  | note | MRPA Quality Management Plan
label | ff5e8247-a060-444b-b123-c786c9ac8d0c |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | f216258d-f9fc-4e8f-ae4f-d31376fad51f |  | note | Typically this consists of but not limited to:
label | 082307e0-2c87-4369-b912-77bcb3c66530 |  | note | i. Certificate of Compliance
label | 8f0c566a-b186-482c-9798-dc94116eb5ac |  | note | ii. Completed ITP
label | 83fe6be9-97d3-4992-8f63-d58a0aa3f73f |  | note | iii. Weld Procedure Specifications
label | 9b3a8ff3-d99a-4044-9611-28e5a1340622 |  | note | iv. Weld Procedure Qualifications
label | 538a2c9d-e556-4ea3-8fa7-d3ea5d7fd166 |  | note | v. Welder Qualifications
label | e3ac1841-7a00-423a-b790-aaa1478e0108 |  | note | vi. Material Certificates and traceability
label | 4b579cf1-da3f-4abf-8793-6229c15cfba0 |  | note | vii. Quality Assurance check sheets
label | a540fd9b-f464-44df-9158-71fad74f02e5 |  | note | viii. Welding Consumable batch certificates
label | 0b471d07-3448-4bf4-aa11-70dc45929a82 |  | note | ix. Coating certificate(s)
label | 5c42668c-34ab-433a-9e40-625b319fe14d |  | note | x. Non-destructive Testing (NDT) Reports
label | b6cacebb-bb2e-4268-8ab2-3ae0e539b385 |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 2c7ba302-9ae6-488c-983d-097bc86a33f4 |  | note | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | 6fc62441-a3db-4b10-9e49-3d405bfe15f2 |  | note | METHOD: Document Review
label | 7fca5419-ece3-4e17-8b4c-2d33569b8042 |  | note | FREQUENCY: Each component
label | d7d2a60f-4252-4e8d-b1b5-17e3f3cadd14 |  | note | CATEGORY: HP
label | f9f947af-e94a-4564-b927-778bac1db284 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 4b483e8c-8bc0-4b96-826b-00ebd9dddd5a |  | note | VERIFYING DOCUMENTS: This ITP
text | f6acda38-e14d-4795-95f4-c6a45e53e735 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Shear Pin
label | 5db32f26-cdde-43c0-a18f-298579e53648 |  | note | REFERENCE: IFC Drawings
label | ea13765f-5c51-4f51-aa4d-ef1fc13eb816 |  | note | ACCEPTANCE CRITERIA: 90mm DESIGNATION TO AS1444-4140 (TYP)
label | 49bfc5e7-a517-478a-8063-530988e5ed3d |  | note | 42CrMo4 MECHANICAL PROPERTY
label | 3bca2a91-9981-416d-bb71-f1368aaa8cf1 |  | note | Reference: Teambinder Material Approval Number
label | 69b369a4-ffb0-4790-bedc-8e4d4f0a8287 |  | note | METHOD: Document Review
label | f9c5d28b-b998-44ac-a350-35ef094edc58 |  | note | FREQUENCY: Nominated Authority
label | c2377306-2486-4108-a631-330f55e13235 |  | note | CATEGORY: HP*
label | 77ba8ff4-44d0-489f-b26d-8aa03081b94f |  | note | RESPONSIBILITY: PE/SE/SPE
label | e4c3cc63-1492-40a5-9c16-0cbbae97c4f6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 18763fdc-7aff-43c9-ad4d-a47debff685c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Bolted Connections Using Direct Tension Indicators (DTIs)
label | be3c0b78-6cfd-462a-90e6-28aae050e1b8 |  | note | REFERENCE: 630.20 (e ) (ii)
label | 6869f2dd-d13c-49dc-903a-71a729100342 |  | note | AS4100 Clause 15.2.5.3 (a)
label | c015bc2a-3f2c-4a97-a5f8-5e0932f54ff6 |  | note | AS5131 Clause 8.5.7 (a)
label | 70062acb-187c-4066-9114-075e55c1d637 |  | note | ACCEPTANCE CRITERIA: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | bd021732-7d14-46b3-ba9f-9e5f97e99849 |  | note | i. technical data sheet or information on the product
label | f7a121a7-03e1-445f-b80c-313ef7abfb3c |  | note | ii. 3 no. min. correlation tests between a calibrated torque wrench and a representative sample of each bolt diameter/length/grade combination to be used in the Works.
label | 2a267aae-484f-4ef1-b800-81b1f439cd86 |  | note | iii. a valid calibration certificate of the torque wrench
label | 037a94ce-5b37-4889-9cff-5d8587e54824 |  | note | Note: Daily records of use and correlation between a calibrated torque wrench are required, see 6.3 in Post-installation.
text | 4774bbfc-802b-4814-8b4a-94790e1d4b8e |  | textbox | Enter: Teambinder Approval number
label | bd529bc9-c83d-484d-9a97-8792608e0e7e |  | note | METHOD: Document Review
label | 4ae70a08-6b95-4065-8e5e-0bc714c49b76 |  | note | FREQUENCY: Where applicable, once, 14 days prior to use of devices
label | 49bf2111-4f0f-4091-9f77-0e1592b96e48 |  | note | CATEGORY: HP
label | 08c73935-2e28-4910-a49d-8f7ca5f26dad |  | note | RESPONSIBILITY: Nominated Authority
label | 9eb70863-f8e6-495e-b5cd-45d10313b38e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | f0d24067-d491-46ee-852c-0c16f7397ae6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Bolt Procedure for Friction Type Connections
label | 1c5261b8-40b4-4c08-926e-c3d4387c7fcd |  | note | REFERENCE: AS5131 Clause 8
label | 9fd7f6b1-1a6c-4642-b408-68d20fe34235 |  | note | ACCEPTANCE CRITERIA: Details of friction-type connection (TF & TB) installation shall be provided prior to erection of steel work
text | 7e38a108-4015-4a82-b0b2-b4cd9ae7219c |  | textbox | Enter: Teambinder Approval number
label | 6fe4f198-9f7b-4e64-ab33-0769f6b4204d |  | note | METHOD: Document Review
label | b464862d-2533-4afb-a530-7dea1835d58b |  | note | FREQUENCY: Where applicable, once, 14 days prior to installation
label | 6625cdb9-7035-4c3d-94fc-5714c9400961 |  | note | CATEGORY: HP*
label | e4c2a844-ea43-46d0-8dfd-b951ad794b8e |  | note | RESPONSIBILITY: PE/SE/SPE
label | 50cdba99-d388-44e2-8f6b-2b27c5d714b6 |  | note | VERIFYING DOCUMENTS: This ITP
text | aeebbfa5-661f-452d-8791-2d5fbd9c189c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Installation Methodology & Work Method Statement
label | 2b6d5a45-93a5-4748-b78c-71c1468140ea |  | note | REFERENCE: 630.2
label | 1a16c7fc-7ee0-4999-9768-2d529e0306c3 |  | note | AS5131 Clause 11.2.3
label | 7289651f-fde1-4b07-99d0-516dc4b46165 |  | note | ACCEPTANCE CRITERIA: Details of how the structural and architectural steel will be installed will need to be provided, including the following:
label | 14d3f7ed-029e-44bb-8f9c-d8431c0da49d |  | note | Transportation to site;
label | dd0e0e04-a4c6-4f05-887d-cc7db3e6ba81 |  | note | Handled on site;
label | cf6ea55c-0b85-46fd-ba22-ee1ccc6da616 |  | note | Erection procedure;
label | 6d53c36e-8cc0-4caa-ac83-6117a1a749f6 |  | note | Lift study (where applicable)
text | 57993b37-bc00-4c1e-9fef-9edab1277e3e |  | textbox | Enter: Teambinder Approval number
label | e79753e1-5235-49de-b76d-bfae9caa0261 |  | note | METHOD: Document Review
label | 324cf337-16e7-4fb7-a962-aa9a11ab3cfc |  | note | FREQUENCY: Where applicable, once, 14 days prior to installation
label | c09730e8-1194-4cca-854c-d852c48eb826 |  | note | CATEGORY: HP*
label | bfec4192-1801-483d-9d3d-1aaeaa3e5b62 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 4149f9ab-7347-47ba-a22a-7ccf8cf61b4b |  | note | VERIFYING DOCUMENTS: This ITP
text | f18cf139-3e2f-4559-9ec5-01ac16ff2584 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 13743ad3-c8b9-41cf-950a-da8e7f90b24c |  | note | REFERENCE: MRPA Quality Management Plan
label | ee10b4c8-ff80-4d41-8dfd-3df959507a39 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 8cb34e72-5c3b-4252-a8d3-5094fcbd0c26 |  | note | METHOD: Document Review
label | 1673814f-7c9a-4150-a64c-3d986b35bc61 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | da475323-06da-4fe5-82e1-f54e30aa4ee7 |  | note | CATEGORY: HP*
label | 8138658d-9277-42ca-b2d8-f092951239b2 |  | note | RESPONSIBILITY: All
label | e1d45093-8bd2-4141-96cd-ca6c953b869c |  | note | VERIFYING DOCUMENTS: This ITP
text | 9e622fb4-c2ec-45de-b0ed-a790892d8847 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection Checklist
label | bd59b6f4-7f6c-43f3-91e9-60baad42cecb |  | note | REFERENCE: IFC Drawings
label | 1a8d080f-79e0-4810-b889-b44962a5676c |  | note | 630.08
label | 83dcec86-e2d9-404c-a377-37e59d3a93f1 |  | note | 630.09
label | e79d6299-400f-419a-a7e1-569f4ce40323 |  | note | 630.20 (a)
label | 7b084868-98b0-49de-bb31-e053fb52e479 |  | note | 631.06
label | 22164d1a-3aae-497a-952a-ee904c2336f2 |  | note | AS4860 Clause 7
label | 673ef87c-a5d9-4230-ac4c-c8f001006a7b |  | note | 631.11 (a)
label | 99c988f1-a70b-4f00-a6ba-c3e44ea504ed |  | note | AS2312 Clause 9.6.4 (i)
label | 863659c5-4e47-4c15-aa49-e3a586f5740b |  | note | AS4506 Clause 2.3
label | 14a917ad-0ed4-4ad2-937c-1269557575ef |  | note | MRPA Quality Management Plan
label | 15028151-8283-453d-a6b7-ae32a755bf99 |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | a72ba747-e2f2-4db8-ad9e-3dd033f814f1 |  | note | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | bb11a8f6-975e-4707-91c9-62aa4ec547f1 |  | note | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | 558b8743-b254-4ee1-8efd-2f5f1be69e17 |  | note | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | 7eccd48f-8ae3-427d-a0bf-9e959fa86bce |  | note | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | 531b98ee-8457-488b-853c-fea4959bf1d2 |  | note | Complete: Materials Inspection Checklist in ConQA
label | 70f81235-98c3-4d70-b582-4dc8aaece0a0 |  | note | METHOD: Measure , Visual
label | 08c9b5cd-89f7-4d1b-86da-a88edf2e4900 |  | note | FREQUENCY: Each component
label | 43705f40-2c20-450b-8453-f52c846f602b |  | note | CATEGORY: IP
label | d1fe19c1-0022-4db1-8cba-238dd4220a4b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 016427ed-a464-4d39-8273-6bd76c619a46 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2d892d49-a8b5-4fba-8f5c-9d638c94176e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Shear Pin
label | 00be09ab-d5b1-4af0-b8f6-d2d81effe1ab |  | note | REFERENCE: IFC Drawings
label | 33692198-db7e-4ee0-a6d4-4b0e0d679313 |  | note | ACCEPTANCE CRITERIA: 90mm DESIGNATION TO AS1444-4140 (TYP)
label | 3d9df11f-750d-4446-bb5e-5da5c9c8473e |  | note | 42CrMo4 MECHANICAL PROPERTY
label | c7f0041e-bae1-4c30-beb0-740aa7ab35c7 |  | note | Inspect Dia and Length
label | 99ab70f4-72ad-440e-b39a-686e9448de6e |  | note | METHOD: Measure , Visual
label | 86f5e5d0-0699-475d-8faa-f226e2579247 |  | note | FREQUENCY: Each component
label | 9a7bb076-b528-42f3-b142-336f2e41baae |  | note | CATEGORY: IP
label | 4cb3f61b-406a-45f0-90c0-513803971a09 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e2a97998-4eff-467a-833e-f96b434dc77c |  | note | VERIFYING DOCUMENTS: This ITP
text | 65fd0bba-235d-4b5d-a574-f468ac6d72c5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities-Temporary Erection (Bracings and Deck pour)
checkpoint-status |  |  | checkpoint | 5.1 Structural Steel Handling
label | 0d77fdfc-b354-4def-8bf9-fdd5e814d94b |  | note | REFERENCE: 630.09
label | 94a1438e-f0bc-49f7-b0ad-bc97fae9700b |  | note | 631.14
label | 316bd785-e8fe-4200-b563-84f6995a0ce0 |  | note | AS4100 Clause 15.2.2 & 3
label | cf4d060b-47aa-4a02-a047-fe34b5f546f3 |  | note | AS5131 Clause 11.5.6
label | ca71431c-1aa4-49fb-9440-03fb1e447599 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | a07e8bd7-5133-4677-aec2-ca78021f3cce |  | note | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | 3b95acfb-7171-43c9-8e09-02143b23c901 |  | note | METHOD: Visual
label | bc5865fa-66b8-4dd7-ad5f-f9229e9a335d |  | note | FREQUENCY: Each component
label | 9f52690b-6851-4cb6-a49d-f23b665e436d |  | note | CATEGORY: IP
label | bed1e110-99ce-4e75-ab97-0a6ac7d12ebe |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0aed11df-f9be-4f99-8867-8faf34fa20b2 |  | note | VERIFYING DOCUMENTS: This ITP
text | dee89802-c045-49b3-8c46-fab19779b300 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Temporary Works
label | 053572f6-3aff-4124-8db1-c361fbde3d37 |  | note | REFERENCE: IFC Drawings
label | 04ecd044-b57c-4ed7-9047-53791bc14aa7 |  | note | ACCEPTANCE CRITERIA: Girders are secured and safe to proceed with bolt fastening Operation
label | 73e30981-d4bb-4645-a9dc-9895879f627c |  | note | METHOD: Visual
label | 0da4663f-4408-4b1b-bbee-6a34c498a47b |  | note | FREQUENCY: where applicable
label | b2d5ad9b-1b49-4bd1-a065-01823422f316 |  | note | CATEGORY: IP
label | 1e2c9892-bc52-4120-9df6-f0571d61e21f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 70d8a303-35d3-414d-b641-0d68bbd02bbb |  | note | VERIFYING DOCUMENTS: This ITP
text | d29cfac6-b8bb-4b00-b8cd-0e7404d6ac29 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel -survey conformance
label | 3c4bc0f7-ecc2-4317-9518-720e7d54bdf3 |  | note | REFERENCE: AS5131 Clauses 11.5.7 and 6.7
label | 3fe28cf3-b5cb-4512-a95c-403ffe1c7e19 |  | note | 630.12
label | b3500f03-392c-4b15-8783-2fc13197aff1 |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances:
label | af1dd62f-02b3-4e19-a77d-bc2b92126d36 |  | note | Level of beam = ±5mm
label | 13f3b173-c6b3-4dcb-85e4-88e68253bc0e |  | note | Location of beam = ±3mm
label | 4bb0371d-48be-43aa-bef3-46e8a9f9100c |  | note | Deviation of beam flange from intended position =L/1000
label | 8abe343f-5184-473e-8688-ab164c772469 |  | note | L=Effective length between bracing points
label | fd1e2906-8962-4bfc-bf23-3ef3a6a2d77c |  | note | Relative adjacent beams level = ±5mm
label | 3a240d54-806d-49a8-bfbc-6f9287f92e21 |  | note | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | 0ca16c5e-80f8-4ac0-810c-2f5d7ea88797 |  | note | METHOD: Measure , Visual
label | 35580d7b-c5e3-4f8f-95d0-694dc4e65f85 |  | note | FREQUENCY: Each component
label | f3da3016-71ab-4b0b-9758-f51c190111c1 |  | note | CATEGORY: IP
label | 506a20de-8de6-49af-add1-d3cdd1a1ca15 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 62faf26a-956a-4e38-95d8-215d4ff1fac1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4e3a7307-3bb9-40c2-9434-be504347e804 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Preparation of contact surfaces on connected plies (Snug Tight Condition)
label | 3e1fba7c-edfa-46fd-a83c-a683b1938163 |  | note | REFERENCE: 630.20 (b)
label | 62283859-b4b3-4214-bf45-209fc2020188 |  | note | AS5131 Clause 8.4.1
label | 6d945635-87eb-4416-a39b-ccb80d69ff8d |  | note | ACCEPTANCE CRITERIA: All oil, dirt, loose scale, loose rust, burrs, foreign material and any other defects on the surfaces of connected plies shall be removed.
label | f16a1b5e-6017-43cf-be65-4ee361535059 |  | note | Burrs >1.5 mm are to be removed
label | 6f0fedd6-b130-4191-989f-3b1143ae9873 |  | note | METHOD: Visual
label | 32a6ea46-5a2f-48be-b97c-d986cc9fbbdd |  | note | FREQUENCY: Where applicable, each bolted connection
label | 07454b42-9f87-480e-9034-a1061ceaba47 |  | note | CATEGORY: IP
label | 6fa29931-76fb-45b8-b8b6-5c07f97f6339 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 62e54aef-842f-4a9e-87b6-78378bdc67ad |  | note | VERIFYING DOCUMENTS: This ITP
text | a7202697-cd94-4324-94cd-6767bc5ffb99 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Preparation of Holes
label | ed05fe57-d20e-46b4-af91-119ab0833953 |  | note | REFERENCE: AS5131 Clause 6.7.3
label | ec8290d6-f05d-43a5-b558-0b9ec74cb879 |  | note | ACCEPTANCE CRITERIA: Holes on the contact surfaces shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | a0abeb0c-96f7-45fb-af0e-f8eeb6df1406 |  | note | Heating of bolts/holes, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | 7b17a860-e509-4fdb-bd0f-58cc8929e275 |  | note | Holes shall not exceed the greater of:
label | 8ac45c70-a255-49ca-a1ee-840ea9b083ff |  | note | 1.25 x bolt dia. OR bolt dia. + 8mm
label | bb866e11-4ed5-47ef-a43c-588122aa1a0e |  | note | Slots shall not exceed the greater of:
label | 1878afa2-d381-4d51-9fbb-8eedb9cbcbd1 |  | note | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | d7110ab1-a9b6-485a-8e98-e08dfefa806e |  | note | METHOD: Measure , Visual
label | 4ed4670d-2622-4af0-84c4-2f47d730d5af |  | note | FREQUENCY: Where applicable, each bolted connection
label | 3d36395e-b9b6-4fdd-9485-3e45b6103763 |  | note | CATEGORY: IP
label | f13e9480-02b6-42a6-a04d-1bfb8835de33 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4e6a3cd7-fbf5-4895-96e8-2c626769cae7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9e160360-1cc9-499d-a2d2-56c4477b66b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | 5f13a511-253c-4e4c-b3a8-183ed1f74e2c |  | note | REFERENCE: IFC Drawings
label | 56ac20ad-346b-4ff1-a896-1b9fa9c6a12b |  | note | 630.20 (a) & (c)
label | 0b12570a-aced-4cda-a8de-528a308888fc |  | note | AS4100 Clause 14.3.5.2
label | 99a30bb3-31f2-494d-8593-3d5d614488a5 |  | note | AS5131 Clause 6.7.4
label | a5635212-0280-416f-bf31-fb9f7ab67f3e |  | note | AS4100 Clause 15.2.5.2 (a)
label | 01a5e63c-db12-49b9-90a2-9e8c7227bb59 |  | note | AS5131 Clause 8.3
label | c2252e4f-2fbc-4740-81f4-b3ca9767b882 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 4dc408b7-0ddf-425e-9abc-4075809088c9 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | a5002cf0-4a9e-45af-b71d-261e135e9288 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | 1b8f6c48-f592-4dc5-a858-84f8a4a689d7 |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 942bf645-6089-4a96-900b-3c4ad6d58e7e |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | beeca6c5-da41-45ae-aafa-216c5ea9557f |  | note | METHOD: Measure , Visual
label | f467cb4a-5c01-4967-97e3-cf57e9cb1322 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 53bd686c-270b-464a-b106-874542e41277 |  | note | CATEGORY: IP
label | 58d3942a-f25b-450f-89c5-06add5f19489 |  | note | RESPONSIBILITY: SE/PE/SPE
label | bf862ff7-82a1-4272-9c03-4236f2bfd998 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3c4b2a54-7a1d-45dc-a76d-0c568fc68237 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Direct Tension Indicator Daily Records
label | 9ee622ab-119e-439f-8615-32cfae171f95 |  | note | REFERENCE: 630.20 (e ) (ii)
label | 144410f5-39aa-42d1-8631-b9599f7ee72f |  | note | ACCEPTANCE CRITERIA: Provide correlation between a calibrated torque wrench and direct tension indicators (DTIs) per bolt diameter.
label | eaab7e4e-29be-477c-8b7b-c12b242864e8 |  | note | Attach: Daily Record(s) of Correlation Between Torque Wrench & DTIs
label | c2e66bde-8ee3-4d4a-9255-8c919351bdb4 |  | note | METHOD: Test, Visual
label | 45721a13-6e7e-4ae7-9c5f-c2ab763b67dd |  | note | FREQUENCY: Where applicable, for each day that DTIs were used
label | 9243e670-c6b7-4fda-b40a-67c7ac0eadcb |  | note | CATEGORY: IP
label | c7907733-e726-4c72-9ae7-2b24bae04e15 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8209b78e-f944-43e7-85d0-dbebdc6c150d |  | note | VERIFYING DOCUMENTS: This ITP
text | 0ab6c9ae-a0bd-44da-b98a-6b2b7e876612 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Fastener Tightening - Tensioning Condition (8.8/TB & 8.8TF)
label | 3e0aa44a-4f20-4f48-91b0-cf0aa01aa646 |  | note | REFERENCE: IFC Drawings
label | 3dd33f8e-40aa-44fb-a78a-092520a63b16 |  | note | 630.20 (a) & (c )
label | cda69820-603a-4165-a266-dff375972553 |  | note | AS4100 Clause 14.3.5.2
label | 54d4c474-97d3-4130-ab27-ace3d0488df2 |  | note | AS5131 Clause 6.7.4
label | a082cb39-823e-4336-bbaa-76ada4803d17 |  | note | AS4100 Clause 15.2.4
label | c9de2439-d709-49a6-bd21-caacc6878e2f |  | note | AS5131 Clause 8.5
label | b5c83306-b99f-493d-8ef5-775c45a2b9f4 |  | note | ACCEPTANCE CRITERIA: Nuts shall be either double faced or washer faced type.
label | f94681b0-6141-4133-a4d3-a331d598c5b2 |  | note | Place bolts, washers and nuts as detailed on the IFC Drawings with the high strength designation on the bolt and/or nut remaining visible at all times.
label | 0bfd03b6-22ab-483d-b44a-bec7ad8c4cd6 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | 6000eafa-0ce8-4e5d-b43d-8074d3e18578 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | f8cb963e-0cf0-454c-8b22-302819ff5eea |  | note | Tensioned fasteners shall begin with the snug tight condition.
label | 1652bcda-e7c7-4339-980b-1c6f981b719b |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 007259e8-f802-4a6d-b4db-c0de3b07fa50 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | fa277eb5-46b8-4504-b36e-e7192da13b49 |  | note | Mark a datum point that crosses over the static part and the rotating part before tensioning via torque wrench, part turn method, stressing jack or direct tension indicators.
label | 1443e0bc-fdd8-4776-b660-68be37306603 |  | note | METHOD: Measure , Visual
label | 0a3c111f-b984-421f-b43f-2c9e5722ccd5 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 434a68f7-49ee-4847-a9a9-6758761ce22e |  | note | CATEGORY: IP
label | 3ea636c3-7d5d-4ff5-809e-5034a5a945ca |  | note | RESPONSIBILITY: SE/PE/SPE
label | 170aca4a-1dd5-43f0-839d-078b1880d7c5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 42400bcc-df95-456a-8124-daa192395753 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Survey Conformance
label | 87f2f1d2-a4be-4650-a69c-012d73649eb8 |  | note | REFERENCE: IFC Drawings
label | 8867c3a4-e1ae-49d4-bdbd-402540a93ef3 |  | note | AS4100 Clause 15.3.1 - 7
label | 8265f3c8-407d-4a53-9aa1-2f4e28491429 |  | note | AS5131 Appendix F, Table F3
label | d6c78cc8-881a-42cf-b6b1-d1233d198518 |  | note | ACCEPTANCE CRITERIA: Tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | 18564c71-9dd7-4a21-8982-7019b3a04f63 |  | note | Level of beam = ±5mm
label | c3c63c8c-b04f-4cc0-9d69-edfcfbcb4d30 |  | note | Location of beam = ±3mm
label | 36a3c4d7-25f7-4097-810a-b8c1f696e5b7 |  | note | Deviation of beam flange from intended position =L/1000
label | 9cc4ca28-47cb-4d06-92a4-3999673f0770 |  | note | L=Effective length between bracing points
label | 1300f76a-b2f9-4595-89a4-0e4a0c93591b |  | note | Relative adjacent beams level = ±5mm
label | 0832a65b-d9eb-4db5-b507-e91d87fcf0ec |  | note | Attach: Survey Report
label | 4b9b440e-65c1-40ef-be3d-865184ae3dda |  | note | METHOD: Measure , Visual
label | 4a3bfe8e-015b-4a85-bfd2-afb5e4f67b57 |  | note | FREQUENCY: After bolt fastening completion
label | 638f6f10-7923-4e19-b84b-c57c11fe2e9e |  | note | CATEGORY: HP*
label | 8f368ff4-50c5-4879-bf22-382cacf74dc4 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 10255b6b-9fd9-4961-945a-b6a9ce9aadea |  | note | VERIFYING DOCUMENTS: This ITP
text | 62b56e03-88ad-4fa8-967d-77b9b4465009 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | c75ca28f-e2a3-4b49-b242-21d5d1780fb8 |  | note | REFERENCE: IFC Drawings
label | 407573a7-ec51-42b8-a19d-114261c80a18 |  | note | 631.15
label | b12741a2-fb34-42ff-a0fb-1f36c7ede070 |  | note | AS4680 Clause 8.3 & 8.4
label | 3a8f6219-2a78-4344-a590-4eca66a91cac |  | note | AS4506 Appendix E
label | 0ae20391-dbf2-4c43-a0e1-ed3237002ef4 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
label | b7ca2112-b938-42e9-b71e-4d01fe1dad09 |  | note | Where damage exists, it shall be repaired using an approved repair procedure.
label | ea0fd089-69c0-4ada-a9ef-26d8c0a5dcb5 |  | note | METHOD: Visual
label | b4331e0d-a0d8-48b0-b6f1-cac110f08a5d |  | note | FREQUENCY: Each component
label | e1fb82ff-9785-4f2a-a3aa-508e2e77ebbe |  | note | CATEGORY: IP
label | 979995d8-794c-49a9-a4b0-502d517bd971 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e64758d5-db5d-40ff-80dc-eaf304b05fa0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 55282eeb-0d09-4073-8f71-72e5478e82e4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 IFC Drawings
label | 170169cb-d651-4933-98d7-95e050483e9a |  | note | REFERENCE: AS5131 Appendix F, Table F3
label | 7fecae4d-c22c-4ec9-a2ea-c1e4068c80a4 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 0b8534a7-331a-41cf-8029-d1c847632e5e |  | note | Departure from RL = ±5mm
label | e5aacd9b-c83a-4d13-bc55-a1247cc3054a |  | note | Departure from plan position = ±5mm
label | 4be00472-11fb-49d3-a196-ce58a997ecc4 |  | note | Departure from alignment = ±5mm
label | f11eb92c-edf9-44aa-9951-c1850188405d |  | note | Irregularities in alignment = 25mm in 30m
label | 1e1f5266-eb1d-421d-b422-93e83cf701d2 |  | note | Location of beam = ±3mm
label | 2cd0d837-be1b-44fa-bd7f-25c122bb8a46 |  | note | Attach: Survey As-builts / Survey Report
label | f060d306-33a4-441c-9432-5b54bee17c46 |  | note | METHOD: Document Review
label | 9810564b-8ffa-47d1-b1ed-c6031e70ceab |  | note | FREQUENCY: Each element
label | b0d48f60-0581-4d3d-8113-c7d5a2b890bb |  | note | CATEGORY: IP
label | a256bacd-5303-4b74-8e15-901285df0f87 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 6c3a61b1-a11b-453b-85ed-be4fe355620d |  | note | VERIFYING DOCUMENTS: This ITP
text | c42facf2-e12b-4f79-b068-f344ebc69447 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | f644895e-9ffe-4e11-9913-0f998c14bc57 |  | note | REFERENCE: MRPA Quality Management Plan
label | 9e02b84d-2e3d-4736-939d-6ba72191ff3e |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 66c21cbd-8465-44c9-b458-01e5eecd6ba8 |  | note | METHOD: Document Review
label | add9a112-834f-4862-85cd-8a5a3196bc2a |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | a81ab6ca-dc85-428a-bd3f-3c9008deb60e |  | note | CATEGORY: HP*
label | 15e8a4c6-1027-4020-988e-671f196bf98c |  | note | RESPONSIBILITY: SE/PE/SPE
label | df039f18-26aa-47eb-b0bd-09e4f550f135 |  | note | VERIFYING DOCUMENTS: This ITP
text | c0eb8051-18ff-48c6-b792-017c9f74bec7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | aca38af2-36be-4df6-b437-7a5761d913b3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1d6d98cf-bf34-4108-a625-a96755c93624 |  | textbox | Name:
text | 8f00dee6-c2b2-4348-a0a4-0e6007beb62d |  | textbox | Position:
text | 07089aa3-a863-401e-acab-62d5c615e715 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Structural Fill (Supply and Install) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Structural Fill (Supply and Install) Rev 0 | 452f2471-f770-40e8-9693-46a632488738
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | bfaef0fc-935f-408e-a219-124018b2d25c |  | note | Document Title: ITP-CIV-Structural Fill (Supply and Install)
label | e926581c-308c-4eb8-8dbc-b0617f534138 |  | note | ITP Description: Structural Fill (Supply and Install)
label | 061274f7-752d-4a87-b31d-6b074b6aa678 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 6f4fee37-1000-46f6-920f-e5f783e682fe |  | note | Revision Number: 0
label | e7e7392a-1927-4e4d-8e9c-418f7996f70b |  | note | Revision Date: 1/06/21
label | f7b88afe-94dc-4dab-ade8-2b16f891df42 |  | note | ITP created by: Matthew Dib
label | 38ddcda9-54c5-4114-b8b6-73b9188051ec |  | note | ITP approved for use by: Aldrin Guinchoma
label | 99089467-972d-4b56-b839-bfbc4ebbcee5 |  | note | 1.1 VicRoads Section 204
label | 76edcb9a-c61f-4cad-a6e2-e19d088b2069 |  | note | 1.2 IFC Report and Drawings
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Structural Fill
label | 54218d18-0670-44da-b072-7a96a0c2bc9f |  | note | REFERENCE: Section 204.04
label | ecd8f733-453e-408b-afa0-7c99321b6fc9 |  | note | Table 204.141
label | a83af239-0850-46c7-9793-076775ff9c9a |  | note | IFC drawings
label | 96ea7acf-18a9-4ba7-99ee-9d806be51931 |  | note | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
label | b01c6ac1-e7be-4b5a-a805-ef8a7ee7b005 |  | note | Scale B
label | 6baf2a52-4409-4d55-afb1-f0395a0b7be0 |  | note | CBR ≥ 6%
label | 1e047f44-ea5d-4611-88af-5f1ba86bcc54 |  | note | Swell ≤ 1.5%
label | a3fd63f6-8b03-4f6d-9bcc-c3ebc3ad8cd0 |  | note | PI (LL) = 6 - 25
label | 3c45f271-7026-4209-a3df-d4cd48d71011 |  | note | Internal Friction Angle = 28*
label | 7a0ec44b-b691-4c47-81bb-309cc5cf0e51 |  | note | Effective Cohesion = 5kPa
label | 678d3854-f079-404f-acff-a74efc562dbe |  | note | Unit weight =20 +/- 2 kN/m3
label | e11c48f3-78b1-4fb4-b8ea-6cbbd97da342 |  | note | Grading:
label | bb382948-7a78-49ef-b2db-0c29983ff227 |  | note | % passing 75.0mm sieve = 100
label | bd637efc-ae4c-4f24-b13f-d64c9f63eb4a |  | note | % passing 4.75mm sieve = 40 - 80
label | 68672389-38f6-4d39-b362-f729b7890178 |  | note | % passing 0.075mm = 10 - 40
label | 0ef67374-3471-4de4-b539-f6d4e5d9ce1d |  | note | Attach: Test Certificates, Delivery Dockets
text | fe5eee66-0108-40b4-80bf-0bfed5d1f74c |  | textbox | Enter: Teambinder Approval number
label | 382075c1-2133-4671-8a80-6b2886f807f9 |  | note | METHOD: Review and Verify
label | b49ec64a-34e4-424b-8c42-31f5aabcad32 |  | note | FREQUENCY: Once per material type prior to commence of works
label | 09742acd-034e-4409-ac12-edac51b68d9b |  | note | CATEGORY: HP
label | 6b9ccfaa-77d6-46b3-a297-4e722d8ee09e |  | note | RESPONSIBILITY: Nominated Authority
label | 5584229f-0f7b-4fbd-9ce0-ef4da7f51bc8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ed2a9cd1-4fb4-4c53-993e-676f753e2f98 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | d6c2c387-1bec-49d3-8188-ed098eee2df1 |  | note | REFERENCE: Section 204.03
label | 2aad9695-ba76-4198-bb92-1793c7ce40a8 |  | note | IFC drawings
label | 167d4993-afed-4b05-9dac-29b3ffba81d6 |  | note | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
label | 36284b18-22ea-449d-adbf-47d0f35e3fce |  | note | METHOD: Measure , Visual
label | 2aa9537b-cb9d-4259-8e06-5419ce7e5185 |  | note | FREQUENCY: Each element
label | d75aa49c-e1e8-40ae-be02-7f4dabeb4fa1 |  | note | CATEGORY: IP
label | 429beb88-f505-4d0d-85fe-79262ddd6cc4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0a96d43c-3131-4dcf-9046-e877a4347119 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6659c5df-b1dd-4f7a-aa3f-85bdc86cadc3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Fill Activities
checkpoint-status |  |  | checkpoint | 4.1 Structural Fill Placement
label | 207fff33-39f4-45c7-bb8d-51cd299c7653 |  | note | REFERENCE: Section 204.10 (d) (ii)
label | e2abe109-b660-4988-888c-aa1dd1032802 |  | note | IFC Report and Drawings
label | d0225f84-c4e3-4b3b-9136-9226bd34b90d |  | note | ACCEPTANCE CRITERIA: Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness.
label | c9457ad2-c1ad-4e97-85b7-8994cc39b898 |  | note | Extent of fill placement to be as per IFC Report and Drawings
label | 0d1e3e51-1286-48fd-88c4-311d8bc08314 |  | note | METHOD: Visual
label | 9ed70481-473c-4820-bc94-14cae7098d34 |  | note | FREQUENCY: Each lot
label | 407c1a5a-bdd1-4aba-81e4-05c73438045c |  | note | CATEGORY: IP
label | 4d56ad1a-cf47-4f7c-ac3f-0c302c66c7ad |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 644a5022-fd03-4722-a32f-f4b7adffab11 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | d721470b-e561-4e44-87d7-781a6192f71e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Keying of Layers
label | 162f787d-813b-497b-8280-9f3e3540bf58 |  | note | REFERENCE: Section 204.10(d)(i)
label | e2b7864c-debc-415d-b3a7-b40a7e211717 |  | note | ACCEPTANCE CRITERIA: Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | 4eff8daa-223c-41f8-acb2-873a2054f67c |  | note | METHOD: Visual
label | 57f55466-2f77-4a09-a2c8-b5abdc858234 |  | note | FREQUENCY: Each lot
label | d7a8bf08-bc98-4818-b0f8-8542d09e4e5d |  | note | CATEGORY: IP
label | 41d0502c-0926-44f6-aaa6-d1db9ca0fb58 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c7ba581a-3eda-42b9-acdd-818a0cd608c2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 905e2ec8-9e48-48e4-86b6-71ecf6cc994e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Proof Roll
label | c0650dab-ab3d-463c-8b88-f1e903795288 |  | note | REFERENCE: Section 204.13 (b) (i)
label | 1de5982f-3f67-4bec-a88e-b481438af4ac |  | note | Section 204.12
label | 11f28bd1-e31a-4d27-8588-fe07994968a7 |  | note | ACCEPTANCE CRITERIA: Withstands Test rolling without visible deformation or springing.
label | 28a3722b-20d3-453e-80bb-9c1880d573ff |  | note | No fill to be placed until the area has been reviewed and approved.
label | df0038f0-4965-49df-bd55-fd1628c557f1 |  | note | METHOD: Visual
label | 2c5ed92f-dfcd-46f4-9dbe-bb306d4bd577 |  | note | FREQUENCY: Each lot
label | d0836696-decd-4564-b1a8-c93421a833f7 |  | note | CATEGORY: HP
label | 4baefb03-68d3-462d-8bec-9cbee19b2ac1 |  | note | RESPONSIBILITY: Nominated Authority
label | 49035d3e-9036-4145-9e4f-c9be3828c110 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | edb5b389-efd8-477e-8752-e403f53aa806 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Compaction Testing
label | 568100fd-1c57-4080-a701-bfdbb9491553 |  | note | REFERENCE: Table 204.131
label | 2408610a-ecef-41a5-9e54-31aa54a5020c |  | note | Section 204.13, 204.14
label | b04e0364-94e5-4305-940f-93b667e8e9ba |  | note | ACCEPTANCE CRITERIA: Frequency = 6 tests per lot
label | 46b5085b-2020-40fe-8a4f-88bba9119541 |  | note | Lot = One day's production or 5,000m2, whichever is the lesser
label | 3d476110-c6e2-477f-b6a3-ee3caea70ec9 |  | note | Characteristic Density Ratio =
label | a4d2d89e-ac72-470d-ab19-3052b6f05ac3 |  | note | 95% minimum when more than 400mm below top of Type B Fill
label | 94943b23-0246-49dd-a748-932069a8a58a |  | note | 98% minimum when within 400mm of top of Type B Fill
label | 1a560c88-dff8-4b14-b3ec-d893b57bf35f |  | note | Attach: NATA Compaction Test Report
label | 3c6afb8b-ba78-4414-b37b-12bd5cc07ae4 |  | note | METHOD: Document Review
label | f73e9bac-a3d4-4839-bbc6-005ccb0fbb23 |  | note | FREQUENCY: Initially test every lot until three consecutive achieve passing results. , Min. every 2nd lot of like material and work
label | d624dc98-2b56-4362-a47b-a7dc0f7bf316 |  | note | CATEGORY: IP
label | f6a82a89-0f30-45ec-994d-d3b19bd06e89 |  | note | RESPONSIBILITY: SE
label | 1a6e97e3-8a00-45d5-b12c-a05c71de0c54 |  | note | VERIFYING DOCUMENTS: Sign ITP , NATA Compaction Test Report
text | 9378a3ac-bbf5-4596-903d-8c5638d9ca01 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Post Compaction Material Property Testing
label | 4f9bc460-9012-40ae-a78b-dd364266c532 |  | note | REFERENCE: Table 204.041
label | 42a53456-418e-4325-b0d2-4a9516bc79a0 |  | note | RC 500.2
label | 23a720cd-6e52-42ed-8aa3-3bfe33e2a5b7 |  | note | ACCEPTANCE CRITERIA: Structural Fill Material shall meet the following requirements:
label | ba8d1dc2-e519-4362-8f7b-5e8e3bde7266 |  | note | Scale B
label | 9b6bc83b-f9a6-48ed-abf8-3cba154c4d3e |  | note | CBR ≥ 6%
label | 111d7250-74bc-4677-b41b-4a4b0f3cf652 |  | note | Swell ≤ 1.5%
label | f823a585-23a5-402d-ae67-bcd53f07140b |  | note | PI (LL) = 6 - 25
label | 1987220d-d9bf-4c63-ad7a-2da0a7ea69dd |  | note | Internal Friction Angle = 28*
label | 3b261c82-d8f0-4c5a-8c38-35cf29138f80 |  | note | Effective Cohesion = 5kPa
label | b10f1cca-912f-4ef3-9f12-27e8c47d8983 |  | note | Unit weight =20 +/- 2 kN/m3
label | 0dbcb3db-ac7c-4973-a3df-540b038bcdfa |  | note | Grading:
label | 468cdec0-43d8-4a42-9e4b-8fb4d9384c86 |  | note | % passing 75.0mm sieve = 100
label | 0a8b0001-1055-4877-89ca-eccc1423be70 |  | note | % passing 4.75mm sieve = 40 - 80
label | 019c6d4a-a229-43e2-bada-3b1300de0f15 |  | note | % passing 0.075mm = 10 - 40
label | 2e91a2fc-4862-4a14-8a22-dbf01b0fef7e |  | note | Attach: NATA Material Test results
label | c3d7da00-56c6-432e-b565-917ec5ef1fed |  | note | METHOD: Document Review
label | d64c026f-0fc3-4f74-b779-9a22e3de5b53 |  | note | FREQUENCY: to be tested once post compaction
label | 2630a627-9604-4cea-92e6-7c9c3c5da537 |  | note | CATEGORY: IP
label | a8481419-ddcf-402c-a11b-0879f11ee874 |  | note | RESPONSIBILITY: SE
label | ae821168-ef04-4b9c-8e3e-88e07397e793 |  | note | VERIFYING DOCUMENTS: Sign ITP , NATA Material Test results
text | 6092d2e4-9816-4e83-b1c8-c1a294bbcf0f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Preparation of final surface
label | ce9bfb2c-aa22-4abc-9b63-071d18f67cb6 |  | note | REFERENCE: Section 204.15
label | b2ac77c9-c0a0-4606-a18e-1a1c9954debc |  | note | ACCEPTANCE CRITERIA: The top of the subgrade surface shall be prepared to level and shape to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
label | 7014ae3a-9982-4e4d-a3c8-47c4729cdf38 |  | note | METHOD: Visual
label | 18882bb4-2d64-4baa-aea8-7135dfa06c27 |  | note | FREQUENCY: Top layer
label | acb00f7e-75f7-4748-aec3-cc22c53c97c4 |  | note | CATEGORY: IP
label | e370a197-57c3-4ec4-b461-b9e3490a169f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 24c997e1-bd3f-41db-b81b-37948f30b1af |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 7e4b6467-74df-4db3-a7fc-5aa622b88017 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 As-built Survey
label | c0fa483c-3aeb-4fa6-872e-58afc0a3d403 |  | note | REFERENCE: Section 204.03 (h), 204.16
label | 510b451d-e389-4f80-b62e-0107ca31323e |  | note | ACCEPTANCE CRITERIA: Scale B:
label | 2859571b-4f18-4e89-a93b-460d66c478d9 |  | note | Min. No. of Measurements Per Lot: 40
label | e924e8ac-f4b1-44b9-b97a-24bdae8745a9 |  | note | Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
label | 5b59e886-35d9-4d91-9425-842b1c905553 |  | note | Attach: Survey As-builts / Survey Report
label | 719609d0-8b83-4f37-b9ad-33d4114bbabb |  | note | METHOD: Document Review
label | 4a6e0c74-eba1-4704-bd00-49a1e6c4b9d8 |  | note | FREQUENCY: Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
label | ca133f91-e3e3-43f8-bd12-091fe80e0a59 |  | note | CATEGORY: IP
label | 962f41de-f6d6-4cd9-803b-823e98eef678 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | c82029bb-2633-44a7-833e-0ac970da1397 |  | note | VERIFYING DOCUMENTS: This ITP , Survey Conformance Report
text | c5917c43-a20e-4c6c-86d1-0d4d44f17ef0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | 4034073a-3090-4f8e-807a-abb1bd4e7713 |  | note | REFERENCE: MRPA Quality Management Plan
label | c5445170-3553-455b-bfb8-ac1623dc4fa8 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 25446fed-df4e-41a0-b20e-ff20c0571fc9 |  | note | METHOD: Document Review
label | e9a3bcef-3047-4563-8d99-2fabf8da6672 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | d18427a7-c9df-4a67-9438-6ce0fc51a69d |  | note | CATEGORY: HP*
label | e71aad62-af06-4c1b-b43f-1095a2c1970a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 580058b3-f084-4f26-9122-bb25c23c359a |  | note | VERIFYING DOCUMENTS: This ITP
text | 28004c64-8aba-4522-9405-afe6edaee20c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | cd70cf15-94bd-41f0-8908-b2e984ca9bd8 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 00978a5f-9a40-48d1-ba49-fab43f5ef093 |  | textbox | Name:
text | 999bec48-33fb-4214-a627-e6db2b57dd02 |  | textbox | Position:
text | 2c217529-c54a-4747-b489-73d3de33a080 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Rail Delineation Fencing Rev 3 | itp |  |  |  | Yes | ITP-CIV-Rail Delineation Fencing Rev 3 | 46334cd3-37cc-41c4-93cc-7902a6050575
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 3f63292a-c4df-4522-96e6-43a7ad356cd7 |  | note | Document Title: ITP-CIV Rail Delineation Fencing
label | 4924cdf3-7644-4c5c-84fa-343d0abb65f1 |  | note | ITP Description: Rail Delineation Fencing
label | 030d1fb2-b5fc-4fd1-ba0e-155905c64745 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 2f657797-99dc-4fa0-b54a-9c9743eb3d0e |  | note | Revision Number: 3
label | 7654b719-59e5-46c8-802d-0b215c12b0a5 |  | note | Revision Date: 11/05/20
label | 7fe730f4-0a5d-4974-a517-209c8623d34d |  | note | ITP created by: Thilan Rathnayake
label | d36756f7-e31e-4d30-8ad7-04acf705971e |  | note | ITP approved for use by: Josie Pavlou
label | 4e975fc6-692f-4117-8aa6-f79b60b1b9a7 |  | note | 1.1 Reference - IFC Drawings
label | 9aaa1848-722c-4614-bf68-c0bee7b772bd |  | note | L1-CHE-STD-005
label | d829c1cb-7202-4cf8-9763-2e3757e1180f |  | note | L1-CHE-STD-025
label | 7e51a570-3a6c-452c-bfe1-c71f07b60941 |  | note | VicRoads Section 610
label | 23a742a3-acf3-4376-b00c-df5b2beb3eba |  | note | VicRoads Section 630
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete
label | c1cf077b-b27e-4dbe-99cf-199ee4a5bf2d |  | note | REFERENCE: IFC Drawings
label | 3a1808e1-9881-4f8b-a748-3110a59873a5 |  | note | Section 610.07
label | 7545d723-f0ae-41cd-a07b-e95b94aa846b |  | note | Table 610.071
label | 351e936f-5753-4c49-87c8-5a6e3c6d0beb |  | note | ---------------------------------
label | 5279d501-e553-4c9f-be08-1a2112c8c73b |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | 09089f3a-bc3c-4fc5-ad15-4789f4d72116 |  | note | 32MPa concrete to be used as per IFC drawings.
label | bab3078d-f0a5-47cb-9162-af2ccdb1a23b |  | note | ---------------------------------
label | c3b479d6-a58a-496f-8c74-11962172efdf |  | note | METHOD: Document Review
label | 77c7b448-a95b-4e13-9ede-1600de724a2b |  | note | ---------------------------------
label | 80f5990c-ef2d-4c34-b77e-efaf23cd731b |  | note | FREQUENCY: Each Mix
label | e668393b-1700-4db3-8a28-55d077b0d0be |  | note | ---------------------------------
label | a9eb389c-05dd-4837-a321-60cb3e7aae0e |  | note | CATEGORY: HP
label | 7f6fcf7c-d293-4ab9-8fee-4d4586e7fff8 |  | note | ---------------------------------
label | 33f2c86c-b6ed-498d-87e8-68a8e0e6bce3 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | a0df54ad-6a6f-44ea-8489-584886a24b50 |  | note | ---------------------------------
label | 62841a36-dcd4-4a77-9888-b4ed76abc180 |  | note | VERIFYING DOCUMENTS: Certificate of Compliance
text | 0f3bebaa-54a6-4df0-b34f-f63797e541b4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
label | dd32db01-1ba2-4f52-9070-7b027d6ae0ad |  | note | REFERENCE: IFC Drawings
label | 4605fccc-d61f-4c8e-93e8-070eaa780e70 |  | note | AS41000
label | 26edf339-4447-4be9-b932-f8eaa42a674c |  | note | AS1163
label | ca5686b9-622c-4323-a49b-35d89ac56629 |  | note | ---------------------------------
label | 0b7387d7-aa65-4899-b466-b4a66ca19f98 |  | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | da374ba3-f262-49d4-b27b-d7d57fb4745e |  | note | Steel section sizes must be checked on site.
label | 81dbda09-e86a-4ec2-86cf-3dfb62d71ca7 |  | note | Steel posts to be CHS with a grade of C250
label | ad2f1f65-e640-4a6d-863f-3922f4d4cc4e |  | note | ---------------------------------
label | 14c981bc-5388-4b21-a8db-26ed497de8ea |  | note | METHOD: Document review, Visual and Measure
label | 44de8282-cbdc-4d84-a3ec-38dacbc2db69 |  | note | ---------------------------------
label | dfbaa744-42ed-4365-bdc1-e844728e8ce9 |  | note | FREQUENCY: All elements
label | d06e37f3-577a-4f2a-a051-77808aae2484 |  | note | ---------------------------------
label | 4cdf00e5-48dc-485e-8b2d-a03c203e1653 |  | note | CATEGORY: IP
label | 32f730b1-d492-422a-855b-485ac6736544 |  | note | ---------------------------------
label | 86acface-a882-4542-9f2e-c1f92d411841 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 37301afe-846a-4e9a-9676-7c9475113a74 |  | note | ---------------------------------
label | a769b76c-b7a6-4711-90b1-dad04cc881de |  | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
text | 9c187260-a88b-40b2-80f0-c82867d4bb1a |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | e7ca53b0-06e5-4f70-a7c8-dcbaf3491186 |  | note | REFERENCE: IFC Drawings
label | 2741d7a6-2b95-4aaa-9333-93245eecf802 |  | note | ---------------------------------
label | 13c057bb-86a8-40ad-bf80-997c124c5080 |  | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | 6d7ad3a2-4139-4704-9b67-6c118c29bc89 |  | note | Offset checked against the running edge prior to
label | b48fdd14-b984-43c5-945f-eaa751e58cce |  | note | installation of posts.
label | 92f2b2d5-7d25-4690-aba7-a2b2d88f3a18 |  | note | ---------------------------------
label | 6cdf03fb-aa93-489c-a09d-224a57f50205 |  | note | METHOD: Measure, Visual
label | 55edd090-ca31-4021-8282-a388329b13e0 |  | note | ---------------------------------
label | 6e47c34c-da97-4829-9613-1061dbc7aef3 |  | note | FREQUENCY: Each element
label | c5e5c4cf-0d1b-4e03-a7e3-4f1722c00ea2 |  | note | ---------------------------------
label | 7d678617-e1b2-45d4-81ce-8f848ece160e |  | note | CATEGORY: IP
label | 8b8edcc4-f25c-41db-89dd-96853d270140 |  | note | ---------------------------------
label | 61db7bf2-f076-4691-8699-cafcb75391b5 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 1643a034-947b-491a-934f-c0aff63bba3b |  | note | ---------------------------------
label | 3aede3b0-bad9-4d99-a7f0-cb4b42e2cfb8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2528af59-5a34-41f5-b2c1-5e3bb91d6382 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Excavation works
label | 56400e85-e8be-4fed-9cc0-edb8443b3f4f |  | note | REFERENCE: IFC Drawings
label | d198c43e-eb16-4996-b350-f62e482b3891 |  | note | L1-CHE-STD-005
label | 5a8cf66e-8241-4d63-80e4-e916163b401f |  | note | ---------------------------------
label | a8f6b41b-8926-4350-8d0a-f2c028276678 |  | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
label | 6a6cc9ba-f307-47e2-a1b0-99ca5f3f075a |  | note | Follow asset owners guidelines for work around their service.
label | 1ae139b5-63ad-4a15-99ad-111499faa974 |  | note | Excavation must use Non Distructive Digging in the rail corridor
label | 1948cb73-1591-4558-aece-04c6f8caef66 |  | note | ---------------------------------
label | 296c9360-9713-459f-a08b-ff77973f7adf |  | note | METHOD: Visual
label | c69244f6-27d8-4051-9c70-a4c11dcbdc2d |  | note | ---------------------------------
label | b3fd76e4-78c6-436c-8718-5eb8dc6fbc00 |  | note | CATEGORY: IP
label | aec4184e-cad3-490c-9b63-29d3193ccb38 |  | note | ---------------------------------
label | 7d011e1c-8170-4cb4-9d00-4894140ccceb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b7f518a5-7369-46fe-8868-40af92ed9aa6 |  | note | ---------------------------------
label | 50f96a0a-4818-403a-a55a-d075d6a8c045 |  | note | VERIFYING DOCUMENTS: This ITP
text | 552a73d4-9e24-45c2-874e-65595394fbba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Ground Conditions
label | 0b98e4a9-07ca-4c1a-bfeb-a2db784748fd |  | note | REFERENCE: IFC Drawings
label | 85f9c9ff-16c2-41a0-9eae-a820a56f3dbf |  | note | ---------------------------------
label | 68e83e1e-7150-4340-b502-d928ccf47ee9 |  | note | ACCEPTANCE CRITERIA: All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | fa11ce43-73ad-4c82-86ff-2005df9ab613 |  | note | If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | 0176ee35-93e1-464c-81cd-c20af4333ab1 |  | note | ---------------------------------
label | 3e54ebca-cd17-496a-af16-6eb6d870df10 |  | note | METHOD: Visual
label | 309632b3-2d0b-4067-9c30-b5767358c197 |  | note | ---------------------------------
label | ca6f1a68-6dc2-40f2-8b71-6ee5d56e50be |  | note | FREQUENCY: Each post
label | a683e053-f8bb-4edc-bd3e-103adc338c4c |  | note | ---------------------------------
label | 354b1eb0-8c69-4632-b873-e4e7cea59667 |  | note | CATEGORY: IP
label | 701d9301-8f29-40cf-b490-54293dd7b0b4 |  | note | ---------------------------------
label | 9e0215cd-78ae-4d39-8e08-72a22575feb9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ae69fda6-99d1-417e-9b4d-04d0c085dc0b |  | note | ---------------------------------
label | 9223d72c-099c-4bf8-907e-690eb3e628f4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 015d54e1-99bf-47f4-9073-abc982710752 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 MTM OHW Structures
label | c4d2a5ff-3971-49cb-be90-3ac5c4519a1e |  | note | REFERENCE: IFC Drawings
label | 0e24090a-80d9-42ae-97f5-2a91ed0c08d3 |  | note | L1-CHE-STD-005
label | 763dc2de-788d-45ba-b15c-f076ea9634b5 |  | note | ---------------------------------
label | 58615a7e-fcd8-434c-9867-dad979cef0e6 |  | note | ACCEPTANCE CRITERIA: Fencing must be a minimum 2m away from OHW Structures.
label | 1f297490-a189-4d52-af07-d0910b8a7d94 |  | note | Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
label | a3f8d586-e549-4b2c-975e-14a1d27f13f1 |  | note | ---------------------------------
label | 8bfcc199-a874-49ea-9fde-159a4c52f830 |  | note | METHOD: Measure
label | 1d0d757a-0ac0-4b46-9702-0c7f0f0b97ad |  | note | ---------------------------------
label | 9a58790f-9aae-4577-b828-865ef2142966 |  | note | FREQUENCY: Each Overhead
label | 65ba920c-8486-4558-afd4-739363ad92a2 |  | note | ---------------------------------
label | cfe87b26-265e-4517-b6d5-a44bb30d3972 |  | note | CATEGORY: IP
label | 5f9c94ea-b387-47b0-80b1-dc1ac5165cbb |  | note | ---------------------------------
label | 76662aa5-4790-48c9-bc33-84d77651bda6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | d5ebc11f-9681-4d91-97c5-d55c09161108 |  | note | ---------------------------------
label | 0db2fa3c-21df-4490-b38a-b03d186679c0 |  | note | VERIFYING DOCUMENTS: This ITP
text | da68b1d7-5233-4b45-a9af-8ea217247682 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Post Foundation
label | 2872c7cb-616b-4a01-885a-a3784b1a54f8 |  | note | REFERENCE: IFC Drawings
label | 2f1f401d-cce1-4d46-8daa-08f4ab0c830a |  | note | L1-CHE-STD-005
label | f001161f-0cb7-4b79-9ab0-078638e65480 |  | note | ---------------------------------
label | 2db6de1b-78c5-468d-aa31-cabb9eda2fa8 |  | note | ACCEPTANCE CRITERIA: Without shade cloth - depth 750mm, 300mm dia.
label | 3963d334-fb71-4065-8379-49cc75178a4a |  | note | With Shade cloth - depth 1100mm, 350mm dia.
label | 9644a69b-b11b-4826-8edf-a95c551a0564 |  | note | DN80 MS Pipe to be installed full depth.
label | 0030082d-4a8c-46cb-a246-06c0575628b0 |  | note | 101.6 x 4.0 CHS sleeve to be installed in the road section of the temporary fencing.
label | d7f26f0d-e4dd-4ca0-ada5-bddbc4b255a7 |  | note | 32MPa concrete.
label | 2a7f9679-576b-497d-a248-a62ad981388c |  | note | ---------------------------------
label | 4535727f-4de1-4a70-a4fc-c63922d6b230 |  | note | METHOD: Measure
label | 12106344-8873-47de-a8e6-05bb6dab14d7 |  | note | ---------------------------------
label | 3c294787-53a4-49ff-9c77-579eb66c9849 |  | note | FREQUENCY: Each footing
label | 9c127c4b-bf59-42ab-a294-7c5f7719dd8e |  | note | ---------------------------------
label | 350f2561-5780-461a-aa90-99637ee86aa3 |  | note | CATEGORY: IP
label | 68851f9c-b2f7-485a-9f4a-b707636f259c |  | note | ---------------------------------
label | 266e78b1-e6b4-41e7-ab4b-be597af21e56 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6f993b86-bd06-41c3-ac37-3ae778ed6780 |  | note | ---------------------------------
label | 7ecc81e5-07bf-42da-b799-671d5ea38b33 |  | note | VERIFYING DOCUMENTS: Post and concrete dockets
text | 3a5b72e8-444f-4c33-9960-d2015b0add5e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Post Installation
label | 28252b6c-6255-41af-83a5-31728386b1fa |  | note | REFERENCE: IFC Drawings
label | b8e54bf9-4449-4631-9e62-5fe19370758a |  | note | L1-CHE-STD-005
label | 745331d1-cea0-4ef7-b8ad-80ef0efea4c6 |  | note | ---------------------------------
label | 54b3109e-966d-4616-ba44-a0430a8d769b |  | note | ACCEPTANCE CRITERIA: Maximum post spacing to be 3m ± 250mm, two spans at 1350CTRS at the end and at Refuge bays.
label | ebebaf0b-70b4-403c-a7e4-342b76892988 |  | note | Minimum offsets from centre of the rail to the fence:
label | d2064c5f-1a51-402c-ae1d-08fdf1a628e4 |  | note | Uptrack - 2300mm
label | 12a48ff8-8e2e-4173-b4ef-ab3bbfc82732 |  | note | Down Track - 2200mm.
label | fc694d85-fb95-4a28-add3-533b6484eaab |  | note | Alignment tolerance: +20mm to -0 (- being closer to the track)
label | efe45d89-cfa2-4856-a6fe-e9f6cb24c8ea |  | note | Max. post height 1800mm above ground level.
label | e13bb9e6-1a03-4ad7-b787-779a543b1d2e |  | note | Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
label | 1643b5bd-e0d3-4b27-84dd-ef8b7d63e03a |  | note | ---------------------------------
label | 7b9a82a7-148e-4113-af92-3fa03b7566f0 |  | note | METHOD: Measure
label | e9e6f75b-c75e-4fe7-9baf-68126b3c11a7 |  | note | ---------------------------------
label | a909250b-85d0-41f0-b914-c0f08df17d6d |  | note | FREQUENCY: Each post
label | ce1c4f86-ed4f-4852-8e55-c9f35a557e37 |  | note | ---------------------------------
label | 151d4845-81f0-40e8-b556-364bfc9658f8 |  | note | CATEGORY: IP
label | 36ba7a0a-7635-428a-a02f-fdd0b420d4e2 |  | note | ---------------------------------
label | 991d2959-b5b7-46c7-8acc-c8f67472d38e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 55357015-cb73-4392-b3e8-d95de691f643 |  | note | ---------------------------------
label | 98a3163f-f1e9-488f-a756-8ce746a81c93 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete dockets
text | d65bafd1-6292-4ca1-b862-d18a88c23eed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Chain Wire Mesh Installation
label | 3f96b4e2-a433-46cd-9c3d-5a0a1866d35a |  | note | REFERENCE: IFC Drawings
label | 66f12ee7-6134-4fb2-977b-9268e411bb64 |  | note | ---------------------------------
label | caec4e2b-8280-4fc7-a499-b1c09791b1ee |  | note | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
label | c6e892ae-6e0f-466c-93e4-b828318aead0 |  | note | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | f4812cbb-a782-40cd-893d-61dc41e1c311 |  | note | ---------------------------------
label | a328d003-583e-4be6-a8e5-62c42ab79c85 |  | note | METHOD: Visual
label | 53c6b775-8527-4c93-82a6-603acac18652 |  | note | ---------------------------------
label | 4b7a43c6-cea0-4fad-9eb2-6d3a3e0713ee |  | note | FREQUENCY: Each element
label | 3bd49061-69e9-42d6-9e61-92c0d3a42fc9 |  | note | ---------------------------------
label | 1ec22f6a-d3a8-43ec-80d6-2caa208419c8 |  | note | CATEGORY: IP
label | 2d22d3e5-cd9f-4d30-aaa1-23009bc6aace |  | note | ---------------------------------
label | 7942d1e3-55b7-492e-ac43-53fae2884a04 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 324d4bfa-1cc6-487e-aa6d-ed55bb6d70f0 |  | note | ---------------------------------
label | 9d6ce4c5-c9b2-4aeb-ba08-aed53a4ead62 |  | note | VERIFYING DOCUMENTS: This ITP
text | c553d0b2-f39a-41d5-a8fb-74b556eb4539 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Bracing
label | 81742cfb-f580-4f5d-9f69-72699bacf12f |  | note | REFERENCE: IFC Drawings
label | 7df98d33-1c2d-49c2-8b5e-71fc6a4ec166 |  | note | ---------------------------------
label | 9c5b7cf8-d66b-49df-9a9f-31087fd5185a |  | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 7e213056-85a5-4bbd-8b2b-eea22bb217f2 |  | note | Bracing to be installed on both sides of the fence at the fence corners
label | b6a5718c-87d1-45dd-a5a1-996cd32f35b9 |  | note | ---------------------------------
label | 0c20dddc-a7b0-4e4f-ae8b-2a98cc08d37d |  | note | METHOD: Visual
label | 7c65b8fd-6e6c-4c62-9e8d-35528ef7290d |  | note | ---------------------------------
label | b23139f6-8c70-45ad-aee9-4b4c588caf71 |  | note | FREQUENCY: Each element
label | a9be059c-d7eb-4f63-a854-126a1f0a1282 |  | note | ---------------------------------
label | f00bdf45-40c1-44df-84d9-08aaca9e5500 |  | note | CATEGORY: IP
label | ff87f2ea-18e4-472a-8e29-a1e83ea6507c |  | note | ---------------------------------
label | a12e9cb5-a7a6-4788-9ffb-bde5cdecad9b |  | note | RESPONSIBILITY: SE/Site Supervisor
text | 9856e0db-fdd7-461e-ad82-caa915cd21b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Refuge Installation
label | d86fe6b2-481e-41d0-b1a3-5d2978aeeeef |  | note | REFERENCE: IFC Drawings
label | 9f5a8c28-2894-42ef-944e-cb6287646867 |  | note | ---------------------------------
label | a865f140-3c4a-455d-a6b3-e87ffd39949e |  | note | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
label | 2e4e1e28-b0d9-4734-b762-c95fa04826ee |  | note | No chain wire mesh to be installed at refuge access.
label | b0faa23f-a23d-4851-a1cd-f15cce11f6f3 |  | note | Refuge Access to be located every 15m max. along the fence.
label | 8060406b-69cc-41c2-b65d-9d48aebe79fe |  | note | 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | 67dcab5b-314f-47fa-806b-b3c0b26c7737 |  | note | ---------------------------------
label | 5965f825-5fe4-42f0-915b-7316fb96b4f4 |  | note | METHOD: Visual/Measure
label | cdef1671-a16e-4797-8411-1148352da5e9 |  | note | ---------------------------------
label | dc1eb67d-2954-4b8b-a77a-67915a08a67f |  | note | FREQUENCY:
label | 4a2af072-2160-4c1a-8a19-f517891432ec |  | note | ---------------------------------
label | da830c26-7790-48ef-ba11-f81d6087fb30 |  | note | CATEGORY: IP
label | b16cc0b3-059f-4568-b2a7-de86a8251458 |  | note | ---------------------------------
label | fb696eb7-56d1-457c-97b7-4c195eada56c |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9458cc56-a33d-46a4-9fa4-3276686b51ab |  | note | ---------------------------------
label | c2dd48e4-a1f8-4390-9688-068d9f8426ea |  | note | VERIFYING DOCUMENTS: This ITP
text | 8e4386a1-2384-4193-a7b8-7450dc8dfde3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Fence Height and Track Clearance
label | 5da7993c-3386-4824-8819-cdd9098e9508 |  | note | REFERENCE: IFC Drawings
label | 9fecae96-738b-4396-bf45-a71fbff0b955 |  | note | ---------------------------------
label | 69fcff01-1a08-4989-b586-f17a45dc29f5 |  | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | 4a879eca-93bc-4f49-8470-51d1a10ee583 |  | note | ---------------------------------
label | ed58161d-a3f7-41e7-9a1b-6387b46d061a |  | note | METHOD: Measure
label | bf6a867c-53b6-4a61-bb6a-8eec7065c0d1 |  | note | ---------------------------------
label | a9a11f5f-4379-4191-9525-7c353eb54845 |  | note | FREQUENCY: Each lot
label | 59697944-919b-4d32-92f0-13303eb0af05 |  | note | ---------------------------------
label | 9d75dcd4-2d59-474e-80a1-4e26dfca9fc0 |  | note | CATEGORY: IP
label | c8e6ff8a-19ad-4e0c-be82-1f6121e412c2 |  | note | ---------------------------------
label | 5904c40a-fad4-446c-94ca-99949a3f40f2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cc4c17b2-fa34-4898-b33d-f53199ea4c97 |  | note | ---------------------------------
label | 135ebdc6-045a-4eac-8592-56f12bcdae9b |  | note | VERIFYING DOCUMENTS: This ITP
text | 611b7e70-fa04-44ad-8538-b263a11004a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | c824f2bf-ffbd-4f26-ac1a-699720b5af2d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | df897994-0bbb-453c-8d8d-a91d655babf6 |  | textbox | Name:
text | ad6a0481-e594-437d-9251-74143e06cb84 |  | textbox | Position:
text | 18c4c59b-7a3a-46b2-a539-6a379a289cd9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Soil Nails Rev 0 | itp |  |  |  | Yes | ITP-STR-Soil Nails Rev 0 | 46f6246f-661d-4d77-a716-97b0d20bebbe
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 7ba5a2c6-61f9-4c2b-aaa6-4e9f1293ab63 |  | note | ITP Description: Soil Nails
label | 61363fde-9ddd-4b23-8742-19f39ab2329c |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | b2567d93-2c0d-43db-96dd-c9f4e08c64d1 |  | note | Revision Number: 0
label | aa289710-31b5-4163-8ab2-f594193fa4d8 |  | note | Revision Date: 3/08/2021
label | cddc1cf9-1f59-4da9-959b-cc250bce0d9b |  | note | ITP created by: Mike Freeman
label | 26b30227-2ec1-476a-bb94-6908b8fb8616 |  | note | ITP approved for use by: Mike Freeman
label | 55acc5a0-993a-42c7-89f0-d2b88fe56f63 |  | note | 1.1 VicRoads Section 610 June 2019
label | 53909fa4-d903-4e4c-a022-c3e4107f1d5c |  | note | 1.2 VicRoads Section 611 November 2018
label | b058b260-77f3-4ab1-8fde-1cb69f1281e2 |  | note | 1.3 VicRoads Section 683 April 2019
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Design
label | 6b6f79d3-1120-49fc-91a8-6a2e862c5d3e |  | note | REFERENCE: 683.04
label | 4568e9f5-ca1c-44db-8ba1-30af4c6ea5ed |  | note | 683.04 (d) (i - xi)
label | 0a849e20-fa59-4543-9710-6a4e151baa48 |  | note | ACCEPTANCE CRITERIA: The Contractor shall submit construction drawings for review by the Superintendent prior to soil nail installation.
label | 66dac0af-a5c6-4bc6-a3d2-53a5672b3fe1 |  | note | See: MRP-DPK-072-00-CSW-0021 (Robinsons Road)
label | 5f03b553-71a5-41ea-a350-e227d9048e54 |  | note | METHOD: Document Review
label | 3302cebf-6801-43a1-b123-e22fd3f94a8f |  | note | FREQUENCY: Once, 4 weeks prior to installation of soil nails
label | 690ed590-2386-4d98-abe9-bce05978f6a5 |  | note | CATEGORY: HP
label | d940b07c-0987-4b9a-9e53-1a0e6fd0cb62 |  | note | RESPONSIBILITY: Nominated Authority
label | 93585ca8-8285-4b8c-b80c-d14e62cc7eab |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release (note this hold point is already released)
text | 15cbe2ca-2fbc-49cd-b981-19948f85f6f7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Nail Certification - Steel
label | 6d804211-08be-43ca-be20-bd8258ffe5ea |  | note | REFERENCE: 683.06 (a)
label | 7b8b0b39-9ead-4f1a-8fbc-4545a4a65c74 |  | note | 683.07 (b)
label | 23ec63d5-ed9d-4480-bc09-9ad94dd5108b |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for Grade 500N materials including couplers (where applicable).
text | cf60f4ec-bb89-4d39-bfb9-72e97b2ae9f2 |  | textbox | Enter: Teambinder Material Approval number
label | 62d5bee4-c50e-45c1-978f-2c5aa1239119 |  | note | METHOD: Document Review
label | 3c3aa61a-6150-42a6-8c43-36f56c8eba40 |  | note | FREQUENCY: Where applicable, once for each supplier, prior to installation of soil nails
label | 071a91a0-2ab4-458e-8a47-387d0edb940d |  | note | CATEGORY: WP
label | d64fa81f-450c-472a-b625-e3d3b64962a9 |  | note | RESPONSIBILITY: Nominated Authority
label | 24da8d78-ef0b-48b2-9dce-192565333866 |  | note | VERIFYING DOCUMENTS: This ITP
text | 11ef2e21-f78f-4ace-b910-69f6b0242f7c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Nail Certification - Carbon or Fibre Reinforced Polymer (FRP)
label | 4c7b65f8-5bf1-42c2-bb0a-fd92fec23eb8 |  | note | REFERENCE: 683.06 (b)
label | 75e3c0a0-ade3-4e40-b1df-d04c3993c815 |  | note | ACCEPTANCE CRITERIA: Carbon or FRP nails shall not be installed until the material certificates for all batches of nails have been reviewed and approval granted by the Superintendent.
text | f10cf3ab-4761-4a10-bc31-5c5b7fc1984c |  | textbox | Enter: Teambinder Material Approval number
text | 983aede7-41ec-42ae-9cdc-bbf52c7187a2 |  | textbox | Enter: Teambinder Approval Number
label | e5893d82-2b34-4dbe-a9a1-be31b3429801 |  | note | METHOD: Document Review
label | 160e6222-9485-4622-9424-c17aa6864b1e |  | note | FREQUENCY: Where applicable, once for each supplier, prior to installation of soil nails
label | f366041d-4a7c-4a46-b192-3fe293ca1576 |  | note | CATEGORY: HP
label | ea93c628-236e-4c7f-9c10-0246697bb2ff |  | note | RESPONSIBILITY: Nominated Authority
label | 4a005be7-f2b9-4b9b-b7e5-72645ec92909 |  | note | VERIFYING DOCUMENTS: This ITP
text | e7ba6f94-4bd1-44c0-be9e-3a65dba72ef1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Corrosion Protection (for All Steel Componentry)
label | 84319f10-0883-4ce1-b043-e7c16a5c3454 |  | note | REFERENCE: 683.07 (b)
label | dbd483ee-aef2-4c8a-9332-9e50ef8562b0 |  | note | ACCEPTANCE CRITERIA: Coatings for corrosion protection on all steel materials shall be either:
label | a72c2723-c0c6-4519-ad1e-7fb88ebea7d2 |  | note | i. Galvanised to thickness as per AS/NZS 4680
label | 3f95008e-66da-4526-8bda-5392fca30831 |  | note | ii. Thermo-diffusion coated to Coating Class 80 or ≥80µm
label | 730bae4c-fe03-4a7d-9b2e-1422d5e57a35 |  | note | iii. ≥80% zinc-rich product with ≥100µm DFT
label | 5173e3b8-3f35-46dd-acdc-7226d72ef1f3 |  | note | Attach: Coating Certificate of Compliance
label | 31bc699b-ba23-420c-afcc-ee37f88cc551 |  | note | Or alternatively, include in the nail certification in the Teambinder Material Approval.
text | b2c9884d-ae21-47af-a1f6-e80e312bba0b |  | textbox | Enter: Teambinder Material Approval Number
label | 6548775e-e4f6-470c-869e-bf51b52e15fa |  | note | METHOD: Document Review
label | 87f8cca9-ba2c-4d23-bb8e-c3b9c8b690ba |  | note | FREQUENCY: Once for each batch of materials, prior to installation of soil nails
label | 4d2fbf17-a75b-4f8d-ada9-77e5184e87a4 |  | note | CATEGORY: WP
label | 8b93d1b9-4ee5-474c-a467-b74b27248536 |  | note | RESPONSIBILITY: Nominated Authority
label | d99ddcfa-e98b-4b4f-b2e1-db8ab9d294c3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5b207632-9dbb-4e02-bc5e-9d627de22965 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Grout Mix Design
label | 700aa31a-1d26-4a8c-89e0-8dabbbc9bdc9 |  | note | REFERENCE: 683.11 (a) (i - iii)
label | 4e44d585-12b8-4556-9c2d-8c725d8ec46e |  | note | IFC Drawings
label | 3011a686-8c05-41a9-a727-b4a2e2df536e |  | note | ACCEPTANCE CRITERIA: The proposed low shrinkage grout mix design with supporting test results to be submitted for review to the Nominated Authority.
label | 8aad0fc3-8055-49eb-837b-06222f6a3b0e |  | note | The following test results and information shall be provided:
label | d6c21b3c-0bc2-48c0-83e6-786ccfb2261a |  | note | i. Water cement ratio between 0.38 - 0.45
label | 1c32a0dc-9b25-4806-9430-cd8a1fc52887 |  | note | ii. The chemical admixture
label | 98ea669b-a2fa-4a0c-9cea-aa340f157a37 |  | note | iii. 7 day compressive strength test results ≥32MPa
label | f4feeb72-8694-4185-8912-c475b22b5c83 |  | note | iv. 28 day compressive strength results ≥40MPa (Robinson's Road)
label | a47de127-b0b2-4243-accf-60ed55481d36 |  | note | v. Flow cone test result between 10-30 seconds
label | 5cc26fe1-51b2-4f0e-95c2-af88f7c06fab |  | note | vi. Bleed test result ≤2% 3 hours after mixing, ≤4% at any time and separated water absorbed within 24 hours
label | 98d459d5-4a9b-4c1e-9f88-84796618517d |  | note | vii. Chloride-ion content ≤0.07%
label | 03405646-75ea-452a-83f9-7a5986f9b4ae |  | note | viii. Sulphate content ≤5%
label | 2704501a-13ae-48c2-8aa9-fb17bc4d7369 |  | note | The grout shall be made strictly in accordance with the approved grout mix design and in the event of changes, re-submitted for review and approval to the Nominated Authority.
text | 1b5e0297-632f-4150-beb7-d94624f1b606 |  | textbox | Enter: Teambinder Approval number
label | 592f92bc-517c-45a9-8ac9-da184ae6679a |  | note | METHOD: Document Review
label | 2ea15100-b8eb-4e01-bfee-7ab2b6f3746d |  | note | FREQUENCY: 2 weeks prior to installation of design verification testing
label | dc37a20d-7f52-4b8c-b9d2-2aaf62da95ab |  | note | CATEGORY: WP
label | faa9e7fe-1ab4-4f73-a73b-94cb3a9551c4 |  | note | RESPONSIBILITY: Nominated Authority
label | 222dfad9-5289-46a9-ab59-c8a6f360e54d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 766ce101-f218-44cf-a69b-a53ffeeb1aeb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Soil Nail Installation, Grouting & Testing Work Procedure
label | cd6d0aa0-0d4b-4c29-b922-db44f444fd67 |  | note | REFERENCE: 683.12 (b)
label | cfda31f5-ad51-465b-9cd5-ad371b4c86c0 |  | note | 683.11 (b)
label | c46e999b-da5a-4aa5-9e4b-a1e784a74bf1 |  | note | ACCEPTANCE CRITERIA: Soil nail installation WP, fully detailing the proposed drilling, grouting & testing equipment, methodologies and reporting, to be submitted for review to the Nominated Authority.
text | 2cf45679-0e57-49ba-94d7-88a1eb574b68 |  | textbox | Enter: Teambinder Approval number
label | 8b063a8b-250f-4c4f-a6f8-7f2141463050 |  | note | METHOD: Document Review
label | 35d57fc7-7a10-4d20-88e9-cefa96cac453 |  | note | FREQUENCY: 2 weeks prior to installation of design verification testing
label | 8e481875-2dae-4a2b-bb2a-7eb4c985fd8a |  | note | CATEGORY: HP
label | acd83263-f93b-42ca-8004-b40331102c97 |  | note | RESPONSIBILITY: Nominated Authority
label | accee83d-66af-46b2-b382-8611944d1d1f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 426a31ff-59c1-4e48-aa7f-76b281fba054 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Soil Nail Testing - Type I / Design Verification
label | 407b5717-9441-41d7-b720-3d8fc589753d |  | note | REFERENCE: IFC Drawings
label | a98f81a0-c835-4850-be9c-7a75b505ca28 |  | note | 683.12 (a, c - d)
label | 80c71988-b44e-4e29-9ca2-9a5388653ee6 |  | note | 683.13 (a - b)
label | 879020cc-68e1-4913-924d-be4e0e99ad90 |  | note | Table 683.161
label | 26d28047-f2b0-46fe-950e-732475ca642f |  | note | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
label | 22897162-7fd7-4a89-99ef-a791aba1c283 |  | note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
label | f9513bf0-0bd5-4169-a2c9-c1a8bd1bcacd |  | note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
text | 97af9efa-fa73-46de-8f03-8356f7f93865 |  | textbox | Enter: Teambinder Approval number
label | 6f9e6ff1-14f5-4a34-824d-4a07dd170dc1 |  | note | METHOD: Document Review
label | c813c47b-1919-4b4b-8086-e459762ce3ed |  | note | FREQUENCY: Once, 3 no. tests per soil/rock type
label | 3861033a-0962-47d8-ba00-02556d9f87a2 |  | note | CATEGORY: WP
label | cc996f1a-9b67-4c45-ac6f-0eaa272c4481 |  | note | RESPONSIBILITY: Nominated Authority
label | a8681394-d7d7-4dbc-b19b-c27596945b2f |  | note | VERIFYING DOCUMENTS: This ITP
text | d31e6fa6-f4ce-4494-a017-7b65caf6c4f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Testing - Type I / Design Verification Test Failure
label | c5ab4764-d7fd-465d-b45d-9b3dcd1252e1 |  | note | REFERENCE: IFC Drawings
label | 5fd23800-e38b-4f80-b0ef-5f9244618ea6 |  | note | 683.13 (b)
label | 62b94d9a-6154-4131-97a7-e788bdf84fc3 |  | note | ACCEPTANCE CRITERIA: Where applicable, if any Type I / Designer Verification Test results fail, Type II / Sacrificial Testing & Exhumation Testing shall not proceed.
label | 262e902b-8894-4833-a5e8-9c70a2fa5ca1 |  | note | Where this occurs, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
text | 69341c18-a203-44c1-a398-01a7f02f967b |  | textbox | Enter: Teambinder Approval number
label | f126ba4b-bf42-4b38-b324-e4a78946ae2c |  | note | METHOD: Document Review
label | e315267b-c3d9-4bb2-9cb0-463a402b3dcd |  | note | FREQUENCY: Where applicable, per failed test result per soil/rock type
label | 577193e0-8d6b-4c4e-b82f-c8a5c93e5e00 |  | note | CATEGORY: HP
label | f59e032f-1bc3-4bf7-8a5e-ea73f75db51a |  | note | RESPONSIBILITY: Nominated Authority
label | 58f5c1e5-c229-4d0d-8a87-88cfcabec62d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9c275705-fd6f-410f-a15a-390647c5e8ad |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 Testing - Type II / Sacrificial Testing & Exhumation
label | 96214e76-b92c-493c-87c6-54cd1b6e4b3c |  | note | REFERENCE: IFC Drawings
label | af2b5567-bcab-4a70-99bb-c2364a82bb7d |  | note | 683.12 (a, c - d)
label | a594ff32-8a20-4d0b-b0a3-b2b1a9969844 |  | note | 683.14 (a - c)
label | ac74aa61-5f83-4453-8194-c1d3faafd614 |  | note | Table 683.161
label | 71f5b76f-2d9f-4348-83f6-195b1113e7a1 |  | note | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
label | 9c184006-a145-4e5b-b133-aceac58c021d |  | note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
label | 9d60501d-9d4c-4963-b1a6-a706e9701534 |  | note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
label | 17abbc2a-4201-4d36-b35f-ec2d19c4950f |  | note | Exhumation of the sacrificial nails shall be conducted in a manner to avoid damaging the grout column and cut into 500mm lengths with ends photographed to prove grout cover of the nail.
label | 2574a312-2067-4544-8cb3-1bc1c093b86d |  | note | Note: Dispensation from Type II testing in rock can be requested if:
label | 329995d0-e216-417e-83da-bbd601ecb82c |  | note | i. All Type I test results pass in that material
label | b32bced3-1efe-4827-ac43-fa756944e8b5 |  | note | ii. The material is not weathered more than slightly weathered and/or less hard than a Rock Quality Designator (RQD) of 50
label | 0fba4053-5492-479a-b413-97b3a8345088 |  | note | iii. Encapsulation sheaths are used for steel nails
text | 75a8a59f-9f05-46cb-88e1-3cfd67266bc7 |  | textbox | Enter: Teambinder Approval number
label | 203200df-9eca-41b5-a870-84df77c5850e |  | note | METHOD: Document Review
label | 68be3072-3d1e-4c14-b88c-6b2d0a205f6a |  | note | FREQUENCY: Once, 3 no. tests per soil/rock type
label | 03f5642c-554c-4fbb-bb11-3c911072530b |  | note | CATEGORY: WP
label | ced06d7f-a818-465c-8afd-7ef0b1c982e5 |  | note | RESPONSIBILITY: Nominated Authority
label | 4d0ca67b-995d-4470-96cf-c5f97e347a49 |  | note | VERIFYING DOCUMENTS: This ITP
text | ac90c670-c81d-4a35-a2c6-48870663a68c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 Acceptance of Test Results
label | b37f1cd6-16e3-41ba-97ab-8da035ba39f7 |  | note | REFERENCE: 683.1
label | 6e6d28bf-be7a-45aa-9c27-1206edc83f03 |  | note | 683.15
label | 1157a3b5-c0e5-4f88-b3b9-53ddae4a892f |  | note | ACCEPTANCE CRITERIA: Installation of production nails shall not commence until the Type I & Type II test results have passed the design requirements (inclusive of any re-design assumptions).
text | 7f1677b3-654c-4d36-b8b8-14c303152d2a |  | textbox | Enter: Teambinder Approval number
label | b09f0d06-e383-40e1-9795-a02106bbf097 |  | note | METHOD: Document Review
label | 21b952aa-39da-41e5-b0b2-56a9da214c71 |  | note | FREQUENCY: Once, 7 days prior to commencing production nails
label | 753e8bc5-b4e9-4849-af3c-a3bcf07bd131 |  | note | CATEGORY: HP
label | f39e52d1-27a3-4f40-bf4d-7258cc9d6fb4 |  | note | RESPONSIBILITY: Nominated Authority
label | 5d2aa23a-f0e7-40ee-9387-2e6a9d9b52ce |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 78a46bb9-0a8d-435e-a9a1-e9d3658be265 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 IFC Drawings
label | b3e96034-2204-4a29-ace8-1872ee7aff6b |  | note | REFERENCE: MRPA Quality Management Plan
label | dfc70d02-faa4-4177-bf17-5a6fe7c84ac0 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 054d9087-27f7-47bb-aea9-d00a6b4430bd |  | note | METHOD: Document Review
label | 260b9dee-c186-4ea7-a43a-0a32aa3e8aa2 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | df2c8d42-ad4a-4387-a34d-78aa475f55c0 |  | note | CATEGORY: HP*
label | 88a0ff94-e960-4b9c-abdb-b7f4766cd65c |  | note | RESPONSIBILITY: All
label | 17884942-0c4a-4784-af0f-4159274bde10 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6e677b7c-e34c-4b6e-a25b-0a6e60c1cad9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Excavation - Change of Soil/Rock Profile from Design
label | 24582732-8b6e-45c6-b887-55fd4ed6691c |  | note | REFERENCE: IFC Drawings
label | 7560ea12-db2c-482f-8180-ecdf085568e0 |  | note | 683.05
label | 761ea395-b174-480c-9f06-12463f6df9ff |  | note | ACCEPTANCE CRITERIA: Excavate in layers shown on the drawings.
label | 6eeff758-4ea0-4fb1-b27b-e777770a97f0 |  | note | Where applicable, if the Geotechnical Engineer's representative determines from an on-site inspection that the soil/rock profile does not match the design assumptions, no nails shall be installed until the design is verified or amended to the satisfaction of the Superintendent.
text | 70757a0f-d07b-44e7-8794-8ed5bb92b729 |  | textbox | Enter: Teambinder Approval Number
label | 700b271b-b904-4726-8b3a-91b459da84ab |  | note | METHOD: Visual , Document Review
label | dc95ba72-f280-45a5-89ff-bfa7cdf2068a |  | note | FREQUENCY: Where applicable
label | 02293e2c-e0f0-4f40-9526-2927c1a9aa87 |  | note | CATEGORY: HP
label | 506411ef-b9e1-43fe-8334-7b73ae289c20 |  | note | RESPONSIBILITY: Nominated Authority
label | af2aab75-ed47-4b3e-90d8-94e7d17a56ef |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 54b5d818-060a-4e61-92bc-376b69a6ee81 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Excavation Monitoring - Short Term
label | ec389ab5-bc83-4677-8ccc-e9c2ca545e73 |  | note | REFERENCE: IFC Drawings
label | 41e2b049-fffc-4985-b990-606b76286f76 |  | note | ACCEPTANCE CRITERIA: Survey monitoring for deflection shall be conducted at the top of the wall and mid-height of the exposed face at every 3rd column of nails in abutments or 15m chainage intervals.
label | 05518b16-d819-4dba-ab42-fde4a9e30088 |  | note | Movement trigger levels from original are:
label | 8b5870ae-afaa-4a4d-8484-2dbdc433f201 |  | note | i. 10mm = Green - continue excavation
label | 15a5857f-9aa5-4b6e-a409-f604fb9490f3 |  | note | ii. 15mm = Amber - increase monitoring frequency
label | 17aa7093-d7ba-46f5-8982-c6d6fa583193 |  | note | iii. 20mm = Red - implement measures to cease movement and stop work
label | 8362707e-2cd9-4125-a417-9cab75661c74 |  | note | Record: Wall Monitoring Data
label | 0078cf43-e38c-47b3-8ad3-9f0ee945d00e |  | note | METHOD: Measure, Document Review
label | f8621c94-0d8a-4091-9088-c0fd33e7f674 |  | note | FREQUENCY: Top of wall = Each day of excavating then once a week for 4 weeks. Mid-height of exposed face = each day of excavating, then 1 week after excavating.
label | a8225d21-d18e-427a-94ff-87fe9c62a73d |  | note | CATEGORY: IP
label | 4bd40877-a436-4f74-a8eb-019ce03972f3 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | f1893dd6-dfa9-4da8-994c-28f31b368983 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6a113138-83af-46bd-a473-42b83cfd103c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Drilling
label | ceb91404-11de-4fb5-99e5-35c3f517c740 |  | note | REFERENCE: IFC Drawings
label | 81a4c01a-cad3-432b-a4c5-564c5b1db762 |  | note | Soil Nail Work Procedure
label | 705c2844-ef5d-4b51-a1fc-dc18a0e405cd |  | note | 683.08
label | c99ed2b0-77cf-4fa4-abad-944e4fb6cbb4 |  | note | 683.10 (b)
label | 4b5ec804-f945-43bd-adb4-9b7130f9fdfa |  | note | ACCEPTANCE CRITERIA: Drill holes shall be the depths, diameters and angles shown on the IFC drawings using the equipment stated in the Work Procedure.
label | ddbcf6bf-147a-4d26-b593-c4703d516c05 |  | note | Where casings are used or sheathing is omitted, the hole diameter shall ensure that the cover to the nail is 40mm min.
label | c480e0a6-9487-4366-91d7-96190962004b |  | note | Drilling records shall be kept including any observations or difficulties encountered.
label | fab6c375-6018-4c4c-a12e-6f22f75925a9 |  | note | Only air flushing is permitted, no drilling fluid or water shall be used.
label | 29f91cec-76fd-40aa-bd9e-005f8e7ef8c3 |  | note | Placement tolerances to comply with the following:
label | 2fd26778-96d3-4dc0-b523-36f16ea940cb |  | note | i. Horizontally = ±50mm
label | e2c343c4-2660-49b3-b28f-ebbb74783290 |  | note | ii. Vertically = ±50mm
label | 159b44a5-ba52-41ac-8bcd-58ef4afed7f2 |  | note | iii. Alignment = 1:20
label | 3846e6c8-a2e2-41fb-bad2-97da9ce1641b |  | note | iv. Straightness = 20mm in 3m
label | 3401f364-a676-44ca-8d62-2ca4837f603d |  | note | v. Inclination = +0° to -3°
label | 854ba7a3-5540-4e7c-bdb3-f12e196fc005 |  | note | Attach: Drilling Records
label | 8ea1ea97-f1a4-4e3b-b761-a49ea3cdd574 |  | note | METHOD: Measure , Visual
label | ef464b62-2fae-4dbe-bc55-61cdb85670c7 |  | note | FREQUENCY: Each drill hole
label | 507be866-1bf7-4333-9c6d-4502acd55f8b |  | note | CATEGORY: IP
label | 9e856827-2e44-4a76-8e0d-3720195e3204 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE , Surveyor
label | 29d91829-0c3b-4cb2-aa0f-ae0e8493531a |  | note | VERIFYING DOCUMENTS: This ITP
text | 4144ceea-95ed-411f-b1a1-076cac835f27 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Hole Inspection
label | 7133097e-5b12-4fc0-8675-f475e97a8c35 |  | note | REFERENCE: 683.10 (c)
label | b0d86bde-fcf4-446b-929e-51ac7e858dd3 |  | note | ACCEPTANCE CRITERIA: All drill holes shall be inspected following air flushing and prior to insertion of the nails.
label | b9fb9e50-c11c-4198-8538-b3e738a0ee95 |  | note | Drill records shall be made available for review.
label | f1f820ce-a57d-44b7-b0cf-03cb847aaf10 |  | note | METHOD: Measure , Visual , Document Review
label | 62256681-d889-43e8-bb82-b4bbf31b4149 |  | note | FREQUENCY: Each drill hole
label | df850925-26b0-4c59-b2d9-8c104d26d4cd |  | note | CATEGORY: HP
label | 413a0389-7aea-4af4-b9cf-c309e1433e58 |  | note | RESPONSIBILITY: Nominated Authority
label | 238a8a89-efa8-4b9e-95ff-a81b9425f359 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 0ec43cd2-8b11-4f3e-9c2b-9ff97fba8b9d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 Nail System Installation
label | 369aee3d-6422-4c6e-88be-cff4cc5dc7e4 |  | note | REFERENCE: IFC Drawings
label | c5a28e25-d096-47af-a1cd-bcb780efed81 |  | note | 683.07 (c - f)
label | c498b08f-0ffe-4515-8fb3-8ccff351bfbe |  | note | 683.09
label | 1910be66-980d-4a56-886d-f5cefcd86556 |  | note | 683.10 (c)
label | b2060dca-7e33-45f2-8096-03191b4a767f |  | note | ACCEPTANCE CRITERIA: Each nail shall be made from the correct material, be the diameter and length as shown on the IFC drawings and be free from defects or damage.
label | c61538b4-39e0-4653-a5df-9a3bc94b2cad |  | note | Centralisers shall be spaced at 1.0m max., ensuring that 40mm min. cover is maintained all around.
label | 6b201f35-0363-49dd-8d1e-f21bb8409226 |  | note | Steel nails shall be encapsulated by a corrugated sheath unless previously approved during the Type I & II testing.
label | 03cf5aac-8706-4600-8728-71184476ffdb |  | note | Steel nails shall be isolated 300mm min. where they are to be in contact with the shotcrete facing using tapes or other approved methods.
label | 2bc7a0df-a0a6-4e40-8f3f-e3284650e9fb |  | note | Grout tube shall be positioned at the base of the hole to displace any moisture present in the hole and to prevent entrapping air.
label | 9c08afe0-1321-429c-9274-49bb0df6012c |  | note | The resulting set up shall achieve the minimum bonding length, projection and be able to resist the forces expected during the grouting operations.
label | 28ed1901-f92a-4380-a8c1-8cbe12f4984b |  | note | METHOD: Measure , Visual
label | 193b9ff5-44e5-4a53-8937-b34774089305 |  | note | FREQUENCY: Each drill hole
label | 0b230ebb-02ef-4207-ada4-fc93bba3bad6 |  | note | CATEGORY: IP
label | 94089e11-a633-4f19-87da-3c539159ef9b |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE , Surveyor
label | af760a27-a955-43e0-8c09-267c8b8663b3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 21a23a7a-dff7-4a57-9f56-d5391e933ba0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Grout Mixing
label | 48f37d70-5030-4b28-bbaa-5249aea806b9 |  | note | REFERENCE: Soil Nail Installation Work Procedure
label | cae8201a-0795-4fff-aeaf-596d88b84adf |  | note | 683.11 (b - c)
label | 795b2c7b-8b26-4368-b5cb-891a51529bb6 |  | note | ACCEPTANCE CRITERIA: Grouting shall not take place when the air temperature is below 5°C and above 35°C.
label | 23dcd1c9-8d57-42c8-8065-c4617ea39470 |  | note | Mixing shall continue for at least 2 minutes and until a uniform consistency is observed using the same equipment nominated in the Soil Nail Installation Work Procedure.
label | a2e0442d-4a4d-448f-b6ba-c4866fe94767 |  | note | Grout shall be discharged/pumped within 90 minutes from the addition of cement.
label | 4ba9443d-ca3d-47c6-897d-d0fb69b4cc1f |  | note | Record: Required information on the Grout Pour Record
label | 589605e9-de16-40ee-bce1-eecca7d0433a |  | note | METHOD: Visual , Measure
label | b8682faf-3cde-47ae-a4fc-ba4022a31375 |  | note | FREQUENCY: Each batch
label | 28bab75b-40ae-484a-ad6b-c1942faf81a4 |  | note | CATEGORY: IP
label | 39aa7395-00a9-4540-8d5a-98dca99be9d5 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 5838cf4f-c22f-4b98-8b78-3df1f0aef31c |  | note | VERIFYING DOCUMENTS: This ITP
text | 941936c7-896a-4add-beaa-64d189f48778 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Grout Testing
label | 74adca9b-1ce2-4d83-bc5e-6ff40b379344 |  | note | REFERENCE: IFC Drawings
label | 8e46791c-411b-41dc-a7f1-f4e5336de2ae |  | note | Soil Nail Installation Work Procedure
label | 363aebc8-a0f9-48f4-adef-a0433d8a4461 |  | note | 683.11 (a) (iii)
label | b3a1074c-417d-4c83-a6c7-751715f066e1 |  | note | ACCEPTANCE CRITERIA: Each test shall consist of:
label | e8ad3869-126d-4102-8251-3ed073845c41 |  | note | i. 3 no. compressive strength cubes = 2 no. 7 day strength, 1 no. 28 day strength.
label | 4a985a1f-d56a-48b1-acf5-27b570793065 |  | note | ii. 1 no. flow cone test = result between 10-30 seconds
label | 46c70eda-fd00-426a-8722-eb503c56be4c |  | note | vi. 1 no. bleed test = result ≤2% 3 hours after and shall not exceed 4% at any time with all separated water gone after 24 hours
label | 99ff710f-f262-4f31-b86f-5114d29ab576 |  | note | Record: Required information on the Grout Pour Record.
label | 30e647bd-6a04-45fe-9929-4cec3997e08b |  | note | METHOD: Visual , Measure
label | 4dffd785-aec8-4d18-bfa5-2e19a0025fdc |  | note | FREQUENCY: Each 5m³ or part thereof batched per lot
label | 911a2a62-d21c-4488-99dd-f80cb184c7b5 |  | note | CATEGORY: IP
label | 8179cfef-0ca2-4e4c-834d-b08846af760b |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 8065579b-75e4-401f-82ca-e7ee41bdc6a0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1608f493-ef6d-4ff0-be2c-ca4901720a71 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Grout Pumping
label | b62a0c8d-c813-4af5-8fe3-e7886ef03f3c |  | note | REFERENCE: Soil Nail Installation Work Procedure
label | f69d419b-1ff4-481d-a88e-96c136e46cea |  | note | 683.08
label | 2922860e-38d5-44ea-aaf8-9e22e4c574c8 |  | note | 683.11 (b - c)
label | a5ece34a-48f5-451f-9409-eb587db54cd4 |  | note | ACCEPTANCE CRITERIA: Grout shall be pumped in a continuous operation and monitored with flow and pressure gauges so that the flow rate is between 0.3m to 0.6m per second. Where temporary casings are used, these shall be extracted progressively once 0.5m of the hole has been filled.
label | b0c5af3c-7178-41e4-93ad-7fc511fe7fce |  | note | The volume of the grout used per hole is to be recorded and checked against the theoretical volume.
label | 665e9b15-1643-417a-b4b5-1356ce2bdd65 |  | note | If grout seepage has occurred, the grout shall be topped up to the required level.
label | 96da5b50-7126-4428-a06a-15482d023336 |  | note | Where applicable, if the actual volume is 10 times higher than the theoretical volume, pumping operations shall cease at the completion of that hole and be reported to the Superintendent - no further grout shall be pumped until the conditions are reviewed and approval to proceed has been provided.
label | 87c19ff9-1063-4d01-b07b-b21609de69c0 |  | note | Record: Required information on the Grout Pour Record
label | 3c7ea4ff-ebde-4f4d-abfd-02f490102ccb |  | note | METHOD: Visual , Measure
label | 22bf0d81-4859-448c-9a80-7c95fd934c44 |  | note | FREQUENCY: Each batch
label | 878d232b-8789-4f99-82e3-a6316162caac |  | note | CATEGORY: IP
label | daa689e5-c7ff-4f4a-a604-22cf6b1e5e0d |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | c247cbb4-555c-45d6-b22f-e3a559bdf5cf |  | note | VERIFYING DOCUMENTS: This ITP
text | acbe63e9-341e-4e47-bb4a-5ad13470e5fe |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Grout Compressive Strength Results
label | d8910491-95d4-4b42-8b84-273c5bdeaeaa |  | note | REFERENCE: IFC Drawings
label | 72d09858-9883-48c0-896a-a2f8bcefb8fa |  | note | Soil Nail Installation Work Procedure
label | e06d3bbb-4661-4aae-ab87-4c80ddae208d |  | note | 683.11 (a) (iii)
label | b113a037-2395-4afb-be1a-0a507971dce8 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strengths to achieve 32MPa min.
label | 00c7dc4e-dcdd-446a-a76a-ca50418d4407 |  | note | 28 day compressive strengths to achieve 40MPa min. (Robinsons Road)
label | 4b91c130-1d5d-45e0-b080-f6c7066e3383 |  | note | Attach: Compressive Strength Test Results
label | c36ebd60-de91-455b-a3a2-ca8342bc74c3 |  | note | METHOD: Document Review
label | b367ac81-c612-4054-aa47-c1a2d3f5ce75 |  | note | FREQUENCY: Each cube
label | ef32862e-f863-4148-beeb-19744e4a4156 |  | note | CATEGORY: IP
label | 85d247f4-4b67-493f-a5c2-941f32080fa1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0fa7d4ee-aeb3-4333-b99c-b061dc915675 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5af25fe6-8789-4a29-9a6a-0d530d61769d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 As-built Survey
label | 786f58ef-fbb4-4860-ba0b-5c2e19353be4 |  | note | REFERENCE: IFC Drawings
label | f10b0931-af57-47d9-9ac0-47520b15214d |  | note | 683.10 (b)
label | 9250bbc0-688e-42d4-9f9c-2dc13e077522 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate nails comply with the following placement tolerances:
label | 220de79b-d254-4ed3-9a68-cbd0af030334 |  | note | i. Horizontally = ±50mm
label | e281894a-bc09-4212-9fce-c6625bce56a8 |  | note | ii. Vertically = ±50mm
label | f2488912-d40b-4401-815f-241207dcc04d |  | note | Attach: Survey As-builts / Survey Report
label | 7414875e-0b40-4389-bf99-c9388269c4e7 |  | note | METHOD: Measure , Document Review
label | 49fa7a5d-1598-40d8-97a5-6168bc98fb0f |  | note | FREQUENCY: Each nail
label | b533a282-701d-48ef-b642-4c4d6b54ed0d |  | note | CATEGORY: IP
label | f9187bc7-ed90-44f6-9fd1-cfdf3328f787 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 7306ffcc-0d9f-4dbf-b78b-c3b0705eb8aa |  | note | VERIFYING DOCUMENTS: This ITP
text | f959416e-cbb3-436e-9b5a-a967ea2f36fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Testing - Type III / Production Testing
label | 3bcc3485-f0b4-47e5-befb-0ae079916e3f |  | note | REFERENCE: IFC Drawings
label | 27b73f10-be7d-4dd2-9646-79630aee215e |  | note | 683.12 (a, c - d)
label | aa71490c-3231-4f7c-8402-49eea4b898a2 |  | note | 683.15 (a - c)
label | 9db53ae3-ba55-492a-8a94-c127a6f02d12 |  | note | Table 683.162
label | 4dd7e902-ee57-438f-a775-7a0d64569b14 |  | note | Table 683.163
label | 41ce0377-2cc9-4101-8b19-4d515c6efcfc |  | note | ACCEPTANCE CRITERIA: 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
label | 15096a81-f61d-4b1b-85e3-f399d8963507 |  | note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.162.
label | 21d45392-4b1d-45c6-9e22-a0deeeef34a3 |  | note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
text | 088f9095-923c-4f19-81c4-c27f92ddbd14 |  | textbox | Enter: Teambinder Approval number
label | b40e8588-cc78-4133-970d-b6ff8838779a |  | note | METHOD: Document Review
label | a3292fd8-d97f-4571-8ebc-370b4490d81c |  | note | FREQUENCY: The greatest value from, 5% of all nails, 2 no. soil nails, 2 no. soil nails per type of soil, 2 no. nails per installation method
label | 41912cf7-7e9c-457b-9a7c-73523bcce71a |  | note | CATEGORY: WP
label | a6c9b548-6278-4dc5-a0c4-f3e5853e6da3 |  | note | RESPONSIBILITY: Nominated Authority
label | 5f71665b-65f1-4ecd-8f28-a0826ca571a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | ae2e39f2-c35f-4989-88f9-539d995eb804 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Testing - Type III / Production Test Failure
label | ffa23874-b5f6-4287-9bb2-3a0d2b24c9c9 |  | note | REFERENCE: IFC Drawings
label | b4c6033d-0593-4ca4-83b3-4d2a61c8a9e6 |  | note | 683.15 (c)
label | d5e70752-c99d-4ef5-a3b9-a69f6e4afb46 |  | note | 683.16 (b) (i - iii)
label | 62b26536-72a7-482a-a487-afccad40e225 |  | note | Table 683.163
label | 7c993639-ad59-405c-b65d-6a92c237939b |  | note | ACCEPTANCE CRITERIA: Where applicable, if any Type III / Production Test results fail, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
label | c3bcd34c-d4ae-45e0-a5e2-02bf701c3d41 |  | note | An additional 2 no. nails are to be installed using updated installation procedures, either side of the failed nail and shall pass the load test - note that the loads may require updating.
text | abd9a398-cc13-45a7-9fe7-a9b3d520879e |  | textbox | Enter: Teambinder Approval number
label | 196b97d2-63c4-4d9f-8242-361d3fa2cc1f |  | note | METHOD: Document Review
label | c6dd1884-da5e-4149-a873-f003984b58c6 |  | note | FREQUENCY: Where applicable, per failed test result per soil/rock type
label | b952240a-789a-4de8-b82a-ad5c89cd23aa |  | note | CATEGORY: HP
label | e116592e-4818-490d-9a41-245b4fbfb006 |  | note | RESPONSIBILITY: Nominated Authority
label | f5d89b8b-bb2b-4bbd-9425-809df8211424 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 0cd74b54-92a3-4bb7-87d8-bf9e4880e8f1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Excavation Monitoring - Long Term
label | f9551ab6-74c2-46bd-98c2-1e70a27c9cda |  | note | REFERENCE: IFC Drawings
label | d7904869-049f-4c9e-ae1b-55e4d36d30fe |  | note | ACCEPTANCE CRITERIA: Survey monitoring for deflection shall be conducted at the top of the wall and mid-height of the exposed face at every 3rd column of nails in abutments or 15m chainage intervals.
label | 5455613c-32ac-4bf5-b3d5-efe81b87f3b7 |  | note | Movement trigger levels from original are:
label | 00d47e48-342a-4832-851a-6a3db661f608 |  | note | i. 10mm = Green - continue excavation
label | 4282c282-4b44-4ba7-be72-dc2e5aa198ef |  | note | ii. 15mm = Amber - increase monitoring frequency
label | 0d76e147-8dc0-4210-a10e-1332e867bf6f |  | note | iii. 20mm = Red - implement measures to cease movement and stop work
label | 31ba4cbc-0bab-447d-ab1f-c41273bde2eb |  | note | Record: Wall Monitoring Data
label | 44c0006e-d4c5-421f-87fe-2bd9e0a45de9 |  | note | METHOD: Measure , Document Review
label | 0a5c6831-ff19-4561-bb1a-58e274e64257 |  | note | FREQUENCY: Once a week for 4 weeks. Then once a month for 6 months, then every 6 months until end of the Defects Liability Period
label | dc1b8c63-3b52-4250-b6b2-2a8682fe18fc |  | note | CATEGORY: IP
label | 070614d2-f4c8-4982-be29-8fbab1cb38e8 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | e2c32806-5633-4d3f-92e2-d3414ea1c154 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8e0f2390-5484-4e0e-898c-90313a4dfa1a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Non-conformance Report (NCR) Closure
label | 13a32706-78fd-4f3b-ab86-0bc6d0331441 |  | note | REFERENCE: MRPA Quality Management Plan
label | c1ab058d-a6d5-43b8-8937-421e5b11f7ac |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 5392e97e-e7dd-4a11-a25a-f2a4ac45357d |  | note | METHOD: Document Review
label | 57589ca6-bde5-49f8-b0f8-787afab3f570 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 044421ae-a649-4b69-bba6-0725aade3c97 |  | note | CATEGORY: HP*
label | bc237400-ec39-4864-a023-e140b5813ab0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d979540b-34ab-4824-abeb-148d78c9f215 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4bf0e3d5-439d-4e42-adbb-97b28e9f138b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 0c56291c-d9ac-45f6-b7d6-6735becc21ae |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 839b204c-174b-4799-8c15-b6648a3bd8f2 |  | textbox | Name:
text | 2aa83859-d10f-4d57-b70d-a4d324b73da7 |  | textbox | Position:
text | 4e28400d-5fc8-42f9-9506-91597c46eaa3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Bored Piling Rev 5 | itp |  |  |  | Yes | ITP-STR-Bored Piling Rev 5 | 47580841-7bfa-4593-9f57-eb9f2f23f7b5
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 4ce27a64-6072-4635-9beb-2667e04f06fa |  | note | Document Title: ITP-STR-Bored Piling
label | bcad1d37-a71f-4cec-9adb-40efb5180451 |  | note | ITP Description: Bored Piling
label | 59cac514-c645-4f30-99a1-8e05c3a7b9e8 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 397e2448-56c7-48bb-bb75-ec25c0a7b0c0 |  | note | Revision Number: 5
label | 642e2366-7285-4151-854f-4b8255b244ea |  | note | Revision Date: 12/05/2021
label | c2bb026f-15c0-455a-b602-fa783d59745a |  | note | ITP created by: Mike Freeman
label | 68187e2f-c04a-4148-846e-582b97873920 |  | note | 1.1 VicRoads Section 606 July 2017
label | 59d1c62e-cde3-47d5-84e9-80a09ca90a24 |  | note | 1.2 VicRoads Section 610 June 2019
label | 409ecd45-d7d6-4856-81ef-7f55ab6ba6a8 |  | note | 1.3 VicRoads Section 611 November 2018
label | 321f7abc-10fb-4210-85ab-eec4b58112ec |  | note | 1.4 AS2159-2009
label | be1d894a-ed94-43ac-93fd-a214fc00f166 |  | note | 1.5 AS3810.1 2018
label | b58506dc-164b-4e15-970a-357d843eba87 |  | note | 1.6 AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 3586338a-7fc4-4f83-8b7b-45b11d29c376 |  | note | REFERENCE: 610.07
label | 78e5449e-b90f-4736-ac47-6d5cdc17c7c4 |  | note | Table 610.071
label | c29d366e-55cc-4b5a-a9e2-8d8471965461 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | b55f202f-99c5-4dcd-8d83-fb3454307197 |  | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 9142bd13-2714-40cb-a5e5-f73272f9b913 |  | textbox | Enter: Teambinder Material Approval number
label | 939fa100-4c63-4996-9f0b-92bfbcff6276 |  | note | METHOD: Document Review
label | 630464ba-fcec-4d50-845b-37a65dd3fe8a |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | b284cb9e-e026-47b0-9401-6002b2205975 |  | note | CATEGORY: HP
label | 445634e9-85eb-4d12-8c6f-d1c9b211d85b |  | note | RESPONSIBILITY: Nominated Authority
label | abe0279c-cf5e-45e5-9a90-e65c61b5c986 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9dfee121-81a3-4ed9-ba7e-219ec1c04d15 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 46df5941-f9eb-4c77-adaa-414262c0a71e |  | note | REFERENCE: 611.05 (a)
label | f2d62a80-e3d7-46f3-9727-a57d6961ebbd |  | note | Table 610.071
label | 51094f65-820c-4fcf-9fbd-b2e848dc8604 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | bfd4c56b-e876-4f0d-8f63-05a26506854e |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | f2917206-a4f1-4525-af90-853c2027aefe |  | textbox | Enter: Teambinder Material Approval number
label | eef530c0-f16d-4551-a0a1-babcec465e52 |  | note | METHOD: Document Review
label | dd7a2abd-8b1e-4ef7-9a7e-0add6ba192a5 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 1d16cbb4-034b-48f9-a020-d82f3498373a |  | note | CATEGORY: WP
label | 37d56fae-7f1e-4185-af45-b562577351d3 |  | note | RESPONSIBILITY: Nominated Authority
label | b3462f5e-7c41-47b7-b512-ddbcc51e9dd7 |  | note | VERIFYING DOCUMENTS: This ITP
text | f54d2639-af17-4108-8b6a-2b3129c3cc0f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 2ad69838-33f3-4615-b0b5-0327fc6ecc42 |  | note | REFERENCE: 610.26 (a)
label | 0bf669a7-fc17-4593-ab92-d32e247bf2e9 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 873830b0-a929-4c23-9999-521999f8b5f1 |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 84c18b4c-3c6d-4aeb-ac99-5f831db3c34e |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | fee9439c-a624-409e-bed0-a29506b35878 |  | textbox | Enter: Teambinder Material Approval number
label | f10c0aeb-5b67-401d-bb7e-f7f816b0b4e2 |  | note | METHOD: Document Review
label | 29a31b61-963c-41c0-8d7d-09524cff68ae |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | eb6ba838-946d-40fc-a76b-734a3d7459f9 |  | note | CATEGORY: WP
label | 023bd231-f9ce-4ffc-8538-7346b72e13bf |  | note | RESPONSIBILITY: Nominated Authority
label | 544dde91-e1a3-4a02-899a-94b174cd4ed4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4c866a36-88de-4b64-86ad-0b11cca9a139 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Piling Operations Work Procedure
label | 57714457-3083-4c43-9db8-5ff311f2fa38 |  | note | REFERENCE: 606.03 (a)
label | 24b85304-51b7-4327-a7ea-b369a9669734 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 6dff5fd1-e7b7-4f9f-8d3b-84330d347b7f |  | textbox | Enter: Teambinder Approval number
label | be2f43cd-f68e-48bf-a11b-f03dcdf166bd |  | note | METHOD: Document Review
label | 96921752-0a1b-4d77-acbf-a92818e0a599 |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | fbc7a8f8-3cdc-404c-ac00-6875e7e6c079 |  | note | CATEGORY: HP
label | a71126eb-6fae-416f-8fee-ccf3b8a4d5db |  | note | RESPONSIBILITY: Nominated Authority
label | ac227da2-b5e2-48a0-9eeb-d4ff2e455645 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 14982e56-b79a-4406-88e5-07f867b3af4e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Temporary Steel Casings
label | 890e20aa-b4bd-47c8-ba83-678dc700e41c |  | note | REFERENCE: 606.03 (b)
label | f249c9bd-8d16-44a9-ae9c-c63bfe2e66cb |  | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | 7d853f5b-9cab-40b3-a7fd-4188c182333e |  | note | Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 63625a48-2a3c-41d6-8e04-9113bccc9615 |  | note | The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | cea87cdd-3118-417c-919d-8c3fa206cc73 |  | textbox | Enter: Teambinder Approval number
label | 1e306228-9a39-4f28-a6c2-8a6438751c32 |  | note | METHOD: Document Review
label | 07fcb19b-9ca8-408c-a188-b2fa6372ed00 |  | note | FREQUENCY: Where applicable, once, prior to use
label | bc5772db-6a53-470a-80f3-d3b0fc46b0e8 |  | note | CATEGORY: WP
label | 04edda40-fb73-46ab-8c1a-32bf4fbd9333 |  | note | RESPONSIBILITY: Nominated Authority
label | 122a6a53-13ce-4e7a-aa48-a5a1b338ce4d |  | note | VERIFYING DOCUMENTS: This ITP
text | c1e8de60-20c9-4776-977e-04a040108bd5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Casting Under Water Procedure
label | 4ea04ae9-cb4a-4907-ad1d-8f8af98fb5cd |  | note | REFERENCE: 606.06 (a)
label | 5f43017f-b401-437c-a000-5907b4b7c03e |  | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | d16f2622-87b2-4ead-924b-d178c7c0acc5 |  | textbox | Enter: Teambinder Approval number
label | 4790ffbb-5c64-45ac-8f15-aa659a4c50e3 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 3b3ce3b9-fef3-43f3-88a9-f00011e03477 |  | note | METHOD: Document Review
label | 35fcf868-14a3-4088-b8fd-f57c0a774399 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | cd1cc6c1-e319-4093-b698-9185b2811d8f |  | note | CATEGORY: WP
label | 710bd197-d82f-48ba-838c-d9876ef0b5e3 |  | note | RESPONSIBILITY: Nominated Authority
label | 206375bb-9da9-4eab-b316-769cc77e061f |  | note | VERIFYING DOCUMENTS: This ITP
text | 3078a295-5230-4aab-b0b2-33642f10ae8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Boring With Bentonite or Polymer Fluids
label | 6f7a3030-25ed-48a9-ab81-9817da14663e |  | note | REFERENCE: 606.06 (c)
label | b8cb22c7-e4ef-48f6-a32c-b2add8820515 |  | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 32502ad2-409e-4eff-b576-7f684936ec0d |  | textbox | Enter: Teambinder Approval number
label | 1c089cac-15df-4eac-8fe2-74851b7aed0a |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 06f3aa9a-8daf-4331-92ee-41d32edab5e8 |  | note | METHOD: Document Review
label | 85da2c07-e0ce-437e-af14-54c8f891d240 |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | 64359c33-ace1-4077-8398-a136256c6ce1 |  | note | CATEGORY: WP
label | 8a47f66e-ea24-4dda-9283-c6902f9ba85d |  | note | RESPONSIBILITY: Nominated Authority
label | ddeedfaf-0d18-46cf-a51d-0c1c60abd2c8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1383ce2b-a3df-4b31-a9d9-423e36d07373 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Dynamic Pile Testing Procedure
label | 6fec49f2-f53c-4d1b-9ae1-a4f28b6933e1 |  | note | REFERENCE: 606.07 (c)
label | e5abe783-b111-4b32-ae83-47f9369c377a |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 4925717c-779a-4459-b537-d18216008a76 |  | textbox | Enter: Teambinder Approval number
label | e4670812-5fc9-47fa-8965-2703ef0c2119 |  | note | METHOD: Document Review
label | f8f65fb7-1d40-47f5-a276-90adea551595 |  | note | FREQUENCY: Once, prior to testing
label | b41bf695-e214-483c-b6e9-30e20083496f |  | note | CATEGORY: WP
label | 356cd7da-d0a3-4206-9b4e-f60a1cf48196 |  | note | RESPONSIBILITY: Nominated Authority
label | bf4af1e6-9ca9-45a6-8063-d176e579b884 |  | note | VERIFYING DOCUMENTS: This ITP
text | 00e80e6a-3f3a-402c-b173-fe4ca9759e40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Pre-qualified Pile Testing Consultant
label | a1c81245-e826-4ec5-810b-2398ffb596b3 |  | note | REFERENCE: 606.07
label | dbd7d7f5-38ab-4c2c-8903-db050ec63ea3 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a pre-qualified consultant who is independent of the piling contractor.
label | 5d81bf53-461d-477d-b877-1e64bc42a4f9 |  | note | Details of the consultant to be submitted for review to the Nominated Authority.
text | 35293069-1b81-4270-b22b-779c85b86229 |  | textbox | Enter: Teambinder Approval number
label | 1bbd8a28-1cd9-4ee8-89ee-5ece5e2ea654 |  | note | METHOD: Document Review
label | e55498d4-24f0-4a2e-a947-44362fad9b7a |  | note | FREQUENCY: Once, prior to testing
label | 2d45fff7-8f7d-43eb-a58d-9e37ef9ae9bd |  | note | CATEGORY: HP
label | c2972f6a-033b-4910-9c24-d8de088ba84a |  | note | RESPONSIBILITY: Nominated Authority
label | 5d3280d3-4904-494c-9da0-7d4ba22f4c1b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | a843d675-cc52-456a-9ef9-eccab21e8f21 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
label | 13f94e35-7438-40da-9e46-fa4cc2197b31 |  | note | REFERENCE: 611.13 (a)
label | 827092fc-bb29-4b51-9f38-d64f0f7fa4d9 |  | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
label | 042039ad-c34e-4a5f-8b75-cc62c613e5f5 |  | note | 611.14 (b)
label | c0f7944c-7bb2-483c-8e5a-38f0f96bb761 |  | note | ACCEPTANCE CRITERIA: Welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | f64b4587-fd89-422c-b46c-0b7c076406a6 |  | textbox | Enter: Teambinder Approval number
label | 7a83c3aa-80dd-4a3b-beee-d668111c2093 |  | note | Note: Tack welding requires the same documentation but is a Witness Point
label | 3e054c06-5f0a-4d37-9478-e71199053b4a |  | note | METHOD: Document Review
label | 68cf42f0-b1e3-4ab6-862c-6c399d3c09c1 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 7b60b193-50ac-426b-8828-558ec43b5fd0 |  | note | CATEGORY: HP
label | ee53201e-a8f0-40b5-9ff5-3f5be638d148 |  | note | RESPONSIBILITY: Nominated Authority
label | f965c57e-0ccd-47d6-9c2f-b80e8c6a8eca |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ffecc083-44b7-4653-8000-eb5f2d6adcd7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 3e70abb4-a470-4a5b-a1cb-e574dde79cb7 |  | note | REFERENCE: MRPA Quality Management Plan
label | b4caba83-36ef-49c1-aa7d-c42641b47262 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 29d8b3c4-e7bc-49ef-8ab7-8ce42b75c3f7 |  | note | METHOD: Document Review
label | 7c0456e7-12b2-4dc6-849e-ed7deaf25e0f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | c0035182-1d43-4d8d-972d-892ebad349f0 |  | note | CATEGORY: HP*
label | 1ec4888b-70d8-436b-9cc2-0e0fc442a025 |  | note | RESPONSIBILITY: All
label | d17a1cde-7e80-4e42-8d19-dc490219642b |  | note | VERIFYING DOCUMENTS: This ITP
text | 8871ed34-c621-4421-aec8-26dd72453987 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 28ac12d5-23fa-4658-8030-67db454d2ee1 |  | note | REFERENCE: IFC Drawings
label | 844bba13-8c8d-4b10-ac2c-680870783156 |  | note | 606.08 (a - c)
label | 43029986-25fa-4286-b098-8c746262cc2c |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | d60cafc8-5a83-4b7c-8c9f-1e381555b193 |  | note | METHOD: Measure , Visual
label | a4c0e3fc-2dec-46a2-9a04-e6fb18b3a9fe |  | note | FREQUENCY: Each pile
label | 09d8c1ab-07d3-4565-b61f-a461e3f74c0e |  | note | CATEGORY: IP
label | f8eb96ab-57d1-433f-84f5-f26d2c22eb4d |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 843106f9-24bc-4810-9a47-937d5c53241b |  | note | VERIFYING DOCUMENTS: This ITP
text | a48976e0-81a0-4284-b8ea-b9bf0e1f645d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | cb58e212-850d-43bf-9391-1041d4cc1ea2 |  | note | REFERENCE: 606.04
label | aeb7c34b-f3bf-438d-b6cd-9916c1e56de5 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not:
label | 62522a97-d1f3-4b16-8bd4-420c6bc623a2 |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | b8fabc60-6c61-4757-887c-2146280aafb2 |  | note | ii. commence within 2.5m from newly cast piles if that pile concrete strength <15MPa
label | 5ba557d7-15ff-456f-99b3-092a5999d94c |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 15eedd64-a3c9-4d53-8093-7aa2c948f2ce |  | note | METHOD: Measure , Visual
label | e70880a8-64e3-410d-8624-67965fd07d70 |  | note | FREQUENCY: Each pile
label | f378614f-1112-4c19-b934-f0d65bba895c |  | note | CATEGORY: IP
label | d5c84765-6b91-492b-a15d-0e0f9bb23240 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 3395ae19-a87d-4f48-9850-ed1e32c27f70 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4cdc1f57-3f3a-442b-91c3-ff1e7257eaa9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | f54b29a0-5e33-486f-9ef2-4fa2b5119f24 |  | note | REFERENCE: IFC Drawings
label | f7f3ab74-3c28-4d03-8d79-6e904b815dd8 |  | note | 606.03 (a)
label | 68edcdf5-e643-4fdf-8445-7a856be63f17 |  | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | cdae7343-a00b-4b50-bb5c-5fff4a9a683a |  | note | Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 50ae8e73-e275-4a1d-8a68-ea1b48ea00ad |  | note | Excavation clean and de-watered (where applicable) for inspection.
label | c5b60b2c-98a7-4ace-b4c6-7537f1a1d3f6 |  | note | Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 3fd4073e-0d22-41e8-a46a-89a98c5dd3b2 |  | note | Excavated material to be disposed of as appropriate to maintain a clean site.
label | 03824e49-0575-4475-8753-f596911fa337 |  | note | METHOD: Measure , Visual
label | c9bf1ff2-7f63-4769-b796-372a413e968f |  | note | FREQUENCY: Each pile
label | 29d448e5-aedf-45f0-9f5d-5acbbf336519 |  | note | CATEGORY: IP
label | 077343ed-32f9-4194-8792-9bf987668c43 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | fb40bbc0-d6b3-4372-888d-4b20af637c71 |  | note | VERIFYING DOCUMENTS: This ITP
text | fa04eb4e-30cc-406d-b5d2-3819d56d5143 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | 171147d3-9f4c-43ae-8cbe-99f0cb672a50 |  | note | REFERENCE: IFC Drawings
label | 6b4e7729-cc90-4688-a8ab-b8e983b3d3a5 |  | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | ec52fb94-4d55-4df0-984f-5960c42af3c5 |  | note | METHOD: Measure , Visual
label | bb956dbd-65ff-4f73-9ed1-22c19a9ad157 |  | note | FREQUENCY: Where applicable, each pile
label | f8408021-ac6b-428d-97a0-d02d80940c16 |  | note | CATEGORY: IP
label | 252d6702-a361-49ce-8bac-5548c27a8a30 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | adee2ae4-137c-4879-99f7-30393b19e99e |  | note | VERIFYING DOCUMENTS: This ITP
text | 04a50c30-f476-40af-a4f3-4d99e60c90ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | 625fae7a-4999-4033-a9c0-0a894867e0a1 |  | note | REFERENCE: 606.05
label | 4bbd0267-8ed2-466b-b913-2adf9759e0db |  | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | ad0f9a92-74c4-4e94-b5c4-ab00177d2ed3 |  | note | Attach: Geotechnical Field Sheet or Report
label | 903ea199-1f42-41f5-86ea-c83770778220 |  | note | METHOD: Measure , Visual
label | 5aa4a731-74c4-40fe-ba7c-03666bbc80e2 |  | note | FREQUENCY: Each pile
label | c1a9f0d9-a4a5-4286-9120-5fb5e19a9342 |  | note | CATEGORY: HP
label | 4d396aaa-7bbb-4653-9187-535b614ba6d7 |  | note | RESPONSIBILITY: Geotechnical Engineer or Nominated Authority
label | 67182c9b-1f59-4989-b026-3bce014d5228 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 86b2604c-63dd-4e3a-888e-5df0fdce5057 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement - Placement
label | ea1dc11e-5633-4b9f-859d-99266519374b |  | note | REFERENCE: IFC Drawings
label | d4b3ef9e-a16e-43aa-a3c9-daebbe615081 |  | note | 611.06
label | 81a72bb0-bfed-457c-b400-56fbb013ddee |  | note | 611.09
label | 6587dcde-db22-42a1-8395-9421a2b8f088 |  | note | 611.1
label | ae9e24cc-7100-454c-b454-4f1c0b7b5a9f |  | note | 611.11
label | b71cfbfd-7782-41e5-8a77-3aa87e6aa7b5 |  | note | 611.12
label | eb03a509-dd2c-43ec-a393-a39cb9cee28e |  | note | 606.06 (a)
label | ec502a6a-c88f-4041-9530-e22180692805 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 90b2e3bb-217f-4fd0-aff5-66b3adcc49f4 |  | note | Projecting reinforcement is the correct length and location.
label | fa3b141d-2fde-4fb5-8a22-e654d8c888e2 |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | c2acb6bc-9b88-475e-8938-a254681c9c9f |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 75cbd0b0-259b-4e5c-a588-0dd68c05fa7d |  | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 2010cd7d-9b75-4ec5-85e5-dbd5fe00acf9 |  | note | Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 6d2adfc3-7c3b-42d3-b361-babecd13e8c0 |  | note | METHOD: Measure , Visual
label | 507214f0-10f5-44a3-8461-89c7774c4b55 |  | note | FREQUENCY: Each pile
label | ba643e76-36d5-48f0-8ca8-8d684607bcdd |  | note | CATEGORY: IP
label | 881d3484-55cd-480d-a16c-a4e12dcde1b2 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | ee1aabc5-478b-4a2a-b867-bb1326119f1c |  | note | VERIFYING DOCUMENTS: This ITP
text | 8a7d89f4-fb91-49e8-85d4-0eb65ff04fe3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | 703c5fa5-4260-4a4e-b19e-4ac16b08550d |  | note | REFERENCE: IFC Drawings
label | 9f2b5798-11f1-498f-98d3-128fc4111a17 |  | note | 610.29 (d)
label | d65c6239-2b5e-468a-b4f4-202bb24756b4 |  | note | 610.43
label | ebf3122a-5a5d-411e-bd12-3d07b09cd079 |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | 549d66b4-909a-43b9-9cf2-3e82e5d32cad |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 5e5900a8-883d-4eff-b18b-2adef6a6ea75 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | c4412293-408d-4170-bba8-ecd5bd4561bb |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 0291900e-2fd9-4b18-9a2d-d39599519873 |  | note | Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 60d2df14-dd19-4b83-9b16-113532455243 |  | note | Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | e36d5337-af52-4b46-b48e-e49eedb4dc2c |  | note | METHOD: Measure , Visual
label | 47d46334-5cae-4a3c-9266-e01ffa3df43e |  | note | FREQUENCY: Where applicable, each pile
label | 88c138ff-960e-4b1d-a059-85bba1a3277f |  | note | CATEGORY: IP
label | cdea8469-0c2a-43b0-b60b-ecb298c7d22b |  | note | RESPONSIBILITY: Earthing Engineer , SE/PE/SPE
label | e0200b28-7d36-4249-bc1f-c5ef2dde5d99 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8353142d-216c-404d-855f-d53e858ba3f5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | 8bdec2f9-4702-4446-bfde-030d4f65a3bb |  | note | REFERENCE: IFC Drawings
label | a720829f-5cf7-4025-90e0-2e97f7ebcb43 |  | note | 610.46 (a),
label | e02f6703-eca4-4058-b9ef-d510527f049d |  | note | Table 610.462
label | 26481499-7e05-447b-b521-b83caea14eba |  | note | (November 2018)
label | 1a9258de-9c21-41d8-9f96-e528f0a24383 |  | note | 610.47 (a)
label | c0125be7-8acc-4de3-a563-a3ecb1242c8f |  | note | Table 610.472
label | 0fffadfe-7d38-45c4-93bd-50c1a043055d |  | note | (March/June 2019)
label | 5f69c605-151f-4176-8865-a3d66c47ce8d |  | note | AS3810.1 Table 3.3.6.2
label | b87ee896-3f2e-41f7-9051-9033ec1c589c |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 758bf293-eb97-4da8-af9e-ac4af16a9822 |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | addadc43-b113-442e-91db-4c3d8b3df9d4 |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 8b56f3e1-4acc-45c1-8632-2e88c24a3fc1 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 7533d66c-9527-4cc6-b386-07d44c9adfe3 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 3ba6fe61-e08f-453b-89ce-44d6a669e259 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 09365aeb-6469-465f-9b82-167dc5699dbd |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 402b8700-3b63-4db9-8a71-31e7c7ef615f |  | note | iii. Ducts and conduit location = ±12mm
label | 370e38ea-add0-47f1-8fa9-3c242cc8832e |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 837b07bd-1741-4bbf-9136-47f877e733dd |  | note | METHOD: Measure , Visual
label | ed78e3d3-30df-4ddb-8014-e5b5fd30d6df |  | note | FREQUENCY: Where applicable, each pile
label | d25a62cb-9f40-4d78-9dbf-133eb61de6e7 |  | note | CATEGORY: IP
label | 86074b5c-9ea7-4b71-b4bc-a25073df87ee |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | fcc69ba3-38d5-4b49-840b-ca9cbc6bd0d7 |  | note | VERIFYING DOCUMENTS: This ITP
text | fcff4233-ccbd-4411-ab26-f00714021991 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | 5eb30069-b8dc-450a-9dc0-a48540805d2b |  | note | REFERENCE: IFC Drawings
label | 73e514b9-1178-4d93-9741-680362d7d4a4 |  | note | 610.18 (a) (ii) & (iii)
label | 09cb9eda-6235-486f-8336-8dc021a4668a |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 9a284f10-ec4d-4110-9cba-5774b64372a0 |  | note | All foreign material has been completely removed from the excavation.
label | b8a97a11-078c-417e-9e0a-955b421eb57c |  | note | METHOD: Measure , Visual
label | c4f8e8a3-3b1c-4701-8349-894b6031d800 |  | note | FREQUENCY: Each pile
label | 85cb4717-2fc3-415d-975b-505b3289cf05 |  | note | CATEGORY: HP
label | f1a41fda-7acd-4a89-8ebf-4b033325530b |  | note | RESPONSIBILITY: Nominated Authority
label | a0530d26-0d09-45ec-9fe0-1dae5e2e3fce |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | dd4065df-37e5-4278-8624-d568f2c16bee |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | 13dfc8bc-5189-45d7-8971-38be416b3926 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
label | 74951cf5-4a18-46c9-a670-c545a338c4e9 |  | note | 610.17
label | 5481b9d4-9bdc-415d-9f40-dd205db3601f |  | note | 610.17 (a) & (e)
label | 4a274ef0-d25a-420a-9f5c-36fb09b0622e |  | note | Table 610.171
label | f90a9826-5ef2-4ea1-8ff9-bb493f732e97 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 089749f3-7b37-4d4c-9116-ffa664a2d09d |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | e55fee87-0dbd-4e98-ac28-cd8bf854f614 |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 258d74b1-02a0-4c57-b17a-f3175dfc0b37 |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 155b3666-c4c9-4625-86d3-3c0097099828 |  | note | Record: Required information on the Concrete Pour Record.
label | 793cad2a-ee54-41ad-b17b-d8bccd28b932 |  | note | METHOD: Measure , Visual
label | bff73a7c-50d4-43dd-9e0a-f759e8e37415 |  | note | FREQUENCY: Each pile
label | 2e7c7290-6cfb-416e-9399-30e9a3c5741e |  | note | CATEGORY: IP
label | 0b6baf18-d859-477d-9eda-2200478e772d |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 04fd6793-f652-4ce8-aa95-c01d1bffed69 |  | note | VERIFYING DOCUMENTS: This ITP
text | d853b390-c6c4-4f1e-9647-9bf3616808ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | dea5ac38-3765-44d5-8412-b34c249cd08e |  | note | REFERENCE: Site Sampling & Testing Procedure
label | f38f2003-9154-425d-9fd6-f01aca3c5c98 |  | note | 610.16 (b)
label | bd4db532-fb5d-461f-be1b-aac72f407002 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 6807f8e1-13d0-4c18-8b66-a0cd1751d471 |  | note | 0m³ to 10m³ = 1 sample
label | 57a935a7-80d3-4f5e-b529-cd3ee819836f |  | note | 10m³ to 25m³ = 2 samples
label | 95faef3b-a96c-4eb2-b936-4c9e79c0b927 |  | note | 25m³ to 50m³ = 3 samples
label | bfd79e90-70ae-4ee3-a437-f13d4eedba1f |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 58657bbf-b547-4a02-a2bb-1715640ec6e2 |  | note | For each additional 50m³ and additional sample shall be taken.
label | ee8bb965-8096-48d4-ae91-28b20463984d |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 49c5e0f0-b49a-42e5-868d-4ce9644853ab |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | cf9f0678-21e0-4176-8a02-d8dd9922194a |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | ae077ddb-de49-4604-aa8f-25d30db10497 |  | note | Record: Required information on the Concrete Pour Record.
label | fc31f4c1-9efb-46b5-86a8-94c662d1795e |  | note | METHOD: Test
label | e9d1d11c-f4c1-4fb7-bf6e-9b69c505b597 |  | note | FREQUENCY: Each pile
label | fcef2738-50d9-4378-9765-492063e526d9 |  | note | CATEGORY: IP
label | 4e4d7438-1e52-4bc3-b8e8-50cc926c5c1e |  | note | RESPONSIBILITY: Concrete Tester , Foreman , SE/PE/SPE
label | 9ef455d0-c868-4df4-a0d9-9735441ace5e |  | note | VERIFYING DOCUMENTS: This ITP
text | 152b05d4-01f7-4044-bf60-6e2f92f263bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | e306100d-5fe4-472f-8894-675002baf6b4 |  | note | REFERENCE: 610.13 (b)
label | 7e6f749b-ff82-46f7-8f67-fc03ed6bb649 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | 5caed2d5-83eb-46c5-9e59-02a1032e9862 |  | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | f3fcdaa2-5095-4faa-beb6-b7f4ca6f8f7d |  | note | Passability = ≤10mm (aggregate height differential)
label | 52ce8ae8-867c-40ad-b034-a61382c8dffa |  | note | Record: Required information on the Concrete Pour Record.
label | 54b10a14-2017-4ed9-894c-320d1813d7b6 |  | note | METHOD: Test
label | c2d44c1f-c3ba-4d47-9b92-c0e295cad230 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 016525dc-dcb1-4063-b49b-ff99333b04f9 |  | note | CATEGORY: IP
label | 7c88ef01-dcf7-49e0-8181-0947a602de20 |  | note | RESPONSIBILITY: Concrete Tester
label | 3b3dae37-f30c-4323-870e-cdec58da14e3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 473ca3dd-fada-491d-b3c0-a446952cc67c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | b63fc3a3-37b7-4ac9-ad47-9eaf279a897b |  | note | REFERENCE: Site Sampling & Testing Procedure
label | e6d014b8-d4fc-49e4-9c60-04a726875117 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | d5de5ba9-25ed-4abf-b98b-a475481b9c8f |  | note | Record: Required information on the Concrete Pour Record.
label | 69307755-00d2-481c-81f4-1870dee4dbde |  | note | METHOD: Test
label | d4e52f89-afdc-4d97-a6be-cbb05b0a59d7 |  | note | FREQUENCY: Each sample
label | 1ffcce85-a885-46cb-9b61-d6c25300da21 |  | note | CATEGORY: IP
label | df8eeeac-33b3-4625-bacb-3342c1620443 |  | note | RESPONSIBILITY: Concrete Tester
label | 247ff6b4-5c7a-4ee0-8f2c-a2f865174a4d |  | note | VERIFYING DOCUMENTS: This ITP
text | 53fd216b-f377-42d7-b988-837bfbef9bec |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | 7ff43118-7587-4f34-b9ca-4b3248840b54 |  | note | REFERENCE: Piling Quality Procedure
label | 89c7cf50-b4cc-42d3-b460-681c61954b4c |  | note | 610.18 (a) & (b)
label | 4e11cbde-a9ac-4217-add6-6ce27fcc773a |  | note | 610.18 (d) (i)
label | a2cb6003-b757-4f59-84cd-a913d2632920 |  | note | 606.06 (a & b)
label | afde1153-4f4e-4f9e-a936-e126412f5ecd |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | 641ed19b-fbda-45e6-84aa-f0d1219ab5dd |  | note | All concrete batches are traceable.
label | c6ead33c-5108-4f81-8e8d-23135474cce0 |  | note | Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 2e6dc2af-4ea0-41e8-bf80-3ae6d15c63ef |  | note | The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 2622346c-07d3-4875-9a50-49051432e903 |  | note | When placing under water, the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 0f07cf2c-fea3-4954-b154-7536aee0c639 |  | note | Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 0fd07e9b-a311-472e-b660-fe00c8b138fc |  | note | Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 6bbb3577-2e14-4fb6-9312-3f1933e35e6c |  | note | Record: Required information on the Concrete Pour Record.
label | a2441358-fad6-4d70-951c-9721dd7eb1f6 |  | note | Attach: Concrete Pour Record
label | 581a7887-440a-470e-adf5-ab1fc3f72340 |  | note | Attach: Concrete Dockets
label | 8771d1ce-f518-4c3f-8114-30cd600a536d |  | note | METHOD: Visual
label | 82935369-c78d-4a39-84b3-c9f7c46092f8 |  | note | FREQUENCY: Each load
label | ac91128b-1b5e-4515-8829-bcd4ea873198 |  | note | CATEGORY: SP
label | 3e37e72d-6951-422c-8e25-3941b546539a |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
text | 4242ac6a-1ad1-4192-9233-799629147c88 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 66f13522-3b51-4deb-ba3e-e06106f87639 |  | note | REFERENCE: IFC Drawings
label | 62f88edc-221e-4e67-a11b-44989c29dcda |  | note | 610.31
label | 83b3f301-4c97-4abb-a6a2-7f24522b40cd |  | note | 610.2
label | b5a796bf-1156-4c25-b4dd-b22e42298f32 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 6d778437-b203-4e8c-9b0e-9151fd812bfe |  | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 82cb8284-e0e7-49c9-89d7-2e2aab6f08be |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | afabe188-dc2c-4843-9ee1-5d93cecd6cc8 |  | note | METHOD: Visual
label | cf937fad-3106-4f7e-9f93-aaea9c048307 |  | note | FREQUENCY: Each pile
label | cb8ca219-dddb-4d9f-9c3b-70258bdce427 |  | note | CATEGORY: IP
label | c721fb88-eda2-4db2-96ad-2949ff2bcbb1 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | e4e4ae65-68c6-479f-a3f7-13d3b8afcbf4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2ac53d43-6049-483a-a0e9-239d244383eb |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | d1d5d446-02b4-4160-84f1-f1baa226ff82 |  | note | REFERENCE: IFC Drawings
label | b14f0138-eb8a-43f2-82e5-4a8e728a1cb8 |  | note | AS2159 Clause 7.2.2 - 3
label | eeb7d372-0a09-4022-9195-6fbe821443c7 |  | note | 606.06 (a & b)
label | 29abbff2-4dd5-48d2-b983-30bd818e5e52 |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.\
label | 4551876a-7351-4b64-892d-3aeb68c445ef |  | note | Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | d04de5fb-032e-4332-b5c2-0667531e51d5 |  | note | Any weak or damaged concrete shall be removed back to sound concrete.
label | 1f6f8e1b-4cd7-4358-9f81-6b5e5af560e0 |  | note | METHOD: Measure , Visual
label | 03aa42ab-6d08-4d01-8a55-7651c30cfe98 |  | note | FREQUENCY: Where applicable, each pile
label | 1edf2590-9c85-4cbf-b98c-e8c68d40edfc |  | note | CATEGORY: IP
label | 62a34320-d0a3-4d77-b60b-a85445fdb713 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e1861c84-fd59-4697-b824-11ffb443275f |  | note | VERIFYING DOCUMENTS: This ITP
text | 32c172e0-6afd-4cdc-a085-a6ef0a628290 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 1b2b8462-75a9-4952-9b6b-bdc1661cd2d9 |  | note | REFERENCE: IFC Drawings
label | b85dfcd8-c70f-4df0-bc88-1e6056639bfa |  | note | Table 610.05.051
label | e88cd26d-be66-42e8-93b8-b63ddaeb8613 |  | note | 610.16 (g)
label | a4da2ec9-1df1-4567-864d-eacce977b658 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 92af7c64-4198-4a8a-9740-dbd869d3b675 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 8766b66b-def5-47ae-9479-28d381051164 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 63123cbe-e463-4dc4-bd74-f571b4417609 |  | note | Attach: Compressive Strength Test Results
label | f6bf04b2-192b-47a2-880e-f5be5f0b8a5f |  | note | METHOD: Document Review
label | c32d6857-a2c6-4b28-baaa-6a73d0f0a260 |  | note | FREQUENCY: Each cylinder
label | 66a28743-30d4-4140-8749-af29d3b9a32b |  | note | CATEGORY: IP
label | ce830a85-8732-47a1-9983-d4efe9446500 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a8cb0d88-0128-48f4-b4d6-4a5e764981ad |  | note | VERIFYING DOCUMENTS: This ITP
text | 3407a05e-8505-40a5-b59e-134cfd555e7e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 2b5716eb-10b1-43b0-afce-9afbbd70ebc7 |  | note | REFERENCE: 606.07 (a, d & e)
label | f7774ea3-4cf9-496b-9416-321f73ed1534 |  | note | AS2159 Clause 8.8
label | 9f3157b5-9cab-4b5f-8825-0c5183cc71d1 |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 680d2cbe-bd5a-4e03-930d-230cff1b3482 |  | note | Cross-sectional area = ≥95%
label | 1ef6e127-5626-46ec-9436-67cbe9701c99 |  | note | If any test fails, all piles shall be tested.
label | 5b366b54-22de-4b14-ab7e-3bac53bd7ede |  | note | Attach: Pile Integrity Test Report
label | b07aebc5-42f3-4763-b435-47889475e299 |  | note | METHOD: Document Review
label | bd68c6c2-e6ed-4f4a-ba3d-2e94b2f775fe |  | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | f1255442-82b4-4785-a7d7-b084d98e3d19 |  | note | CATEGORY: IP
label | 88e3b8a3-264d-4d44-abda-7ff551172f96 |  | note | RESPONSIBILITY: Testing Consultant SE/PE/SPE
label | 11b5810f-330f-4c46-b400-04fac8825fb2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 517b7c4c-c177-4b56-b093-15a5c6f373b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Static Load Testing
label | fc3971ba-6cab-4faa-b833-7c55583fbfb2 |  | note | REFERENCE: IFC Drawings
label | 9057c971-858d-47d4-9b2b-e45d7ef4bbbb |  | note | 606.07 (b, d & e)
label | e9a3a309-872c-4b40-9f7f-e449f1b00412 |  | note | AS2159 Clause 8.4
label | 68ab0768-c903-4002-bd95-d5f1a56409aa |  | note | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | 1e3346d4-7bf0-437e-a8c5-b99ed4c8de04 |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | f9c4e160-fcd5-4a2b-9b92-bd7451bb264c |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | a31e7e10-8a02-4ee4-a0d8-33421808eed9 |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | 06370530-41a9-48bd-9b4f-5a46ad472a75 |  | note | Attach: Static Load Test Report
label | a8700a9c-d3b1-4ec7-b8f0-166e7a2d950f |  | note | METHOD: Document Review
label | 90159633-9f89-4fe6-abae-e254e4897190 |  | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
label | fa7f813c-3ecc-4dd1-b1f3-68f37508b964 |  | note | CATEGORY: IP
label | 3a6ccc86-918d-4d2f-b6d7-80b934d4c09f |  | note | RESPONSIBILITY: Testing Consultant , SE/PE/SPE
label | f62efad8-047a-4e6b-bd98-a4d6e4e6be26 |  | note | VERIFYING DOCUMENTS: This ITP
text | bc1d967d-39f2-45bd-87bb-f211d67574d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | 515170de-6a48-40fc-ac1a-beb4cb85b686 |  | note | REFERENCE: 606.07 (c, d & e)
label | 83f9b8cd-df5d-4d8d-9502-9a5c3093fee7 |  | note | AS2159 Clause 8.7
label | 67aff411-9aa8-4ddd-ac90-e18a8687e8a4 |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | 52502f4c-c1fa-4c23-870b-a61a34df1f38 |  | note | Measured Ultimate capacity = ≥ values on IFC drawings
label | 0322b52f-a1de-4b35-92f3-18cd5405e30d |  | note | Attach: Dynamic Pile Test Report
label | 36f39a3d-522d-4eac-a126-6774e2dbe346 |  | note | METHOD: Document Review
label | 33f27b14-5a63-4746-9c92-b549728c5939 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | 6496f4b9-93b3-4601-bf62-503e9968963e |  | note | CATEGORY: IP
label | 6ba47f91-e945-4638-91ec-b046320da02f |  | note | RESPONSIBILITY: Testing Consultant SE/PE/SPE
label | d885ad10-4071-4f4b-8f1f-15a069e5eec9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8a21dd6f-c312-46d8-91d1-245f98b247b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | 57847950-41ba-4a10-8b6b-50001d9aba83 |  | note | REFERENCE: IFC Drawings
label | f03c990a-95b5-4f9e-9231-128a41c7533d |  | note | 606.08 (a - c)
label | 31e26405-7a1d-4a44-aec4-0ecf49b1797a |  | note | AS2159 Clause 7.2.2
label | 7dbc8cd1-5335-4a03-b427-42cf758fcb3c |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | e952d03c-592c-41cc-be4e-727724cd7b29 |  | note | i. Pile head plan location = ±75mm
label | 4c95a758-bd5a-481f-b437-c5b64f2458f7 |  | note | ii. Variance from vertical or rake = 1:100
label | 7b728822-9919-4bfa-84fc-61056d40912a |  | note | iii. Irregularities in straightness = 1:100
label | 4177af16-05de-48e4-9cf2-f3ea01ef6777 |  | note | iv. RL = ±25mm
label | feffa8a8-ad33-4998-b82c-b373556c6577 |  | note | Attach: Survey As-builts / Survey Report
label | 74b5c54d-c03c-46c3-95d7-7fbcaf580d44 |  | note | METHOD: Document Review
label | f55191e6-6609-49c0-898b-5976903ed2af |  | note | FREQUENCY: Each pile
label | 81b08ccf-c622-44f0-b630-b8faa5824d77 |  | note | CATEGORY: IP
label | 053839df-dea7-489d-83ee-a6014b3b1102 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 3b377502-ce42-4400-b340-128ce5b0f358 |  | note | VERIFYING DOCUMENTS: This ITP
text | d245a07d-d913-471a-a34f-7be9cf5f4ffc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | 00f1c29c-2691-45a8-b9b3-f7b10df49f2f |  | note | REFERENCE: MRPA Quality Management Plan
label | 21efda6e-ef7b-4a2a-8d45-08cd55b159af |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | ae870be8-0793-4a97-9a8b-31a103e72cc6 |  | note | METHOD: Document Review
label | 54850229-8412-4f9a-aff4-778d0ff54919 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | a2e7d5ff-81c8-4f0d-aa21-22ecfb87f66d |  | note | CATEGORY: HP*
label | 40e718f0-2a08-4e2c-8063-6e1c6227ed12 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cf5821f3-063f-4208-88b6-29a17e79b269 |  | note | VERIFYING DOCUMENTS: This ITP
text | 58832145-468a-4c62-ab8b-f934237ec0ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 05f5693c-d1c4-49f4-8ac3-5513cd6da6ba |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d97eea69-6a6c-4b00-8655-5e5a3d2510a7 |  | textbox | Name:
text | bf4f1b3d-8be7-4d6b-afe2-6bd40a65297c |  | textbox | Position:
text | 01af0182-a438-4f50-877f-71759b91605f |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Sheet Piling (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Sheet Piling (Supply & Installation) Rev 0 | 47fb9f01-8f7e-4d03-9a3f-2a13c1186397
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 89eb6a17-06d4-4659-bf85-988a7a4886a2 |  | note | Document Title: ITP-STR-Sheet Piling (Supply & Installation)
label | c8d40034-3bd4-43d5-9312-174694bdea02 |  | note | ITP Description: Sheet Piling (Supply & Installation)
label | 5fa027a0-1f78-49aa-8737-9c8c237fb75d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ea1db1e3-f531-4fbd-a749-1df8e69455b2 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | b40e9287-eb3c-4bdf-ac0d-c7ddbed93b7a |  | note | Revision Number: 0
label | e322b9cb-18a6-45a1-865e-45748003044d |  | note | Revision Date: 08/02/21
label | 21181af9-b8dc-4230-aded-cc36612b198b |  | note | ITP created by: Mike Freeman
label | d18638bb-fc5b-433e-bfd0-82ea441f2c56 |  | note | 1.1 VicRoads Section 640 October 2013
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Certificate of Compliance
label | e350e8ed-0614-47ca-8786-9a45c0b8a265 |  | note | REFERENCE: 640.03
label | f38c4765-d390-43d8-95fa-ca19d0a6d46e |  | note | ACCEPTANCE CRITERIA: Provide a certificate of compliance from the sheet piling manufacturer confirming that the sheet piles comply with specification 640, inclusive of the interlock seals where applicable.
text | f7cb7e95-dfd1-41f5-8f23-f18d7f2f8f78 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 7f55d996-784b-4d71-82c9-0dd4d73610ee |  | note | METHOD: Document Review
label | bba51025-ea78-4b66-a402-604856617d60 |  | note | FREQUENCY: Once, for each sheet pile manufacturer, prior to commencement of works
label | dc6c6e41-94b7-4e64-afbe-c71ee382ee7a |  | note | CATEGORY: HP
label | 855bebf2-3e66-401f-b403-182d9417fa2b |  | note | RESPONSIBILITY: Nominated Authority
label | a722e1ea-dbc8-4faf-bbbf-ec3dd16a4c39 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 553415ec-538c-40ab-a981-f439fa9e7f20 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Driving Guide, Threader & Driving System
label | 6185e8a1-10e7-4ce4-9993-bfc724efeefe |  | note | REFERENCE: 640.04 (c) & (d)
label | 3a67d319-dd16-44da-aec7-8b2b6de9aa1d |  | note | ACCEPTANCE CRITERIA: Details of the proposed driving guide, sheet pile threader, driving system, installation calculations and helmet and cushion information (where applicable), to be submitted for review to the Nominated Authority.
text | ab4f5869-3740-46ee-b8d7-336e2536bb00 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 57cc4521-73d3-493d-87a9-86cc536d8872 |  | note | METHOD: Document Review
label | ec49dcb5-e8cf-496c-8b06-7c3e1e979fa3 |  | note | FREQUENCY: Once, for each different piece of equipment or system to be utilised, 14 days prior to commencement of works
label | e90a6750-7a46-4f6b-a735-d69bb68e767b |  | note | CATEGORY: WP
label | 0ad7572d-4392-4b3c-8a5e-11481dbaf03b |  | note | RESPONSIBILITY: Nominated Authority
label | 98929fbc-4130-4796-99a2-62a6d385797b |  | note | VERIFYING DOCUMENTS: This ITP
text | d3fb2f68-ad1e-4b85-b726-39ccf5befe43 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Welding Specifications & Qualifications
label | f9a0109e-5a82-443e-9512-00618452b9a7 |  | note | REFERENCE: 640.04 (f)
label | 2421e4a9-ce9f-4619-910a-103a6e3bd625 |  | note | ACCEPTANCE CRITERIA: Where applicable, shear stud welding or welded splices and connections of the sheet piling shall not commence until the welding specification & qualifications have been submitted for review to the Nominated Authority.
text | a04f41cc-2e04-4e10-8431-3280c4495793 |  | textbox | Enter: Teambinder Correspondence Approval number
label | c7d9b787-5331-4d9b-a250-e81d6a610e31 |  | note | METHOD: Document Review
label | 02e01e1c-3e49-425c-b4e4-21d3cc4ee0a1 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | cb9318e2-f823-4cc9-adb1-b0f55dbc1ee5 |  | note | CATEGORY: HP
label | 01d0c947-cdcc-423c-a170-8a792d845f96 |  | note | RESPONSIBILITY: Nominated Authority
label | d664d498-d55c-4ffe-aef6-36f5951a7b53 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 22b5290f-11c4-4720-9ef9-dd5b1c9c6acd |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | ad3fd172-a88b-479d-89e0-26eeb3d71ab5 |  | note | REFERENCE: IFC Drawings
label | 19d57a63-8485-4656-9406-316ac2c0f6e9 |  | note | 640.04 (g) (i)
label | b2b1185c-28a0-4143-a208-73037a52cc64 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±50mm at the sheet pile head.
label | bbda1e32-fb8b-497b-878b-e2ba72d12f4e |  | note | METHOD: Measure , Visual
label | fa98e288-8b9d-4a2e-9d6a-0c7a2a566137 |  | note | FREQUENCY: Each element
label | 6b900d2c-ac89-4209-8887-d8acde5a8005 |  | note | CATEGORY: IP
label | 631217df-0772-4fc5-b62f-5bb9328e4859 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | d7fd9078-052a-4d9b-bbf1-130de2db0da3 |  | note | VERIFYING DOCUMENTS: This ITP
text | f91e95be-c19b-4db7-95fc-04c83d2da9a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Marking Depth Increments
label | 48fad793-2c87-46c9-8ea8-eacac4f46310 |  | note | REFERENCE: 640.04 (b)
label | 4f26d0b9-647b-42e6-9c88-12629e507a5c |  | note | ACCEPTANCE CRITERIA: Sheet piles shall be clearly marked at 500mm intervals from the toe upwards to indicate embedment.
label | 130412f7-e074-494e-a798-0ea0f495d9e2 |  | note | METHOD: Measure , Visual
label | fa4aae8d-c214-4c1e-b5d2-0d03f02d2e4e |  | note | FREQUENCY: Each element
label | 0e21e7dc-81b6-4883-b3e6-b82617c3075c |  | note | CATEGORY: IP
label | 26d0e4d2-9444-4f4b-8262-0cb873e17b69 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f9b22216-c2fc-4875-9363-9590ac8ee11d |  | note | VERIFYING DOCUMENTS: This ITP
text | 2761a6a5-b48a-40b0-98f7-f40b47878a75 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Driving Operations
label | 2899e630-c394-4314-80bc-c705ea4fd42f |  | note | REFERENCE: 640.04 (e)
label | 391ea8f1-338a-481b-acd9-b6b20f19ad21 |  | note | ACCEPTANCE CRITERIA: After commencing driving, each pile shall be checked periodically for verticality, interlocking and to ensure that it is free from damage at least once prior to reaching full embedment.
label | b41dac39-1709-4af8-a599-3fe6de997e85 |  | note | Sheet piles shall be driven to the levels shown on the drawings and care taken not to disturb adjacent piles.
label | 670e5a96-892c-4c96-9b76-de74f1189f60 |  | note | METHOD: Measure , Visual
label | 36da00e8-19f7-4862-b565-47126e076ccf |  | note | FREQUENCY: Each element
label | 7a8dbd09-6de3-4fd4-898d-cf5d590dc8bb |  | note | CATEGORY: HP
label | 8e709fb7-d400-4c7c-9906-3389ff918602 |  | note | RESPONSIBILITY: Nominated Authority
label | 9d4a03ba-5f7d-4cf9-a93d-ac6aa22b401d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c32df479-ab47-425a-96da-8cf8e77090bc |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Trimming of Sheet Piles
label | 850e256b-5451-4460-966e-97e79a0e7d4f |  | note | REFERENCE: 640.04 (f)
label | 84407555-79b1-4ef9-85ad-7c8c744effb4 |  | note | 640.03
label | 2c68c2b9-bc71-45f3-a27c-6e2029ab4979 |  | note | ACCEPTANCE CRITERIA: Where the required depth cannot be achieved, subject to approval, the sheet pile shall be cut off by suitable means such as flame or saw cutting, leaving the end square, straight and free from burrs or imperfections (if not encased in concrete).
label | df1a222a-4de4-45eb-b8e0-1b5d2c7c3949 |  | note | METHOD: Measure , Visual
label | 3c1d28ba-3291-444d-bba4-5774d30a9a8b |  | note | FREQUENCY: Where applicable, each element
label | 0c6027a8-fcb9-40c7-a5d8-7ba1c1b967ca |  | note | CATEGORY: IP
label | 934b9db5-4788-4fdc-8272-4ee32f68ed3b |  | note | RESPONSIBILITY: SE/PE/SPE
label | d6abe02b-aac8-4355-bbd8-0a04ca2a13f7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 89b5f9a7-e38a-4906-97d9-c7d401c122cc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Extension of Sheet Piles
label | edf8eb5f-e646-4d05-99a8-0e02b10fb4d4 |  | note | REFERENCE: 640.04 (f)
label | 50e71e0d-d3b6-43d4-9bf3-5894c2437dcd |  | note | ACCEPTANCE CRITERIA: Where applicable, extending the sheet pile length to achieve the required cut-off RL, shall be conducted by full strength butt welds as per the approved procedures.
label | c3c88b6d-00af-4970-a4ed-ad3204125821 |  | note | METHOD: Measure , Visual
label | ef21641d-fc6f-42f3-8497-ddc253c9c827 |  | note | FREQUENCY: Where applicable, each element
label | 2839cb4f-6b55-4524-a1bd-859e757d34e0 |  | note | CATEGORY: IP
label | f11355b6-034a-49c0-b631-5bdfd8fdf2be |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9146bb91-0058-4163-adc9-e61cf1441a62 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4d5dbcd7-27d2-44a7-bc13-857943454483 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Weep Holes
label | d5d44097-6e28-48a2-8589-74c53cf249bd |  | note | REFERENCE: IFC Drawings
label | cd2cf00b-4984-4ba7-a4ff-0a25a10bf32b |  | note | 640.06 (d)
label | 46dff962-07ea-40a6-84be-d84d5a22ab6c |  | note | ACCEPTANCE CRITERIA: Where applicable, drill 15mmØ weep holes through the centre of the exposed sections of sheet piles at a minimum of 1m x 1m spacing.
label | 5d5a31db-f654-4d1b-9bde-31fd9051018c |  | note | METHOD: Measure , Visual
label | 4682d904-0f03-49c9-a861-2051503b489b |  | note | FREQUENCY: Where applicable, each element
label | ea0c6f2a-b2e0-4097-a6ab-ce28c2173d8f |  | note | CATEGORY: IP
label | 71bfb1df-d0ea-4738-ad59-4eb5c0edbf32 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d4c7c68e-a214-4cd9-b03a-d478791abd40 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5447e9ff-351b-473f-875d-c7e4261b7f45 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Repair of Damage
label | 403735e1-8972-4f4c-a047-c406d0f903c2 |  | note | REFERENCE: 640.04 (a)
label | a8b05e9a-6615-4f46-968f-cb577408c3c2 |  | note | ACCEPTANCE CRITERIA: Where applicable, any damage to the sheet piles shall be repaired to the satisfaction of the Nominated Authority.
label | a8eb41d4-3f7d-4668-8d11-cebc6d3ed514 |  | note | Any repairs that do not meet this requirement shall be replaced.
label | 0c3b1b19-9103-47ad-a70f-7c2862f59161 |  | note | METHOD: Visual
label | 37ca2df4-c17c-4613-8618-47e4eb09b50e |  | note | FREQUENCY: Where applicable, any damage shall be repaired by suitable means
label | 2621ded0-f748-4182-ba95-49650d071dec |  | note | CATEGORY: IP
label | 03092301-f2b2-41c5-9951-042322295e59 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b27e2ed1-9d32-4e93-8d57-282cb7e1b005 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0cb97dba-17a8-4a9d-a28c-221e1c33da75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 As-built Survey
label | 4f2c0c7f-1767-433c-8c2e-7ced847d88cd |  | note | REFERENCE: IFC Drawings
label | cd2a7e6f-225d-4832-9127-09b1eef6c30a |  | note | 640.04 (g) (i) & (ii)
label | 04b37b1a-c286-4750-ab06-c631fa5bf337 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that the installed elements comply with the following:
label | 29a542f2-52f2-4b2e-9fd4-2297beff29c8 |  | note | i. Deviation of plan location at pile head = ±50mm
label | 057d36ab-80c8-4a2d-8b14-ea284def498c |  | note | ii. Deviation from vertical = 5mm/m of sheet pile length
label | d483ca8f-ab07-42b5-b63b-e6bbac8836ee |  | note | Attach: Survey As-builts / Survey Report
label | 98cd9a01-671f-485c-b6b9-d1f3bc01ca3b |  | note | METHOD: Document Review
label | 0763d3cf-ee02-4e92-9dc8-43596c73511f |  | note | FREQUENCY: Each element
label | 0d79b74b-6c33-4c95-b478-754a3eae632a |  | note | CATEGORY: IP
label | ce415521-a347-4576-931d-f133b7677502 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 61d51072-3dad-4ac9-9adc-0a30f8095c9c |  | note | VERIFYING DOCUMENTS: This ITP
text | 58886459-0aa7-48dd-b7d7-82fafc8ee8ff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Non-conformance Report (NCR) Closure
label | f35da236-848d-4cf1-bbf1-a1a0f327422c |  | note | REFERENCE: MRPA Quality Management Plan
label | 4be9dffb-82a8-4b2c-9a5c-740e53d86432 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | a71eea01-d32a-4872-ad28-c797f07a674b |  | note | METHOD: Document Review
label | 13c678d6-3a4e-4da2-aedb-ce7e63777fc1 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 9eb8dd6a-3edf-49dd-a4b0-b75fd4d75948 |  | note | CATEGORY: HP*
label | 495c0cff-1e26-404b-9c9d-9ae0fc4f6821 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 60ef4a46-d7db-4051-86c5-6d564b29591f |  | note | VERIFYING DOCUMENTS: This ITP
text | 21d213f2-9d37-49ea-a124-02baa54ef5d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | e1f3e573-315e-414e-9296-98c6c20687b7 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 2a6f5c53-526a-4484-9ea2-57db1679fb6f |  | textbox | Name:
text | ed8576e4-ddea-409f-9f8e-42aa061182ce |  | textbox | Position:
text | f258b5a9-c68a-44f9-9b30-68759001b0c3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Traffic Signals - Civils (Supply and Install) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Traffic Signals - Civils (Supply and Install) Rev 0 | 4ccb6592-9a77-457b-a3fd-601cbc6a6dc2
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 85a2d204-0079-4387-a8a2-2bb8a6ed8560 |  | note | Document Title: ITP-CIV Traffic Signals - Civils (Supply and Install)
label | 2fd30022-efcd-450d-9d84-defb50a6771a |  | note | ITP Description: Traffic Signals - Civils (Supply and Install)
label | cd1c301d-1ef8-4f71-9e30-d0e12884fb63 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 6d4080e3-faed-4583-b46f-eaef42e8df16 |  | note | Revision Number: 0
label | ff5e3e1e-e5e3-4731-9564-8b0c403c2483 |  | note | Revision Date: 20/08/2020
label | e7ab2282-b0de-47ee-9f43-7b84f16b880c |  | note | ITP created by: Saaf El-Zubaidi
label | f9ba6508-2fbf-4c59-9a65-fec48b3f2f76 |  | note | ITP approved for use by: Josie Pavlou
label | ba54eaf8-4985-4cb3-9e09-f32916268bd1 |  | note | 1.1 VicRoads Section 730 October 2013
label | 0c77de47-4510-42f9-a4fb-77eeea4339e7 |  | note | 1.2 AS3000
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Vic Roads Site Plan
label | 725bdad7-dc06-40a0-a077-89d1e77413e0 |  | note | REFERENCE: Table 730.041
label | f7ecd3cc-7dbd-4d2f-b603-ae8e2e0a2d6e |  | note | ---------------------------------
label | 2c513aed-75f1-42c7-beae-f7ce2c66e6cc |  | note | ACCEPTANCE CRITERIA: Scope of works, equipment requirements and placement of equipment shall be as shown on the VicRoads Site Plan
label | 207f2de9-8ce8-4f34-8670-f1b81f1f0999 |  | note | ---------------------------------
label | 5feb120a-3d48-4fed-bcde-1482463ac925 |  | note | METHOD: Review Document
label | 5abe25f3-d494-4a6e-a044-af8ad746e937 |  | note | ---------------------------------
label | 4dca5d63-6ffc-44ae-a201-a8a8f2f0d9f8 |  | note | FREQUENCY: Prior to commencement
label | 425f2714-890a-4c16-9171-fb92d5ff1df8 |  | note | ---------------------------------
label | 4468ff84-c398-4961-8820-23d46b2bb708 |  | note | CATEGORY: IP
label | 882209e0-b38d-42ab-9b2a-9b2dcc4214dd |  | note | ---------------------------------
label | 13612ff4-3e56-4d1d-969a-2544b3d498a1 |  | note | RESPONSIBILITY: SE
label | d771b3a3-8f70-4df6-929c-47804c2e526d |  | note | ---------------------------------
label | 3e630d0e-1502-41dd-b554-db6381b6275b |  | note | VERIFYING DOCUMENTS: Attach: VicRoads Site Plan
text | 5a46f1e1-2e05-4c30-be72-10b9b0eaa1d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Subcontractor Prequalification
label | e2fd59db-94e0-4c34-bdb0-cf53ea89ab2e |  | note | REFERENCE: Section 730.01 (c)
label | d2ca0be8-1bdc-43c0-927a-eec6fe954e34 |  | note | ---------------------------------
label | 0badcd1b-978b-40c6-bb34-10de3aacb7dd |  | note | ACCEPTANCE CRITERIA: All works associated with the installation and commissioning or remodel of traffic signals shall be undertaken only by contractors that are pre-qualified at the STS level under the VicRoads contractor pre-qualification scheme.
label | a817075b-678b-405f-847d-f404e7f58145 |  | note | ---------------------------------
label | 885732a4-e514-4490-8e9a-dffc78ba3f89 |  | note | METHOD: Review Document
label | 876e3451-7533-4bd2-9ac0-953e681a8551 |  | note | ---------------------------------
label | 6deb2f85-8d8f-4d81-811e-e6759d769d1d |  | note | FREQUENCY: Prior to commencement
label | e0107a73-82a6-4c57-97b9-178139aaef5a |  | note | ---------------------------------
label | 8efb7501-2544-4b4f-8f93-c2311e7d8da7 |  | note | CATEGORY: IP
label | 159c84ac-ad3a-40a1-8e02-e7ba1a27449b |  | note | ---------------------------------
label | b3afe0cf-ca01-453a-9ee9-f0626ccfef69 |  | note | RESPONSIBILITY: PE
label | 82cb4c1c-f1da-48ed-a005-3953d4b8914d |  | note | ---------------------------------
label | 22782fa9-e876-444d-bae9-a793c763078c |  | note | VERIFYING DOCUMENTS: Attach Subcontractor Prequalification Certificate
text | 9ad93b95-906f-4635-8ead-f2e997c8b0bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Material Fabrication and Supply - Traffic Signal Hardware
label | 9bd4a760-264d-440a-ba80-22cdbd68ac5b |  | note | REFERENCE: Section 730.05
label | ea4f5147-48ec-41ef-b398-17fac0848732 |  | note | ---------------------------------
label | e289fcfd-763a-4ef5-9fb0-46d9f2aea3e3 |  | note | ACCEPTANCE CRITERIA: The fabrication and supply of all components for traffic signal works shall conform to all relevant VR Specs and Aus. Standards.
label | 8c159a40-2900-4fb0-a9fb-2b635aab14bc |  | note | To comply with: VR 'TCS' series specs, VR 'TC' series specs, AS1742, AS/NZS3000 and Victorian Service and Installation Rules.
label | dfe9281d-3125-48cf-b174-d3e1bd1cb50a |  | note | ---------------------------------
label | 38fdc91d-6db3-4088-81f9-0da71e1d51c0 |  | note | METHOD: Review Document
label | eb508f91-82aa-42cd-af1a-6d168a9fb717 |  | note | ---------------------------------
label | b64ffd30-9181-4d60-b71c-cbf42b5efada |  | note | FREQUENCY: Prior to commencement
label | 3a1c5b3b-1518-43e3-a24c-77f7a1344f06 |  | note | ---------------------------------
label | c95bbda3-8434-4f12-925d-d72fd41281e0 |  | note | CATEGORY: IP
label | 3ea230ff-14cc-4227-a5e3-cd8bb812f8ba |  | note | ---------------------------------
label | 061b7286-195e-4e82-8f25-5ffcc5f72121 |  | note | RESPONSIBILITY: PE
label | e9d373aa-01e9-43ce-8bea-2ab476996719 |  | note | ---------------------------------
label | 1dccb7e1-7afd-4f40-8934-f7bd43782593 |  | note | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificates
text | 7cb3ea0f-789b-4382-bd75-7edbf2b1ff37 |  | textbox | TB Material Approval No.
text | 60536538-2c2f-4def-9408-d7776f7894f4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Equipment to be supplied by VicRoads
label | 0b1e065e-b46b-4316-aab7-b8ff475876cd |  | note | REFERENCE: Section 730.06
label | 855f1940-7f36-4cf8-9d45-3074469611af |  | note | ---------------------------------
label | 278ffdce-dd2a-446a-b595-bd52e3e26b02 |  | note | ACCEPTANCE CRITERIA: VicRoads will supply or arrange for the supply of the following items:
label | e7f6a648-942a-44a8-ad0d-a0b84b6451a5 |  | note | (a) the traffic signal controller and associated vehicle detector units
label | 8771944d-7fac-49f6-bef8-960e67edc9e9 |  | note | (b) communication devices, such as Dial-IP modems
label | b4f5bd10-916f-469f-8d73-456e15aed0b0 |  | note | (c) ‘DUSC’ units.
label | b7a2a754-66c2-41c7-99f3-78f6e93f539e |  | note | Contractor to provide VR a list of materials at least 20no. working days before delivery is required.
label | 70c94580-c93b-4688-8ad1-fd352a738021 |  | note | ---------------------------------
label | a77184a4-aa2a-4476-9d93-4dacbc51803b |  | note | METHOD: Review
label | 49d86cc2-766e-4dae-8852-5ae613d5d965 |  | note | ---------------------------------
label | ca7c1e09-638c-408b-a9f5-12897cf41d4d |  | note | FREQUENCY: Once
label | fe52f2bc-a8be-43bc-8816-5c47b742eb0d |  | note | ---------------------------------
label | 4774a7f2-dd75-43f8-bbe0-eea3d272f12d |  | note | CATEGORY: IP
label | c980ef70-de7d-4066-81e5-b587bc229e50 |  | note | ---------------------------------
label | c6997f9a-43b0-4a15-b195-ceeccb3d9e88 |  | note | RESPONSIBILITY: PE
label | dccccccf-bc0e-4965-9225-7e777c7f8205 |  | note | ---------------------------------
label | 8ed972aa-3c2d-40c6-b1dc-329c653bc7b0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1fa97c4d-d34c-4e1e-bfd8-cc3289ded0f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Equipment to be supplied by the Contractor
label | f233d197-bdff-4094-9ebd-1e31a0624dfe |  | note | REFERENCE: Section 730.07
label | 2c2a78e6-07a2-413c-a35a-5e86aab3043b |  | note | ---------------------------------
label | 39059e14-2248-442a-8342-d316881d77e6 |  | note | ACCEPTANCE CRITERIA: Contractor shall be responsible for the supply of all equipment, items and peripherals required for the completion of the works.
label | b5e11ffd-5da1-44e3-9a93-bdc9875dc740 |  | note | Where applicable, all equipment proposed for use shall hold current VicRoads ‘Type Approval’ certification or Product Acceptance. Refer to Item 2.3.
label | 82210f75-2650-44e6-a19c-069a89b8957e |  | note | All equipment, materials and fittings supplied by the Contractor are to be new. Contractor to ensure equipment used is compactible with all equipment.
label | 02ec6ecc-0507-47be-bfb2-37b22326d518 |  | note | ---------------------------------
label | 5c065e95-232d-4fb7-afe9-8a62d643a9d2 |  | note | METHOD: Review
label | fcd36a98-6029-4d08-aea7-3c9c7a1e5a7c |  | note | ---------------------------------
label | f86f6870-47a9-4a04-83ac-3a7bd2f44b6e |  | note | FREQUENCY: Once
label | 6e382238-bf13-478f-8c4d-7e769afb57ed |  | note | ---------------------------------
label | 6ea2cc20-3a23-4ead-83bf-7fde5ab3de7e |  | note | CATEGORY: IP
label | 4474ab0a-8e58-40e3-b8af-b37b1c65acc5 |  | note | ---------------------------------
label | 710b83b0-04d4-4b15-9ec4-3aa93ce1ed34 |  | note | RESPONSIBILITY: PE
label | a4af89a7-de45-4c28-bb9f-8b0d08bd7912 |  | note | ---------------------------------
label | bd1df1a8-3be5-4012-ad46-55781e8916b3 |  | note | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificates
text | e8be9658-656c-4a8d-811b-8b680ee9247d |  | textbox | TB Material Approval No.
text | ee69a01f-da62-44e5-abf6-3acd115975bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Concrete Mix
label | 2c9459c2-bf0b-43d2-a533-f32a48862d4c |  | note | REFERENCE: Section 730.12 a)
label | 23254370-c433-489f-ae9d-89fa7fbbb7e7 |  | note | ---------------------------------
label | 6ccdfd9c-d9d3-40f6-a6c1-7cee7ce6098f |  | note | ACCEPTANCE CRITERIA: Concrete shall comply with AS1379.
label | ae7bed33-9bd6-45d9-9006-332c533f49b9 |  | note | Concrete grade to be as per relevant Vic Road Standard Drawings.
label | 09a55f6e-fd17-49a6-8306-20c4475f2162 |  | note | ---------------------------------
label | 0bcb3240-3332-45ac-a96f-15882f9e5bc0 |  | note | METHOD: Review Document
label | 05513895-eaf7-45e8-b7d4-4db27a95aecd |  | note | ---------------------------------
label | b8625237-9190-4679-87dd-86104ba702f3 |  | note | FREQUENCY: Prior to commencement
label | 422e6abe-cc99-4d97-9407-9f1ac8c431b4 |  | note | ---------------------------------
label | dc81de39-1642-480e-a7b2-95dad8145be3 |  | note | CATEGORY: IP
label | f3845176-8623-4db2-a7dd-43665bbdeef7 |  | note | ---------------------------------
label | 385c686e-2314-4c4b-88fa-9ffe40bf3216 |  | note | RESPONSIBILITY: PE
label | 61cc52f4-70d6-4450-b986-a53084833eba |  | note | ---------------------------------
label | 6a5f354e-3ab2-4c94-a15d-072e07a00217 |  | note | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificate
text | 746516ce-043e-4793-942e-9fff19770411 |  | textbox | TB Material Approval No.
text | 5071ee54-ff25-4e11-b6f2-40cd6882c52f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Material Fabrication and Supply - Electrical components
label | 37853252-38a2-4ef2-ae45-906f4f77ee44 |  | note | REFERENCE: Section 730.14
label | bbab4f00-148d-4108-9671-78a14a7489ac |  | note | ---------------------------------
label | 79aeeb3e-61b2-4c5d-98b0-a27c4667c40b |  | note | ACCEPTANCE CRITERIA: All electrical works, conduits, fittings, materials and installations shall comply with the requirements of AS/NZS 3000 Wiring Rules for all traffic signal related works.
label | b7404c93-b212-40a5-826a-4f65b377fe9c |  | note | ---------------------------------
label | 819d6748-3587-4254-9136-e93da4043e5b |  | note | METHOD: Review Document
label | 9b636370-1fad-4af6-9662-ac1259a7e24f |  | note | ---------------------------------
label | 5c77e7ac-9cb9-4cd7-afc4-6365df824535 |  | note | FREQUENCY: Prior to commencement
label | cbf2c483-630f-418b-876f-bb33c8f5872e |  | note | ---------------------------------
label | 33384e32-0fec-4ed5-b2f8-fa97f7681c90 |  | note | CATEGORY: IP
label | eb510a08-5058-4657-9521-2142e5c24f40 |  | note | ---------------------------------
label | b2852b70-60ef-4898-8803-f3d391acc5eb |  | note | RESPONSIBILITY: PE
label | ca22d812-81b2-4eb0-b845-c5f5c026e634 |  | note | ---------------------------------
label | dbadcee0-50d0-436b-bcff-e663c8ceefbf |  | note | VERIFYING DOCUMENTS: Issue to TB and Attach Material Certificate
text | d01296c6-7291-4c22-95f7-20c4584c3a38 |  | textbox | TB Material Approval No.
text | d5d03b26-fd3a-4640-9296-c83bf772e06d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Pre-Installation Meeting
label | c07a9dc8-f366-48fe-9a35-12332017cdb9 |  | note | REFERENCE: Section 730.08 (b)
label | a86f85e2-22a5-47a8-b4f0-a843b9e5a0ab |  | note | ---------------------------------
label | f64138f6-33ac-416d-a3cc-20843101963a |  | note | ACCEPTANCE CRITERIA: The Contractor shall mark the position of pedestals, poles, controller bases, pits and conduits in accordance with the drawings, in the presence of and with the approval of the Nominated Authority, Vic Roads, service authority and others as appropriate.
label | d2014731-5c12-4dcc-9a68-fea30d4e29aa |  | note | On satisfactory completion of the pre-installation meeting, the Superintendent will issue to the Contractor a copy of the Pre-Installation Report.
label | 784f43ca-b9d7-4a1c-ae7e-629770f87651 |  | note | The Contractor shall not commence installation of the traffic signal pedestals, poles, controller bases or pits until the Pre-Installation Report has been approved.
label | ce41d563-9761-467d-b756-fd79aff63014 |  | note | ---------------------------------
label | 28f9bb53-05e1-43e5-b330-d602ac3d95b4 |  | note | METHOD: Records
label | a892876c-d8c6-4b09-b0bc-4ec5157bd0d5 |  | note | ---------------------------------
label | f8cfd8b7-2f5f-416a-87ed-6a2a60e878c5 |  | note | FREQUENCY: Prior to commencement
label | d4c939ce-dcbf-4294-8148-c1db3973d8a0 |  | note | ---------------------------------
label | 25c6e510-fc46-470a-82ab-822a810491c9 |  | note | CATEGORY: HP*
label | 82b87ef7-a5a1-4002-935f-ab24b4bb635b |  | note | ---------------------------------
label | 7e6d90a8-4cf2-4f8d-83a1-6de1e849b7a5 |  | note | RESPONSIBILITY: PE, NA and VR Representative
label | 72b9f583-ec66-429e-8527-feef9639802a |  | note | ---------------------------------
label | a60849e6-7a5d-4d8f-ade5-cdfa9f1334c7 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Pre-Installation Report
text | 2fecda87-86cf-4f1f-9f1c-ce8c18b9b8b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Service Proving prior to commence of new works
label | 44bf34e3-abe8-4cd1-b85a-b3ae70d3939d |  | note | REFERENCE: Section 730.09 (a)
label | e9e03bab-8383-46e0-8c3f-0d615f0416e8 |  | note | ---------------------------------
label | 645f360a-15b9-4708-a3a5-8dee3061fd70 |  | note | ACCEPTANCE CRITERIA: The Contractor shall be responsible for locating and proving all underground and overhead services. Any consultation with, and authorisation required from, other authorities under relevant utility regulations and codes shall be the responsibility of the Contractor.
label | adf4f59b-431b-4cc8-9bfa-0a095a31e6dd |  | note | ---------------------------------
label | 59076039-dcae-4401-a459-48c92cde3fd0 |  | note | METHOD: Review
label | e0d52d3e-0738-4cc1-8e96-82ce08f7652c |  | note | ---------------------------------
label | d386506f-c8a1-4bd9-9d2b-0d1a224fe29b |  | note | FREQUENCY: Prior to commencement
label | c7d79855-8826-461f-b02f-34b687ee121e |  | note | ---------------------------------
label | cc2766c2-6a10-4c1a-9c50-6e9f96b86d6e |  | note | CATEGORY: IP
label | a417a3ff-cebd-492c-b655-1bf6797f2260 |  | note | ---------------------------------
label | da7b758b-19d7-4b04-ad93-674f5cfda0ef |  | note | RESPONSIBILITY: SE
label | 63a3eecc-93f8-4a21-8e46-22b627696677 |  | note | ---------------------------------
label | b382a3d9-45ec-4ee9-bee5-ad62a33309c6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b3d0f70-101f-4f74-984d-1d36ac80ff02 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Survey Set-Out
label | 907ddcff-db30-49f1-9f86-9681528a5a39 |  | note | REFERENCE: IFC Drawings
label | c1ed545a-bfcf-4f2b-b4c7-06ce726b7b3d |  | note | Works Agreement
label | b01fe44a-bd48-430f-858f-a435d74ef5fe |  | note | Section 730.11
label | 18cd7563-30f6-4693-a31d-0b5c1dc9b37c |  | note | ---------------------------------
label | e6819c97-da71-4cca-adca-404c05ae374d |  | note | ACCEPTANCE CRITERIA: Survey to mark out works as per IFC Drawing.
label | 94e64f03-7ee3-4b71-ad96-55c5597850ac |  | note | As per Item 3.1 VR to inspect the set out of Pits and Conduits for Traffic Signals prior to commencement of works.
label | 3f7231c1-b47f-4ff7-a0ba-c8111e6dd99c |  | note | No part of the signal hardware is to be closer than 500 mm behind the face of the nearest kerb line, or closest vehicle path if no kerb is present. the minimum clearance of 5.5 m shall be achieved between the lowest part of a lantern installed on an outreach and the roadway directly beneath it.
label | 828cd7b7-3908-4635-a409-b011ae82e97d |  | note | ---------------------------------
label | 57a5c572-2bde-41a0-af9b-283e7d83d87a |  | note | METHOD: Visual
label | 281cb4c2-d7eb-49c2-bbc2-d9608a5aa377 |  | note | ---------------------------------
label | 0c0fe5e6-6cf6-454e-874d-f82d012058a0 |  | note | FREQUENCY: Each item
label | 34e4010a-f23e-47b2-8b87-42d4d1e9fb62 |  | note | ---------------------------------
label | 67cd900b-6b53-48dd-9a96-18ab9c53c0eb |  | note | CATEGORY: HP
label | 7051ae8b-f81b-4f1e-ad08-95760472b0fb |  | note | ---------------------------------
label | c52d326e-d39d-4120-b621-9d7328591f2a |  | note | RESPONSIBILITY: Surveyor SE, VR
label | d9e039f5-175e-4fdd-b639-83a49c506eff |  | note | ---------------------------------
label | 9e7172e7-d73e-4a78-96d7-ba1f5ef92584 |  | note | VERIFYING DOCUMENTS: This ITP
text | f5f53ed2-6b3d-47d2-9379-8004c68500a6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Material Inspection
label | 8e03ee11-bb84-4e2b-8eb8-3a341c49d49f |  | note | REFERENCE: Design Drawings
label | 9aaf6d6c-f2e1-43fe-abbf-f3aa64a1b9dc |  | note | 730.05
label | b2160234-b2e2-4ef8-b386-65603035ab49 |  | note | ---------------------------------
label | c17b3b13-12d2-4339-9a28-1b8644b3d36e |  | note | ACCEPTANCE CRITERIA: Supplied items are:
label | 079c126e-fbaf-47d1-9825-ed6c8b9a84ed |  | note | - To correct spec, class, size and quantity
label | 196466e6-e6d2-4b04-89fd-de3271edfd3a |  | note | - Defect free, safely and securely stored
label | 392fdff9-6db3-49f2-afb6-1bfcc0aed538 |  | note | ---------------------------------
label | c02f88fa-4023-4476-bb70-1ab941f77e5d |  | note | METHOD: Records
label | 64440483-049f-4259-a972-2dda6b093371 |  | note | ---------------------------------
label | 190ed5d6-dd7e-430d-b525-55c81b71000e |  | note | FREQUENCY: Per Delivery
label | 6e4ec159-d5ae-418e-b3ed-abddc992b53a |  | note | ---------------------------------
label | 8ae99ef2-60d3-432f-9413-b2819cc8e398 |  | note | CATEGORY: IP
label | 9377b3f0-d327-4b24-91cb-9cb9687bff50 |  | note | ---------------------------------
label | a1dbdf39-8fde-49dc-b351-6abea0322bb4 |  | note | RESPONSIBILITY: SE
label | 6ebb031a-5638-41cf-8da6-07617e9d4eb3 |  | note | ---------------------------------
label | ed607dbd-5efc-48ad-a098-3ed292d17aa1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8d4a3c6a-c5de-4c48-810c-36f0799f2fcf |  | textbox | Date Completed:
checkpoint-group |  |  | section | Traffic Signal Civil Works
checkpoint-status |  |  | checkpoint | 4.1 Conduit Installation
label | 68475979-40d1-4a37-9654-905cef04eed8 |  | note | REFERENCE: Section 730.09
label | dbe263ea-9fc7-4bba-9e64-c5e6c6043a36 |  | note | Specification 733
label | 09c23b92-142b-4a06-a795-0ade6b51ca27 |  | note | ITP-CIV Conduit and Pit (Roads)
label | 07638194-9e81-40cd-8b83-95dfa0eeb5ad |  | note | ---------------------------------
label | c501071e-66ce-4463-8910-e2715011648c |  | note | ACCEPTANCE CRITERIA: All electrical conduit installation works for traffic signals must be carried out by, or under the direct supervision of, a VicRoads pre-qualified traffic signal Contractor and in accordance with the requirements of Energy Safe Victoria.
label | f8f634a0-274b-4ded-b17b-231f5ae3efce |  | note | All communication conduit installation works are to be carried out under the ‘on site’ supervision of a licensed cabler.
label | 7b9a40ab-b2ba-4307-94d1-0351f91c24f7 |  | note | ---------------------------------
label | f5b61d73-cb4b-4e0a-a82b-777a22b7a3a6 |  | note | METHOD: Review Document
label | 6ef99096-bee7-4527-a2e2-0973ae446db8 |  | note | ---------------------------------
label | 2119bb57-1611-4821-9a15-ee8e2140d88b |  | note | FREQUENCY: Prior to commencement
label | 35838ada-431e-40ff-81d9-c448808152b8 |  | note | ---------------------------------
label | a4e86943-e522-46f8-b305-c1d76bc4be98 |  | note | CATEGORY: IP
label | 5cffc589-2262-49da-a74b-133ce5796a55 |  | note | ---------------------------------
label | 4a7bf2c8-220f-4a61-8735-30511061234f |  | note | RESPONSIBILITY: SE
label | d30dccf7-e84f-49cc-ba2c-0919b5f1e083 |  | note | ---------------------------------
label | 42ee3a1d-caf2-4319-b23e-c3c5481b4fb4 |  | note | VERIFYING DOCUMENTS: Attach Subcontractor Prequal Documentation
text | 2c008f54-7681-4bc0-b739-fe27ac980f49 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pit Installation
label | 297a1658-0673-48b8-ac6d-9d811682de4c |  | note | REFERENCE: Section 730.09
label | 872645bd-85be-4ff7-8cd1-145d305488bf |  | note | Specification 733
label | 13d2f649-86c8-4758-9ced-30bb921382c6 |  | note | ITP-CIV Conduit and Pit (Roads)
label | a092090c-24ad-411f-9fa4-f8196ae18a2a |  | note | ---------------------------------
label | 8d691794-dd5a-4f72-aaef-24eed69e4c40 |  | note | ACCEPTANCE CRITERIA: All cable pit installation works for traffic signals must be carried out by, or under the direct supervision of a VicRoads pre-qualified traffic signal Contractor and in accordance with the requirements of Energy Safe Victoria.
label | 19c0ee99-5948-4ddd-88e2-fa895316150d |  | note | ---------------------------------
label | 3d35c58c-36e7-41ad-b673-a42424c1c319 |  | note | METHOD: Visual
label | aac92e09-c557-407f-896c-bc5a36fff6a8 |  | note | ---------------------------------
label | 1d585f42-6b6b-4359-8e97-f0c225336dc6 |  | note | FREQUENCY: Prior to commencement
label | f0995c6d-c185-450c-9b18-0be547b70088 |  | note | ---------------------------------
label | 045a4cd2-1a0f-46d8-ac08-4e21538dabea |  | note | CATEGORY: IP
label | 5e2fc334-bfb6-45d2-b605-f90072c16830 |  | note | ---------------------------------
label | 22b23e7b-874e-4b00-bb3f-861541b69b2e |  | note | RESPONSIBILITY: SE
label | 11910933-0443-4b05-9879-0889b3e47853 |  | note | ---------------------------------
label | 3df6628e-2bec-45a2-a588-6e704218d041 |  | note | VERIFYING DOCUMENTS: Attach Subcontractor Prequal Documentation
text | 24f89249-4f11-419a-bf8c-35d58ed094b5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Foundations
label | ab4904bd-79bc-46b2-be87-b2bf0ce4811c |  | note | REFERENCE: Section 730.11
label | 6f3a7fa2-33a4-4de1-b988-416d5fd380a9 |  | note | Design Drawings
label | 9b65b780-b9c9-43af-a112-18fe3b776f79 |  | note | ---------------------------------
label | 2f414523-e4b8-4e3e-8eb4-3c07d171138a |  | note | ACCEPTANCE CRITERIA: Foundations shall be constructed in accordance with the drawings and as approved at the Pre-Installation Meeting.
label | 864f1eb7-7706-4345-ad49-1c9c274a9198 |  | note | Foundations and footings shall be as specified in the VicRoads Standard Drawings for the specific item of equipment they are to support, as listed in Table 730.111. The standard foundation for an MA, JUMA and JUP shall be a bored pile.
label | b89ca533-607c-4817-bcf7-cead22060025 |  | note | ---------------------------------
label | 3589b6f1-3507-4d6f-b0b4-faf7a2f2a678 |  | note | METHOD: Visual
label | b148d4f1-76d9-4927-bf7e-8845f30e5d1a |  | note | ---------------------------------
label | 6831e073-5c0f-421e-9742-f7e78bfe22cd |  | note | FREQUENCY: Prior to commencement
label | 1f3c8f10-4110-47bc-b8e1-2cb688b67139 |  | note | ---------------------------------
label | 00478fba-4b05-40ce-bcee-c9031cb529ed |  | note | CATEGORY: IP
label | 3fc82b2f-97a4-4674-9266-7d3446053066 |  | note | ---------------------------------
label | 35eca352-4f32-4134-93b8-eaf75d63ea0b |  | note | RESPONSIBILITY: SE
label | 96d0d4d1-5fde-47a3-93a4-01787378ecd4 |  | note | ---------------------------------
label | e289cc74-665b-47c3-a5dd-69927f77ab1b |  | note | VERIFYING DOCUMENTS: This ITP
text | 0f5d11c5-6aa5-41c8-9a03-4113e027e481 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Inspection of civil works
label | 6e1bade6-cba5-416f-8072-f268f2282ad6 |  | note | REFERENCE: Section 730.11
label | 9deb1b8b-a053-49d4-a1ae-753049a51788 |  | note | ---------------------------------
label | b81d97e5-3b11-4d7a-aaa7-286001a36987 |  | note | ACCEPTANCE CRITERIA: All conduit, pit and foundation works shall be inspected by the Nominated Authority and Vic Roads prior to the Contractor covering the works.
label | 59db6ffc-7b67-480e-9d27-d17dabbb134f |  | note | ---------------------------------
label | 9415e8b4-9559-4ed9-92df-cfed43795c5c |  | note | METHOD: Visual
label | 0bded0ad-5b42-4eb0-aa77-ba529634d81e |  | note | ---------------------------------
label | 92cdc1ef-50c7-4a1f-8028-93752992fbdc |  | note | FREQUENCY: Per lot
label | d156508b-a5e9-4e56-b3dd-1bba9d6dfed0 |  | note | ---------------------------------
label | 94f43ac4-5bc1-43ee-8d7d-2806f629362c |  | note | CATEGORY: HP*
label | 59a90235-c808-4035-b95d-cc1317dc71b8 |  | note | ---------------------------------
label | 10662368-8f63-4111-b205-9e718116b23b |  | note | RESPONSIBILITY: SE, NA and Vic Roads Representative
label | dd6cfe9e-0022-4f7a-ade8-49e67d5b18a4 |  | note | ---------------------------------
label | 19a4c0b9-5a83-4439-9958-ac9abd186404 |  | note | VERIFYING DOCUMENTS: This ITP
text | b181c7f1-a4f6-4fae-8763-c580f9e098e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Concrete Placement
label | f0df81d5-901a-429f-9334-328fbc81e996 |  | note | REFERENCE: Section 730.12 b)
label | 05a5ce22-f6db-403c-9e0d-6383ae7f5fa4 |  | note | AS1012
label | f46a952d-88b0-4e26-a2d3-40f7e4624f60 |  | note | AS1379
label | 4bbc1380-e14a-49d9-b66d-98dd877f8b45 |  | note | ITP-CIV Bored Pile
label | ed9c860a-8fdd-45ad-81d4-d20c0193b303 |  | note | ---------------------------------
label | dfaadc71-2f37-47c9-aaa1-c74a79fcb92c |  | note | ACCEPTANCE CRITERIA: Where concrete is placed in a bore hole, it shall be compacted with immersion type, high frequency vibrators.
label | 433ca9ef-6948-4f3e-a734-172ce2486912 |  | note | Concrete shall be placed through a tremie tube, shall not be dropped from a height greater than 2 m and shall be guided away from reinforcement.
label | de797a6f-60a5-4b5d-a00b-d82eff914742 |  | note | ---------------------------------
label | 00ca0583-39fd-42a7-b9b6-0aa37e563213 |  | note | METHOD: Visual
label | c151f839-97d4-427b-bcf9-7d100f4462b1 |  | note | ---------------------------------
label | 09671442-f5e5-491b-abd6-bc3416a87576 |  | note | FREQUENCY: Per lot
label | 01895fbf-0e36-4a92-a16f-cca930972439 |  | note | ---------------------------------
label | 5ae67ddc-f997-4932-bcbc-f804b202bdf1 |  | note | CATEGORY: IP
label | 8c51cab1-9b32-4a11-b6af-6204dbc92de8 |  | note | ---------------------------------
label | 734e9e46-3c21-40ee-a68d-55206c6d0e1f |  | note | RESPONSIBILITY: SE
label | fe2f1a3d-c631-41fd-8a93-12db38ae93c8 |  | note | ---------------------------------
label | 958fd91b-f5c8-43be-b7cf-c15af7380167 |  | note | VERIFYING DOCUMENTS: Attach Concrete Dockets Attach Bored Pile ITP
text | cc8721d3-6d7f-44de-aac6-f67c9c08a138 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Concrete Testing
label | 0573cec2-bf55-4db1-90b4-e9230c72f01c |  | note | REFERENCE: Section 730.12 c) & d)
label | 5b383495-0352-493a-ae27-0ffc8ff07ee1 |  | note | ---------------------------------
label | c5b9cb16-21c4-46e2-b256-fa82c091ae58 |  | note | ACCEPTANCE CRITERIA: All grade 32MPa concrete shall be sampled and tested in accordance with AS 1012 and AS 1379.
label | 31d29ea4-b612-4561-afdc-a8578e856679 |  | note | 1no. cylinder to be tested at 7 day and 2no. Cylinders to be tested at 28 days.
label | 4354e403-a637-44fc-87e7-3e50528cf10e |  | note | ---------------------------------
label | 6929985f-7403-4af3-a19a-5eca97d4bff0 |  | note | METHOD: Review Document
label | 4249bf86-3540-4ee1-b25c-930de4b58971 |  | note | ---------------------------------
label | 04f1482e-fc33-49f0-9403-764fcf55b415 |  | note | FREQUENCY: Per lot
label | b3dda78e-55d9-43fb-93d6-1d00ad8b32b4 |  | note | ---------------------------------
label | c92edd1c-abed-4bd8-8f64-f9cb24403d19 |  | note | CATEGORY: IP
label | e92d1451-37c0-4cc0-94ef-dccebef4fc34 |  | note | ---------------------------------
label | b123f828-89dd-4680-badb-0a4df96b3194 |  | note | RESPONSIBILITY: SE
label | d1dba3b0-ddb9-403a-b44d-6ea6b22168f6 |  | note | ---------------------------------
label | 5a268262-7d2a-494e-8007-708d35161416 |  | note | VERIFYING DOCUMENTS: Attach Concrete Test Report
text | 1bcc7297-6ba0-4998-b4e6-aee753322c41 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Traffic Signal Hardware
checkpoint-status |  |  | checkpoint | 5.1 Standing of Pedestals and Poles
label | 46ac931c-298d-45a7-ab5f-c6c28800b271 |  | note | REFERENCE: Section 730.13 a)
label | e1c6ef20-b7f1-404d-abab-0e3ea8cab50d |  | note | SD TC-1201
label | 101d1766-3638-4026-ba20-497ba1577868 |  | note | Design Drawings
label | 92978fad-d49a-4dcb-86a0-dcc327b08098 |  | note | ---------------------------------
label | 23c896a1-05c4-47a1-8f72-e3eeba188321 |  | note | ACCEPTANCE CRITERIA: Pedestals and poles shall be installed in accordance with the design drawings and relevant specifications.
label | 133a77c4-08ce-41e4-81b9-0a446e8daef2 |  | note | Pedestals shall not be stood within 48 hours of casting of foundations.
label | 10e28a04-4cf7-4e8a-979b-f69db76405f6 |  | note | Poles shall not be stood within 7 days of casting of foundation.
label | 048445f1-8ea4-4143-a44f-484b8bcbf7f3 |  | note | ---------------------------------
label | 40b8c6eb-c4e0-48fa-a6ff-c6935e86f9b0 |  | note | METHOD: Visual
label | 829ccd17-b627-4c54-9736-9f159bc3415e |  | note | ---------------------------------
label | d2b2e714-0aa6-419d-9a11-d3a1f5a482f3 |  | note | FREQUENCY: Per item
label | 24dc559d-ed92-4cbf-823b-0ec7f23c90da |  | note | ---------------------------------
label | 4f91c921-d7ff-4b66-9568-2f75f00273b9 |  | note | CATEGORY: IP
label | 8ea1bf53-f9e8-4de7-bb23-5fb493ff6e79 |  | note | ---------------------------------
label | 26b992b6-4ad1-48d8-b62a-afab337353c9 |  | note | RESPONSIBILITY: SE/PE
label | 4bb2793b-d420-4734-abae-3a43c54fb38a |  | note | ---------------------------------
label | 3deca313-61f3-4b3e-8f4a-6ef979304c85 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9ba4033f-7403-49bd-8e50-2ba7b31538a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Lantern Requirements
label | 3ac97913-bb65-4743-9481-30b88d398155 |  | note | REFERENCE: Section 730.13 b)
label | 8f64c466-ed8e-42b4-834e-aa79c1c81e75 |  | note | ---------------------------------
label | 25491d12-6a7b-405a-828a-10e00e8a9c04 |  | note | ACCEPTANCE CRITERIA: All traffic signal lanterns shall be LED type, excluding minor remodels where QH lanterns are permitted.
label | fa744068-9f06-40f3-b018-645979ba705f |  | note | A mix of LED and QH lanterns is not permitted.
label | b7c83486-7612-4e97-b979-abf0eead4ff0 |  | note | ---------------------------------
label | 37d31868-cda8-4688-bf7e-b9b4574dacf1 |  | note | METHOD: Visual
label | bccaff56-5c7c-4b80-80aa-56a9add102ed |  | note | ---------------------------------
label | 5e693980-0098-4a75-8d7d-0e363a2477ce |  | note | FREQUENCY: Per item
label | fa3be447-6302-485d-9885-a8b830d80293 |  | note | ---------------------------------
label | c4e05206-33f6-4f92-8a19-9ebf0e1665b9 |  | note | CATEGORY: IP
label | 1d7d1f9c-c9bf-4dd7-b242-0b96f3a31fc0 |  | note | ---------------------------------
label | eb18df51-7da2-4329-b6de-e66366e02228 |  | note | RESPONSIBILITY: SE/PE
label | 2509b457-ef32-4231-b69a-22b3868fc647 |  | note | ---------------------------------
label | dde70af9-904f-47e2-926a-0f2971744fcc |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 247ca9c0-6f11-444d-b8db-698c4cbba039 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Lantern Installation - Mounting
label | a30a9b5a-bcc2-4d88-8149-a15b05902135 |  | note | REFERENCE: Section 730.13 c)
label | ad64a98f-9cf6-46ad-8062-84992a82a662 |  | note | SD TC-1115
label | ee8ba92e-fb5f-4ba9-9839-07289b4120c4 |  | note | ---------------------------------
label | d55df1bc-8462-4cdc-9cd7-b4a1da8fa3af |  | note | ACCEPTANCE CRITERIA: Lanterns shall be mounted vertically using straps securely fixed to mounting brackets.
label | 2c45a490-1d90-4628-80b7-598eee6aaf1c |  | note | Upper mounting brackets shall be orientated in accordance with TC-1115.
label | 7775b2fa-f842-41b7-ade1-0fa2adc4084d |  | note | ---------------------------------
label | 56933279-a30a-43b9-ae82-805aeac98f0c |  | note | METHOD: Visual
label | de0f9c45-bc91-45e0-8f4e-eff06936c299 |  | note | ---------------------------------
label | a407930c-448e-41f7-917e-874685ebe457 |  | note | FREQUENCY: Per item
label | 00c51032-bcd9-4579-a7cd-39713aa7b514 |  | note | ---------------------------------
label | 937d8b7b-c522-44ce-aeef-3ffd158522af |  | note | CATEGORY: IP
label | 5d3329cf-83d1-481d-95b6-839196c07c24 |  | note | ---------------------------------
label | 5bfb4db1-cfc1-405a-b9ee-ac9707fad2d9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 180a0ad9-839e-4933-ba1d-17baf3a19963 |  | note | ---------------------------------
label | 6ea856eb-5f13-420e-a0a1-b7a99869bc65 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a9176827-e453-410c-afd8-5f869d3633f8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Lantern Installation - Cabling
label | 8e5c3e5b-bb82-4b94-a003-9b5735fa797b |  | note | REFERENCE: Section 730.13 c) (vi, vii, viii and ix)
label | b6ab1bdc-b318-4e4c-abeb-7560397cd5e1 |  | note | SD TC-1119
label | 46072746-739d-4a73-ab7d-9e70f5aa8793 |  | note | ---------------------------------
label | f65fac99-ff1a-4cfa-a792-eeb1423c6d20 |  | note | ACCEPTANCE CRITERIA: External cables and conduits shall be fixed to pedestals, poles or supports with the desired length as per the relevant standards.
label | f0443e52-4894-4ffb-bae3-89e7d254dee1 |  | note | Cable connections to lanterns shall be made with continuous lengths of cable; no joins shall be allowed.
label | aac3d7a6-1223-44ab-94dd-3ebea37e3143 |  | note | ---------------------------------
label | e717f5be-adf9-4394-a855-86b9daed7113 |  | note | METHOD: Visual
label | e2cd21a7-c8e0-4da2-b19e-f82863395309 |  | note | ---------------------------------
label | c19e0b65-94b3-4452-9465-b748922a6c16 |  | note | FREQUENCY: Per item
label | 92ebeacc-109d-411a-89fd-7d14f330efd2 |  | note | ---------------------------------
label | 1557d129-4494-4812-ba88-d83e2d24b2c0 |  | note | CATEGORY: IP
label | 9cebfa87-93bb-4e26-a4a4-c3c28da76299 |  | note | ---------------------------------
label | 8c3857a7-1bf2-47d9-81f5-d246b894009f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4e6c1401-694f-4900-802b-1e264ee6c737 |  | note | ---------------------------------
label | c4f13096-d557-4a33-aafb-b28f4aa89a65 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ca9634d5-827b-4726-97e5-dbcc7e0fb088 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Lantern Installation - Mounting Height and Alignment
label | 5d5461e4-2e84-4880-b8da-91bc58dc1fb8 |  | note | REFERENCE: Section 730.13 (d)&(e)
label | 49f56e8d-1964-4462-9043-9e2db1d7e6af |  | note | SD TC-1112
label | 4c8bce60-c509-4bf7-b203-f0f8a863bee5 |  | note | SD TC-1116
label | e8d26ae3-6f32-4f17-a1e0-62b7b6f450da |  | note | ---------------------------------
label | fddb779c-1b9d-43c3-891d-79b26692e3f9 |  | note | ACCEPTANCE CRITERIA: Mounting heights for 2A and 2B pedestals are to be as per SD TC-1116.
label | 24cf43cd-1a41-4807-b5f7-44a10ceb9ff4 |  | note | Lanterns on the outreach of a MA or JUMA shall be mounted in accordance with SD TC-1112.
label | 88d82ab5-e09a-4e51-a0be-c0d8f1be7d59 |  | note | Vehicle lanterns shall be aligned to provide optimum visibility for approaching traffic, and aimed at a distance before the stop line for the following:
label | a2e7610d-b317-43e9-86ea-2e8210275cb7 |  | note | - Primary - 240m
label | 67cac176-c866-431a-b1dc-cc689f590b88 |  | note | - Secondary - 150m
label | eeab9ff7-0d06-4570-bd58-183a9e798885 |  | note | - Tertiary - 5m
label | b1ca36bc-6fb5-4726-9e5f-cc3187a4191e |  | note | ---------------------------------
label | dfb99aad-1acd-4f8c-9efa-5af75137c016 |  | note | METHOD: Visual
label | de4a5d67-1b87-41be-8c9f-b8d533a6172d |  | note | ---------------------------------
label | bc2d3c48-19af-4776-8938-9d45e8d91edf |  | note | FREQUENCY: Per item
label | 6c0dbb7b-d7fd-490a-8dca-be4acf655b86 |  | note | ---------------------------------
label | 5459d5e3-28c2-4f9b-ac01-756b43e58c6e |  | note | CATEGORY: IP
label | 2b40d9b8-625a-4218-b740-a73e40ec3530 |  | note | ---------------------------------
label | 0383cf5c-17e4-44ae-b748-8eb24fec8b80 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | a9f7ca4f-e900-46ac-a330-c6f516464d0a |  | note | ---------------------------------
label | 34d338e8-c7f5-45ec-9458-ec83224bdef7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 3623bb2e-4c35-4eb6-9a7b-8be22980ae81 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Lantern Installation - Target Boards and Visors
label | a7683361-0924-4c50-9b00-14e1c6f90a70 |  | note | REFERENCE: Section 730.131 (f)
label | b38ebcb3-96c0-4b30-bf49-6a72b7413611 |  | note | SD TC-1119
label | 61a89711-4776-43d4-8a26-e8e548f14674 |  | note | SD TC-1127
label | 4cfc453f-f8c1-43e7-aa57-8fa961f7172f |  | note | ---------------------------------
label | 80b57e9a-aaad-4415-b81c-c9f446582fd8 |  | note | ACCEPTANCE CRITERIA: All target boards shall be metal and fitted in accordance with SD TC-1119.
label | 983795a1-876b-444d-81f9-35eecf0c8f3f |  | note | Visors for LED lanterns shall be fitted as per the below and Table 730.132:
label | f2cf4cb6-be7f-476c-8760-20f931d802e5 |  | note | MA/JUMA - Visor Type 1 - Both Sides Cutaway
label | cb837d25-f2a7-4e92-99cc-b18eadb85752 |  | note | L/H Primary - Visor Type 1 - Both Sides Cutaway
label | 3aaceb42-b4e8-41cb-a3a4-d80e01f16e09 |  | note | R/H Primary - Visor Type 1 - Both Sides Cutaway
label | bde86556-f64b-408b-b5cc-f4420bb11876 |  | note | Secondary/Tertiary - Visor Type 3 Short
label | b69c9ecc-9ad3-41dd-bf73-a46450749084 |  | note | Pedestrian/Bicycle - Visor Type 4
label | 83a8d58b-5e77-4e08-9e8b-26b6784a898f |  | note | ---------------------------------
label | 63569211-c423-4c09-96e2-4f6ee3d7db1a |  | note | METHOD: Visual
label | 1881c13d-8ac3-47c7-8dad-d702919b35f5 |  | note | ---------------------------------
label | b5dbdf21-7f51-4f58-8317-879db517adaf |  | note | FREQUENCY: Per item
label | 97abb0a4-9ad6-4d42-96e9-c535a01e96fe |  | note | ---------------------------------
label | 71c54208-0ef3-4ac9-9082-0b0176dbc9c3 |  | note | CATEGORY: IP
label | c0deed04-3cc5-43c8-bace-2af18be198e5 |  | note | ---------------------------------
label | 6ce15838-0e09-4e32-aa98-047d163a8ce3 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ea759481-6c70-4502-8cc1-eefaa9de8ddf |  | note | ---------------------------------
label | 67c4f150-3c4d-40c2-b53d-66da4d3cfb87 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 3bb2af5e-ec16-46ec-a634-968fddc96631 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Installation of Pedestrian Push Buttons and Audio Tactile Devices
label | e525a5e1-2331-432e-8639-cb6a46154be3 |  | note | REFERENCE: Section 730.131 (g), (h)
label | d48d1a10-8bff-4654-b5c7-d18fe69b0813 |  | note | SD TC-1116
label | 7426d8ea-776b-4497-820d-0ccdaa93b515 |  | note | ---------------------------------
label | 7f06cd3c-02b7-45a2-9e4f-5a0152361097 |  | note | ACCEPTANCE CRITERIA: Pedestrian push button assemblies shall be mounted clear of any access openings and such that the centre of the button is 1.0 m above FSL, as shown on SD TC-1116.
label | dff79f17-5115-405b-b5be-9b1eb8365115 |  | note | The face of the button shall be at right angles to the direction of the associated walk lines. the tactile arrow indicator shall be orientated to indicate the walk direction.
label | a27c9fe6-d151-4ac2-ac03-c26f3315c59b |  | note | If required, audio tactile units of the type nominated shall be mounted as shown on SD TC-1116.
label | 753115e0-ef39-4c54-82ab-f2ccf8ebf764 |  | note | ---------------------------------
label | e2a97902-33b1-482d-949b-634fc4a1a3c3 |  | note | METHOD: Visual
label | 5cb2da59-1a44-478c-a19b-748d035dfb5c |  | note | ---------------------------------
label | 79c21b2c-7710-46a7-a919-23e85f77971b |  | note | FREQUENCY: Per item
label | ebb870ac-8bec-4595-871c-813109496c27 |  | note | ---------------------------------
label | d805f248-01cb-4eef-b0f0-77c1af8451b5 |  | note | CATEGORY: IP
label | 4c4ef299-cab5-435e-9325-64e996bdb286 |  | note | ---------------------------------
label | 2762bb25-ac8f-4a36-b516-106794c93633 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6a89c21a-57e2-438d-aaa4-d5dbe7036317 |  | note | ---------------------------------
label | a3c5694e-9bf5-4d54-9c19-17be100db4f0 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e6a83df1-1c7c-4a2c-a408-c4b22db2de28 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Non-Commissioned Lanterns
label | 7644cb95-b120-4239-94c6-87aa4c9ea387 |  | note | REFERENCE: Section 730.131 (l)
label | d4fd788d-1f3f-4bba-93ea-cc9ff5cb1a13 |  | note | SD TC 1131
label | a604bc54-c37a-4960-bfd3-87d837bc29e3 |  | note | ---------------------------------
label | dd405e98-2b4f-43fc-aea0-9b249adbf350 |  | note | ACCEPTANCE CRITERIA: The faces of all installed but not yet operating lanterns shall be covered, specifically 'NOT IN USE' signage on vehicle lanterns that have not been switched on.
label | ba8bb54b-a32a-4efa-845f-175455cea46e |  | note | ---------------------------------
label | 4676a8e3-e460-4546-99b7-aa82c90fe516 |  | note | METHOD: Visual
label | 23981bc8-959c-4b9b-a0ad-98662b33d362 |  | note | ---------------------------------
label | ccd445a7-8813-4690-91ee-df425108a68c |  | note | FREQUENCY: Per item
label | 3b947b2f-7b6a-42b6-8732-3892347fd57e |  | note | ---------------------------------
label | ffaa4b4a-048e-484f-beb0-3651bb089125 |  | note | CATEGORY: IP
label | 1b0ce810-83dc-4d77-a3f7-d3ff1032157b |  | note | ---------------------------------
label | 99d7d0f7-13ff-49be-8fa8-1afe68416208 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9a251612-25de-491b-83e2-e8417f4a9ce6 |  | note | ---------------------------------
label | 45efbedc-951a-44fc-8e8d-05da79253987 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 76774dd4-1361-4e55-957a-8e8d97f7a443 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Hardware Inspection
label | 9c39c524-92bd-47a4-9e41-be997da35cf8 |  | note | REFERENCE: 730.131
label | 744af339-a77e-4948-af2a-af1507497ba0 |  | note | ---------------------------------
label | e93972f8-2f91-456c-8202-4f13c5dfff93 |  | note | ACCEPTANCE CRITERIA: All installed hardware shall be inspected prior to works proceeding by the Nominated Authority.
label | 3c4b2e1c-4892-48b6-840b-49dc0dfa7652 |  | note | ---------------------------------
label | 442a9289-c031-48fb-b427-021dd161b66c |  | note | METHOD: Review
label | 950d8e63-416d-432d-90cd-6b5273aa1e41 |  | note | ---------------------------------
label | 3a249c33-e855-4701-9cf8-3f371966ea7b |  | note | FREQUENCY: Per item
label | e754ae45-cbe0-4414-80c4-d13fa9f29bf2 |  | note | ---------------------------------
label | 3d310b7f-fd10-46b5-83c1-9a612285e70e |  | note | CATEGORY: HP*
label | 6ebae838-4657-4691-a72f-fdf59b1d18e8 |  | note | ---------------------------------
label | 149e8a49-2dd2-4b3c-a982-4bd8babcc0fc |  | note | RESPONSIBILITY: SE & NA
label | 5795d41b-150d-409f-8a01-b7314b098691 |  | note | ---------------------------------
label | 6d3e3ee3-43a3-46ae-ab1f-12f5ea1f48ea |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 5630d3f5-fb93-4fe6-ab14-fe54ddb7f37c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 8f9de161-8715-4758-b2ee-3306a8d54473 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 364f8c9f-00a0-4567-b1b6-43569a46db75 |  | textbox | Name:
text | e4baf7d9-d6ed-4b0b-a626-533dc792c614 |  | textbox | Position:
text | 9b8fad1b-1dfc-4acc-80ad-957886c54f90 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | itp |  |  |  | Yes | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | 4dcc3252-7831-4b06-8646-3e836780a682
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | adae9d4d-b67e-4c8c-aaaa-ca344a1cd214 |  | note | Document Title: ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3
label | 1d36f9ac-c9e7-4e17-aaeb-017851de1a0b |  | note | ITP Description: Structural Steel Barrier Rail (Supply & Installation)
label | 792bf003-8c59-4d58-9178-795580743704 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 5c6256de-ad4f-49d2-8146-fb0565543594 |  | note | Revision Number: 3
label | 4d780a5f-9ea4-4460-b3ca-6b6a9768570b |  | note | Revision Date: 4/05/21
label | 65f36246-429d-45a5-ac16-f2cbef85a2db |  | note | ITP created by: Mike Freeman
label | ad9a9a91-dc9f-4891-b621-cb6fc84ef27b |  | note | 1.1 VicRoads Section 610 November 2018
label | 0a57e4bc-0928-44d3-b036-66fad85d22d8 |  | note | 1.2 VicRoads Section 610 March 2019
label | 793e5c6e-9454-405e-90bd-1c89f1cfc756 |  | note | 1.3 VicRoads Section 610 June 2019
label | b47fa068-1e1d-47bd-9539-332bc982f002 |  | note | 1.4 VicRoads Section 630 October 2013
label | 894e378f-d39b-45b1-b9d0-8adc79b0929e |  | note | 1.5 VicRoads Section 631 February 2009
label | 35352c9e-4d3e-460e-9e06-b32e1e3e3d35 |  | note | 1.6 VicRoads Section 671 October 2013
label | 0e0e1850-379e-4faf-ba67-4b5af4125e13 |  | note | 1.7 AS5131-2016
label | e3deb57d-08e9-4b83-adf3-a9cbdc230d8b |  | note | 1.8 AS4680-2006
label | f40c4561-1199-4964-9817-c758f7ce7d51 |  | note | 1.9 AS2312.1-2014
label | 45a9e833-3a9f-4d31-a5be-f375892c1c5a |  | note | 1.10 AS4506-2005
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 24ba9873-986a-43b0-aebd-66aa8b6eb822 |  | note | REFERENCE: IFC Drawings
label | 8ba2419d-0b76-419d-9889-bfdea3e350cc |  | note | MRPA Quality Management Plan
label | b0a2ac9f-a8d8-4c49-9fb9-96783a34faf8 |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 2ae71416-f8ef-4432-a408-ec83d4b18a73 |  | note | Typically this consists of but not limited to:
label | a2f9837b-9e96-4511-a404-e61bf5295532 |  | note | i. Certificate of Compliance
label | ed1b38b3-5435-46a7-84f0-fce5a02994bf |  | note | ii. Completed ITP
label | 22a5d432-acef-44cf-bddb-8ea601fccb84 |  | note | iii. Weld Procedure Specifications
label | bae44cca-3c88-47bd-895e-3f0dafd8dc4a |  | note | iv. Weld Procedure Qualifications
label | e507cd92-82f5-446c-90d1-5684a8406b73 |  | note | v. Welder Qualifications
label | 675423c6-468f-431e-ae36-daee189c87d5 |  | note | vi. Material Certificates and traceability
label | 8cc03af0-098c-47e9-86e7-f544929d8f11 |  | note | vii. Quality Assurance check sheets
label | b4620a60-120c-4f60-bdfb-f99cff3a1b1d |  | note | viii. Welding Consumable batch certificates
label | ce8b8200-9d6a-42c6-bec2-de110e7b5c11 |  | note | ix. Coating certificate(s)
label | 47eb347b-4c8a-461b-8f5e-f59fb88217c3 |  | note | x. Non-destructive Testing (NDT) Reports
label | ccfd3af2-4f85-403b-ba3e-a5e0cce102fa |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | b5e9c16d-2956-4563-84c3-c4664686b5dd |  | note | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | e2cc4b4b-469e-4234-9617-2c5c06f0a781 |  | note | METHOD: Document Review
label | 7ef3e7e9-f596-4baa-88f6-10d30556176f |  | note | FREQUENCY: Each component
label | 1cf1b100-e5c1-4da4-b1c4-fe6a58c7001b |  | note | CATEGORY: IP
label | 44939e93-ab3b-4801-ac4e-f471ed49f1da |  | note | RESPONSIBILITY: PE/SE/SPE
label | be6db382-36bb-4886-9b97-f7e8ac6dca64 |  | note | VERIFYING DOCUMENTS: This ITP
text | 338e1872-e604-47ff-949b-ca0a82af5e7f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | 65824a36-7567-4d6b-bd1e-1fa3ee29cb72 |  | note | REFERENCE: IFC Drawings
label | 7116611b-467f-43af-ab67-33bb9724afe5 |  | note | 671.04
label | 0d7a902d-718c-48ce-a64f-fbd6a8b5c7c1 |  | note | 610.33
label | cebe679f-ed7c-483e-b269-9948b18544f3 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 29944583-3750-4d34-88ff-e8bc1515a4ed |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | 9888b049-32a9-48df-82dd-3a4fd1be21e7 |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | 88b793b5-64a7-4898-a1a8-9c654573ca2b |  | note | iii. have a flowable consistency
label | e2c5158c-dfef-44d9-a446-fdeab7c1a6b7 |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | f4caa0b0-dc8e-4a27-99f2-e034e8b6b9de |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
label | edfd52bc-fc37-4373-a36c-f366e3d8ddaf |  | note | Enter: Teambinder Material Approval number
label | 2a962a0e-f026-49a5-ba2a-b14365fcdcf2 |  | note | METHOD: Document Review
label | 186aa31e-7efd-48a7-a04c-33ad8d746167 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | d2ecd355-d8cc-4cc7-8ce9-3e2a1013b650 |  | note | CATEGORY: IP
label | fc8086bc-1325-417d-bd7b-972ba9ffdabc |  | note | RESPONSIBILITY: Nominated Authority
label | 9e5cb82d-16f2-4610-afc9-3a192c6bbe74 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9288a082-f3b9-497d-ad5d-1698bc6f99ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | f397e5b5-d1cc-43c5-8820-486924d0ef27 |  | note | REFERENCE: 610.23 (d)
label | acc70afb-f477-4742-b58f-eb0a3f0196ff |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 1aadd829-bb9d-41d0-bc5b-5d23a1d1e37c |  | note | Note: This may be the same product used for the concrete curing
label | f715a5cb-917a-47ac-ab17-d8b8c3d3bce5 |  | note | Enter: Teambinder Material Approval number
label | fc27712b-b114-4925-9cb6-1be2100d2bdf |  | note | METHOD: Document Review
label | 28c57106-de44-4019-adc3-4751326396e3 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | 338b68b6-4f77-4cf3-8773-4f62cacdfc35 |  | note | CATEGORY: IP
label | a5908c82-5e52-49b0-9f61-41008a791fdd |  | note | RESPONSIBILITY: Nominated Authority
label | 589f62e8-a15a-4725-84b2-281d15ba0d62 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2708e1e8-41ac-4384-b0dc-5dea0b5884e5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Curing Methodology (for Grout and Mortar)
label | 875562d7-cf5b-44ef-b984-1a9a89ad1857 |  | note | REFERENCE: 610.23 (a)
label | 9de6b0a4-657a-4b36-9ef6-f3870500e030 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 16fbf39b-38de-4c45-9579-37504d435ca3 |  | note | Note: This may be the same document used for the concrete curing.
label | 857647c4-ce33-4ad6-8a59-816bc48c377a |  | note | Enter: Teambinder Approval number
label | 5685c014-f7bd-4675-8a4a-2bcca30b89b3 |  | note | METHOD: Document Review
label | c4756361-759b-4322-bd29-dc8e4641eebc |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | 5a1d76af-9235-4766-8b12-3ae103e9e915 |  | note | CATEGORY: HP
label | 2a8e3c44-94ba-49c5-a05c-733abc27e4e0 |  | note | RESPONSIBILITY: Nominated Authority
label | 2037a5c7-67d3-4bf1-b408-cdf83e575bf6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1ac4ee65-76e1-4910-b8fb-8071dfca6091 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 97ed0588-be40-4a21-9caf-918ee83815f0 |  | note | REFERENCE: MRPA Quality Management Plan
label | 89566f2a-79ec-4a28-a359-defd4f9a224c |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b0c36f0d-68c4-403b-af54-1eaf01f98423 |  | note | METHOD: Document Review
label | 49122914-9b98-4f71-aa7d-913d898dbdb1 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | df60dee1-ce17-446d-b5ca-d1e47b2c246f |  | note | CATEGORY: HP*
label | 9a21a790-9e27-4477-bb0f-96f6727e69c3 |  | note | RESPONSIBILITY: All
label | 7ac017c5-882a-4b26-8789-8ca42e517b4e |  | note | VERIFYING DOCUMENTS: This ITP
text | 1adc9dc0-393f-4c9e-95c3-3e80b7d58ab7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection Checklist
label | 1cf5630f-1230-4b4b-8daf-987804c1b3d4 |  | note | REFERENCE: IFC Drawings
label | 59a0543f-60ac-47ab-bca5-74e5e9ba0d79 |  | note | 630.08
label | fb657cbf-8ccd-4140-a143-e5178064c86f |  | note | 630.09
label | 2a328178-fb1a-48f3-b49e-9e4798c6d365 |  | note | 630.20 (a)
label | 141e21ec-e84c-4731-91b9-cf75a3b2b587 |  | note | 631.06
label | b5d9a857-6cb8-4e8b-a098-4f5a40cb0d4f |  | note | AS4860 Clause 7
label | 276eaa04-056b-4656-9daa-eb5c0dafa100 |  | note | 631.11 (a)
label | e58e3859-1fef-4f07-9ed2-15403201efaa |  | note | AS2312 Clause 9.6.4 (i)
label | 4ef2e693-b97a-495a-b14e-e842389a055d |  | note | AS4506 Clause 2.3
label | 17ab2c08-2c14-410e-9334-8734e2e4b28e |  | note | MRPA Quality Management Plan
label | 06c9fd94-1f36-49c7-8a8c-e8d6622accea |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | e37b0f04-c69a-490b-817e-d10772720fe9 |  | note | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | f4f265d3-5472-4da6-ac27-12e326be5d16 |  | note | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | 96e914ce-886d-4f8c-bcad-31ad9c638a6f |  | note | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | 1129b51b-7334-4cac-8d23-175a8217c628 |  | note | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | 8a33a754-efa3-492d-875d-196c481a939f |  | note | Complete: Materials Inspection Checklist in ConQA
label | 489b6819-8178-4da9-84a1-038359e65079 |  | note | METHOD: Measure , Visual
label | 66fef421-af83-4432-bc30-4d3a08ef178e |  | note | FREQUENCY: Each component
label | 5c3c3df8-5621-4ede-9387-1d0159be7d5b |  | note | CATEGORY: IP
label | bc1a3b08-cfbc-4ac3-867f-c4cbedcf6f46 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 393ee02a-37a4-4a34-8640-6a99143a4087 |  | note | VERIFYING DOCUMENTS: This ITP
text | d411b96d-dbda-4bb1-ad46-aed53ad127fa |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | a8979a74-ff16-4eea-ba26-7317c934bb90 |  | note | REFERENCE: IFC Drawings
label | 2c15f710-8366-4526-abf3-f6f44992378b |  | note | Product TDS
label | 206fc1d8-3811-4a79-a2bd-077d5706af66 |  | note | ACCEPTANCE CRITERIA: Prepare the surface in accordance with the Product TDS.
label | c6873c17-7a74-442a-9d6e-d45803caba3d |  | note | As a minimum, ensuring that it is clean and free from laitance.
label | eefd6b77-2659-434e-975f-1aabace684de |  | note | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
label | 8523ccff-4dbe-4831-91a4-fba87c5f6cc6 |  | note | METHOD: Measure , Visual
label | aed6f142-6089-41ae-a8c3-89adb4f7772f |  | note | FREQUENCY: Where applicable, each post location
label | e39ae37e-b065-4c0b-8adc-ae0b6bc18bab |  | note | CATEGORY: IP
label | 51046109-2670-4d69-880c-52d7e9a48171 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0cdd815c-bace-4560-82d3-6feb55cd05e0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2368695a-90ae-4a46-8ff8-993d3589eac0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | 023aa73b-c30e-41ba-a333-efec6f1bb697 |  | note | REFERENCE: 630.09
label | c5f2670a-bc64-4680-8029-a65df01c04f6 |  | note | 631.14
label | a72b0939-f202-4486-a4bf-ce496a0c114b |  | note | AS4100 Clause 15.2.2 & 3
label | ce7a3207-0e28-4836-8887-8a5fa0d8c97c |  | note | AS5131 Clause 11.5.6
label | d2493af3-9a12-4387-b663-a335ecf81be1 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 0d948f38-5989-466e-9369-cfdc17f6ad3a |  | note | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | 7e55525d-2211-46e2-99d8-5d17e2ef6c95 |  | note | METHOD: Visual
label | 20ef1ef2-40f5-4c36-8944-f84b7fd8bbd4 |  | note | FREQUENCY: Each component
label | edc1eb4d-cb65-4711-94c7-314c7f5075aa |  | note | CATEGORY: IP
label | a8234679-0256-49d8-a3ca-693648bf65ff |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9a14190e-51d0-42cb-b9d7-174a9c7885eb |  | note | VERIFYING DOCUMENTS: This ITP
text | 0ea1d0f7-01c0-4cec-b63a-542603443b9d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | 2a801d1f-9bd7-4b85-9f6a-741a03a82262 |  | note | REFERENCE: AS4100 Clause 15.2.3
label | 4395999b-416f-4e96-8b82-8ee4b595a663 |  | note | AS5131 Clause 11.5.7
label | 1ec78c75-2854-4ce6-aed8-0f2b6a86847d |  | note | 630.12
label | 58359ad3-8bc5-42b1-81fb-9749d4dd4183 |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | ba91d928-b985-47c7-a345-bfb3ce5837f4 |  | note | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | 5c988e39-a283-4d9a-88d0-9dda9eff8424 |  | note | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | c50898e0-732b-4dd4-8dec-7ffdb8f825ce |  | note | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | 96571110-58c0-47ec-b24e-dc1ed3de9dc5 |  | note | Holes shall not exceed the greater of:
label | 2c2a3685-2cbc-4203-b05f-077ffe43914d |  | note | 1.25 x bolt dia. OR bolt dia. + 8mm
label | 31a129ad-e8c2-46b2-8122-023d587b4025 |  | note | Slots shall not exceed the greater of:
label | 20a282cf-7e19-4d9a-a023-885c68dd4c36 |  | note | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 078d055c-3a8e-4a98-a92a-e201aa795131 |  | note | METHOD: Measure , Visual
label | c6a02271-dfe7-4817-ae19-324a0d770007 |  | note | FREQUENCY: Each component
label | 09cb488b-ffe1-47f4-9e43-1a1484c72cb9 |  | note | CATEGORY: IP
label | a8823ece-c9a1-4ec3-8b99-d4c4fa33caad |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ec10c4b-6da0-4a17-bff5-0344165f8a11 |  | note | VERIFYING DOCUMENTS: This ITP
text | d4ba7532-1a8d-47b8-b3b8-2b01fe6a6930 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | bc34da90-b9e0-4ab4-95c7-c50038a2fad7 |  | note | REFERENCE: IFC Drawings
label | d2ec75a0-e0e1-45e0-9b8b-295ed2a9ddff |  | note | 630.20 (a) & (c)
label | fda4fa86-81c1-4040-93e7-8c5e7626edc4 |  | note | AS4100 Clause 14.3.5.2
label | fd3a7455-8e65-40ab-951e-754ac258c7e6 |  | note | AS5131 Clause 6.7.4
label | 770780e0-3143-43a8-a71b-10a4cb87c994 |  | note | AS4100 Clause 15.2.5.2 (a)
label | f9ed3133-bad3-4494-87a4-39b67344e28a |  | note | AS5131 Clause 8.3
label | 9a49125d-ec7d-4097-9699-c99892b4db09 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 6db9d23e-70cf-4664-81d7-0591aa177073 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | 17cbcd94-fcb6-4540-b3b2-0b680d40c073 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | b845b681-a234-4f90-b7b3-3150d6cdb266 |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podgier spanner.
label | b4dbe196-1fb2-4902-bddd-fccee394d272 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 9deade1a-63f5-4701-bdc2-021172775b94 |  | note | METHOD: Measure , Visual
label | 148a2e8d-e241-4886-825d-a9061e857670 |  | note | FREQUENCY: Each bolted connection
label | 15026e97-81eb-4b80-8b94-7bc71125b8b0 |  | note | CATEGORY: IP
label | bfc87069-62fa-4821-aab2-092cfc102538 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c5516ecd-3b78-402e-9926-c67eb62646be |  | note | VERIFYING DOCUMENTS: This ITP
text | 1b284228-e681-4a56-8146-4f5ad4e3887e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Survey Conformance
label | 83ae5c26-8740-4c86-8d60-bde5dc3d1b26 |  | note | REFERENCE: IFC Drawings
label | 1866abde-26a1-46bc-9f1a-413ce8eabc52 |  | note | 671.06
label | 52c2e729-f399-40a6-85f1-44530f5cbbe6 |  | note | AS4100 Clause 15.3.1 - 7
label | d996070c-84c5-444e-b0c9-dac3331d4d5d |  | note | AS5131 Appendix F, Table F3*
label | 5dbf100d-a253-4845-be6f-582f342dbf6d |  | note | ACCEPTANCE CRITERIA: Railing posts shall not be grouted until verification that the Works meet level and location requirements within the tolerances below:
label | 2c1c6756-9e02-4a8a-8952-6752395d28c7 |  | note | Departure from RL = ±10mm*
label | 9b3cee75-90c5-451e-b6db-8b2d19ef35f2 |  | note | Departure from plan position = ±25mm
label | 6e72b565-d14e-4dc8-831c-ac9be196877e |  | note | Departure from alignment = ±5mm
label | 31b6a611-676c-433d-997d-679b07a227dd |  | note | Irregularities in alignment = 3mm in 3m
label | 9b8e385b-d372-4f1b-899c-8aa3eae29688 |  | note | Variation in joint gap width = ±3mm
label | 17c4710c-eaaa-416c-9175-4f1be5b1c42d |  | note | Projection of bolt = +25mm, 5mm
label | be539dff-513d-477f-bb4c-0a79eb5fefb2 |  | note | Attach: Survey Report
label | c6b68eca-dd20-49d5-9d6c-ebe71cf3975f |  | note | METHOD: Measure , Visual
label | 923e4b58-16aa-48c9-887e-d61aff74c7b0 |  | note | FREQUENCY: Each post location
label | b9c591d0-f182-4f7b-8d86-961459d76c01 |  | note | CATEGORY: HP
label | d691a511-f7d0-4873-a157-c8707740a66b |  | note | RESPONSIBILITY: Nominated Authority
label | 8ca25511-2a96-44af-b16d-496a0c6e82e6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 73f82146-01f0-4f19-8027-ea8120884931 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Base Plate Formwork Construction & Placement
label | 9ff622d8-ff24-46af-9ccd-f415969a1754 |  | note | REFERENCE: IFC Drawings
label | 5f4f80d6-bd60-4d79-a509-d32e8209eef6 |  | note | ACCEPTANCE CRITERIA: Dimensions as per drawings (typically flush with base-plate sides and underside).
label | ddffbf4e-b81d-43d8-94ed-ad45f6373607 |  | note | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | 4433e25a-4eb6-4909-b5a3-40c12c29228d |  | note | METHOD: Measure , Visual
label | 95244109-caec-424a-a40e-f2b6f805aa4c |  | note | FREQUENCY: Each post location
label | 4b0c7391-4b91-4d1f-9315-bdcb839a07b0 |  | note | CATEGORY: IP
label | 59759c1a-51b2-4cd3-b2fe-fd2268044a63 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 493c896f-06b6-4522-9956-88352074473b |  | note | VERIFYING DOCUMENTS: This ITP
text | e23648d8-cfcc-43f8-9c63-5243c9b2d3e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-soaking Concrete Surface
label | 68bafdeb-10a1-440d-b091-b45f0aa7dd15 |  | note | REFERENCE: Product TDS
label | 27bce66a-0c40-47d2-b397-0bb50cd2222f |  | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | e36a7c5f-422b-48b3-aa06-222e2399d13b |  | note | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | 0af2f6a7-dc1d-4928-97e8-f1686ebd078e |  | note | METHOD: Visual
label | b315d835-2983-42e3-86ff-28932cbf0f8d |  | note | FREQUENCY: Where applicable, each post location
label | e8ae89f8-6a41-4041-b266-a3aa444bbf4e |  | note | CATEGORY: IP
label | 1e07cfce-9e7d-43cc-aead-aab159abe444 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4f52e84f-f981-4614-8aec-7c9d66a251a9 |  | note | VERIFYING DOCUMENTS: This ITP
text | d074d7fe-dc26-42fe-a7a4-555da426a8d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions
label | 1c99cd6f-048e-4a3d-bfa7-795e3e48aaa4 |  | note | REFERENCE: 610.17
label | 5892b3cf-9551-4b08-a266-91aae9d18c4e |  | note | Table 610.171
label | 67239f9c-c2ea-46df-9e40-058e30b04f46 |  | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | 8420ce35-f614-4164-9d61-ef74b6a796d3 |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 73a43a26-ff86-4842-b858-65975704725b |  | note | Record: Required information on the Grout Pour Record.
label | 16539809-ade1-4884-a09c-e9186db136fb |  | note | METHOD: Measure , Visual
label | d9e5dc6a-4d78-4ece-8157-e29e713eb967 |  | note | FREQUENCY: Each lot
label | bf44f8ee-5dbe-482f-8edf-a02f52cc47fd |  | note | CATEGORY: IP
label | 4599fbab-5d65-491c-9cc8-01ccfd66854d |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 789a01a6-4bde-443b-ae51-4886374e309b |  | note | VERIFYING DOCUMENTS: This ITP
text | 2482e769-6792-49ff-9f91-1caa4e8733b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Mixing Product
label | c8281654-1654-44ee-a762-42abb3e078fc |  | note | REFERENCE: Product TDS
label | ab723bf7-25c7-4aa7-8eab-1fcdb1e17bf0 |  | note | 610.28
label | b6aa5e1d-9f8e-4dd2-b5ca-1c156c1b0241 |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 50e89f1a-1a75-45b9-a619-3ffdc46f7c21 |  | note | Only whole bags to be mixed with potable water.
label | fa0ec530-fe15-4f57-9b19-867842b2ef7c |  | note | Volume of water matches the required amount for flowable consistency and accurately measured.
label | 5884cd4e-57eb-41bb-99b2-689c989d9df4 |  | note | Product poured into the mixer slowly.
label | 25f18c00-269c-4199-b411-4ba881f6cb3a |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
label | c734638b-c38e-4165-b384-8e752c845bcb |  | note | Enter: Required information on the Grout Pour Record.
label | b0448c43-08f8-4b1f-8e4c-fa0006315cab |  | note | METHOD: Measure , Visual
label | a808b417-be61-495e-9dc8-d5130d01da93 |  | note | FREQUENCY: Each batch
label | 211ee0d3-10a5-4355-b4e2-52ededdfb695 |  | note | CATEGORY: IP
label | 1b27dbf0-f6ca-4118-8b4d-be6e86253309 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 58f1f11d-ed80-48aa-b069-7de13e885c7d |  | note | VERIFYING DOCUMENTS: This ITP
text | 21d910d4-8d2f-4f89-93a7-4028be6ba927 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Product Testing - Compressive Strength Cubes
label | 42ba2d43-d3ae-4032-8957-14210aa0203a |  | note | REFERENCE: 610.28
label | b68ffb99-bc47-4ca9-a306-1255fbbe91ad |  | note | 610.33
label | af9ef3d6-e74a-4aeb-9293-25b6cda1bd02 |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | 31996608-fde6-4acb-966d-41d1d7438333 |  | note | Testing is be in accordance with the following frequencies:
label | 64b095bb-6b41-453a-8761-be7a152735d4 |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 853d8362-6d83-4548-95b0-51df3509c9e1 |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | e361237f-83bd-41a0-8eb3-50a84673690a |  | note | Enter: Required information on the Grout Pour Record.
label | 50308706-ee6f-45dc-9b40-efe0181f8d23 |  | note | METHOD: Test
label | 6dc91826-d0d4-4bbe-bb88-6b63dc583b38 |  | note | FREQUENCY: Each lot
label | 41931124-c56c-4e4b-badd-1d681a5a87c1 |  | note | CATEGORY: IP
label | 751a5a0c-d77b-4eb9-9813-79ad6e14e74c |  | note | RESPONSIBILITY: Tester , SE/PE/SPE
label | aac092ba-e9dc-4c89-846f-1db9523a7b91 |  | note | VERIFYING DOCUMENTS: This ITP
text | 94cb63e0-3ee0-46ab-b53c-e8ce72790bba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Placement & Compaction
label | f088ebed-3592-4123-b778-2f4339758e6d |  | note | REFERENCE: Product TDS
label | 32a8ba10-88ef-4e04-aeb4-773155b8ae53 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | e307c596-bdf3-4b81-922d-61177e910df2 |  | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 6dc7bf3d-1f07-4779-bf45-7ead629ae744 |  | note | Product should flow to all areas and self consolidate.
label | f6ed13cf-37a8-4f3e-8dbf-4b7a0f29cfd3 |  | note | Product that stiffens or is showing signs of stiffening shall not be used.
label | d5f40cf5-7a4f-4ae7-8258-04d6ec50c6af |  | note | Enter: Required information on the Grout Pour Record
label | 9f921ce9-3908-4a45-a912-e815caa65802 |  | note | METHOD: Visual
label | 0cca327e-9a83-4402-b536-45cf328717c4 |  | note | FREQUENCY: Each post location
label | 2e55a8f2-3d38-4ad6-9f07-036ae57ee547 |  | note | CATEGORY: IP
label | dd266388-858b-4627-884a-cf6cc7d6ea2e |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 48b23b17-2c5a-4c8a-9ccc-b0391c5330e7 |  | note | VERIFYING DOCUMENTS: This ITP
text | d214f6ac-ddbe-4d31-9486-278e908a312b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Surface Finishes & Protection of Works
label | ace981c0-07f1-4357-ac1a-1f810793a9d8 |  | note | REFERENCE: IFC Drawings
label | 246f5d7e-4fbd-48ee-9fff-9c1995b18414 |  | note | 610.17
label | 0721160e-7900-49d2-b369-d8754776e541 |  | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | 4baa4a75-421c-43f1-bee3-a6ad0787420c |  | note | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | fd39a96a-85d5-4e1f-8ea3-126018406586 |  | note | METHOD: Visual
label | c670e816-5998-40a3-88c0-d135ad1cf990 |  | note | FREQUENCY: Each post location
label | b8da96f8-61e8-4044-a583-7fbf70518957 |  | note | CATEGORY: IP
label | 5dac41dd-90cb-47b9-9e63-eef4e12f022f |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 3dbb4239-3f39-44e9-92ed-a2b2803e20f5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 36ebf752-32bf-4a01-87ca-478cd3c8c735 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Curing
label | 543bc34f-8995-4266-a5d1-f2561747c121 |  | note | REFERENCE: Curing Methodology
label | 4602c0ff-f3fa-4683-859a-1b5285619890 |  | note | 610.23
label | eb6881bf-0770-4be3-be48-1cc8b2da4f65 |  | note | Table 610.231
label | 3ac877eb-d0c4-48c6-a824-4a8f22991b0d |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | fdc579c2-f455-46eb-9465-908c0984118f |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | e8fe8da4-e5a2-4507-bd5b-a4383d96e274 |  | note | METHOD: Visual
label | 433253a6-d757-42d3-9683-77a8fd31b7b1 |  | note | FREQUENCY: Each post location
label | f9fb252d-d4cf-45b1-b0f9-b357ee6b6f85 |  | note | CATEGORY: IP
label | c05f1761-92ae-4f2d-a2c8-2a94acfa3b80 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 6173bb2b-7cca-412d-940e-6498f3afcc38 |  | note | VERIFYING DOCUMENTS: This ITP
text | fcc969ec-16d8-43c6-9a3f-3f34be053f1d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | 0a1f3085-4550-4e42-8797-9974bcaed756 |  | note | REFERENCE: IFC Drawings
label | 712bc534-7327-466b-af20-6f4ba9620d01 |  | note | 631.15
label | d9429056-7e61-478a-9812-fa876c8f42a1 |  | note | AS4680 Clause 8.3 & 8.4
label | a12326fd-5862-40f3-ad73-a4677169e5e7 |  | note | AS4506 Appendix E
label | d9f77c06-a6e9-48ee-8e69-0b2298e00003 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings .
label | 7069ac07-8f96-4831-8aae-43c2de4629ff |  | note | Where damage exists, it shall be repaired using an approved repair procedure.
label | f6c8743f-baf7-4add-9ac9-c6f3ebc0e5c7 |  | note | METHOD: Visual
label | 93956f1b-4a0b-4695-9628-a13eea5b3bac |  | note | FREQUENCY: Each component
label | b47be97c-71d6-40ec-8818-5ef2593a0bfa |  | note | CATEGORY: IP
label | 39d80471-79c9-45e1-bf39-665695d2055a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8e10dcc6-f5c5-488e-a6a7-41fd888ea76c |  | note | VERIFYING DOCUMENTS: This ITP
text | 3e52737e-5713-4f68-bae9-485a050aa00a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | b7347ea4-383d-4d30-979a-eaa90dec6f81 |  | note | REFERENCE: IFC Drawings
label | 0ed92d9c-26a8-4848-88a7-1f0fa3b9e6b8 |  | note | Product TDS
label | d7d4688b-c8fb-4bba-87b9-f926f591cc82 |  | note | 610.28
label | fceeca48-001c-4c33-9b55-9d63d208e177 |  | note | 610.33
label | 7eea0992-1749-476e-b72e-92fdc1f6ff90 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 28ebbd6c-5bb7-49b7-8584-263901aad96f |  | note | 28 day compressive strength per sample comply with the design strength.
label | 76188b2a-219e-4728-a861-d897ae4adf78 |  | note | Attach: Compressive Strength Test Results
label | 7c7123a5-8db1-440b-a091-7a625f6e3808 |  | note | METHOD: Document Review
label | 4fd0907f-3b38-4a58-8199-e204aa3fb353 |  | note | FREQUENCY: Each cube
label | 0c158708-7996-423f-a5e4-a6ff65a55045 |  | note | CATEGORY: IP
label | 574382e9-8f84-42c0-8363-66dbc1f49580 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dd98eef6-bfd9-4386-a9cb-db7bf277318e |  | note | VERIFYING DOCUMENTS: This ITP
text | 6ac54f55-2784-4a37-8fb7-974fa13f19ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | 5059e770-687f-4211-b884-b7bbec704616 |  | note | REFERENCE: IFC Drawings
label | 606114f0-1f95-4e33-a5c6-b11fbb55e1f5 |  | note | 671.06
label | 9baf6b69-5a44-4cbd-988c-e58254687485 |  | note | AS4100 Clause 15.3.1 - 7
label | a514014c-6ab5-4b08-9c2f-e7f87d21b63d |  | note | AS5131 Appendix F, Table F3*
label | 516e7563-152c-4774-b38c-2dfa7a4cce29 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 7c07e500-5502-4c90-99f3-f71c84db5c01 |  | note | Departure from RL = ±10mm*
label | e5c23d32-179c-4bce-a5e8-b40eb1d7b7b2 |  | note | Departure from plan position = ±25mm
label | ed2aff12-7f2e-4b03-9a91-6b970443feed |  | note | Departure from alignment = ±5mm
label | bd7eadf6-72be-4982-92c7-3b749529b4cb |  | note | Irregularities in alignment = 3mm in 3m
label | 78d670b2-e8a6-4331-ae4b-b60f9806dc6d |  | note | Variation in joint gap width = ±3mm
label | 88886655-a112-465a-955f-0a2d101b3499 |  | note | Projection of bolt = +25mm, 5mm
label | 3e733762-e86f-467e-894c-f4f91fe008d2 |  | note | Attach: Survey As-builts / Survey Report
label | 3ea5bb83-505c-40db-96f2-45d9f1ebecd8 |  | note | METHOD: Document Review
label | a281d4c8-fe33-41ae-b257-8ea894a58b5c |  | note | FREQUENCY: Each post location
label | 90f70d61-ea87-4266-838e-bba064d6badc |  | note | CATEGORY: IP
label | a373a05e-5efa-4b4c-a491-fbf5aab92190 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 252e35f0-9c17-41c1-bdd0-1ad38e1070af |  | note | VERIFYING DOCUMENTS: This ITP
text | fddf4fbd-5aed-402e-9aa4-4e239874c64a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 87e9b031-15c3-4aa7-8b59-b80bdd347a89 |  | note | REFERENCE: MRPA Quality Management Plan
label | 86e3ad6b-bea2-4858-916d-a8fb91570e7a |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | aa14db83-f6e2-4641-ae89-4f4f8a29a0b1 |  | note | METHOD: Document Review
label | 8988be7e-5a6d-4c5a-a144-4e215efeeba4 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 3406899d-5b87-4d62-8859-487e24e556f2 |  | note | CATEGORY: HP*
label | 23ac5cdf-5f1c-4cc6-8fdb-c4ec6b55b367 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1b8119c7-bec1-47cc-942e-a9e48e094a43 |  | note | VERIFYING DOCUMENTS: This ITP
text | 23b28d35-c858-4c58-9fc5-5b22bd250857 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6ad4a7d4-ddfe-4d26-8cef-b362e7ef1e66 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 39e74f11-9794-4284-8e50-a948fccefc9f |  | textbox | Name:
text | 5c2170dd-7a7d-4a8c-8d2c-68082e6cb0c8 |  | textbox | Position:
text | 57649ec3-a8e6-40f5-9c95-cf56ba425236 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | Conduit and Pit (Roads) - Installation Rev0.0 | itp |  |  |  | Yes | ITP-CIV Conduit and Pit (Roads) - Installation | 516b1e74-5325-4f2b-80d8-7fec9ca480f7
checkpoint-no-status |  |  | checkpoint | Reference Documents:
label | a1685c80-5b00-4d13-bdbe-070a2b77a611 |  | note | VicRoads Standard Section 733 (April 2019)
label | 6e7ac56e-3696-4ff9-bd51-9b4b61181310 |  | note | VicRoads Standard Drawing TC-1220
label | d183bfe0-4ee6-4052-878e-fefe4d039395 |  | note | VicRoads Standard Drawing TC-2204
label | f0ea1335-5dac-4e2f-a77d-5c43ee90163d |  | note | ITP Revision: Conduit and Pit (Roads) _00
label | 1ea7663b-0fb4-478a-934c-8c74133e5c48 |  | note | ITP template approved by: Romualdo Magpantay(October 2019)
checkpoint-status |  |  | checkpoint | Refer to VR Standard Drawings
label | eaa6b6ba-5c2c-4675-bc0c-c8f78f77bac4 |  | note | Install conduits, pits, and pit surrounds as per Design Drawings, VicRoads Standard Drawings and manufactures guidelines.
label | 5e275a43-0fa2-45aa-b2e1-2b69d2b7d959 |  | note | Refer to VicRoads standard section 733 for reference to applicable standard drawings
label | 08dfae57-a4f0-427c-8f5f-0c1e4c442b8c |  | note | - - - - - - - - -
label | ede69420-90d3-4625-be63-75c9164313de |  | note | Reference - Table 733.071, Table 733.072, 733.073, Table 733.074,
checkpoint-status |  |  | checkpoint | 2.1 - Bedding
label | 81e8782c-10f7-4316-919f-5a27a18542e8 |  | note | Bedding material shall be placed and compacted to refusal for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation.
text | 477bf2eb-ff4f-4e05-b9c9-94e1fcfbaee4 |  | textbox | Bedding Material used
label | 64f50daf-388f-4fc9-97be-9baf58b426d7 |  | note | - - - - - - - - -
label | 60f4744a-04d2-4f19-bc51-bd3e887c4b30 |  | note | References - 733.06
checkpoint-status |  |  | checkpoint | 2.2 - Inspection prior to filling
label | 256d3984-d100-47a1-8a84-39603179cd75 |  | note | The Nominated Authority shall inspect once the bedding material laid and conduits in place, prior to filling
label | 9aa9afbf-6da6-487f-9b59-2448082e93d0 |  | note | - - - - - - - - -
label | e0f7da59-d0ac-48f5-8da3-40e402a0f357 |  | note | References - 733.06(b)
holdpoint |  |  | signoff | Nominated Authority Hold Point
checkpoint-status |  |  | checkpoint | 2.3 - Marker tape
label | 9e023526-69b0-4cb6-b972-f7db27d080a4 |  | note | 100mm wide marker tape is to be installed 300mm above each line of conduits in all trenches. Where electrical and communications conduits are provided in a shared trench, electrical wiring is placed on top of a single traceable communications marker tape.
label | ad6e902f-6e2b-43e6-8487-6db6822dd509 |  | note | - - - - - - - - -
label | bdcffae6-353e-4306-9c59-6c9f4b3629ce |  | note | References - TC-2204
checkpoint-status |  |  | checkpoint | 2.4 - Filling
label | 20e094c1-9b8e-4d1d-b996-4c2ba622bfa8 |  | note | Bedding material shall be placed and compacted 150mm above bedding previously placed.
text | 83e872c3-41d5-4766-8add-da652ca6dbdb |  | textbox | Backfill profile used
label | 89b7eac1-e470-4687-a2ba-618354087be6 |  | note | Conduits under area to be paved:
label | bfa2c27f-3bdd-4420-acc5-006b96afcf8f |  | note | - Selected backfill to underside design subgrade level.
label | 4f1df337-9c07-431d-b4f8-0f4a7c279472 |  | note | - then, Specified pavement material
label | 09323053-81cf-4fbb-98be-3b766873ae25 |  | note | Conduits under area not to be paved:
label | 51f0f087-1482-45db-82fc-8457c6ef3073 |  | note | - Selected backfill to 400mm above top of conduit
label | 2237a827-d366-4097-a9df-572348c47e11 |  | note | - common backfill to FSL.
label | 59ac6e16-5201-44dc-af0c-3adb9e78b067 |  | note | Conduits through existing paved area:
label | 8a3efeff-3940-4167-be8f-125d4e3925ba |  | note | - Select backfill to existing subgrade level
label | b51316fb-c738-4ff9-a0c0-2a1b7f345792 |  | note | - then, Restore pavement.
label | ad74915a-bcea-4202-86e2-4a057b7adcc9 |  | note | - - - - - - - - -
label | 2860820b-f0f3-4b82-934e-cf9954c51fed |  | note | References - 733.06(c.)
checkpoint-status |  |  | checkpoint | 2.5 - Maximum number of conduits per pit type
label | fe1a1751-03e1-4e19-a35f-d1281346bbb8 |  | note | Conduits as per design, ensure the maximum number of conduits in a pit does not exceed the numbers shown in table 733.075
label | 8acc4666-a90b-4182-984a-7a6bb6667b50 |  | note | - - - - - - - - -
label | 2015b395-d0bd-4667-a700-d2af91a82b11 |  | note | References - 733.07(h)
checkpoint-status |  |  | checkpoint | 2.6 - Pit lid surround inspection
label | a9c6536b-488e-4de4-9df3-ec979671397e |  | note | Before the pit lid surround or pre-formed collar is cemented into position, works shall be inspected by the Nominated Authority
label | 51036d78-a19d-455c-beff-770199c942a5 |  | note | - - - - - - - - -
label | e0ae9ab0-0ac6-4743-a965-88a4186a75a9 |  | note | References - 733.07(c.)
holdpoint |  |  | signoff | Nominated Authority Hold Point
checkpoint-status |  |  | checkpoint | 2.7 - Draw Chord
label | 0bd2d039-7914-4ead-beb7-1ad69ee6d63a |  | note | Draw chord is installed in each conduit run where no cable is pulled.
label | 833d611b-b94b-4d9c-968f-ffa5118229ac |  | note | - - - - - - - - -
label | e3319124-2108-4981-85b4-92cfd21dee3d |  | note | References - 733.05
checkpoint-status |  |  | checkpoint | 2.8 - Certificate of Electrical Safety (CES)
label | 7aecd9e4-0e50-4672-9cc2-15a639536a7f |  | note | Certificate of electrical safety for all conduits and pits installed.
label | 1f2f5158-15a5-452b-ac07-4c6e9f0446c0 |  | note | Suggest labelling each pit with unique ID on as-constructed drawings for ease of reference.
label | 1ef4f1c6-94ad-4e47-b72a-9ce1cabc7b48 |  | note | - - - - - - - - -
label | 0d934e1b-5d29-4376-8678-380252936ef3 |  | note | References - 733.11
checkpoint-status |  |  | checkpoint | 2.9 - As-Built Records
label | 81468f3d-2dd5-428b-9d5f-964a2e6a17ef |  | note | Record on As-Constructed Drawings and Survey pick-up for master CAD file;
label | 0864beac-ff4c-4f1e-bf9e-c530073481ed |  | note | - Conduit size, Location and depth.
label | e526939b-9b80-4f94-a6dc-c9ac974e2b7d |  | note | - Pit location, size and type
label | 0276b9d1-b045-47a7-af26-859a8481eb56 |  | note | Check Works Agreement for project specific requirements relating to stakeholders.
label | 1c2b904e-e6c4-4440-b21c-1797820765da |  | note | Suggest labelling pits with unique IDs for ease of reference.
label | 040d9e7f-86e5-43d0-bb7f-9b5ad8316369 |  | note | - - - - - - - - -
label | 8f5ad1d4-f0ec-461f-812b-4dc064e6264a |  | note | References - 733.10, 733.11
checklist-sectioned |  |  | checklist | ITP-RAIL-Formation - General Fill (Supply & Install) MTM Rev 0 | itp |  |  |  | Yes | ITP-RAIL-Formation - General Fill (Supply & Install) MTM Rev 0 | 5732e6d4-4810-4bf4-9f20-ecb48b212e5a
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | fc4ffc4b-0ceb-45da-a202-9729d7d8a9b1 |  | note | Document Title: ITP-Rail-Formation - General Fill (Supply & Install) MTM
label | 00d0a502-df4a-473d-bbac-92d2dea03f92 |  | note | ITP Description: Formation - General Fill (Supply & Install) MTM
label | 3ce5b3b6-d06d-4966-a527-12b9dde319af |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | 4ea95047-7a20-48d1-8321-c2ecbf207e99 |  | note | Revision Number: 0
label | 95c7bbed-2c27-4695-9146-fa9ba8b35f11 |  | note | Revision Date: 28/06/2021
label | c556b9e0-e58b-4eab-98fe-33c0471bdf2e |  | note | ITP created by: Yasna Naicker
label | 538d7626-95b1-47b1-923b-70d79a6495af |  | note | ITP approved for use by: Romualdo Magpantay
label | b47c9f1f-f75b-44e8-9021-c0e10c344637 |  | note | 1.1 - Drawing Pack - Rail Track and Civil - MRP-016-C-ACD-REP-03-NWACPW-0001
label | 522ecd14-3670-4a4e-ad76-fc06ba578e43 |  | note | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification - L1-CHE-SPE-178 (VERSION 2)
label | ba06ddf0-8fb8-4825-b307-094f2afe4948 |  | note | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard - L1-CHE-STD-029 (VERSION 3)
label | c71be930-34f4-4231-a1e9-fea26f06d948 |  | note | 1.4 - Australian Standard - Methods of testing soils for engineering purposes - AS 1289
checkpoint-group |  |  | section | Preliminary/Material
checkpoint-status |  |  | checkpoint | 2.2 Verification of General Fill Supply Material
label | c4802bfe-54c6-4088-83dc-a606ab4b1abc |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9.5
label | 7c654aab-43f7-4917-8df0-f313ef139cce |  | note | Table 1
label | 0ef423f4-dbcd-44a5-9367-6da6a156bfb6 |  | note | AS 1289
label | 99fbbafe-232e-4fa5-adb4-e75a5d7fc997 |  | note | ACCEPTANCE CRITERIA: General fill shall comply with the criteria listed in
label | c0eacaea-1152-4859-a34f-afedf3e79954 |  | note | Table 1 (L1-CHE-SPE-178 - Clause 9.5):
label | 60dad9f0-6fef-4e28-a8cf-0034c91ed02d |  | note | Soaked CBR - 3% min nominal
label | 5f54364d-448e-42c1-a8e5-baa79371f349 |  | note | Plasticity Index 9-20%
label | 2ff25de0-0f63-4a4a-af26-57819faa979c |  | note | Dispersion (pin hole dispersity) - ND1/ND2
label | 03ee0c39-1a15-406f-a4c8-09aeb1269cdc |  | note | Dispersion (Emerson class number of soil) - not to be class 1 or 2
label | 78af02e7-b007-4d2c-87a4-783e94902d7c |  | note | Collapse strain - to be agreed by MTM geotechnical engineer
label | c48dae6e-3f3d-472c-a559-543ca47a2207 |  | note | Free swell index - 2.5% max.
label | cf382554-9607-42d1-b4e9-a23add3cf019 |  | note | Soil soluble salt content - 3%
label | 72ab454e-3a58-4ef5-ad26-9c590f493715 |  | note | Organic content (dry weight) - 2% max.
label | d117f6b9-6402-4792-b6fe-613a6face21c |  | note | Refer to AS 1289 for Tests
text | 902764e6-8ccb-4683-97c6-9e241454bffa |  | textbox | Team Binder Approval Number:
label | 08649587-3bad-4eed-a7ee-f856baabe82d |  | note | METHOD: Visual , Review Test
label | 89f48112-f2e4-497d-beca-93059608d33a |  | note | FREQUENCY: One test per 1000m³; Volume < 1000m³ at least one set of tests shall be carried out
label | f9bf9d6c-4cb1-4c8b-8b31-653dbeff2f57 |  | note | CATEGORY: HP
label | eb3b045f-aebd-4ed7-95c7-ab9c95481c98 |  | note | RESPONSIBILITY: SE/PE
label | 1af67384-1c89-4610-b84a-175bbefa1acb |  | note | VERIFYING DOCUMENTS: Supplier NATA Material Conformance Certificate
text | ec4ef711-2f62-496b-838b-03283be4e9f1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | General Fill Preparation and Installation
checkpoint-status |  |  | checkpoint | 3.1 Survey set out
label | 0c4e3661-64f0-43b3-ae1d-62c739c97d20 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 8.2.1a
label | 1d88084a-2424-4e53-8bae-5cbaebeedd6b |  | note | ACCEPTANCE CRITERIA: Survey control requirements for setting out and validation of foot prints, level & slope angles
label | e65a7b3c-358e-49ea-9c2f-befb4d392fb8 |  | note | METHOD: Visual and Measure
label | ad2e015c-3627-48f1-8c6c-5ca6a6ca80f4 |  | note | FREQUENCY: Prior to Commencement Each lot
label | 23945f33-55d9-4080-a60f-d09a44a7cc1e |  | note | CATEGORY: IP/SP
label | 3bfdb990-df5c-45a0-a39e-0dec3722d114 |  | note | RESPONSIBILITY: Surveyor , SE
label | ecb87af1-b152-4322-967b-10fd4a71530a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9e483cc7-5637-4e18-b213-fe983b7a387e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Place and spread the General Fill Material, For track constructed on embankment
label | d724cbc5-77c6-44ed-929e-ed8287512135 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.2
label | 075d3d89-af4a-4051-8784-97ebf776a0d8 |  | note | IFC Drawings.
label | c322133e-fa17-43b1-886c-a07dd380c404 |  | note | ACCEPTANCE CRITERIA: Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | 57c3a771-aac6-4caa-a1bf-0f34846673cf |  | note | METHOD: Visual
label | 5ccde21a-f875-4b79-87e3-7664580065d7 |  | note | FREQUENCY: Each Lot
label | cbdf6d63-1400-4eed-a1fb-eff58dde3b76 |  | note | CATEGORY: IP
label | 94718320-a449-4a5c-90c9-63102352c336 |  | note | RESPONSIBILITY: SE
label | b17f1ad0-2163-4491-80ad-310bc6d0fff9 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 814602f8-a43c-4f1c-badc-548d3dd23915 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Confirmation of material compaction & strength by Proof rolling
label | ca65f78d-687d-4ac8-a2d4-64d7497cde51 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9.4.1.a and Clause 8.6
label | dfedbd6f-ff49-49f7-acd2-56c35b210686 |  | note | ACCEPTANCE CRITERIA: Proof roll as per L1-CHE-SPE-178 - Clause 8.6
label | 78b4ee76-e771-4c10-bf19-ba10f3c35d01 |  | note | To confirm the material compaction and strength have been achieved. Earth works layers shall be compacted so they are capable of withstanding proof rolling.
label | 17d28d31-192d-4980-a6ed-330161ccdf78 |  | note | Unstable areas detected shall be remove, reworked and or /improved as agreed by approved representative.
label | 8b3070aa-a7b4-49f6-b41d-192fe25773fa |  | note | METHOD: Visual
label | 961e1cfc-0231-4365-8f97-9f1ddd4445d2 |  | note | FREQUENCY: Each Lot
label | 90be8721-42dc-458f-b98d-7e7a701b11be |  | note | CATEGORY: HP
label | 694463c3-f282-4c37-bc44-66c6602af152 |  | note | RESPONSIBILITY: SE
label | 32fcf153-1c6e-408b-a798-55a62b754d7e |  | note | VERIFYING DOCUMENTS: MTM/NA representative signoff
text | e7ecdf07-aace-40be-b09c-dddf48606f56 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Onsite Compaction Testing to specified densities
label | c31a3919-5dc7-48c1-a2f9-40b977c46f6e |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.2
label | 118bcef4-d9a1-4c8b-928a-71ddede346ff |  | note | Australian Standard - AS1289
label | 53df3758-2783-47d9-a66f-c4168486da1f |  | note | ACCEPTANCE CRITERIA: General Fill shall consist of suitable material that shall be compacted to a minimum characteristic value of density ratio 98%
label | 83062738-7991-4398-9e65-d4c656ab276a |  | note | Refer to AS1289 for tests
label | bbebb977-0220-4e1f-bb82-68f9a5559aef |  | note | METHOD: Visual , Review Test
label | 52a7f34b-42b6-4457-8b23-d60b3fcd3f13 |  | note | FREQUENCY: One test per 1000m³. Volume < 1000m³ at least one set of tests shall be carried out
label | 71b30427-15f3-4622-bbae-a46c2bdab8c5 |  | note | CATEGORY: HP
label | b9579951-a150-4937-8c10-2e1c9283e72d |  | note | RESPONSIBILITY: SE/PE
label | c4e165cf-f519-4b4b-b790-558c82adf516 |  | note | VERIFYING DOCUMENTS: Sign ITP Standard compaction test
text | 9628d5d8-af76-4f1d-9f49-5296ee60a16c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post Installation
checkpoint-status |  |  | checkpoint | 4.1 Survey Conformance Report/As built
label | 857aa28e-2343-47bd-8bda-cf7fd17ff1e6 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 10.1.6
label | 6636ece5-357e-49f1-bf18-874b1b33c3d6 |  | note | ACCEPTANCE CRITERIA: General fill on embankments shall be installed within +/- 40mm of approved design surface level
label | d9774c4f-7d33-4497-806e-3b6158e1c6a4 |  | note | METHOD: Survey
label | b5d14dd1-6841-48be-a893-9cc57c252c93 |  | note | FREQUENCY: Each Lot
label | d48b552e-fbfe-4def-9c9f-dc0a1053701e |  | note | CATEGORY: IP/Survey
label | b34cc3e4-b41c-4cdf-a783-7b282415e9c3 |  | note | RESPONSIBILITY: SE/Surveyor
label | 93c8e958-9356-4e13-9778-f307aa395277 |  | note | VERIFYING DOCUMENTS: Survey conformance report
text | 06022f85-3f18-47e7-b6d8-58841ab68717 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | e87daa93-68ad-473b-89b0-0bb4c21a4485 |  | note | REFERENCE: MRPA Quality Management Plan
label | 3796c2a9-fbc2-43c8-bc34-b7fd72224391 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 1550f4b8-3c75-4b51-91b1-278937f52ded |  | note | METHOD: Document Review
label | 83e96ac6-4a9a-4464-9dc7-df00f7679d6a |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 5912436b-ba5a-42ef-95f8-c727f23a0f9a |  | note | CATEGORY: HP*
label | 663f52b7-9cd6-4e2d-8782-8b5ba37c650f |  | note | RESPONSIBILITY: SE/PE/SPE
label | e13d352a-a002-4747-a2d7-591eb3003939 |  | note | VERIFYING DOCUMENTS: This ITP
text | 96c85b56-5c7b-4287-8f85-c9535846f19e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 7accc9e6-8dfc-498a-a1d8-af657f96129c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0433abf3-977b-410b-8ee2-47d96af41b87 |  | textbox | Name:
text | 1f118b6b-828d-41bc-a470-78f8312a567f |  | textbox | Position:
text | d71fd629-b41b-4bf5-9289-926c4d483af1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-CFA Piling | itp |  |  |  | Yes | ITP-STR-CFA Piling Rev 4 | 574e4246-e25f-4e17-9b7a-93c230b83bca
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 7c502f61-6960-409b-b367-45a0a605aa08 |  | note | Document Title: ITP-STR-CFA Piling
label | 51515e20-e404-4bb1-9f07-612d5e73deed |  | note | ITP Description: CFA Piling
label | 9a3ff12c-6d9a-4b11-80c2-ab16ecf25013 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | d1beac71-1782-4e4c-a383-b4a79d78628e |  | note | Revision Number: 4
label | ede0e416-52e7-4d4c-835f-7c039b17b127 |  | note | Revision Date: 12/05/2021
label | a69ae8cb-c10f-4b66-b78f-d0393c5df921 |  | note | ITP created by: Mike Freeman
label | 4f5d4fdd-da0d-483d-8700-4dc3502660aa |  | note | VicRoads Section 607 March 2015
label | 4b87a692-51cf-4dce-99fc-a44b069decc1 |  | note | 1.2 VicRoads Section 610 June 2019
label | 5e1b1dca-1e93-4b65-9454-2d4337efac9a |  | note | 1.3 VicRoads Section 611 November 2018
label | 26d0cfb3-b5c2-45a0-8b2c-5c7877f37ef5 |  | note | 1.4 AS2159-2009
label | 1576c0e7-167d-4134-b351-15a0e5119f1e |  | note | 1.5 AS3810.1-2015
label | 7086552f-aa0c-4b0f-8558-555253bf50cd |  | note | 1.6 AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 504f2a39-482d-42cf-9299-4c5777b78694 |  | note | REFERENCE: 610.07 Table 610.071
label | 4479763f-cae0-4f3c-a819-b444485c33a4 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | bbb6b4e4-2aed-46f1-926e-b42d6953bfbb |  | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 2a5dfc4f-01e0-49a9-9319-4aa4f3b43277 |  | textbox | Enter: Teambinder Material Approval number
label | 47f4280f-934f-42f7-beef-da050e91232b |  | note | METHOD: Document Review
label | bc1bc3c4-cd0b-4792-b025-c473b65797b7 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | d8a5d15e-f0b2-4ec3-a06a-6cd7c503a214 |  | note | CATEGORY: HP
label | 0433dbca-540c-4b77-9eed-7ae6b37f6049 |  | note | RESPONSIBILITY: Nominated Authority
label | b8568095-cbfb-495e-b96c-fd3bab733bda |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 6f731be0-99f4-4c2f-8919-d0586a489945 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | dd1e611a-ccd2-4f12-a16e-a861bfd03b65 |  | note | REFERENCE: 611.05 (a)
label | d6bddd42-6277-4205-a999-6958cd6a1e2d |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | e8aceada-1f57-43c2-8217-77266ccad5e8 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 4cfb4b7f-2a8e-4aac-ac11-2a3cd731e800 |  | textbox | Enter: Teambinder Material Approval number
label | 6e68f5d7-9ead-4523-85bd-e19a387dd947 |  | note | METHOD: Document Review
label | 2295c051-b836-450d-9a77-a72a3edcc8a6 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 4bb8b189-f2a0-4d15-9844-7331573dcb73 |  | note | CATEGORY: WP
label | 515c5752-5f79-4df7-a4c0-a1d4915c089b |  | note | RESPONSIBILITY: Nominated Authority
label | d80a7a79-bbb4-474f-baa2-9583c7a4a1f8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9c575896-e727-4988-98ce-c13178eba51b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 4123a839-a375-456b-9a1d-db6895732fce |  | note | REFERENCE: 610.26 (a)
label | 2ef6012a-06a1-43da-932e-2869e71b8bd8 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 7ada480f-6425-4f71-afdf-ca9a1a692bc2 |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 0e33a8e5-aeba-4a8b-95ab-a1c947b1e8d2 |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 5ae8643a-e3c2-47cf-8163-4b8ce13a5b82 |  | textbox | Enter: Teambinder Material Approval number
label | 7daa33a6-1003-42d3-a717-6da023f06d6a |  | note | METHOD: Document Review
label | c513a700-d7b3-4968-a4b6-724c8e5a5080 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 8e16f5a7-a857-4b35-86dc-5833f7b04719 |  | note | CATEGORY: WP
label | 85f4a5ea-cf60-42e8-9714-c7efa8727957 |  | note | RESPONSIBILITY: Nominated Authority
label | a1c2ba5d-10a5-46f2-93a1-3101427c03ce |  | note | VERIFYING DOCUMENTS: This ITP
text | a18d2b01-a723-4b35-87ea-e24ad4ccf378 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Piling Operations Work Procedure
label | b810f559-2499-45b6-81fb-5d4e8aef144a |  | note | REFERENCE: 607.01
label | 02ef7ec0-1dda-4178-88bb-a3c67798dce4 |  | note | ACCEPTANCE CRITERIA: Where concrete CFA piles are proposed for bridge foundations and other structures on or over roads, the following documentation shall be submitted for approval to the Nominated Authority:
label | 26fbbe20-0624-4008-b824-8ed23be3409b |  | note | i. plant & equipment for the Works
label | 3f532cb2-0d3d-4cf1-a81d-4fc6be23ea81 |  | note | ii. method statement for pile installation
label | 000b988f-e215-4b4b-a478-3e9eb62f01d6 |  | note | ii. ITPs for installation & testing
label | 90bad35e-b389-4573-91fc-2fc3689e931e |  | note | iv. training & experience of piling crew
label | 38ecdb60-c615-4e26-bffe-b06e6916f711 |  | note | v. training & qualifications of on-site & off-site engineering & geotechnical supervisory personnel
label | a8fb4184-d06b-4219-9900-75da0089ce9c |  | note | vi. the method for achieving verticality & pile position
label | 34ef7d82-00b1-459a-be57-df9190828de2 |  | note | vii. the method of measuring penetration rate & torque during augering
label | 9a781e49-0a0f-47d4-92ba-06e4d9ad6d55 |  | note | viii. the pile design and founding level (if this differs from the design)
label | f53e8755-b420-481d-a1d2-4507013a4e22 |  | note | ix. the procedure for checking that the pile toe has reached the anticipated founding stratum
label | 4865c917-f30c-4c5f-8188-1a37d6fdf66e |  | note | x. the procedure for reviewing the design of the pile if ground conditions vary from the anticipated conditions
label | 2e037fad-1c9d-4f91-933f-e52e7ece7a69 |  | note | xi. the method of extraction rate of the auger
label | 5bfeed41-bd67-413f-89e3-313837ee37bd |  | note | xii. the method of measuring & monitoring concrete line pressure
label | 436293b5-03f4-4c13-bc59-2cb51dbc43ea |  | note | xiii. the method of recording concrete flow
label | bcf5d08a-682c-4de0-9681-52ad4bf4a3f3 |  | note | xiv. actions to be taken if the concrete supply pressure &/or flow is not maintained
label | b89763b5-f779-4e44-a85b-83ef0ef7f086 |  | note | xv. the method of installing the reinforcement cage & ensuring the correct cover
label | 39938194-de86-4396-b223-1beae5493b9c |  | note | xvi. the method of spoil disposal
label | 0cad3357-c969-4eee-ae0c-f5defa44955d |  | note | xvii. the methodology of determining the pile capacity below the ultimate retention height of the test pile (for earth retention piles only)
text | c2516975-2a37-400c-ac56-d3f97e21ec4d |  | textbox | Enter: Teambinder Approval number
label | 0c31673e-b858-4d01-aa4e-ab4369efa6fe |  | note | METHOD: Document Review
label | 75aa26a3-0f0a-4d50-abc0-d9e464e3a8a9 |  | note | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
label | 32b2b7c1-41e5-4f00-b87a-480c63dd9091 |  | note | CATEGORY: HP
label | 7c396c69-3c91-4eb5-897a-ec645bce2a31 |  | note | RESPONSIBILITY: Nominated Authority
label | f99fb8e1-141f-4b1f-ada9-39cb99694182 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 54933c3b-f8ef-41cc-8c9b-d0b584a9e03b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation (Continued)
checkpoint-status |  |  | checkpoint | 3.2 Casting Under Water Procedure
label | d756141c-3cf9-4a61-a7b1-f46bd844f3db |  | note | REFERENCE: 607.04
label | 5da64d93-e99e-4398-96cd-ea1187cc64a5 |  | note | ACCEPTANCE CRITERIA: Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
label | 80632f63-de7a-4900-8b51-8edfc5233a93 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
text | afaf408f-0d5d-4ae6-b0a3-84586ebe12c4 |  | textbox | Enter: Teambinder Approval number
label | 593efef4-e237-4f0e-9555-d8d31db841ee |  | note | METHOD: Document Review
label | 98459456-570e-4937-832a-4fbe1fe12c09 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 235b2e8f-9890-4d63-8895-5d5942574bb2 |  | note | CATEGORY: WP
label | 00a4998b-c61a-4625-84cc-bc094b275dcb |  | note | RESPONSIBILITY: Nominated Authority
label | 4c2ba663-4b81-4d29-91a4-ff04252e71e4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1a243704-abd8-458a-b515-9c6a22b617b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Dynamic Pile Testing Procedure
label | ba65f9be-56d8-4df3-8779-c0426072c84f |  | note | REFERENCE: 607.01
label | fdf4b543-940f-4afd-abae-39348e8e935b |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
label | da41c607-bb2e-43ca-a317-e5ca1bcd526b |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
text | f20d83cb-3ffb-47af-b9ad-c584b370d267 |  | textbox | Enter: Teambinder Approval number
label | 8fb50ba1-9457-4289-92a9-2034abc0b243 |  | note | METHOD: Document Review
label | 4c95d366-d2d5-4347-91e7-dc4c473b859c |  | note | FREQUENCY: Once, prior to testing
label | df313dca-75e3-4ff3-bf6c-dcb2b7a3f69c |  | note | CATEGORY: HP
label | 5d5686fa-21b1-4382-939e-5311c6d33a29 |  | note | RESPONSIBILITY: Nominated Authority
label | ca07c943-bca9-4082-b5fa-cf840359ffaa |  | note | VERIFYING DOCUMENTS: This ITP
text | b113ce09-4884-49a2-b4fd-ed3230d79433 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Pre-qualified Pile Testing Consultant
label | 81e6c0f4-640a-44c3-9872-527539840136 |  | note | REFERENCE: 607.07
label | 55c21469-6b94-4307-ad1e-06bbdfdb940b |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a pre-qualified consultant who is independent of the piling contractor.
label | e6f5dfbe-dfa2-4af2-9678-75c0c555c9fa |  | note | Details of the consultant to be submitted for review to the Nominated Authority.
text | 42d27642-cca9-4c0a-ac70-8a20f988db17 |  | textbox | Enter: Teambinder Approval number
label | 776f1799-d67b-4490-9f3a-43115601b2e9 |  | note | METHOD: Document Review
label | 80b698f2-2774-4e6c-a12d-815e6df06389 |  | note | FREQUENCY: Once, 2 weeks prior to testing
label | 424d5a93-1b6b-458a-b537-dd1504c3d56d |  | note | CATEGORY: HP
label | 6f79e528-0b72-4d3f-a47f-bd4de8c14501 |  | note | RESPONSIBILITY: Nominated Authority
label | 49c6b26e-9fd8-4709-b13e-eaa3a28f6212 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c5e106fa-5c72-4df3-9b42-e67d28e0f961 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Reinforcement Welding Specifications & Qualifications
label | ded184f0-b9f4-4c94-a999-1fdbe79b3939 |  | note | REFERENCE: 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
label | c8d9e2d4-aa6a-40d9-a564-85ad6caf69d6 |  | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
label | b63671e3-a3e6-4975-8ce1-d425ade0387b |  | note | Note: Tack welding requires the same documentation but is a Witness Point
text | aa9125b5-ad57-4708-9074-c5cfcd8e76fb |  | textbox | Enter: Teambinder Approval number
label | cc8b1a08-c3c0-42e3-b6e2-ded47b08e732 |  | note | METHOD: Document Review
label | 6aa30d74-f5d6-4d99-baed-5ce3962a0af6 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 33f01d23-c70c-41d3-b6cc-635c3decde0d |  | note | CATEGORY: HP
label | 299ac877-7061-4fd1-96a7-5be23375763a |  | note | RESPONSIBILITY: Nominated Authority
label | 43b5de44-ef85-4de9-8d10-91c22c75e24f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b3a3a8ad-3c70-4f4e-9f4d-687db2acaf7e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 9e6b4fd8-87f0-42f9-a84f-c58398a6dc69 |  | note | REFERENCE: MRPA Quality Management Plan
label | bdfc995b-3150-4ee4-bdcd-4eddbc4e34be |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 33a94218-0543-4358-8fd2-bf2d816b5a31 |  | note | METHOD: Document Review
label | eb4bc90c-cf5f-4be3-bbbb-64dad7bc3aed |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 98df4285-0ff5-4a19-b033-5fe3c6311e43 |  | note | RESPONSIBILITY: All
label | d7e3786e-aa8e-4126-8586-9d92419c4bdc |  | note | VERIFYING DOCUMENTS: This ITP
text | 41e840d7-6105-49fd-99af-9dc5a75dd9f7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 160a52e9-c4ce-4fc0-b1eb-b08a999fce8b |  | note | REFERENCE: IFC Drawings 607.06 (a )
label | b403c33f-565a-494b-994e-dec8f63e4a0b |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | dc9c3e3f-1bde-4ed6-879c-e2aad1a5c2ff |  | note | METHOD: Measure Visual
label | 4914c351-6dae-4cd5-ad03-512588a7f848 |  | note | FREQUENCY: Each pile
label | 93ff964e-1c38-4b75-8d8d-13e8f29cc407 |  | note | CATEGORY: IP
label | f1679229-416d-4ba4-8a37-70b843b407b1 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 772ea2cf-01a6-40ab-8160-21bda2cbe268 |  | note | VERIFYING DOCUMENTS: This ITP
text | 34b735bc-368a-46f9-bdcc-5a1a814f9307 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 920630a1-571e-4141-ac2e-1cfd1192f6a8 |  | note | REFERENCE: 607.05
label | 24681f43-2ed4-4092-bda7-7f00a444a998 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not: i. result in damage to adjacent newly cast piles due to ground vibration. ii. commence within the lowest dimension of either 2m or 3 x diameter, from newly cast piles if that pile concrete strength <15MPa
label | 5b0d725f-bc9b-433d-a22f-f77097627ff0 |  | note | METHOD: Measure Visual
label | 52783a7b-557c-4679-8f94-9b17e1b2776b |  | note | FREQUENCY: Each pile
label | 4576035f-1c9e-4b1b-9cf6-df07a8fd34b4 |  | note | CATEGORY: IP
label | 60182ad4-17dd-4735-8583-fc45881cc0fa |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 18a7d582-d4fb-424f-8ae6-8e920f96b135 |  | note | VERIFYING DOCUMENTS: This ITP
text | ecc5c138-21c1-46ee-947d-47444a4a8b73 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Reinforcement - Inspection
label | 8bb588ea-66fc-4da8-a6b5-bc07ee4d9065 |  | note | REFERENCE: IFC Drawings 611.06 611.09 611.10 611.11 611.12
label | 43a4bfc0-ba3d-4446-9b47-c33bd974d5fc |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 0a117d9d-a91c-47f4-a180-a18f0d63bb0c |  | note | Projecting reinforcement is the correct length and location.
label | 32987395-c066-437a-9813-13eda56fac92 |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | 508f23b6-16a9-4b1a-9101-83e31fd0641c |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 87c3245f-0f6c-4be9-ad64-3699e9833baa |  | note | Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | dc05f709-88f5-4334-9c9f-f359563eb998 |  | note | The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
label | 575c8ff9-8bf8-4224-b648-2e8aa62f64b6 |  | note | METHOD: Measure Visual
label | a11842ae-81cd-4a57-81fe-0d37666dcf1b |  | note | FREQUENCY: Each pile
label | 6cbcb408-9962-4230-9088-c63d69569214 |  | note | CATEGORY: IP
label | 11fa1816-e086-4806-a31c-be0dd772d336 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 72eb6df2-a91c-4670-be3e-78067e71b9f0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 747ecf14-065a-47e7-8e25-1845c266d3ff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Reinforcement - Electrical Continuity
label | b8596cbc-f2a8-4d52-89b0-f6c3f675b50c |  | note | REFERENCE: IFC Drawings 610.29 (d) 610.43
label | 026b3a64-b5a5-4e83-bb8b-2ea276463684 |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by: i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable) ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar) iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required. Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 16e39217-8f10-4309-bdbc-72b07b81b940 |  | note | METHOD: Measure Visual
label | 5c9d8b0b-4d6f-473a-b3f1-43ea06b09efd |  | note | FREQUENCY: Where applicable, each pile
label | 151813cc-c01d-437e-bb0b-68f13e8ae3de |  | note | CATEGORY: IP
label | a1de6b89-9805-4fe2-a144-a2fa67db8592 |  | note | RESPONSIBILITY: Earthing Engineer SE/PE/SPE
label | bca38cf5-86ba-4ca4-a5ce-b46ab10d4d3b |  | note | VERIFYING DOCUMENTS: This ITP
text | 56bb294f-9afe-4283-a245-6c71ba6e61dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Augering Operations
label | f10a5f43-8e10-4996-b6cb-08ed651e2d97 |  | note | REFERENCE: IFC Drawings 607.04
label | 254a7b6c-48e5-401c-979a-905c9975e769 |  | note | ACCEPTANCE CRITERIA: Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer. The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process. Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
label | a6759da7-e0ee-4b75-939d-7e78ccbb9620 |  | note | METHOD: Measure Visual
label | 9cbfc20f-dc70-4b25-add7-34fac037be39 |  | note | FREQUENCY: Each pile
label | 3805b5c2-23d8-405a-a2bf-600109d53e14 |  | note | CATEGORY: IP
label | b8adc346-1f9a-47a4-8ea2-8b168df2d592 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 532f96dc-c4b0-4139-850b-88c5f6e08641 |  | note | VERIFYING DOCUMENTS: This ITP
text | 770b2a4c-517a-41a8-bfe0-200e3ed77996 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Inspection of Excavated Material
label | 24445bb5-aa0a-4537-ae2c-17335d2766d5 |  | note | REFERENCE: 607.04
label | 49c779ed-ee51-4099-b165-843e5c3c68d5 |  | note | ACCEPTANCE CRITERIA: Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions. Attach: Geotechnical Field Sheet or Report
label | 40305560-6775-469a-87a8-c2e835456dea |  | note | METHOD: Measure Visual
label | ff45cdb2-a598-4733-844e-29f70c0997b1 |  | note | FREQUENCY: Each pile
label | 2189b339-7031-4921-949c-a0476482c52f |  | note | CATEGORY: HP
label | a157e622-36ee-4855-81ee-660b696bc30e |  | note | RESPONSIBILITY: Geotechnical Engineer or Nominated Authority
label | 8eeafbee-488e-4c8d-835b-6a47f7fec545 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 6836f690-f81f-4858-9617-e976fbd0170b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Increase in Depth Beyond Design
label | 9be04b29-fbfa-47de-b844-f7f96b9a1b38 |  | note | REFERENCE: 607.04 (a - d) Piling Operations Work Procedure
label | 4a8ff52e-2b56-4d94-82a5-c11547713c8e |  | note | ACCEPTANCE CRITERIA: Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity. A full account of the changes shall be submitted for approval to the Nominated Authority: Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
label | 2932ebfe-2481-4310-b71b-fd45aa6f9a75 |  | note | METHOD: Measure Document Review
label | 709ba39d-c790-4992-aa34-2a055400357a |  | note | FREQUENCY: Where applicable
label | 9ac5e348-d3d8-45c3-84be-3c77fd8e269e |  | note | CATEGORY: HP*
label | d2a59c18-7a70-4c5d-8b08-4ec809e0e0cb |  | note | RESPONSIBILITY: Nominated Authority
label | f717514a-5a42-4fe9-b49c-89eea9c888d4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 79a6dfe7-3eb3-4063-a70f-7b64517727ff |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Weather Conditions & Evaporation Limits
label | c559cfcf-b175-4a76-b5a9-d3a645e96b63 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
label | 82ace5f6-12a0-47a5-9b29-2c8d23592c48 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
label | 43ac973c-ffaf-4e73-8ab4-5c6ed55b091d |  | note | METHOD: Measure Visual
label | 8edbf7e3-634f-4618-8e46-485adc06e941 |  | note | FREQUENCY: Each pile
label | 1d1fc509-8815-42bb-90de-ad5c989d0047 |  | note | CATEGORY: IP
label | 76d4e641-86a5-4cac-bd4c-da8b8ec39a31 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 5b716fe5-b449-4b41-aac0-151ae9cdf074 |  | note | VERIFYING DOCUMENTS: This ITP
text | d1c2c472-548e-42e5-a30b-225ec951a466 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Concrete Testing - Sampling Frequency
label | ba257862-7ea6-4ce8-9e34-660f36d9a1c4 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
label | b3c8a5e0-32ad-4185-89a7-d163981f2a95 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 71f30fe2-8316-4f62-bea0-a35ea2f06e2a |  | note | 0m³ to 10m³ = 1 sample
label | 85ccc3d9-d6fe-44b2-ad04-d81059741d6e |  | note | 10m³ to 25m³ = 2 samples
label | 52613b42-39f5-4ca5-b52b-ef28114b871f |  | note | 25m³ to 50m³ = 3 samples
label | 79ba3800-5b27-40bc-ab43-0fc22871c3d9 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | a0dfa371-6b0a-4e2b-ac2b-8d6fa9217c1d |  | note | For each additional 50m³ and additional sample shall be taken.
label | 6eabf55d-9b33-4c30-87da-9ac70c5cd2bc |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 29193b2f-74d3-46b0-8ea6-5faba66ab8c5 |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 95cde35e-207a-4af7-bf91-e7d3f58a400c |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | b85c0954-6b1e-4cc2-ba64-d5c50d8234b0 |  | note | Record: Required information on the Concrete Pour Record.
label | 3a7ef252-71f4-433b-b255-4478e554e621 |  | note | METHOD: Test
label | 27d59ea9-f2e7-4e4d-a848-f7fa2eb68f51 |  | note | FREQUENCY: Each pile
label | b676f242-82bb-4cae-841f-4e4a47c75971 |  | note | CATEGORY: IP
label | 8bbc1ec5-6ee1-4e0c-8dde-e38b0df8067f |  | note | RESPONSIBILITY: Concrete Tester Foreman SE/PE/SPE
label | d73de53d-73e7-44dd-9160-f1f0d3facb03 |  | note | VERIFYING DOCUMENTS: This ITP
text | ca3419b4-1c2c-4c52-b166-264d0a3fca7b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Concrete Testing - Spread, Passability & Viscosity
label | 80f689e3-52cf-4520-93c9-1038657c5d3c |  | note | REFERENCE: 610.13 (b)
label | 104848f5-2bcf-461c-998f-54f4a686faad |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
label | e5817bd7-4610-48c7-be74-cc1a9252a91b |  | note | METHOD: Test
label | 148af6be-1284-49da-bf58-4a6c30359f5e |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 7a91a63c-7d34-4abc-a60b-61790bcd12e7 |  | note | CATEGORY: IP
label | c8867586-7fbb-42a0-83f7-9aa4290ba0df |  | note | RESPONSIBILITY: Concrete Tester
label | 17940862-086d-459b-b866-1a2abfc467c8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 142151f2-6df1-4614-b354-f92610c01ba6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Compressive Strength Cylinders
label | da1d6a40-cc0c-4ee2-9547-50f4d6f86b78 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | f0405ab8-a09a-447b-b3d4-e0ceab6ab7be |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
label | 8a5ffd68-b4f7-4cfd-95ef-11d3480ef01c |  | note | METHOD: Test
label | 49576c67-899c-49ad-aabc-f4e6a654b96b |  | note | FREQUENCY: Each sample
label | 6491256e-3fc0-4d36-8e6d-aab1261bfdd3 |  | note | CATEGORY: IP
label | a9d6e9c5-7606-491f-9b21-4edd2f34a110 |  | note | RESPONSIBILITY: Concrete Tester
label | dce9e481-6126-4994-a3f0-59d0ed9f3d9a |  | note | VERIFYING DOCUMENTS: This ITP
text | 213e9053-bd2f-4557-bc38-3a86250a9a82 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Placement & Compaction
label | 0d2bdcac-199e-489a-9f27-ae1bf00cf989 |  | note | REFERENCE: Piling Operations Work Procedure 610.18 (a) & (b) 610.18 (d) (i) 607.04
label | 48fcf562-41c6-4e2c-8145-d477559a1de9 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 4977ce35-fce1-42f8-b6c2-70605c26dbda |  | note | The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
label | 26d7dde4-2f1b-4620-8dfe-9880efb1d5d6 |  | note | The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
label | 5ace2156-6a80-46e2-8582-4b2c705a130f |  | note | Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
label | 15d69b23-c9d3-403d-88a0-d1097da87451 |  | note | Record: Required information on the Concrete Pour Record.
label | f1864540-9589-4cf8-a8c2-fe7da24d8c9e |  | note | Attach: Concrete Pour Record
label | cd59dfab-0d90-447e-92bf-2af7258531d1 |  | note | Attach: Concrete Dockets
label | de762eaa-91d9-4dde-8cf1-e8882e8cf26a |  | note | METHOD: Visual
label | f04c69bf-f354-4ac8-9783-b3c40746fa21 |  | note | FREQUENCY: Each load
label | 60feedb2-6fd0-487b-a297-dd487556e72e |  | note | CATEGORY: SP
label | 317046d0-daf7-4185-bcb0-8f1ef7f3a229 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | c1bebf1b-e155-4ac0-b8d6-4ba9630330f6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 66200a10-f3df-4de1-b06c-676c2b13a384 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Reinforcement - Placement
label | d276c6ea-30bc-48cf-acdd-80f73f8e9a21 |  | note | REFERENCE: IFC Drawings 607.04
label | 47f70296-8e6f-46f6-a1b7-e2223a2623bf |  | note | ACCEPTANCE CRITERIA: The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
label | 8d6d429f-76d9-44e0-ae95-b7a8d8bce711 |  | note | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
label | e5cbff6d-4a5a-4905-8c5f-71844ee80daa |  | note | If the cage cannot be positioned into its final level, the pile shall be rejected.
label | 964fc6d0-ae43-4b97-a807-54caf1060dd6 |  | note | METHOD: Measure Visual
label | 8ac6c828-1b45-4076-aa74-58a37c675fdd |  | note | FREQUENCY: Each pile
label | fe89da09-9eb2-4020-9d73-c7128a307e76 |  | note | CATEGORY: IP
label | e3e04bc1-9154-4c60-a411-7ad1b4df9352 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | a73c6090-43d0-45e8-a332-647085e3a525 |  | note | VERIFYING DOCUMENTS: This ITP
text | a7182de8-c38e-4b53-ba46-c61b5f460878 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Cast-in Items
label | 6d4810c8-4bcc-44e8-a2bc-6b9f7fb94b60 |  | note | REFERENCE: IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) AS3810.1 Table 3.3.6.2
label | 2663f0bd-f13e-4288-ada7-ee0eca50d75b |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement..
label | 465b39f1-1980-45b3-80b2-c213efd18ff1 |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 9417feef-0bbc-4912-a478-517c6bb00a9a |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 53689637-45f6-4e12-bb42-3addbbe3edaf |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | e1b724ac-d6bf-48b4-ae82-64f88723bee3 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | e92d4d49-5d9b-4ce0-910f-fa18bd4cde2f |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 1d13d31a-bbf8-4a6d-94ee-bac39459fd07 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | f093e277-178c-4506-a2ba-e8ba60c13656 |  | note | iii. Ducts and conduit location = ±12mm
label | 3b700263-03e8-46ba-84ff-ee6429d59a96 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 597d476f-8d2f-4834-8aa1-72bb6ad3490e |  | note | METHOD: Measure Visual
label | d48cd681-e331-4b41-9907-62cbb252f035 |  | note | FREQUENCY: Where applicable, each pile
label | c6533834-38ff-4ec8-b540-41371095392e |  | note | CATEGORY: IP
label | 9fa89456-4f8b-42fe-93d1-8e8a1121d8ac |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | bff0322a-0416-4e7c-803c-b9138a0b0267 |  | note | VERIFYING DOCUMENTS: This ITP
text | 752cb5af-5754-42b7-92b1-f5ba4f2f3c6b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 071f57ea-adce-4400-81ac-bb9ffcac533e |  | note | REFERENCE: IFC Drawings 610.31 610.20
label | cc0cdacd-8008-4373-8f32-00940092c372 |  | note | ACCEPTANCE CRITERIA: Where applicable, surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 99e3ad6e-80ec-4dba-859b-6daef947f4d2 |  | note | METHOD: Visual
label | 0ab8773a-77ee-43c7-9b3e-7733da5a60ca |  | note | FREQUENCY: Where applicable, each pile
label | 06f88740-6c2e-4b5a-a109-b8d55774a0f9 |  | note | CATEGORY: IP
label | c98ca9ab-49bb-4418-ab4e-545e091d732d |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 48e4e900-7962-4bfd-8e3a-c49987ebf49a |  | note | VERIFYING DOCUMENTS: This ITP
text | 861b4043-ba86-4e4d-9dc9-c43b31a5baf9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | e988110f-695f-43d8-9fbb-cacf0f60a306 |  | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3 607.04
label | 7bf1a0e9-17ca-4f02-bc47-f39b6effe113 |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | 1dcd4bcc-c0da-408b-88c8-f74318124457 |  | note | Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 082ea061-0c7d-498f-bf0f-424a4590bd73 |  | note | Any weak or damaged concrete shall be removed back to sound concrete.
label | 50a7df07-5b43-4f9f-a65e-f46ac5a73a5d |  | note | METHOD: Measure Visual
label | 4c228f45-8055-493d-95d0-de2aa89d14d6 |  | note | FREQUENCY: Where applicable, each pile
label | c6833185-7fa4-47c2-b3ed-f384eb5ee99c |  | note | CATEGORY: IP
label | ce0d395d-3f16-4f5d-a4de-fbb0a89b2143 |  | note | RESPONSIBILITY: SE/PE/SPE
label | fcf56337-2860-4250-b156-880ec4c1b818 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6816759b-10c1-44a3-8147-0233e40086ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 2482939f-a076-419d-b1a1-fa0f5b18d3e6 |  | note | REFERENCE: IFC Drawings Table 610.05.051 610.16 (g)
label | f32a43f6-c303-4646-ac26-29ffcfaa861b |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
label | 4ed7c948-4515-4df2-81fc-ee3ef5862c67 |  | note | METHOD: Document Review
label | de1cf5bf-4ee8-43de-9355-95f440bcceb0 |  | note | FREQUENCY: Each cylinder
label | bd5deac9-3ad1-4691-9221-1c3b4e8cc89d |  | note | CATEGORY: IP
label | c9e0a994-6fab-4fbd-8711-4634af151418 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e8389bad-ee38-443a-ac46-c5d185bf9774 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0e5d95e7-3288-4dd7-b537-13873d0bae79 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 14ca632a-b47f-4e16-9855-8325307816a8 |  | note | REFERENCE: 607.04 AS2159 Clause 8.8
label | 71ea829a-d9a2-4e98-ae0c-39da7534ca0d |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting. Cross-sectional area = ≥90% Attach: Pile Integrity Test Report
label | 66654f52-8c3c-407c-a913-562ab65941c8 |  | note | METHOD: Document Review
label | 8397c5f8-13ed-4404-8e02-8683f551f86e |  | note | FREQUENCY: Each pile
label | 4a6a45a7-8c57-471f-9f53-dcdbfb9ee949 |  | note | CATEGORY: IP
label | bf436a9d-dc52-4ab1-9e75-deb040c1312f |  | note | RESPONSIBILITY: Testing Consultant SE/PE/SPE
label | 09ec89af-f83d-40ef-bcba-524e0e92fb6c |  | note | VERIFYING DOCUMENTS: This ITP
text | a77dc1c4-03de-47f7-a649-01b05d664178 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | 3466b639-b5c7-4756-8b5b-ea4ac5281481 |  | note | REFERENCE: 607.07 (b) AS2159 Clause 8.7
label | 5c378945-e442-435d-9806-650317db39de |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength. Measured Ultimate capacity = ≥ values on IFC drawings Attach: Dynamic Pile Test Report
label | ee022af4-3e37-441f-82db-2a9890242765 |  | note | METHOD: Document Review
label | 9e6fb2cb-48c1-4161-891a-aaca8d8c1799 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | 8fc3423a-17c3-416d-83dd-9a9ff8f485f4 |  | note | CATEGORY: IP
label | 8b90e697-e022-4c3e-a243-fa767e3decb2 |  | note | RESPONSIBILITY: Testing Consultant SE/PE/SPE
label | afc61460-a84b-498d-879b-4af9cd0ebdb1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 99fd25ae-b4ae-49a8-adb9-7c3c5b1fd37b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | fa8b8673-f174-458d-9072-8866d44f2591 |  | note | REFERENCE: IFC Drawings 607.06 (a & b) AS2159 Clause 7.2.2
label | 4265a958-32b3-4f42-bc1a-f3644c535a64 |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 8b35250d-a094-41bd-b504-c47ef9545b3f |  | note | i. Centre of pile head plan location = ±75mm
label | 1d4ce3cc-d56d-445f-96e4-af813b975e46 |  | note | ii. Variance from vertical or rake = 1:50
label | 03bc0101-4819-4bb0-ad93-f21b05d6e600 |  | note | iii. Irregularities in straightness = 1:100
label | a7860a5a-d96e-4afc-b235-1db5f63fb1da |  | note | iv. RL = ±25mm
label | ee496361-b319-40ae-8c01-18a0ea46617e |  | note | Attach: Survey As-builts / Survey Report
label | 9e05655b-fdb3-4ee2-aa81-13f2ba41e499 |  | note | METHOD: Document Review
label | 4f87fb5b-728d-4146-9bd3-827f2d327efa |  | note | FREQUENCY: Each pile
label | 23b0b8cb-f099-4043-a017-2d027701ab49 |  | note | CATEGORY: IP
label | c6b4bc34-4596-40b6-bd76-d6ac72b20476 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | db7dd9ca-a781-4e97-8086-9ef5e036fe4c |  | note | VERIFYING DOCUMENTS: This ITP
text | c32927c7-2bb6-46e5-b8dd-95cbf6d9d286 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | 39f69717-806e-4cbf-8741-952c09d1a4af |  | note | REFERENCE: MRPA Quality Management Plan
label | b5ee7182-264e-4a50-afb2-ed3907b7113b |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 558bd43c-4bd9-4927-850f-fbdf4a762f1f |  | note | METHOD: Document Review
label | 124cdd04-a472-40c8-9f45-4d129799598b |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 693d76ca-3488-4e20-abb5-a2b4eaf88d32 |  | note | CATEGORY: HP*
label | 0ade223b-1147-496c-9c69-17bc06397518 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 775cf99e-8ab6-4f31-afef-4c10ee550afc |  | note | VERIFYING DOCUMENTS: This ITP
text | 84b9a5f1-0fbd-4797-8146-f8a9507d4493 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | b46b68f2-23c7-4834-b9bb-6f23653ba14b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7ce6fde8-f979-47da-844f-44c09486951e |  | textbox | Name:
text | 04c56a2f-9e79-4836-bacd-424cd5c7095b |  | textbox | Position:
text | c9145090-0fe8-4a69-9991-5768f19cfdae |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | Stormwater - Pipe and Culvert Installation Rev0.0 | itp |  |  |  | Yes | Stormwater - Pipe and Culvert Installation Rev0.0 | 58a209ac-c915-4ad6-b962-9f366a68c05c
checkpoint-no-status |  |  | checkpoint | Document Reference
label | 6a36b10f-153b-4f82-974f-8062bdc8bbbc |  | note | VicRoads Standard Section 701 (April 2019)
label | 967fd870-5097-492c-bb85-b0f782631f79 |  | note | VicRoads Standard Section 705 (October 2018)
label | 232f74ef-500a-4c27-963c-c3f37e910e22 |  | note | Revision of ITP template: Stormwater Drainage_00
label | b5e6390a-657e-42ac-9dee-90a76339c507 |  | note | ITP template approved by: Michelle Edgar, October 2019
checkpoint-status |  |  | checkpoint | 3.1 - Conformity with Drawings
label | 54b40914-46d8-48d5-9dcc-f146912a1981 |  | note | Nominated Authority Hold Point is released.
label | b4aa2071-4e94-4092-85e1-cccad67b57d2 |  | note | Position of all culverts have been confirmed by IFC drawings.
label | f45f696b-b13a-4afa-809a-8b32bc69a1a1 |  | note | Notify the Nominated Authority of any design change.
label | d1c4f73f-1ca0-4b77-8110-b861adfefd34 |  | note | - - - - - - - - -
label | 6e4c2eb5-2188-460a-9890-c08b7dc04d6a |  | note | References - IFC drawing
label | b1260e2b-bc99-4d53-8d36-3206b46cfc70 |  | note | - - - - - - - - -
label | 19bac70d-b359-44f2-a247-6089a880248e |  | note | Verification Record - Nominated Authority Hold Point is Released where drainage lines as per IFC drawings.
checkpoint-status |  |  | checkpoint | 3.2 - Pipe or Culvert Details
select | 252da321-52f7-4a7e-b09c-a195c331f8fb |  | dropdown | Pipe Supplier: | Rocla
select | 18ff51ad-4bf9-4f86-8dd7-4d13205c7148 |  | dropdown | Pipe size (mm): | 1050,225,300,375,450,525,600,675,750,825,900
select | da5815fe-b757-44cd-a3b4-e8b9fdaa4c05 |  | dropdown | Pipe Class: | Class 2,Class 3,Class 4
label | b03a5d5c-962c-4648-9079-3222c145a682 |  | note | - - - - - - - - -
label | 45d27dd8-637e-44c8-8571-daa24eb38d7a |  | note | References - 701.04, 701.05
label | e88ab3fe-384e-4fe1-8baa-c82e1c74cd3a |  | note | - - - - - - - - -
label | 4fda85aa-aa1c-4f17-8f10-f92584743f71 |  | note | Verification Record - Refer Teambinder Material Approval for approved proprietary products
checkpoint-status |  |  | checkpoint | 3.3 - Trench Excavation
label | 9552eca0-1d11-48f3-ad6f-7c25640ce609 |  | note | Excavation for the installation of culverts shall include all excavation necessary to prepare the foundation and provide the full depth of culvert bedding.
label | 05d05e4e-ad7d-4a6a-b16a-7de1db202c77 |  | note | - - - - - - - - -
label | b69ef7fc-afb1-47b9-86c6-9992a1ca14e7 |  | note | References - VR 701.14 Table 701.141, VR 701.09
checkpoint-status |  |  | checkpoint | 3.4 - Bedding
label | 4936c113-811b-4fa8-8c70-f63f92980a0e |  | note | Bedding material shall be provided and placed for the full width of the trench. Compacted thickness of bedding material following shaping necessary shall be not less than:
label | f4019800-babd-41e0-9f20-e59156a93ecc |  | note | -100mm where D<1500mm
label | 95dced09-fd4e-4df5-8d33-269ace1da009 |  | note | -200mmwhwere D≥1500mm
label | ce9f772a-27d5-450a-8032-319593811f45 |  | note | - - - - - - - - -
label | d17b07c9-b369-4ff4-bdf7-96f04a098e75 |  | note | References - VicRoads Spec 701.15, IFC drawing
label | 54777c2b-5a8f-41f1-b723-22501374487a |  | note | - - - - - - - - -
label | 12b1c5e0-ee0e-417c-a076-9b0bc6a78217 |  | note | Verification Record - This signed ITP
label | 29885dc6-1caf-480f-9bae-a9bc14393f81 |  | note | Bedding material used is approved by Nominated Authority. Refer Teambinder Material Approval.
checkpoint-status |  |  | checkpoint | 3.5 - Bedding Testing
label | e332c6ec-683f-4990-9451-b5e5186fde1a |  | note | Bedding and back fill materials shall be placed in layers not exceeding 150mm loose thickness.
label | aae1e3ad-2033-4243-9d7e-ef1a7778146f |  | note | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | 177e4ea8-7882-4a74-ae47-fee847033376 |  | note | Bedding shall be compacted to refusal using hand held mechanical equipment and material(Swell equal or greater 2.5%)and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | c92d9f51-b47e-4420-a7fa-fac7dd268927 |  | note | - - - - - - - - -
label | a14823b8-1318-485e-938f-34db66492ac4 |  | note | Verification Record - Record Test Request Number
label | cc94cfeb-8cb7-4f87-a7ea-b7ab0a888808 |  | note | Attach test reports
checkpoint-status |  |  | checkpoint | 3.6 - Laying
label | f3feb9ac-ad5f-457c-8696-8ec300b710de |  | note | Rebate and socket ends of pipe section and shall be placed facing upstream and be fully entered.
label | 88ce743b-facb-4a91-9955-a4ec29486bce |  | note | The lower portion of the pipe shall be in contact with the bedding and shall be shaped to accommodate the joint collar and supported along its full length.
label | d6533e21-13c1-4f43-8d00-5f4489729c17 |  | note | - - - - - - - - -
label | 2eabe293-f70a-4647-a22f-787629d34306 |  | note | References - VicRoads Spec 701.16, 701.17, IFC drawing
checkpoint-status |  |  | checkpoint | 3.7 - Lifting Holes
label | 965b44f8-9dd2-4cca-9deb-00c24586c403 |  | note | Pipes shall be laid with lifting holes uppermost.
label | fb038986-b995-4fca-aba0-f061ebc95f71 |  | note | Lifting holes shall be plugged or otherwise closed off in accordance with manufactures instructions.
label | 99628e0d-5d0f-4c75-8f4c-3d5dbfa7bcad |  | note | - - - - - - - - -
label | 289713ad-0048-427c-a5b8-ec7abe4e5a88 |  | note | References - 701.17
label | ad06af26-1b9a-4f76-b5c3-a0ae6059a6d9 |  | note | - - - - - - - - -
label | ecce6505-9b04-468f-99bd-4e2a37ed60b6 |  | note | Verification Record - This signed ITP
checkpoint-status |  |  | checkpoint | 3.8 - Survey conformance
label | 53b0f37a-ce6a-4813-b49a-da504fbb192b |  | note | Each run of underground drainage shall be Survey verified prior to backfilling.
label | cc001f53-1368-4a62-80d2-24c8c50b8b6a |  | note | Offset pits to kerb +/- 20mm
label | f5fa6eaa-6fc6-4f2a-9ba0-53f29a0ea0fd |  | note | Plan location pits not adjacent to kerb +/- 100mm
label | 5a978c6f-9eb7-42c7-9ae4-ef10d1102a7e |  | note | Invert level of pipes at pits +/- 50mm
label | 1aca822b-1849-4abf-93b4-5ac45a8552a0 |  | note | Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | cae55f5e-107e-49ab-ab06-5d10579a1567 |  | note | - - - - - - - - -
label | 3fafce2f-0c5e-4e15-b112-6c6279d253c9 |  | note | References - VicRoads Spec 701.09, 701.18, IFC drawing
label | ffb476db-2ea2-4880-acd7-1c31e0813682 |  | note | - - - - - - - - -
label | c9d9acd6-1902-4f25-b2b6-fdb475034e25 |  | note | Verification Record - Survey pick-up drainage line. Provide in CAD;
label | 8ee40512-de23-4677-a1ef-d9a6c5dce8e5 |  | note | Plan location pits
label | 86a55712-99be-4db2-ad8c-73d9d34cfa96 |  | note | RL pits
label | 3b1493c3-125a-488c-b691-a280b7fdcbf1 |  | note | Invert level drainage line at pits
label | 1d279cb7-428f-4118-bd5c-f535f77b0e2a |  | note | As-built grade of line
label | f58ad6d3-a2ea-49af-b0f2-3d644663efb2 |  | note | Red-line mark-up drainage plans and long sections to show As-Constructed details.
checkpoint-status |  |  | checkpoint | 3.9 - Requirement for Testing and acceptance of compaction and moisture content(Testing of Backfill)
label | ee11ed5b-81c1-4d84-96e6-05d7a236471f |  | note | Bedding and back fill materials shall be placed in layers not exceeding 150mm loose thickness.
label | 76dd0dab-208f-4e61-9099-8c56ad1c8452 |  | note | Test -minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | 5f119446-1cdf-4db6-ab45-8ce32efbe219 |  | note | Backfill shall be compacted to density ratio not less than 97%. material that has a swell equal or greater 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 14e625a1-fd98-4fa0-adf4-a994400c9b46 |  | note | - - - - - - - - -
label | 85386189-0f9a-47c2-a0f5-da3ac476c30f |  | note | References - VicRoads Spec701.19, 701.27, IFC drawing
label | 18118c67-7601-4686-aa46-f461e000bd60 |  | note | - - - - - - - - -
label | 885a7ff7-a9bb-4930-89fd-5be47fc9d9af |  | note | Verification Record - Record Test Request Number
label | 9ff22b67-d0cc-44a5-8a21-f7f84701b844 |  | note | Attach test reports
checkpoint-status |  |  | checkpoint | 4 - Inspection of drainage line
label | dcee1712-6c35-41f5-a348-cc92e6b5b60a |  | note | All Drainage line constructed shall be inspected after completion of earthworks to subgrade level and prior to construction of pavement layers, by independent Testing Organization using closed circuit television(CCTV). The report shall be provided to the Nominated Authority
label | 92783fed-dc70-4b36-8708-c5499d0ab083 |  | note | - - - - - - - - -
label | 0b804ec2-5229-4591-8877-1dea5c2f1103 |  | note | References - VicRoads Spec 701.28, WSA 06-2013
label | 7ecb9361-6284-4c19-8a82-8c7f512aa128 |  | note | - - - - - - - - -
label | 96356775-3e96-432b-8d02-df32b8af256c |  | note | Verification Record - CCTV footage file name and location
holdpoint |  |  | signoff | Nominated Authority Hold Point
checklist-sectioned |  |  | checklist | ITP-CIV-Horizontal Directional Drilling Rev 0 | itp |  |  |  | Yes | ITP-CIV-Horizontal Directional Drilling Rev 0 | 5f699272-26bb-4709-bc13-10feb407047f
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | ca98298b-07e7-4ef0-adbb-c566ad86d056 |  | note | Document Title: HDD - SEW Sleeve
label | 5d843dad-15c5-4b6d-8ef6-82111bd900ab |  | note | ITP Description: Horizontal Directional Drilling
label | ce55ea5c-6a86-4fe4-ba29-0e2128dc504b |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 53cb3d0d-2485-46f1-a350-d99e478bf9e7 |  | note | Revision Number: 0
label | b0d908d6-b50d-42f1-843a-645e62ccc0bc |  | note | Revision Date: 08/05/20
label | bb30e821-1b6e-4a97-81f3-7529171807c7 |  | note | ITP created by: Thilan Rathnayake
label | c012f62a-4134-49b7-ae32-bf275d8c77e1 |  | note | ITP approved for use by: Josie Pavlou
label | 4f90936e-fdf6-4f6f-9c21-6c04e27a142b |  | note | 1.1 Reference IFC Drawings
label | bd667a91-7512-4350-be4b-e0ab86443e19 |  | note | 1.2 Reference AS 4799 (2009) Installation of underground utility services ad pipelines within railway boundaries
label | e6e574e7-5a22-43ad-9255-f523655f6dbd |  | note | 1.3 Reference MRWA-W-210 Underground crossings
label | 722af9b3-9967-4895-b369-00cfe7f243e8 |  | note | 1.4 Reference MRWA-W-213 Trenchless construction
label | 490406bd-1f07-49ac-8cda-5bcbe671b0b5 |  | note | 1.5 Reference WSA 03-2011 V1.1 Product and Material Information and Guidance
label | 2508f8d5-0446-45b6-a9ec-11e3d7e08e13 |  | note | 1.6 Reference L2-TRK-PRO-032 Track Procedure Maintaining Track Integrity - MTM
label | 276a2a20-8ac7-45d4-b930-e2d6976c2232 |  | note | 1.7 Reference D/17/62901 Design Requirements & Guidelines - Civil Works on, under or over VicTrack Land
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Pipe Sleeve
label | da253e70-6a03-48c2-90be-ee70ef58da28 |  | note | REFERENCE: IFC Drawings
label | fbb5c90b-78c0-4dd5-920a-e6c629934f62 |  | note | ---------------------------------
label | b9085ed9-db42-4a0f-b84d-3db1eedceab7 |  | note | ACCEPTANCE CRITERIA: The structural adequacy of pipe shall be confirmed with the pipe manufacturer to meet the standard of the 450PE-100 PN16 IPLEX Polyplex Pipe Sleeve.
label | 975b9a18-a428-4bb4-bd06-7a605b341746 |  | note | Obtain approval from VicTrack for sleeve material prior to construction.
label | 8c6d89ab-90ec-459e-8731-41f7145377ec |  | note | ---------------------------------
label | 45ac238a-9e56-4e86-8fc1-8967249eb4f4 |  | note | METHOD: Document Review
label | adf2880a-0aae-421a-9441-3b3b107afe55 |  | note | ---------------------------------
label | 27d70020-8fe5-4138-a8d1-b4c871adde90 |  | note | FREQUENCY: Prior to Commencement
label | 99056fc1-3935-4164-8147-aa021aa685b3 |  | note | ---------------------------------
label | 38a5d564-3c2d-429a-a31c-2b411d268c38 |  | note | CATEGORY: HP
label | 34c4c988-dd58-43b5-af5b-f642f1925260 |  | note | ---------------------------------
label | bf955c47-4ff4-46a2-99a9-5245c3b9de32 |  | note | RESPONSIBILITY: SE
label | 3065edea-4894-4c48-84b8-277cf1272db6 |  | note | ---------------------------------
label | d6289756-c048-4563-8a12-75d10b7ac3bf |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate
text | cd2857bc-3558-4df9-8165-40c1a2d56c36 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Grout
label | b8eafdf3-c810-4c80-8099-036e5ac8fa47 |  | note | REFERENCE: IFC Drawings
label | b77a4aa5-c1f0-4c3d-9141-af01a07c1477 |  | note | WSA03 2011 - 3.1 - Part2, Section 15.15
label | 1116baf2-68ec-46d4-8576-f647a95d38dc |  | note | MRWA-W-210
label | 73f8b5bc-e70f-40e2-8e69-9ff92a9bdb96 |  | note | ---------------------------------
label | c76a000b-2cfc-4da3-877b-9c5335aec53f |  | note | ACCEPTANCE CRITERIA: Grout strength to be 40MPa
label | a86e8b61-b0e7-431b-a327-14a4d51cde3c |  | note | Grout shall be a high flow, cementitious material.
label | 3633b45c-18f0-4018-8ec5-bcf36354744c |  | note | ---------------------------------
label | e59893a7-2979-4fba-b6cb-323d1278058e |  | note | METHOD: Document Review
label | acbc4925-9c65-4946-8799-2953d93179d9 |  | note | ---------------------------------
label | 3ac858c7-abf8-4abb-85a1-e06cb0ea0dda |  | note | FREQUENCY: Prior to Commencement
label | e066d01f-6d99-4f92-9eca-f1940c2ab34d |  | note | ---------------------------------
label | 33bcbeb7-11df-494e-9308-a26576a47d3d |  | note | CATEGORY: WP
label | 87de630e-4917-4a86-81a6-4c8c8f827e88 |  | note | ---------------------------------
label | 4f2b2170-64de-4a7c-9e0f-2daead9131fc |  | note | RESPONSIBILITY: SE
label | e5e5ce26-9106-4772-80b0-a52cbcec3c56 |  | note | ---------------------------------
label | bc382aa8-9f45-4864-9ada-c4e44bdc9c1d |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate and TDS
text | 43b884ad-d4f9-4fef-891d-2915957e3376 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Drilling Fluids
label | 5898d4db-bc7f-449e-a1b5-7c37e67a3869 |  | note | REFERENCE: IFC Drawings
label | 181d0149-c68f-4e3a-bd36-5fa3765e1d57 |  | note | ---------------------------------
label | 38cb5c00-32c9-4977-96d3-dc751389e6c5 |  | note | ACCEPTANCE CRITERIA: Bentonite to be used at the drilling fluid.
label | 36607a41-38f3-448f-a7ad-a6d32badcae3 |  | note | ---------------------------------
label | ef0369d1-4836-48fb-bf3c-547f912d5b76 |  | note | METHOD: Document Review
label | 12f86fb4-733d-4e3a-91b0-a576c7d72164 |  | note | ---------------------------------
label | 6fee4fad-0a0e-486f-8ba2-836b478902f0 |  | note | FREQUENCY: Prior to Commencement
label | df036394-f162-40a1-93cb-ec736ebc139c |  | note | ---------------------------------
label | 38ec96d8-5558-428d-b516-0111e98880ec |  | note | CATEGORY: WP
label | 7ec3d669-5851-430d-90c8-d73eadc33bc3 |  | note | ---------------------------------
label | 760f1fc6-1f6f-43a3-ab54-a48cda64a3ec |  | note | RESPONSIBILITY: SE
label | 0e60d329-43b4-44d0-9dbb-23e59f560c3a |  | note | ---------------------------------
label | cc8e5ae0-28db-40be-a7b3-f80657498562 |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate
text | d9498fbc-8dda-4bbd-8743-2140d7170961 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Marker Post and Marker Plate
label | f1059490-a9cf-460e-a48c-3ef832837e91 |  | note | REFERENCE: IFC Drawings
label | fc64bb80-fd7e-49ac-a4f6-1ad237781ac2 |  | note | AS4799-2000
label | 7123e19c-3394-4f4b-ae15-1b300e09af7e |  | note | ---------------------------------
label | d77336a3-ccd8-4543-83d8-0288e8ead76f |  | note | ACCEPTANCE CRITERIA: Be of non-combustible material for the marker plates and of at least fire-resistant material for the pole.
label | e80e361a-750e-458f-89d3-dfa1299f46a6 |  | note | ---------------------------------
label | c4eb836b-861c-44f5-b004-88e480ce67c9 |  | note | METHOD: Document Review
label | d8b650ec-f92f-496c-a8a3-8a0fcfeff10a |  | note | ---------------------------------
label | 0b2b183b-9e29-4bd6-80eb-19a3c209270d |  | note | FREQUENCY: Prior to Commencement
label | bd1928bf-b52f-4d21-862b-f4e46fb1b9db |  | note | ---------------------------------
label | 0a3dbdd8-adf7-4d72-aa9c-9ea636a6e221 |  | note | CATEGORY: WP
label | 71de733c-924c-4db8-8588-ed41615c3c64 |  | note | ---------------------------------
label | 5c0ed230-6585-4ea7-805e-c6aa66a38a22 |  | note | RESPONSIBILITY: SE
label | bfa827cd-ee55-42e1-a084-c24ea45480f5 |  | note | ---------------------------------
label | 2c3c94e8-0337-4e8e-b149-f163bdb893ec |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate
text | f640dbf6-1c15-484e-8b57-7252080ec819 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Poly Welding Qualification
label | 9277f040-95e3-462b-9296-2c8be34b5bee |  | note | REFERENCE: IFC Drawings
label | ef0d1a32-768b-424e-950a-25ea6c441a34 |  | note | ---------------------------------
label | 71934861-d6c4-4b29-a8be-a7b154f2bdce |  | note | ACCEPTANCE CRITERIA: HDPE welder qualifications to be supplied
label | 76dba860-d241-490f-b0a6-bda1b17ddc86 |  | note | ---------------------------------
label | 6796eb52-d89e-4ad4-9be0-ae3758b3ac7a |  | note | METHOD: Document Review
label | 5dbfb4a9-2499-4729-8550-4f22a39a6ad9 |  | note | ---------------------------------
label | eed2d164-5a1e-4eab-a1a1-f486e6d65c5f |  | note | FREQUENCY: Prior to Commencement
label | 5cc55574-70e1-4f64-8fa2-59fa42fc0b81 |  | note | ---------------------------------
label | 92023543-df81-48ea-a39a-a4903b1f843f |  | note | CATEGORY: WP
label | 92ce3cdb-e01e-42ff-aa99-9b12a4a28b79 |  | note | ---------------------------------
label | 83a82e86-f8c2-481a-b93a-ccc55c177463 |  | note | RESPONSIBILITY: SE
label | 036ff581-0371-4f6a-a623-3bf9d457763d |  | note | ---------------------------------
label | 35047eb9-ed73-48fd-aabb-8ca4922f4fdf |  | note | VERIFYING DOCUMENTS: Welding Certificate
text | 436b5618-9611-48fe-adb3-9937db45ed98 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 97bfc2b7-d99b-4c20-a1b7-569db80e6d88 |  | note | REFERENCE: IFC Drawings
label | a1c75f07-714b-4e79-8eaa-b4b566eedac8 |  | note | MRWA-W-210
label | 8bd5eea3-4e75-4be6-9ce7-b30cb84d30e8 |  | note | D/17/62901
label | eb96e9f6-6c92-4e2e-9e4c-726187029f57 |  | note | ---------------------------------
label | 2411a76d-daab-4d84-ad1a-b3b5c34664bd |  | note | ACCEPTANCE CRITERIA: Set out line and level of drilling works.
label | 92974b32-f772-4c64-a02d-aff268515101 |  | note | Survey to mark out existing services.
label | 55f3c685-3df4-4116-8fe1-3c41faf1419c |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | 032131f7-f897-4ba2-afdb-5c4df11ff32f |  | note | Sleeve must achieve a min. 2000mm verticle clearance to tracks. Check FSL of track after lowering works.
label | 801eaf26-2911-4a7d-8eec-1384cdce3022 |  | note | ---------------------------------
label | 73173c60-90de-4315-b6db-697e096ef682 |  | note | METHOD: Measure, Visual
label | aac7aa69-724b-4972-9280-98403cb3243a |  | note | ---------------------------------
label | 810b3364-ec23-45eb-a398-8be03799babd |  | note | FREQUENCY: Each element
label | 67f69950-606e-413c-9728-4461b3b6c530 |  | note | ---------------------------------
label | ab577179-b550-4fc1-95da-6d5a8d0523df |  | note | CATEGORY: IP
label | 6404d984-377f-4cea-adc5-a8dcb6bdb5ad |  | note | ---------------------------------
label | 7f0f1653-7788-4946-ade3-bb7328e89eb6 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | c4e567fe-67cc-4da5-a984-1c44a7b175a4 |  | note | ---------------------------------
label | cbba423c-512a-4091-875c-f124ea9bff4d |  | note | VERIFYING DOCUMENTS: This ITP
text | 498fcdcd-a273-4294-9e6f-23181609a322 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Ground Conditions
label | 648f4f08-758f-4df1-88b7-9e5fef2a422a |  | note | REFERENCE: IFC Design Report
label | 80b4a5fa-055e-46ac-ab97-91cd537694a1 |  | note | ---------------------------------
label | 5a1b973f-5313-416b-9389-95f165952aba |  | note | ACCEPTANCE CRITERIA: Assumed ground conditions are clay and free of water.
label | ddec0a85-4ff4-4f0d-8938-eda5d46cf929 |  | note | Geotech Engineer to be immediately notified if the excavations encounter different materials than expected
label | 418b138e-55c4-45a0-b172-520230908d47 |  | note | ---------------------------------
label | 9d498033-118e-4fe1-b1cf-7c3e2b456546 |  | note | METHOD: Visual
label | 514bd953-5b6b-4fe2-890a-ee9a6e9ae397 |  | note | ---------------------------------
label | 8d4debdc-2216-4077-a9a1-da12d730ba11 |  | note | FREQUENCY: Each lot
label | 8fdcb0c7-67ad-4cfe-9feb-02961bb4774c |  | note | ---------------------------------
label | b687e573-142a-4cbf-8e4f-564b8e446715 |  | note | CATEGORY: IP
label | c9d0f612-0e19-426d-a21d-3f004fbab273 |  | note | ---------------------------------
label | 1aa3aa9d-4bca-4ea0-8c36-40addb16ec65 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 21006477-68e0-4072-ad96-d6d72cd84c5f |  | note | ---------------------------------
label | 88f39e6f-eb0f-4b65-9349-8bbc32e2689f |  | note | VERIFYING DOCUMENTS: Photos, Sign ITP
text | f70bf20f-b949-4b1a-8da3-6fb2025bfabf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pilot Hole Drilling
label | b38c45d9-a18a-4449-a3dd-95cd44cdc07f |  | note | ACCEPTANCE CRITERIA: 75mm dia. Pilot hole to be drilled and rod left inside drill hole.
label | 462304b2-7abc-46d4-8365-4ffb12a694e8 |  | note | To be left open less than 24 hours.
label | 255ab40d-fa60-441a-abde-f7145c3191e9 |  | note | ---------------------------------
label | 6233f7ed-809e-4883-8dda-04dfa85e6cdb |  | note | METHOD: Visual
label | cc8611cc-4c3a-439f-8df7-403d50b0f789 |  | note | ---------------------------------
label | 7b649694-98ee-4449-bc34-04e0532aeb07 |  | note | FREQUENCY: Each lot
label | e2054f3b-047c-4c22-8bc5-15b3a0ee3396 |  | note | ---------------------------------
label | 61404c24-7ebd-42bf-8d69-357c74fe220d |  | note | CATEGORY: IP
label | 93b7728c-1984-4f9b-8354-bfe4c54d06a9 |  | note | ---------------------------------
label | 7783acdb-474f-448c-a02c-7b72d5055cc1 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 16c3845f-4a0d-4e9d-a246-2d093fa6fcb8 |  | note | ---------------------------------
label | 477d43a0-aac3-4df9-bee0-4fa29cc0311a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c289b0dd-9c42-479a-8497-df14bb75cf9e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 HDD Monitoring
label | cc202eb9-4779-4d79-b128-89f66817d755 |  | note | REFERENCE: IFC Drawings
label | 88178a55-1a44-48b7-ae76-a4478a20fa7a |  | note | MRWA-W-213
label | 51009021-407c-4128-bcbe-3b1dca5d4993 |  | note | ---------------------------------
label | eda218c6-edce-4ef9-83f9-1c68cf1f0b50 |  | note | ACCEPTANCE CRITERIA: Inclination and path being monitored as per design alignment.
label | 5255003a-adad-412d-afd6-7650d33ac190 |  | note | Ensure bore hole blockage and fluid losses are detected and addressed by:
label | be71b291-2615-438e-ae32-e935e965b9e6 |  | note | Monitoring drilling fluid volumes, monitoring annular pressureand monitoring cutting returns.
label | cd2ebdb0-68aa-432f-806d-f93697388944 |  | note | ---------------------------------
label | ee606bb9-6e47-4b60-aca6-d7332bd4e870 |  | note | METHOD: Measure
label | 44809629-47ba-4894-96df-486636c0fcbf |  | note | ---------------------------------
label | 94b66f5c-a022-46a6-a33b-e96cdecec3ff |  | note | FREQUENCY: Continuously through installation
label | d092dff4-723f-4a0e-afbc-90d97167cf0c |  | note | ---------------------------------
label | d92be2f6-2d35-4222-8e3e-3bf72dbb1182 |  | note | CATEGORY: WP
label | 6dc91288-fcad-4b12-b843-f06a775e9c90 |  | note | ---------------------------------
label | aa4dc801-415a-4f7d-9227-3789bec001f1 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | da8955ba-d073-4819-85f1-a26824a74020 |  | note | ---------------------------------
label | 765db136-14d4-46b1-8ded-4873a4ae6f44 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 5534892f-f534-478b-b039-acd7f11e39c6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Pipe installation
label | f24156be-f0da-46a2-b8d2-6f80a4a5e54b |  | note | REFERENCE: IFC Drawings
label | d5b104bf-7e1d-4684-baa6-488d4ed3b48d |  | note | D/17/62901
label | 622acd37-8f1b-4b10-a082-a0e537b9d624 |  | note | ---------------------------------
label | 740d9258-f785-451c-b1a2-daf1c4a0873a |  | note | ACCEPTANCE CRITERIA: The 250mm diameter opening is bored, immediately followed by 500mm diameter bore and pipe being pulled through. At max, it would be a couple hours of an unsupported 250mm diameter opening.
label | ab81e8cd-a9ae-4ee8-82a9-f4288440f1cb |  | note | Diameter of bore is not to exceed diameter of pipe by more than 50mm.
label | 7c764cbf-bc03-4d8c-82ba-5039ab949b03 |  | note | Pipes to be installed in straight sections with no excessive bending in the pipes
label | 4124d643-e957-40ab-881d-1d4bda9655db |  | note | ---------------------------------
label | 7cf5f627-fd20-4e26-99f1-afb6aa3ce417 |  | note | METHOD: Visual and Measure
label | 02613f9e-1beb-4fe6-b79e-0697d1cf3c28 |  | note | ---------------------------------
label | f9acc8cc-8864-410e-94f4-11c43a84004a |  | note | FREQUENCY: Each lot
label | 4e6c4914-44ce-43ad-9d37-0eeb08a15d4b |  | note | ---------------------------------
label | e39fecbb-bed5-4b83-b288-d7916765f60f |  | note | CATEGORY: IP
label | 8aecd910-922c-4f26-a1e3-15f4dd069243 |  | note | ---------------------------------
label | 347c34a6-e99c-4be5-883a-7c5932a7a620 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 71d637b5-8ab8-4e7d-91cb-cb68ffe5b4c7 |  | note | ---------------------------------
label | 77f6419d-0e3e-4644-ba65-bd911bf74628 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 36c9cce8-c02a-4476-8e18-b6404148697d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Track Monitoring and Ground Settlement
label | b9238da3-cb64-4470-865b-31b803151201 |  | note | REFERENCE: IFC Drawings
label | c833cfea-24b0-4dd4-aa8e-1dfaacff9ebc |  | note | ---------------------------------
label | 06280707-38b8-4740-8559-a3de2ba1e47d |  | note | ACCEPTANCE CRITERIA: Both tracks are to be monitored at 5m intervals either side of the centreline of the under bore for
label | de80cc21-e1dd-4cde-9658-0ca39d8580e9 |  | note | 10m either side of the bore centreline (20m in total).
label | 94a0827b-dfb0-4120-99ab-4f25bdf5c343 |  | note | If movement above the predicted amount (> 15mm) is visible or any tension cracking is observed at the surface or within surrounding areas, then construction must cease, with drilling fluid still being pumped, MTM and the Geotechnical Engineer notified immediately.
label | bcaa43a3-199d-4fdb-8cb6-5385a78ce5c4 |  | note | ---------------------------------
label | 271dd8c0-29d0-4d8e-a488-028f0d4e07be |  | note | METHOD: Meausure and Visual
label | 972f5ea4-9083-4dd0-bb33-244eaa8cfd5c |  | note | ---------------------------------
label | 0b0c94dc-feb7-4498-a43a-fc70d8e276a7 |  | note | FREQUENCY: Continuously through installation
label | 849a4c9b-a66c-4f69-94ce-1b2649b11339 |  | note | ---------------------------------
label | 829d694f-5496-4a9e-884d-9de88b22b944 |  | note | CATEGORY: IP
label | 823549d2-5406-4615-aef7-5c9ed26d307b |  | note | ---------------------------------
label | 99594869-3709-4b32-ab60-3138ec8cdbbb |  | note | RESPONSIBILITY: SE/Site Supervisor/Survey
label | 3548c5ee-2f8d-4ff6-bd18-0d091617b322 |  | note | ---------------------------------
label | c1c3654f-14f7-465c-b5fb-8be58a55c962 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6ead4228-c34a-46c2-a8fd-0d99a250e4a3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Welding
label | 797cdaf8-4903-4e53-a05f-9f98f08274ab |  | note | REFERENCE: IFC Drawings
label | b79f6e9b-bb8a-413a-a7e1-bed1ae343078 |  | note | ---------------------------------
label | f9830c96-83f7-4eed-af6e-0bc85926bfd7 |  | note | ACCEPTANCE CRITERIA: Joints are to be butt welded.
label | 930e997a-652b-4b50-a2c4-f032212088b5 |  | note | Weld map to be supplied and identify unique joint numbers.
label | 3dd136be-9263-41e5-a70a-ffedb63ccbc9 |  | note | Butt Welding records to be supplied.
label | 811155b6-6873-4621-90f7-0c1e1bed751a |  | note | ---------------------------------
label | 1a5d7d31-f4dc-441a-b43b-6845d66c5846 |  | note | METHOD: Record and Review
label | 083b3c20-0f68-4cdf-a474-1f723a2cf0b2 |  | note | ---------------------------------
label | 9373177c-e5fe-43f4-abca-e0acba370670 |  | note | FREQUENCY: All Joints
label | 6c547f76-077e-42fd-9387-f8b0b16add93 |  | note | ---------------------------------
label | e57413ed-ff45-474f-806e-a26c55bbb740 |  | note | CATEGORY: IP
label | 74d5ebd7-41a0-47a8-898b-3ef2abdd53b0 |  | note | ---------------------------------
label | 46efdde6-4b35-47fd-a662-7de24313b153 |  | note | RESPONSIBILITY: SE/Site Supervisor/Survey
label | bd5706dd-9830-42aa-8045-14823a03d9ad |  | note | ---------------------------------
label | d508852d-b2bf-4764-af1b-6a8f54c73688 |  | note | VERIFYING DOCUMENTS: Sign ITP Butt Welding Records
text | 2d998e47-3c91-4943-afd8-f4a40de4a107 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Grouting
label | e9835495-7cbb-49c2-af76-54fe1b134641 |  | note | REFERENCE: IFC Drawings
label | ba85a6d4-c744-4eea-95d2-b63a7c605a58 |  | note | MRWA-W-210
label | 07eb7c1c-de6e-4ac0-8dbc-b036ee1982c0 |  | note | ---------------------------------
label | f7e95847-13f9-4498-9fbd-061221042939 |  | note | ACCEPTANCE CRITERIA: Pipe annulas to be grouted with liqufill with 40mpa strength immediately after installing the pipe.
label | 4201fece-3485-4b60-8b21-453cb3fcd552 |  | note | Fosroc Conbextra GP TDS to be followed.
label | 4212ccbd-ae01-4eb9-bbc7-23feebb8f725 |  | note | Initial setting time is 5.5 hours prior to trains running.
label | 229b5269-7a09-45d2-824e-371f261367e5 |  | note | ---------------------------------
label | e6dfd884-5d51-4cfb-9f36-f15b7ed72d90 |  | note | METHOD: Review
label | 8324764e-7acd-4414-88fd-60252212a6fb |  | note | ---------------------------------
label | 8547175e-31dd-4747-98fe-d94d273ad993 |  | note | FREQUENCY: Each lot
label | 222aa9ae-1fa9-4f67-b7d4-d936c57a69cc |  | note | ---------------------------------
label | daa2ef62-0456-4652-ad8d-f4561005e1df |  | note | CATEGORY: IP
label | a25e29a1-d8b0-4f45-a149-f78831ce0465 |  | note | ---------------------------------
label | 134abc91-244c-4c74-99e1-38774a6938fb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c6b5a5a8-c9b9-44b9-bb3a-e9946bd3e8e0 |  | note | ---------------------------------
label | 1acef88a-bab9-4d2b-8ec2-6d2ef5d532bf |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 09d65b23-368a-4230-a96b-473371b7b449 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 CCTV
label | 689424cc-a3ae-4ef3-a2b0-a1ccfc51cd5c |  | note | REFERENCE: IFC Drawings
label | a848b5cc-eb3d-4c3c-b35f-5790d3a2bbd9 |  | note | ---------------------------------
label | 8054ff52-c85c-4307-b8f7-d4847f5ff53e |  | note | ACCEPTANCE CRITERIA: Pipe to be inspected with CCTV to ensure pipes are clean, have not been cracked and joints are water tight.
label | 3ed3a306-32f1-4de5-b6dc-55640136068e |  | note | VicTrack to be present.
label | 48a75d45-2050-4b42-b325-887a3a338642 |  | note | ---------------------------------
label | 1b5044dd-2196-4dcc-9801-4dd2b99195c7 |  | note | METHOD: Record and Review
label | 37c3f91b-8ddf-4712-bf82-9e2c4b66dc31 |  | note | ---------------------------------
label | 1a1d5b52-a095-42a0-955a-2f6fcfd0a10f |  | note | FREQUENCY: All Pipe
label | 315cad55-24c5-465e-8617-9208d4a061a7 |  | note | ---------------------------------
label | 80c196e3-ab64-4085-befc-3a1894f0a768 |  | note | CATEGORY: HP
label | ecd60878-f65c-4e78-b96a-0c72d40d1ec5 |  | note | ---------------------------------
label | 7668d200-04b2-4dfd-9dcb-a885e3d77069 |  | note | RESPONSIBILITY: SE VicTrack
label | 7b2b7138-f1f0-454b-a873-13c79ae0ccca |  | note | ---------------------------------
label | 50726d23-38a4-473b-98b0-915762d6dd67 |  | note | VERIFYING DOCUMENTS: Sign ITP CCTV Footage
text | 75528d51-9eb6-41e5-a0e1-b707f9fba018 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Pipe Completion
label | d7f98880-ee73-4ef2-ad38-dc9c2041bb4e |  | note | REFERENCE: IFC Drawings
label | b4ba1551-0fd9-4991-b795-4b1258522ebf |  | note | ---------------------------------
label | 11106d64-aae3-41ad-bfaa-d646220cecbb |  | note | ACCEPTANCE CRITERIA: End of encasing pipe to be sealed at each end by synthetic rubber and sealed with T304 steel branding strap
label | edf52747-92db-4a20-b4e8-da65b4efd2f2 |  | note | ---------------------------------
label | d3a5ac92-2652-4838-ad8b-2153a6d0d9d0 |  | note | METHOD: Review
label | 9f4a82f9-5527-49ba-91d5-6c67854a5a65 |  | note | ---------------------------------
label | 7e190c46-ad11-4170-831f-d18a862be5a7 |  | note | FREQUENCY: Each end of pipe
label | 3a97924d-ea7b-456b-ab1c-939e1a486431 |  | note | ---------------------------------
label | 0f85b2eb-01db-4bd9-9cba-6ab81b03811c |  | note | CATEGORY: IP
label | c717f361-1c39-4baa-949c-3628fe98e799 |  | note | ---------------------------------
label | 83b273aa-2b21-4ed9-85ac-eb261f311fff |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ee1e792c-b3f9-4da0-a0cb-9309ad9f74b4 |  | note | ---------------------------------
label | 7e20bd94-e804-4a05-8196-df3ad67df832 |  | note | VERIFYING DOCUMENTS: Delivery dockets Sign ITP
text | 009debd5-a43c-4268-bfba-f2f8f125b208 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Reinstatement
label | 58bb75f0-db06-4e8d-b1f7-8e267239bffa |  | note | REFERENCE: IFC Drawings
label | 49f6f6aa-6e9c-4674-98a1-806a850c7011 |  | note | ---------------------------------
label | 0fac6902-b451-4235-accc-fc066c20794b |  | note | ACCEPTANCE CRITERIA: Entry pits, exit pits and trenches within the railway corridor to be backfilled using approved fine crushed rock material. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 51e6aca9-2bb5-4874-81dc-3188265d48c4 |  | note | Vic Track Engineer to inspect.
label | f8622af1-a48c-47b4-89ec-ad6d3ea68a9e |  | note | ---------------------------------
label | dc33b612-fec7-41b5-aa48-b9d4b4304a8e |  | note | METHOD: Review
label | a54e715f-037e-4e5e-b746-bce8c6d6150e |  | note | ---------------------------------
label | f7c0d6a9-d9bd-4bb8-a6c1-8b22f301250e |  | note | FREQUENCY: Each lot
label | dcccdd43-b41d-4842-841c-38b8b6996535 |  | note | ---------------------------------
label | f678a905-8dd4-4795-a81e-764eb51ab857 |  | note | CATEGORY: IP
label | 237bd3f5-f51c-41e5-8edb-5e52f8861662 |  | note | ---------------------------------
label | 5ad1506d-9b3b-4d5c-9fa6-a1bd9bdcebe0 |  | note | RESPONSIBILITY: SE/Site Supervisor, VicTrack
label | 82a3d48e-bed8-4b89-b20f-3484949d81e3 |  | note | ---------------------------------
label | 52ab400f-e27c-424e-a4cc-152948ee3ec8 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 8b373b92-f49b-45dc-aadc-b55bd48cfcda |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Marker Post Installation
label | cb7446a7-8c1f-4d1e-b3e5-5f9eeadeec1b |  | note | REFERENCE: IFC Drawings
label | bd655dd8-58d5-4633-b529-f5462ea9fe8d |  | note | AS4799-2000
label | 04af49c6-09ac-433b-9fdf-26139ca09460 |  | note | ---------------------------------
label | 7fcad40d-9e83-4b45-a285-7437d05cacd6 |  | note | ACCEPTANCE CRITERIA: Marker posts to be installed at every 200m intervals, any change in direction and at the entry and exit points of VicTrack property.
label | d69643c5-564a-45c9-a84a-633f1a3dfd87 |  | note | Marker Posts to be placed facing the rail tracks within VicTrack property
label | 04f7ebf3-1840-4051-88ca-edd43b77c2eb |  | note | ---------------------------------
label | 24ca609d-f3da-48e1-b27c-0822826a9d92 |  | note | METHOD: Review
label | 40e3c6b1-9c79-4152-b375-4e28f1cf2e7f |  | note | ---------------------------------
label | d0f845cd-6259-449d-b52d-44d17abffb61 |  | note | FREQUENCY: Entry and Exit Points
label | 4e8219c8-189c-4fff-8c2d-e76f1667c993 |  | note | ---------------------------------
label | bd32dfc8-d765-4048-81ef-ef56788ad282 |  | note | CATEGORY: IP
label | b9b8dcbe-4c54-48f7-aa22-9384a953d367 |  | note | ---------------------------------
label | f1334ca8-5c3a-46bc-a9df-2a6e212e2e14 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | a8aa07b3-e98d-4d95-b374-5bbb9dd0e72e |  | note | ---------------------------------
label | dcdcfa8c-f961-45dc-9b9d-58271ff37a3f |  | note | VERIFYING DOCUMENTS: Sign ITP Delivery Dockets
text | dc8493ae-ab90-44a0-94e2-665460e6686d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Marker Plate Installation
label | 3d48f96d-e1f7-4efd-9496-82c5514af2bc |  | note | REFERENCE: IFC Drawings
label | e4cd46d6-ebf3-44bc-b57f-1486f35bdf80 |  | note | 0
label | 063a102a-1d95-4e60-b6c3-f5ed476a4de3 |  | note | 0
label | b2617180-d9d7-43fd-8b03-26a444f32aa6 |  | note | 0
label | 57b8e722-0966-45cd-8920-e39c0aaad353 |  | note | 0
label | 4868f4bc-7018-43c1-90b6-d4e28a6c347d |  | note | 0
label | c2088265-9b47-4357-9654-27ed41bdf454 |  | note | ---------------------------------
label | 0b8b6b86-e6fd-4085-82c1-8c680d4e94ab |  | note | ACCEPTANCE CRITERIA: 50mm x 8mm Galvanised Steel Plate Welded to Post
label | 071918e6-019f-4ed6-b3ac-90d675e10b6f |  | note | Marker plate riveted to post with 8mm insulated aluminium rivets.
label | cbce4b5b-c6bd-4edf-b5e8-490ff8d22232 |  | note | 0
label | 98446ddb-3436-4899-b427-bb1067be80b3 |  | note | 0
label | a5b475b0-9e00-4ac7-9181-741f63f917ee |  | note | 0
label | 685bc43a-5e99-447b-8489-9315907fb320 |  | note | 0
label | 9e30b051-21dc-4d8e-945a-f87f2f1fd1c5 |  | note | 0
label | 3a1ea314-5470-4329-9256-eb775e88ae49 |  | note | 0
label | 7bb12c4f-777d-43f2-b961-343d098a1e5b |  | note | ---------------------------------
label | c4adbfcd-e2d4-4b2c-9c03-67281f31ee71 |  | note | METHOD: Review
label | 8271b281-754c-4afd-b7be-4e67ee4f5817 |  | note | ---------------------------------
label | b660e075-3008-4ab7-9d21-68845e00aefc |  | note | FREQUENCY: Each Post
label | cf01a830-a0ac-45a6-ba77-20148d461587 |  | note | ---------------------------------
label | 564fa6b0-16a0-4f7a-a7dc-659157de4e2e |  | note | CATEGORY: IP
label | e4b82b02-4644-4106-b997-615ab398d56a |  | note | ---------------------------------
label | 8b40ad98-ec72-4543-81ee-0bdbfeedeee8 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 5ce86495-3d2b-4651-9753-681b28594e2b |  | note | ---------------------------------
label | 19d7d28d-efb2-4698-a907-804acad1d7ae |  | note | VERIFYING DOCUMENTS: Sign ITP Delivery Dockets
text | 027c5b7e-a911-4e1b-b6f6-88e3c9d97c75 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 As-built Survey
label | 8af2cca3-b1a6-4663-9f15-2d8f651a7513 |  | note | REFERENCE: IFC Drawings
label | df22f41f-9bf9-45cb-a291-1e0cdab90816 |  | note | ---------------------------------
label | 449b7021-de17-4def-aa27-e8975d39851b |  | note | ACCEPTANCE CRITERIA: Survey as built report to be compiled.
label | 0b15b42f-37a0-4587-bae8-bd8dba078f48 |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | 2e479a78-f8ab-46d4-b935-2b32a0943b79 |  | note | Sleeve must achieve a min. 2000mm verticle clearance to tracks.
label | 09a1c08e-8c16-4a58-8cbd-2a742cd45ece |  | note | Autocad and PDF reports are to be supplied to:
label | 0d13e7c5-9a17-4075-93e4-bff5244995b9 |  | note | services.applications@victrack.com.au
label | c9cbb454-9d14-48c9-835f-fab5aeb26cf2 |  | note | ---------------------------------
label | 3fe4b5ce-31fd-4412-aee4-95f7099d471a |  | note | METHOD: Document Review
label | 74079bec-8254-4d23-82f1-c3b802af5109 |  | note | ---------------------------------
label | ec9019f0-eea0-42f8-a258-1cf0a0ef1a66 |  | note | FREQUENCY: Each element
label | 3e1adef3-2d84-4a90-924b-20ef629d394b |  | note | ---------------------------------
label | 25a01e40-a85c-4033-968c-aecce8b6890b |  | note | CATEGORY: IP
label | efda3b1b-233c-4a77-b2a7-9071fc1e309d |  | note | ---------------------------------
label | 73b4dcc1-6f6b-4319-91ee-66bdbb2d8c52 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 133af071-0b08-41ed-aa12-68b0f71ba052 |  | note | ---------------------------------
label | f109068f-451f-4550-a1d4-7e646229001e |  | note | VERIFYING DOCUMENTS: Survey As Report
text | 0f8f9936-cd40-47fc-8182-e27f2a7d5c22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Track Inspection and Maintenance
label | 68e67450-3a09-479e-b294-324c85ee5601 |  | note | REFERENCE: IFC Drawings
label | 4046d3d2-717a-4cee-95b9-044dcc910a9d |  | note | ---------------------------------
label | f64f0664-514c-4f4e-88a4-1156bfe9abd2 |  | note | ACCEPTANCE CRITERIA: Once works are completed, survey to confirm settlement of the track and ground are within the
label | cfc75276-4f33-48d1-914c-4a95273b6368 |  | note | predicted design settlement values.
label | c0463765-f9ec-4591-aed8-7be970c476e1 |  | note | Not > 15mm
label | ae6dc80c-c6ae-455e-b85f-0adbedfebf6b |  | note | To be provided to MTM prior track hand back.
label | 3a129c80-81d1-4f47-98af-14b43331ef04 |  | note | Where track has been disturbed beyond the tolerances, realignment and/or maintenance is required by a qualified sub-contractor.
label | 0477439f-0051-4997-9102-bc34133ef5d8 |  | note | Attach: Track Inspection & Maintenance ITP/Taylor Rail ITP
label | c4cd2d01-10d3-4683-9650-aa5c30e1b76e |  | note | Attach: Track Measuring Sheet
label | b471d68b-3221-4b31-a96e-c9f6db7c8fed |  | note | ---------------------------------
label | 7aa4b33d-1c02-41bc-ad1c-5f2c207c5e22 |  | note | METHOD: Document Review
label | 1ae87692-be7d-45bc-9c7e-69a7e896422e |  | note | ---------------------------------
label | 8676cada-05b4-484d-a333-fa1792faffca |  | note | FREQUENCY: Each element Where applicable,
label | c3903d94-bbc4-4f01-991a-b61ecfe3e5e4 |  | note | ---------------------------------
label | b9b5391b-6d63-45ed-8fed-b204e61ba11f |  | note | CATEGORY: IP
label | 3df88a7b-31e7-4fd6-a6f9-fd61d15b2830 |  | note | ---------------------------------
label | a2cdfa31-b95c-49da-b421-6f4b6a04e10b |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 7237ae5b-e7e2-4a73-ab04-f4c9a1db3b1e |  | note | ---------------------------------
label | fe543877-9451-491e-a852-f580d3f49793 |  | note | VERIFYING DOCUMENTS: Survey As Built Report
text | b4a0fbc5-96f3-4710-a397-d101fe19a8c9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Red-line / As-constructed IFC Drawings
label | 7ed7ab39-46a0-4994-90f4-124488221003 |  | note | REFERENCE: MRPA Quality Management Plan
label | 15872009-ee5b-4032-8ac9-1fccd59eaa68 |  | note | ---------------------------------
label | dd6f15d2-8875-4792-8b80-ac82b6b8eea7 |  | note | ACCEPTANCE CRITERIA: All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | 01347473-e893-4b41-9c75-2529e93650a7 |  | note | ---------------------------------
label | 2396c33a-fb0c-46a1-b17b-a18cb739d38c |  | note | METHOD: Document Review
label | 4cf76d22-6213-483d-a035-3be3c57eda67 |  | note | ---------------------------------
label | 2856d229-b355-4dc7-a9e5-fc81777b5d4f |  | note | FREQUENCY: Once, after construction of the design package
label | 27a78dea-7370-4cda-ac83-d605e0c04820 |  | note | ---------------------------------
label | e82ee2cb-9d76-4ace-8414-0b6b1eac0b4e |  | note | CATEGORY: WP
label | b9bed2d3-fe35-49df-90ac-8bcc3f0d287a |  | note | ---------------------------------
label | b0c352c6-ac37-4d36-a9b4-9a256b86350e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 60329399-b8e9-4419-b080-ff9a894092d5 |  | note | ---------------------------------
label | 68ce36db-87a7-4f97-bfae-62ad47da701b |  | note | VERIFYING DOCUMENTS: Red Line Drawing Pack
text | 9d22b3f7-43dc-4d4e-96e7-ae2a582b9e3e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 4fcf723c-57a9-48f3-b6c4-14f9dab918e2 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1a9ccb91-ad5e-4f5a-a21a-8a41000033ec |  | textbox | Name:
text | c0c1865f-b9c2-4a74-abc6-6a88ddfd7dd8 |  | textbox | Position:
text | 8d71b536-d786-41da-b6ee-46c1c35464f1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Expansion Joints (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Expansion Joints (Supply & Installation) Rev 0 | 6695f76f-965b-44e8-8345-e61932bba09f
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 8b254bee-1e2b-49eb-9f5d-0be3ab3ad04a |  | note | Document Title: ITP-STR-Expansion Joints (Supply & Installation)
label | 5bb3a7da-c39c-48cc-84b2-d06cf978a412 |  | note | ITP Description: Expansion Joints (Supply & Installation)
label | 5bd9ae11-a165-43db-abf0-3f38a2e57984 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 92d6be52-1f48-4e57-87a2-1c59d98da347 |  | note | Discipline (e.g. CIV/STR/RAIL: STR
label | f8a9872a-c920-4a64-9a27-c78759d25cae |  | note | Revision Number: 0
label | b7036f65-dcb4-4fd0-9627-1929a7a29b5f |  | note | Revision Date: 16/11/20
label | b97c98d7-a339-4f53-b698-a5018e8e61c5 |  | note | ITP created by: Mike Freeman
label | e79a63f9-0630-4e22-8d13-8d23ab191330 |  | note | ITP approved for use by: Mike Freeman
label | 46836c3b-6682-41c1-98cc-30b8835c8bb6 |  | note | 1.1 VicRoads Section 660 January 2018
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Expansion Joint Design
label | e53e0264-114d-41c6-9d3e-4d1a95f948e7 |  | note | REFERENCE: IFC Drawings
label | f104aece-7574-4cf3-86ae-1843542e3051 |  | note | 660.03
label | 42884814-4a01-43d8-aefe-ccc7183f6e55 |  | note | ACCEPTANCE CRITERIA: The expansion joint system shall match the drawings.
label | 7e49c84a-1ca2-4d0f-91cf-5d86391d94a6 |  | note | Where an alternative product is nominated, the following criteria shall be met and information submitted, (where applicable) and approved by the Designer (for Design & Construct) or the Nominated Authority (for Design only)
label | dbce61ac-9d2a-4e23-a4a4-1a78aa0b984b |  | note | i. details of provisions for inspection, maintenance and replacement
label | 8bd71616-fc0f-49a7-9c67-25a8eb3844eb |  | note | ii. anchorage system details
label | de230b2f-4837-4707-91ed-32f0b10f30b4 |  | note | iii. geometry for casting block-out
label | 61b457e5-9e92-4ae8-8767-3334a59bde29 |  | note | iv. product shop drawing or similar
label | 3b1c79e8-7b6e-4d65-a4ff-53ee2330baad |  | note | v. treatment at kerbs, pedestrian footpaths and barriers
label | 9ce3fd67-fed2-42bc-ab8f-681ee722c194 |  | note | vi. alteration of reinforcement and/or embedments
label | 0a932221-68fb-45d8-8674-f4fc8d23cf29 |  | note | vii. details of nosing material, adhesive, backing rod, sealant and seal
label | 1f428321-ab74-4ff4-b32c-d2573114df22 |  | note | iix. evidence of satisfactory performance and durability of the product under equivalent conditions
text | 22d0aee5-edfb-4ed7-848d-a1e3f614ec70 |  | textbox | Enter: Teambinder Correspondence Approval or RFI Number
label | b5fbc90a-da20-4686-bac2-faaa27a04200 |  | note | METHOD: Document Review
label | 477b9f5f-8e58-4de5-ba79-50ed46d9b0e3 |  | note | FREQUENCY: Where applicable, once, within 4 weeks of acceptance of tender
label | 5e0a9649-f2ed-404c-b7b6-e21a791d871a |  | note | CATEGORY: WP
label | 7a666506-dae1-4601-a976-f7aa2c0a0c13 |  | note | RESPONSIBILITY: Nominated Authority
label | db0ab6fd-c266-4759-b8df-06d54a43ef7b |  | note | VERIFYING DOCUMENTS: This ITP
text | 659f047f-24e5-4c7b-a4b6-975837f593a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Expansion Joint Components
label | 409681d0-2cbd-4fda-b494-4416a2298908 |  | note | REFERENCE: IFC Drawings
label | 976b182f-1e70-40b3-a2c8-729b5a2f9993 |  | note | 660.03
label | 9228677f-444a-47a8-9c23-068e44911177 |  | note | ACCEPTANCE CRITERIA: Steel components are to be manufactured to the requirements of the Drawings and AS5100.4 and galvanised to AS/NZS4680
label | 9db586df-1c39-4d3c-818c-0eb1b71ecda9 |  | note | Attach: Quality Assurance Records
label | 35493bfc-5ec8-4206-928c-49bcc6b40db7 |  | note | METHOD: Document Review
label | fbceb134-695a-4f49-8266-1990be070551 |  | note | FREQUENCY: Where applicable, for each element
label | 8970b93a-3fef-4cf5-a232-af4720af5613 |  | note | CATEGORY: IP
label | a512f783-e125-4fa2-bb06-aca77117adee |  | note | RESPONSIBILITY: SE/PE/SPE
label | ce416428-a057-4a67-913c-dd1838447878 |  | note | VERIFYING DOCUMENTS: This ITP
text | 12aca36f-04b1-44e3-af11-559f3a345941 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Joint Sealant
label | 646357a1-f94a-4f15-81f6-f005f12263d1 |  | note | REFERENCE: IFC Drawings
label | 7892556e-5c5e-428a-acc7-c7734b5573ca |  | note | Shop Drawings
label | 99a1f696-18aa-4c38-ac88-909de3539e27 |  | note | Installation Manual
label | 69f4e9f0-013f-4608-aee8-44f507b86700 |  | note | 660.04
label | 348b0296-ea2a-40b6-9309-528b24fd9d74 |  | note | ACCEPTANCE CRITERIA: Where applicable, the joint sealant shall match the Drawings and installation manual or be an equivalent product for trafficable uses.
text | 121b609e-3d8d-4a64-8947-42369d5f6a26 |  | textbox | Enter: Teambinder Material Approval number
label | 1446eb6a-cc91-4c0f-892b-2602f850fb03 |  | note | METHOD: Document Review
label | f2a59651-6d52-49c5-a6a4-5446d9ab8271 |  | note | FREQUENCY: Where applicable, once for each product
label | aa086e01-5771-4e1d-b09c-b7d45378df0a |  | note | CATEGORY: WP
label | 02dcbb0c-1023-4777-8603-fd65c8e411b5 |  | note | RESPONSIBILITY: Nominated Authority
label | 66a41890-46d2-410c-a766-61c0b793dacb |  | note | VERIFYING DOCUMENTS: This ITP
text | f0e2b66c-017b-4db0-9afa-820232f9ebce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Bolt Tensioning Procedure
label | 3ab2e5bc-c82d-4a32-bfaa-ce9786c10a99 |  | note | REFERENCE: IFC Drawings
label | aae0e4e3-22bf-4704-a4e9-870e4d4e4377 |  | note | Shop Drawings
label | 38be4460-1004-4d3c-aaca-c069ac05df1d |  | note | Installation Manual
label | 65aaa1ce-fcf0-4079-9268-242c0e62c30e |  | note | 660.04
label | afc6635f-e93a-4b4b-aca3-933529db96c2 |  | note | ACCEPTANCE CRITERIA: The Contractor shall submit a bolt tightening proposal to the Nominated Authority.
text | 033a50a9-4eea-4634-8106-a214710f02c7 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 4f14aac5-aa17-40d9-8d49-fa65d409b2a3 |  | note | METHOD: Document Review
label | 38067f97-f518-4338-81cd-fcccf0daa35b |  | note | FREQUENCY: Where applicable, 2 weeks prior to installation
label | 3f43943b-ccd5-472e-87c8-292156ecd025 |  | note | CATEGORY: HP
label | 3337cd80-007c-43b8-a17f-75601c38bc0c |  | note | RESPONSIBILITY: Nominated Authority
label | 055c04dd-af4f-4338-92fb-801809e77fa1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 0a34b2a5-7233-48a7-b6e5-7a34e4975268 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 Installation Temperature
label | 9a95e5db-deeb-417e-b0de-a790f8ca3827 |  | note | REFERENCE: 660.04
label | d46f51c6-8f06-4b14-9ddf-81fa7184a8c1 |  | note | ACCEPTANCE CRITERIA: The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers.
label | ca9ff464-22bf-4d58-b19e-8db35ca60f92 |  | note | Planned pour time to also be within this temperature range or adjusted.
text | 4c2de4c7-50d9-46db-9d7d-829e7a78e51d |  | textbox | Installation Temperature
label | aa353829-8327-4c22-8e35-a2206703facf |  | note | Ambient Temperature at Concrete Pour = See Concrete Pour Record
label | e3d2b08c-d844-4d14-802d-b88141d340b3 |  | note | METHOD: Measure
label | 3f95546d-9708-43f9-b0fc-3555b5219c39 |  | note | FREQUENCY: At the time of installation
label | 647ec825-9113-4dea-a253-d50cd4017e16 |  | note | CATEGORY: HP
label | 0b860b84-6454-416f-bd45-8f97560c1f42 |  | note | RESPONSIBILITY: Nominated Authority
label | a809adc5-2522-483b-ba73-07c7d14da5eb |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 901bcbc0-f761-49a9-b37e-ee3d12244415 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Expansion Joint Placement
label | 7f324f0c-f8e6-4e89-bfd0-2b230fb477ad |  | note | REFERENCE: IFC Drawings
label | bf7de9a0-ad5f-4a1e-9d60-a4d0bbeaf569 |  | note | Shop Drawings
label | 8ddce515-023a-4718-8dc9-42b836d50c58 |  | note | Installation Manual
label | bf6b4b80-c3ed-4609-a426-09a77a4d1fe1 |  | note | 660.04
label | f31b6058-5eb7-4bef-b4e1-22cad92bea05 |  | note | ACCEPTANCE CRITERIA: Place the expansion joint to the survey marks to achieve a top surface parallel with the longitudinal grade and cross-fall of the FSL and in compliance with the Drawings, installation manual and tolerances
label | 5d751ea1-b51d-4680-b7c2-b44e3b27cc15 |  | note | Joint gap = ±3mm
label | 860365c1-4417-4135-ab40-ba9ddca565b3 |  | note | Deviation from plan alignment = 5mm max.
label | a5e7f0d0-313e-448c-9456-8998c7fe2a57 |  | note | Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
label | 36f90146-8982-4c73-a8ae-f9e55b0fad38 |  | note | Record: The expansion joint ID onto the Red-line Drawings or Survey Report
label | df23167b-a29f-4faa-aca6-a3e7b71faebd |  | note | METHOD: Measure Visual
label | 941273ac-3b1d-4a01-8584-39da21d3776e |  | note | FREQUENCY: Each element
label | efc23e4c-f569-4489-8098-2d3d9d93c106 |  | note | CATEGORY: IP
label | 3f93668a-a3eb-4c86-93b1-2abb4b1c6c30 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | a8eadb4c-2d9e-45cb-8cf9-b557d3545908 |  | note | VERIFYING DOCUMENTS: This ITP
text | d8e95faf-a66d-4708-bce8-658f96b251d6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pre-pour Inspection
label | d66a7a47-20bf-4916-83f9-6dd8306a0f97 |  | note | REFERENCE: IFC Drawings
label | de3834d5-04c2-4cba-996f-7c0e27458e44 |  | note | Shop Drawings
label | 5c68bae8-c2f0-482b-8d1f-edcc18ae4c3e |  | note | Installation Manual
label | f4ed2bce-b51b-44d1-a58b-e28811ed7046 |  | note | 660.04
label | 78f94805-2e7e-4440-a510-572109e600fd |  | note | ACCEPTANCE CRITERIA: Reinforcement design to match Drawings and any RFIs to eliminate any conflicts with the expansion joints and/or embedments.
label | 0b286e03-8ae2-4589-bf3f-cb9cbcef6318 |  | note | Tolerances to be within the stated values in 4.1 above.
label | f5780a2b-8b57-421e-a6a9-1a37fd906c4f |  | note | Temperatures to be within range or adjusted accordingly as 3.1 above.
label | 0e601b97-793f-49d0-94b3-b22fee61c9ed |  | note | METHOD: Measure Visual
label | aeac60a2-dcc8-4098-ae7a-ada06fbd4893 |  | note | FREQUENCY: Prior to concrete pour
label | 2b55e767-6f10-4b94-8270-fb2fd5b50d4a |  | note | CATEGORY: HP
label | 2a178058-639a-4c0e-88b5-cb1576113a87 |  | note | RESPONSIBILITY: Nominated Authority
label | e23838a7-3271-4394-a6b8-45cb639471ad |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 953e5419-eddd-46b1-af97-d8d9cc160c59 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Concrete Placement
label | 997c44cb-e119-4737-8cfe-00200e511ad9 |  | note | REFERENCE: 660.04
label | 4199793e-bf1c-4396-90ac-5ffa13f686ef |  | note | ACCEPTANCE CRITERIA: Complete: The relevant Structural Concrete ITP before proceeding with this ITP.
label | 3ffc4685-0535-453a-b0e1-d1f1235d4a55 |  | note | METHOD: Measure Visual
label | f6db0a22-48db-4ba7-93d5-bff795c9342e |  | note | FREQUENCY: Each Element
label | feeb5036-e472-4b3e-b072-5630f255eec4 |  | note | CATEGORY: IP
label | 211a574b-5b4b-4ccc-9473-85d5910af0ca |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 578bfcf6-42b9-44fd-8cc6-47a692dd6e48 |  | note | VERIFYING DOCUMENTS: This ITP
text | eef082a5-c99b-4dbe-b78b-ad3b16f318f7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Post-pour Inspection (Vertical Faces)
label | b7caf674-80ba-4956-a0e0-90b778ff48b3 |  | note | REFERENCE: 660.04
label | 05ef1817-5531-49c8-a946-55feb276e7cb |  | note | ACCEPTANCE CRITERIA: The vertical faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
label | a56bbb28-2a56-4420-bdbd-41278c3ab04b |  | note | If voids are present: Complete: Cementitious Patch Repair ITP
label | 458b7b38-3899-4b5d-909d-84e7271e963a |  | note | METHOD: Visual
label | 20817ccc-2e02-4ae1-adfe-908bd4dd1b5a |  | note | FREQUENCY: Prior to joint sealant (where applicable)
label | 509299d1-6779-4711-8cdf-53e277a40e15 |  | note | CATEGORY: HP
label | c88e6608-3c58-480f-a100-fdc4f6849c28 |  | note | RESPONSIBILITY: Nominated Authority
label | 0488a886-c48a-4d6a-88e0-e79f37de50eb |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e49d341f-0854-4b35-b901-9f3455389e83 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 Bolt Tensioning
label | ae1195c6-0220-4b7c-aff7-c0aea2b02264 |  | note | REFERENCE: IFC Drawings
label | 2f50376a-3bb6-4608-95cc-1bc1704eb53f |  | note | Shop Drawings
label | 7465657c-4a55-49ab-8ac5-74e53709bb5d |  | note | Installation Manual
label | 1ed9b7e8-8212-4e61-9053-77f80ca22de2 |  | note | 660.04
label | bdb50ce3-58fe-4f89-820c-410fd8692882 |  | note | ACCEPTANCE CRITERIA: Bolts shall be tensioned to a maximum of 65% of the ultimate strength of the bolt, using a calibrated torque wrench, the part-turn method or another approved method.
label | e8dfbc37-0d4e-49cf-a8ff-676fb631f40a |  | note | Tensioned bolts shall not be re-used.
label | 0660d4e7-23a3-444c-85b7-1e566a066113 |  | note | If the required tension can not be achieved, raise an NCR.
label | a8790c19-3353-4c02-b2db-4d7a17473a07 |  | note | Attach: Torque Wrench Calibration Certificate (where applicable)
label | 4f69220d-9d5e-4cdb-a3ba-0829ade75019 |  | note | Attach: Photos of Tensioning or Marked Bolts before and after tensioning
label | 8684956b-4779-45be-9577-dfd7c9523734 |  | note | METHOD: Visual Measure
label | c7a01896-a5af-4df7-844c-4a7aaab3ddcc |  | note | FREQUENCY: Where applicable, each element
label | 17177683-5309-4c2d-8e38-d154dfa03442 |  | note | CATEGORY: IP
label | e13c5e77-0308-43cb-87a8-fef36fdf1b0f |  | note | RESPONSIBILITY: SE/PE/SPE
label | a012e970-d015-420f-a529-6a2b349fbb1a |  | note | VERIFYING DOCUMENTS: This ITP
text | 3b489562-c6f7-431e-8be2-bd6678b5b5a3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Compression Seals, Inserts and Membranes
label | b78764b6-926c-4bb9-a7a7-9dfef240305a |  | note | REFERENCE: 660.04
label | bc3b6d13-fc70-4216-9ebe-cda9987de006 |  | note | ACCEPTANCE CRITERIA: Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
label | e7f9c74e-ba08-4673-8c38-aa3ec3791cd1 |  | note | If seals are bonded with the nosing, the surface shall be prepared and primed and the adhesives placed in accordance with the adhesive TDS.
label | 8325d6af-e9e9-4aa1-90de-f8345dae8a7a |  | note | Completed joints shall be watertight.
label | c881d5e1-2775-4827-9e43-a56e14d4f208 |  | note | METHOD: Visual
label | 461addc4-72d8-48d0-b685-7c16a84c2bcc |  | note | FREQUENCY: Where applicable, each element
label | 916be061-9fcc-4f53-b9d3-29d671b7fd17 |  | note | CATEGORY: IP
label | 2900140e-6dd2-468c-9507-2769c4030ace |  | note | RESPONSIBILITY: SE/PE/SPE
label | a52288c5-553c-43c7-99a7-77eacc34e81e |  | note | VERIFYING DOCUMENTS: This ITP
text | ee9c4aa4-ee7f-41bf-b485-4b1690c30ea9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Nosings
label | 12032b67-d62a-4a9f-9eb5-71b1d719da83 |  | note | REFERENCE: 660.04
label | 6e3a6118-b3fc-4b69-b6c2-94c35383f673 |  | note | ACCEPTANCE CRITERIA: Nosing materials shall be mixed and placed in accordance with the manufacturer's recommendations.
label | 798081ec-628b-4abd-a4ce-ffd6fafec296 |  | note | METHOD: Visual
label | 3875b1df-e9d2-42a9-8db8-81d0f4f76301 |  | note | FREQUENCY: Where applicable, each element
label | f5c7d8f2-43e4-407e-b5f5-de210e6a5864 |  | note | CATEGORY: IP
label | 2314cbad-433e-41e1-908b-8d90610b05c7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f48b04e9-3a94-472f-b685-7b26ade01644 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4bfd3968-ddf4-480f-8ac1-8f452b48f1c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Post-pour Inspection (Tensioned Bolts & Concrete Bearing Surface)
label | dd8f20b2-12a1-43ef-bcc1-ff6da14a8511 |  | note | REFERENCE: 660.04
label | e4481041-af73-4106-8321-9aa1207e3f8e |  | note | ACCEPTANCE CRITERIA: After the anchor bolts are tensioned, the full length of the joint shall be tested by tapping with a hammer to ensure that there is no presence of voids in the bearing surface.
label | 2d6cbaa6-a3bb-4e9d-9b50-651ce4dc8032 |  | note | If voids are present: Complete: Cementitious Patch Repair ITP
label | 478759b0-158b-4031-b8ce-861d4111b5da |  | note | Where joints are removed for inspection, the bolt tensioning process shall follow 5.2 above after replacement of all tensioned bolts.
label | 4ca18b40-1e3c-4468-a3de-4c0077a1190c |  | note | METHOD: Visual
label | 48029f07-2c39-47c1-b895-0b62e837da12 |  | note | FREQUENCY: Where applicable, each element
label | 24bff3d6-e851-4249-8154-02a98bf05ea2 |  | note | CATEGORY: HP
label | 142d99ee-0cbf-4408-8fdd-a4fdf83e238e |  | note | RESPONSIBILITY: Nominated Authority
label | 9ecbaf76-d1f3-424d-a450-dffb7fcda1a4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 2451852e-5002-4bb8-a97a-e2cc6195f634 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Trafficking of Joints During Construction
label | 8696988d-126e-4ab5-99eb-8c6a46059b66 |  | note | REFERENCE: 660.04
label | 03c64da7-0668-4afa-a74e-dff5488650e3 |  | note | ACCEPTANCE CRITERIA: Joints shall not be trafficked until all components of the joint have achieved adequate strength to support the traffic loads without damage.
label | e646822e-0993-44ca-833e-9a4bdd12a87b |  | note | Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
label | 57e54513-ad0b-41e5-874a-87ed9958528a |  | note | METHOD: Visual
label | 165326d4-aded-42ab-9867-ae3275679d3d |  | note | FREQUENCY: Where applicable, each element
label | 883af806-1a34-43d6-a3da-9768e9689ca8 |  | note | CATEGORY: IP
label | b58fd65d-4fab-4d68-85e3-ffaeadeb08fc |  | note | RESPONSIBILITY: SE/PE/SPE
label | d7a975bc-6bd8-4c3b-8126-de5b7eab692f |  | note | VERIFYING DOCUMENTS: This ITP
text | efb403a5-5e6a-4f1b-a61f-b14bdcbdf4bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 As-built Survey
label | d0208239-c036-4083-8bd1-eedb3d2f3d22 |  | note | REFERENCE: IFC Drawings
label | 6f272cae-678f-4e3f-a65b-589440829af0 |  | note | 660.04
label | 43d009c4-273a-44d4-9b90-b8edfdb13e72 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 4.1. above.
label | 19d82847-aac4-4d10-b784-7c259a6f080e |  | note | Attach: Survey As-builts / Survey Report
label | 40841cda-bf93-4dc9-a252-c1015d93817b |  | note | METHOD: Document Review
label | 1432e9d5-fcc0-4380-b98f-3a1735083dee |  | note | FREQUENCY: Each element
label | 2b30eb23-1d90-4b61-abdd-c8e843a07f35 |  | note | CATEGORY: IP
label | 0d4c9a90-7f9d-4b5f-9d8b-abe65f344cfb |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | da6470cf-192e-4ba2-8b1e-88a4b5ab7fd5 |  | note | VERIFYING DOCUMENTS: This ITP
text | a7186387-c61b-486a-99f6-e893a7e32582 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Non-conformance Report (NCR) Closure
label | 40ea4e55-c608-4d48-aa84-46ee81ce109d |  | note | REFERENCE: MRPA Quality Management Plan
label | 85163165-1449-4160-a999-e513bc5aae94 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | ce9fa79a-5a87-4111-9e13-d8f59f26c214 |  | note | METHOD: Document Review
label | 8ef5660e-55e9-41bf-9384-88160f747a23 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | a58ed3a9-af46-43bd-bd85-740cd9da5614 |  | note | CATEGORY: HP*
label | e7482c4e-9edb-4b53-a508-3e97f4d34568 |  | note | RESPONSIBILITY: SE/PE/SPE
label | aa85753c-70fd-4705-9ebe-6b24cfd038d3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0868fcab-eb6c-415a-87a8-2f0b633c592a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | c6441a2d-74fd-46d8-9fe9-42469d3fe3b6 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 90089a3b-ffa7-4280-bf7a-0ab118a045ea |  | textbox | Name:
text | c769e556-e1b4-4ffc-9248-87ddd214fc26 |  | textbox | Position:
text | 519be863-37e0-4147-8fe8-cabef142c2dd |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Precast Retaining Wall &/or Architectural Panels (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Precast Retaining Wall &/or Architectural Panels (Supply & Installation) Rev 0 | 6c7e41e2-cb4d-45f4-869f-9c294bc1cc9c
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 0a7217bd-ecd6-41b9-acfe-4f93e50d12fc |  | note | Document Title: ITP-STR-Precast Retaining Wall &/or Architectural Panels (Supply & Installation)
label | 0ea4186c-bcec-4541-9107-085935eea43f |  | note | ITP Description: Precast Retaining Wall &/or Architectural Panels (Supply & Installation)
label | 7aebacf0-2578-42e1-9b48-6f1d20963c74 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | e0ec9e71-ba32-48f8-bda1-5c9549cce373 |  | note | Revision Number: 0
label | 5ceca549-8369-4c6a-9918-b840a5b5a860 |  | note | Revision Date: 17/05/21
label | 2141a887-1dcd-4692-8ce7-558623b13793 |  | note | ITP created by: Mike Freeman
label | 135737d9-0544-4f47-ac40-e6da7c7b0ebc |  | note | ITP approved for use by: Mike Freeman
label | 92ac0454-8639-49c9-bba9-7f13a13e2ef4 |  | note | 1.1 VicRoads Section 610 November 2018
label | 8a3da656-dee8-4d62-b7d9-acd4b5769215 |  | note | 1.2 VicRoads Section 610 June 2019
label | 82511cd5-c9d4-4953-928e-2311aa3805ae |  | note | 1.3 VicRoads Section 620 May 2009
label | 3333aba0-f6e8-4e09-bc88-60fe4958dabd |  | note | 1.4 VicRoads Section 630 October 2013
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Precast Elements
label | caea95e2-688e-4fd7-a60f-170d805ef91e |  | note | REFERENCE: IFC Drawings
label | 8432c93a-48d5-44d0-bc5d-dbe11f56e177 |  | note | 610.46 (a), Table 610.463
label | e92e3dec-bb75-4f2e-8263-01050c7eb383 |  | note | (November 2018)
label | c8397375-3923-46df-892f-490f029fd287 |  | note | 610.47 (a), Table 610.473
label | fecf7f9d-1c55-4d70-a1af-e97fc3ebf081 |  | note | (March/June 2019)
label | c078609b-76c4-425a-86ec-01868c423f6f |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 3cf892f9-ea31-4edf-aac0-a1f3029bc24b |  | note | i. Certificate of Compliance / Birth Certificate
label | 1e73222a-0ddf-4466-92bb-a8460baf5487 |  | note | ii. Compressive strength test results
label | 859d3fcf-8220-4c41-9b2d-cae6ed9f90d1 |  | note | iii. Precast Lifting Design
label | 29d3498c-49c8-4aaa-934c-bbf18b267af7 |  | note | iv. Pre-pour check sheet / ITP
label | 8d4442a2-3ff9-498d-946f-578e7dda5813 |  | note | v. Post-pour check sheet / ITP
label | 66dd9eb4-0cbf-4f94-9eb0-0e711b2d2cf2 |  | note | vi. Covermeter check record
label | 745f6918-8a97-4c4b-858f-69f80ab7cf4e |  | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
label | b184fff2-aa6e-47f4-8045-d199730daa8e |  | note | Note: Different revisions of 610 have different clause numbers
label | 9c4d6fb3-3026-44c6-8f28-e8a875a32153 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | 74f26076-17c6-402f-8a93-d3079124a6be |  | note | METHOD: Document Review
label | b30d27c6-b278-4751-841a-c46a0262bc91 |  | note | FREQUENCY: Each element
label | 538a0289-c950-482e-87d5-c59eac55f666 |  | note | CATEGORY: IP
label | 40bf1065-e630-42c0-95df-544b65ea0595 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 83d6cb44-6d95-461a-b561-ff3c5e5e6673 |  | note | VERIFYING DOCUMENTS: This ITP
text | b32a6ed9-f4da-4e8c-a1d2-97aec33c0117 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Joint Sealant
label | a15a49d2-8c02-4687-8ce0-2d2a70aadb1f |  | note | REFERENCE: MRPA Quality Management Plan
label | bdf5668c-9736-4929-b34f-f676ad33987e |  | note | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
text | d777ad29-c33e-4e12-ae17-13210716c43e |  | textbox | Enter: Teambinder Material Approval number
label | e79251c9-253a-4f8e-a6f9-aba3d9e25e9c |  | note | METHOD: Document Review
label | 63417be1-1db3-4a63-90e9-7c630b266411 |  | note | FREQUENCY: Once, for each product
label | d900fda2-0e41-44f7-a4c6-b54c42b87533 |  | note | CATEGORY: IP
label | 284f9919-40c3-43e3-87b0-2efef1a6d3e7 |  | note | RESPONSIBILITY: Nominated Authority
label | 7eae9d72-6433-4b03-9d66-f1fc0ba084c9 |  | note | VERIFYING DOCUMENTS: This ITP
text | d41e546f-7bbb-4cc6-ba93-5bd82ca29fe9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Foundation Concrete Compressive Strength
label | 6f545f03-14a4-47c4-9f05-46c865598bb1 |  | note | REFERENCE: IFC Drawings
label | 524c4c18-853b-411f-a17b-0d3da9e04ef3 |  | note | Temporary Works Design
label | ae3e1eae-569a-439a-8e3f-5fcc327e5175 |  | note | ACCEPTANCE CRITERIA: Check that the strip pad, strip footing or post hole compressive strength as shown on the Temporary Works Design or IFC Drawings has been achieved.
label | 2dc14907-8b65-45ff-ace1-8361892ff59a |  | note | METHOD: Document Review
label | 1f09f5b1-6435-4303-a1ef-e829d9103706 |  | note | FREQUENCY: Each installation location
label | 46dababa-e023-4b7a-927c-f4fd5a293f94 |  | note | CATEGORY: IP
label | 3fb600bf-c9c8-47d6-8a5a-1d93e3eef897 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 596091a9-2862-451e-ad72-eaaf3b6bd477 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2fe4155a-8130-4039-a22a-fa5552d731cf |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out of Precast Elements
label | 893e0213-2173-4bf8-ae9d-a0834063e861 |  | note | REFERENCE: IFC Drawings
label | 0f8fa900-cc9b-4810-a14a-5758d565878a |  | note | 610.46 (a), Table 610.462
label | 2ebf7ef7-1086-44e2-8f06-3f403f12b86b |  | note | (November 2018)
label | 32632737-8378-4f24-a4be-2184c12eb93a |  | note | 610.47 (a), Table 610.472
label | 074861fa-d0bc-4d0c-931c-279e421bb9bb |  | note | (March/June 2019)
label | 882efdc2-2d98-4d49-a290-5f7acdf99bdc |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
label | e47dd566-e709-427b-96dc-b312e9ee409d |  | note | Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
label | 8efa94b3-8bdb-4cd3-b95e-24abbb29564a |  | note | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | ff1a1436-94a3-4c9b-9d28-eec25fa958a7 |  | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | aa6ee5d9-87f8-4cd6-99e2-471cb470bfe5 |  | note | METHOD: Measure , Visual
label | 21dfd6f6-87ae-473d-b87e-dc5292426cc9 |  | note | FREQUENCY: Each element
label | b854bb1b-f9a0-4bb9-8b8d-06bc0a28796e |  | note | CATEGORY: IP
label | 63ee5d08-ebf0-4d0d-9c25-79188a5985d1 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | fa6c2a6e-e40c-48ac-a35a-a5a2cbd22209 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2334f338-fbd6-4db2-a1e2-bae5815b9251 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Bearing Shims or Bearing Strip Placement
label | 0af4fb0a-447c-416d-820f-bb1b83508c2b |  | note | REFERENCE: IFC Drawings
label | dc0da747-f63b-4d17-9b26-ef1fe01abb65 |  | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | b5a4fd41-af36-4d0f-9aeb-d97de655f261 |  | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | afdd1e97-6e7b-4119-8fa3-b192ecfec31d |  | note | METHOD: Measure , Visual
label | c098a87b-9a87-47f3-9be0-233f70b7aaac |  | note | FREQUENCY: Where applicable, each installation location
label | b4d87143-110b-4ef6-a751-028ea748f07b |  | note | CATEGORY: IP
label | 8a35b030-131f-4f70-9648-e6d8eac1065f |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 978f3797-e2e5-40e3-8ea1-e53a1fba2635 |  | note | VERIFYING DOCUMENTS: This ITP
text | 43e69259-3cbc-4c64-a162-74c1f0c7a116 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Materials Inspection Checklist
label | ca737dbf-8874-4bde-ac52-2d4bc647d140 |  | note | REFERENCE: 620.06
label | 18e8f04d-4eaa-47bb-b3fe-01404ee0e202 |  | note | 620.07
label | e176b86a-e98f-4812-9cb9-b531d7083576 |  | note | MRPA Quality Management Plan
label | ad4f5290-c34c-4e01-b29e-1639066a7206 |  | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | b700297c-5cf2-464d-a5b6-0cebe05ce333 |  | note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | 02231f3b-b82e-45df-9e45-305d1c8d07a0 |  | note | Elements shall have unique identification and orientation marked (if applicable).
label | 65b90e00-bd35-45a0-a9e4-8dbcb5df7b3a |  | note | Complete: Materials Inspection Checklist in ConQA
label | 8015b9b7-367f-49c4-996d-a6c657e6f3d1 |  | note | METHOD: Measure , Visual
label | 5afdcbec-2682-456b-b757-20e341a39300 |  | note | FREQUENCY: Each element
label | 04f60eca-530c-42aa-81c4-687baee6a273 |  | note | CATEGORY: IP
label | 3d43638c-c70b-4cd8-b834-e38fde15660b |  | note | RESPONSIBILITY: SE/PE/SPE
label | ddf2f733-aa82-496f-8745-54b93e868703 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8206dd80-656f-47ed-85f9-02c0e2b2b314 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Precast Handling
label | 23b3ae95-3935-4333-8ba7-9e0b44cebce9 |  | note | REFERENCE: 620.07
label | 61b63285-774a-4b5e-81bb-79f1bd02ee01 |  | note | Crane Lift Study
label | ebc3802c-1162-466c-a336-56997625cab5 |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 01aa03fc-1341-4a74-9e5c-398ea54da699 |  | note | METHOD: Visual
label | bd04a0e8-5283-44c4-8f98-abcfe6fa1304 |  | note | FREQUENCY: Each element
label | d771c45e-4f60-42ed-94d2-a3932c3a08b8 |  | note | CATEGORY: IP
label | 60dfb70c-30d4-49ca-ae76-f517a8349a89 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1b4012d5-33c9-489c-99b7-d24eac118b65 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4e421f46-0d4a-430b-b56a-99b37c3259a7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Precast Placement
label | 40a058bf-df3b-4ae8-ac6a-6598e2e05810 |  | note | REFERENCE: IFC Drawings
label | d6f8dbc2-941d-407c-830e-d3adeb723ddd |  | note | Temporary Works Design
label | 52678714-1615-4d2b-80f2-4ecc6929d903 |  | note | 610.27
label | 9920c5ad-eec3-4318-a0d3-e60736fb013b |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed into location or and not released from the crane until sufficiently braced, wedged or restrained by bolted connection, in accordance with the approved Temporary Works Design and/or IFC drawings.
label | 7d7a403e-f252-4f8f-9844-67b087f53637 |  | note | Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
label | 1727be5f-5ddf-4efe-af87-d51da4031dd5 |  | note | The nominal gap between elements is as per the IFC Drawings.
label | 4476bb30-5f2e-42e9-bd4f-e278506a3b9b |  | note | METHOD: Measure , Visual
label | 5feac08b-af7b-416d-b4c8-b96f4db37b8a |  | note | FREQUENCY: Each element
label | 5a1cb1dc-9e47-46b0-b831-a9032f384c79 |  | note | CATEGORY: IP
label | a873416c-b17f-4ca7-89da-bb6889b6513e |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 7448f4ea-f62c-4fb9-b771-0fb76caa9851 |  | note | VERIFYING DOCUMENTS: This ITP
text | 18fb511c-f145-4dc3-902d-5e9056a2b1fb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Waterstop Seals, Compressible Seals & Isolation Joints
label | 7530591a-4f28-4c14-b6f7-b7b97922b771 |  | note | REFERENCE: IFC Drawings
label | d688e701-2723-4948-b1f8-2e2c527f326f |  | note | Product TDS
label | 90b05512-e69c-4d4a-a05c-da3d86cc27b5 |  | note | ACCEPTANCE CRITERIA: Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
label | 2813005b-5615-4015-b83f-063eee85fe7b |  | note | Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings.
label | 165c539c-34d5-4b31-a75f-bf783d9914d1 |  | note | METHOD: Measure , Visual
label | 173556d4-b90c-4500-be3e-ee9efe6fd2c2 |  | note | FREQUENCY: Where applicable, each installation location
label | ab626685-3f20-4756-8728-1dd48a345a86 |  | note | CATEGORY: IP
label | ae773490-1e59-4d61-8419-88146076f1ed |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | e83174a6-12b2-476a-ab2d-da526a194fbe |  | note | VERIFYING DOCUMENTS: This ITP
text | e13d286b-5d03-4496-86b9-812e02a7d462 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Subsurface Drainage
label | 61cf78e6-45fb-4033-917c-811f1b374859 |  | note | REFERENCE: IFC Drawings
label | 5a2fca44-128d-4faa-bc83-9f96e4236fa6 |  | note | 702.03
label | ddff3546-d17f-47a3-b032-8e133c30b895 |  | note | 702.06
label | a5899f68-6f61-4738-90ee-ff98c333b94e |  | note | 702.07
label | 98f53abf-a20d-44cf-9a9c-4b9b581f894c |  | note | 702.09 (f)
label | 8c7ced7f-5b7b-4990-afce-1f92918092b1 |  | note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
label | 0d4701fa-43d1-43a3-9093-014606d88338 |  | note | The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings.
label | f75b2e6f-d161-48bf-b85a-4b67c4723ab4 |  | note | Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
label | 0c68f6bb-7faa-4f22-95cb-d2bc5c5feb5f |  | note | Weep holes shall be checked for obstructions.
label | 8a45175d-2bbb-49bc-ba40-e04f3c1cff95 |  | note | METHOD: Measure , Visual
label | 47b859c1-4980-4c22-a600-07defb56aee5 |  | note | FREQUENCY: Where applicable, each installation location
label | 158441ff-d763-4060-b49e-e9f20ad1fc95 |  | note | CATEGORY: IP
label | dd798cc3-0102-48e4-b93a-d72cd0ae9bfe |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | c4e29cdf-b450-46e9-b1c4-73c9fb5f026f |  | note | VERIFYING DOCUMENTS: This ITP
text | 3b7f4872-0be8-40c1-9611-cf5776780ce7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Connection Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | 745e4760-708b-4344-abcf-4a6572f6ff15 |  | note | REFERENCE: IFC Drawings
label | c3a94603-ef27-408a-85e1-9eacc2782f66 |  | note | AS5131 Clause 8.3
label | 49698af3-b7a5-42a2-8f0c-d069ae6ff9cb |  | note | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | 86fd1061-a238-4a08-8d94-d6f87f843f06 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | c559beb7-07dd-40ef-9eb5-935309d1c5a9 |  | note | Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 11653a1e-8266-46fe-be8f-25b6d78db209 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | e48e36f5-03a1-4244-b541-1285bf597887 |  | note | METHOD: Visual
label | 6c42c7a7-aa2b-4dfd-ad7b-4176e4dcfbab |  | note | FREQUENCY: Where applicable, each bolted connection
label | ac85cb28-1ac8-4742-9721-d076bec1c874 |  | note | CATEGORY: IP
label | 51a57309-84a3-400f-bb29-97c5f099da46 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d5b64bb6-5bc2-4713-bfa5-f7d1d8ba966c |  | note | VERIFYING DOCUMENTS: This ITP
text | ae63e86c-a835-46a8-ba64-2c9be61bb9d3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Precast Traceability
label | 79b463b1-618b-4267-a36d-1714a1d15790 |  | note | REFERENCE: 620.09
label | 7e9e5a86-db09-476e-9cad-78df81ad683e |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | d420b653-378b-414d-a59d-e674f365662a |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 17858331-d7c6-439d-9e2f-fc020d4eed3d |  | note | METHOD: Visual
label | a6eb8769-1497-4f0a-a19b-c4011a046f23 |  | note | FREQUENCY: Each element
label | 8f3dc7d0-7760-4b0a-a7f4-0b786811e083 |  | note | CATEGORY: IP
label | 76781464-ba65-4742-8a6f-179c5853fdf1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 54e3fe60-c0ef-4926-a992-63f583cce654 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2e25bd03-b8ee-4c63-b8d9-8cba8fd99e45 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Joint Sealant Application
label | 1afaed02-4847-45e0-9e30-9e501f828ab9 |  | note | REFERENCE: IFC Drawings
label | 38525afb-f8b9-4c6b-b763-b9f9b44bd279 |  | note | ACCEPTANCE CRITERIA: The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
label | 1fb32dba-6786-41f7-9445-7e697c477cf4 |  | note | METHOD: Visual
label | 27447496-df01-427a-905c-cd3dcedacfce |  | note | FREQUENCY: Where applicable, each element
label | 764b01a7-dfec-4bb1-8e60-bf9732efcd4c |  | note | CATEGORY: IP
label | 26b17902-1081-4462-a7c2-4452c71c71e1 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 6ec25448-1ba7-40bd-bd22-af9f58209dbb |  | note | VERIFYING DOCUMENTS: This ITP
text | 44b1f8e2-ea0d-45a0-b4b7-800251159c3f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Flowable Grout Pour
label | 7f335f76-9769-491f-b287-b5947c53ef02 |  | note | REFERENCE: IFC Drawings
label | 10effdfd-9ce7-4256-babb-8eed7e3725a8 |  | note | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the foundation following full sealant application.
label | 76c7f4b4-982a-4df0-9d65-68155f52eb5f |  | note | Complete: Grout Pedestals & Bearings ITP
label | 509877a7-32fb-4b10-831f-59ce8556f15f |  | note | METHOD: Visual
label | 419b6012-5e93-432d-bcb1-fd6643759c47 |  | note | FREQUENCY: Where applicable, each element
label | 28abf983-af23-42a4-b5f5-8614bf15562d |  | note | CATEGORY: IP
label | a5b235f4-d499-492e-8ddd-20d602d4098b |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 500412f9-4dae-4191-aee9-83c6759ce7f9 |  | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
text | 9b84ba5a-2bfa-4aa2-aa71-5e23e9446e6e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Backfilling
label | 617be304-0460-415a-b853-0b03b1015daa |  | note | REFERENCE: IFC Drawings
label | 7e7e5902-cfb4-472d-b332-1db3d7a90c26 |  | note | ACCEPTANCE CRITERIA: Backfilling materials and compaction shall be the type and layer depth shown on the IFC Drawings.
label | 3bc2e614-dfca-4299-88fa-b2ff5509840a |  | note | Complete: Subsurface Drainage (Supply & Installation) ITP
label | d03f99ad-1038-4cf4-944f-0daba9fc1294 |  | note | METHOD: Visual
label | dc110db5-367f-413b-92cb-b523f02190bb |  | note | FREQUENCY: Where applicable, each element
label | e2365075-8d09-4408-8b1b-4ce43aebb49c |  | note | CATEGORY: IP
label | 9dfbcc31-9b1c-4653-9f69-0c676258cf00 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 7b1fd1d7-8115-49a4-9379-87a31a81b2e7 |  | note | VERIFYING DOCUMENTS: Subsurface Drainage (Supply & Installation) ITP
text | 22bcc4f5-2909-4ef6-96a0-a7692ca7e26f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 As-built Survey
label | eb4dc464-8b60-4df2-b6d1-2d85c8c7e8c8 |  | note | REFERENCE: IFC Drawings
label | b403514b-13e2-47e6-944f-8f8473578ee1 |  | note | 610.46 (a), Table 610.462
label | a40abefc-9ec9-494c-99dd-30294f534133 |  | note | (November 2018)
label | 1ef6f033-9cc5-4605-9a14-3c90d1fca082 |  | note | 610.47 (a), Table 610.472
label | 2dc61072-e6f2-47ea-aa4b-340f232e8f8e |  | note | (March/June 2019)
label | aba9afd0-15a6-4eea-930c-aa502aec65e8 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | e4e38289-efb1-47f8-90ad-d73cb9584825 |  | note | Attach: Survey As-builts / Survey Report
label | f36e990f-c479-4214-8b38-c503c29d2e01 |  | note | METHOD: Document Review
label | af690f08-ee99-4216-a973-c326232d53ca |  | note | FREQUENCY: Each element
label | 32de10f4-4e0c-4867-9463-b2e81940b190 |  | note | CATEGORY: IP
label | 3ac65fef-29a7-4430-88dc-74f9d5682439 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | c1103c91-e27b-40a8-98cb-b680c3711633 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6a0736ba-8e60-46d1-a166-c3a29584f7d5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Non-conformance Report (NCR) Closure
label | fa487bd3-9423-4228-aa2d-a28317e470f9 |  | note | REFERENCE: MRPA Quality Management Plan
label | 56d294c5-6696-4b1b-8559-c86905872726 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | a946fb08-3082-4799-a5b7-b54294478e8d |  | note | METHOD: Document Review
label | 70c01ba3-fd95-4d0f-9589-53f3b7f5b317 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | ac5f6e67-78f8-4ffa-8ee6-5712a78081c3 |  | note | CATEGORY: HP*
label | 73d0c157-627f-47d1-9460-ef2eb2c52ace |  | note | RESPONSIBILITY: SE/PE/SPE
label | 95e90dd0-d7c2-45aa-83b5-8a373fb17078 |  | note | VERIFYING DOCUMENTS: This ITP
text | b9d735d1-6bd9-49e0-9c22-bd42f82656be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6e219756-d44a-465d-ac8a-f396bc1f5f1b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | db686161-ef52-4c9e-94cc-4cce42e919c8 |  | textbox | Name:
text | 21511bc6-d023-4412-9e8c-d452e1bfe17a |  | textbox | Position:
text | 4e820c60-3663-44d5-a692-96396fccb47c |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Lime Stabilisation Rev 0 | itp |  |  |  | Yes | ITP-CIV-Lime Stabilisation Rev 0 | 6ff43f1c-a65e-4479-a78c-e65a18ed16cb
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | cfb8de63-39e0-4bf4-86d7-9138271ed3d2 |  | note | Document Title: ITP-CIV-Lime Stabilisation
label | 4b37a7f0-236c-4c8d-8ecc-38b5f374b063 |  | note | ITP Description: Lime Stabilisation
label | a5bf1982-86d7-41fa-ba21-31d939027f87 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | fe4d0dcc-6785-47f1-88d7-39730322720a |  | note | Revision Number: 0
label | 3febc768-524f-4a21-99fb-a86641f447ed |  | note | Revision Date: 25/09/2020
label | 11dcaa89-ccb7-491b-859a-bf7953b19884 |  | note | ITP created by: Matt Velcek
label | ededcfba-d7bd-4b9b-8847-98f1f01fa512 |  | note | ITP approved for use by: Romualdo Magpantay
label | 6a0547ef-903d-46e4-903b-5a2625b07b57 |  | note | 1.1 Vic Roads Section 290 (July 2019)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain conformance records for materials
label | c7d5904f-27c5-4558-bd73-de31d17315c5 |  | note | REFERENCE: Vic road 290
label | 0a869a5c-c414-4d74-8d6d-ca42d381f6ef |  | note | ACCEPTANCE CRITERIA: • Quicklime
label | a98b9048-9a6b-4638-a037-f3737cc22d34 |  | note | • Hydrated lime
label | fe0a6770-6c56-44ee-b777-51daefbfe696 |  | note | • Slag / lime blend
label | f3e13d6e-0441-4280-bb16-ce85ae22e08b |  | note | • Cement
label | 5720adc3-ff68-4882-baeb-7b98c766f2ba |  | note | METHOD: Doc. Review
label | 9bc8b64a-8b5e-4d8b-8845-c650a0c6a4f3 |  | note | FREQUENCY: Prior to Commencing Works
label | 62f36e44-2b23-4b93-8a9b-de228203eb03 |  | note | CATEGORY: HP
label | ce777fe3-5afb-4992-ac3d-c13af2328ccc |  | note | RESPONSIBILITY: SE, NA
label | fe325884-a150-4d48-90a3-16ce655c441a |  | note | VERIFYING DOCUMENTS: This ITP Insert TeamBinder Approval No.
text | c3d65236-61e1-452c-9d0c-18f8424ff8b5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Carry out a trial stabilisation section by a particular combination of material, equipment and method
label | c9302d3a-ef35-42df-b130-a2b170858dbc |  | note | REFERENCE: Vic road 290.11
label | 3e91c4e2-1ae6-4c07-945a-836adf0bf995 |  | note | ACCEPTANCE CRITERIA: • The trial section is to be about 100m in length
label | 0624ced3-f1f8-4943-bc19-c6f907654709 |  | note | • If the trial section is not conforming, a new trial section needs to be constructed
label | d5f04677-12f2-4cf9-b6a6-53bb21670f4a |  | note | METHOD: Doc. Review
label | 3ce39c01-554a-40ee-a87f-dc8149696c73 |  | note | FREQUENCY: Prior to Commencing Works
label | f4932122-3391-4883-a42c-e5ffa1918ef9 |  | note | CATEGORY: HP
label | f67f0137-7f19-4311-a461-ab44f7762a80 |  | note | RESPONSIBILITY: SE, NA
label | 7f59cd87-2a60-4601-91e5-e62f4914a763 |  | note | VERIFYING DOCUMENTS: This ITP Insert TeamBinder Approval No.
text | 8923e441-cc1e-4dc1-a905-cc512e348ed6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Submit the test result & Mix Design /Spreading Rate
label | 84b8f102-f5bd-498a-8323-31f4effa6a48 |  | note | REFERENCE: Vic road 290.11
label | 97f32033-e3ce-40f9-afae-47f1a057bb01 |  | note | ACCEPTANCE CRITERIA: • Submit work method and test results from a trial section of stabilisation
label | 5d2723bd-8c1c-4eb9-9e40-d58198ea8888 |  | note | METHOD: Doc. Review
label | 3d0439f9-7bde-4865-8db8-b0adf3fe8357 |  | note | FREQUENCY: Prior to Commencing Works
label | c039b7b2-d98a-4281-817d-19510791f64b |  | note | CATEGORY: HP
label | 12371146-bee4-443f-8cf9-4ad356f7f806 |  | note | RESPONSIBILITY: SE, NA
label | a9600d6e-fafc-4e9a-9c57-acde4184df60 |  | note | VERIFYING DOCUMENTS: This ITP Insert TeamBinder Approval No.
text | 875b3698-96df-49f0-b1b1-824ea60092a7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Rip and compact layer(pre-treatment Earthwork) to be stabilised and trim the surface parallel to designated grade level
label | 04118934-0d43-4fe2-8967-aaf92dd5ec2d |  | note | REFERENCE: Vic road 290.10
label | 65a98a11-7d5f-4086-8a0b-3fcf202b13f3 |  | note | ACCEPTANCE CRITERIA: The material to be stabilised shall be pre-treated by scarifying or pulverising to the specified depth to provide an even surface capable of being trimmed to meet the requirements of clause 290.04. Any hard rock particles larger than 75 mm shall be removed from the scarified material
label | 67f35495-33b9-45d4-8e11-a31e23614de9 |  | note | METHOD: Inspection
label | 0243e3f6-f52d-4556-a0e3-2458ddfb42dd |  | note | FREQUENCY: Each lot
label | 96ad7dd2-af9d-4dca-9e5e-294fd2497989 |  | note | CATEGORY: IP
label | 6750d51a-a22b-4481-b405-3c5757c78015 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7607fddd-d781-4eef-a94d-4d2a73ac1b17 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | eac1cb9e-a869-4ab4-9391-215e4b90e415 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 The spread rate is to be:
text | 79a81d20-5b68-40c2-b79a-485fa41146e5 |  | textbox | Quick Lime: |  |  | %
text | 2ed9bc6e-c531-4366-8370-ac24702ad0e5 |  | textbox | Depth: |  |  | mm
text | bedf4a4c-3846-48cf-8963-1b8e461d68b2 |  | textbox | Rate: |  |  | kg/m2
label | db13f1e9-d1d0-4497-90c9-24918b8ce24c |  | note | REFERENCE: Vic road 290.09
label | 53a36b5e-d928-4274-a28b-6bd90bb29df4 |  | note | ACCEPTANCE CRITERIA: The details of mix design and work methods as agreed in trial section
label | 807bf401-402a-4e35-987d-56c471c63b78 |  | note | METHOD: Inspection
label | 1d24a9ad-6acf-47b4-ab9f-ba0c7092ad7b |  | note | FREQUENCY: Each lot
label | bf513017-075f-4c99-b882-6f76592e5ae2 |  | note | CATEGORY: IP
label | f4cb9429-f953-41a3-8a5c-9f7c3bb330d1 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8363f48d-d59e-4622-96d7-157acb734866 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | b2d40709-3148-4cf1-84ed-123acaa07e83 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Spread the stabilising agent using a mechanical spreader
label | af06a98b-7ddb-41c9-a9c1-bf3bbd0b4991 |  | note | REFERENCE: Section 290.10c
label | e898604a-f85a-4545-98b9-61b252996166 |  | note | ACCEPTANCE CRITERIA: Immediately following the completion of spreading of the stabilising binder, the Contractor shall check and record the Average Spreading Rates and the Uniformity of Spread in accordance with clause 290.13.
label | bbca7500-d167-42b5-8101-89a7908532d3 |  | note | METHOD: Inspection
label | ea0f314b-fef9-466e-97f4-6130d1b3d25a |  | note | FREQUENCY: Each lot
label | 86f60a9a-24d8-49e1-b49b-07100abc14a2 |  | note | CATEGORY: IP
label | 7892e9f5-f8f3-4162-a215-ab0310b8f966 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6608d7b4-80af-4dc8-a227-acb8450fa44b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | acf7c387-688b-466b-a2f8-4508bd9e1869 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Commence slaking after spreading
label | 96c85042-6c2d-4521-8fc9-ef90e95be606 |  | note | REFERENCE: Section 290.10e
label | c78c0aac-8383-44e9-aab1-238ed675250d |  | note | ACCEPTANCE CRITERIA: Quicklime shall be slaked with sufficient water to allow full hydration to take place. Full hydration will be deemed to have been achieved when all quicklime that has been spread has changed from a cream coloured granulate to a fine white powder and there is a cessation of rising vapours
label | b716791e-1977-4f5b-8647-c3b9083c20d5 |  | note | METHOD: Inspection
label | ae77488e-d5ab-4f48-8da5-479ec2438869 |  | note | FREQUENCY: Each lot
label | bdbe719e-b320-4d79-94b0-59f0f1891bb7 |  | note | CATEGORY: IP
label | 0a4bf3cb-8d76-44c4-ba3d-959c8199a089 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f8f44525-15e0-44eb-b5a1-03e3fa3cdaa9 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e0a84e12-1b44-4270-b682-e2ea48efc0b2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Spread and compact the stabilised material to specified compaction
label | b9d2fd0a-db5e-4df9-9fdc-0b63d34f1a12 |  | note | REFERENCE: Section 290.14b
label | ee86f50f-03d1-422a-8ebc-f0f43e262e47 |  | note | ACCEPTANCE CRITERIA: Lime stabilised material shall be compacted to comply with the requirements of Table 290.141
label | 24314921-f942-421b-a7f4-807d170c49fc |  | note | METHOD: Inspection
label | 88ea1fd8-e830-48d2-9c06-06075269637e |  | note | FREQUENCY: Each lot
label | 0a73bc95-d22d-4fd0-b318-7ee8cd4ce0ad |  | note | CATEGORY: IP
label | e2a54c19-e386-4b86-b159-0bc7070c49aa |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 18e5bf4f-9e97-41ae-9814-1695b7592a66 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a67de93a-d662-48c3-b397-a5c7a1fa4a7d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Density Testing & Test rolling , Trim surface to design level
label | df408efd-1829-409b-9bf0-2636b34cc270 |  | note | REFERENCE: Vic road 290.12
label | 277c5404-9f1d-47a2-b728-d4ecb5260412 |  | note | ACCEPTANCE CRITERIA: The final surface trimmed
label | f59fb730-32a5-4782-8a0a-53f4eb62b1a8 |  | note | METHOD: Inspection Testing
label | d1bc879a-8243-4477-911e-fa18c528b04c |  | note | FREQUENCY: Each lot
label | 4151e8a6-6c50-4bf1-aea6-704d05a832c0 |  | note | CATEGORY: HP*
label | 5de16f09-510e-43d2-a232-8ef8d383a174 |  | note | RESPONSIBILITY: Nominated Authority
label | a160770d-d0c8-4a60-a379-4f1056a2bee4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 17b1f8ff-bc6e-4b5d-8d33-bdce0cfe8393 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Maintenance & Curing of the stabilised layers
label | f708bbde-bd0f-472e-a4fb-bd3a67e5fa2e |  | note | REFERENCE: Vic road 290.16
label | 312a2617-b31d-4d29-b2d7-2a0efd61dd8e |  | note | ACCEPTANCE CRITERIA: Protect stabilised layers against rapid drying by keeping the surface of the layer continuously damp until such times as a covering layer is placed.
label | 8e727e46-a653-4451-8d2d-1145de1934cc |  | note | METHOD: Inspection
label | 9c83a168-d58a-4a04-8f55-007e4a15200c |  | note | FREQUENCY: Each lot
label | 9412b9b2-c7c4-4cdb-9e7e-87379f20647d |  | note | CATEGORY: IP
label | 2c2ec690-aaa7-49d7-8d17-cd91740b7e80 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2d43d936-4f5d-496a-89f0-8b0e8ada3c17 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ce6813b9-eaf6-4281-9bab-489e6af0c474 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Attached and verify Subcontractor conformance records/signed ITP including relevant verification sheets
label | a38e0d65-760a-441f-b781-38cf86fa14a5 |  | note | REFERENCE: Vic road160
label | 0687cc6d-2097-4213-ab0f-c346f9d5374c |  | note | Vic road 290
label | f876c653-3ac4-4cbb-83b0-bff40f88c8a5 |  | note | ACCEPTANCE CRITERIA: Check conformance report against project conformance criteria
label | b6095800-daa1-457c-bf70-9fe0a765d7e8 |  | note | METHOD: Doc. Review
label | c0d8b0c2-8812-478f-8f7e-e5ffd9eed61a |  | note | FREQUENCY: Each lot
label | e80dd677-983a-4c92-b46a-b16f2f36d215 |  | note | CATEGORY: IP
label | f3c97ba6-10fd-4aab-8858-76908b7241ac |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7e7fe9f2-6fe7-4a53-bab0-ea6179142b2b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 449962e4-9b7c-412e-92b1-c363e6e8a71d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 As-built/constructed Drawings
label | c62f00e7-a079-4f75-8a05-9f0f97904175 |  | note | REFERENCE: Vic road 160.A9
label | dbea7950-b7f0-4714-9d06-3a82d9c1c934 |  | note | MRPA Work Procedure
label | a1875f6a-13a8-4301-8487-10c64641d174 |  | note | ACCEPTANCE CRITERIA: All RFIs, NCRs and changes to the IFC drawings are captured on a controlled set
label | bfc9fe0c-d05d-4e19-916c-f820f235d27a |  | note | METHOD: Doc. Review
label | 71992f8a-dc36-476f-a098-fb2855369b25 |  | note | FREQUENCY: Once, at the end of the construction period
label | ac75443e-c3fc-4a22-add7-ffea15782ce4 |  | note | CATEGORY: HP*
label | d0988253-4628-4bd2-9945-91061b0d0bf5 |  | note | RESPONSIBILITY: PE/SE
label | b9e293b9-32ab-414c-b350-8570bb0bd735 |  | note | VERIFYING DOCUMENTS: As-built IFC Drawings
text | e6da8c7c-af48-4461-babd-778b0cf032f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | cbf657df-91e3-40af-a58d-076f742d462e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 805e4c3a-516a-4ba3-8d21-e266efbd9a7a |  | textbox | Name:
text | b92f8687-fd1a-4ce5-9e09-59cff15d92c6 |  | textbox | Position:
text | cddc4285-95ba-4473-9e3a-68c66c4b5b2f |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Bored Piling (OHW Foundation) Rev 3 | itp |  |  |  | Yes | ITP-STR-Bored Piling (OHW Foundation) Rev 3 | 7305bca4-b935-4f7d-8b2a-21a289150174
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 0b65cac3-f08a-4d50-9b81-34b3a50870e3 |  | note | Document Title: ITP-STR-Bored Piling (OHW Foundation)
label | c91a4619-12d0-46be-b45c-5203903dc330 |  | note | ITP Description: Bored Piling (OHW Foundation)
label | 5174790e-db12-4bd4-83c7-a70f0641395a |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 285e2a4e-8cf4-457a-acf9-d905499198a9 |  | note | Revision Number: 3
label | 3a7d540f-c9b9-4d9a-8d66-4c7c37af71b6 |  | note | Revision Date: 12/05/2021
label | 100d2f36-924b-492e-a717-9fa9716dcb55 |  | note | ITP created by: Mike Freeman
label | b1267f0c-a58b-4824-9695-c7b9904c6324 |  | note | 1.1 VicRoads Section 606 July 2017
label | b90a169a-e1bd-4a03-bcb4-9018917a9154 |  | note | 1.2 VicRoads Section 610 June 2019
label | 716276e7-ca45-4d58-b5d5-94dad9349f6e |  | note | 1.3 VicRoads Section 611 November 2018
label | 2db96844-0066-4b50-b0f7-f59e0de3f0a3 |  | note | 1.4 AS2159-2009
label | bb794393-0c01-44c9-8019-4f35b655849a |  | note | 1.5 AS3810.1-2015
label | fc519285-8f60-4157-aa32-78d1554defb7 |  | note | 1.6 MTM L1-CHE-STD-058 Rev 2 July 2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 39ad28ac-ef08-46a6-8a3c-fe0923c59b7c |  | note | REFERENCE: 610.07
label | ac62ad81-1eff-4f07-ad22-8b63fbb89737 |  | note | Table 610.071
label | 227c7e23-e106-4669-a3f4-1189f1641dea |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | b8c52abe-a945-4e9d-8251-a38cb9437086 |  | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 4deb1a95-7e05-4e09-b987-af390bb0c5e4 |  | textbox | Enter: Teambinder Material Approval number
label | 7d25a205-8081-4a2b-980b-fa6aa32f2db8 |  | note | METHOD: Document Review
label | be47b89c-77d9-4400-a54e-e3040936d4f5 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 8a2895b6-a923-4f40-8424-40fd16f75250 |  | note | CATEGORY: HP
label | a1256ede-99e1-4329-bc25-d85b8db632cc |  | note | RESPONSIBILITY: Nominated Authority
label | be24635c-827a-4c81-80a4-1376d086aac6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 14ab146d-6632-47f9-80dd-6c6e5e9bdf59 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | f2b22504-cfea-436e-91ec-485ea45cbdcc |  | note | REFERENCE: 611.05 (a)
label | 86817971-cd71-487c-b3f4-e41507cc7cf5 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | 6540f7d7-b78b-4005-a329-522402e358aa |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 60e0d5c4-31a2-4048-86d2-875ffdf606b8 |  | textbox | Enter: Teambinder Material Approval number
label | 9234d1e1-ce2f-48e1-94a1-9d97ddca6b6a |  | note | METHOD: Document Review
label | 0a4bff65-7b51-4a3e-85fc-36630fd8013e |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | b6c2fc72-4b2d-43c7-9f3b-1ed84be601d1 |  | note | CATEGORY: WP
label | 9cb20c15-a0af-4fe5-a076-86ea2742a815 |  | note | RESPONSIBILITY: Nominated Authority
label | a58fbf22-c449-4984-a544-5e52cab27009 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0a2d125a-a383-403a-bf1b-c3d1a8df4a52 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 331c982d-ab60-40b9-b225-93c1dd1af8c4 |  | note | REFERENCE: 610.26 (a)
label | 889938f1-72db-41af-8014-1fbdf13b29a6 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 51800c77-2e75-4992-a78e-309f896fda51 |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | adf6c928-1a39-4c80-9f6d-57dcabdb57e8 |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | ff7ee489-d6b3-40cf-9917-4bc17ba3a22d |  | textbox | Enter: Teambinder Material Approval number
label | effda2b2-691b-4f57-b882-11769a4c129a |  | note | METHOD: Document Review
label | e1b969d2-af34-4536-a270-eb700ab85858 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 6a9f0295-0621-4d66-bd96-4dc1dba72b80 |  | note | CATEGORY: WP
label | a0c4c821-be6c-40fd-a2aa-fac86c09b6e3 |  | note | RESPONSIBILITY: Nominated Authority
label | b4e8be78-4d02-4643-9992-d2251db5b8a2 |  | note | VERIFYING DOCUMENTS: This ITP
text | bef20946-d7ed-4645-9a90-0e68ba3dc799 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Curing Compound
label | e25e24d9-e817-420b-af2f-59ba7f231013 |  | note | REFERENCE: 610.23 (d)
label | ba0b5135-f6bf-47bb-9c8e-280f97e90177 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | a595a363-8c34-462c-824f-21747b5a27b0 |  | textbox | Enter: Teambinder Material Approval number
label | 34166df4-6dc1-414c-a70a-a13024118a47 |  | note | METHOD: Document Review
label | 78b715d0-9dee-4670-9e7c-4b338dc2c1ac |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | b4c8f92b-0c00-4dfc-9d14-5017bb839d8f |  | note | CATEGORY: WP
label | 67600c9d-af18-43ee-b2c8-8f1df07f0413 |  | note | RESPONSIBILITY: Nominated Authority
label | af1bdfb6-5e5c-4360-ba1c-1a94c27f81ca |  | note | VERIFYING DOCUMENTS: This ITP
text | cfa46a6a-4dd9-47c2-b440-a980c09f0ef7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Piling Operations Work Procedure
label | bedf03f9-4b4b-4bb6-864c-247c3fa5dd6a |  | note | REFERENCE: 606.03 (a)
label | 2da76e35-89ae-484e-b99e-678e5f9a08a0 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 0af7d1d3-dd79-45ea-ab96-e5dff13632f3 |  | textbox | Enter: Teambinder Approval number
label | dc061630-faf0-4333-8b10-21a005fad5ea |  | note | METHOD: Document Review
label | 82212346-834e-4707-92da-bf178e311cee |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 79259ec6-36a9-432b-8059-b2002891449b |  | note | CATEGORY: HP
label | bdfd5303-b650-44c3-884f-b65eda6e2d72 |  | note | RESPONSIBILITY: Nominated Authority
label | 3e29aa82-cff2-49af-a079-d3f49a7e039b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 680eee8e-1bbc-4e28-a468-f3d3edc6859b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Temporary Steel Casings
label | 3a26be1a-65d1-4c01-a690-1612f9fc9a8b |  | note | REFERENCE: 606.03 (b)
label | 769e934d-e0f7-4fe6-8796-a2b44f12b007 |  | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | 5367aa75-643f-4ce4-a292-6d44403e5709 |  | note | Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | e00fadfe-6ba8-4db6-930e-908605d0e1ea |  | note | The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | 92acd849-1b86-4177-8998-ab8224da3284 |  | textbox | Enter: Teambinder Approval number
label | 1e87c8c7-7866-4dd8-b7eb-600a9cad4d70 |  | note | METHOD: Document Review
label | e0a2df34-43bd-4f71-a0d6-50ae0a874086 |  | note | FREQUENCY: Where applicable, once, prior to use
label | 1f281268-f1df-46af-9dca-f8f602f6387b |  | note | CATEGORY: WP
label | 132d3025-c8c3-4f42-8ccf-1cbeaf82d57d |  | note | RESPONSIBILITY: Nominated Authority
label | e6b458d5-97bf-44c6-85d3-598a85399682 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7f9f95af-a39d-4d59-8e35-f3072ccddb6b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Casting Under Water Procedure
label | ebd3b4f3-78bf-410e-a0bd-1e97f07e7819 |  | note | REFERENCE: 606.06 (a)
label | 8d42dc8c-1d4f-4ab7-9ff6-6a662134d07c |  | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | 9e9b0031-0c63-4dec-9251-4b9e905ff749 |  | textbox | Enter: Teambinder Approval number
label | d20b1360-8a8e-4db7-9ae8-5c16c4e2756f |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number.
label | 703c00f3-ffb5-447b-be4c-e17d12cadf5d |  | note | METHOD: Document Review
label | 02b1c675-f094-413d-a4e1-462f519078c9 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | a314aadd-5505-41e7-8aee-1a8bd59bd6f3 |  | note | CATEGORY: WP
label | 1388009b-3e15-40a7-bf46-ba2c8ad5c3c4 |  | note | RESPONSIBILITY: Nominated Authority
label | 247c04b3-f08b-47eb-a7ac-419baec2dd43 |  | note | VERIFYING DOCUMENTS: This ITP
text | 22d12a56-a554-45d3-8906-49bd80c5f4af |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Boring With Bentonite or Polymer Fluids
label | f0809921-354f-43f4-bb69-d7c56edecd8c |  | note | REFERENCE: 606.06 (c)
label | 9289a257-f245-487d-8f8d-daebd187ac4f |  | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 023c2ac0-c7ec-4a1b-a114-9e923804db88 |  | textbox | Enter: Teambinder Approval number
label | c1d492ca-dcb1-424d-a6ef-1949ce742410 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number.
label | 4736cf17-468a-4aae-9790-d65430c75a74 |  | note | METHOD: Document Review
label | 0d64564b-aa3b-42b9-83b6-6e7eb16c7a3f |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | b8a8e238-9720-4cef-ba1b-1f3909b363fa |  | note | CATEGORY: WP
label | 587f6a3c-ab31-4161-acea-2da5c8be4bf5 |  | note | RESPONSIBILITY: Nominated Authority
label | 43e51645-7c7a-49a2-a4d9-8020f1fa2766 |  | note | VERIFYING DOCUMENTS: This ITP
text | c09c95f4-1a5c-425e-8798-fb5342bc1212 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Pre-qualified Pile Testing Consultant
label | 0d43fa2e-5f28-48ba-b548-0db92534ca20 |  | note | REFERENCE: 606.07
label | 81dd5f62-a956-4c50-827a-25bc475c10b9 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a pre-qualified consultant who is independent of the piling contractor.
label | 0890bb22-4f18-413f-90d4-87a122ffed15 |  | note | Details of the consultant to be submitted for review to the Nominated Authority.
text | 227f626b-940f-4d4c-aa36-0c0942ec87d5 |  | textbox | Enter: Teambinder Approval number
label | 4c47def2-30a5-4a71-b458-057aa0fd2878 |  | note | METHOD: Document Review
label | ad46b37f-141e-480a-932f-7164956ce773 |  | note | FREQUENCY: Once, 2 weeks prior to testing.
label | bb0b2718-bc6d-4999-9101-e1e59f54a547 |  | note | CATEGORY: HP
label | b243003a-4bf2-419e-ba91-9a8cebcafffd |  | note | RESPONSIBILITY: Nominated Authority
label | 49f78c7b-f45e-4ece-b523-602431269cdf |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | f5bd4621-d797-4753-8e9a-4c22078b498b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Reinforcement Welding Specifications & Qualifications
label | 5955aded-aa2c-4fd7-a16e-38d4b5c718c2 |  | note | REFERENCE: 611.13 (a)
label | 31c8963d-b6e9-4dc0-bf56-2ea9a24a2132 |  | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
label | da14b0ce-c2ef-4033-b2d1-e9cc0a3f3460 |  | note | 611.14 (b)
label | d33b5f73-af4b-4895-9f53-059724cde021 |  | note | ACCEPTANCE CRITERIA: Welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | bf8f9374-7902-4d6d-a596-38838adbcfa5 |  | textbox | Enter: Teambinder Approval number
label | 0b1fcc3b-cac9-434f-9649-f5959fb2588d |  | note | Note: Tack welding requires the same documentation but is a Witness Point
label | 34aeb02c-2839-433f-b067-c31413631832 |  | note | METHOD: Document Review
label | 35d42990-7e8e-4241-88cb-016e2b840309 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 6a39ae15-d3ad-4b45-bdf6-d92a2df9ce98 |  | note | CATEGORY: HP
label | 3c5653f9-246c-4e41-8820-b74ad903fc21 |  | note | RESPONSIBILITY: Nominated Authority
label | 9fea66d4-5ed7-4ee9-81dc-cf8ae9364d08 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 5c45b3f1-1ec7-49cc-ba76-fa18bb97cf47 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 9c36389e-1352-4066-9101-22e96c367653 |  | note | REFERENCE: MRPA Quality Management Plan
label | 3ae1f1de-1289-4618-816d-0c50cf4b041e |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 9050de2e-976b-464a-952e-2fa15db9f077 |  | note | METHOD: Document Review
label | 556eaaa3-2554-48fb-8c34-564b5f8f728e |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 8cd6fb0b-15a0-43d1-9bd2-cacb8be033f5 |  | note | CATEGORY: HP*
label | 4b90e828-a7f5-4d07-ac00-2390efbc28d7 |  | note | RESPONSIBILITY: All
label | 23700c95-d513-47fa-ac2c-ca0c33b15a55 |  | note | VERIFYING DOCUMENTS: This ITP
text | 62ededde-084d-49c7-9a3d-bcec615ae80d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 26079e65-ebe4-46b2-9fd9-e4cd86890eef |  | note | REFERENCE: IFC Drawings
label | 4917935a-7501-4deb-a5ac-4f7e55f653e6 |  | note | 606.08 (a - c)
label | 767be317-6c1f-4439-b611-8b8db198134a |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 2e14f5f2-2efa-482f-bbdc-3493780895b3 |  | note | METHOD: Measure , Visual
label | bf470ca6-a23f-4bf5-962d-cc358982661e |  | note | FREQUENCY: Each pile
label | 7117abf6-b4e0-4e6d-a7ca-bd360e115821 |  | note | CATEGORY: IP
label | e6b406be-ee0d-42b4-9f2e-e95d8cf9e816 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 0862efe0-1c58-48cf-bd58-80a20d348e0f |  | note | VERIFYING DOCUMENTS: This ITP
text | bef9f503-6a13-42b3-9374-e5f08006861c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 540d5c32-1d18-4dde-8489-3a73a1aa88af |  | note | REFERENCE: 606.04
label | 2b034707-73e0-4366-9c7c-4641e3e6acb5 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not:
label | 94955b57-2bdd-4729-81fc-1ecae2be4237 |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 187e614e-811b-4eb3-8ead-65da18755250 |  | note | ii. commence within 2.5m from newly cast piles if that pile concrete strength <15MPa
label | 0f8134ca-bfcf-484b-ae77-ad368a8f88d0 |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 5df84afb-1de8-45fb-96ea-5659d3012f60 |  | note | METHOD: Measure , Visual
label | 9ecb4d55-e167-4095-9f5b-507c9f9e3e46 |  | note | FREQUENCY: Each pile
label | 42c87503-b030-4f24-871d-cabc29fa5bda |  | note | CATEGORY: IP
label | c66bf1fa-90eb-4a7f-b145-2f163d7fbaa7 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | c733a77b-76ba-4b61-b0c1-3a34b195b867 |  | note | VERIFYING DOCUMENTS: This ITP
text | e33a60c7-bc89-4ec5-993e-9c97b937635f |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | d355debd-6d06-43b1-a445-d83edd0a6f6f |  | note | REFERENCE: IFC Drawings
label | 462f8294-2907-4871-a4c8-dfe81ad756f7 |  | note | 606.03 (a)
label | 42fb0309-dd66-4caa-a4e6-ce363244e8f3 |  | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | ce3ea90f-9af7-4ec8-9242-1b3c149b1039 |  | note | Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | b374faff-8fe6-4d0e-904d-55c450d70440 |  | note | Excavation clean and de-watered (where applicable) for inspection.
label | 36ac9151-cc28-4da1-89d3-148a6fcbf6bb |  | note | Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | ad5528b7-3a0d-4b8e-9cca-c156e253ae49 |  | note | Excavated material to be disposed of as appropriate to maintain a clean site.
label | 493a6684-5db6-48f8-8aea-c67f10fc3591 |  | note | METHOD: Measure , Visual
label | 9fae375a-04ee-4a4b-b461-c34fc7d6670f |  | note | FREQUENCY: Each pile
label | 14c0356b-e89e-4007-bfa1-be97d122fc4b |  | note | CATEGORY: IP
label | d7bb9d4b-1de5-4032-82e3-38a0da61ddd9 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 8ce85fa4-b57c-4272-97d6-1f709ca9cd73 |  | note | VERIFYING DOCUMENTS: This ITP
text | a813f270-c714-4d3e-b3fa-f486f77a065b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | 346b2d6f-e935-4328-be5e-c18ba177110f |  | note | REFERENCE: IFC Drawings
label | 2259b2c5-b075-4fa5-b2ba-bf6d7ae11683 |  | note | ACCEPTANCE CRITERIA: Formwork / formatube shall be used to ensure the top of the pile is at the required RL.
label | 07292885-bdde-4645-b9a2-c7342f9fa9a6 |  | note | METHOD: Measure , Visual
label | 6a5d3a0a-4159-4f2a-a2c0-129daeb6121a |  | note | FREQUENCY: Where applicable, each pile
label | abbbf0af-31a4-40c3-8ae8-3ec32a531371 |  | note | CATEGORY: IP
label | d41f65e5-bf92-4270-957a-05a314e3d94b |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 02417a19-46ea-4d94-8e62-11880a0ff293 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1254a4e5-cb48-45fb-aa92-39e70b5fb3a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | cc75cfb7-6105-4ac4-af1e-e464729b6ebf |  | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 45473256-8ade-45c3-8099-ea2049785b44 |  | note | Attach: Geotechnical Field Sheet or Report
label | 47ed4f2f-bc39-49e0-ab35-349834091101 |  | note | METHOD: Measure , Visual
label | 618d7677-6895-428a-b231-23fbcae9f0ca |  | note | FREQUENCY: Each pile
label | 52004d83-73da-428d-91ce-5d3114dbfadd |  | note | CATEGORY: HP
label | 89e1d14e-8620-43c0-a57a-2a5f6771cd93 |  | note | RESPONSIBILITY: Geotechnical Engineer or Nominated Authority
label | d54901fe-c35b-421d-874c-526e49e228d2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 2746232b-8e4b-45de-a526-881b94d0d5ed |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement Placement
label | 71b14e95-40bd-4f97-996f-34ceeb9154f7 |  | note | REFERENCE: IFC Drawings
label | 25f0c5f0-b576-44ea-a56b-f90b54eae64d |  | note | 611.06
label | 78bad2c7-5649-4117-9cc2-da102b7a9565 |  | note | 611.09
label | e021bca3-9a32-453f-858e-d175ef34357e |  | note | 611.1
label | f4c9cecd-2e15-40d7-a23d-2b05da8120f2 |  | note | 611.11
label | 1281ad5f-8a3a-466c-a7d6-45143c357da8 |  | note | 611.12
label | 08776ec9-c63b-40a1-bd50-aca47c1d6298 |  | note | 606.06 (a)
label | 2b8e3320-3221-4c30-aa8c-7e50bbc99a80 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | f3204cd4-d014-4218-8370-6914dd8916ae |  | note | Projecting reinforcement is the correct length and location.
label | dd74d11a-b683-426a-8640-f0d9d6f4318d |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | b2f82f66-19ea-4b99-95b4-f22f5bf1cf46 |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 1c2d8767-fc4c-499d-82c8-09996f9e0129 |  | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 0cd7763d-20cd-43b7-b3bf-49bc43e68892 |  | note | Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | b362b690-23ef-4419-9350-1a2aa90e391b |  | note | METHOD: Measure , Visual
label | a845bc51-fb5c-4e9e-b3a9-daccb53f0421 |  | note | FREQUENCY: Each pile
label | 57f50ae8-5919-428f-b63c-fc49bcadfcaf |  | note | CATEGORY: IP
label | 80ff74ba-5f2b-42e2-9d6a-cc05968e299e |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | a0be2fcc-b44d-4022-8551-145520c5dc5a |  | note | VERIFYING DOCUMENTS: This ITP
text | 1ab9da27-6224-4c0e-882e-ae333e6f3324 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | ccc1f00f-4fa2-4e89-aad0-c2bf9eefc567 |  | note | REFERENCE: IFC Drawings
label | 1aaf8e9f-76b6-455a-9125-0b72fdce1919 |  | note | 610.29 (d)
label | 6ae4c33b-8c3a-487d-aaf2-e2a7d575c04e |  | note | 610.43
label | d2460355-73b7-4cdc-8529-512314e53e7f |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | cf1a6bb9-22fa-4e38-9232-5bb6bcdce55f |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 010eb0f9-c529-4eab-985d-9a22dcd196e3 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | 93a07656-4a9d-4cd8-b291-142966bf7e58 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 13db87a0-3f1f-40ab-8336-686c7c2015c2 |  | note | Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | bd267533-0cd3-4c30-a24c-0e7a6a7a7909 |  | note | Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 8e1e4131-d5bb-4421-ab5b-79cd8f661580 |  | note | METHOD: Measure , Visual
label | f5a99a1c-f6c6-4152-9ab0-0c39b5571c6c |  | note | FREQUENCY: Where applicable, each pile
label | 96fa33d0-e1d3-41e5-872d-f7872799f576 |  | note | CATEGORY: IP
label | ea88852b-4cbd-4822-b913-73598201458d |  | note | RESPONSIBILITY: Earthing Engineer , SE/PE/SPE
label | b1c5c6d6-95dc-40c0-8567-359b8800e5a1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 92e2dd65-a779-443a-8ea2-4a0a608feb22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | ed8bc6c0-1f48-4dda-ada0-4eb40455c921 |  | note | REFERENCE: IFC Drawings
label | ffea49de-4f88-47f4-be99-e8fdfdd9a891 |  | note | 610.46 (a),
label | 31add246-549c-485a-a715-4f3206d10f8b |  | note | Table 610.462
label | 0fa7adcd-426d-4dbc-8a1f-ae41e790511a |  | note | (November 2018)
label | 3db702bb-db95-4d2d-b0fe-b6301bdfd30e |  | note | 610.47 (a)
label | 85e1b5ec-0da6-499e-bb38-6b05efb7a862 |  | note | Table 610.472
label | 2de9b2d7-fe0a-47b5-82d3-2a000c5cba50 |  | note | (March/June 2019)
label | 95c03829-41c5-48f3-8959-27d764b4bf81 |  | note | AS3810.1 Table 3.3.6.2
label | 1830946f-cbd9-4174-8f0b-fd213d4e9254 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 8422249c-e56b-4c91-bd9e-49939f053080 |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | a41cf4f7-700f-4ebc-b88e-7b84bfd39d1f |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f9ee1f70-7f63-439f-9a70-6b0a8bda1846 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 04c0c6c2-8f04-4d2e-944b-f5f54a067250 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 1516bccb-b802-48ea-b231-50c36c7f05a6 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 46c9141a-870c-45d7-9083-9b4292f946b3 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 00b53d27-ee59-46ce-abc1-34a2388969e4 |  | note | iii. Ducts and conduit location = ±12mm
label | 0e3bdcef-6e49-4c88-9586-aca508f5c85e |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 26db0fa5-2c6a-4913-a84e-92d14b4c5134 |  | note | METHOD: Measure , Visual
label | 9de118d4-a9b5-4050-9fb3-36982779c706 |  | note | FREQUENCY: Where applicable, each pile
label | f223a692-a801-407e-851b-d761fc1eb784 |  | note | CATEGORY: IP
label | ca006fb2-9e51-4931-88d8-855979e42b24 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 1945d34c-cc80-4264-902b-24e46bc15957 |  | note | VERIFYING DOCUMENTS: This ITP
text | a9fa28db-ee26-4fd1-b536-a068f34bd391 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | 86e6927f-6e97-4cb7-99b8-70c700b8f1c6 |  | note | REFERENCE: IFC Drawings
label | 77b4797f-d0e4-4117-a752-8c3c9933ed46 |  | note | 610.18 (a) (ii) & (iii)
label | e8512bf5-6628-457c-b893-ce8dccff2752 |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 073951d4-5685-4f4e-a11c-04e4d9d37a98 |  | note | All foreign material has been completely removed from the excavation.
label | 9b743ca5-e8f3-4778-9f61-9f4e072e9fdc |  | note | METHOD: Measure , Visual
label | 4c159898-7d35-460c-b533-12257f9c7cde |  | note | FREQUENCY: Each pile
label | ae37dbe8-5de2-4712-b522-17c1b256753f |  | note | CATEGORY: HP
label | f847d69e-0f05-4e64-885c-5798f3d1df51 |  | note | RESPONSIBILITY: Nominated Authority
label | 5c8e2deb-97e3-4711-a5e9-cf5d4e933cf9 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e8dd306e-bcd9-4c61-a166-7095d8a221e7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | 9fcbec9f-87e2-4d62-a634-d762d020dff9 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
label | 7e669203-0f8d-4144-b20c-2b3992c8d781 |  | note | 610.17
label | 827b6c16-f8b9-4c0a-a495-e077e8469988 |  | note | 610.17 (a) & (e)
label | e5418854-7263-4e37-b541-ca0f4056053f |  | note | Table 610.171
label | e51a2295-6c92-407b-a220-c4cf98b60360 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 3b03f0f6-a25f-4830-850c-c1076e93c01b |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 2aa68aa5-f20f-4c03-afcc-28fa95483836 |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 7bc5f9f9-f200-4770-8b7d-6e8ea66b5a1a |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 8687896c-dfe0-4b1e-9953-5bc3eae29a99 |  | note | Record: Required information on the Concrete Pour Record.
label | 9a4e47fc-4043-46b0-b6d3-aa3d860bdf17 |  | note | METHOD: Measure , Visual
label | 544bd278-7e07-420e-81ec-71374c3c972b |  | note | FREQUENCY: Each pile
label | 6d793d04-4083-462f-8e8d-ebd418cb1ec9 |  | note | CATEGORY: IP
label | 97770a42-5505-464d-ac6b-81e921dafe01 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 3d80672a-4d6a-44f7-9155-838d7c8f4b01 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b0d8df3-d974-4f7a-8c1f-a424fad0a2d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | aed4fd7e-a2a5-42d9-b3fe-5ce32cdfb777 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 37c021f0-91da-4de1-af51-74fe146285e8 |  | note | 610.16 (b)
label | 9bb88dc9-3888-464f-8e6b-7efe22de2750 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 534d9d70-fde3-4d0c-9ee9-ad4a384c9178 |  | note | 0m³ to 10m³ = 1 sample
label | 3517b1ad-d0eb-4b94-b593-a96de732a53c |  | note | 10m³ to 25m³ = 2 samples
label | 84a54d06-1e6a-40fe-8f7a-1aa6fb4500dd |  | note | 25m³ to 50m³ = 3 samples
label | 2f02e9f2-af75-44c2-abd4-986cfa2a7298 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 716f626d-dc21-420e-bcdd-e9a03dba4406 |  | note | For each additional 50m³ and additional sample shall be taken.
label | 1df2c792-46f9-477a-9817-c8a50030798d |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 8ced28d7-f659-41a4-906e-2813c6a87773 |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 2e3b8962-b87c-4307-9d80-64c3567cff5a |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 6e0fc8df-22a0-418a-8378-3399690ce5da |  | note | Record: Required information on the Concrete Pour Record.
label | af28b409-6ad8-47d5-af88-620037d90e6a |  | note | METHOD: Test
label | d128a844-b3b8-4d08-9ab6-2d2c909613ef |  | note | FREQUENCY: Each pile
label | 2c6dfc07-3656-4ff0-8885-08e5802b721c |  | note | CATEGORY: IP
label | a2729b5f-e521-456d-8fbe-f9c18a215ab7 |  | note | RESPONSIBILITY: Concrete Tester , Foreman , SE/PE/SPE
label | 7d55990d-d7c1-4f7e-a6f5-d238eb6e06f4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8771d094-3029-48bb-99e4-0e8ee70ff06f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | 8242c765-47f0-4c1b-a935-60071aa79df1 |  | note | REFERENCE: 610.13 (b)
label | b40f879b-6c47-45bf-ad6e-311c03b949a1 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | 18667b6a-3085-42e4-84b2-99adb3f2f6e7 |  | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 4e88553c-b40a-4ec2-8b26-e9e8fa301726 |  | note | Passability = ≤10mm (aggregate height differential)
label | a5149ff7-fcc9-4a2d-bcd2-5e0dd556b1e4 |  | note | Record: Required information on the Concrete Pour Record.
label | 8b7be3f1-a470-48ab-a74c-a188363d316b |  | note | METHOD: Test
label | a4d6a3dc-e7e2-4fef-9833-47275b6fabf9 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | ee93777a-de0b-40a1-bef3-7cd76bdd610c |  | note | CATEGORY: IP
label | 05910495-e279-4eeb-9497-ac7e11ee3bcc |  | note | RESPONSIBILITY: Concrete Tester
label | 0248413b-639f-4e50-801a-205fe9106f32 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9c3b31e9-f995-4592-8cbe-c60276e172a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | 18bcafb3-bc6e-48a9-9e5a-8f734ee055ef |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 50c78106-f907-44a1-8e3d-231550facf1f |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 3b53502b-c81d-4874-bcb8-7575f503793a |  | note | Record: Required information on the Concrete Pour Record.
label | b436c4fb-b2c4-478c-837f-fd1815fd9809 |  | note | METHOD: Test
label | 4bda72bd-5a29-4c4a-81ad-e5a9bde7d8b9 |  | note | FREQUENCY: Each sample
label | ad174912-54c4-4e71-b7b4-8cc8e06b3305 |  | note | CATEGORY: IP
label | 1feeaa91-9d79-46f5-8a0a-32b2943d086b |  | note | RESPONSIBILITY: Concrete Tester
label | 8a48747a-4d4d-4d7f-a690-ff0672e0d3fd |  | note | VERIFYING DOCUMENTS: This ITP
text | 29f003bb-187c-42ab-b971-cbc8f23d47dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | d0a19141-78a1-40a9-9dd5-75f5257ca9e9 |  | note | REFERENCE: Piling Quality Procedure
label | 2f8d7ac1-7e14-4d16-9a25-83fa04d3e7bb |  | note | 610.18 (a) & (b)
label | fa4e0bf3-a5b7-4910-9be0-6631d71bfec5 |  | note | 610.18 (d) (i)
label | 02282a33-74ba-4e6a-9bb4-ffe214334ecd |  | note | 606.06 (a & b)
label | ba133e4c-d383-4b82-8c8b-31e5dea00f8a |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | d356ea67-58c3-4533-a38d-9a40e6b4e242 |  | note | All concrete batches are traceable.
label | 07ffcd86-4d4b-4a54-bb4a-9a0e86a26bed |  | note | Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 5192554b-1c6a-4f37-b457-1fd8f216051a |  | note | The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | edb073d1-c4e3-4922-9db7-06538e82d079 |  | note | When placing under water, the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | cc59c8ed-8c0f-4be2-a67a-79084305aa72 |  | note | Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 4e509859-7ff6-493b-be70-e58d3733eb09 |  | note | Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | a6ce56b7-3cfa-4235-8dfd-14190cbe64dc |  | note | Record: Required information on the Concrete Pour Record.
label | 9bd6a195-da5e-4e59-a682-ee494c9f7d0b |  | note | Attach: Concrete Pour Record
label | 316cba6e-5f22-4517-9bf4-cc9d30adf330 |  | note | Attach: Concrete Dockets
label | 4e413dd8-c85b-4ae9-906b-02eff82bfab5 |  | note | METHOD: Visual
label | c0554a7b-9ffd-4a99-8301-421129c30391 |  | note | FREQUENCY: Each load
label | 3232964e-1b08-46ad-a00e-78c79a59e8ea |  | note | CATEGORY: SP
label | 323f57de-9114-4238-afd1-eea2d9d04a1d |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
text | 8be32d35-6720-4d37-8e12-5fe2a8b570e1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 0c9d1af0-9e84-40a2-bd15-1766973cc26e |  | note | REFERENCE: IFC Drawings
label | f2e9d32d-6bf1-4fca-b156-72de75c340d7 |  | note | 610.31
label | a9989a81-3a32-49ee-a2a2-82840c1e7dcc |  | note | 610.2
label | 2edb9aa1-14ac-4e8c-8be7-88b8a8fa4261 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 8d90467d-6307-483a-a10f-984b7ce8f869 |  | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | b1a247d6-e862-4ce4-afd9-a2721e658bb6 |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | c25dbaeb-de9b-4c31-9b78-c5fc9902f9f1 |  | note | METHOD: Visual
label | 0df24f97-2068-423e-84b5-2500a43c20fc |  | note | FREQUENCY: Each pile
label | 11378023-0504-4c19-9db4-68b811eca820 |  | note | CATEGORY: IP
label | bdfe9b2f-e87b-407d-9dfa-ccfffdbf45a4 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | f5c28fa5-9746-4d4c-80b2-7dab9d967bcb |  | note | VERIFYING DOCUMENTS: This ITP
text | 498876a6-c2f3-4e2c-b546-6d458ea7930b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Curing
label | 369a8af6-070f-447f-b1e7-dd2894a690db |  | note | REFERENCE: Curing Methodology
label | 2efa23b1-b9be-469b-95e7-a49317cc0c2e |  | note | 610.23
label | 44452c3e-359a-4381-bfee-b499a9a768b4 |  | note | Table 610.231
label | 2590d6ec-820c-4584-81a0-fe9a028eadda |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ef077aa7-109f-43d1-bf79-dce12e42b35a |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 53b0ec4b-b84e-474c-a010-0ed8aff9bc38 |  | note | METHOD: Visual
label | 70652a10-83ec-4ea5-9710-2e40990060a2 |  | note | FREQUENCY: Each pile
label | f87f6fce-f0bb-4969-98df-018ad44e343c |  | note | CATEGORY: SP
label | 262df353-bdb4-482b-81ee-7adf0673804c |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | f3f2846e-4053-4df8-83b9-b464cf491023 |  | note | VERIFYING DOCUMENTS: This ITP
text | 55e29f98-4a4f-4f87-944d-a2675153d962 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compressive Strength Test Results
label | bdc74fa5-4df7-49db-803e-879973fc6c64 |  | note | REFERENCE: IFC Drawings
label | 38e4c2f6-5a7c-4cc1-8884-a91dd91068d7 |  | note | Table 610.05.051
label | 0fdc5da2-a1c7-4745-8e52-901acc86da63 |  | note | 610.16 (g)
label | 0cfecad9-872e-4e2b-996e-8db0f08ee2be |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 2aabfac3-a632-4310-b2a0-ce6454ee9156 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | b49aab90-4cab-46b8-9c74-af4dba7514a1 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | a354e858-ba26-4864-9fbe-2ec6b1bb8791 |  | note | Attach: Compressive Strength Test Results
label | 1226c65d-0b03-404f-b3ca-429514a4ad53 |  | note | METHOD: Document Review
label | 79319f69-7419-4ebf-9234-5126dca37cb0 |  | note | FREQUENCY: Each cylinder
label | f82a0289-8fc2-4dae-bb01-8154e12d44fb |  | note | CATEGORY: IP
label | 7fed2ff9-c04d-468e-b5fe-625043cae85a |  | note | RESPONSIBILITY: SE/PE/SPE
label | f0bebb9d-5fef-41de-97a2-7a92282ac887 |  | note | VERIFYING DOCUMENTS: This ITP
text | 095ecf42-2b25-4bd7-bf37-d38ec6672451 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Pile Integrity Testing
label | e061f2ae-9969-4915-af5c-9b0ef9266ead |  | note | REFERENCE: 606.07 (a, d & e)
label | 91111c25-5238-495f-a279-e261ef3b0644 |  | note | AS2159 Clause 8.8
label | 1fbe3b1d-2951-4ac4-b5a4-fa461420731c |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | bf8319c3-e5e3-43ac-bcd0-c5451fc057fc |  | note | Cross-sectional area = ≥95%
label | d7297512-286f-46ed-9cfd-d4a81adba560 |  | note | If any test fails, all piles shall be tested.
label | 779ee0d5-00c8-4987-92c3-928fa1a70d9a |  | note | Attach: Pile Integrity Test Report
label | 1e27c7c9-b9cf-46e6-be52-90d601cc9c5c |  | note | METHOD: Document Review
label | 8f1e35db-827d-4107-a76f-1b2390a88991 |  | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | c4cc91ec-01be-4f36-b44e-a4fc5e230af5 |  | note | CATEGORY: IP
label | 50b3ba0e-aa6f-4602-8033-658217f5decc |  | note | RESPONSIBILITY: Testing Consultant , SE/PE/SPE
label | 2a208de5-8643-4d79-9657-b2bf87f26723 |  | note | VERIFYING DOCUMENTS: This ITP
text | 07e0b182-9439-4303-81bf-192bb036e8c8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | a5053fe3-c7d8-4701-bab1-f04274b108a2 |  | note | REFERENCE: IFC Drawings
label | b86fef4a-276f-4843-be09-85c05145cd1b |  | note | 606.08 (a - c)
label | 1f2c27bd-9f49-4253-ae7a-34bcf9070a0b |  | note | AS2159 Clause 7.2.2
label | 50936434-812c-4d7d-89f3-37103fa69fae |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | 88c6a7cd-d4f0-47bd-9a6a-d11ca9b8dd05 |  | note | i. Pile head plan location = ±75mm
label | f102db9f-6da5-4b4a-aaaf-4c39d5fa52ba |  | note | ii. Variance from vertical or rake = 1:100
label | a6342a05-6327-4dcf-a046-a5d412110462 |  | note | iii. Irregularities in straightness = 1:100
label | d74ca588-e983-4350-a92f-d082e33982db |  | note | iv. RL = ±25mm
label | 7269a9ee-c935-4dec-8863-00ca139c62b8 |  | note | Attach: Survey As-builts / Survey Report
label | b040062b-37f4-45e3-b5a0-986009997430 |  | note | METHOD: Document Review
label | 714eae9a-59b5-4dff-80f6-9065a6645542 |  | note | FREQUENCY: Each pile
label | f784de7e-b8fc-4288-b3a4-c868507b82da |  | note | CATEGORY: IP
label | 79e4833e-21f1-4b3a-86a9-3f63e708ca1b |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 671cb36a-0d65-4aab-ace1-0b52681a7379 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7fa558f1-61fa-41a7-bd4a-1a0ad365caaa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 2ecd26ec-6417-4d03-8806-4c28f6051ffb |  | note | REFERENCE: MRPA Quality Management Plan
label | 1a585a2c-d3ff-4a3a-9bf7-d6bcdd0f8d8a |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 5dffc051-9954-4ed7-9d0d-69f978869cc0 |  | note | METHOD: Document Review
label | cab74a96-c952-4a6e-8b26-c2c58c711739 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | fb2ef58e-d9a6-4e43-be8f-348ac077010e |  | note | CATEGORY: HP*
label | 866bb310-b692-4a46-a7db-ac52d4baea26 |  | note | RESPONSIBILITY: SE/PE/SPE
label | aec83d30-0d6a-4935-8c38-d8c5897da9cd |  | note | VERIFYING DOCUMENTS: This ITP
text | 53d1602b-bf63-4a23-bb42-0eaab6306222 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 42d40b0c-b834-4d2e-9cde-dd78aa2fa60b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a4c197e7-151e-4533-8407-74a36e6b91da |  | textbox | Name:
text | 37a8f2da-1f69-4302-a2e1-350b989b0d48 |  | textbox | Position:
text | f1020d27-6b7c-4f6e-8797-f1043a9ff2cf |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Structural Concrete Patch Repair Rev 1 | itp |  |  |  | Yes | ITP-STR-Structural Concrete Patch Repair Rev 1 | 7548d179-a583-4c50-9249-943896815d79
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 5b2b10f9-ded5-4826-aa36-9c795e276236 |  | note | Document Title: ITP-STR-Structural Concrete Patch Repair
label | b7e0bbf7-902a-419f-a23b-fcc64cd9d53d |  | note | ITP Description: Structural Concrete Patch Repair
label | a6826a3a-5a2f-4ee3-be11-30b422146e3c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ec5627a4-6f4d-4728-8502-e9a8ee90ae99 |  | note | Discipline (e.g. CIV/STR/RAIL: STR
label | 5ff276ab-a705-4e46-b972-f4124e4fe0b5 |  | note | Revision Number: 1
label | fd2e9355-80c2-4a3f-bc74-47ed95bf8d28 |  | note | Revision Date: 8/04/20
label | b369a0ad-7e80-42ab-a98e-5e159fd18caf |  | note | ITP created by: Mike Freeman
label | 7c470a37-1221-4933-8b41-0abb820cdde4 |  | note | ITP approved for use by: Mike Freeman
label | 067457bd-15c8-49d7-9576-366a47fcf263 |  | note | 1.1 Reference VicRoads Section 689 December 2017
label | 4302dbda-fbc2-4187-89c1-64ff05308428 |  | note | 1.2 Reference VicRoads Section 610 November 2018
label | 2ea7e4ff-0c66-4e35-b550-13fdc6e3c537 |  | note | 1.3 Reference VicRoads Section 610 March 2019
label | ff7627ad-e156-4e39-a0e8-2e668aba971a |  | note | 1.4 Reference VicRoads Section 610 June 2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Repair Mortar Selection
label | fafa99ad-224f-490a-9381-aa49f6b97f68 |  | note | REFERENCE: Product TDS
label | 3ce068a0-c2fb-4b0b-bfcb-39c31b5b8535 |  | note | 689.06
label | 9679ab33-ebb5-4296-9680-5bdd632751ce |  | note | Table 689.061
label | 0428808c-ad32-420c-afdd-dce9177bdf4d |  | note | ---------------------------------
label | 0d38088e-0bdf-4a97-a009-8eb8bd0d146a |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | a00a8b35-d7c1-4af2-9c50-38ee470626df |  | note | i. able to be hand applied in vertical and overhead sections up to 30 mm thick in one application with no slumping;
label | d7623179-d0bf-4138-bfe9-9e8b152126fd |  | note | ii. drying shrinkage ≤600 microstrain;
label | 24a0b5a8-75a9-4815-8a1a-9d672079ed1f |  | note | iii, minimum wet density of 1600kg/m³;
label | eaac8acd-f3f9-443a-87ff-58916f5c10d5 |  | note | iv. achieve the strengths and bonds conforming to the requirements in Table 689.061.
text | 7e5d18bd-ff0d-4bb9-9ee7-7af183ab0b82 |  | textbox | Enter: Teambinder Material Approval number
label | e6a2d119-22d2-418d-bd20-935159f9b2a6 |  | note | ---------------------------------
label | 5b48517e-ebf0-42bf-86c4-8cbb07a179f1 |  | note | METHOD: Document Review
label | b3c28374-d6cb-4583-92a8-369b49430cfe |  | note | ---------------------------------
label | 692ee2b4-3dda-48ba-8a35-093afe19b635 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 827edc20-07fc-436c-89c4-d0aa68eb9e04 |  | note | ---------------------------------
label | e46cef70-efda-4d78-a17f-0cd1e0156be4 |  | note | CATEGORY: IP
label | c0b92e69-1554-4a9d-854b-effbdf1bdc1d |  | note | ---------------------------------
label | 2150f4b7-75e4-43a6-bba7-2246edcddbb0 |  | note | RESPONSIBILITY: Nominated Authority
label | 54e11387-2ae8-45d1-859a-e939bdff26dd |  | note | ---------------------------------
label | 2a9f0558-5858-4f64-96c1-0c91ea79bb01 |  | note | VERIFYING DOCUMENTS: This ITP
text | b6186714-add9-41d3-9c87-0e826120bfac |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Fairing Coat Selection
label | 00de30c4-c92e-4283-b40d-0b55950dff25 |  | note | REFERENCE: Product TDS
label | de4c2f98-f54d-499c-9e5f-d2ebdcde4dc0 |  | note | 689.06
label | 408c8f49-0988-41e4-86c0-e75ecc773be3 |  | note | Table 689.061
label | 177ca05e-4662-4e62-b234-d9ac9326b2da |  | note | ---------------------------------
label | a761dd10-ee44-4443-89df-f343cb700b79 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 16201cbd-37c9-475e-b68f-9e2746a83778 |  | note | i. able to be applied to 0-3mm thick;
label | c232bd32-84c6-47f4-af39-51b350056c21 |  | note | ii. able to cover a large area without shrinkage cracking.
text | 66850e4f-36aa-46ce-9e7a-40f697623637 |  | textbox | Enter: Teambinder Material Approval number
label | 3051e39f-79ac-4e74-af4a-77cf7d58d5c4 |  | note | ---------------------------------
label | d25c639f-8e45-43a5-afb7-8e1ed7f67e39 |  | note | METHOD: Document Review
label | 8bce07e1-2a91-43ec-ba23-17fac8756b3e |  | note | ---------------------------------
label | 1c7544c7-e27e-421d-b7f7-b222df35c0ee |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | dcfcbd11-756e-4861-9e16-1ceb2236b7a9 |  | note | ---------------------------------
label | 0205f4dd-3260-4891-9ad6-c2ae75ba896b |  | note | CATEGORY: IP
label | fad40178-aa47-4c77-b238-5c4098d2eec5 |  | note | ---------------------------------
label | 272a1508-21b5-4c94-8ebb-93ad3379e1c1 |  | note | RESPONSIBILITY: Nominated Authority
label | 16ef2411-306f-4083-9907-dc88fe84dd41 |  | note | ---------------------------------
label | 89612f38-62d3-408a-a274-d266c310964f |  | note | VERIFYING DOCUMENTS: This ITP
text | f8f65431-c471-4ffd-8665-06e3fc8cb57b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Reinforcement Primer
label | b88e4f15-8f47-4003-ae0b-a683e01ddfe1 |  | note | REFERENCE: Product TDS
label | bff63de7-b443-4d30-8932-e5d01ce7cdba |  | note | 689.08 (d)
label | 8e4c4bec-2cf3-438f-ad69-5a67cfca8760 |  | note | ---------------------------------
label | 2b179438-78a5-4196-8250-f9e8f14f2241 |  | note | ACCEPTANCE CRITERIA: Product nominated as part of a repair system (normally nominated in the repair mortar TDS)
text | e5fd59fe-ab93-4576-bc78-f0f2a513022a |  | textbox | Enter: Teambinder Material Approval number
label | f5a06b93-3951-40fa-ab2d-206719704717 |  | note | ---------------------------------
label | f77ea602-e161-4b22-a3c7-df7aaceae959 |  | note | METHOD: Document Review
label | 49a18862-7ada-49d0-be26-4859fbd64f9d |  | note | ---------------------------------
label | 9c74b68a-6b19-4d5a-9e05-15377158c945 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | fd859987-dfd2-4bc1-812f-b81773926f16 |  | note | ---------------------------------
label | d3d01471-a04e-408e-8663-b1fd65f5588f |  | note | CATEGORY: IP
label | 769c92db-7686-4ae5-b2f4-43d5a62a39c4 |  | note | ---------------------------------
label | 5dc151d3-e333-4b5b-9478-1f3edab7f293 |  | note | RESPONSIBILITY: Nominated Authority
label | 83d83cd9-4022-464a-80b2-4b17ad58a88f |  | note | ---------------------------------
label | cef30284-e70d-4364-af15-1bf88855ddc7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 146b0f42-3071-4074-bd3f-0f2698bda729 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Substrate Bonding Agent / Primer
label | 246e7bc5-6fb8-4355-90fb-447e9c10ec6d |  | note | REFERENCE: Product TDS
label | c9880a9b-cae5-4192-a7de-f3d5a786526f |  | note | 689.08 (d)
label | 2fb8c68e-5577-468b-968b-25c507e43974 |  | note | ---------------------------------
label | 4ad58189-b17b-4757-a374-079e594fe2e8 |  | note | ACCEPTANCE CRITERIA: Product nominated as part of a repair system (normally nominated in the repair mortar TDS)
text | a100b6be-3541-4ab6-a85a-316d8ed3d784 |  | textbox | Enter: Teambinder Material Approval number
label | c5dd672d-7810-4c09-91a4-e77354bd2d55 |  | note | ---------------------------------
label | bf063b12-c36a-42a5-89dd-cfa0b3b7eb9e |  | note | METHOD: Document Review
label | e03935be-057e-42a4-b5d7-51d7162ebcb1 |  | note | ---------------------------------
label | d99776a5-4d1d-4d2b-9efc-173306e1cf9d |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | 5cff9936-65e6-4f7a-894b-0988646098a0 |  | note | ---------------------------------
label | eadfb269-d7b5-4997-917c-3f5d19a805e2 |  | note | CATEGORY: IP
label | ec047144-7189-4429-b469-7784f1fc18b5 |  | note | ---------------------------------
label | 48ecf719-3c3c-4ff7-8f63-f54b3195d547 |  | note | RESPONSIBILITY: Nominated Authority
label | 8cbcf79a-4146-47bd-97c3-863db368b86e |  | note | ---------------------------------
label | ee912972-5303-4b59-9f4d-c02c44ebfb73 |  | note | VERIFYING DOCUMENTS: This ITP
text | d90b1c97-ad85-4754-a9e0-84eea64ebcaf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 6a74cefc-05b9-4ead-9bc2-0a713f3a6774 |  | note | REFERENCE: 610.23 (d)
label | 532a84d0-dae8-4bde-81ea-6ad749f8fd58 |  | note | ---------------------------------
label | 577b0ea6-3bb0-43b7-8a55-08e8b3c1a7db |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 38a12c7e-a604-447b-aece-deb05da1f5e4 |  | note | Note: This may be the same product used for the concrete curing
text | 131f6f76-a220-444c-aee0-2195000d9e2d |  | textbox | Enter: Teambinder Material Approval number
label | ce22dcda-3183-41ee-bbcb-0e81a042b108 |  | note | ---------------------------------
label | 24d8e068-16a0-48e1-996e-2abdb66a10a8 |  | note | METHOD: Document Review
label | ce2335e5-236e-44da-ae56-86221647cb66 |  | note | ---------------------------------
label | 4d40f52c-1bad-402c-a38b-3ecabc82549e |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | d827f42a-2e64-464e-80f1-51fc0800f337 |  | note | ---------------------------------
label | 9c0089b1-d788-4dfc-b638-bbb02a2c7699 |  | note | CATEGORY: IP
label | e3fea4a8-7b50-45ab-938c-eac7f2dc3140 |  | note | ---------------------------------
label | 32605f4f-f7ac-4ed0-8a94-a0a09aef95e2 |  | note | RESPONSIBILITY: Nominated Authority
label | 932661d1-7099-43e7-a7c4-a7613182a305 |  | note | ---------------------------------
label | 09031b73-f407-438a-93d1-3a181fbc9367 |  | note | VERIFYING DOCUMENTS: This ITP
text | d532f57b-8c28-4ceb-9fcf-ee11c408b0b8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Assessment of Affected Concrete
label | cdaf0f1c-897f-4899-91a6-e3cd904847de |  | note | REFERENCE: 689.02
label | a3ed64e1-c088-4d09-9f96-7160f34c5731 |  | note | ---------------------------------
label | bfadc984-3a5c-4eb4-8ac9-ebb1d59b6a21 |  | note | ACCEPTANCE CRITERIA: Contractor shall assess the affected concrete to determine influence of spalling, deterioration, and honeycombing on the load bearing capacity, serviceability and durability of the structure.
text | 60508cc6-c020-4d19-8f67-09574a7aa31c |  | textbox | Enter: Teambinder Correspondence Approval number
label | c5b29312-1c98-46ef-b6ca-f4d56a9e60d2 |  | note | ---------------------------------
label | 857dfdcc-537f-4196-9eb9-da63f72ac987 |  | note | METHOD: Document Review
label | af5ee9d0-f800-4ab6-953e-3b246816808d |  | note | ---------------------------------
label | a9d334d1-a805-4b10-809d-bdeee0114082 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | eb85d9dc-8008-4b9f-a715-343709234687 |  | note | ---------------------------------
label | c3d26577-08cb-4d91-a253-b2e7fed7673d |  | note | CATEGORY: HP
label | 682b9ddb-4217-4247-a67e-2155527e30aa |  | note | ---------------------------------
label | 85cc873f-c789-4d2b-b736-bbddc7227d07 |  | note | RESPONSIBILITY: Nominated Authority
label | f4ad9b1e-8eca-4017-b030-76c2de3271c8 |  | note | ---------------------------------
label | 3d156451-b007-4aed-9d65-4cafd31de2ea |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | a4ccc68b-b95c-4011-b433-9cee6a3485c3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete Repair Work Method Statements
label | 5c188a06-38e8-4a13-9e22-653e3861e98c |  | note | REFERENCE: 689.13
label | 121ec46a-e831-42f1-b530-ee4828a972e2 |  | note | 689.08 (e) (iii)
label | 9a8fa520-236f-4fb0-a9ee-5856068ae13a |  | note | ---------------------------------
label | e3c0bc6b-a10b-4642-9179-f3b58148c317 |  | note | ACCEPTANCE CRITERIA: Contractor shall submit a detailed procedure for the specific patch repair works.
label | a4a7153e-b305-4db6-a1c0-ec817c3b43bb |  | note | Generic or incomplete WMS's and ITP's will not be accepted.
text | 529da29c-61d5-47f2-8cc6-1fafe45a086a |  | textbox | Enter: Teambinder Correspondence Approval number
label | 7594645a-cd94-406d-a7c8-1b810357b705 |  | note | ---------------------------------
label | 06354b28-f5fb-47c1-ac38-1353b2b544a1 |  | note | METHOD: Document Review
label | 9e894c29-0304-4d23-943b-cbfe54423250 |  | note | ---------------------------------
label | 6665668e-b1fe-4be1-929a-3358d3757c4f |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 316188b7-1ae2-4aa4-8b94-b77ba9043d91 |  | note | ---------------------------------
label | c9956221-ff1b-463f-8956-f0739d1b017f |  | note | CATEGORY: HP
label | 6a885e78-c954-4bc9-879a-768ee943cc6f |  | note | ---------------------------------
label | 886888ce-9bee-4d66-9ef7-8e052df6c265 |  | note | RESPONSIBILITY: Nominated Authority
label | 9178d1f6-99b5-4fbe-9266-3be543950bb4 |  | note | ---------------------------------
label | e52fb047-1790-4ed6-8b80-745208d56004 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 63a54008-fbfa-4f37-a48a-5c16bb2809dc |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Deviations from Manufacturer's TDS and/or Specification
label | f57082c5-80cb-47dc-8148-2f869424caba |  | note | REFERENCE: 689.08 (a)
label | 04ce70dc-13a5-46fa-a1e0-71f1d583117a |  | note | ---------------------------------
label | 483c2f35-ef74-4e1d-a60f-7788cab3683f |  | note | ACCEPTANCE CRITERIA: The contractor shall perform concrete repair work in conformity with the manufacturers specifications.
label | c8148f8f-b16e-4e1b-941d-78ed64d84940 |  | note | Any deviations from manufacturers specification must be submitted for approval as an updated WMS and/or ITP.
text | 162159e2-17d3-4015-8df6-63f9822feb84 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 4576dd63-e05e-4d84-90e9-1050baff6b3a |  | note | ---------------------------------
label | 8eb1a504-77db-4070-bcf0-204ece18e086 |  | note | METHOD: Document Review
label | 568ea0ec-0f92-4d99-b1b8-819933be3a3d |  | note | ---------------------------------
label | 414efc4f-a2a7-46c5-96b2-3ad7b996d754 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | c6ea5d28-55c8-48ec-bf28-94f8cd648677 |  | note | ---------------------------------
label | 8ec0af17-2ffe-418c-b2ee-6dc761255b4b |  | note | CATEGORY: HP
label | 413d78a8-bb4b-4400-9f12-a1aee3c6b883 |  | note | ---------------------------------
label | cac01e05-9563-40c8-887f-110eab416426 |  | note | RESPONSIBILITY: Nominated Authority
label | 88771eb7-fb20-4bf0-a113-0fab808f4271 |  | note | ---------------------------------
label | 1d035fb8-ae38-41ef-908a-684d5fc1b5f0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 48b8a738-b99c-4c89-9221-fa2cacc8ea9d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Curing Methodology (for Concrete, Grout and Mortar)
label | 4a84be27-edb8-408d-9498-8965631205c6 |  | note | REFERENCE: 610.23 (a)
label | fcff4d57-f030-4e03-ab73-2aa0070e46ba |  | note | ---------------------------------
label | 60a1ffb8-2bb9-4d26-a9a1-0232d68974b8 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | afb718d0-9e37-4c31-be1e-fc9d25abfdd0 |  | note | Note: This may be the same document used for the concrete curing.
text | 906fcfc9-146b-4e47-8595-ffbd83586612 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 8b235128-f9bc-4440-bdaf-7722861dea08 |  | note | ---------------------------------
label | cc7315f8-7f33-4901-892d-20e04af7e68b |  | note | METHOD: Document Review
label | 07eada80-eb87-4c4b-bf89-582d797f89fe |  | note | ---------------------------------
label | 79b40ad9-8e7f-45df-89e5-20f8d1b5f0fc |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | 6975a73e-b4e9-4863-9a94-6f99327fd71a |  | note | ---------------------------------
label | c2670b97-6ce2-441f-b9d3-aae0ed64df85 |  | note | CATEGORY: HP
label | 883521d4-7e0f-4bbd-b0af-099e21f06b11 |  | note | ---------------------------------
label | 1205c9fb-1fdc-45c9-a43b-fee507b230d4 |  | note | RESPONSIBILITY: Nominated Authority
label | a34107dc-0f8a-40f8-904e-5a5f93b193e2 |  | note | ---------------------------------
label | 3ae8ec31-4542-476f-8545-4c7831b24944 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3e7804af-b878-4b4d-9807-1afe096a9af4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Concrete Patch Repair Toolbox Meeting
label | e79b08eb-a455-41a9-b6d1-5171363c7b26 |  | note | REFERENCE: 689.13
label | 1b505857-fbef-45e0-841c-435b905e46e5 |  | note | ---------------------------------
label | 0042f9b7-2f68-4410-9a74-627701911059 |  | note | ACCEPTANCE CRITERIA: Concrete patch repair toolbox meeting held to discuss the quality requirements.
label | 14a44a3a-eada-4a2b-9b79-eb4043814e4f |  | note | Minutes of this meeting to be submitted to the Nominated Authority.
text | ec945db2-af71-41ca-8834-5e8bb4e069ae |  | textbox | Enter: Teambinder Correspondence Approval number
label | 5427d97f-467e-4234-8cd5-240a693775b3 |  | note | ---------------------------------
label | 4993c266-25cd-445e-9c39-dd96651087dc |  | note | METHOD: Document Review
label | 6f85f4f1-297b-47f8-ad60-334d0a0e38c7 |  | note | ---------------------------------
label | 1f5b67d0-af36-4fe7-aaad-47411ec36647 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 3bc250e8-1466-46f6-b12a-c7320a8d5773 |  | note | ---------------------------------
label | da01043e-43bc-45c0-9129-856be5e395e0 |  | note | CATEGORY: HP
label | 9c04615a-1673-454d-aefe-9c39fc66e2b8 |  | note | ---------------------------------
label | cd922ace-9825-4991-ab07-3f20aef0c003 |  | note | RESPONSIBILITY: Nominated Authority
label | fb252a55-e9c3-4763-97b8-ce26bd42565c |  | note | ---------------------------------
label | a2090e0d-b23b-42d3-848a-971e31926290 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 85c641a1-0c6c-40eb-b9fe-22203023f47a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Contractor Competency
label | 8ff33e61-e2c9-49ff-bd83-8777481913c9 |  | note | REFERENCE: 689.05
label | d7c44d82-c8a3-4a63-8188-48ee2ec5abd9 |  | note | ---------------------------------
label | a46106be-e95a-4e54-8102-699313987e1e |  | note | ACCEPTANCE CRITERIA: Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application.
label | c0261025-19ff-44b1-b7c8-fe0888d2aba3 |  | note | ---------------------------------
label | 43131a24-b012-447b-9fb3-a3361ea19289 |  | note | METHOD: Document Review
label | 121cd89b-e3a8-4d75-9e1f-cd1f46d53b3a |  | note | ---------------------------------
label | eb8facd1-045d-4954-819d-35642e253b85 |  | note | FREQUENCY: Once, for each personnel, prior to starting Works
label | 0dfbf1b2-1ce5-4cfb-a6ca-0cd9f766110f |  | note | ---------------------------------
label | a44f77f6-e78c-4865-9c21-7eadb7834e9e |  | note | CATEGORY: IP
label | 0f214849-f2e3-4503-9977-fcc5b22a29d7 |  | note | ---------------------------------
label | 32613ce0-d01c-4bb5-847d-c8b7a00d2784 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 047dfc37-edfe-4fd1-998c-1ca23b905cf5 |  | note | ---------------------------------
label | 04c9a30b-74b5-40c4-8882-91d889cd5c6a |  | note | VERIFYING DOCUMENTS: This ITP
text | feca91da-f544-4109-8596-e3ced1aaecf7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Surface Preparation
label | 65c9fe26-5dfe-4143-bb3f-4cb60f3b9870 |  | note | REFERENCE: 689.08 (b) , (c) & (d)
label | dbc8742a-ecc1-4d96-92c7-492fed89a27a |  | note | ---------------------------------
label | 5a2b9b0a-d709-4714-bb2b-27e1b78f1d53 |  | note | ACCEPTANCE CRITERIA: Concrete broken back to dense, sound concrete.
label | 397ac08c-ca81-40e7-8b9a-9b388eff9fed |  | note | Any exposed reinforcement witnessed.
label | 179ac2b3-d446-4f2d-872f-5b1c1d14f04d |  | note | Resulting cover allowance:
label | e0cf811a-9ab9-4dce-9b17-a24c5de15e4b |  | note | Exposure classification A and B1 = 20mm minimum
label | 9b3ed7e1-3c50-4b59-9857-2381040782d1 |  | note | Exposure classification B2, C1 and C2 = 50mm minimum
label | a5151b57-f965-44b8-8a06-84a047366a3d |  | note | Where applicable:
label | abe4f6eb-ac88-4d80-bd56-63ddcb81dbec |  | note | Reinforcement primer applied with no or minimal concrete coated.
label | 7012e0e1-1535-49f7-ba8e-ea213bb78e60 |  | note | Substrate bonding agent/primer applied, waiting for it to be tacky.
label | 8e1440bb-04fb-4c44-82b1-47f4ba8a0000 |  | note | ---------------------------------
label | 404abd1a-87c6-489d-93b4-96eb77fc8452 |  | note | METHOD: Measure, Visual
label | 5e1b76c2-c0a7-4500-8194-16c783e65a5a |  | note | ---------------------------------
label | da5948fd-6fca-4bcb-95dc-478998634baf |  | note | FREQUENCY: Each element
label | bd2618a9-5a29-40ff-a087-90bb8fb1f410 |  | note | ---------------------------------
label | 5b17a0c2-ea73-477f-a61d-18113b31d8e9 |  | note | CATEGORY: IP
label | c223d711-b1fc-4b45-bc65-a57fd49d49c0 |  | note | ---------------------------------
label | 8dff1ae9-a668-4042-9286-8609e2ab1107 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3332dbbf-ae12-4a0a-bafd-e08c1f52e44e |  | note | ---------------------------------
label | f2290790-79ec-4dab-8ab8-b5e2f456e71d |  | note | VERIFYING DOCUMENTS: This ITP
text | 6e4818ae-f75b-4940-9ee8-9ea048f32536 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pre-application Inspection
label | 7a47ed7a-0373-4e8d-9164-21a33fb348b7 |  | note | REFERENCE: 689.08 (e) (i) & (ii)
label | 9b01c8b0-3eee-480e-9c33-c2daa3889bd4 |  | note | ---------------------------------
label | 1cac1c80-5042-4248-a7b6-ff7db6cca758 |  | note | ACCEPTANCE CRITERIA: Reinstatement of prepared areas shall not commence until:
label | b4538e8c-839e-480a-81a1-215fc36e2fd5 |  | note | i. a joint measurement of the repair area by Contractor & Nominated Authority
label | 05b78ac9-43b0-49a4-ad1f-5c886b817012 |  | note | ii. evidence the area conforms with specifications
label | ea261931-2445-40b7-8d6c-c1ce56c0a00f |  | note | ---------------------------------
label | 5a72362b-3d73-44bc-a455-580bb9ffd397 |  | note | METHOD: Measure, Visual
label | cd2f2d1f-4dcf-4aa2-9b01-db35b0787ba8 |  | note | ---------------------------------
label | bb5a00e3-6e82-4a0d-919d-4c4d28f5af78 |  | note | FREQUENCY: Each element
label | 291fbff1-53f3-4146-aa4b-b47fc567e716 |  | note | ---------------------------------
label | d938974a-7bd3-4676-a543-bd90af3a635d |  | note | CATEGORY: HP
label | 9b939b94-75b5-4999-a306-902416320898 |  | note | ---------------------------------
label | 1855575c-2d7b-41cf-aa1a-b004abe6eeac |  | note | RESPONSIBILITY: Nominated Authority
label | 89610fcc-701f-40ce-a30c-afa204059439 |  | note | ---------------------------------
label | ae8face5-ccc1-4f0d-a338-c7d62199efc5 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 8c06b87e-eefe-460c-a789-b184cc97e2ed |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Material Reference
label | af6d7cf8-3eaa-4390-9d4f-1d63e07b6c8a |  | note | REFERENCE: 689.07
label | fb0f433f-78c0-453b-8be3-c88aad5fbbb7 |  | note | ---------------------------------
label | 75698d75-1ea1-4472-8397-12877ad02737 |  | note | ACCEPTANCE CRITERIA: The following information shall be provided with each batch of material, clearly marked on each bag:
label | 3b7f9172-507e-47eb-832a-82503a72681a |  | note | Manufacturer's name and address
label | 8c90f948-76da-4e52-9f3f-91386feae24d |  | note | Product reference
label | be777465-2fd9-4b81-9d08-2fc6c8700e82 |  | note | Batch number of identification
label | 9c949e86-63e9-4458-a8d3-6d835e4e9ba7 |  | note | Quantity manufactured in the batch
label | abcbc27f-0b0d-4a2e-84ac-35d36b2885b3 |  | note | Certificate of date of manufacture
label | ee534695-fbdb-45c2-bf65-a546561bea25 |  | note | ---------------------------------
label | 27319e51-a0d0-44b4-8172-bf7550c1907c |  | note | METHOD: Visual
label | d9486c46-7b50-4ded-9cb4-dd8573dd4852 |  | note | ---------------------------------
label | eb86ec47-90d4-456e-a4ba-fa535e3cf516 |  | note | FREQUENCY: Each bag of product
label | 29058753-e4bf-4839-863c-b23ea02346b9 |  | note | ---------------------------------
label | b4b6abdb-91f2-45df-b687-7f3717f1b5fe |  | note | CATEGORY: IP
label | f2d3fdcd-bc53-4ab5-ae41-ec3aa17801d0 |  | note | ---------------------------------
label | e29b6a28-5aa8-4598-a68a-8deb3eb6a8c0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d4a05a32-af7c-48c4-959e-d98084999d16 |  | note | ---------------------------------
label | fea4ff34-66fb-441d-8411-6460dca59e1b |  | note | VERIFYING DOCUMENTS: This ITP
text | 1adb271b-3d7a-4f3a-ad10-42f93765741c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Weather Conditions
label | 926338f2-a915-4f71-b036-bbb534b47019 |  | note | REFERENCE: 689.08 (e)
label | 4f329fef-7480-4b34-8f98-f1c27d63fbca |  | note | 610.17
label | 01fcd892-c42d-41a6-bdcc-64e19e023a30 |  | note | 610.17 (a) & (e)
label | 2a836a4f-3dbc-4be8-b93f-5f0f9c366e19 |  | note | Table 610.171
label | aa989a99-1730-4dcb-90b2-45f6e981638b |  | note | ---------------------------------
label | cdec453e-62e9-4239-bfd4-a3144c4bed23 |  | note | ACCEPTANCE CRITERIA: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 8faa8a80-5c3a-4b88-bb48-9968152bf0a0 |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 0809f5f5-40b5-4d7e-905a-24404ea17018 |  | note | ---------------------------------
label | 0cc2f8f1-f508-4e0d-8023-5d9e6c5623f7 |  | note | METHOD: Measure, Visual
label | 253acfd7-141f-4141-a828-f1abbba23db0 |  | note | ---------------------------------
label | c0b06e01-590a-461e-b39c-3928d5d72fc2 |  | note | FREQUENCY: Each element
label | 4d24f523-beff-4deb-acb5-800ab4fbeef6 |  | note | ---------------------------------
label | 14606707-8113-463e-af38-cba6e37ece8d |  | note | CATEGORY: IP
label | 18c55dfe-a8fe-4706-9deb-fe913fc9519c |  | note | ---------------------------------
label | df9bf0a1-be71-4e63-871d-5cfd7816a104 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1a6798c2-e113-45b6-bfd7-aae8ada9f6a6 |  | note | ---------------------------------
label | deb088dd-3982-4907-a268-e403718e96ff |  | note | VERIFYING DOCUMENTS: This ITP
text | a3c2c429-e37b-47b3-aa10-ccfeadc46f0a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Mixing Product
label | edef4e66-acea-47bb-979a-4b1bf8a6d459 |  | note | REFERENCE: Product TDS
label | 0b696145-f58a-49a8-8b2f-47bbdbcbdec0 |  | note | 689.08 (e)
label | 2d93369d-b6ed-440e-8203-3b45d2af7838 |  | note | ---------------------------------
label | aa018888-6e38-4aea-9505-a5de7d8e5def |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 0c553581-6b48-42fd-91f5-9ffccff1af26 |  | note | Only whole bags to be mixed with potable water.
label | fde322c9-08db-4a6a-a366-9840df6dbfec |  | note | Volume of water matches the required amount for the consistency required and accurately measured.
label | 04eed40c-ae0e-4b61-850e-14f66574d922 |  | note | Product poured into the mixer slowly.
label | 580a239e-8790-4777-8c2c-9146c85b65f3 |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
label | dfb1b968-54a9-42d4-95b2-9aa4daa50cc4 |  | note | ---------------------------------
label | c4589e41-15ac-4109-a8f1-d298f21e50da |  | note | METHOD: Measure, Visual
label | dcc4a2df-2d8f-4832-b924-016a6ab3551f |  | note | ---------------------------------
label | b9306c29-23ca-40bd-9e1c-fe7415cca73f |  | note | FREQUENCY: Each batch
label | e63c8182-19d4-4315-8281-d21280e3c831 |  | note | ---------------------------------
label | 3b30a659-2d95-4a57-bb2c-e0487651c21c |  | note | CATEGORY: IP
label | effe935d-9e12-4b93-acdf-0c8dc3b4d549 |  | note | ---------------------------------
label | 897cc8b8-65b9-44ec-956f-470078bf2997 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9fd424bf-cbf6-4a30-ba79-6ac479f81972 |  | note | ---------------------------------
label | c10e1b16-42e2-4875-b518-ea9fc116d89c |  | note | VERIFYING DOCUMENTS: This ITP
text | 7c16b831-f6fa-48ac-b981-caada1c38126 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Product Testing - Compressive Strength Cubes
label | 55e836c1-fcdb-43a6-a0ec-122022647b58 |  | note | REFERENCE: 689.12 (a)
label | 63fe7cb0-c9d4-4105-9f03-3e5aa687acde |  | note | 610.28
label | 344d28fb-6b59-4acf-81fb-5219bee61fc5 |  | note | 610.33
label | 32a10c23-9317-4930-9388-ea493ae652d4 |  | note | ---------------------------------
label | 9eb30fdc-2bf3-4c78-9d9f-82f922e0990e |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | c19689f0-2200-4998-be03-eb20eda4dd4d |  | note | Testing is be in accordance with the following frequencies:
label | 855aa999-b8d5-44f4-987a-2ae86b3eb0f0 |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 8619dca2-f5fc-4277-8481-c5869505e669 |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | a1218f86-8295-4c9c-9168-458cbc3ce308 |  | note | ---------------------------------
label | 9818492c-645e-4535-926c-1fd1ee9b1797 |  | note | METHOD: Test
label | 2dbf1a84-6a89-4ea4-bad5-fb2f6495c93f |  | note | ---------------------------------
label | 073a8e1c-c748-45f6-a822-bc4c282f6261 |  | note | FREQUENCY: Each element
label | 762037e2-767e-4f38-b7e1-59fe1c9e48f4 |  | note | ---------------------------------
label | 97da932c-a1bd-4683-9df3-8f551082da67 |  | note | CATEGORY: IP
label | bb2385d4-928e-4207-9ca3-346bc49f79b0 |  | note | ---------------------------------
label | 2a9e7c7b-4386-45e6-9381-e585867a06bb |  | note | RESPONSIBILITY: Tester, SE/PE/SPE
label | cd8d07f2-2aeb-402f-b932-1b13279a3f47 |  | note | ---------------------------------
label | d41360ea-1d50-448d-9234-de2238cd570b |  | note | VERIFYING DOCUMENTS: This ITP
text | ad889ff0-a2f2-4be8-a0ea-42383f0024e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Application
label | 55744848-a62b-4622-9e64-9d5e51028339 |  | note | REFERENCE: Product TDS
label | fc051730-3795-47e2-b75f-c8cf3c925223 |  | note | 689.08 (e)
label | 0a9db5e6-d9ea-424c-b86f-a3cef358763f |  | note | ---------------------------------
label | 77825dc1-105b-475d-9c2d-dfe20ec89fa4 |  | note | ACCEPTANCE CRITERIA: Where a surface primer has been used, ensure that this is still tacky - if not, reapply and wait until it is.
label | 012ca93f-33d6-4488-832a-1c2c121a3695 |  | note | Where formwork has been used, ensure that this has been coated with release agent to prevent bonding to the repair material.
label | e8e9f023-f41d-4ea7-9f4a-6b7380fa3176 |  | note | ---------------------------------
label | 3ee6e33b-46c1-4ab6-895f-6d315c7ff60e |  | note | METHOD: Visual
label | bfcb23b8-9536-498e-835d-96a22cac1fc8 |  | note | ---------------------------------
label | ef156230-cb67-48b9-af74-f811e857f822 |  | note | FREQUENCY: Each element
label | 8eebe25a-c12a-42c6-b4e8-f04c257f6fad |  | note | ---------------------------------
label | 45346493-8efa-4918-86f2-3e5233234c8c |  | note | CATEGORY: IP
label | b59d06e0-b6ce-4ec6-8aec-28017ae839bc |  | note | ---------------------------------
label | b6169c6a-9787-4064-b221-90208d429e14 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 62da5176-57bd-4148-a2b0-22fd77a3a027 |  | note | ---------------------------------
label | 5d0ea684-db6d-41af-9456-81b0ef561e44 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8fae63d0-6521-40b2-803f-c64d4ee3e067 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Surface Finishes
label | e098bce9-2741-4911-b226-a2ecf92ae908 |  | note | REFERENCE: 689.10
label | a43d4644-6a95-4180-8988-e3497fff3559 |  | note | ---------------------------------
label | db8660db-4c39-44f7-a75b-5c38ef059193 |  | note | ACCEPTANCE CRITERIA: All surfaces to match the surrounding surface finish by use of steel forms or steel trowels.
label | 48895bf0-ba49-4182-a390-dcf9e66970f8 |  | note | Craze cracking to be limited with no cracks at the interface between the substrate and patch, however, a maximum crack width of no greater than 0.1mm.
label | 3b2b9227-1388-4621-9a84-36c9e2d7f292 |  | note | If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | c9720c40-c26c-47c8-a670-4a7426b82c31 |  | note | ---------------------------------
label | da29ce77-84c8-44eb-90d0-bfc4d77cb7b8 |  | note | METHOD: Measure, Visual
label | f132185c-1f07-4c37-ac30-baf6b0cb0345 |  | note | ---------------------------------
label | 87f6033b-4b82-40d1-90f7-bb15ff916e4a |  | note | FREQUENCY: Each element
label | 9b5ae303-50c1-49d4-898c-1b4eeda83319 |  | note | ---------------------------------
label | 6f34bbbf-925b-4b17-b991-08a3ee3a9e19 |  | note | CATEGORY: IP
label | 174ed91f-e930-4f54-9100-88eae5c7580c |  | note | ---------------------------------
label | 1f560b0c-43ea-4406-bce6-e2c606344bd8 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 12281a97-9455-488f-8d15-ec6cdd128cf9 |  | note | ---------------------------------
label | a6b96c3d-ff9b-4e91-99a7-8291f75af342 |  | note | VERIFYING DOCUMENTS: This ITP
text | 01eb7dc5-24b3-42ec-8f23-24f0c223d4cb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Tolerances
label | b735b7aa-fb64-4375-b284-ac91b4e0d417 |  | note | REFERENCE: 689.11
label | 3673f47a-a45e-4dfb-a6cd-57ad15ca4710 |  | note | ---------------------------------
label | 20233b40-5b51-422f-8e54-feed46f9ba6d |  | note | ACCEPTANCE CRITERIA: Tolerances applicable are:
label | 9e820638-aecb-4476-9d88-08f6b9590608 |  | note | Edges: ±3mm
label | f9d1ddc8-048a-406d-b295-a83a2e8557f0 |  | note | Surfaces: ±3mm
label | eea2eaf2-269f-49ea-82a5-cf11cb2f16ed |  | note | Maximum allowance for irregularities: 3 mm with a 2 m straightedge
label | c78d5efe-d0c5-442c-962c-65da6fadfdca |  | note | Maximum allowance for unevenness: 1 mm with a 300 mm straightedge
label | a55b6d98-e8a0-45b4-8633-1946eba4792a |  | note | ---------------------------------
label | 5fcc097d-e705-4adf-abbc-cc95a69efa58 |  | note | METHOD: Measure, Visual
label | 06bb2a58-99bc-4797-8d2f-0e4d1dee90da |  | note | ---------------------------------
label | 2841fdee-1073-4bba-be24-344d48538283 |  | note | FREQUENCY: Each element
label | 55c8ae9a-0029-4615-a58a-52e98ed516c1 |  | note | ---------------------------------
label | 2393641b-64de-4780-a363-e5fd279bdbfa |  | note | CATEGORY: IP
label | 953d1582-cc25-4514-ba00-ca10c01b406c |  | note | ---------------------------------
label | 112f5bf3-6caa-426c-942b-17c3a88cf2f6 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 05bfdb14-a990-4962-8b45-24208f5c93d0 |  | note | ---------------------------------
label | a22240a0-5ec7-4feb-8dd9-ec6338e99fb1 |  | note | VERIFYING DOCUMENTS: This ITP
text | b0a3988b-0ec2-41d7-b402-0950ddcd758e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Curing
label | 1d17263f-6ad5-40d1-86e6-9a40a747e544 |  | note | REFERENCE: Curing Methodology
label | 02e7af74-bd47-4f35-bb44-79ae08de0926 |  | note | 610.23
label | 0c7d1427-d6dc-4c8f-9800-c53b83adce37 |  | note | Table 610.231
label | 3b792212-7667-44f3-a5a2-8db580861974 |  | note | ---------------------------------
label | 34f7d206-271e-4dd3-912f-3433097e5502 |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | c4e33a93-eb9e-4710-b157-2b96c5ea3fe4 |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | b8cfda32-867f-4483-820b-69e82072ce54 |  | note | ---------------------------------
label | 120a2ffd-89ee-4c89-96a4-0c0b2782898c |  | note | METHOD: Visual
label | 3bdba693-06d3-4db9-a375-c5eb3a03c5c2 |  | note | ---------------------------------
label | d0375e93-851a-4ec4-989a-2df6d2fd380e |  | note | FREQUENCY: Each element
label | 502584f4-9e88-46a2-9af8-5dc2fe1d8d75 |  | note | ---------------------------------
label | 024ebbfb-e88a-4e5f-a074-76c6cf6856b7 |  | note | CATEGORY: IP
label | 661aecf1-c135-4809-92b3-a4b22a73055e |  | note | ---------------------------------
label | a73c3732-4941-450e-ba41-c4c8af32ef6c |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 83f9b9a9-98aa-476c-b118-bb902d94e83a |  | note | ---------------------------------
label | 626ede88-2ef1-45f2-b54e-4113c2c64da9 |  | note | VERIFYING DOCUMENTS: This ITP
text | e869795f-8759-407e-918a-7f3a3ce907f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compressive Strength Test Results
label | 1d80c81a-593c-4532-b82d-46e1292ce86c |  | note | REFERENCE: IFC Drawings
label | 505c3499-f333-499e-a6e8-ae37f9bd24aa |  | note | Product TDS
label | df972ca4-8651-4c31-a5c2-a191314ac553 |  | note | Table 689.061
label | 22097c79-a6bf-430d-a749-fe0394441abc |  | note | ---------------------------------
label | ba657202-a4b0-402f-a2e2-d6836ab62090 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | af3d1d67-b1be-4d3a-b69a-d028ca9ffac4 |  | note | 28 day compressive strength per sample comply with the design strength.
label | bfdc44da-8395-4e2e-9b71-a42bb2553d68 |  | note | Attach: Compressive Strength Test Results
label | 0acd5c03-6c5a-46e8-8103-8e4c75864e32 |  | note | ---------------------------------
label | fd8dea1c-964a-4a60-8244-3bef5c2f73aa |  | note | METHOD: Document Review
label | 3d79aa8e-a18f-46be-8899-638741f3f0dc |  | note | ---------------------------------
label | 09a4dd9d-d5e8-445a-b0ac-e618495a2d03 |  | note | FREQUENCY: Each cube
label | f50ced4d-311b-48ff-b60b-1040c03a3b4b |  | note | ---------------------------------
label | da0a28f6-fafc-4376-aea9-f6e6765e415c |  | note | CATEGORY: IP
label | 285c1bb9-4215-4a85-b205-57246fb18bd4 |  | note | ---------------------------------
label | 5058b43e-4fa2-46c9-b264-06a819d59329 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3ad7d01b-d8c9-45e3-95ad-ed87fe6b2306 |  | note | ---------------------------------
label | 16241405-8a6d-456c-9a62-fadd27512abf |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b39d5e4-7988-4804-aac2-70987cc36081 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | 1fc9d1fd-0f03-4f19-80ad-adab513a1085 |  | note | REFERENCE: MRPA Quality Management Plan
label | 540041cd-0882-465a-b69f-9567185034e4 |  | note | ---------------------------------
label | a5f1acb7-d490-4b81-a9e3-c6ee7e70fddc |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | b60c104b-6178-4b14-b721-5a79de45e5d8 |  | note | ---------------------------------
label | c30178ce-e27d-4037-9126-15536dbcb388 |  | note | METHOD: Document Review
label | cd7db235-5bbc-4066-93d8-38fe0869b29f |  | note | ---------------------------------
label | e26214e5-59ad-42da-a45c-e6858d461054 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | eb190034-591d-417d-91f6-dc87338d8de3 |  | note | ---------------------------------
label | e7ab022c-3358-400b-a571-5bc1afc899f1 |  | note | CATEGORY: HP*
label | 7b247b39-6a6f-4fab-8b0f-8f2426ae20cb |  | note | ---------------------------------
label | cd10105b-4ac7-4026-bcc3-caf5a4a267a7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 04c79f0a-b99f-477b-b254-59b18cf4231c |  | note | ---------------------------------
label | 087dfe87-3295-4d28-9e8f-055eb6ce77c0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1618f0a3-7f71-45bc-b829-5b9316d74d5e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | e77793de-75a6-4239-b274-168ef643440c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 855ee6f2-ff42-48a9-919f-72ca61a34f47 |  | textbox | Name:
text | 2f3836e7-62a0-4759-90f8-724792e2a9e5 |  | textbox | Position:
text | 7328fe71-68af-4767-9dcd-bf18dea22e56 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | itp |  |  |  | Yes | ITP-CIV-Kerb and Channel (Supply and Install) Rev 1 | 75cb2d66-c75a-411d-a60f-6649c4d6ee3b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | bf5a93e6-cadd-4272-b52b-8e7ecc334f33 |  | note | ITP Description: Kerb and Channel (Supply and Install)
label | 98857f7e-6df7-48a3-a044-641ef9c346e7 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 26eec72a-2017-4d78-b820-285a225e54f7 |  | note | Revision Number: 1
label | 38cda143-a2e0-48de-95a5-eba7bb5111a7 |  | note | Revision Date: 28/08/20
label | 75f0b9bb-91eb-4cb0-bd06-668e7cb35af1 |  | note | ITP created by: Saaf EL-ZUBAIDI, Isaac & Velcek
label | 0be47783-5fef-4626-89da-8b1b29c853d6 |  | note | ITP approved for use by: Josie Pavlou
label | 5eded922-9431-41c5-950b-55eae8281b92 |  | note | VicRoads Section 703
label | 4d93d8a7-f34c-4d35-b260-77ed3af47377 |  | note | VR SD2001
label | e10ffc6b-b9fc-4bc4-83cf-bb9708485032 |  | note | VR SD2102
label | 7fe7a274-dab4-4ec1-92eb-3ad7254cbc54 |  | note | AS 2876
label | 32a2ad43-255c-4037-92c4-a22e2c1bd82b |  | note | AS1379
checkpoint-group |  |  | section | Preliminary Works
checkpoint-status |  |  | checkpoint | 2.1 Check for correct documentation
label | 9d638470-95ad-4633-9f67-eb338bfd0f7a |  | note | REFERENCE: Drawing and Drawing Register
label | 120054e9-a8e1-4e18-8ce0-04e6ab4eec65 |  | note | ---------------------------------
label | 8265ba6c-7b47-414f-8682-37bbeea16f54 |  | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are : -Using the correct and complete set of drawings .- All drawings are the latest version
label | 2a7d9217-01b0-432d-a036-1b005111d77b |  | note | ---------------------------------
label | 57ae00d7-0b5c-4314-9de0-06c341913e50 |  | note | METHOD: Visual inspection
label | 510862d9-d1b2-482d-bbd7-5dd875e7869e |  | note | ---------------------------------
label | 80148902-7b6e-4e75-9a1f-3a1641e2f368 |  | note | FREQUENCY: Prior to commencing any activity
label | b542eb42-0041-4ad7-84c3-0f26254dc2c5 |  | note | ---------------------------------
label | a56f5a10-3a38-4e24-9fd2-33cafdde2013 |  | note | CATEGORY: HP*
label | 65a87046-b0bb-4c9a-a573-c2ac37e31187 |  | note | ---------------------------------
label | 7fbe9c32-5987-4c15-aba1-8ad731f1b83b |  | note | RESPONSIBILITY: Site Engineer/Site Foreman
label | b97520a3-22c9-4dfb-8eb2-f4ab8f5ac959 |  | note | ---------------------------------
label | 87902cfe-d9a8-49e4-8a59-8d1e0a9bfeeb |  | note | VERIFYING DOCUMENTS: ITP Signed
text | 70ec4a33-1bd2-4e3e-9375-e32929f05f8c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Mix design
label | 4b10fa2d-d4ae-4fa5-a55d-b0a28b6b1633 |  | note | REFERENCE: SD2001
label | b7150b4d-ed9b-4ab7-9cd9-bdc84dc1d496 |  | note | AS1379
label | 26682514-6d94-4c0b-a3a0-3abf8130c77b |  | note | Section 703.05, 703.06, 703.07
label | 172d2923-dc98-471b-808a-7d7fe2622d34 |  | note | ---------------------------------
label | 0c1dc611-53a9-49ec-9ef4-5269f7d142b4 |  | note | ACCEPTANCE CRITERIA: Approved VR mix design to be used.
label | fd1b708e-b4aa-4837-aae1-7e085716fc13 |  | note | Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | 0258e9ae-587f-46d3-9753-ca7cc9a0c5e2 |  | note | Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
label | 696f5743-c6b1-44ac-84f6-5fc7dd116980 |  | note | ---------------------------------
label | 2ab42684-9adf-49d3-b905-ef6f8d1ce16f |  | note | METHOD: Verify
label | dda0525c-b256-4931-99b0-9522ee75d905 |  | note | ---------------------------------
label | b683c04d-e82e-4f71-b5fd-765e65f8b041 |  | note | FREQUENCY: Prior to commencing any activity
label | 2142595e-2dfe-434f-a985-fa7fd065b984 |  | note | ---------------------------------
label | 53ce5c2e-5069-4386-9b05-299b7fd5688a |  | note | CATEGORY: HP*
label | a02538da-785a-4fb9-978c-f69d5d23b171 |  | note | ---------------------------------
label | 7d855273-a41f-4f98-bef5-58e95dc85ba2 |  | note | RESPONSIBILITY: Site Engineer
label | 2b05bc01-e22d-4173-b681-062766a0594f |  | note | ---------------------------------
label | e7ab4b9c-b091-4a55-9933-338ca166f9bd |  | note | VERIFYING DOCUMENTS: ITP signed/Mix Design Certificate
text | 6ad46e19-e045-48f4-8e18-95487b5c6286 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bedding Material
label | bacb202b-76ff-47bc-9cf6-dfbf6ddfc9c2 |  | note | REFERENCE: Section 703.21
label | b7404390-3d0e-46ec-92ff-941050f0eacf |  | note | IFC Drawings
label | d12b9e8d-c2b7-4700-94e9-e27e08b7529a |  | note | ---------------------------------
label | 30bd4ef1-d344-4156-95fb-74e49a42fe37 |  | note | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
label | 841d288e-bbee-41e4-a0c0-3a7209f6ec91 |  | note | Beaconsfield Car Park: Bedding shall be size 20 mm Class 2 Crushed Rock in accordance with IFC drawing detail
label | 47f4a578-3ac6-43a4-866e-c5cc2f44f8a3 |  | note | ---------------------------------
label | f41f1efd-913b-4db7-9d8f-9678b5475f89 |  | note | METHOD: Verify
label | a652f067-d0c4-4563-9e46-ae34dc001b87 |  | note | ---------------------------------
label | 3400c1b0-e02e-46d5-9e14-2ea2f42785f3 |  | note | FREQUENCY: Prior to commencing any activity
label | 8f40b1b3-dc29-465d-848a-7d220218cea8 |  | note | ---------------------------------
label | 78a5e66e-778e-423d-90dc-5198d9716588 |  | note | CATEGORY: HP*
label | 2234daf8-1672-4b71-b490-f1340cb40e41 |  | note | ---------------------------------
label | c460d00d-8154-4766-9fd7-15b1809c6f10 |  | note | RESPONSIBILITY: Site Engineer
label | 36d965be-f111-4430-9e2d-f01896a14476 |  | note | ---------------------------------
label | 95bad6a8-0bf4-4bbb-b454-a3e45c7675db |  | note | VERIFYING DOCUMENTS: Material Conformance Certificate
text | 6b1ad9f8-3604-4e63-9e52-428c1fca0008 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Curing Compound
label | d6daabaf-2c55-4661-9a5f-62e942876db6 |  | note | REFERENCE: Section 703.10
label | 07feb4b0-aef3-4caa-bb0f-6136cc92f1f1 |  | note | ---------------------------------
label | a2130682-1a51-4e95-a224-4d326e4f78a3 |  | note | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
label | afa1cd49-b001-466b-ae49-aeed50f06933 |  | note | ---------------------------------
label | 15dbfc03-b731-418d-9b09-69c623659549 |  | note | METHOD: Verify
label | f9027386-5d3e-42b4-a994-c516e44e5f75 |  | note | ---------------------------------
label | 626e5472-d136-4751-9daa-c979e1f24762 |  | note | FREQUENCY: Prior to commencing any activity
label | a36fe187-90bf-4784-ad66-f3b1549e02b2 |  | note | ---------------------------------
label | 9b2a9a0a-241d-4c19-829f-ff4b5fb02976 |  | note | CATEGORY: HP*
label | 12545bfe-b5e8-460d-9d40-a585d751622b |  | note | ---------------------------------
label | bb82bef6-3dc2-4047-ad16-bcc725bde5b7 |  | note | RESPONSIBILITY: Site Engineer
label | 6226469f-5e3c-46a1-bfbd-68915bbbbfe1 |  | note | ---------------------------------
label | cfefda3d-50ed-4094-914b-6ef2caf7b5a9 |  | note | VERIFYING DOCUMENTS: Material Conformance Certificate
text | f2d470ec-ab83-4333-afac-6d13820d5ad5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Setting out
label | 67914f92-4a6c-4205-bb22-a6b4e15e3a40 |  | note | REFERENCE: Section 703.17
label | ca916733-2a36-4b59-af96-833b0aa6cc4b |  | note | ---------------------------------
label | 218faa95-0a77-4e3c-b955-148faa2bfedc |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
label | e11c9a45-7959-4007-9ef6-8fc3b45b48b0 |  | note | The superintendent will review and confirm set out.
label | 177b5f88-92c1-47ab-a992-fa9d04ffa1ae |  | note | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | 7b00a84c-727c-4366-a4d9-c11e546ab7a9 |  | note | ---------------------------------
label | 89e04158-93c3-402e-8ad3-0ed95e83c578 |  | note | METHOD: Verify
label | b70e6dc1-355d-42ad-b564-4db20d891bed |  | note | ---------------------------------
label | 713b132d-6c80-4978-aeb4-b0f6c05883ed |  | note | FREQUENCY: Prior to start
label | cbcdf8f2-dc19-4a46-a704-fb23a982bfc6 |  | note | ---------------------------------
label | 445076e0-6bbb-4b01-b272-702ade21dce5 |  | note | CATEGORY: HP
label | 12e00563-7248-40b3-a824-8ac87a4176f3 |  | note | ---------------------------------
label | fef95a2f-bc26-49d1-b025-e91652b90e02 |  | note | RESPONSIBILITY: Site Engineer / Superintendent
label | db41496b-e282-4b44-afa9-6058f9baa9aa |  | note | ---------------------------------
label | 147330fb-8d51-43ad-8c25-ec96be68e2aa |  | note | VERIFYING DOCUMENTS: ITP signed
text | a53e875f-d718-4b28-b60a-2590b67c90b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Temporary drainage provisions
label | 45140ec2-5b81-4d01-83cf-6e1f9d00ca78 |  | note | REFERENCE: Section 703.18
label | 6ea6f12c-832e-4c4f-8acd-cacf7d90bca2 |  | note | ---------------------------------
label | 15af68c2-bfd2-4a92-b304-7764e9065b52 |  | note | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels ,temporary diversion of discharge of drainage and storm water to be in place.
label | dd8216f4-1be6-44d9-a5fd-5bf7bf1d513e |  | note | Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | eaa8ea62-620c-4bc2-9b2c-3fd272faea7e |  | note | ---------------------------------
label | bfe138a1-226b-43ff-aade-a4a530ee1836 |  | note | METHOD: Visual inspection
label | f84113b6-25ef-4dcc-b376-2a72ccc7b787 |  | note | ---------------------------------
label | 4f204bda-3a0f-495d-8502-76f7ecd64822 |  | note | FREQUENCY: If required
label | 7e7775b9-a819-4870-a11a-59ffe9518850 |  | note | ---------------------------------
label | dbd23a75-6eb2-45a9-bdae-19823489ba53 |  | note | CATEGORY: WP
label | ef545baa-223e-44b5-a8da-3b269c265c56 |  | note | ---------------------------------
label | 73146624-4001-4bc8-a8c0-7acbde7edca7 |  | note | RESPONSIBILITY: Site Engineer/Site Foreman
label | 2a70e3c3-7ca5-45f7-aaa0-aec83cc36e4b |  | note | ---------------------------------
label | 55f39d03-b297-439b-b7c7-5acbcc472b8a |  | note | VERIFYING DOCUMENTS: ITP signed
text | e0691150-2187-40ed-a76c-d7190eff6a59 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Bedding
label | 96eb17f3-c0af-4313-bae4-822d5c38b29b |  | note | REFERENCE: Section 703.21
label | bb6b9818-d5c4-4ab8-8f49-3aa9e6fcd188 |  | note | ---------------------------------
label | e292be18-90f8-4c51-8a5d-cd9765f352a7 |  | note | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm .
label | 6d1bd515-1b2b-417c-822c-2385ffae53c3 |  | note | Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
label | 004795c2-d4e0-4e5c-a9cd-784d0a6c1eb1 |  | note | ---------------------------------
label | 62a4e36a-4408-4015-a844-5c3f05eafe70 |  | note | METHOD: Visual inspection
label | b6c91791-31e8-470d-9324-ad016688c10a |  | note | ---------------------------------
label | 31c42783-1bff-4bf4-bc71-a425c4e06e78 |  | note | FREQUENCY: Each lot
label | 49602ade-3234-4912-bb17-71f956c2867a |  | note | ---------------------------------
label | 095ad1c9-b1ca-45e3-aa33-3396c00b429f |  | note | CATEGORY: WP
label | 776063c8-c4a8-4387-8b7a-bc3fcd5ef753 |  | note | ---------------------------------
label | 279a388e-df2d-40d6-91df-ad477ce18844 |  | note | RESPONSIBILITY: Site Engineer/Site engineer
label | 31ba0045-e51b-442f-9508-5fe3fdbe1579 |  | note | ---------------------------------
label | cacaa18d-42b5-4f92-8fc4-17f177fc9464 |  | note | VERIFYING DOCUMENTS: ITP signed
text | a29f16c4-eae3-48d1-b0d9-b7a572f27d02 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Formwork
label | 61a3bdae-0c7c-4811-87ad-a2d210910c1c |  | note | REFERENCE: Section 703.12
label | 27a8da9a-1ccb-4b61-8894-d2928e610033 |  | note | AS3610
label | edc428b5-4a93-4b42-bca9-c66416190b68 |  | note | ---------------------------------
label | 5e49d5d7-ec85-451c-8526-ff7639f53141 |  | note | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 19fc9973-6712-459e-b48c-a864f34b180d |  | note | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | d2582c5f-f238-4ec4-a674-4d60d0970ea0 |  | note | ---------------------------------
label | 10ab4a17-1fa6-4cc3-88ce-5addcfbf3ad8 |  | note | METHOD: Visual inspection
label | 0f72291c-0871-4f79-b6f1-fb8fe14583ab |  | note | ---------------------------------
label | a9e6e9d1-5df5-4004-b114-a581921aac47 |  | note | FREQUENCY: Each lot
label | 85a272b0-4352-42fc-8757-755a9723602b |  | note | ---------------------------------
label | 129d389d-c729-4f3a-ac8a-e4bae88a4a35 |  | note | CATEGORY: WP
label | e1453f53-9a1e-4b97-b11a-ce1a7e0a005e |  | note | ---------------------------------
label | a4d34782-dd35-40b6-aba2-18bd6930f124 |  | note | RESPONSIBILITY: Site Engineer/Site engineer
label | f33a6738-26e2-4153-921b-a155ada92950 |  | note | ---------------------------------
label | 50a870bb-1ea7-49d6-a111-cd2704824848 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 5a0722ed-18d1-44d0-a212-4404007f9455 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Pre Pour Check
label | 3276bb7d-2e5e-43d2-a6ad-50a2bf4a9e7f |  | note | REFERENCE: Section 703.09
label | 411459a5-828c-4e5a-b8b4-e3ee1e27012f |  | note | Section 703.21 Section 610.17a), b) & c)
label | 58c478a0-778c-4d5b-a8e4-52f249c8f683 |  | note | ---------------------------------
label | d14a273b-e08f-4400-a115-8dd28c09bee9 |  | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface .
label | 4a2bcd7f-e93d-4f14-9ae5-bdeb1c55c71a |  | note | Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | 348675b2-f81f-4e62-ab0f-f54de9468107 |  | note | ---------------------------------
label | 9b75065e-37ae-47d2-81d5-8c0cc4e6264a |  | note | METHOD: Verify
label | d2759aac-f015-4ec7-9daa-5b8fca94c590 |  | note | ---------------------------------
label | db26fcc9-ced9-4ab3-8b75-10dc29246be7 |  | note | FREQUENCY: Each lot
label | 53570945-5f8c-474e-9a76-a9867cdc11b4 |  | note | ---------------------------------
label | 464f404b-3003-482f-9fac-4fc7271421f8 |  | note | CATEGORY: HP*/WP
label | 5a0cad26-ce7e-4e07-8c27-6d9c7c8625c1 |  | note | ---------------------------------
label | 0ddcaa6b-cb71-4f6b-bb03-4fd94f5814cc |  | note | RESPONSIBILITY: Site Engineer/Site superintendent
label | 6f6eb98e-5722-4e54-8868-4df8d4d6ff1d |  | note | ---------------------------------
label | 1050dce2-5eb1-4089-9487-c1a989518687 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 6bb37c2a-c78f-4721-8d49-7c3b0dd0b071 |  | textbox | Ambient temperature-----°C
text | 28f05bd7-e021-4f05-b5e1-f2a516c97f29 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Concrete placement
label | 187f34bc-00db-48a1-bd44-7b1f4f30d28b |  | note | REFERENCE: Section 703.08
label | 5f79ab2a-6037-4d3b-b8a6-b925f6e14212 |  | note | Section 703.23
label | 361fd2c4-60ac-4892-b97d-2debe19b5779 |  | note | ---------------------------------
label | 6045751d-c54b-45d2-9b2f-6915cf0a8c95 |  | note | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | 0face41c-787b-4dd0-b843-d2d106bd58a0 |  | note | Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | f3405dff-c1e0-4a34-8f79-dd22a536efed |  | note | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | 55cf84cd-4daf-4fbf-a4ac-5d2fa533a13c |  | note | Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | 354f8337-1e74-42ea-84df-d09195142ecf |  | note | ---------------------------------
label | 0269acf1-c2fc-4ce5-8305-de4eff77411d |  | note | METHOD: Site inspection
label | e64698cf-f9e6-4511-922d-fa054dd0dcda |  | note | ---------------------------------
label | c368cc84-2b7b-4111-a3dd-fc9995c6b033 |  | note | FREQUENCY: Each lot
label | 3bcf9795-f310-46fc-b756-b27c8ac48f54 |  | note | ---------------------------------
label | 64900613-c52f-4b07-ae0d-4e6a0ee5597e |  | note | CATEGORY: IP
label | c8c331e5-a9df-46ab-ab57-ffe9b1fd4a20 |  | note | ---------------------------------
label | d92a7b50-2803-4be4-8d3e-948745dcdcdf |  | note | RESPONSIBILITY: Site engineer
label | 25386be5-0f63-49e9-aa0a-d97bd3462d22 |  | note | ---------------------------------
label | 87abe954-24f4-4482-8fa4-e29fcde1c30f |  | note | VERIFYING DOCUMENTS: ITP signed
text | 506a0020-cf71-4410-8c77-16cdf20d1bb6 |  | textbox | Concrete Temperature ---°C
text | 33aa5360-08d1-43fc-8034-9fd668e8f06e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Transitions
label | 294a5edb-f356-436e-a598-1b836c357d29 |  | note | REFERENCE: Section 703.24
label | 48f6bf51-9a0a-4f53-af4d-142aa2ac96e4 |  | note | ---------------------------------
label | 77131749-36a8-4db1-8a4d-92365fd94349 |  | note | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 25344015-e174-4c0b-9bf2-ae5081488163 |  | note | ---------------------------------
label | 36c82d9a-17c0-4e4b-b42b-3efde50f8dcd |  | note | METHOD: Site inspection
label | 8ba9027f-3258-48ed-b5d4-890e39454487 |  | note | ---------------------------------
label | bb93c69c-6852-4293-9855-ba0f7425c63d |  | note | FREQUENCY: Each lot
label | 76953d2c-59fd-4ca3-a264-ea07701c67fc |  | note | ---------------------------------
label | 501ee5bb-3912-4a18-a06d-efa2a03e7afb |  | note | CATEGORY: IP
label | 955dce00-0da0-4c50-a381-1702e2e5e35f |  | note | ---------------------------------
label | 90a1eb27-3914-46a2-bf82-e9ceb2f3ec1f |  | note | RESPONSIBILITY: Site engineer
label | 27c80209-ce39-4b6e-a40a-5d3464a197d1 |  | note | ---------------------------------
label | ac4851f7-b045-4863-8f48-4c0e2ccdb221 |  | note | VERIFYING DOCUMENTS: ITP Signed
text | a33f93f4-c93c-4c66-a3e3-fbd3fd17f0b6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Surface Finish
label | acf13f34-56bf-4001-9935-e5c08539f0c6 |  | note | REFERENCE: Section 703.25
label | 836fa0d5-2707-4c77-9586-2e282250fa53 |  | note | ---------------------------------
label | 35cfc003-d310-4065-a400-c1cad9d1a70b |  | note | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | 76421c20-fa80-4c93-a205-a6d9e142d151 |  | note | Renderings shall be applied within 30 minutes of extrusion.
label | 55f72db4-694e-449b-8ce4-0731099bc918 |  | note | Concrete to have a neat appearance and uniform colour.
label | 09b824a5-7a5d-4809-bce1-56d1461a0488 |  | note | Class 3 finish required for external surfaces.
label | 4e212f96-0ba4-4d23-9580-cd504638d968 |  | note | Class 4 finish required for permanently hidden surfaces.
label | f6cbde3b-8e4f-4b18-a7e3-de8099ed8399 |  | note | ---------------------------------
label | dfa87634-e515-4bf7-887a-b4e7696a5d33 |  | note | METHOD: Visual inspection
label | 3d43df9b-ba68-4271-8fae-28bc6e09480b |  | note | ---------------------------------
label | 3fc50a29-b7aa-4f59-84a6-1eb6ee0b9be5 |  | note | FREQUENCY: Each lot
label | 635b6187-7124-4fdb-909a-ded4fb35fc43 |  | note | ---------------------------------
label | 0eaa9343-2b61-469a-999a-dbb44c0c8d71 |  | note | CATEGORY: IP
label | dc52cb76-134c-4275-b875-7a4df3c32ae5 |  | note | ---------------------------------
label | 499d8844-9b43-4139-aec3-cbb59b86d77e |  | note | RESPONSIBILITY: Site Engineer/ Site Forman
label | e66ba90d-0edb-4829-ae2b-2325912b6a0f |  | note | ---------------------------------
label | ce2881b9-5e9c-456f-9afc-d654584533e5 |  | note | VERIFYING DOCUMENTS: ITP signed
text | f8e3e4b0-f7e9-43a6-a358-dca18161a102 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Formwork Stripping
label | 3bc7012f-4e09-4a52-8455-a757b7a22ff9 |  | note | REFERENCE: Section 703.12
label | 2468ce29-d94f-4f59-9b87-9eb014b731cf |  | note | AS3610
label | 7a616254-3fcb-4206-8e7f-d2c73bdfef77 |  | note | ---------------------------------
label | 60811f2b-c1d9-4038-be13-c27513fa50db |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
label | a793f4dd-1e6a-4b42-bf64-1602eaa77a62 |  | note | - External faces 2 days
label | 09069ece-baa0-42b0-b483-9456834be347 |  | note | - Permanently hidden faces 1 day
label | 8aff8926-3380-4308-8e8f-e9de16ff3aea |  | note | ---------------------------------
label | f1e43a4c-da68-4f6e-9791-702ba766cb96 |  | note | METHOD: Visual inspection
label | 8f4389a5-0f81-4136-9e6e-9c9ba34f98b6 |  | note | ---------------------------------
label | ba48537c-9b50-4632-b2a7-e1f08d9ea3a0 |  | note | FREQUENCY: Each lot
label | 895f9592-cb09-4f7f-af9d-fc9af4ef7fc2 |  | note | ---------------------------------
label | 77137f80-7d56-4e01-b9e2-eec523aa2181 |  | note | CATEGORY: IP
label | 8320b9db-e799-48e7-9714-b64bd8eb926d |  | note | ---------------------------------
label | 71760cb0-22cd-4f1c-b59f-2c0cb62a5dd4 |  | note | RESPONSIBILITY: Site Engineer/ Site Forman
label | 915a71d7-6467-4455-9228-ca1b2147ec12 |  | note | ---------------------------------
label | 617eb238-f048-4bd8-8eb8-c4685054615f |  | note | VERIFYING DOCUMENTS: ITP signed
text | 676197db-020c-499d-a4cd-f104d52f88ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Tolerance
label | 10483a69-30d7-474d-aedf-0432730abe64 |  | note | REFERENCE: Section 703.15
label | ec3cd9b7-fe6a-4ba3-bbda-cd3b6381603c |  | note | ---------------------------------
label | a6c94436-f221-46d3-b92b-40e139f72801 |  | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
label | aed74b95-eb49-4883-9819-0c92b35b4ed2 |  | note | Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | 58014450-c905-4f3e-9297-3731e2f27f86 |  | note | Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | 71cb8f20-7950-4287-992a-e0f73c85e2c8 |  | note | ---------------------------------
label | 58444205-d56b-4b0c-9d78-ce758108cbe0 |  | note | METHOD: Verify
label | 6a0695bd-5a68-44fc-810a-4d2573847cb6 |  | note | ---------------------------------
label | fc4d14a3-6c4d-469a-bd85-6fd9549779cb |  | note | FREQUENCY: Each lot
label | 0f76ff60-8c24-4ed2-bcf0-8bcc2efc78f7 |  | note | ---------------------------------
label | 2989cbc7-5d97-4cda-b6cb-b469a33ca57c |  | note | CATEGORY: IP
label | 236f0f36-1d95-4438-a5ca-1f27ce9893dc |  | note | ---------------------------------
label | 1ba453f9-33fd-414a-889d-122b246c550b |  | note | RESPONSIBILITY: SITE Engineer/surveyor
label | 6a3afb3a-822a-47e9-a374-f17f8dddc6d5 |  | note | ---------------------------------
label | db7feb10-d0a5-4eff-baf4-fff4d46c519c |  | note | VERIFYING DOCUMENTS: ITP signed
text | fe653558-af92-4cf0-a096-4321e0657fe3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Curing
label | 33fa5db4-d641-4fa7-9c97-517dbead20ab |  | note | REFERENCE: Section 703.10
label | 401843bf-904d-41bf-909a-81d49fa75889 |  | note | ---------------------------------
label | 9f9d0c30-44b9-4d0c-a545-1765e9b8240f |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | e3d3eabc-ab2b-4abe-827d-30e15be2342c |  | note | Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | 7d13dd18-cbf9-4f01-bbbd-a0f367b98fc0 |  | note | ---------------------------------
label | 24629265-f682-4ebd-844d-d50a479820c1 |  | note | METHOD: Visual inspection
label | 5ea9c3f1-8b1f-4492-b8dc-0bc0cb42d93c |  | note | ---------------------------------
label | f52807f6-6525-4e6a-8a40-8d4c69bd00a2 |  | note | FREQUENCY: Each lot
label | 6878a34d-20cf-4701-a7e5-3f262767afa5 |  | note | ---------------------------------
label | 65fa024e-1a7b-4ea5-b7ef-a5b73fcf43cd |  | note | CATEGORY: IP
label | edde0d1e-ba70-4fac-8acf-dbf3d46f6400 |  | note | ---------------------------------
label | 4ea4dd0a-a70e-413d-a0d5-f851cd541975 |  | note | RESPONSIBILITY: Site Engineer/Site Foreman
label | 920c7206-598f-44e3-9464-ec6874e2bf98 |  | note | ---------------------------------
label | 6ac6d633-d83c-4bde-8b53-2be4be522707 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 9a3c33db-6500-4ff5-8bf5-c67755b6b750 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Joints
label | f1a88e2e-5d90-4ede-b241-e8105b598091 |  | note | REFERENCE: Section 703.26
label | 5c203828-df31-4ea5-a02e-112f623b1af7 |  | note | ---------------------------------
label | 6ff53700-f464-4068-a8a3-7e64f579e985 |  | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | 52d8c776-59f3-4ba8-a9e6-c950447e1282 |  | note | Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | 60e27595-0306-4de2-bef8-2d0c2736e81c |  | note | Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | 10ea7cf2-0917-4aa4-974c-475541175b76 |  | note | ---------------------------------
label | a3ef9c82-3bec-4b9e-9acb-b7e54ae0a90d |  | note | METHOD: Verify
label | bbb7a8c0-c9be-4f02-a461-39c047ecfec7 |  | note | ---------------------------------
label | def98fa5-d2e0-4a7d-8b9a-010489b80966 |  | note | FREQUENCY: Each joint
label | a677dedb-ff96-4824-ab37-0bf8466110c9 |  | note | ---------------------------------
label | b039298f-00c0-4dbf-bebb-b9488408a8b6 |  | note | CATEGORY: IP
label | 4d7bebba-13db-48d1-b3ab-3b9fe53bd9a4 |  | note | ---------------------------------
label | 9de09ccb-aa32-47ef-9261-896a60d8b660 |  | note | RESPONSIBILITY: Site Engineer / Site Forman
label | 56dd2893-9e57-4c18-9492-1d8b6cad0992 |  | note | ---------------------------------
label | 2954cdc0-d056-4987-94f8-ae708965cc52 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 60dd5eaf-046a-4e6e-aaa8-8a755d9b7066 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Backfilling
label | bff9b761-f3bb-4378-abd0-3a4e2d7cbe55 |  | note | REFERENCE: Vic Road spec 703.29
label | 9025a465-5066-4fbe-9a21-e50158f6d30b |  | note | ---------------------------------
label | c1e16a0d-6f58-4bcc-9402-e8b18afb4202 |  | note | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | 41f5f817-1a8a-41c7-ad15-bf6547d163a6 |  | note | ---------------------------------
label | d839831b-2ed7-4574-8e7b-0341fe1bf826 |  | note | METHOD: Verify
label | ae43d840-e2aa-4923-b9cb-5b0ad9e23192 |  | note | ---------------------------------
label | af369e95-23a6-4ceb-b972-71e846c113c7 |  | note | FREQUENCY: Each lot
label | aedb7fed-1cf7-48a9-9ff8-cfc5e2a90d7f |  | note | ---------------------------------
label | 6e35fa3f-3957-42c9-b89e-a50d0a95ca67 |  | note | CATEGORY: IP
label | 2b426fd5-adb1-4356-a491-54e861ab8e5f |  | note | ---------------------------------
label | fa7af1cf-3542-49f5-a85c-3f0954666cb9 |  | note | RESPONSIBILITY: Site Engineer
label | c0fe6f53-37b2-4814-bef2-7762c5080cf4 |  | note | ---------------------------------
label | 105ed75f-8d79-49e5-aaf0-561d62b2f207 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 783d9cbe-5314-4396-a93d-6bb0235d6802 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Protection of Concrete
label | bae73c58-f6b1-449e-8bdc-f7450e015b87 |  | note | REFERENCE: Section 703.27
label | 160b1b33-6230-4a9f-ba2d-1290d6a6fc88 |  | note | ---------------------------------
label | b0b9d7e8-b423-462a-9cd6-65cf2cd9610b |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
label | fb1ac42c-4b0a-40c7-bd29-81d26659acc1 |  | note | ---------------------------------
label | 15e8fb83-24de-400e-8d9c-6e01b68dee72 |  | note | METHOD: Visual inspection
label | 4d141166-37b5-4125-aeac-2dccf5b7b434 |  | note | ---------------------------------
label | b19305ae-f078-4df4-aa7b-826e01838e3e |  | note | FREQUENCY: Each lot
label | 6fc2582f-ce4a-4be9-a828-ac8f79fd2c38 |  | note | ---------------------------------
label | 13f08bec-25de-42b2-8f63-4a2d2f7b865c |  | note | CATEGORY: IP
label | 71dfbbc1-555c-4857-8cbc-80430ffee44a |  | note | ---------------------------------
label | 50ad4193-bbd2-4336-bd90-94bd25a018b8 |  | note | RESPONSIBILITY: Site Engineer
label | 8270f74e-ca01-460b-94bb-ac2bd8365cf4 |  | note | ---------------------------------
label | 0cfa6882-228e-40ca-8123-64fedd272b29 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 4c9db5d5-e7bf-4813-8c1e-811daf959bb6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Cracking of Concrete
label | 0db6b613-150a-4647-8ee0-0aefb50dd232 |  | note | REFERENCE: Section 703.30
label | 369af505-99fb-48e9-986d-93697cdca5db |  | note | ---------------------------------
label | 6a525384-0456-438f-929f-5956a991bc1f |  | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | a43c61c5-fc63-49a0-82ea-3bb497cbf98b |  | note | Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | d99aed9e-777c-442a-8763-31d1acff6d05 |  | note | ---------------------------------
label | 5f8b0e06-4d2b-419b-b035-3f2f1e5595b1 |  | note | METHOD: Visual inspection
label | ee12ba93-e7e4-4279-b4d5-11a579e12c3b |  | note | ---------------------------------
label | 8c533cc3-7be5-4111-bfb1-263595a9afec |  | note | FREQUENCY: Each lot
label | ff1bd543-f86c-4d05-b503-60529a29dec5 |  | note | ---------------------------------
label | 992c06c8-4486-4704-8c0e-f0bdee254533 |  | note | CATEGORY: IP
label | 45ad04da-c556-4b68-a09a-0f9b43d7fdb4 |  | note | ---------------------------------
label | a78d7597-6ae1-4efc-b25b-82f8921c7a27 |  | note | RESPONSIBILITY: Site Engineer
label | 90b10943-e121-40c5-8d6f-9c1e64b4cd89 |  | note | ---------------------------------
label | 6b26369c-91b4-4b17-828c-3df40633b449 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 0059a5a9-0dd0-4a8e-b7c6-94634935b22d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Survey Conformance
label | 12800a65-90d3-4ee3-a0f5-aa228b7ea7cd |  | note | REFERENCE: Section 703.15
label | 8ad736ba-24d6-4446-8238-77fc944ab478 |  | note | ---------------------------------
label | ea367f90-df4e-44e0-ba44-f8d4c549ddba |  | note | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
label | 1d736a1c-013f-4c7b-b213-2cf660ca6866 |  | note | ---------------------------------
label | 9658a37e-c4d2-4f33-91f5-0187bd710f96 |  | note | METHOD: Document Review
label | e8b6bdbf-32ea-4620-b41a-4cea5725077b |  | note | ---------------------------------
label | e0fd0375-c815-41cd-934a-812cf3af3b0f |  | note | FREQUENCY: Completion of each lot
label | aa2d3a6a-8838-46b0-a1e3-e5bb8e6f543a |  | note | ---------------------------------
label | f1134825-cb51-46c0-9af1-28b56238cd45 |  | note | CATEGORY: WP
label | 5d5eac72-a6f4-4819-9dcc-2195afce0e53 |  | note | ---------------------------------
label | a55953ba-fad3-44f5-97f3-18124f317384 |  | note | RESPONSIBILITY: Project Engineer/ Surveyor
label | 2d7b1986-ba6b-40d6-a172-850d178a85ae |  | note | ---------------------------------
label | c605936b-d00c-4796-a79e-573f935482ba |  | note | VERIFYING DOCUMENTS: As-built survey records
text | cbb8c697-e319-47bd-a57d-dbcd653a0813 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | 0c030b74-1a80-46aa-85ef-5c5d924cdbb9 |  | note | REFERENCE: MRPA Quality Management Plan
label | 21e182c8-a67a-4811-bdb9-eb96e5a64de6 |  | note | ---------------------------------
label | 0a17ed1a-39e3-4363-b869-fe32ce4cf22e |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 46cdfdb9-9e78-421b-9e4e-b90107e51c8b |  | note | ---------------------------------
label | a74a380e-306c-4a80-bad5-dae1d0223711 |  | note | METHOD: Document Review
label | 85c2ce3e-c732-4cfa-b5fd-3f55d69269b0 |  | note | ---------------------------------
label | 8e710f23-e004-40d0-80dd-cbb0e3fd09a8 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 3d4a247b-f9ea-40f0-a469-077fa1cfdd5e |  | note | ---------------------------------
label | 63d79b1d-7be0-4d18-b67b-cd4007ea9207 |  | note | CATEGORY: HP*
label | 91bdf50d-0d1d-4505-a04f-46d533808b37 |  | note | ---------------------------------
label | 711f6d9e-289e-4d03-9ca6-86a310479dd5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7591efc4-24d1-4bdf-8880-afb47cc3eb3a |  | note | ---------------------------------
label | eb04787b-20fe-4190-9846-27944976f77e |  | note | VERIFYING DOCUMENTS: This ITP
text | b98a3d32-8bc2-4d54-a4bd-4cc8e9461ceb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 4ea403e6-91e1-459a-95a0-2f25350a849e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 73ea5f9a-1dba-4c87-82db-25032fef3c8c |  | textbox | Name:
text | 36d9e745-022d-4e6e-ae7f-e9daeec0e66b |  | textbox | Position:
text | be0bb1c5-ece1-456a-8c39-844d6b1ef5b3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Subgrade Preparation - Road Rev 1 | itp |  |  |  | Yes | ITP-CIV Subgrade Preparation - Roads (Supply and Installation) Rev 0 | 7c30e17e-848f-4a40-aced-1527c6640cc9
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 5a443e98-eeee-4e3f-9be8-3242c4451ae8 |  | note | Document Title: ITP-CIV-Subgrade Preparation - Road
label | ef7cdc88-044e-4f15-96b0-6bb2c534b173 |  | note | ITP Description: Subgrade Preparation - Road
label | ed6f1a7b-863f-41a3-a861-6559bb95fc6b |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | c527188d-f1b4-4431-9590-aff945cd8b5d |  | note | Revision Number: 0
label | ff9e77a9-15a3-4050-a182-21801058b527 |  | note | Revision Date: 9/07/2020
label | e5e29786-0745-40ec-b851-cc328468bc4b |  | note | ITP created by: Patrick Cusenza
label | adecd949-c24d-4441-8476-8d14caaa0ff9 |  | note | ITP approved for use by: Josie Pavlou
label | 375e5772-2e64-4d39-bc45-44ea22cc7850 |  | note | 1.1 VicRoads Section 204
label | e0be1925-85ba-4369-a271-179c397d4eb8 |  | note | 1.2 VicRoads Section 173
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 2.1 Survey Set-Out
label | 69460805-18b0-48c7-875b-ef06f4c8b751 |  | note | REFERENCE: IFC Drawings
label | e5c15f27-4fdb-4c3b-b62d-629c240979ab |  | note | ---------------------------------
label | 283979a3-8e1b-4b4f-8af0-6307995841e6 |  | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | b98d8d6d-36da-4d43-96b2-487b3adc9da6 |  | note | ---------------------------------
label | f520c2c1-c375-46cb-a77a-f0195f2cec24 |  | note | METHOD: Verify
label | 89a3b763-ef55-451c-b72a-d8991844215d |  | note | ---------------------------------
label | 34c1686a-adb5-4a70-a99c-632c7a5f3ff3 |  | note | FREQUENCY: Prior to commencement of excavation
label | 342cb149-cfde-435f-aebe-3b67c118fa54 |  | note | ---------------------------------
label | 3344bd5a-ffa3-4026-8c55-9772b906c1c5 |  | note | CATEGORY: IP
label | 10f2cf4f-446a-4b06-8a1a-583614f08a69 |  | note | ---------------------------------
label | 33465e18-6e34-43a7-8f77-70e22db39ac7 |  | note | RESPONSIBILITY: SE/Surveyor
label | 1bc2a237-a0e4-49ad-9029-0eeaf89dd82f |  | note | ---------------------------------
label | dc246345-7478-463d-b738-83b12a3bf859 |  | note | VERIFYING DOCUMENTS: This ITP
text | 45a61604-166d-4c3c-9e67-c2ce925c8378 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Subgrade Material Properties
label | bcd90432-723a-42ce-af61-e7343f1479cd |  | note | REFERENCE: Section 204.06 e)
label | adfd80bb-f421-49df-8e56-c6a6c7e32076 |  | note | ---------------------------------
label | a2b71dfe-e888-464e-9f62-263eaa9ff740 |  | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type A.
label | 626fcf02-c817-438e-996d-c78562befc07 |  | note | Assigned CBR ≥ 2.5% and Swell ≤ 1.5%
label | 834023a0-78f4-4670-b61c-221e8a80d6ec |  | note | Max Permeability = 5X10-9 m/s
label | f053b6f7-5a76-41bd-8ef6-adc5c34386c2 |  | note | Grading: 75.0mm 100%
label | 17dd8858-5719-4ed1-bc3c-6c960588ba8b |  | note | 4.75mm 40-80%
label | a30216c6-b475-4533-a289-4b0f3c54c3be |  | note | 0.075mm 10-40%
label | ba56de3f-685e-475a-9ad0-3bcf6078d3ea |  | note | If parameters are met, rip and re compact to a depth of 150mm.
label | ea6a0dfe-13fa-469a-a4a6-790cedfbd6f3 |  | note | If parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | 5ad1f5a2-160e-4bd8-ba20-4e781d577bb8 |  | note | ---------------------------------
label | ee608293-4242-4765-b68e-ec29ce7162d7 |  | note | METHOD: Test Point
label | 2e0d590b-6f7f-4f36-9056-f557db09ffef |  | note | ---------------------------------
label | b7b5d2dd-eafb-46f0-8a0e-af93848af30d |  | note | FREQUENCY: Each lot
label | 3a28323b-08cc-486a-b095-d8c2606e8799 |  | note | ---------------------------------
label | a3d54a3e-005e-4807-ad63-12566bfebe11 |  | note | CATEGORY: TP
label | dbeeaac9-cb35-43b6-a138-113904c414e6 |  | note | ---------------------------------
label | 16356778-fe78-4f24-8eaf-17dfb34bb604 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6bf14e96-8fa1-4dc7-9225-f65a7e0e34de |  | note | ---------------------------------
label | b4934a76-bacf-498b-8d96-f02d8303637c |  | note | VERIFYING DOCUMENTS: Sign ITP Test Report
text | ac698a2d-c8b1-485d-8ccb-8b52677b7ea3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Inspection of Subgrade Material
label | 291d48b8-6054-4a33-bd1a-4324f05750b3 |  | note | REFERENCE: Section 204.06 c)
label | 53a27b73-ab45-43ee-9072-8dbe8950a8a5 |  | note | ---------------------------------
label | 63e6c8f4-6daa-4665-b793-1e96eb39d7d5 |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | 610f2fd7-bd5c-4bbc-a060-e49c4855e396 |  | note | ---------------------------------
label | 1d4effe7-7990-40e4-98c9-b032ada30615 |  | note | METHOD: Verify
label | 0bec1380-6c6d-4f0e-87cc-52640c56ce93 |  | note | ---------------------------------
label | af271780-5353-47d4-afa9-361ed9e8e520 |  | note | FREQUENCY: Each lot
label | 26aa37d6-2328-4041-a70b-71f2bbc0a9b7 |  | note | ---------------------------------
label | 38130d39-7b63-4ee3-825a-8107f41199c8 |  | note | CATEGORY: HP
label | 972f91f8-2866-48e1-9a60-e511509c4f02 |  | note | ---------------------------------
label | 34e5bd21-a79b-46c6-937e-3b565d99906a |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 81bd533f-c162-4713-8bd6-d1e6d9c166a8 |  | note | ---------------------------------
label | bde83b8c-a0b4-467a-a4ef-c1192acbb1af |  | note | VERIFYING DOCUMENTS: This ITP
text | 3def7115-a4c6-49f1-a0ec-3043ce50e5f1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Material classified as silt
label | a6611c4c-379d-4200-9c5d-23d457a5d24c |  | note | REFERENCE: Section 204.04 b)
label | 3993c8a7-bbb4-4287-bcec-81325c836001 |  | note | ---------------------------------
label | 5e5cf9d3-bf21-4174-8764-b90c426c6576 |  | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | cf7753a3-57f2-44ca-af3e-cb6f92bfcabb |  | note | ---------------------------------
label | 1473c44b-a3ff-421f-ae3a-23412c4e658e |  | note | METHOD: Document Review
label | 1d28e892-fc0a-4cc6-bb7e-05c50aa999e5 |  | note | ---------------------------------
label | 44eadefd-d2bd-4615-81b3-775532fa9839 |  | note | FREQUENCY: Prior to commencing
label | 7e42bdd6-822d-444e-963b-04b9b3a5540e |  | note | ---------------------------------
label | 5116353e-0600-4aa9-97f9-36e4352e80ce |  | note | CATEGORY: HP
label | c0266da6-2ea0-4606-8821-b933bda95498 |  | note | ---------------------------------
label | 938cfefc-bf5d-48d8-a38b-c7274ba275c9 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | ed0e401f-61cd-47aa-9628-169ca73f3fdb |  | note | ---------------------------------
label | 3eb664a6-a73c-4684-b424-0a1b373af428 |  | note | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation Signed ITP/ records
text | 3f6fcda7-3a25-4bc6-bca4-76216c0b4dd2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Acceptance of Rock Subgrade (where applicable)
label | a062582b-3033-4826-9d1b-02c8ce8bcc1c |  | note | REFERENCE: Section 204.06 f)
label | 9fb599da-2ec4-4deb-80fb-1bc0fa7f619c |  | note | ---------------------------------
label | e1aeb5a4-5e6b-4ce9-a657-aaf81f2409a9 |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | d3faf053-f137-4b0d-8096-796ed7afde0b |  | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | d6d6bfe1-eff3-4393-bf96-3900fda127b8 |  | note | ---------------------------------
label | 9624800c-64df-40c2-b756-45c102b7e39d |  | note | METHOD: Site Inspection/ Document Review
label | 4f04177c-3546-4113-949a-0fd2be36a832 |  | note | ---------------------------------
label | 304a377c-7c31-47db-9faf-25c5cb352688 |  | note | FREQUENCY: Prior construction of the regulating layer
label | ffd61933-6693-4608-93fd-ab0806a0d2bc |  | note | ---------------------------------
label | e8cc5abe-c86a-4987-b39c-f62c64c38132 |  | note | CATEGORY: HP
label | 639a1e7a-aa92-4118-97ff-ad79a3b1f557 |  | note | ---------------------------------
label | 253c0961-d50e-451e-903b-9de20fc38c85 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | ca8af37c-5c84-47e6-a583-ce026bbe3852 |  | note | ---------------------------------
label | 38fb5826-3e1f-43cd-a0ed-5cc994bfd3ba |  | note | VERIFYING DOCUMENTS: This ITP
text | d5ce517a-c4f6-40ad-ab8f-0aeb12380183 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Unsuitable Material
label | 278acc45-ae0f-4e14-a007-90833560091b |  | note | REFERENCE: Section 204.07 d)
label | 616ee7cb-e43c-494b-b5e8-736ec9185476 |  | note | ---------------------------------
label | 01fea66d-0b38-4481-b799-3ecd20a646a9 |  | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | 09178dc3-0761-4977-b968-1a1be2850d4a |  | note | ---------------------------------
label | d55aca79-5d9d-4aa8-9732-99a1857f2edd |  | note | METHOD: Visual inspection
label | 2e577878-4d4b-4dfe-84b0-b5d2d999f1b1 |  | note | ---------------------------------
label | 6551e173-04bf-4fb7-8859-77278ffab405 |  | note | FREQUENCY: Each lot
label | 331b861d-5884-4391-b0c9-0438e71b2892 |  | note | ---------------------------------
label | 7560aad4-106f-4ca2-a4ea-bdd860af33f2 |  | note | CATEGORY: HP
label | 37f5251c-e5e3-46da-ac84-dc38bd0af98e |  | note | ---------------------------------
label | af3d26ca-fbba-416b-b8e4-4adff3c125bb |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 3fdeab15-1ee4-48bc-bc60-238bc6fee621 |  | note | ---------------------------------
label | 9f5012ec-9c93-47df-b8d0-17e0f0b71fef |  | note | VERIFYING DOCUMENTS: This ITP
text | d7c1b28c-c032-491e-8719-b5c699a5b510 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Unsuitable Material
label | ba4f7574-ce92-473f-bab3-061b15471624 |  | note | REFERENCE: Section 204.06 h)
label | a409acce-763b-4fc2-beeb-d4f27a55fa1f |  | note | ---------------------------------
label | 53aea90f-3593-4828-8c38-75214f92a9cf |  | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | b6d1dd48-fe3d-42d2-8475-12efb54cc9ca |  | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | 5f5ccf1c-f4a0-4572-90be-5eabfe5d7543 |  | note | ---------------------------------
label | 5430b623-eeba-42ed-b31f-a9d980339f0d |  | note | METHOD: Visual inspection
label | 864b1a01-4e90-4547-8474-ed6e4f226334 |  | note | ---------------------------------
label | 1802fc0a-1356-41d0-840a-6b6450523400 |  | note | FREQUENCY: Each lot
label | 7f0075df-40ee-426f-9841-725a344c60f5 |  | note | ---------------------------------
label | 648f1dcb-ad60-4385-aacd-f8c164137f25 |  | note | CATEGORY: HP
label | 683940e6-ad52-4b09-bef7-6a0dcb41cfa1 |  | note | ---------------------------------
label | 061c11ba-3036-4b60-9eca-bda4d16c9460 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 1744fc40-dbb3-42a0-8df5-ba079cf80a93 |  | note | ---------------------------------
label | 06fd8faa-b156-4c36-a8e7-ee4216374122 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2a23f214-6248-4993-aafb-a605db4ad0d8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Cut to Fill Zones
label | 24eab164-ef0d-4b2e-8944-305656cdeb9f |  | note | REFERENCE: Section 204.06 g)
label | b71aa3b3-aec8-4ced-ae0e-ad4fc98af7b2 |  | note | ---------------------------------
label | 8ad66217-d0de-449b-a65f-d50073a77585 |  | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | 250f548f-e929-44e4-af09-9a0b9c0ac50c |  | note | ---------------------------------
label | 76da708f-83fa-4a86-9608-da483b5da76d |  | note | METHOD: Site Inspection
label | 43fa03c0-dc10-481d-983e-d9f60106fa24 |  | note | ---------------------------------
label | b2a8bf95-dca5-4f6e-91f9-729decc434c0 |  | note | FREQUENCY: Each lot
label | cea74848-50f9-400a-b30e-4fc9ec5f69d9 |  | note | ---------------------------------
label | 958eb4f9-c3a7-4e10-8fb3-48f7d829b9b2 |  | note | CATEGORY: IP
label | e8bbcdc2-bceb-4a97-b997-d0e7b4d432c4 |  | note | ---------------------------------
label | 0ecc8e99-1e90-435a-8850-93d974c929ce |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c3a8c8f0-56fa-4104-8670-dacdc4180599 |  | note | ---------------------------------
label | a5e72e2f-3155-40f7-aeb8-966f62b0ae08 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 1dce2182-7b09-49d1-86e1-74ce8cc1dcd5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Proof Roll
label | 55fd725e-9b7b-4814-813e-e7063fa1cf2e |  | note | REFERENCE: Section 173
label | c9e60443-3c84-42c0-9b12-284863dd9352 |  | note | ---------------------------------
label | 01190730-3cec-4cad-aff9-d3f466b507b5 |  | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | 1cd36d6e-01c0-4023-bd02-25dde7d89076 |  | note | ---------------------------------
label | 6669e4aa-45ca-4a92-b2e7-828c6b92d8da |  | note | METHOD: Visual inspection
label | 46d1f2a0-7620-4435-9406-c684d85fd9c9 |  | note | ---------------------------------
label | 3edd1b48-c97a-40a3-b6ff-af761a3dfcf9 |  | note | FREQUENCY: Each lot
label | a67553bd-c570-4d14-8866-549554f888a3 |  | note | ---------------------------------
label | 98a20f46-71de-4a1b-b35a-808ff0e14291 |  | note | CATEGORY: HP
label | d84f2b24-d1c1-4372-a376-64e1033539d1 |  | note | ---------------------------------
label | 75af242b-90f7-41c2-80e5-98bf8012dc83 |  | note | RESPONSIBILITY: Site Engineer/Superintendent
label | a917a391-66f1-439a-a42c-3ed0c12684ad |  | note | ---------------------------------
label | 680beda6-8229-45bf-b5cd-06ea6a0edf29 |  | note | VERIFYING DOCUMENTS: This ITP
text | e755ef51-0848-4efc-aab9-64b8df101670 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 Compaction Testing
label | 94a46269-e81e-4b04-9875-fbfe4b36a0bf |  | note | REFERENCE: Table 204.131
label | c6f57f0f-5bd1-4c79-ae0b-71b5146afd60 |  | note | ---------------------------------
label | f1fec17c-9b40-4f54-8181-42c29028743d |  | note | ACCEPTANCE CRITERIA: Type A Material placed within 400 mm of top of Type A Material
label | 8d2f95ab-fdaa-4a1c-90db-be5f8c10c16e |  | note | Scale A: Characteristic Density Ratio 99%.
label | 395f56ab-9064-41dd-9189-49d4d199e629 |  | note | Scale B: Characteristic Density Ratio 98%.
label | 9c100142-1fd1-4c99-8296-34e6fae72f4c |  | note | Ripped and re-compacted material below Cut Floor Level
label | cf9fb9d9-5892-466d-a76c-6bc44b47417a |  | note | Scale A: Characteristic Density Ratio 99%.
label | 4a163674-5ee4-4707-b6ae-9cc49576386d |  | note | Scale B: Characteristic Density Ratio 98%.
label | df21fa2b-22a0-4438-9112-dfa178f49980 |  | note | Note: Princes Highway is Scale A, South Gippsland Highway is Scale B
label | 83127e83-6a7c-4223-841c-4c514c17c417 |  | note | ---------------------------------
label | 76093e9c-2d4c-4fad-b96a-41199b935f1e |  | note | METHOD: Test Point
label | f2571850-d7f0-4664-8c67-841cc1ac3eb6 |  | note | ---------------------------------
label | ebf11775-456e-462b-80d8-1bfe5f59c38b |  | note | FREQUENCY: Each lot
label | 21a9a4ac-79a1-4d42-a0ab-70ca1190bc46 |  | note | ---------------------------------
label | a2e0f777-3a99-4298-a6f0-fbadba0dd944 |  | note | CATEGORY: TP
label | a21eb30f-7963-49c5-b3bf-38f8d70376a2 |  | note | ---------------------------------
label | fb1fb048-8ff2-45e7-bcc2-661cc4596bec |  | note | RESPONSIBILITY: Site Engineer
label | 5da74fd1-e222-4b78-93c0-f7c910f31bc3 |  | note | ---------------------------------
label | e9f15121-3960-402d-9cb5-e5dfcc0e2e7e |  | note | VERIFYING DOCUMENTS: Test Records Lot Register
text | 144c5de4-749b-4f76-a740-360725f22e48 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Post Compaction Material Property Testing
label | 109d301c-e968-49b6-8e5c-16e5a6c78e08 |  | note | REFERENCE: Table 204,041
label | 54556256-5b7d-470c-9844-e74338a41343 |  | note | Table 204.141
label | b625db54-4bd5-4f4f-bbc3-d09731b67cb7 |  | note | Section 204.14 a) or b)
label | 0e3151d4-5b70-4d13-9fc9-140955b66309 |  | note | ---------------------------------
label | d0225445-6ba9-43c2-8e1d-35bcf29c1e7a |  | note | ACCEPTANCE CRITERIA: Material Properties:
label | a5f08f78-4977-4fcd-b869-fb38a49c7741 |  | note | CBR ≥ 3% and Swell ≤ 1.5%
label | 563f5c2d-9a20-4f5b-b02e-ceb32ed7a08a |  | note | Max Permeability = 5X10-9 m/s
label | 91a9ac66-1200-4391-b7d3-8dca2e09010f |  | note | Grading: 75.0mm 100%
label | 93868bb8-dfef-4cda-bb38-817b63b2ba09 |  | note | 4.75mm 40-80%
label | a3c63830-da22-44b7-815a-a3d8deacba4e |  | note | 0.075mm 10-40%
label | 429c07e4-7566-44b6-887a-e5d81f8b1cb8 |  | note | Max. PI x%Passing 0.425mm = 1000
label | 6b248fd0-88fc-4c8e-9799-8e76c5556051 |  | note | PI = 6 to 25
label | 0f09ec0b-2d3e-4be6-82c1-bdd117359c60 |  | note | Scale A:
label | b5795287-ae3f-47c1-ae09-d5aa5d99589e |  | note | CBR & Swell
label | 723cf9d9-fe7d-44d2-8c63-996bfccc56b2 |  | note | Initial - 1 Lot Test to determine Assigned CBR and swell
label | b855b712-df14-4f46-97d9-405d4841041c |  | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | ce0f6c51-0605-4df3-8078-02eb181d217c |  | note | Max Permeability
label | 095220c6-efd3-400d-826f-8763b92a5d5e |  | note | Initial - 1 test per 2 lots
label | d2bb38a1-0e5f-4fa5-9c53-67c4e9d7aacc |  | note | Reduced - 1 test per 4 lots
label | 9db2fb99-7089-493a-acd4-714b8a29d388 |  | note | Grading:
label | 398f3f9a-bd89-49bb-8873-573a0739764d |  | note | Initial - 1 test for each lot tested for compaction
label | 19b148da-6da3-4edb-baf6-ec1b47c73a51 |  | note | Reduced - 1 test for every second lot tested for compaction
label | 1ecf60e6-2317-447b-a3fd-36fadd00b87f |  | note | Max. PI x%Passing 0.425mm & PI
label | 1a4da99b-14f9-402d-99c3-4563dbf90aab |  | note | Initial - 1 test per 2 lots
label | 51bc1979-b982-4d8a-9b67-6b310900ea11 |  | note | Reduced - 1 test per 4 lots
label | 8e806be0-8ffa-499d-b6f4-6178bb665e7e |  | note | Scale B:
label | 57f5e2a5-0a14-42dd-87ea-cd4cc8418303 |  | note | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | cfe23ac3-a1b6-4511-8907-029a540d51c1 |  | note | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 939ae965-d54f-4e66-b5fa-7e4e62194e86 |  | note | ---------------------------------
label | 3058ee3f-8ebb-4c23-a586-1568c26b4932 |  | note | METHOD: Review Document
label | ea293b5b-d090-4e0a-9912-d8b6a52b1c2f |  | note | ---------------------------------
label | 18fc3631-9d54-4d73-8496-d26020b3a73e |  | note | FREQUENCY: Refer to Section 204
label | 0e2d7b55-bc1e-4b90-b050-6df0364127b2 |  | note | ---------------------------------
label | f38a770b-722d-4076-b91f-ce58ccb67c21 |  | note | CATEGORY: IP
label | 07683f0c-5d70-40d1-8c2a-d217ab2ef482 |  | note | ---------------------------------
label | c53769bd-451c-4a82-a8ba-3751d4d44be4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 74bed452-04f0-4369-946d-a847d8d65c1f |  | note | ---------------------------------
label | 87718fd2-4561-490b-858d-72e987e51ccf |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Material Property Test Report
text | 6ad402d8-11b2-4b7f-9baf-6d20918d2c9c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Type A Fill/Verge Activities (if applicable)
checkpoint-status |  |  | checkpoint | 4.1 Type A Placement
label | 44a9e4bf-640c-4628-8dae-f9e6bae54df6 |  | note | REFERENCE: ITP-CIV Type A Fill - Road (Suppl and Install)
label | cb47c005-c814-44da-85d8-754f3bbfa3c4 |  | note | ---------------------------------
label | 8a987322-171e-4cc7-b845-eb9cdb836188 |  | note | ACCEPTANCE CRITERIA: If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | 4776c8c4-8845-4563-8654-ad216fc49adb |  | note | ---------------------------------
label | ec4e0425-dae4-4d97-9647-33b8b2525004 |  | note | METHOD: Visual
label | ae19609d-ffb2-4db8-801e-0339be684886 |  | note | ---------------------------------
label | ec3ec073-6ae8-4720-9c6a-234d99beb0a8 |  | note | FREQUENCY: Where Applicable
label | b2d5551a-c2f6-4ee6-8826-ecbfcfbd8b1c |  | note | ---------------------------------
label | 7c8a2eff-007e-437c-b2d8-b7bbed2f409e |  | note | CATEGORY: WP
label | 1daa1515-785d-466c-8010-a9470cae206b |  | note | ---------------------------------
label | 1b236390-4c9b-4c86-871b-03dbfc2ebcd8 |  | note | RESPONSIBILITY: SE
label | 012e7a2e-0106-43be-abb2-830bf23a27bd |  | note | ---------------------------------
label | eaff1f1d-6372-473d-a9dd-d9553c63fc43 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | f79d297a-c18e-42df-a7e0-097fb88c6b47 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Survey Conformance
label | beaf9c04-57c3-4f3a-ad0b-7a2e113c8249 |  | note | REFERENCE: VicRoads 204.03f,g and h
label | 525bdc9a-360c-47e2-9c8b-1764c9220b1a |  | note | ---------------------------------
label | 7baa59cf-f3be-43e3-85e0-7c63ec204499 |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 2956b201-c736-48d3-9b83-8395760e91f4 |  | note | Level tolerances (Scale A - Princes Highway):
label | ef8e256d-64f2-48a0-9cf6-5d68224b1cf6 |  | note | Range x = +5, -15mm
label | daa69796-b57b-44da-9e22-f181cefa6fa9 |  | note | Max S = 12 mm
label | c48dad98-cb0f-40bf-936a-44d406449841 |  | note | 80 measurements per lot
label | fba8d91e-ecff-45bb-bce2-2da2db3c1a2e |  | note | Level tolerances (Scale B - South Gippsland Highway):
label | 5c045091-ac15-44ca-9fbd-77cdc5b770d0 |  | note | Range x = +5, -25mm
label | 82a8d1e9-d2ab-4f69-9b6f-39e1e165adb9 |  | note | Max S = 15 mm
label | f3dac0e6-803a-4172-a4a8-f509508c9419 |  | note | 40 measurements per lot
label | 50640a57-d39c-4c8e-b179-6504ef12f1cb |  | note | ---------------------------------
label | 25900d4d-1a5b-40e6-a025-1db673de6c78 |  | note | METHOD: Review Document
label | f9f53c53-64be-4c35-a18b-028cb365d7dd |  | note | ---------------------------------
label | fc29d7ed-7120-4464-a822-e5d7c11faf31 |  | note | FREQUENCY: Each lot
label | 423fb580-9e33-473b-9e71-883287ca5687 |  | note | ---------------------------------
label | b9dc579e-1e8b-49be-a948-7f5f69b0a900 |  | note | CATEGORY: SCP
label | c5a60527-009d-4f63-ae4d-2b0cbc5659bf |  | note | ---------------------------------
label | 2f6c07a4-7e35-4b7e-a0af-921cad8187ff |  | note | RESPONSIBILITY: SE/Surveyor
label | 14332360-4501-4a18-8566-340d0d8f4b7f |  | note | ---------------------------------
label | 9135fd40-48b4-4318-a548-6ff71f5b5f71 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Survey Report
text | c33736b9-f91f-404b-914f-828d8c0b8ac2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 7352f203-f288-49a3-8df6-7c6f3bf37c2e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 3b0c0446-9819-4e24-adf1-911fbd8bc622 |  | textbox | Name:
text | fffd9801-1c36-4a00-9992-0b9202f87e05 |  | textbox | Position:
text | 6073dc2e-28be-4660-80eb-919436d833c1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 0 | 81613cad-49b0-463e-8a01-6a34129ab002
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 70dfeb8c-235a-4570-9160-bf73ec8359a4 |  | note | Document Title: ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling)
label | a8bfeb50-283c-4c9b-bf88-85d8d5159071 |  | note | ITP Description: Footpaths & Shared User Paths - 2 (Concreting & Back-filling)
label | 59e8734b-ba55-4d96-b132-8bbc90fc5afb |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 42ade854-ce7f-4b8b-991f-e3c4df71199a |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 4da1a536-ab46-45ca-9154-b956f677968a |  | note | Revision Number: 0
label | 06156089-16ba-483a-be0b-ef918c4e1bdb |  | note | Revision Date: 22/06/2020
label | c970c061-de8e-44ab-80ca-24e223084d97 |  | note | ITP created by: Lachlan Macready
label | afb41ec9-9a94-4ab6-af92-df8a97b95c4a |  | note | ITP approved for use by: Mike Freeman
label | fcad52e0-0bd7-4e52-8fd5-263a2c095769 |  | note | 1.1 VicRoads Section 703 June 2018
label | 7cae96ce-056f-4777-ad2d-b8fdb3450480 |  | note | 1.2 VicRoads Section 610 November 2018
label | 2caf18c8-79b4-4ccf-8670-9a78ff79466b |  | note | 1.3 VicRoads Section 714 April 2018
label | a3914845-614b-454a-820b-1f96b1b18c2b |  | note | 1.4 AS1379-2007
label | a1d8cc71-1681-40f3-aec5-e350ffd4f801 |  | note | 1.5 AS3610-2018
label | 23bc346e-5fb3-4f54-9b79-0d9f0d969608 |  | note | 1.6 AS4671-2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | b208f7ae-1c89-44a6-9068-5d27e91996b3 |  | note | REFERENCE: IFC Drawings
label | cbd9c28b-44cc-4942-a4b2-d0d4338730f1 |  | note | 703.05 (a)
label | 56c4c309-c00d-46a5-90c0-772ae6b73c60 |  | note | 703.07
label | 934730df-87de-49be-b8f7-b9f35c528273 |  | note | MRPA Quality Management Plan
label | 359a2502-8ecb-4c99-8811-b8868d40d9cb |  | note | ---------------------------------
label | 862d477b-15a8-40c8-afd2-f178d542391b |  | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | 2f30e209-71dc-47fa-a17e-a2e8e42a3e98 |  | note | Paving concrete mix conforms to AS1379.
label | 6f3c8d02-23bf-454a-ad45-01877ceaf4ea |  | note | SUP concrete mix is registered with VicRoads.
label | b56466ea-2a3c-453f-b8f9-e3fbed821246 |  | note | No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | d8755b23-b9ca-42a7-8289-c5b31c5a5efb |  | textbox | Enter: Teambinder Material Approval number
label | 8e3421af-da59-4ec2-99cd-e6addbd5da86 |  | note | ---------------------------------
label | 20dcf29c-9d9e-4b2f-a989-111aac2b7004 |  | note | METHOD: Document Review
label | 081e6d8b-29f7-4ce7-a41b-8c323e8a128d |  | note | ---------------------------------
label | e38c7954-41da-427c-a6c0-db3e8656f572 |  | note | FREQUENCY: Once, for each mix design, prior to placement of concrete
label | 3264de01-07e8-4ce4-be3d-52f3160d1f74 |  | note | ---------------------------------
label | ce34cfd7-604c-41e2-b870-e3e50008e2da |  | note | CATEGORY: HP
label | e58b9698-3d80-45fd-86f4-b2816dd4b723 |  | note | ---------------------------------
label | 9e614816-c03b-4d2f-bf91-677e3f807779 |  | note | RESPONSIBILITY: Nominated Authority
label | ec0719e6-131d-41a4-b26b-7c6c9b9a5646 |  | note | ---------------------------------
label | 50e48bf0-45a4-495b-8897-b9dca4772af4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3a27f8da-4c08-4c92-bd9f-5d471b6a0997 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Reinforcement Certification (or ACRS Certification)
label | d8115578-7750-46bd-bce3-081977917a84 |  | note | REFERENCE: 703.13
label | c350a8ec-3891-48ea-8496-b8036e692c8d |  | note | MRPA Quality Management Plan
label | dd37fbf2-a334-42b2-9b2a-e0a3060159ea |  | note | ---------------------------------
label | 0a125c70-32bc-4a4a-a597-8a358fef4006 |  | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | 595631a8-4317-49ab-89e9-5da52faccc22 |  | note | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
label | 00ff85f4-35c5-42c6-b395-3dc0e2350b5f |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | cc4231d7-0740-40de-a4ff-d21b24412a75 |  | textbox | Enter: Teambinder Material Approval number
label | 99ef544b-94d7-407c-98d7-2fcfeb5468c6 |  | note | ---------------------------------
label | dad13ad9-23f8-4a73-a886-97d889bd9349 |  | note | METHOD: Document Review
label | 314425a8-095c-4c95-8c63-96fe60c6b154 |  | note | ---------------------------------
label | 1fd92124-a47b-44eb-915e-d51e44fccbbc |  | note | FREQUENCY: Once for each supplier, prior to placement of order
label | b68bab41-b138-402e-afa0-76b47c485376 |  | note | ---------------------------------
label | 90a42a4d-fd9f-47dd-afcd-d091443e04e8 |  | note | CATEGORY: IP
label | f2ee7ce7-e3d2-45ae-978d-c088a237c730 |  | note | ---------------------------------
label | 9bb10543-cebf-4d50-b063-0458b3ee8af7 |  | note | RESPONSIBILITY: Nominated Authority
label | 2c1291e9-2ab1-4e7b-9621-08b07daa1047 |  | note | ---------------------------------
label | c339a0fe-03e0-4aa5-a446-bf1a4699c517 |  | note | VERIFYING DOCUMENTS: This ITP
text | a5d1cc1e-114c-4449-956c-f6140432d174 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Evaporative Retardant
label | 1101f4e1-9217-4eb3-a4ce-f2108ea037fb |  | note | REFERENCE: 703.09
label | b282fbff-708f-4a7e-9e56-3a896a2803c0 |  | note | 610.17 (f)
label | b2c2e8a7-1caf-47a8-85e2-cf58feb895af |  | note | ---------------------------------
label | bc348701-a96b-423b-a4e5-cf9b9340c476 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | bb4df4ea-20d2-40e9-b457-01bb0d9385fb |  | textbox | Enter: Teambinder Material Approval number
label | 8f231570-88fb-4d58-bcf8-154d5964826f |  | note | ---------------------------------
label | 104ec317-f7a6-4bf3-8b42-b73b22ec6b27 |  | note | METHOD: Document Review
label | ec21fc10-4e2d-4fc7-bac3-4c5f63459e27 |  | note | ---------------------------------
label | ba336ce9-3aad-4ce8-9ff0-f64144e55e0f |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | b3ea9fa0-9b1f-4d8d-8f50-721979f0cd85 |  | note | ---------------------------------
label | 92941788-5b48-4ae8-849b-16a96bf9f663 |  | note | CATEGORY: WP
label | 00a167c4-7a2a-4b04-b33e-2db3a68aa0d0 |  | note | ---------------------------------
label | 57f4f82b-c8f9-4b25-96e8-a3443776afce |  | note | RESPONSIBILITY: Nominated Authority
label | 9db04fe4-b162-4481-a644-785dacbaef4f |  | note | ---------------------------------
label | fd6ed0e1-8e92-46f1-90f9-58d4f7b23b11 |  | note | VERIFYING DOCUMENTS: This ITP
text | fdd0d093-814d-4020-ae54-f579f34695f4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Curing Compound
label | 4eb22e17-42e6-453a-af0c-5aaf072cf115 |  | note | REFERENCE: 703.10 (a)
label | 3d776f4c-e4bb-4e53-ad37-a4e0e40354d7 |  | note | 610.23 (d)
label | 8db14cee-e1db-4c2e-b40c-6937d9a2cfc3 |  | note | ---------------------------------
label | 5ad590b6-2ba9-4a6b-bfe2-cdb8ff52ca40 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 23a4469b-8c59-4854-b50e-c80995063a5b |  | textbox | Enter: Teambinder Material Approval number
label | f48d3ae6-0c19-4e07-8699-cfa12422ed1f |  | note | ---------------------------------
label | 062426b7-4336-4e4e-941b-148b7c6bf41b |  | note | METHOD: Document Review
label | 16e8f172-fcb5-4702-9217-59ab897d23ae |  | note | ---------------------------------
label | 1c34b4b0-a162-48d7-82a4-71b6c42b2521 |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 275d446f-0f8c-4b9f-8d8a-608b951e4326 |  | note | ---------------------------------
label | 97b38c8e-56ef-4eaa-85be-f9d4425ec25d |  | note | CATEGORY: IP
label | a9315474-74eb-4099-b32c-089554571c74 |  | note | ---------------------------------
label | 5e183c71-bf27-477e-a68a-0d80b4b7f806 |  | note | RESPONSIBILITY: Nominated Authority
label | 87a7a578-4b40-4cb7-b72f-3b711b0e2cf1 |  | note | ---------------------------------
label | aca7fc5c-e438-42fb-a321-9de0878d6ed2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 58d4dcc2-5f63-4f91-9079-8b205189c733 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 IFC Drawings
label | 65242d3c-9e41-40be-bad7-8901f12f0d72 |  | note | REFERENCE: MRPA Quality Management Plan
label | 6e86cebc-13a7-483d-9630-89819cf82c27 |  | note | ---------------------------------
label | 324e6dd3-a22f-4561-a127-4930573c1c45 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 2ee18a47-00fb-448b-b302-ae31f6d21005 |  | note | ---------------------------------
label | 020276c1-77e3-41a3-8aba-61ab9094815f |  | note | METHOD: Document Review
label | adbd737d-0a61-4374-817d-77ac72172267 |  | note | ---------------------------------
label | b5b607e3-af02-406c-8e87-cb099cf8ffe3 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 9dbcc673-751a-404b-bd86-884a571dca3b |  | note | ---------------------------------
label | a69441ec-ab40-43a2-914b-e9823534fde7 |  | note | CATEGORY: HP*
label | 2d68a320-e29d-4df4-ab8a-715215b40b40 |  | note | ---------------------------------
label | 4b1b094d-ae83-46d5-9884-5a27cc79a405 |  | note | RESPONSIBILITY: All
label | da06bf22-1f73-4aa6-8dda-7ccc0eb9f2b0 |  | note | ---------------------------------
label | 8fcad42a-0de7-413d-83d9-72ccc2036dd2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 57730c73-0978-4431-9fc9-51a5ee953c22 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Formwork Construction & Placement
label | 74eab841-2103-4292-be55-08e097d7a4a9 |  | note | REFERENCE: IFC Drawings
label | 558412d3-fc02-436e-940c-3bee27fb6816 |  | note | 703.12
label | 6d7aed1e-9269-4d1d-a402-e6976c7d1886 |  | note | ---------------------------------
label | 291a54d3-e899-4575-b151-9d5bfd14faec |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | e1f7b9c4-9d7e-4081-9ea6-5162c9c7c554 |  | note | Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional comformance.
label | 90eb1c96-45b4-41bf-b476-e5992a55f877 |  | note | Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 37ccb3f3-a305-4637-a431-b7ad8027a61e |  | note | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 7eeaad99-40a7-48bb-b8ea-b245f2884717 |  | note | ---------------------------------
label | 1ca1db57-aafe-4b8c-a49b-46c4c74e3ad8 |  | note | METHOD: Visual Measure
label | 45134c5c-1c11-475e-bf73-b03bee9f3312 |  | note | ---------------------------------
label | 8ce69d57-b5cf-4182-a012-7e85cd16a53d |  | note | FREQUENCY: Each lot
label | 7b39c014-89c7-4f71-bd47-b78e184ff2d7 |  | note | ---------------------------------
label | 0bb18f12-0461-4494-b777-acab2c520bce |  | note | CATEGORY: IP
label | be8e6e0f-5f40-48b7-b904-4437f090d35d |  | note | ---------------------------------
label | 7b3146bd-2d7c-4ed3-b491-4cae8b88058e |  | note | RESPONSIBILITY: SE/PE/SPE
label | b150e67a-e026-4eae-8fbe-3984afb934e4 |  | note | ---------------------------------
label | 6134a21f-335e-48d1-b317-75cab55c0a41 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5bb1cad6-9fa8-4f4d-80c2-2531308d0913 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Construction Joints & Matching Exisiting Surfaces
label | da9880f3-0b61-488f-8bb5-8a9864ca665a |  | note | REFERENCE: IFC Drawings
label | 92f4fafb-03bf-4e4b-8ac7-637e4aaab3ff |  | note | 703.24
label | a5dc6040-1421-494e-a218-edc78fd64798 |  | note | Relevant Council Standard Drawings
label | 1df50a81-15ad-4bb1-8405-bb1347a9c287 |  | note | ---------------------------------
label | f6c85684-ec82-49b7-9b72-718257f7c3d7 |  | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | 388fc5eb-731c-4d89-ad53-7e1787c1a3f9 |  | note | Consult the relevant Council Standard drawings for the joint detail, these may require:
label | cae4592d-7491-4374-be88-0b5727f17ff8 |  | note | i. Concrete cutting of a shear-key
label | 70810682-8d34-4b09-b42d-f2fde4aea4de |  | note | ii. Surface rouighening
label | 44ddd239-7f32-4a7c-9201-751637d7b7cb |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | 0af8544d-513d-4f91-abfa-25002a808f73 |  | note | iv. Cutting a groove for sealant
label | 455e88a1-75f9-48ef-95c0-a2b4b24527cf |  | note | Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 01d4ed0c-12e1-43d2-8557-2f627acee7c3 |  | note | Transitions between different profiles shall be made in accordance with the drawings.
label | 5e06f352-1942-4106-8af9-2602950f73b1 |  | note | Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | 666a0674-cac1-4a86-9532-eaeba8476d89 |  | note | ---------------------------------
label | 1a54e58f-1a91-436d-b3e5-00641b3798ef |  | note | METHOD: Visual Measure
label | 1855217e-6013-48df-8a21-8c739f4ac3b8 |  | note | ---------------------------------
label | feee684e-078f-487e-83b6-68b77c940a5f |  | note | FREQUENCY: Where applicable, each lot
label | 9b4fcb11-f469-445c-af65-0074b72fad71 |  | note | ---------------------------------
label | 5e049b75-34c9-4251-a43e-7d429495f2bb |  | note | CATEGORY: IP
label | d9e4210e-7771-4180-99a2-2d6ad4455a7f |  | note | ---------------------------------
label | 5e2b896c-eede-4e4a-9839-8752e0386f73 |  | note | RESPONSIBILITY: SE/PE/SPE
label | faeb47e9-84ca-4cf1-887f-20c170a6169a |  | note | ---------------------------------
label | 3b0a8a98-23ad-4acc-9888-6a03ff523468 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7977192d-a348-40f0-988b-4fe415de2b92 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Isolation Joints
label | c5b9529f-b7fd-45be-b84d-330ce120b59c |  | note | REFERENCE: IFC Drawings
label | 82bfaf71-e467-4ee5-8871-9c467a71c068 |  | note | 703.26 (c)
label | c67da7ba-62ea-4a83-91c0-ccbad6106d50 |  | note | Relevant Council Standard Drawings
label | 7ec281de-7a87-4bc5-bf4a-45475a13de6d |  | note | ---------------------------------
label | e45167d9-1f7c-495e-9a96-ff2f5785bac0 |  | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | f2a32fca-6c82-4710-9e86-8bac9acc6c25 |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | 584fa9be-c333-41c0-a3e1-7c63852711da |  | note | ii. at any location marked on the drawings
label | 9c2ea105-b1f0-449d-94a7-aaa44ccbfaa2 |  | note | The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 39d66d12-4413-4106-92e7-a8b7b35fb34e |  | note | ---------------------------------
label | 321903d6-5651-43e6-a93f-224057a28e6b |  | note | METHOD: Visual Measure
label | 66a62a5f-ed49-4195-9043-428c977d374f |  | note | ---------------------------------
label | e8a7ebec-3c8a-4df6-9e11-ad5a508edd0f |  | note | FREQUENCY: Where applicable, each lot
label | e37386e8-5b1c-4f5f-aeb7-244ea438b2d0 |  | note | ---------------------------------
label | cf3db7b4-dbb2-4eb1-98f4-370744f11e8e |  | note | CATEGORY: IP
label | c38226ac-37ad-4b8a-a38f-c0e58e8775c3 |  | note | ---------------------------------
label | 5c450508-3de2-4c55-bdc3-a6a6483cd65c |  | note | RESPONSIBILITY: SE/PE/SPE
label | ed7fadf1-52e1-43ae-aec8-cd4b837ece2e |  | note | ---------------------------------
label | 1ee3e537-1081-49d8-a9b8-fb07c941521f |  | note | VERIFYING DOCUMENTS: This ITP
text | 48fdc400-1625-4592-a788-e9a6b73512cf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Expansion Joints
label | d35c41d8-1f5a-47d5-86f9-174219cc7ffc |  | note | REFERENCE: IFC Drawings
label | a715a101-d337-4b91-b847-cb4d43694e04 |  | note | 703.26 (a) (ii) & (b) (i)
label | b411cc7b-38fa-4e3c-ab91-fde15ce843ac |  | note | Relevant Council Standard Drawings
label | 8d3639f1-ba31-4254-b288-830367a0e3fc |  | note | ---------------------------------
label | 3b02b6fe-b1a1-45b2-a8e2-4606864a7dc7 |  | note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
label | 08cb1450-884b-492d-83b2-fc0285fdbca9 |  | note | i. on either side of vehicle crossings
label | b8db80d9-f517-49eb-ad7d-901942f94cca |  | note | ii. at junctions with existing footpaths and shared use paths
label | a989189e-2c51-41f7-be90-33abb832ac22 |  | note | iii. at junctions with bridges
label | 56fc23e0-0047-4605-b9fc-01bcc2eecc5f |  | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | 6d1b6c91-d3db-437a-89b9-36ac0b4e19d1 |  | note | The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 468120ef-cfc6-47dc-b3cd-8ba0dae6345f |  | note | Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | b2f19c58-fbdd-4838-a8b3-4f7c687dd7f2 |  | note | Alternatively, a proprietry joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | d1be3818-d0d5-4915-b9b7-ff8a784ee509 |  | note | ---------------------------------
label | 72d659a2-1a36-49bd-9a88-0f0c1e130824 |  | note | METHOD: Visual Measure
label | 5259a67a-508c-491e-99d2-a2f7b3ad2dc0 |  | note | ---------------------------------
label | 725d5ec6-b56b-4dab-94d0-fc3cd86bcfbd |  | note | FREQUENCY: Where applicable, each lot
label | 4f27bc87-ad5e-42bf-82e2-817743a1b709 |  | note | ---------------------------------
label | 0f4a53d2-c42d-4908-a3a4-646540aeae8b |  | note | CATEGORY: IP
label | 1db11f09-bbc1-4ec8-9e3d-f17eb7ddb8c9 |  | note | ---------------------------------
label | 44f6c8f6-06bb-4dba-83a1-9bbac55c196e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 59d39af8-27be-4642-98ab-1ded78430289 |  | note | ---------------------------------
label | ffd7c548-0585-4264-b06f-bc99b2f9ac10 |  | note | VERIFYING DOCUMENTS: This ITP
text | 218e0f11-e933-4fff-80da-3c2ac17e4516 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Reinforcement Placement
label | a46f1c9a-7fdb-4a45-bfdd-64fa5c1e7bfd |  | note | REFERENCE: IFC Drawings
label | 2f08eb4a-b4a4-4e6f-bd86-23ca1448c3a0 |  | note | 703.13
label | 9571b565-1814-48c0-bcc1-57118d0d092f |  | note | ---------------------------------
label | 9e97b165-8319-426c-9510-10ad224d8454 |  | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | 1b42ed18-32db-4d26-880a-02b818b299dd |  | note | Any splice lengths achieve the minimum length and are in contact for this length.
label | 72737768-002f-49c4-8552-7a4ffc45fe17 |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | b9bfc210-b28f-4567-9cf0-24d615228f9d |  | note | The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | 942f0637-8159-4be0-b68c-f35adc281966 |  | note | Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
label | eb03ec86-cf93-4f34-80a4-2c1f57203b54 |  | note | Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | 4a405a4e-6db1-4876-bb23-64817df9d729 |  | note | ---------------------------------
label | 1c3ecc21-160b-4225-90db-deaa9669e404 |  | note | METHOD: Measure Visual
label | 9d815d82-1121-4079-b795-1da4ac496345 |  | note | ---------------------------------
label | d4de1d1e-d489-4fbb-81b4-9fbe8d6918ef |  | note | FREQUENCY: Each element
label | 4100a3cf-aab6-45f7-a067-d7e7c8610744 |  | note | ---------------------------------
label | db310531-8b6d-4231-97cf-fb449f834d44 |  | note | CATEGORY: IP
label | 5e740e1b-c523-4151-b2f2-892bd7200c8c |  | note | ---------------------------------
label | 672696b7-1510-4c4d-a203-701846bc2c86 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 1e608a17-1cbb-468f-b2a2-8e5c54474dde |  | note | ---------------------------------
label | cf983608-ce33-461a-a35b-429270b7ee27 |  | note | VERIFYING DOCUMENTS: This ITP
text | b8b570f7-391d-46af-9050-5f72e94cde2b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Provision for Permanent Signage
label | c665e6de-0a2d-41ef-a2bd-ff1fd72f69a0 |  | note | REFERENCE: IFC Drawings
label | 1908d8da-c8c3-4ab8-bd13-1a6404d6ef7c |  | note | 703.22
label | 78bfa5a9-06e5-44e0-a6a6-451bb043d218 |  | note | 714.06 (d)
label | d9ee474f-3e19-40e6-8ce9-044dbff574c0 |  | note | ---------------------------------
label | ffe25aa0-7d2f-4b93-bdcc-85a3a04c670f |  | note | ACCEPTANCE CRITERIA: Where applicable, permant sign post sockets shall be installed at the locations shown on the drawings.
label | 8cae7369-e3a0-449d-b2fb-4ea3e5ed5df6 |  | note | The Nominated Authority shall confirm the positions before the final locatiing of the signage commences.
label | afbdd469-a36f-4348-aac9-0969b879b4de |  | note | ---------------------------------
label | 2725e022-9e4e-4725-8755-bd5b824d7848 |  | note | METHOD: Measure Visual
label | 513e775c-7fd1-43fb-85e0-a0f1de96e99b |  | note | ---------------------------------
label | 08769808-90ba-4feb-aacb-d17d1500748c |  | note | FREQUENCY: Where applicable, each sign post
label | 15116e19-1816-4d7d-9287-f57e0cc11a26 |  | note | ---------------------------------
label | d551c147-3f9f-49b6-a528-93ccd95e0e62 |  | note | CATEGORY: HP
label | e2842925-9fbc-4121-ac17-33ad59f0c4af |  | note | ---------------------------------
label | 81b84bb3-deef-4056-a6b3-c5fd6ae2a1ba |  | note | RESPONSIBILITY: Nominated Authority
label | f3a17f4d-9758-4acf-b2d2-ce226775a662 |  | note | ---------------------------------
label | a2fa78e3-6b6d-4fbe-9e12-0d98dad064ea |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 771612b1-88d3-46cb-9344-08b25dbea120 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.7 Pre-pour Survey
label | 05a5014d-7072-45f8-a7f0-2e06a02b4c7e |  | note | REFERENCE: IFC Drawings
label | 81771778-9225-4412-8218-1be22022f7b9 |  | note | 703.15
label | b3285b20-9b61-4f38-aaf1-429d11e4b30e |  | note | ---------------------------------
label | 098a8e89-9d7f-4db8-b329-0800fca35d01 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | 39c7158a-3f3d-4e83-84e1-46755e0606dd |  | note | Erected formwork and base layer within the tolerances below:
label | 4aed24fe-21c2-479f-a7fa-47d64fa674aa |  | note | Departure from RL = ±10mm
label | 6f483ba7-27d0-41b0-a8c2-d83a78440fb5 |  | note | Departure from alinment = ±10mm
label | 4f41e5df-ea3b-446e-8910-20ee7477f14c |  | note | Rate of change of deviation from RL or alignment = 10mm in 10m
label | 756bfbc1-42e4-4f99-b0f9-9aeecf87a095 |  | note | Irregularities in alignment = 5mm in 3m
label | 127184d3-1aa8-45b4-826c-efb0015b1d90 |  | note | Section dimensions = ±5mm
label | d11efa79-9814-4ef2-86c6-74404e2c90ae |  | note | Section dimensions (less than 25mm) = ±3mm
label | 66a9031c-712e-4e78-80b3-8da23de1ac95 |  | note | Width of pavement = -5mm, +15mm
label | dd818a46-b783-4e90-8449-26692f6d9bc4 |  | note | ---------------------------------
label | d6f56f08-ddac-437d-b949-340e57b66a72 |  | note | METHOD: Measure Visual
label | 65e6f248-32f0-4d92-a01d-a09851182647 |  | note | ---------------------------------
label | 51b9029e-7b82-4f65-8dd5-709e6ed798ea |  | note | FREQUENCY: Each lot
label | 511ac73b-9e62-4790-a9f3-3699621f85fb |  | note | ---------------------------------
label | f927724c-a1ba-4113-addc-2ddbab224291 |  | note | CATEGORY: IP
label | b0658850-e8ce-4d6d-8c25-9bafc37f49df |  | note | ---------------------------------
label | 4c2ad87e-0929-448f-80bc-5a9a26eb6cb1 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | d0813c80-cde1-4b7a-9f21-677f0663e9b1 |  | note | ---------------------------------
label | 6f3e7ab8-4d63-46e5-a897-5f0d57ba4257 |  | note | VERIFYING DOCUMENTS: This ITP
text | 16449163-92b5-49c2-be5d-c1b835232d35 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Pre-pour Inspection
label | c22804da-d550-407c-af2f-4abe773dc36a |  | note | REFERENCE: IFC Drawings
label | de318b13-b59f-4bfa-b9ec-156c87d0865d |  | note | 703.15
label | 82ae41bd-1e42-4f41-9a5c-0fc406ceace9 |  | note | 703.21
label | 8e2552d5-5e79-4e62-aea9-7cc2722607df |  | note | ---------------------------------
label | 89d03332-da48-4ad9-91a9-02c2f18d370e |  | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | 72cedccf-7046-4d6c-80fc-0105db1d74d1 |  | note | Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | 6a1113fe-20da-4ecb-801f-c7a5a5502ea6 |  | note | ---------------------------------
label | 87c95270-6ef4-4419-81a8-488440d7c97b |  | note | METHOD: Measure Visual
label | 28ceed9d-d98b-4de2-a16d-8bec87b15183 |  | note | ---------------------------------
label | 8b94a1f0-b1df-4bf6-b16a-87d05457c579 |  | note | FREQUENCY: Each lot
label | 0ce78506-9636-4a91-9273-54db608a6194 |  | note | ---------------------------------
label | c02fd3f3-1fee-4658-87c5-7263c711a8fa |  | note | CATEGORY: IP
label | f4ac5bdb-e099-4d05-a020-fae433e27dbf |  | note | ---------------------------------
label | aa00a303-7b7d-4157-95cb-af5f1c82fc88 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f6f90bff-37ef-4e60-88cb-caba8e392a66 |  | note | ---------------------------------
label | c1aef6ae-8ba8-41bc-ae42-d51d8324c91a |  | note | VERIFYING DOCUMENTS: This ITP
text | b6feea19-c42b-4c15-8f89-935be2683faf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Weather Conditions & Evaporation Limits
label | 966750bc-c095-427c-808b-9f781ac57375 |  | note | REFERENCE: 703.09
label | b9f174bc-070b-4c5d-a787-06436295ea00 |  | note | 610.17 (a - f)
label | ad8a7596-3f8a-4769-ac87-44c11903e81f |  | note | Table 610.171
label | ba73a737-88a5-4434-94b5-273ec52bbdd5 |  | note | ---------------------------------
label | b6f1ddd8-4f64-432a-b90d-83de45b126c6 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | 89c5e406-c75f-4edb-98c0-2db5e8b74119 |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | a171e149-d7b7-4935-b2ec-090991d8de8b |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 7f25b15a-cdc7-4faf-9837-0ceb147f1961 |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 0765b4d8-39be-40ef-a4f6-24fa1b0af9e4 |  | note | Record: Required information on the Concrete Pour Record.
label | 66d7bffb-c1cf-4c49-8315-007e1b9dd382 |  | note | ---------------------------------
label | 33a0d3d5-3991-4622-b763-a59e051d80c7 |  | note | METHOD: Measure Visual
label | 643a0d47-e562-4d36-baf1-566e38e72f59 |  | note | ---------------------------------
label | 751634fe-56a6-4ff8-bd54-5fe6e121b808 |  | note | FREQUENCY: Each lot
label | 0e789238-1e61-4b6e-8384-1a4a681916c1 |  | note | ---------------------------------
label | aa70bdab-7cbb-48ff-87a2-be93585eaf70 |  | note | CATEGORY: IP
label | 372a57c2-6dba-43d5-8e9f-a3a035b8aec7 |  | note | ---------------------------------
label | 5e204b31-cacb-4548-b81e-a11ab02a88ea |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | bc8dfd25-4010-4157-bb5c-927889398997 |  | note | ---------------------------------
label | 380fb5f0-fec7-4e2d-866f-4fe540681d1e |  | note | VERIFYING DOCUMENTS: This ITP
text | 49d5071a-d444-4808-8613-d0fdfb35ea2b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Concrete Testing - Sampling Frequencies
label | 2118c76b-38c1-41e0-ae4c-4bbd9a4e06af |  | note | REFERENCE: 703.11
label | efb01812-2bb8-4a3a-94a6-a3c326b13a0c |  | note | 610.16 (b)
label | f6436782-b839-496a-9620-4fdb6da7e074 |  | note | 0
label | f57ca426-c4ae-47d3-bebb-edfdd9ba3971 |  | note | 0
label | 9f4ee2bd-eaf6-4839-9309-c996f03d6ffa |  | note | 0
label | de68ec38-8bb2-41d7-8a22-0f2698dccc61 |  | note | 0
label | 7acfbff0-9430-4bcb-9c6d-97d22d24e6da |  | note | ---------------------------------
label | b4e68098-5fcc-431c-82d9-f3b2450d825d |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 131130c0-2e61-473d-ad08-f644bc5816d3 |  | note | Shared User Path:
label | a3f17285-b587-4b7a-b334-4219dd915f4d |  | note | 0m³ to 10m³ = 1 sample
label | e4f67886-68e2-451c-ab8e-d6a8509dac5e |  | note | 10m³ to 25m³ = 2 samples
label | 115e2972-6707-45c0-8567-cf4aedec15b2 |  | note | 25m³ to 50m³ = 3 samples
label | ad8b9690-17a4-47ad-b23f-5a2780a573ac |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 479f3d6b-c007-4499-81f5-36ebcfd7bfb0 |  | note | For each additional 50m³ and additional sample shall be taken.
label | 8241a2d5-9ad8-4561-a478-eaedddee20ad |  | note | Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
label | 8089004f-407b-4159-b7c3-cc07be818510 |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | bc3f731f-3687-42b2-8ea6-97238ddc0d68 |  | note | Footpaths:
label | e6c4c1e4-25dc-4f29-bdaf-df591f0eb70f |  | note | 0m³ to 50m³ = 1 sample
label | 0a64d02c-3766-44a6-81e1-463199790bd0 |  | note | Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | b0aa7f1b-3e72-474d-b893-1faee13f0086 |  | note | Compressive strength cylinders = 2 no. 28 day strength.
label | 0f158349-d705-4fa7-8950-0c72cc944aab |  | note | Record: Required information on the Concrete Pour Record.
label | 18cb91e7-753c-4f8d-aa02-7d839ceba285 |  | note | ---------------------------------
label | 74fd5a7c-0b66-4ed8-8328-def6e8a951a6 |  | note | METHOD: Test
label | f5753c78-728c-4f96-bfc8-beb94544f7d1 |  | note | ---------------------------------
label | dabcfe1c-6292-4dfe-b445-a64f6307f20d |  | note | FREQUENCY: Each lot
label | 297c1a80-8e71-4037-b273-de0ef0effae4 |  | note | ---------------------------------
label | 75ff78eb-ce3a-4017-9acb-371b299aad22 |  | note | CATEGORY: IP
label | 999583bd-0232-40c4-aed5-bfca17c34bbf |  | note | ---------------------------------
label | 43943d91-5108-460a-b2e8-59a8a1ff72ee |  | note | RESPONSIBILITY: Concrete Tester Foreman SE/PE/SPE
label | d4c89d48-3459-48da-93a8-76dcbb45fe8b |  | note | ---------------------------------
label | b756783a-ea0d-4e4a-b0c4-96f6abbbe4fd |  | note | VERIFYING DOCUMENTS: This ITP
text | 22aa6ffc-d140-476e-9929-d0f9f1d76cab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Concrete Testing - Slump
label | 1f4f2553-9f23-49eb-b8a0-c9710910ddcf |  | note | REFERENCE: 703.11
label | a09ca74b-1f78-43db-8b2e-70a1cdcac643 |  | note | 610.16 (c)
label | 8226e052-0536-453d-871c-5040c1d0952d |  | note | ---------------------------------
label | 5c80af76-c2a2-49ef-99f9-a5fb4aef3a01 |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | ed925bb9-f1d5-41c2-8667-8008139bf560 |  | note | <60mm = ±10mm
label | cc52b0fd-7d1d-47ae-b2f2-68343e6a3e10 |  | note | ≥60mm to ≤80mm = ±15mm
label | 226420fe-4e93-4f61-9283-ea4b61d241f1 |  | note | >80mm to ≤110mm = ±20mm
label | 79608840-cc87-4749-830a-146dcb79f133 |  | note | >110mm to ≤150mm = ±30mm
label | 935c035b-5ae6-4a04-b159-a8d7f3ad6d95 |  | note | >150mm = ±40mm
label | 06c4b331-5095-4b09-86ae-67fc5ebe0076 |  | note | Record: Required information on the Concrete Pour Record.
label | ae0052b8-316b-4004-b2d3-7d3f605159d9 |  | note | ---------------------------------
label | f7983e5b-dc9f-4bd8-a354-67568abf779c |  | note | METHOD: Test
label | a724d5d0-53ce-4f95-b16d-0aafc1072230 |  | note | ---------------------------------
label | 09c93381-f648-4fed-840b-e506855f56d4 |  | note | FREQUENCY: Each sample
label | dfde2e85-6807-465d-a851-ee5b54d7848f |  | note | ---------------------------------
label | 279b8537-b6e5-4299-a59b-9f31468c21ae |  | note | CATEGORY: IP
label | 80f2c605-4edb-4af1-9161-dd7773d0030a |  | note | ---------------------------------
label | b98a98cd-70bb-44cd-837c-e05f19ee53a2 |  | note | RESPONSIBILITY: Concrete Tester
label | 7e972175-155c-40f7-b4c3-c53a0c7dd9be |  | note | ---------------------------------
label | 6e230d62-150e-4142-ba6d-d17a134f9cfc |  | note | VERIFYING DOCUMENTS: This ITP
text | 0fca7399-a59e-4213-bfd7-05bcde44041c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Concrete Testing - Compressive Strength Cylinders
label | 741d9794-5b02-4e14-a7d0-eda807494777 |  | note | REFERENCE: 703.11
label | cb98b509-9c93-4353-a991-ecb29b8aec3c |  | note | 610.16 (d)
label | 9391d866-7534-43f6-bb51-779da0d6f5db |  | note | ---------------------------------
label | 25dc9cdc-1069-415e-8f77-25c0d1d70da2 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | fbe39da2-1aed-4928-9a43-53e4151d9361 |  | note | Record: Required information on the Concrete Pour Record.
label | 646f2f01-20d1-4d21-9fb4-905a806154df |  | note | ---------------------------------
label | 1715180c-6bd3-430d-a9e6-6a6a53623cfc |  | note | METHOD: Test
label | 74d8a81c-bc86-46f6-9c0b-d79f4e39c9ca |  | note | ---------------------------------
label | 77bbd0ce-984d-48bd-b30e-eaec5b563ff6 |  | note | FREQUENCY: Each sample
label | b08869e2-daab-47f2-87cc-9a4b75452be8 |  | note | ---------------------------------
label | 3a45003f-735e-4932-ac4a-a309fdcfc384 |  | note | CATEGORY: IP
label | 3d27c4c7-d179-4292-8aa8-715c3fb18588 |  | note | ---------------------------------
label | 58507bdb-37f3-41c5-8d34-51099888f5bb |  | note | RESPONSIBILITY: Concrete Tester
label | c039dbef-dc59-48b4-ac48-d49e05c11be2 |  | note | ---------------------------------
label | 9182a9e0-1982-40a7-9620-8c951ce8e80d |  | note | VERIFYING DOCUMENTS: This ITP
text | 857ae88a-a499-4819-b5ef-316dcb4c1760 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Supply & Discharge Rates
label | 1a45bf3b-a43e-49cd-abf5-9264bcfe6112 |  | note | REFERENCE: 703.08
label | 62951e07-ead5-44bc-84b4-1317199ebcf9 |  | note | AS1379 Clause 4.4.1
label | a9d46cd6-6ed8-4d4e-8d70-9b9e73966937 |  | note | AS1379 Clause 4.2.3
label | cf56b7f6-5fcb-4180-a7e9-6a5c16305aa0 |  | note | AS1379 Clause 4.2.5
label | 17a79191-78a8-4eb2-9108-cbcea6d4b1a3 |  | note | ---------------------------------
label | 5725cc8e-fa15-49eb-ad45-c6a5c31cec1a |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | d39c26ec-2abc-4fbd-8828-5d6a3dc85f7a |  | note | Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
label | ce4d38b2-54ee-4f50-ae5a-9c65aa75f359 |  | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | c606abbd-280c-4673-b509-0d21bc95ac62 |  | note | If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
label | d1d16714-22be-4962-aec1-ce27dc2d4154 |  | note | Record: Required information on the Concrete Pour Record.
label | 205e2404-83de-44ab-a0ff-e86c25f5fd1d |  | note | ---------------------------------
label | 671def9b-eda5-457a-832b-6c9e6cd144ec |  | note | METHOD: Test
label | 3fec05fe-51c0-47dd-a79a-ea9e533eb35b |  | note | ---------------------------------
label | fa56ab3d-30e4-4c55-86d7-8dffd7ebdb0d |  | note | FREQUENCY: Each sample
label | 053f164e-9a57-4178-9ca6-62cc24156410 |  | note | ---------------------------------
label | 5c5a1249-1799-4ea8-9889-5d725884c120 |  | note | CATEGORY: IP
label | 22ffea56-0695-442f-98b5-1f0f928afa5b |  | note | ---------------------------------
label | 1f3d5a51-f688-4c2b-972c-c184b0587601 |  | note | RESPONSIBILITY: Concrete Tester
label | 9be90a40-dc8e-494b-b8a9-634652c542a7 |  | note | ---------------------------------
label | 10781917-f9dc-45b9-b42c-e86abaf73666 |  | note | VERIFYING DOCUMENTS: This ITP
text | 97041610-3412-4d4b-b4a6-4b131e970d50 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.14 Placement & Compaction
label | 78259613-8e62-46de-b85d-d2aa268e402b |  | note | REFERENCE: 703.08
label | 9df94106-fa84-44e1-8c94-1f882ec85910 |  | note | ---------------------------------
label | 3c88b999-4176-41f2-a2d4-90dc885a9922 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | b33912f0-cc24-4e64-b78c-b54aee293bc4 |  | note | Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | 3f458652-bfc5-42ae-b1a2-8348f21ab64c |  | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 0f819eb2-1c28-4a6c-a0cc-db0377e0b720 |  | note | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | 818b7a31-5d3f-46a8-a020-2495b219f424 |  | note | Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | d78f4c7b-1375-4e83-b4a6-f86b56cca1b4 |  | note | Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | bd294fcd-e6ef-410e-b310-12dab3375463 |  | note | Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | 99a46890-5de3-4576-a8ba-d05a8905583f |  | note | Record: Required information on the Concrete Pour Record.
label | afc7ab3e-802c-4db7-b18e-5dcb3596ccf6 |  | note | Attach: Concrete Pour Record
label | 956c36ef-ddee-43bd-ad9d-7ecefdb9fe52 |  | note | Attach: Concrete Dockets
label | fe040790-b54e-4ddd-b7eb-b1532ce73403 |  | note | ---------------------------------
label | 3d6b3c93-772e-4080-a3b1-9e56a2481e80 |  | note | METHOD: Visual
label | 65960567-e1c1-45c1-8ef1-39768711b456 |  | note | ---------------------------------
label | 95868011-2b03-479b-9573-6b5afab5d98c |  | note | FREQUENCY: Each load
label | 08de4839-accb-4d3a-b44e-ade7969561e6 |  | note | ---------------------------------
label | 69ccbefc-18c8-4aad-959c-294971b9d483 |  | note | CATEGORY: SP
label | 76e5f09c-c3cb-47b0-851b-ff64ba007a49 |  | note | ---------------------------------
label | 859ae24a-fa42-491d-b273-f1ef5d74f140 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | d9869e19-10ce-4e44-8c61-2bc20ee9d401 |  | note | ---------------------------------
label | c390333a-db68-4c02-b93a-bb58aba4af78 |  | note | VERIFYING DOCUMENTS: This ITP
text | a6d5c28c-1c49-4d50-bdcc-9538018750a2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.15 Surface Finishes
label | bb0dc052-333e-4d18-883f-18a878145d09 |  | note | REFERENCE: IFC Drawings
label | 15956546-b1c7-4975-82f8-d932302bcb19 |  | note | Relevant Council Drawings
label | c981aa24-8ebd-4390-af7d-85f1909b4f9f |  | note | 703.25
label | 5badd501-4f84-4374-a0c9-c0db4c81c5d2 |  | note | ---------------------------------
label | 9b7d0958-87e0-4661-a50f-d0e51f4b5e88 |  | note | ACCEPTANCE CRITERIA: Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
label | e3ed28b0-15f8-47eb-94b1-a46d227f5278 |  | note | All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | 1f3ae83e-e307-46b7-afa5-62581ad1467e |  | note | ---------------------------------
label | 07d48dcb-cc07-46ed-afc9-51e420f95beb |  | note | METHOD: Visual
label | b0e8028d-a762-4caf-afbc-9270158f6686 |  | note | ---------------------------------
label | 53e326ce-5db9-4d51-a2d7-76c09b554db6 |  | note | FREQUENCY: Each lot
label | 04f2af17-70ad-4058-b864-9ab33f939bfd |  | note | ---------------------------------
label | 2072c5bf-aaa8-443b-8585-1bb182e9caa4 |  | note | CATEGORY: IP
label | ea0b4d2f-55c9-4cc2-875b-f307d5f3ef1d |  | note | ---------------------------------
label | cf69e7ca-644b-4d89-a6b3-dd4bf22e9c2e |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 6f07a0c3-49e8-473d-89d0-ae0179ed76d6 |  | note | ---------------------------------
label | 3b3b1323-2853-4362-a176-f73c1150668d |  | note | VERIFYING DOCUMENTS: This ITP
text | b78ca896-116f-4f0c-a26f-4e1b6355f447 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.16 Marking of Conduit Locations
label | 7a35bfe1-421d-464a-a13f-8494fbe84a53 |  | note | REFERENCE: IFC Drawings
label | 3f1660c9-f6e0-4d6e-9022-7453b81a279c |  | note | Relevant Council Drawings
label | f02edbb0-a413-4457-a883-4dcdaca7ca23 |  | note | 703.28
label | 42e14f6e-89f2-452b-a72a-fbe27a78e6af |  | note | ---------------------------------
label | 105a0873-1105-43ed-b61d-20e0134c2cb9 |  | note | ACCEPTANCE CRITERIA: The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
label | 7a563c10-917c-439b-b4aa-2bbdabd2cbe4 |  | note | ---------------------------------
label | 68660c91-cb18-4f55-8bac-8c4cc09d2574 |  | note | METHOD: Visual
label | 9e80d056-7b23-4a90-b154-499fad9ec925 |  | note | ---------------------------------
label | 4090b57f-ebda-4b1c-aa12-2d30449dfa41 |  | note | FREQUENCY: Each lot
label | 73ca87a0-43ca-4a0c-b7ff-51e3df0dd7da |  | note | ---------------------------------
label | b14e0b59-ae49-4e32-8555-d538ac22dc97 |  | note | CATEGORY: IP
label | 9bea1d17-fd48-435b-a214-1bfa3a81e3ec |  | note | ---------------------------------
label | 40dcade8-7388-408b-bd1d-d9df300bd5ab |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 13a0e570-8a44-404b-8681-64cf81d883d0 |  | note | ---------------------------------
label | 23ad094c-d664-4528-9925-24f5c154f56a |  | note | VERIFYING DOCUMENTS: This ITP
text | 49dca3e2-f582-4a91-8784-883356f67108 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.17 Footpaths - Crack-control Joints / Weaken Plane Joints
label | 64f963aa-862b-4b19-bc06-7f04c0f39949 |  | note | REFERENCE: IFC Drawings
label | 7fea3f59-4c1d-43ab-a13c-7ffcdbd6643e |  | note | Relevant Council Drawings
label | 384f4c70-da54-49e8-a9ae-fe1d3e7fb111 |  | note | 703.26 (b) (ii)
label | 0cc71b7c-bb9c-4801-bac8-c891bc6ae928 |  | note | ---------------------------------
label | 45de53ed-f8e4-4f84-b634-f71416ac8cb9 |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | d66bffba-eba3-4cbe-99ca-8444719c117a |  | note | ---------------------------------
label | 404a9cbc-123e-47d1-b8a4-7fe1b9ed368c |  | note | METHOD: Visual
label | 6310a602-d836-416f-905a-618dc846d942 |  | note | ---------------------------------
label | b34e0580-7733-4e44-a3c0-164c7ba61042 |  | note | FREQUENCY: Where applicable, each lot
label | 16037c93-d3e4-498b-a56b-69c64eff7f81 |  | note | ---------------------------------
label | 6208e728-fe57-4d2b-8cb1-d36cf1bea11a |  | note | CATEGORY: IP
label | 3801d0e6-1c46-4278-9b8c-7d0d60a1ab26 |  | note | ---------------------------------
label | 3da3b8b5-e572-4694-82d4-c95c67c195b9 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | ec03de9e-7692-4452-8709-dc9c8d7668f0 |  | note | ---------------------------------
label | daeb937f-6fa4-4729-a6bc-730c102438e5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9309b48a-bbec-4e09-b9e6-d633787de0f2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.18 Curing
label | 485aef1f-8478-4b17-b0ca-4709ab76c356 |  | note | REFERENCE: 703.10
label | 88e0876b-bc27-4631-bc9c-459f1c30d1ce |  | note | ---------------------------------
label | 8bc1e2a7-826c-4e20-b81d-37d2bc7e625d |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | d204bf06-182b-4689-b84d-44a07cdabf28 |  | note | Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | 15bda626-f01f-43d6-af6c-e36bee8485f9 |  | note | The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | 6ced64a2-277a-4c41-9589-120a7c1ab7ea |  | note | Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | 6dfe5247-1ecb-4601-a171-808833eb4821 |  | note | Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | a27a3e84-1e54-4328-9bd9-ae97604fe1fb |  | note | ---------------------------------
label | 9134bd31-6fd6-4cdd-8dfb-ceab7d052178 |  | note | METHOD: Visual
label | f274cd3d-4823-4dbd-856c-c2f4478b449c |  | note | ---------------------------------
label | b36cb175-ae64-4a1a-bef8-5e0571a4a95c |  | note | FREQUENCY: Each lot
label | 0f91a1e6-ca40-4b08-8d87-4af1ba057353 |  | note | ---------------------------------
label | fb10bf21-b3bc-4018-8cee-63fc4957b57b |  | note | CATEGORY: IP
label | 8e97ef09-9572-4ad0-9abc-b51a0aacd32d |  | note | ---------------------------------
label | c5f7b14f-1e5e-46ab-91d3-ee9a27d26e1b |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 5a85ff23-9c00-438b-a628-4950c8fe889a |  | note | ---------------------------------
label | fb72d662-8b02-4481-af58-798669dff24f |  | note | VERIFYING DOCUMENTS: This ITP
text | 7e1dd554-39d1-4b6c-819b-4374690e288d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Shared User Paths - Crack-control Joints / Weaken Plane Joints
label | 4db81c05-992e-462f-aa19-7f9e15dfde41 |  | note | REFERENCE: IFC Drawings
label | 09438a51-2ace-4a35-9f7a-b1663e4cb2a0 |  | note | Relevant Council Drawings
label | b72ab755-5af7-4321-b42e-35c5ae79faab |  | note | 703.26 (b) (ii)
label | fe0e1375-9228-4e94-8b5c-84d926a3048a |  | note | ---------------------------------
label | 1a4d831e-de74-4985-bf38-bfb978fbc52c |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | affd4dc9-fcd4-479d-9238-3e2eed2bf50f |  | note | <20°C = within 24 hours of finishing operations
label | 0b47951d-3571-408e-87e1-ebf1d6230042 |  | note | ≥20°C - 35°C = within 4 hours of finishing operations
label | e0cfff4d-a460-42f6-8cea-c39b16da77fb |  | note | ---------------------------------
label | c4cd04c3-a24b-4a6d-8947-2a309e8ae8d9 |  | note | METHOD: Visual
label | bae22746-8bd1-487c-a92d-9ce5807249c9 |  | note | ---------------------------------
label | 3826b251-b8f6-4658-83c4-c96cc378bc87 |  | note | FREQUENCY: Where applicable, each lot
label | e1af0a4b-118c-4fe4-b41e-fced47bc802f |  | note | ---------------------------------
label | 93042168-1017-498e-93c2-80d32195ad17 |  | note | CATEGORY: IP
label | 9d117c72-6da0-4d3c-a377-a225d34a9c29 |  | note | ---------------------------------
label | d3ed40f3-ef2b-4111-84a0-0f6a8c97b6e7 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 9024d6e8-ee54-4452-a1cd-8381f0a4183e |  | note | ---------------------------------
label | 8703155c-56ef-44ef-9c87-292cc28070b7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 35ea482d-b8e4-4e19-8dc3-323f3540d61a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Protection of Newly Poured Concrete
label | 54fb3045-f98c-4f7a-8df8-ea6e43e76e1e |  | note | REFERENCE: 703.27
label | 469da08b-ccfd-4f8d-a578-f1904ee47e8a |  | note | ---------------------------------
label | 7e138c7c-23e6-4766-9fd7-a5668db01169 |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | 723ab6b5-406b-4f81-82f2-4213ecf49021 |  | note | Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | 25c67cb3-38bd-4a81-b860-a9836fd7cf7b |  | note | ---------------------------------
label | b250271a-3820-47cf-9773-c85820e774cf |  | note | METHOD: Visual
label | a47c30d7-80bb-4cd2-92bf-be32782deb90 |  | note | ---------------------------------
label | 65a2fe2f-5606-45e3-bfbc-7be18268117b |  | note | FREQUENCY: Where applicable, each lot
label | 5b6cbef4-3a3d-4fd0-9001-f7a5b60952d9 |  | note | ---------------------------------
label | c198a0be-e9f1-4cd2-b975-51548113b499 |  | note | CATEGORY: IP
label | 665113a8-c867-46cd-ab45-bb26679d1eed |  | note | ---------------------------------
label | 2b488a29-8128-45c4-9716-5682283d8c81 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 976bc07e-da1e-4aeb-a720-0f333cf41211 |  | note | ---------------------------------
label | 7bc8456d-2c0c-4cc9-8010-6fbdf5e296a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | ac3eb064-8d0c-4e1a-acf7-ff3a6bbbc211 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Stripping Formwork
label | 95cc24b1-5ced-4a6e-972b-6e9349917f92 |  | note | REFERENCE: 703.12
label | 8b1ffcfb-c2e9-4a2d-85c2-4579cd53f820 |  | note | AS3610 Table C2
label | a4c04337-7e55-4dd3-88ac-ce47b92d2465 |  | note | ---------------------------------
label | 297729a1-d561-496b-bd4b-066c5c20d0b4 |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | 018edb1b-3b83-43f1-a3b1-15dc57227903 |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 1e0111f9-5534-4345-bed1-217450d7eed7 |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | 7c8fd4af-9061-4fe0-a6bc-fa0c5e95824b |  | note | ---------------------------------
label | f44207d5-7971-4bbf-a035-a04d27042175 |  | note | METHOD: Visual
label | 010310e7-95a1-4214-aa5c-2ca7ebb75662 |  | note | ---------------------------------
label | 2e80a7e6-6a38-417d-87ae-6299d4afe10f |  | note | FREQUENCY: Each lot
label | 176a9546-942a-42bb-91bd-b33b7f92f4ba |  | note | ---------------------------------
label | 4ce83a9f-634b-449c-a130-bf62716c387e |  | note | CATEGORY: IP
label | 7beba316-0626-4ed0-b4b7-906b46f9fd56 |  | note | ---------------------------------
label | 2b967e4e-632b-4bb9-9495-ac00ed669313 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 4479ecd8-3326-42e5-892d-2c4578e420eb |  | note | ---------------------------------
label | 8515b9d0-90b0-44b5-8a0e-1bf00c984fd6 |  | note | VERIFYING DOCUMENTS: This ITP
text | f2389f4e-8532-4d4b-894c-30b1283b0e4e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Backfilling & Pavement Restoration
label | 6d3af3fb-e00c-4553-9644-fdbf32262536 |  | note | REFERENCE: 703.29
label | b0975ecc-1aaa-427e-8b6b-97cc4b10782f |  | note | ---------------------------------
label | 2a12033b-16d5-4dde-ad37-ef57a756f606 |  | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | 9700f11d-ef61-41a3-af93-b1481ea8a2eb |  | note | ---------------------------------
label | 19210ec2-3c7a-40fa-bb0a-f60864885568 |  | note | METHOD: Visual Measure
label | dbe031c0-3740-4ca2-9123-f1114b56e479 |  | note | ---------------------------------
label | d45aec0d-2b14-48f2-8e98-6e3472307e2b |  | note | FREQUENCY: Each lot
label | 61017d6b-31be-49f0-b819-e9ae12496670 |  | note | ---------------------------------
label | 6fbf4428-05af-4f02-b049-da7d700b456a |  | note | CATEGORY: IP
label | 733fb704-bd87-49d4-9757-ce24c59631f9 |  | note | ---------------------------------
label | b23fd233-e562-4b7d-9594-6c9bc2129f15 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 63806d57-0b64-404a-94cc-a05056975f73 |  | note | ---------------------------------
label | 52c40a15-cd32-43c4-bdfa-81f1869b77d8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 74358a52-4042-4a93-b97e-f5205ece998a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Surface Inspection - Cracks
label | 59dbbfbe-6252-4b30-a4de-b1deb0e9d19b |  | note | REFERENCE: 703.3
label | a88b44ec-cdcc-450e-adee-8a04d7320c1f |  | note | ---------------------------------
label | 7c87eff9-8e74-4ff4-a5c1-740ca063648a |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | 00dba02a-4cc9-4053-bf30-8bc785e19a48 |  | note | If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 488bd310-04cf-4f5b-b092-76603bac0567 |  | note | ---------------------------------
label | 7b552a01-9f31-404d-bebd-2739f9b7b00c |  | note | METHOD: Visual Measure
label | 5a5c5078-b2ee-4016-9823-c0d7cdf41c87 |  | note | ---------------------------------
label | 17704da6-44a4-49dd-8d6f-ca029275a429 |  | note | FREQUENCY: Where applicable, each lot
label | 4ca6637b-d6ef-442b-9073-580b87e45208 |  | note | ---------------------------------
label | d5ed1ddb-b990-481f-b353-dfabb23a1924 |  | note | CATEGORY: IP
label | 5e06dd50-167b-410b-830c-c22ae3c78735 |  | note | ---------------------------------
label | d8997b01-c314-47d0-8660-c62d2010637b |  | note | RESPONSIBILITY: SE/PE/SPE
label | f86d4c0e-8213-47d5-a255-baf9314f20bc |  | note | ---------------------------------
label | 11ebf972-7d6b-4bac-8ea2-e4bdd9f32bff |  | note | VERIFYING DOCUMENTS: This ITP
text | d73e9da8-0730-4ad5-bf6b-3caa69850e96 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Surface Inspection - Surface Finish
label | cdd21917-84da-476b-a979-bd2fe1080211 |  | note | REFERENCE: IFC Drawings
label | 5713a263-b854-425d-aca0-87bba5076e55 |  | note | Relevant Council Drawings
label | 8d7eedad-1413-4636-ac61-d8ad9408f50a |  | note | 703.25
label | 7cfbe4f4-14e3-4df8-a2e6-cee3b22f617a |  | note | 703.10 (a)
label | ab41d125-1cff-4ae4-82d5-df43adddc4b5 |  | note | AS3610 Clause 3.2
label | 5ecf69ca-af9f-4fb0-8705-57b7440f8e0a |  | note | ---------------------------------
label | 8f8576b8-a42f-45c2-b5fa-1f16f3bc63e3 |  | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | 1a778e90-0460-440b-9d71-54fd06e90c10 |  | note | All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | 918d190f-ec32-4282-a76b-abe9ffff9168 |  | note | Class of finish:
label | c57fd7ae-50de-453a-8a58-d6d8971ccfe1 |  | note | Permanently hidden surfaces = Class 4
label | e5c693bd-e7f4-443d-9385-d4924967287e |  | note | All other surfaces = Class 3
label | ad17da5b-141c-4149-abb0-ea3a8728f9fa |  | note | At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | 1d6f5d74-b1ad-4d8a-b8d2-ff1a98b1b9e1 |  | note | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | a1e33922-6c13-44cb-aab2-659e3baa06c2 |  | note | ---------------------------------
label | d58be3bd-af23-4b0a-8acf-5ce100f743e3 |  | note | METHOD: Visual
label | 64a65f9f-e922-48a2-9d09-eeefd577cfe2 |  | note | ---------------------------------
label | 624994a0-32ec-4c34-baaf-c0b3ecbf9931 |  | note | FREQUENCY: Each lot
label | 7da714c5-e630-4a0f-99d4-8f907cfb477b |  | note | ---------------------------------
label | 838e75b9-2666-45fb-bc3d-d50e9b2c6dd4 |  | note | CATEGORY: IP
label | da1c0495-eb8a-4ee4-b633-4b7b109f8de5 |  | note | ---------------------------------
label | 0c29f78e-7515-4f95-ad79-cc200770fa3f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6f1a86c6-1bf8-401f-a767-42051cdc88f8 |  | note | ---------------------------------
label | 0d8810d3-f2e6-4a1d-8743-85397cbfcd6b |  | note | VERIFYING DOCUMENTS: This ITP
text | f78f34de-db6c-46dd-92fa-0fded934a78b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Compressive Strength Test Results
label | c75082fb-d9f3-4cdf-a539-b13b0de5814c |  | note | REFERENCE: IFC Drawings
label | ffee21b5-8471-4317-a94d-d1f2fca04963 |  | note | Relevant Council Drawings
label | 1efc811c-1c8a-433f-bc41-1a7b95d78036 |  | note | 703.11
label | 74301988-cc42-481f-af65-78619949dea7 |  | note | Table 703.111
label | a8cc1daa-46da-4c58-b17f-1b96a4f151c9 |  | note | Table 610.05.051
label | 9122a58e-fe12-4ad3-a6f0-d9f3e851757c |  | note | 610.16 (g)
label | f6a45213-1f44-43fa-ab7a-8d403321dc33 |  | note | ---------------------------------
label | 871ccb66-1a39-45ab-93d2-011dcf27d9d2 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 4eaaba3b-4a84-48fb-9392-0e9ccf75732c |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 6f21e462-2718-4eb2-8a7f-ced001c2ce64 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 2ba76453-2c0c-414c-bc6d-b34dc700543b |  | note | Attach: Compressive Strength Test Results
label | f4d503f2-17c3-4682-a677-6efd42debcf3 |  | note | ---------------------------------
label | 7b8d25e2-774e-4be3-86fe-386dbef6f19f |  | note | METHOD: Document Review
label | 740d0ef9-ef57-422f-a40f-34ce8da03cca |  | note | ---------------------------------
label | b1118b3a-e422-46ab-acdb-0ac1e2a8cd37 |  | note | FREQUENCY: Each cylinder
label | f3ad8899-52ba-4c16-9ea7-3c3669f52542 |  | note | ---------------------------------
label | 51fea423-b8f2-4779-a9bc-9af117a81b98 |  | note | CATEGORY: IP
label | 4e6bffcd-6a7d-4ff6-8615-c7850c77a83e |  | note | ---------------------------------
label | e8b0531a-b8d3-4c5b-aca1-43ba5d1fcb83 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 42bc3c6f-5749-4e3e-95ef-37705a2cb5f3 |  | note | ---------------------------------
label | c074936e-7d88-48e6-86d5-1ff1b26069f6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 006206ce-b6e3-41a1-ac9f-e38ce8ca7641 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 As-built Survey
label | 64c19e66-411f-4853-bbb9-096c370cc76a |  | note | REFERENCE: IFC Drawings
label | e9199fd5-3faa-44dc-a20c-0ca57104b99c |  | note | 703.15
label | 97cf50d0-f155-42a4-8fb1-b867e733727b |  | note | ---------------------------------
label | c5d01b77-2003-40ef-8440-98d4bcb335f8 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 7cfcc8c0-e952-4ff9-b790-b02bdd49a5c1 |  | note | Departure from RL = ±10mm
label | f345d4e6-67dd-45cf-944f-564455f81d49 |  | note | Departure from alinment = ±10mm
label | 18b74f97-b8aa-4864-b85a-861121ea9a51 |  | note | Rate of change of deviation from RL or alignment = 10mm in 10m
label | 0f75b926-d5af-4b90-ad1a-03f5be4370d0 |  | note | Irregularities in alignment = 5mm in 3m
label | 6d9792a8-6752-4d94-9375-7bc134100d0e |  | note | Section dimensions = ±5mm
label | bac1b74d-e252-4989-af2a-12ade8618f34 |  | note | Section dimensions (less than 25mm) = ±3mm
label | 5f64096f-3aee-457c-9356-e934ca20dd34 |  | note | Width of pavement = -5mm, +15mm
label | 4decf30b-7569-46c8-93d1-f7ed5d723fc1 |  | note | Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | 4cfbcd81-2f81-4b09-a019-66b78f02807f |  | note | Attach: Survey As-builts / Survey Report
label | 3f367b6a-a768-464f-bd32-7a76e301f00f |  | note | ---------------------------------
label | 81e33656-8200-4b9c-b7d7-9a06700f3f9b |  | note | METHOD: Document Review
label | 37a9515b-70bb-4eb1-93b5-20949e472c99 |  | note | ---------------------------------
label | fafdf3a0-133b-4ff4-809c-b0d47e6568c9 |  | note | FREQUENCY: Each lot
label | de5ec7f7-4f70-4214-97fa-95a0783b4a86 |  | note | ---------------------------------
label | aaf3270d-cd45-472b-a4a8-fb728937c108 |  | note | CATEGORY: IP
label | a1862260-42f8-46e7-8a87-f061dc9eb7eb |  | note | ---------------------------------
label | debf573b-8563-475d-a7e7-8fd3db7f4ca9 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | c0590937-f8fd-4690-8958-f943cf81453c |  | note | ---------------------------------
label | 21c141c3-87ee-4f09-b8be-5c8f6b68f3d9 |  | note | VERIFYING DOCUMENTS: This ITP
text | f96cdbc8-151f-402b-82d9-0801ed1ba6de |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Non-conformance Report (NCR) Closure
label | cadd873a-3758-4d0f-a3f8-6ef27c5d16a4 |  | note | REFERENCE: MRPA Quality Management Plan
label | 426005b3-c52c-43b1-a2d8-d31261bf5257 |  | note | ---------------------------------
label | 7cb42884-34b4-455f-a906-ce795f8461d0 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 82b869ab-b3c5-49f8-8543-0318bbd187b7 |  | note | ---------------------------------
label | d273a224-79d5-43fb-be8b-4da74b907900 |  | note | METHOD: Document Review
label | f0a8bb67-a669-4142-95cf-0b3f92b3be32 |  | note | ---------------------------------
label | fdda1af0-03de-436d-8d7d-14815b1aa9b9 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 308e0049-bb1b-424e-93e1-291f27f01d6c |  | note | ---------------------------------
label | 1575c9f5-549c-44af-a25b-a964c67dc569 |  | note | CATEGORY: HP*
label | d08afadd-58a8-4058-a4c7-b2a636d4320f |  | note | ---------------------------------
label | dc9ccf62-fff8-4c66-9a3b-86377deb1ee8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 794172ca-2b98-41ee-9c63-7e240d2f0e90 |  | note | ---------------------------------
label | 20c010f8-e32c-437c-9f38-2818892e51dc |  | note | VERIFYING DOCUMENTS: This ITP
text | 5b63d1a0-3740-458d-8933-bfad9c0452e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 65ec7487-bd98-44fd-b520-6927eaf51f60 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 464d14b7-e453-4495-8d05-ec0c76d6994c |  | textbox | Name:
text | 07876364-c447-477c-8fd2-653cba96b68b |  | textbox | Position:
text | 691f382b-b161-47cd-ac0c-c549cb97766f |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Bonded Anchors (100 Year Design Life) Rev 0 | itp |  |  |  | Yes | ITP-STR-Bonded Anchors (100 Year Design Life) Rev 0 | 8e558b82-d6b5-4385-ad68-33d63affa1b9
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | d2d489cc-6448-44e3-9811-783c443aa6a8 |  | note | Document Title: ITP-STR-Bonded Anchors (100 Year Design Life)
label | 704ebcf8-ec1b-4e44-828a-eda063dbea9c |  | note | ITP Description: Bonded Anchors (100 Year Design Life)
label | 7b1146c0-7395-41da-809c-bc8b7a613d62 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 7bf7cdfd-0916-4b19-87fa-698fb8cb5143 |  | note | Revision Number: 0
label | 173ad3ef-4e9d-44dc-bf5d-5b0d1312a33e |  | note | Revision Date: 12/08/2021
label | 84778511-7e29-42d5-b7a5-4fd7d35c7659 |  | note | ITP created by: Mike Freeman
label | 6e98b237-ced3-48e6-816b-7e5ca7f447cb |  | note | 1.1 VicRoads Section 680 November 2018
label | 953cd13a-d534-415b-825c-2bac56abdd40 |  | note | 1.2 VicRoads BTN 006 January 2018
label | 7419f549-0e54-400d-b4f3-7a074d181b31 |  | note | 1.3 Teambinder Correspondence Number MRP-MRPA-GNC-XDM-1346
label | 9e25ca41-c33e-4db2-9bf1-5ad962586c42 |  | note | 1.4 Teambinder Correspondence Number MRP-MRPA-GNC-XDM-2385
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bonded Anchor System - Chemical Adhesive
label | f2808601-d449-4803-b42c-48b00ef4791c |  | note | REFERENCE: IFC Drawings
label | 4c5bd2c7-9ff5-40c6-abda-d623a8e935ff |  | note | 680.05 (a)
label | d39c2cf9-efef-401f-9db9-893453cccf60 |  | note | 680.05 (b) (i - vi)
label | ae8da5a9-7942-4c16-9180-56493219bc19 |  | note | MRPA-RFI-00660 & MRP-VICR-GNC-XDM-0052 & (Robinsons)
label | ae6ff5b4-104b-4c22-b730-9c7f920c6bce |  | note | ACCEPTANCE CRITERIA: Bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
label | f0fac3d8-655c-4501-91a5-6d6a09cf09f1 |  | note | i. ATIC SPEC 38
label | cce9a6f1-e172-44de-be1e-1744a1af24d9 |  | note | ii. EOTA EAD 330499-00 or 01-0601
label | fda66902-fe13-4282-9b6b-04b41ac18a73 |  | note | iii. ICC-ES (USA)
label | 0e69d0c9-9b5c-443f-b2d5-40cb963c732f |  | note | Note: MRPA has D.o.T direction and approval to use only Hilti HIT-RE 500 V3 or Iccons BIS PE Gen 3
label | f1ca961f-2e30-4fc8-959f-88ee97bedfd1 |  | note | Teambinder Material Approval number:
label | 350b235c-cf9b-460c-9f80-fe9f8d5d5c91 |  | note | MRPA-MA-000192 (Hilti HIT-RE 500 V3)
label | 766b210d-1297-4459-a62a-cacf9288ef61 |  | note | MRPA-MA-000275 (Iccons BIS PE Gen 3)
label | 3cf5bb17-82bc-46d6-98d4-2e4d2bc0d376 |  | note | METHOD: Document Review
label | aa4b3a6f-1cb1-4db0-b627-aae8ec2f8a3a |  | note | FREQUENCY: Once, per product, prior to commencement of Works
label | a2f07542-d52f-4908-b216-35b5427b585c |  | note | CATEGORY: WP
label | 6114926a-152c-48de-aabe-69c707752e6e |  | note | RESPONSIBILITY: Nominated Authority
label | 3d0454ed-9076-40c6-866c-fb8717d9e231 |  | note | VERIFYING DOCUMENTS: This ITP
text | 86769757-b70e-4b83-b86c-568bf7e9d16d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Bonded Anchor System - Reinforcement
label | c3c05ad5-2226-4fa8-8f19-a82709422293 |  | note | REFERENCE: IFC Drawings
label | 498da3d3-e4e0-4730-88a7-ae86153ab7e8 |  | note | 680.05 (c)
label | a2421e68-96af-4092-a530-587f203f8062 |  | note | 611.05 (a)
label | 46cfccb6-168b-4ac0-932f-55a1f31ed612 |  | note | ACCEPTANCE CRITERIA: Where applicable, current ACRS certification for materials and for bar processing.
label | 173a0b4b-306a-4053-a72f-47d18edf0f1d |  | note | Anchor bars need to remain uncoated (black) for durability purposes.
label | b1c7ca3b-88fa-456d-9c8a-fa39f0bd83a1 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 91223d6f-895c-4b92-be32-9df14fd0d5d1 |  | textbox | Enter: Teambinder Material Approval number
label | 776df62b-45df-47d5-8ff7-d709668d9259 |  | note | METHOD: Document Review
label | c95a8b0f-2560-4877-bb57-3285885d9173 |  | note | FREQUENCY: Where applicable, once for each supplier, 14 days of award of contract
label | f1549784-2b73-40e4-b662-5c158c2b1b54 |  | note | CATEGORY: WP
label | b63da408-d935-4fa8-ba1c-c99257afc73b |  | note | RESPONSIBILITY: Nominated Authority
label | 8e01ccc8-4b00-4d1c-85ef-5554f0d424c6 |  | note | VERIFYING DOCUMENTS: This ITP
text | d614f767-b3aa-45b9-80a6-d4386bb13726 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bonded Anchor System - Stainless Steel Anchors
label | e43cb656-48c8-4c31-a621-3545e0d83166 |  | note | REFERENCE: IFC Drawings
label | 0e895f13-8f8a-40d6-b474-42afcbb14467 |  | note | 680.05 (c)
label | c0f9bd24-763e-4c36-a975-d4e1caade236 |  | note | ACCEPTANCE CRITERIA: Where applicable, stainless steel grades 1.4401, 1.4404, 1.4362 and 1.4571 (marking A4) may not be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
label | 9d26de5e-2d6a-4aaa-9730-1d56fad92bff |  | note | Stainless steel grades 1.4529 (marking C) may be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
text | 7d2a8d73-db64-4d27-ab9a-dc23e3f1fbd2 |  | textbox | Enter: Teambinder Material Approval number
label | f7ac8be9-1a71-44e1-8e11-8fe7dd87c781 |  | note | METHOD: Document Review
label | e2c872a6-1e59-45e4-907b-9e932b823c04 |  | note | FREQUENCY: Where applicable, once, prior to commencement of Works
label | 7955ab5d-c603-4e7e-91c5-128564299a53 |  | note | CATEGORY: WP
label | b958ef62-0c31-45f1-9324-3b7c17bdb613 |  | note | RESPONSIBILITY: Nominated Authority
label | 00881015-45dd-4384-9b51-4488bde73e5f |  | note | VERIFYING DOCUMENTS: This ITP
text | 4861a16d-1575-40f3-bfa4-a8d439f0daf8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts
label | 4217fa6f-e8e6-497d-a254-35955f290580 |  | note | REFERENCE: IFC Drawings
label | 2e176d4b-3bc6-49d5-a96f-20ae35a77a9e |  | note | 680.05 (c)
label | 3cd9c7b2-0612-436b-9096-646a269d5c47 |  | note | ACCEPTANCE CRITERIA: Where applicable, bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
label | 2942f8ba-dbdf-4494-aa25-aba748e5d9e4 |  | note | i. ATIC SPEC 38
label | 805bba6f-65ea-45db-b120-a6764b847ed8 |  | note | ii. EOTA EAD 330499-00 or 01-0601
label | cbfe1d3e-51cf-440e-8673-0ef7b0bd4637 |  | note | iii. ICC-ES (USA)
text | 0b15ae54-e827-41c8-8a00-f43279174d44 |  | textbox | Enter: Teambinder Material Approval Number
label | 1a350091-5709-4a49-a47c-7829018240a9 |  | note | METHOD: Document Review
label | 239dcb12-8f67-435f-a7ab-12f38e949df2 |  | note | FREQUENCY: Where applicable, once, prior to commencement of Works
label | 12289c61-b30e-41a2-9ecc-e096abe22d41 |  | note | CATEGORY: WP
label | a403d969-5105-494f-a581-cece72e7063b |  | note | RESPONSIBILITY: Nominated Authority
label | 522e8c21-c27c-4106-93be-4764bcee1b5b |  | note | VERIFYING DOCUMENTS: This ITP
text | b4c04a22-97e0-44ed-8f84-005ae221cc33 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Alternate Product or Changes to Existing Product
label | fa69e083-2fe7-4050-9bb7-2830d6e9fd7d |  | note | REFERENCE: 680.05 (a)
label | ead236c4-f75e-42df-8c5e-50ac9d08ab2e |  | note | 680.09 (b)
label | b6289ccf-ab99-489a-9700-09f9348a3168 |  | note | ACCEPTANCE CRITERIA: Where applicable, if an alternative system is proposed, where a bonded anchor system falls outside the scope of certification or where directed by the Superintendent, ultimate tensile load testing shall be performed to validate the bonded anchor system meets or exceeds the intended durability and load capacities.
label | 5d445ba8-0b2d-465f-9e24-f0da5eaddc12 |  | note | A sample of 5 no. anchors per combination of adhesive type, anchor orientation, type, grade, diameter and concrete grade shall be installed in accordance with the manufacturer's installation instructions, load tested and results reported by a third-party accredited testing authority.
label | a3d9a2f8-b7bc-4ee6-9da0-597ad87e92d1 |  | note | Results of the ultimate testing to be submitted to the Nominated Authority.
label | cdf03600-46a5-4ec5-a4fd-3eb5b46805b4 |  | note | Note: MRPA designs are following the ETA certification of the adhesives
text | 7217897d-f2a2-48e2-b733-5858fa549518 |  | textbox | Enter: Teambinder Approval number
label | a590d74a-feae-4e64-8079-bf84f276b1a4 |  | note | FREQUENCY: Where applicable, 2 weeks prior to installation of anchors
label | e5c4e115-73a0-47ba-ae5a-15cea9a8299b |  | note | CATEGORY: HP (N/A)
label | a014a460-e07d-4e29-8dea-43b576c3122e |  | note | RESPONSIBILITY: Nominated Authority
label | 0e87eda6-ecdf-4b29-8004-b292ef4020a4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | a051085a-cb36-4afa-846c-bf212e3b69dc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Documentation & Procedures
checkpoint-status |  |  | checkpoint | 3.1 Design of Bonded Anchors Subject to Tensile Forces
label | 0859be97-f359-4df0-8006-91cc5d3ffaaf |  | note | REFERENCE: 680.04
label | fa1fd98d-4710-4f83-bccc-8dcdcc746546 |  | note | BTN 006, Clause 2.6
label | 8729a1c4-6878-4bfb-9b34-6a53bbb1c73b |  | note | ACCEPTANCE CRITERIA: Where applicable, if it is proposed to use bonded anchors in full or partial tension, submit full details of the proposal, including a Proof Engineering Certificate of Compliance, for the approval of the Superintendent.
label | 19d12e52-090f-414d-9695-816966b4e1a0 |  | note | See:
label | 5746fd80-e131-4eb2-a6a3-515dcd18b111 |  | note | MRP-016-C-ACD-REP-17-NWA-CSW-0001 & TRP #181 (Clyde Road)
label | 9c97b366-3cb1-42de-9f6a-8c8815dce975 |  | note | MRP-072-C-AURE-REP-20-DPK-CSW-0001 & TRP #326A (Robinsons Road)
label | f3d174a0-9d58-4f4d-822a-2c469ffc76ac |  | note | METHOD: Document Review
label | cd801670-91d4-4c23-b8ed-b7b99490d403 |  | note | FREQUENCY: Where applicable, 2 weeks prior to installation of anchors
label | 2587a301-6159-4563-98fa-8e858f65d391 |  | note | CATEGORY: HP (N/A)
label | 9152b267-7946-4e09-9da7-c4e7155f1d99 |  | note | RESPONSIBILITY: Nominated Authority
label | 75c6f245-4f2e-40f0-a0f7-3931f7fafe73 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3b8a03e2-7172-49cd-87f3-22d318510e83 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Bonded Anchor Work Method Statement
label | a22f3ea7-1207-4a07-8d08-05fa38845c86 |  | note | REFERENCE: 680.11
label | fa48b3e7-6b31-4517-bfb9-c975c1b1359b |  | note | 680.07
label | 52f185e9-407b-4ca5-829f-28079446ce5f |  | note | ACCEPTANCE CRITERIA: Bonded anchor WMS, detailing the method for locating reinforcement/tendons/services, equipment to be used, load testing regime and repair of concrete (spalled and cracking) to be submitted for review to the Nominated Authority.
text | 51ab810c-19ab-4985-a55e-aa13e95427da |  | textbox | Enter: Teambinder Approval number
label | 325a40f4-72e8-49d0-a3f7-c4fe39aab743 |  | note | METHOD: Document Review
label | 29f53356-3afb-4774-90b2-94d4fa06058c |  | note | FREQUENCY: Once, prior to trial installation
label | ea561620-86f4-41ed-95d0-380524d79f43 |  | note | CATEGORY: HP
label | 19b6e105-3cd0-4782-bfcd-756b2f4177fb |  | note | RESPONSIBILITY: Nominated Authority
label | a58d7bc5-4c7e-4aa5-9317-af9fb6c19a6c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c57cb758-045a-4b9e-9e75-722dcc76fb1a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Load Testing Work Method Statement
label | 5e9b6702-dd11-41cd-8238-088d81169f66 |  | note | REFERENCE: 680.09 (a)
label | 84cf55ef-ccca-4942-aded-0a0dbd984e5d |  | note | ACCEPTANCE CRITERIA: Load Testing WMS, detailing the target loads (1.5x or 2x the design loads), load increments, duration for the load to be stained at each increment, testing frequency, measures if fail occurs and equipment to be used.
label | 2ea48e2b-28e7-4fad-80f4-f31502f9f7b9 |  | note | Additional testing equipment requirements:
label | e22439bf-1fed-4475-99c7-78fd16da1dc8 |  | note | i. capable of measuring the applied force to an accuracy of ±2%
label | 477fd98d-7033-4635-93d3-4ad8e32eda3e |  | note | ii. capable of measuring the elongation with an accuracy of ±0.02 mm
label | df445eca-97b3-4096-a7bb-48222a9c3322 |  | note | iii. have a valid calibration certificate
label | a31f5b98-1926-4a87-8a57-85c79841d491 |  | note | The above is to be submitted for review to the Nominated Authority.
text | ac85e9d3-661c-4fb4-92c7-e1de660a1147 |  | textbox | Enter: Teambinder Approval number
label | 82e5ce77-b042-498b-9e0d-bbb8a3ae327a |  | note | METHOD: Document Review
label | 133212ff-3ecf-4085-9f67-d4f1a7c44aeb |  | note | FREQUENCY: Once, 1 week prior to prior testing
label | 7e175ad3-c4e0-4820-9538-9ad7a16946a8 |  | note | CATEGORY: HP
label | c29e8033-391e-4baf-b31e-f5b992aad7b9 |  | note | RESPONSIBILITY: Nominated Authority
label | 581ce4c0-aba4-464e-87f8-041cd3c79b86 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | fd523449-0f4c-4cd4-8736-1214070168ed |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Competency & Training of Personnel
label | 1784d060-db79-41b2-8405-d67e3c18cb39 |  | note | REFERENCE: 680.06
label | fb1244de-671c-4ab5-a121-d0563dfd83bc |  | note | MRP-MRPA-GNC-XDM-1346
label | 95e53c8a-7b5e-49ee-b4dd-07b706113956 |  | note | MRP-MRPA-GNC-XDM-2385
label | 931bf3cb-774f-4e15-891f-88615ccffb7f |  | note | ACCEPTANCE CRITERIA: All bonded anchor installation crews and direct supervisory personnel shall be listed on the "AEFAC Certified List of Installers" and evidence of this submitted to the Nominated Authority.
label | 37017c57-2db6-462c-82a8-1e30b498f930 |  | note | See:
label | 2455fd4f-45e7-4021-b3bd-56ae5a77f482 |  | note | TRP #181 (Clyde Road)
label | dc1155ff-0d01-490a-be0c-291ff1b89d21 |  | note | TRP #326A (Robinsons Road)
label | 2be6edf6-ca6b-4af5-9b5a-617484e9daff |  | note | METHOD: Document Review
label | 81d8f450-0f95-4239-9e11-7a1a81444632 |  | note | FREQUENCY: Once, prior to commencement of Works
label | 2d22d3c5-ca4d-4417-a0f8-735713a4ace7 |  | note | CATEGORY: HP (N/A)
label | f2ceba81-d17a-4e34-be60-a667a3d79165 |  | note | RESPONSIBILITY: Nominated Authority
label | c3a9a1df-8cf7-4f89-aa8c-78f792937caa |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 7fa7c9b2-2061-4eca-8ba0-3b57b922d00f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Chemical Adhesive Training Toolbox
label | 8a77e17c-12fe-4648-b4a6-7827b350bafe |  | note | REFERENCE: MRP-MRPA-GNC-XDM-1346
label | dabc1f32-6ea1-4402-b16b-aad02f6f90d3 |  | note | MRP-MRPA-GNC-XDM-2385
label | 207423fb-f42b-44c6-a81d-d594f44ad027 |  | note | ACCEPTANCE CRITERIA: Works shall not proceed until a toolbox is conducted by each chemical adhesive manufacturer, covering the specific installation, quality and testing requirements relative to the approved adhesive.
label | 3e4ed5ac-8d2c-4619-a181-75acd583294a |  | note | Minutes of this meeting to be submitted to the Nominated Authority.
label | 39f90fc2-50c3-4005-9212-bd014b718941 |  | note | Note: A D.o.T representative should be in attendance
text | 491e7de0-e1ef-4d09-8da7-81e8e7803d60 |  | textbox | Enter: Teambinder Approval number
label | 0608385b-a4a2-4953-8622-b1c6c16e7523 |  | note | METHOD: Document Review
label | ec67ec2d-2544-4744-a48a-435fcec5541d |  | note | FREQUENCY: Once, for each work crew, prior to commencement of Works
label | 7acee09f-0baa-4af5-96cf-9fa7e2e0172d |  | note | CATEGORY: HP
label | df88f8c0-b61b-4010-b24a-a22cb6c4133d |  | note | RESPONSIBILITY: Nominated Authority
label | 8a65bc1c-0409-4f87-a871-479760b68c3f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 8849810e-b81a-4252-acee-dc8947517aa1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Trail Installation
label | 7258a85d-1d20-4b60-b51a-ff35ee7ca06e |  | note | REFERENCE: MRP-MRPA-GNC-XDM-1346
label | 8f9960ed-136e-475d-94e4-0bf2855713da |  | note | MRP-MRPA-GNC-XDM-2385
label | 9d9ee014-31f0-49f7-b603-4ccb2d742116 |  | note | ACCEPTANCE CRITERIA: Works shall not proceed until each work crew assigned to the project site can demonstrate compliance with the manufacturer's installation instructions by installing a sample of 5 no. anchors per combination of anchor orientation, type, grade, diameter and concrete grade as per the IFC design.
label | 0e54656f-3403-475e-b52b-affa406595f4 |  | note | Where the presence of cracks exist or are to be expected, an additional 5 no. bonded anchors shall be installed in each combination to the above.
label | 872ff902-0a0b-48cb-9961-600f9f1ffa2c |  | note | Evidence of this trial and attendees to be submitted to the Nominated Authority.
text | 3fbe1f3b-7b1a-4f75-b772-a82d2a9d9f63 |  | textbox | Enter: Teambinder Approval number
label | f1ac62b1-d9df-436b-bd55-16da79e9bd12 |  | note | METHOD: Document Review
label | 88a58549-07f1-4ecd-8d8b-5fd54eb7e667 |  | note | FREQUENCY: Once for each work crew, 14 days prior to commencement of Works
label | b3caa865-bd35-4be7-897d-c20d465b9150 |  | note | CATEGORY: HP
label | b3fbdf2d-a273-4266-93ea-fc7c04661c45 |  | note | RESPONSIBILITY: Nominated Authority
label | 339c4f41-0b7e-4443-9132-9c05b9711a6c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b4fef4dd-5909-43b1-9027-ec8a9d4d1ede |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Installation Equipment
label | c4dc6a84-e81b-4596-a51b-1252dcd7f0db |  | note | REFERENCE: 680.07
label | 009603bc-99ff-4e1c-9ee7-55e085a2c801 |  | note | Manufacturer's Installation Instructions
label | 5eb47dfa-6e86-4ba5-ba04-5ec0d490a3eb |  | note | ACCEPTANCE CRITERIA: Bonded anchors shall be installed using the equipment specified by the bonded anchor system's installation instructions.
label | 3f640437-3125-4dfc-bb63-e4c07fb67bf7 |  | note | This includes drill bits / dustless drill bits, diamond cores, roughening tools, cleaning brushes, mixing nozzles, piston plugs and extensions.
label | de32ff01-eeb7-48d6-a9f5-ef8258599a77 |  | note | METHOD: Visual
label | ef629f3f-1619-48b5-b584-f657f573cfe7 |  | note | FREQUENCY: Each discrete population
label | 7f900efa-41af-4c30-ad4b-77ec70fbfec6 |  | note | CATEGORY: IP
text | 9c2c44e1-27df-431d-b9cf-fb9b9a240e21 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 680.08 (a)
label | ca134ed4-d39e-47fc-945d-fced3c035b6c |  | note | REFERENCE: Bonded Anchor Work Method Statement
label | 72685135-f55a-4320-a260-b19bb67975e5 |  | note | 610.46
label | aee638e2-577e-4889-8a39-0be3b553e71b |  | note | MRP-MRPA-GNC-XDM-1346
label | 5db3ee7c-251b-4617-b187-334ba7ea0e54 |  | note | MRP-MRPA-GNC-XDM-2385
label | 2258ef17-ee38-4136-afc2-0b5d9c12a6a9 |  | note | ACCEPTANCE CRITERIA: Locations of bonded anchor holes shall be positioned at the design spacings and angles using a calibrated covermeter or ground penetrating radar (GPR) to ensure that no damage occurs to reinforcement, pre-stressing strand, ducting and embedded services.
label | d96cbfb8-275d-4579-817e-3a2d0c2b23cd |  | note | Where clashes are detected, adjust the anchor spacing locally if able to do so, maintaining the maximum and minimum spacings, edge distance and cover requirements.
label | 47bc4a78-e016-4c65-afa4-220653022395 |  | note | If unable to adjust the locations, consult the designers to provide updated locations.
label | eff770ec-cfb7-40b3-bfd6-baf07ccc064a |  | note | Note: The marked out locations shall be traceable to determine a discrete population of anchors and installed by the same work crew.
label | 066ec360-9ef8-43b3-9537-aa847f050ba2 |  | note | Note: Installation of anchors must not occur until the concrete is both 28 days old and the concrete strength has achieved the 28 day strength.
label | 121c8e20-73cf-4126-ae6d-e5381fabccda |  | note | METHOD: Measure , Visual
label | f18be313-5dc5-4afb-a35c-8826fcf93889 |  | note | FREQUENCY: Each anchor
label | a991d079-fae0-4d9c-bf31-d2cf09d7d412 |  | note | CATEGORY: IP
label | dc721c13-c89e-43cc-b11c-fa53efeeffa9 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 78b3f35a-d001-463e-9806-d81f3e8e16ba |  | note | VERIFYING DOCUMENTS: This ITP
text | cc1f1075-1b0a-4fa0-850f-4fb105735a25 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Hole Drilling/Coring
label | 07d018d6-921a-461a-84b0-e5787f3b9aab |  | note | REFERENCE: 680.08 (a) & (b)
label | 482cec79-2606-495f-918b-a146bfc6a8bf |  | note | Manufacturer's Installation Instructions
label | ad3df634-708f-41a1-a334-ee80e1cebbb2 |  | note | ACCEPTANCE CRITERIA: Holes shall be drilled or cored in the orientations, angles (if not perpendicular to the concrete surface) and depths shown on the IFC drawings.
label | 6d3f8f2a-f185-4a8e-8a9d-a107102549ff |  | note | Drill or core diameters shall be those shown in the manufacturer's installation instructions..
label | 1522f591-d1a6-4491-9dec-d912ce3303bd |  | note | Coring may require the internal surface of the hole to be roughened.
label | 64baa3dc-de5c-4105-a263-44d8f4842c2c |  | note | If reinforcement is encountered during the drilling or coring process, cease drilling immediately and relocate the hole.
label | 1e699e81-e97e-4360-96bb-452ce83a8e33 |  | note | Refer to section 6.4 for repair of abandoned holes.
label | cc194e6c-3dc3-45ca-aadb-3aafba824b5f |  | note | If reinforcement is damaged, consult the designers to provide a clear direction moving forward prior to continuing installation of that discrete population of anchors.
label | 3b25a123-b44f-408b-836c-93c888252ecd |  | note | METHOD: Measure , Visual
label | 9ea34150-ef8c-4e7e-8582-ac842038dd5e |  | note | FREQUENCY: Each anchor
label | 52fa8212-3613-4ab0-bb51-1ef19d5d3c83 |  | note | CATEGORY: IP
label | 5a39d10c-6464-4f60-bfdc-a668186bb70b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 41b9dd98-758f-4b6c-92f8-211d7752bf0e |  | note | VERIFYING DOCUMENTS: This ITP
text | beb6e08b-7689-43c3-bfde-4723325e6306 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Hole Cleaning
label | 976b02ee-7025-481a-8e49-80cc066dd56a |  | note | REFERENCE: 680.08 (a) & (b)
label | ed8d48b5-bfba-4c8b-bd02-25d1590614ea |  | note | Manufacturer's Installation Instructions
label | cdb44286-39b7-495b-93d0-623333556bbd |  | note | ACCEPTANCE CRITERIA: Hole cleaning shall commence as soon as practical following the drilling / coring process to remove debris, dust particles and moisture / free-standing water (where required).
label | 96a1e67f-4892-4cad-9ceb-c4e0a979e422 |  | note | The process shall follow the manufacturer's installation instructions which is a repetitive sequence of brush cleaning and air flushing, resulting in no dust detected on a finger-tip when in contact with the internal wall of the hole.
label | 4ba5d934-2fc9-4ebc-ac01-7712d5e598f0 |  | note | The minimum hole depth shall be verified before proceeding to the next step.
label | b98265c4-87c7-4862-984f-5fe88b76aa3c |  | note | Note: Where hollow-tipped drill bits are used in conjunction with a vacuum drill, cleaning may not be required - consult the manufacturer's installation instructions.
label | 16f52b28-180f-4bc9-9e66-16b23c520839 |  | note | METHOD: Visual
label | 332e41b8-a2dd-4829-a544-f8d2de558957 |  | note | FREQUENCY: Each anchor
label | 6aefadde-a2cf-45d5-98ac-cd465fef3e4a |  | note | CATEGORY: IP
label | 0b0c8575-f9cc-465b-95c8-9767e470836c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0e258782-aec1-40d0-9dc6-e698bd8302e8 |  | note | VERIFYING DOCUMENTS: This ITP
text | d2e7f17a-aef8-4511-a16d-3ab4054fd3aa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Substrate Temperature
label | 38d5e326-e3c4-4f60-99bc-e1f51ae3f0a3 |  | note | REFERENCE: 680.08 (b)
label | 455a0ae7-86f8-4bd9-93da-68ca60489cd7 |  | note | Manufacturer's Installation Instructions
label | ccea916c-8621-4d98-991f-6486d862c99e |  | note | ACCEPTANCE CRITERIA: Bonded anchors shall not be installed where the temperature of the concrete is less than -5°C, or greater than 40°C or outside the limits shown on the manufacturer's installation instructions.
label | fd64e85c-9d8b-475a-b45a-c7660992503b |  | note | Record: The substrate temperatures at the time of commencing the discrete population, the corresponding available working and curing times and the temperature at the completion of installation.
label | c008042a-96dd-45ff-9cd2-a7d090c05287 |  | note | METHOD: Measure , Visual
label | f006b8c1-4887-4c23-b609-21cb00a0d4da |  | note | FREQUENCY: Each discrete population
label | 7b9ca191-1d10-4d08-872d-69c76602110e |  | note | CATEGORY: IP
label | 7702ad41-bb6d-4544-b7df-a22fff82576e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0c307fc4-b372-4edf-b78b-9999c7299ee1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2c345601-2752-4819-8c3a-93563bd146a8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Anchor Surface Condition
label | 694bef54-07f8-464b-bbdb-318aa5643de9 |  | note | REFERENCE: 680.08 (b)
label | 31ba9e44-bdf2-4c7f-8b7b-fb8721ea121f |  | note | Manufacturer's Installation Instructions
label | c048ef17-ab3d-4c05-b527-2d469cf254b6 |  | note | ACCEPTANCE CRITERIA: Anchors shall be clean, free from debris, oil and other contaminants.
label | 9e9339a2-e8dd-41cc-b54d-f2e222b31629 |  | note | Note: Any coatings have been factored into increasing the embedment depth
label | 9aa7fd84-4dcf-4184-8d38-e2a7a8f51a3e |  | note | METHOD: Visual
label | 8b201c0f-5b6c-40d6-8e75-d772ce64c974 |  | note | FREQUENCY: Each anchor
label | b03fd5c3-fca3-4a8f-bc49-00d8310505e0 |  | note | CATEGORY: IP
label | f1e64ce8-a3a1-4cf9-8c0c-e81ccfb5021b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 67068104-e9af-4e62-8dd3-42f21af16499 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4f152f87-f4e8-4448-a7aa-5d65fe80dab6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Adhesive Injection
label | fd08e36a-3ae7-4a43-9b70-dd80cc9694e3 |  | note | REFERENCE: 680.08 (a) & (b)
label | 25bcff37-4a81-4ff2-80b9-b3f48864f941 |  | note | Manufacturer's Installation Instructions
label | 8a4272c1-d779-4926-8f59-16d17df976bf |  | note | ACCEPTANCE CRITERIA: Connect the specific adhesive, cartridge gun and required injection equipment (nozzle, tubes, piston plug and valves) for the task and discharge the initial adhesive to waste to ensure that only fully mixed product will be used in the Works.
label | dd405c39-07dd-48c0-ba4c-df9867d5c089 |  | note | Note: Repeat the "initial discharge to waste" for each new mixing nozzle used and do not modify the nozzles.
label | d0cf7aac-ea87-48e8-85ed-f84e08b77321 |  | note | Inject the adhesive into the hole, starting from the base working towards the substrate surface at a rate that prevents the creation of air voids, until approximately 2/3 of the hole depth is reached, checked visually prior to the insertion of the anchor.
label | 347b2c8d-8f56-4a6d-96f7-4c63c4b5b087 |  | note | METHOD: Measure , Visual
label | 61949107-e854-4af9-a628-9be97f8497fd |  | note | FREQUENCY: Each anchor
label | 1d92ee39-9ac2-4643-a72a-09738c1766a1 |  | note | CATEGORY: IP
label | 7e636d07-9d68-4e42-bc92-9c3783acfc30 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 88d9abb1-5558-472c-91af-67317819e377 |  | note | VERIFYING DOCUMENTS: This ITP
text | e2608463-44ea-47cc-acbf-36fa4324faa1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Anchor Insertion
label | b0d793bf-4f99-4319-8961-c95d4c0c5c1d |  | note | REFERENCE: 680.08 (a) & (b)
label | 0b7b6cf4-34e1-4c11-8b5e-910135682c10 |  | note | Manufacturer's Installation Instructions
label | a55f4d08-1c30-4d06-808a-f43ade0d0a1e |  | note | ACCEPTANCE CRITERIA: While the adhesive is within the temperature dependent working time, the anchor shall be inserted and verified to the minimum embedment depth with a singular twisting motion, to ensure that the adhesive completely surrounds the anchor.
label | 0ce1c348-9933-4a3c-82d1-c7b5a553337d |  | note | Where required, the anchor shall be centralised within the hole using temporarily supports to provide a uniform film of adhesive around the anchor and Excessive adhesive shall be cleaned from the substrate surface.
label | 73969033-8964-4312-b9f7-4e104e73a590 |  | note | Loss of adhesive during the working time shall be prevented by sealing around the anchor as required.
label | 144f1611-acd4-4e05-91e1-408a79bdcc23 |  | note | METHOD: Measure , Visual
label | 62eb4fac-aaeb-4a20-871f-df30e18e163d |  | note | FREQUENCY: Each anchor
label | c3754309-c7d9-4755-a78c-b41a8d1c2ccf |  | note | CATEGORY: IP
label | 0a16916f-24a3-4161-b968-7d1ec82f98f3 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0feea83c-ca6e-49c0-b652-bcc416e42d03 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1dc89f88-3dbf-4096-bf62-e902f7b3d11d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Adhesive Curing
label | d7da090d-07d6-456a-b90b-e273244b79fd |  | note | REFERENCE: 680.08 (a) & (b)
label | fab2e36b-acba-468d-a870-66487bfbce5d |  | note | Manufacturer's Installation Instructions
label | 91c1f701-123e-4d7f-9d9e-b98b2bf045cc |  | note | ACCEPTANCE CRITERIA: The anchor shall not be disturbed, moved, loaded or torqued during the specified temperature dependent curing period before proceeding to the next step.
label | ee30a4c4-6c52-4096-81a7-fe0d1a7dce3c |  | note | METHOD: Visual
label | 999e76f2-4677-43bf-a290-5c852e4f3493 |  | note | FREQUENCY: Each anchor
label | 95eafba7-be6e-4168-9fd2-dabc34ac8f2a |  | note | CATEGORY: IP
label | f6d70263-4e4f-41c8-a843-f20daf3c87da |  | note | RESPONSIBILITY: SE/PE/SPE
label | eeb2bd0b-ef4d-4b17-9cf6-6bbb35b4cada |  | note | VERIFYING DOCUMENTS: This ITP
text | a86e4611-3aa6-4168-8b2a-8b9b49ba78cc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Proof Load Testing
label | 783fa4ed-697b-4a45-b82e-dc5427105c84 |  | note | REFERENCE: 680.05 (c)
label | 8649e5c4-a84f-4e95-a017-b77ad7aadcf7 |  | note | Load Testing Work Method Statement
label | 58752b88-17c6-4732-af00-6c657d9eb9c8 |  | note | Manufacturer's Installation Instructions
label | 714132d6-79a3-4a52-aec1-e7cf3387f90d |  | note | MRP-MRPA-GNC-XDM-1346
label | edcba557-726e-4158-a22f-3df75293216e |  | note | MRP-MRPA-GNC-XDM-2385
label | 45ddc7b0-30d5-4ba8-a04a-594a2c830e2d |  | note | ACCEPTANCE CRITERIA: After completion of the curing period, bonded anchors shall be subject to proof load testing, as outlined in the approved Load Testing WMS.
label | 1552c3d1-68e5-4fe0-aad4-67386c711d1d |  | note | Anchors subject to tension shall be tested at:
label | 7a55aecd-eeb4-4ef3-9377-491ae39344c0 |  | note | i. 10% of the lot
label | 1b91c025-aa20-4753-9f8e-8da0048050b7 |  | note | All other anchors not subject to tension shall be tested at:
label | 28f2050b-5051-4a34-80fe-58339cd161f9 |  | note | ii. The greater of 2.5% or 5 no. anchors
label | 2bbc8a6a-573e-430a-a06e-a6ecc1ac3d4e |  | note | Test results shall be equal to or greater than the factored tensile or shear loads and equal to or less than the maximum displacements shown in the Manufacturer's Installation Instructions.
label | 19f41e42-a4a9-4036-be06-c138cce110cb |  | note | If any anchor fails the proof load or is displaced beyond the limits, the entire discrete population shall be tested for compliance.
label | 020abd94-f6df-4abc-92f5-a022507ec293 |  | note | Refer to section 6.2 if the entire discrete population fails.
label | 7a2db1e8-46b6-4829-af4a-86210f23f3a1 |  | note | Attach: Proof Load Test Results
label | 5b367589-e619-40fc-a6eb-57dd6508187d |  | note | METHOD: Document Review
label | ddf48462-13c8-4892-a5c9-1fe8759fee4d |  | note | FREQUENCY: Each discrete population
label | 44822ce0-5235-4131-a4e1-8b95ce0d8697 |  | note | CATEGORY: IP
label | 8016f675-d5c3-4b55-95dc-804900f90844 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 20b30354-b682-468c-bb1b-c856554c9238 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4beb61a3-1eb1-4064-a590-cebbbcb6e8e4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Failure of Proof Load Testing
label | f91bd294-98f5-4a6d-922d-c37158939b9a |  | note | REFERENCE: 680.05 (c)
label | bc454de7-06c8-48d2-8d39-172e4d9eda39 |  | note | Load Testing Work Method Statement
label | 2fbcf37e-6ce8-4d6b-9f60-a7a3cddf16f4 |  | note | ACCEPTANCE CRITERIA: Should an anchor fail an ultimate tensile test, or an entire discrete population fail a tensile proof load; rectification proposals must be provided to the Superintendent for assessment prior to any further installation.
text | 16033bed-eb33-486a-8821-92fd77b8a461 |  | textbox | Enter: Teambinder Approval Number
label | b54368eb-8204-45fc-91e5-45a74828c847 |  | note | METHOD: Document Review
label | a0a9a7d4-2e98-4185-9c4b-5e81ba54e665 |  | note | FREQUENCY: Where applicable
label | d2e3cf3b-ac7a-4cfd-8170-0f65c22eca1a |  | note | CATEGORY: HP
label | bbeb7047-e7cc-4877-b94f-a62ef10bc661 |  | note | RESPONSIBILITY: Nominated Authority
label | 9ed5017e-0a92-4686-9f8c-fd975161fe82 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 13872398-ac73-495d-aa42-506bd47c854d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection - Cracks
label | 5bd67bca-5dcc-47eb-8e77-33ed2e94aa93 |  | note | REFERENCE: Structural Concrete Crack Repair ITP
label | c5eae7a1-05c7-4e9e-ae3d-12bc2931f3ec |  | note | MRP-MRPA-GNC-XDM-1346
label | 6e698ee5-a568-46dd-914a-ccf1420102fc |  | note | MRP-MRPA-GNC-XDM-2385
label | a39e6504-b550-47a0-8bd6-bc575be288ee |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.1mm.
label | 3adb596e-904e-433c-95a8-6fbbe7eed13f |  | note | If cracking is observed follow Structural Concrete Crack Repair ITP (Specification 687), for investigation and repair but repair methodology MUST be via the injection method.
label | bbe0dbc5-8780-47e0-8439-009a9e9eae28 |  | note | METHOD: Visual , Measure
label | 257956f1-9f74-4093-ac49-67a4e0f2394e |  | note | FREQUENCY: Where applicable, each lot
label | 80c9cdea-9a35-4303-b1b9-5a2996c2cc78 |  | note | CATEGORY: IP
label | 6ff94c39-bc60-4b0f-a3f5-3a6540b9cced |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8e2b339e-8529-440c-a5f8-de4a29b9dff0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 60de2fb0-6b8b-4fcc-ab18-2c5edd801580 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Abandoned Holes & Post-testing Spalling
label | 5353ef77-7713-4ca1-a19d-895362d5e80b |  | note | REFERENCE: IFC Drawings
label | 12f6796a-ce8a-4a23-86e7-496f5d4249a9 |  | note | Structural Concrete Patch Repair ITP
label | 18afee94-027d-42dd-93a0-c048c5b6cf16 |  | note | 610.31 (a) - (n)
label | bb981c20-fff4-4e2d-9e22-82c5c5e606fe |  | note | 610.32
label | f4aaca53-4356-4603-9354-a4f06d323bd9 |  | note | ACCEPTANCE CRITERIA: Where holes have been abandoned, follow Structural Concrete Patch Repair ITP (Specification 689) for repair.
label | c5625dd2-f233-47cd-8dd5-63b62f11666f |  | note | Where spalling around a tested anchor has occurred, preparation of the repair shall follow the Structural Concrete Patch Repair but the repair may allow for the newly cast concrete to create the cover.
label | e4291d46-58cc-4af8-b398-f21956c63785 |  | note | METHOD: Visual
label | d9f44671-f5a3-46a0-a16f-f69a822661ef |  | note | FREQUENCY: Where applicable, each lot
label | 6d4e8828-43ae-40fd-8e9a-a66e326b27ac |  | note | CATEGORY: IP
label | 8a8123f6-fa39-4baa-9f57-3f74963023ad |  | note | RESPONSIBILITY: SE/PE/SPE
label | d4db0e83-e136-4356-b765-2e80a84c0178 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7f5fcd29-2a3e-402b-8fbe-5b2bacbd1701 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Non-conformance Report (NCR) Closure
label | d6171eb7-42b4-42b7-9eb8-f3b5e1586ea7 |  | note | REFERENCE: MRPA Quality Management Plan
label | dc3a43fd-c828-467f-8d73-6827068b3b7c |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 127e2cdd-2a4f-451a-b1d8-a3d086b9738b |  | note | METHOD: Document Review
label | 8736dd0e-17ca-42ba-8104-7745b902c63a |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | a1b4d2a4-2c06-4490-93ed-febdb714054d |  | note | CATEGORY: HP*
label | b16815c6-137d-4bf5-9c12-7287374c2ce1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d95082d5-c68a-45b2-81b7-1dea1d7842a4 |  | note | VERIFYING DOCUMENTS: This ITP
text | e14ad00d-cb03-4566-9437-f575419f9d84 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | bf7f0aff-6957-4dc6-8fda-02f5009b761a |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5c3f4d30-76bd-4730-835b-1348bcd24694 |  | textbox | Name:
text | cdfe5fab-05b5-42c7-b631-832b3793694f |  | textbox | Position:
text | 5c4ec767-ba5a-4222-a274-0810a0341b54 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV Landscaping - Ground Preparation Rev 1 | itp |  |  |  | Yes | ITP-CIV Landscaping - Ground Preparation (Subcontractor) Rev 1 | 8e58c777-14ca-4c4b-93cb-34c8e2e2900b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 54aa1edf-46bd-5ffd-a3d3-c59c0f6ab808 |  | note | Document Title: ITP-CIV Landscaping - Ground Preparation
label | 591a952c-aa38-5df0-931b-4b2ba47249eb |  | note | ITP Description: Landscaping - Ground Preparation
label | fe758ead-b93e-55e2-8021-634ed3156d46 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | b2467485-0836-556b-ad65-30fd6191c228 |  | note | Revision Number: 1
label | 1992dffb-2e62-54fa-a496-d9fb4d0e71d8 |  | note | Revision Date:
label | d851e3fd-8582-5f4d-9c25-9cf268acdf36 |  | note | ITP created by: Bunni
label | d20f2783-ddff-5b70-9710-8edc5b38be55 |  | note | ITP approved for use by: Josie Pavlou
label | b304c46b-5d3f-50ce-a832-04047a5ad391 |  | note | Reference: VicRoads 720
label | 770dacee-c21b-5645-8a0f-89690c78d43e |  | note | AS 4454
label | 93251715-72a3-5bc3-b009-7652d859d9f1 |  | note | AS 4419
label | cf2d59df-75a2-569d-a1cb-2c95ab74732f |  | note | IFC Drawings
label | 663e054a-2c9e-50dc-8d4e-7b95690286ac |  | note | Sub Contractor ITP
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 1.1 Check for correct documentation
label | 432b4716-1f3e-59e5-95e3-7e47c017a654 |  | note | REFERENCE: Drawings and drawing registers
label | 59837a08-f877-5047-bef5-f6b833e748a2 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 6894982e-6d3f-5309-a1b7-f908125ef42a |  | note | Using the correct and complete set of IFC drawings
label | b61c475c-952d-548e-8621-66098360f598 |  | note | All drawings are the latest revision
label | 97b90916-baa8-56bf-94dd-1530666f2bea |  | note | METHOD: Document Review
label | ee2020b7-ec5a-5f00-a0bf-96702a5e9b0c |  | note | FREQUENCY: Prior to Commencement of works
label | 223c59ab-8e59-5f6e-b4a7-cb27ab7b0ce2 |  | note | CATEGORY: IP
label | c970b088-e4a7-5f39-bd2b-a7b336319319 |  | note | RESPONSIBILITY: SE
label | 0f6c2610-3458-5365-889b-b069bd346c6b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 09f77bf2-aaad-5ac9-9f2d-2963014a6eab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 Submission and records
label | 641c497c-2aa7-5ef8-a939-9115d48e45cd |  | note | REFERENCE: Section 720.03
label | 4d830a9d-5e1f-5afb-88b9-4b91bdc6f46b |  | note | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
label | 0cf4ca79-dc9a-5db3-914e-b9932ca2449a |  | note | Following information shall be provided to the NA:
label | 8802a215-03b4-5da4-a1f1-ade3aba0e913 |  | note | Samples
label | 779fbb21-ed04-58ba-8117-c1f018e22b6f |  | note | –Mulch
label | 063533e0-2b12-574b-b2d6-f2d738b4d350 |  | note | –Imported topsoil
label | 52a9bb00-5d02-57b1-a6ee-6e26c8a9b64b |  | note | Records
label | bb30fca5-0c08-5928-b37e-295651cf3b3a |  | note | –Details of suppliers
label | a8aa0171-bc9d-5cba-abcd-2a31bdf0ec6c |  | note | –Soil tests on imported topsoil
label | 05d9acb4-6860-5403-ab58-98785cd59a20 |  | note | –Copies/Photos of fertiliser labels
label | 82abd02e-4fee-585c-9760-054aa0b3d361 |  | note | METHOD: Document Review
label | c1783e05-5a7a-5d1a-ad90-1c3284f1f545 |  | note | FREQUENCY: Prior to Commencement of works
label | eb142bdf-758a-52cf-8f18-d095ec40bc3d |  | note | CATEGORY: HP
label | 215b119b-ece7-5e60-9cb3-aa9e499420fa |  | note | RESPONSIBILITY: SE, NA
label | 4c5763d9-10bd-53a9-8fe8-52b37c8f2ad1 |  | note | VERIFYING DOCUMENTS: Issue to TeamBinder
label | 5860d56e-22fd-5238-a242-a45b92d4265c |  | note | Attach: Records & certificates
text | f75dc222-6ac0-58a5-980c-765f89c5ec56 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 1.3 Supply of topsoil
label | b44584c8-f8d2-5097-acbe-aae9fe05d144 |  | note | REFERENCE: Section 720.04
label | dd31c036-4b1f-5b6f-afb5-a66872351c28 |  | note | Table 720.042
label | 68548f49-2a46-53ef-b3df-c7bbc0f4df36 |  | note | IFC Drawings
label | 2c2b1819-34fe-55f9-a648-24089da841d6 |  | note | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
label | 796f1e4a-85f3-5c62-9e31-69f3068e9081 |  | note | Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings.
label | 51cbb112-3b57-5021-abbe-dd276693ae5c |  | note | METHOD: Verify, Doc. Review if applicable
label | a82f612f-4c9d-51ee-b343-eb26d7c696ce |  | note | FREQUENCY: Prior to Commencement of works
label | 630854c8-b11b-5dba-9255-b9143d0cdf87 |  | note | CATEGORY: IP
label | b26a0f04-cd6a-5e77-ae6a-d9bab1f39531 |  | note | RESPONSIBILITY: SE
label | 35856d08-d903-5dea-93bb-60b1d9756006 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 40dc9645-0fe3-5df6-899e-ce0c51a85e50 |  | note | Attach material conformance docs/Test Report
text | ac900e20-9b9a-5ff4-9d53-b9608565b18d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 1.4 Supply of Mulch
label | 67d01fdc-6a8e-58ac-8409-e08363c8190c |  | note | REFERENCE: Section 720.04
label | 67d0ea99-bd06-51d8-81ed-29d33c25860a |  | note | Table 720.044
label | 79818d8e-4f71-5359-9bd2-2d4c8071371b |  | note | AS4454
label | 625631d6-5822-538b-8278-be114ae0d179 |  | note | IFC Drawings
label | 960131b0-73d5-5857-bfdf-52ef195f9ba5 |  | note | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
label | fea55dd2-fdd1-543d-9e41-68a130915104 |  | note | All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings.
label | 96cd82b7-4b64-5cc4-9610-d84396505c1a |  | note | Imported Wood Mulch shall comply with Table 720.044.
label | bfc006f8-dbb4-51cd-bc99-d8588eb7fb3e |  | note | METHOD: Verify, Doc. Review if applicable
label | d9bbe160-67f0-5830-aceb-31846469ceca |  | note | FREQUENCY: Prior to Commencement of works
label | e0cebff9-ae0d-52a4-97b8-613274609128 |  | note | CATEGORY: IP
label | 342ed125-f082-5499-872b-27f6eb9b2e50 |  | note | RESPONSIBILITY: SE
label | 9db22392-0a7b-5495-ba83-345d95a8179e |  | note | VERIFYING DOCUMENTS: Sign ITP
label | f2202dff-50d3-5479-b38d-6f44b9929cc1 |  | note | Attach material conformance docs (if applicable)
text | 6c418810-5f2d-572c-bb4b-c0a88152f508 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Site Preparation
checkpoint-status |  |  | checkpoint | 2.1 Subcontractor ITP
label | f4ebd8c3-736d-5a88-b386-20482755a57c |  | note | REFERENCE: Subcontractor ITP
label | 8447c1fd-7a7d-52a4-a063-b729c20f418c |  | note | ACCEPTANCE CRITERIA: Subcontractor ITP to be reviewed and approved by MRPA.
label | 3efbec7c-9914-5e27-a7c9-3a638a3f76ed |  | note | METHOD: Document Review
label | 91d27267-550f-59fe-846d-9857298fe29f |  | note | FREQUENCY: Each Lot
label | 90373765-8d94-5dd0-83f9-12b65da73da2 |  | note | CATEGORY: WP
label | ce4364cf-56b1-5b1b-8466-32c8e284bf75 |  | note | RESPONSIBILITY: SE/PE
label | e82a4b7d-14f6-5099-a594-43a078c42afc |  | note | VERIFYING DOCUMENTS: This ITP
label | a1dbbd6d-b587-5ffe-9c8a-985ff4a33007 |  | note | Attach completed Subcontractor ITP
text | 6226dd0c-20c9-589e-8860-4196c01f883a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Soil Additives
label | 4a5340b0-f563-5898-ba32-b5ba6729e2cb |  | note | REFERENCE: Section 720.07 a)
label | 67b5371c-0229-55ac-a6b0-9e8e298355be |  | note | AS 4419
label | 6f4ace27-8c2c-597c-938c-bfc7e02360e9 |  | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | 1b0faf17-aac2-5053-8b1c-3a935caa2dc5 |  | note | METHOD: Document Review
label | c559b33a-c55d-5c77-9d4e-3eba5bc13bfc |  | note | FREQUENCY: Each Lot
label | 75cd23f0-219e-59d9-b750-3a9e453378ab |  | note | CATEGORY: IP
label | 3baefc0e-9fd6-53dd-a89a-ee0716d11b5e |  | note | RESPONSIBILITY: SE
label | 60da0080-c3bd-5562-9a02-64cbd104a8b8 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | f1ea557a-376b-5396-9e93-7297425a0cc6 |  | note | Attach Test Report
label | 3cbf6eab-606c-5297-adb0-d314d8feb246 |  | note | Attached Delivery Docket (if applicable)
text | 522647ab-75ea-503e-ae62-331ef1a0aa04 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Ripping of subsoil
label | 7b041a92-b3bd-5ff8-b8a5-84d1175d2194 |  | note | REFERENCE: Section 720.07
label | 8e539966-3c02-584d-adad-e41d53e05824 |  | note | Table 720.071
label | 1cc0d94b-4113-5edc-856a-0d169d2fd93c |  | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP.
label | 701dd641-8291-565f-a1a4-21d799a9820b |  | note | Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
label | 95a8b4ad-cbaf-5c75-bcf8-0bf57dd495ab |  | note | METHOD: Verify
label | 7bf8897d-626e-5b5c-8a1c-c8a5aa1e7730 |  | note | FREQUENCY: Each Applicable Lot
label | dfd3d447-873f-57a8-b4be-7677db27c1cd |  | note | CATEGORY: HP
label | e7b80419-195f-5eb1-b7fb-be7de718db8c |  | note | RESPONSIBILITY: SE, NA
label | 747dd7bf-32d8-5ffc-8387-0843c0b9f630 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 07bb85b7-6a8e-5309-9da5-3d87e961ee61 |  | note | Attach Lot Map/Marked Up Area Inspected
text | 69a59d9c-fbaf-5809-bf06-6a2429d39ae7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.4 Topsoil application
label | c5bec64f-c4d1-550e-953f-e9481a3c864d |  | note | REFERENCE: Section 720.07
label | 318334a4-5d17-5473-ada6-3353a7e97e61 |  | note | ACCEPTANCE CRITERIA: Site topsoil shall be used wherever possible, in preference to imported topsoil. Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in table 720.071.
label | ae19388f-e11a-5792-b0ee-f637ebe13862 |  | note | • Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
label | e03a0069-1573-57bb-86e4-d5fe78efc8c0 |  | note | • Planting Areas in disturbed areas steeper than 3h:1v = 100mm Minimum
label | 7b28725d-e3be-5007-bb93-820dd24a7c1b |  | note | • Grassing in disturbed areas =75 mm, except 100 mm in swales
label | 622e596d-a0d1-5582-8841-440cdaab74d9 |  | note | • Individual Tree Planting within grassed areas =150 mm in disturbed grassed areas
label | ca8f0fc2-c03b-56a4-8bea-66113466b9e6 |  | note | Topsoil shall be spread on planting areas and grassed areas.
label | 39169b31-0bab-5e0d-9953-dd6a762e1a2a |  | note | Note: Topsoil shall not be compacted.
label | ba89e3d0-a186-53c9-b835-c4340a5727d4 |  | note | METHOD: Verify
label | f19f03e7-353d-5fe4-b5ce-b993374cfe4b |  | note | FREQUENCY: Each Applicable Lot
label | 3c376262-f0b5-5b45-9f85-0150d7ef4ba8 |  | note | CATEGORY: IP
label | 9e957042-f61c-5363-ae04-694755d859d1 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cc30c16f-f5b1-5d29-82f0-f6a0dbc42519 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 2f09ec7b-1395-5d64-96db-4cc2ff4aa45a |  | note | Attach Delivery Dockets if applicable
text | 783adcb8-03d7-5957-ac90-e2eaa24ba39f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Topsoil FSL - Topsoilling and Cultivation
label | f661d209-099b-5330-bddf-cea3eaec9e21 |  | note | REFERENCE: Section 720.07
label | 1d44518f-4ca3-5844-b5d4-1d0d420c3137 |  | note | ACCEPTANCE CRITERIA: Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
label | 71020d3a-0fa4-59fc-a77a-b18aa9a9e000 |  | note | METHOD: Verify
label | 052b682b-6ff4-518e-b91c-d691abdc8213 |  | note | Each Applicable Lot
label | 2deb9eb8-cd7f-5fd6-84d7-f6fc3600ae6d |  | note | CATEGORY: HP
label | 6443df0d-11d0-5567-8be4-8fd6a514bc79 |  | note | RESPONSIBILITY: SE, NA
label | bf11fd76-ac5c-5244-ac9c-8a93cc163f6c |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 0b545492-102d-54f6-a362-7c0ce69205ff |  | note | Attach Lot Map/Marked Up Area Inspected
text | 08a82e1f-9580-5812-923d-a4ad49c469b8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.8 Mulching
label | 4f4aefec-b776-5737-a41d-7eb2c50264e7 |  | note | REFERENCE: Section 720.08 a)
label | 8dc4b938-0c69-5c73-ae71-93e396a9a40e |  | note | IFC Drawings
label | 644c418b-3e85-5955-b00f-b8ad390d1bd9 |  | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
label | 5ff16d02-06ae-5a18-ac44-d1307ee67fdd |  | note | METHOD: Verify
label | 278411dd-1a4d-5523-ba3a-a219e0d50b74 |  | note | FREQUENCY: Each Applicable Lot
label | 98bc173d-2b1b-5c13-8aa3-93f774a50f4d |  | note | CATEGORY: IP
label | 8c5cbdee-f2ec-5007-9595-478bd9c8b0ef |  | note | RESPONSIBILITY: SE, Site Supervisor
label | 03d499df-1ed8-58e1-9ced-9846ab4c3bcd |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 7b7f385a-d252-5775-9136-3c79963ba586 |  | note | Attach Delivery Dockets
text | 1a009d93-6db3-5bbd-a601-829cf7459743 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Weed and Erosion Control Mat
label | fe5655a2-a364-5754-afbc-773436225846 |  | note | REFERENCE: Section 720.04 i)
label | a96932d6-6677-55e3-997e-4c0ba7ab9366 |  | note | IFC Drawings
label | 73f7b297-a9b5-53cd-bfb1-afd288c6427b |  | note | ACCEPTANCE CRITERIA: Verify
label | b9aca16c-7953-52cb-87f5-9580551804cb |  | note | METHOD: Verify
label | ea5f02d2-5b51-5e73-9ffa-794717b1f371 |  | note | FREQUENCY: Each Applicable Lot
label | 27074a86-35c0-5410-abb4-ecb5e56577de |  | note | CATEGORY: IP
label | c7e76118-ffc0-5d60-b22f-def53db8d25d |  | note | RESPONSIBILITY: SE, Site Supervisor
label | 00dc8859-ea41-579c-9a7c-bd67aae5b0bc |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 76560868-7706-53a0-84fa-757b729cb748 |  | note | Attach Lot Map/Marked Up Area Inspected
label | 6acf3692-1576-52b0-a636-b2fdbaf51261 |  | note | Reference TeamBinder Material Approval No. if applicable
label | 3d1d3e7d-9378-5d0d-924e-27eb8a93d1cd |  | note | Attach Delivery Dockets
text | 15835e1a-11f5-5a18-bc32-c3fbf49c1e77 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | db510735-a7a6-5335-bb51-9d8bfdd81e22 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c674afec-b3af-5fb5-9147-cdde16e6b714 |  | textbox | Name:
text | b31dc730-0904-5b6c-b94c-5d729c6170cb |  | textbox | Position:
text | 02fc396a-4710-50ae-b20a-52f4eefc9078 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | Materials Inspection |  |  |  |  | Yes | Materials Inspection Checklist | 90e17762-dd7a-464e-9b48-8d2400b5093d
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details:
text | d7357789-b485-4963-abe1-485435e60709 |  | textbox | Project Details:
text | bd1ddad0-59b7-41ca-8b93-ec569e72b217 |  | textbox | Project No:
text | f1e4c619-3444-4b23-8aef-a0d040aa1aa0 |  | textbox | Lot No:
text | a69655e5-d413-408d-bca5-94497d2cc9b6 |  | textbox | Delivery Docket No:
text | bb3c7c3e-0681-446f-a30f-b7fb67b96621 |  | textbox | Nominated Equipment:
text | 26898025-afc6-40cd-b0c4-098cf03bdf54 |  | textbox | Delivery Date:
checkpoint-group |  |  | section | Packaging Inspection
checkpoint-status |  |  | checkpoint | Is the condition of the packaged goods acceptable?
checkpoint-status |  |  | checkpoint | Number of packages in the delivery match that listed on the freight list/packaging slip?
checkpoint-status |  |  | checkpoint | Does the delivery match the order?
checkpoint-status |  |  | checkpoint | Do the contents of the delivery match the freight list/packaging slip?
checkpoint-group |  |  | section | Material Inspection
checkpoint-no-status |  |  | checkpoint | Verify each item meets all the criteria listed below:
label | 93b7c5e0-c656-418f-8805-00b82e1a7be7 |  | note | Is supplied in the correct quantity
label | 88443e14-0b4f-4fcf-8ab2-f4c5cb639582 |  | note | Is complete in all respects
label | 10feed41-a26c-4242-9970-378d373bc40a |  | note | Is the correct make and type
label | 2517b9d9-7851-4b21-a841-38f99422b352 |  | note | Shows no evidence of transit damage Is clearly and correctly labelled
checkpoint-no-status |  |  | checkpoint | Fault ID:
label | a19bfef3-b531-4ff7-b7b5-d0d1015a9896 |  | note | OK = Meets all criteria
label | 712a9688-1f5b-4d5a-a243-27e22ed89501 |  | note | QI = Quantity incorrect
label | 015d505b-e6a8-444a-a6a9-dddd4bf8ba20 |  | note | IN = Item incomplete
label | 78a27a91-6fe1-4b82-a95b-665f92a2c949 |  | note | MI = Make or type incorrect
label | 7b38f4cd-0c9f-4b40-85f8-e57aac1dd7aa |  | note | TD = Damaged in transit
label | 9b04ee90-80fd-452b-8b8a-90ac0f251931 |  | note | NI = Not properly Identified
checkpoint-status |  |  | checkpoint | 1
text | cfcf00cb-3fdb-4a2c-8914-84bf4783a252 |  | textbox | Qty:
text | 8fc186e7-4992-434b-a117-b590cb65b559 |  | textbox | Description/Part or Serial number:
button | 2299a5e4-5757-4c98-acff-5be7a2daf30f |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 2
text | 3e9e7e94-49e7-4547-bc37-d0d376384142 |  | textbox | Qty:
text | e2114911-6794-447a-b411-60dabb199968 |  | textbox | Description/Part or Serial number:
button | 999907ab-b121-4659-bbff-defd56904185 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 3
text | b09b9382-3ad4-4f7d-8432-e5b9d7514de7 |  | textbox | Qty:
text | 8ac87746-0fd3-4bdc-9532-1effe9bbe9c5 |  | textbox | Description/Part or Serial number:
button | f75729b7-fe67-4edb-a68f-d7f78cb8cfe1 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 4
text | bfded274-3b12-4965-8bfa-3e16ef7e3a9d |  | textbox | Qty:
text | 246e6d9c-fc52-4801-b975-9114115dbb8b |  | textbox | Description/Part or Serial number:
button | 2e33d34c-bf54-4be1-a03b-3bb632187291 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 5
text | 00391823-f930-4b07-97d2-02a5f32d9a6a |  | textbox | Qty:
text | 20bc3b57-ec49-4c07-8c25-0347765015a9 |  | textbox | Description/Part or Serial number:
button | 942b3e55-54c9-49ca-85cd-03d85fc25278 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 6
text | 513b8587-47a8-44ac-8d3d-14558bf39bb9 |  | textbox | Qty:
text | 0c7de041-9cb1-4132-9215-ee5d6f4d5683 |  | textbox | Description/Part or Serial number:
button | af7767cb-4d53-4e67-ba6e-f43ddafdc441 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 7
text | 75364265-03ac-4d33-ae82-d8c85ab72dab |  | textbox | Qty:
text | e235474f-8d6d-4cce-91c0-79a14ca0568a |  | textbox | Description/Part or Serial number:
button | 74187bb8-083c-487e-b298-064d9cb9015b |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 8
text | 2b9c5a01-8510-40a9-8ca6-779e7ac7f64c |  | textbox | Qty:
text | 44b3e9ec-0c4c-4d24-b4ae-aa0896666ced |  | textbox | Description/Part or Serial number:
button | 63ed11d3-8348-4d07-a481-e43200f5384a |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 9
text | fee46d09-cfe3-4d8b-98a7-8dee87d86fc5 |  | textbox | Qty:
text | 21c40884-e591-4087-817b-35604a1e8146 |  | textbox | Description/Part or Serial number:
button | bf79ef2c-c40f-4b4b-ba7e-3f2414a8f19d |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 10
text | a5bf3863-d854-4c23-93f0-7bf7b45dd7a7 |  | textbox | Qty:
text | e50c7dbd-ca7d-43f3-9cb8-5504d22825d9 |  | textbox | Description/Part or Serial number:
button | cd78f640-7166-4198-b6b5-3633122d04b5 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 11
text | 6ceb426a-61e0-49dd-98d8-1bc81317abd0 |  | textbox | Qty:
text | c5bb3dae-9b0d-48ad-92ef-99ab6471c494 |  | textbox | Description/Part or Serial number:
button | 4481d520-87e0-435f-84f7-537c6dd460dc |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 12
text | d8dedce3-0261-4ef4-ba4c-936bca5efbeb |  | textbox | Qty:
text | 6e05e689-7b61-46b0-a322-6f9e72441074 |  | textbox | Description/Part or Serial number:
button | 8ec72698-0ea9-4523-a206-de51d127d054 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 13
text | afb5b7c4-b561-4edb-8071-ac0dc8e21389 |  | textbox | Qty:
text | 6e5e115b-355b-4b1e-b4b5-ac5452dfe28e |  | textbox | Description/Part or Serial number:
button | 0a51a108-ed32-4e1b-8392-b11132718158 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 14
text | 9b6146d4-7f6b-4bd4-adcd-860627b1628c |  | textbox | Qty:
text | 0df3ef3d-9902-42f8-8901-141a3c85a97b |  | textbox | Description/Part or Serial number:
button | 417e7ca3-0b2f-4ce2-9743-b8e202ccd645 |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-status |  |  | checkpoint | 15
text | 07588345-b577-44b9-8169-8dc5f4845373 |  | textbox | Qty:
text | 99ba23b6-9fab-4643-959a-cb86a5a5604d |  | textbox | Description/Part or Serial number:
button | f692a24b-3711-4e04-98bb-5b7a174d1ceb |  | button | Fault ID: | IN, MI, NI, QI, TD,OK
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Accepted By (MRPA)
text | 53931074-0dc6-468d-9ea5-6de0c4c7e125 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 1 | itp |  |  |  | Yes | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 1 | 919bd0fc-5bfb-45df-85b6-6829a76cf8b1
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 6c9b118e-4b27-4f18-a30b-295e600c0351 |  | note | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
label | 3f252573-69a9-4941-8cd3-e1b07494ba4c |  | note | ITP Description: Concrete Coatings (Protective &/or Decorative)
label | 389d5da9-2a04-4b09-b2f1-3e49d239398c |  | note | Discipline (e.g. CIV/STR/RAIL:
label | 025270d1-3e2d-4d72-b8dd-19f77f5beff3 |  | note | Revision Number: 1
label | f39dee5f-6ebc-4833-aee6-9a8e5f8b89ac |  | note | Revision Date: 14/04/21
label | 43075d36-c280-4fae-8a57-a734d0c1a11d |  | note | ITP created by: Mike Freeman
label | 542007e8-2c19-42bb-8408-0351dbdb0423 |  | note | ITP approved for use by: Mike Freeman
label | 34b808fc-116d-480e-8ba6-2b3b548f3e96 |  | note | 1.1 VicRoads Section 685 November 2018
label | d35fb0b2-8753-4e73-a959-56af6c46f4af |  | note | 1.2 VicRoads Section 686 November 2018
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Anti-graffiti System Selection
label | 883175e2-650b-42b0-bff7-7848e82af639 |  | note | REFERENCE: IFC Drawings
label | d30b4d49-8ad7-4ede-8e2e-820913af3d17 |  | note | Coating System TDS
label | 22de64ce-730f-40ab-9b4b-88339a44ba04 |  | note | Surface Cleaner TDS
label | db98aab8-04ab-4a5d-aa97-4216d7277b5a |  | note | 685.04
label | 5f761de8-e7fe-4c33-9912-ba26a0ed44ea |  | note | 685.06 (a) & (b)
label | 4467c340-979a-468a-aa09-bf8e7f0c30e4 |  | note | 686.04
label | ce9bd1e8-cb87-4f71-82ff-1c3e440b63ad |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | fb50310a-9f61-4f0e-950d-587ffe61a188 |  | note | i. be either a film-forming or a penetrant system
label | 82027b19-ae89-4378-8e8b-cf0908bd24aa |  | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
label | d8afe959-668c-4692-bc16-265cf015e830 |  | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
label | 04392ee4-269e-4115-bb23-a8481f5ba779 |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | 1ed3e1b6-c79f-4d47-9e1c-d6c844b08421 |  | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | 7b7b57c1-4a04-4eac-91e0-daa3548c4f88 |  | note | vi. application thicknesses (film-forming):
label | 1418a987-3c4d-4e8c-b8e0-7c8108077c1a |  | note | WFT total = 175µm min. OR
label | 078474d7-3159-4535-bb7d-ddece5278bc8 |  | note | WTF per coat = 88µm min.
label | c72cfda4-24e6-4679-bec3-f22d5dfd7ce8 |  | note | DFT total = 100µm min.
label | 0cbf68ab-8051-439c-9777-2737b7f8a07b |  | note | vii. adhesion to substrate (film-forming):
label | 106f06ff-3d52-4730-bff2-9c7340d578b4 |  | note | 0.75MPa min.
label | 12b38122-5741-4055-b504-77372500bafa |  | note | viii. application rate (penetrants)
label | 0fd5af89-c680-4c41-b4c8-89bc499a67de |  | note | as per the minimum thickness on the manufacturer's TDS
text | 1f7a287f-b889-40e7-935f-92cb4d2851fb |  | textbox | Enter: Teambinder Material Approval number
label | 6303e018-7180-4c05-be3b-b79394ab3999 |  | note | METHOD: Document Review
label | ecca6e75-f2c2-43fb-a3cc-09f2326eec75 |  | note | FREQUENCY: Once, for each coating system, 14 days prior to application
label | 2e64aafa-6bc8-4cda-9450-b069135122d9 |  | note | CATEGORY: HP
label | 9ca8a13d-e6a7-464e-a283-92630d8194c8 |  | note | RESPONSIBILITY: Nominated Authority
label | 8c9a8675-7a4e-4ce8-a65a-09fa8bfd407c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | bd2585f7-389d-4884-a430-1ebff4cf0109 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Decorative & Anti-carbonation System Selection
label | abcc1d25-803e-4cb6-a2a7-3484b60a5abd |  | note | REFERENCE: IFC Drawings
label | b45cef14-2b65-4caf-ae23-c4255d82ba9f |  | note | Coating System TDS
label | 91af125a-73d0-4d34-ba68-4fe240a844c3 |  | note | Surface Cleaner TDS
label | c3b433b7-2636-4bbb-96b3-f12cd75e5094 |  | note | 686.04
label | c9faeb7f-4a91-4a97-8c59-7c75816e339c |  | note | 686.05 (a) & (b)
label | bace77ed-30a4-4ca7-9efb-99a032f78f85 |  | note | Table 686.051
label | 60928ef2-0990-4793-b801-230f103940e4 |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | 6027d4e0-cfcf-4ff7-b423-59a0b2043556 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | 36e57282-226f-4a0b-b43b-083ae29ca9b7 |  | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | b2ddd51f-aa4a-4f85-b0c8-22daa8fbb9f1 |  | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | c07aec8f-4c82-48d7-bd01-c2d168b72a21 |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | d99a521b-f178-4d48-83cb-9ff482654d02 |  | note | v. be guaranteed to last for 10 years of outdoor exposure
label | 34f159c2-35d1-4fcd-bd0f-71f6ace06063 |  | note | vi. application thicknesses:
label | 01d68a92-2c7f-48a0-b48c-f2c77fc0271b |  | note | WFT per coat = enough to achieve the total DFT
label | 61333696-0632-41d3-aea5-88b5c3087f17 |  | note | DFT total = 150µm min.
label | 76818305-d214-490d-8753-3ebe7c6eb553 |  | note | vii. adhesion to substrate:
label | 0c4e6b71-6fe2-4a20-a3fe-d9548b61738d |  | note | 0.75MPa min.
label | a4828a0f-f8ca-4bff-95f1-5256b63e61b8 |  | note | viii. able to bridge cracks up to 0.3mm wide
label | a31982f7-911d-47b5-87d1-7d4bcdda88ca |  | note | ix. able to be re-coated within 24 hours
label | 656e9c30-4ca4-4858-ad4b-0277245ee8bf |  | note | x. have a minimum pot life of 1 hour
label | 6a94c48f-4bfb-463a-a014-c9ee12146b87 |  | note | xi. compatibility to an alkaline surface
label | d2ab4908-82e2-4ca8-8b8b-369687ed73f6 |  | note | xii. equivalent air thickness >150m
label | cb771287-e908-46b7-b544-fcd42f539af6 |  | note | xiii. equivalent concrete thickness >450mm
label | d7e6df2a-3b5c-4b70-98b7-031071a7ba27 |  | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 84538ad7-9e63-4c72-a749-cdf8c7d5e0ea |  | note | xv. Water vapour equivalent air layer <4m
text | 82c81893-585d-4c7f-a7b1-97215b79cab7 |  | textbox | Enter: Teambinder Material Approval number
label | 3f58881f-8c4b-4a7c-b090-4d889846da3c |  | note | METHOD: Document Review
label | e2c0c293-cce4-4e25-9c59-326446a74e3c |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | f9178b77-1c29-45ad-83df-7f412d5a94e5 |  | note | CATEGORY: HP
label | cda9db7f-fbca-4f0b-bb5a-c880b3325254 |  | note | RESPONSIBILITY: Nominated Authority
label | 9f6948d5-fbe7-40bf-8467-d9fcfce0dc30 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3e77fe6f-c813-4954-8ce7-396067040053 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Decorative, Anti-carbonation & Anti-graffiti System Selection
label | 41a1ecb3-7220-4081-aabc-2b857af3e40a |  | note | REFERENCE: IFC Drawings
label | e422f135-b4df-4b6b-9d69-40fe1922073c |  | note | Coating System TDS
label | 130654b8-f5d2-407d-943e-934669be0db7 |  | note | Surface Cleaner TDS
label | 04bc25d8-792f-4d92-be59-e5a064dbec94 |  | note | 685.04
label | c48af9d7-4e7f-42e9-9e76-e8e73802dfb6 |  | note | 685.06 (a) & (b)
label | 7455f478-62b5-4e5d-b878-b1102cd44449 |  | note | 686.04
label | ef206a6b-ada2-4dcf-9ef1-9f7d53b23938 |  | note | 686.05 (a) & (b)
label | 9aff2803-30c9-4b6b-824b-51aa845bea0a |  | note | Table 686.051
label | a24b4042-f584-4fe5-89a1-b113f07cf732 |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | 87bd3c58-fb30-4fe3-987a-77c5f1393659 |  | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | f9a8a667-6098-4b07-a8bf-d27f0046098c |  | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | 3d1faee8-9658-434d-9984-8ea9febb5b57 |  | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | 09ef6437-bd95-4b5e-be42-04a05649a469 |  | note | iv. be non-yellowing, colour-fast and not subject to fading
label | b9b1ef8c-9cc6-4985-b63a-f13a74cf583c |  | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | 4668351f-f42f-4f1f-856b-9f6df8954637 |  | note | vi. application thicknesses:
label | 79a14f6e-06b1-4e41-9d87-b0866d488858 |  | note | WFT per coat = enough to achieve the total DFT
label | 18034373-2472-4b27-b902-71224dee44ec |  | note | DFT total = 150µm min.
label | 54bc9eed-2300-467d-8577-41bcea1a6120 |  | note | vii. adhesion to substrate:
label | 12b599cd-aa6d-4057-a6bf-f3ebf399d71d |  | note | 0.75MPa min.
label | 993dd121-dcd4-4488-a7c6-ef95835ef5e9 |  | note | viii. able to bridge cracks up to 0.3mm wide
label | 8d7be93e-760f-461b-b74d-d8e0cfe3ed71 |  | note | ix. able to be re-coated within 24 hours
label | 6e8aacea-46e7-4ca7-b263-85fba5355244 |  | note | x. have a minimum pot life of 1 hour
label | c13bb674-03cb-4646-b51d-292948e04b16 |  | note | xi. compatibility to an alkaline surface
label | 9daeea8f-63b3-43aa-8c5a-1ffcee1e5211 |  | note | xii. equivalent air thickness >150m
label | 71d788ec-df3e-489c-ab45-29c77f9e6ae0 |  | note | xiii. equivalent concrete thickness >450mm
label | 48b2e011-fb1f-406a-93ec-6200096b60cf |  | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 9b3fb778-2517-4f2e-9a25-5a692fa34b77 |  | note | xv. Water vapour equivalent air layer <4m
text | 23d56d81-cf0d-44aa-806d-b8fd12382d12 |  | textbox | Enter: Teambinder Material Approval number
label | 30a0fa65-3c68-4653-bb14-71213e9f98f6 |  | note | METHOD: Document Review
label | 6ec3a0d4-8ef8-4284-bf2a-78520875b19f |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | ab5ad6a0-c713-4ac7-8399-23b19f45d8ba |  | note | CATEGORY: HP
label | 5c6fa425-8d1f-4e54-bc11-6137f4c5ace9 |  | note | RESPONSIBILITY: Nominated Authority
label | a1668b33-c7e9-4b7d-8334-b74311c7787c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3f3d98c2-2ad2-4f08-aaad-9b21026992cc |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Atmospheric & Splash Zone (Dual Protective) System Selection
label | 9efd7935-d70e-429b-9137-bd1daeb6a492 |  | note | REFERENCE: IFC Drawings
label | 83c443ca-ee3d-476c-808c-e1973868c915 |  | note | Coating System TDS
label | 7480b13d-7bac-46b7-abc1-c36ad0338521 |  | note | Surface Cleaner TDS
label | aa036687-a913-448f-b57a-18e2a814ba90 |  | note | 685.04
label | a3ba19a7-7e32-434a-8ce2-9a9bb49c4c10 |  | note | 685.06 (a) & (b)
label | 41ed2f0b-8ec4-4476-a2a7-6c6ccd253767 |  | note | 686.04
label | 2fe95fb9-472a-47d2-92da-8dde512c4cf7 |  | note | 686.05 (a) & (b)
label | 9aa660a1-c07f-4112-813c-9b74089d542a |  | note | Table 686.051
label | c4122c4f-ff77-4923-a9e8-0e158267282b |  | note | 686.05 (c) (i) & (iii)
label | 005b18f7-b076-4359-81eb-a5f6dc570b9a |  | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | 71183c89-9409-4b86-8cdc-16441696438c |  | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
label | 0b777285-e85f-4ac1-81e3-385a5a6b2699 |  | note | ii. all coats to be compatible with each other
label | f9094e1d-9212-4c33-8a7d-ddd78427593c |  | note | Penetrants:
label | ec0e2fd0-0a15-4854-b884-5a0722935a2c |  | note | iii. active ingredients:
label | 1e2c04b8-eb37-4008-b5d9-18dc20de3806 |  | note | Silane = at least 95%
label | 6068cf95-c381-437c-88be-1de1c74a1eac |  | note | Solid silane & silane cream = at least 80%
label | 2b045edc-50d8-42e7-97d8-679e31619381 |  | note | Silane-siloxane & siloxane = not specified
label | f05f7ff3-029a-40e0-90fc-8745bb537a5d |  | note | iv. application rates:
label | 68edd164-d5be-4efb-b8ee-086453e6477e |  | note | Silane = 2 applications of 0.3L/m² min.
label | 43953ad1-243c-4f12-b54b-9a3da7c3e717 |  | note | Solid silane & silane cream = 1 application of 0.4L/m² min.
label | a5627150-d827-4137-841c-3c985f7177fa |  | note | Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
label | 36470b52-7a34-4c78-8b58-ddaede05b066 |  | note | Film-forming coat:
label | b789097f-f1b3-4671-8437-bd1f9bf2521c |  | note | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
label | 574fc6e2-8332-48b2-99ef-98044c91850f |  | note | vi. to be water or acrylic based, solvent-free
label | 9720a217-0aa0-46da-a80a-e296cba58573 |  | note | vii. to be non-yellowing, colour-fast and not subject to fading
label | f2542686-1bb5-4660-85eb-776a7e7cecec |  | note | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | 9865b33a-ec53-4dcf-bc8e-957fbc3ac415 |  | note | ix. application thicknesses:
label | 48ba526d-b241-4af6-84d7-7151bbdbca08 |  | note | WFT per coat = enough to achieve the total DFT
label | 6dd3c01f-4983-4273-96cb-b23ec324503b |  | note | DFT total = 200µm min.
label | e8415930-cf43-4477-b5d8-48336095fac9 |  | note | x. adhesion to substrate:
label | 4fb79437-2e87-4830-a151-b83d81921d6c |  | note | 0.75MPa min.
label | e1fbea66-9542-434a-85b7-52a7922d4814 |  | note | xi. able to bridge cracks up to 0.3mm wide
label | cb718414-ca6f-495a-9f39-b54a410a6c07 |  | note | xii. able to be re-coated within 24 hours
label | 5337263a-4534-4a44-bc15-a98c9ceddff2 |  | note | xiii. have a minimum pot life of 1 hour
label | 5a54d995-0253-4277-bc92-e977ba77562b |  | note | xiv. compatibility to an alkaline surface
label | 1a81708a-a3d8-4212-bee8-3c6254038ec3 |  | note | xv. equivalent air thickness >150m
label | 20945110-58c7-4aae-8852-2f661f1bc1eb |  | note | xvi. equivalent concrete thickness >450mm
label | 141cf1b6-fbdd-436f-8f33-89f62daf285e |  | note | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | 6c0feae2-9aed-421c-b517-731d29af2578 |  | note | xviii. Water vapour equivalent air layer <4m
label | 23f1e5ea-1e57-4ed0-a080-3b9ca02e8918 |  | note | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
label | f9afb4c7-67d8-49dc-ae32-f10061234124 |  | note | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
text | 0561c0f7-e485-4460-8571-98523644d479 |  | textbox | Enter: Teambinder Material Approval number
label | 4851be93-ce0e-43e1-b16e-742b81e44e35 |  | note | METHOD: Document Review
label | 09db1669-c28a-4c1f-ae61-1651603e4c68 |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | eb48a16e-d018-446a-922f-7c6335c5ae34 |  | note | CATEGORY: HP
label | f175e790-3f73-4f0a-9e3a-8915486c33e7 |  | note | RESPONSIBILITY: Nominated Authority
label | 59e49efb-12df-4301-b9cf-61119bd87fc3 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | f537b599-361e-458c-874e-9ee4b9fe35fa |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Work Procedures
label | 05f56d90-f93a-4114-88a2-c9585aa51c71 |  | note | REFERENCE: 685.05
label | b153b597-933c-4442-afd3-08b0aebadd07 |  | note | 686.04
label | fe43f990-69c2-44f3-aac3-cbaa49f2467a |  | note | ACCEPTANCE CRITERIA: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
text | 95713a0f-f7e6-463a-8264-f0a6d5af69c3 |  | textbox | Enter: Teambinder Hold Point number
label | af076ce3-29d9-4166-a967-4cc1f680f788 |  | note | METHOD: Document Review
label | 3f70f6b5-43ba-488b-86ba-221662d7af4f |  | note | FREQUENCY: Once, for each coating system, 21 days prior to application
label | f142fab0-5a0f-4255-bcce-3ea11479f1d2 |  | note | CATEGORY: HP
label | 68329936-22e2-4b3e-b4fd-eb7dd2edf878 |  | note | RESPONSIBILITY: Nominated Authority
label | 8dee1843-ba04-44ac-86c8-8bcf3dbf8abe |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | bf09fffb-fcfa-4ed0-9375-39190f98e890 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Coating Personnel & Equipment
label | afac648f-4912-43f6-b73a-2de4d8b4a385 |  | note | REFERENCE: Coating System TDS
label | 45e92134-017d-440d-b642-1c78cd80e4f9 |  | note | Surface Cleaner TDS
label | 4d57cf34-c5a2-4a46-ae61-3912f3e2fdb1 |  | note | 685.16
label | 079a62c6-945b-428a-a45b-044805a3d9d9 |  | note | 686.18
label | 32ac6bea-2acd-4800-a0e2-ba13b2f6db0b |  | note | ACCEPTANCE CRITERIA: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
label | e0c5956a-599f-4ab7-9725-2f01a92a4289 |  | note | Application personnel require 2 years minimum experience.
label | 0d4faf26-097d-40cb-867c-b727dc4d1f9d |  | note | The supervisor shall remain present at all times.
label | fecc0748-11f3-4a00-8567-2607c90cbaa8 |  | note | Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | 3ed6a41e-8ec2-4038-9f8e-8fb72415b476 |  | note | METHOD: Document Review
label | 74274a40-ea2f-4cdc-a309-232f02f182ff |  | note | FREQUENCY: Once, prior to application.
label | 41409e2b-7861-463d-b97c-95bf6b78cbf5 |  | note | CATEGORY: IP
label | 177abc9d-1a5c-4d44-9620-490b600bd187 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c035e1a9-69e2-4387-a1ff-01e01b84dc1e |  | note | VERIFYING DOCUMENTS: This ITP
text | d93644d1-85e5-42ad-b84e-70206b557789 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Protection of Adjacent Works & Property
label | 0321b00c-3758-48d5-a5b3-10a89ca8d497 |  | note | REFERENCE: 685.17
label | 71e9359a-833e-4f8d-8ea9-9684d1a85a51 |  | note | 686.10
label | 6c2f9b87-e6b6-4e51-85a0-04f224d64719 |  | note | ACCEPTANCE CRITERIA: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
label | 0c4d14a6-59a2-4f17-a35e-377f05132ed2 |  | note | No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
label | d79227ad-ac95-42df-beec-f135762c867c |  | note | Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | 4a7e0c5a-ad63-4b9a-a126-ad246c060ac5 |  | note | METHOD: Visual , Document Review
label | d2ee0432-43ef-47bd-aa77-012f5f6d867a |  | note | FREQUENCY: Where applicable, 2 days prior to application.
label | 8e03ca63-767d-46cb-842c-8da2536ac146 |  | note | CATEGORY: HP
label | 2c3c935f-3812-478b-97b7-c8eec5761aca |  | note | RESPONSIBILITY: Nominated Authority
label | 610194b7-a601-49c9-8147-095fc14f2e62 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 98d97c55-38d7-4e21-bafd-6000242b2058 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 Minimum Concrete Curing Period
label | c59b883f-b4f8-4295-b8b4-cdfdf17768a6 |  | note | REFERENCE: 685.08
label | 87393eef-b89e-4750-a671-0e7d3cd6c9f1 |  | note | 686.16
label | efd0193a-11c6-445e-a0cc-1c6bd1106a94 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be coated until the minimum concrete curing times have elapsed:
label | a52b4845-4b0b-4a06-a901-e2c294f3ba51 |  | note | Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
label | e532ed2f-5d07-4492-90bc-91e0c04d2e21 |  | note | Accelerated cured concrete = 14 days
label | dcd2abe0-d945-4c8a-9044-994f51245700 |  | note | Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | c20b8d60-8e7c-4cf8-ae46-89c5189b5b9d |  | note | METHOD: Visual , Document Review
label | d1ed7555-3ab2-4a04-8899-2fb9150d4339 |  | note | FREQUENCY: Once, prior to application.
label | 0ff93d78-ca6d-4e01-a467-767c3eda3b46 |  | note | CATEGORY: IP
label | 42f06a1c-bad7-4e6c-8f50-08e74e4cfcb7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2584d47a-c1eb-4c38-be35-2f583e031154 |  | note | VERIFYING DOCUMENTS: This ITP
text | c138c71f-4aea-4530-9b31-faed8e83cb7e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Trial Application (or Past Performance) Inspection
label | 634cba0b-f186-4f10-95ff-41b0ffe14e3f |  | note | REFERENCE: 685.11
label | 42b26a83-5a2e-4d31-bebc-15acf20e56b5 |  | note | 686.13
label | abcd5078-a017-451d-8775-d80dd3261c40 |  | note | ACCEPTANCE CRITERIA: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
label | 92f74395-1be9-4544-823b-38d97556c3f4 |  | note | Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | b7151638-602c-4338-81d7-ce58e00273f8 |  | note | Attach: Inspection Photographs OR
text | 84482361-a5fb-4d16-834b-7a04bbbe6cb7 |  | textbox | Enter: Teambinder Hold Point number
label | 4076a6ea-062b-4240-8f15-ba64e22613b6 |  | note | METHOD: Document Review
label | baad99a2-fe24-4672-81ac-13ae813b2493 |  | note | FREQUENCY: Once, for each coating system, 7 days prior to full coating application
label | 10c40ea6-0e3e-4d2b-b0ac-5dd2d412f52a |  | note | CATEGORY: HP
label | d9f16b01-46f9-43c9-acb2-2f909569106b |  | note | RESPONSIBILITY: Nominated Authority
label | 21bf24a5-a400-40f7-8c72-1790029c6f03 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9624170a-b6a2-4fd1-bdad-b4172e7e491c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-application Activities
checkpoint-status |  |  | checkpoint | 3.1 Material Records
label | bc75f519-c0da-482b-a980-90ed5265efc1 |  | note | REFERENCE: Coating System TDS
label | ff1470f5-d90d-41a2-840d-f5924d58a4d5 |  | note | Surface Cleaner TDS
label | ce53b4c0-5a02-40ae-8951-74bf4e93204b |  | note | 685.10
label | 40ef839d-9784-41dc-8811-1454f17c7557 |  | note | 685.12
label | 36ec15ee-3793-4643-aa8e-7de5e049f171 |  | note | ACCEPTANCE CRITERIA: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
label | 56d66174-da5a-4545-bef6-7db4c9111831 |  | note | the manufacturer's name & address
label | 9ba92a0e-d05f-4652-8117-e98188b1c13f |  | note | product reference
label | 133a7a79-fc91-424e-ab1b-b2cc5cb7d23f |  | note | batch number
label | c9d0c3b3-d877-40a8-9785-f511d4934b4b |  | note | quantity manufactured in the batch
label | 78186a48-b9f3-4dc3-8849-ca0ba271afdf |  | note | date of manufacture
label | 66ef5ae2-5c75-400e-bae6-26e3f1193918 |  | note | Product beyond the manufacturer's shelf life shall not be used.
label | ae0346bb-1524-4e57-9848-dd156ceea30d |  | note | Each product shall be traced to final location.
label | 9a9166c7-16b5-4474-8c34-523c665a5e91 |  | note | METHOD: Visual
label | 929bf52f-1332-468c-b75e-ca3830550383 |  | note | FREQUENCY: Prior to application
label | d9eea630-47d5-435f-bc0a-b3f61cd63cd2 |  | note | CATEGORY: IP
label | c79cf201-c386-4fac-bdb4-43cca51314be |  | note | RESPONSIBILITY: SE/PE/SPE
label | f15a0693-e78c-449b-9521-4d39e67e3175 |  | note | VERIFYING DOCUMENTS: This ITP
text | c8ce1c71-158c-49d9-b641-69e96f43d61d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Weather Conditions
label | af739133-69e3-4732-b249-da8a5c13265c |  | note | REFERENCE: Coating System TDS
label | 43cf37bf-55d3-4cba-8e5e-bff79e7c6d5f |  | note | Surface Cleaner TDS
label | 7748b9c6-8b18-430a-88de-483c35fb5fcd |  | note | 685.09
label | b28d5484-d0cb-4d87-bf13-9d7ee46568d0 |  | note | 685.12 (a)
label | e4faa2ca-41a7-408e-9ee5-94e6e0b8ee77 |  | note | 686.11
label | 60365b91-0506-478f-b0af-c46ae98929b7 |  | note | 686.14 (a) (iii)
label | d961b7aa-4a54-439e-944c-bdae1ad06fe1 |  | note | ACCEPTANCE CRITERIA: Coating systems shall not be applied under any of the following conditions:
label | a4be99bd-54c5-466e-bfaa-786c630ce0e3 |  | note | i. windy conditions where spray/splatter may be generated
label | 8c5049c5-73d2-457c-acaf-de9afc7ff6d1 |  | note | ii. when wind-borne debris is likely to contaminate the uncured surface
label | 7f3b24ae-2956-40ee-b9b9-6c9da15f6d93 |  | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
label | aebfdbc8-7614-4abe-bb96-43fd6317354d |  | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | da811d49-de03-43b4-985c-856ae3532d1f |  | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
label | 127b681f-18f0-4c8c-99e2-491f9e619a3a |  | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
label | 3839078f-613a-459f-ac5e-48493e2a7b37 |  | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | e9cf3d02-a024-4092-a04b-f82d02567ec9 |  | note | Weather conditions are to be recorded.
label | 47a5f971-f623-4cc5-846b-9481fef4f0f1 |  | note | METHOD: Visual , Measure
label | 1f097b88-40fd-476e-a78d-5917c1b5654c |  | note | FREQUENCY: Prior to application and every 4 hours per shift
label | c2aaf7b0-7d1b-4e43-8160-ad2684cc97cf |  | note | CATEGORY: IP
label | 9b6195e4-aae4-4920-bb3a-18f6192709f4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 320ddc5b-563f-4a9a-ae82-f5225930f5f6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 20ddbd4f-4173-46f2-8f5c-19657830301a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Surface Preparation
label | 758b4f47-1f49-42e2-8dcc-9f7bd02818eb |  | note | REFERENCE: Surface Cleaner TDS
label | 4174823d-f07a-49a8-a972-6cfbaab153aa |  | note | Coating System TDS
label | cb392ca3-7532-4738-8942-830feb2591d9 |  | note | 685.05
label | aad1ca29-5104-48ab-9572-4302c9065e4a |  | note | 686.06
label | 4b491cfd-d8e4-4ef4-9ef1-ea0e820441db |  | note | ACCEPTANCE CRITERIA: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
label | d9f160c0-1524-4e7e-84bf-00018d7eb41b |  | note | The surface shall then be flushed with water.
label | a2ca59f0-7ad2-4a75-a81f-3123c8ba9e3d |  | note | Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | 9fd0ceac-b289-476c-a0e0-b504d17759cd |  | note | METHOD: Visual
label | fdee179b-7d8a-4b18-8b68-a6cac2f61c1d |  | note | FREQUENCY: Once, prior to application.
label | bd2c91b9-c015-4b2a-9135-c9e63e824212 |  | note | CATEGORY: IP
label | 711add92-6d46-4a6e-8abd-0c0d982dd8f0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7cb63a76-3ee4-414f-8072-50b18c151e32 |  | note | VERIFYING DOCUMENTS: This ITP
text | f39386aa-6d83-4383-b233-03d0d617b21d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Surface Moisture Testing
label | baa5437f-7d65-486a-afa6-0e59d56adbf3 |  | note | REFERENCE: 685.12 (a)
label | f7cbde35-f4c0-4a12-a470-1ca6c2199281 |  | note | 686.14 (a) (iii)
label | 3700ecdb-e0e6-459f-b1de-4963b951ca6f |  | note | ACCEPTANCE CRITERIA: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
label | b0fd5dae-0b3d-47bf-a899-46106b848485 |  | note | Surface moisture conditions are to be recorded.
label | 74f88ab3-ae6e-4cef-ac0d-ffcb928cdb6e |  | note | METHOD: Test
label | dd6e06fd-3933-4d22-bca4-a22d0b2cfc40 |  | note | FREQUENCY: Immediately prior to application, 1 no. test every 50m²
label | 076d1587-00a0-4f79-bdb8-a582c735bcc4 |  | note | CATEGORY: IP
label | a52ca2e4-2f91-4aea-9a42-fcc9eef290a1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 34250e59-8c91-485a-b43a-85ff80c3969c |  | note | VERIFYING DOCUMENTS: This ITP
text | b5db707c-95e9-445c-825b-7d0ac4e30ac1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Application Activities
checkpoint-status |  |  | checkpoint | 4.1 Method of Application
label | adde0daf-36ca-4888-87bc-0c35d9599eaa |  | note | REFERENCE: Coating System TDS
label | f44adf3f-c741-4ac8-a8fc-7e71e1637f28 |  | note | 685.07
label | 5a33ad0f-89d4-413a-bf22-d80c65068e83 |  | note | 686.07
label | 1fe3092b-8296-4033-b87c-3db5ae3d4625 |  | note | 686.09
label | 1f60231e-96d2-48e2-bc4d-e68c3a68c6fb |  | note | ACCEPTANCE CRITERIA: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
label | bf1f6c49-fc12-4f73-8a8c-948b5d86960a |  | note | Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
label | 7f4ce3a6-329f-41cd-80af-e334eae6d966 |  | note | For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
label | 9ee486b5-e02c-43f3-9e76-43d2d3dbe0f3 |  | note | Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | fd8660e0-0980-414a-aa6a-cb61a4d78368 |  | note | Attach: Coating Application Record
label | 036f334b-6963-480e-85bf-3de55007fdd6 |  | note | METHOD: Visual , Measure
label | 2d109899-911e-4110-aa8f-211f9ec03f49 |  | note | FREQUENCY: Each coat
label | 220d1de4-aeb0-4f6f-a611-959b2417b64a |  | note | CATEGORY: IP
label | 4f70cdc3-1820-4f07-9987-0229efb04600 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dabb6bb8-7d1a-4361-aba7-4f58f573e26e |  | note | VERIFYING DOCUMENTS: This ITP
text | b2a6cee2-6ded-4f9b-a2c8-68388c7945fa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Wet Film Thickness (WFT) Testing
label | 53f373e5-daa6-4ec9-b0ce-bb10d68c9457 |  | note | REFERENCE: Coating System TDS
label | 8e53cca0-e6d3-4575-8949-e2659dd9395c |  | note | 685.12 (b) (ii)
label | 8cc93072-9261-461d-8251-880702460daf |  | note | 686.14 (b) (ii)
label | a71a3b0d-8990-4b7e-82e6-330f15f2643d |  | note | ACCEPTANCE CRITERIA: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | 2096f1d4-fe2c-4ed2-a6d1-1b1d79f14221 |  | note | Attach: WFT Test Results
label | 46e298be-6901-4aae-93b3-1ad8e2079162 |  | note | METHOD: Test
label | c073266d-0f93-47ae-bb07-14fb49bb7064 |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 9d33bf05-a682-4194-bd42-3995620ea488 |  | note | CATEGORY: IP
label | 4ad731af-48d5-47e7-9b77-d0c4b7133755 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 79931c9d-ccb7-4dde-8a37-49fc29add9d4 |  | note | VERIFYING DOCUMENTS: This ITP
text | dda8ece0-d1e3-4eeb-951c-e7d173c4ec4b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Inspection & Defect Identification
label | e2258be9-39de-45bf-9880-a6bf5d84aaed |  | note | REFERENCE: 685.07
label | ad050be8-82a3-4c83-9ca1-16ee662f5fe3 |  | note | 685.13 (d)
label | a6671ff7-a8fe-417b-aa99-67b0502b80d8 |  | note | 686.07
label | 877ec1a5-a1d0-45a8-9014-1412952cfc93 |  | note | 686.15
label | ee86c164-d9d7-47f1-8a08-1a408d7331a9 |  | note | ACCEPTANCE CRITERIA: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
label | bfc2a302-5a45-4d83-8e02-95b766487e93 |  | note | Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | 6b5fd178-1aa1-40e0-b5a1-ab4fb3ce43fa |  | note | METHOD: Visual
label | 9e80fe3b-8d04-418d-aaa6-b1c28f46297f |  | note | FREQUENCY: After each coat
label | d7243b9a-3779-47a3-aed9-be2720ae74b1 |  | note | CATEGORY: IP
label | a5d30d9d-9cd7-4381-8ff2-74915b2c2bec |  | note | RESPONSIBILITY: SE/PE/SPE
label | eba0a17f-a5f6-42ad-8882-652ab6da489e |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b6533a0-11d4-4683-9ed9-60854e609e15 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Drying and Curing
label | c853ce90-f62e-485c-a3a7-abcf3ace6514 |  | note | REFERENCE: Coating System TDS
label | fb79fb91-a8f2-48cf-9aa3-96e989434816 |  | note | 685.17
label | 64d1ad5a-e027-4b7b-bfe2-5fe28a951a25 |  | note | 686.10
label | f7df2153-97a5-45f6-801a-89bae29fad68 |  | note | ACCEPTANCE CRITERIA: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | 3f83dee3-15cb-4682-97bb-c0876eceb45c |  | note | METHOD: Visual
label | 74353c76-29cc-4da9-9a4a-0158633edd5e |  | note | FREQUENCY: After each coat
label | 9f51c145-d06a-4c70-9a74-381086aec181 |  | note | CATEGORY: IP
label | 2c806dbf-ad2d-4f14-84b4-9e2e5903176e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 388c2707-402e-443d-b7cf-0c4ef009b343 |  | note | VERIFYING DOCUMENTS: This ITP
text | 22f24f9c-66d9-4532-88d2-5893d746daf3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-application Activities
checkpoint-status |  |  | checkpoint | 5.1 Clean-up & Waste Disposal
label | 5db4ec95-27e4-4cca-b9b2-237a423bfe7b |  | note | REFERENCE: 685.09 (c)
label | ea22c4ab-2ab7-4b9b-bf0e-d658fccaac73 |  | note | 686.10
label | d729c1c3-c6e8-4119-9585-c1755435be6d |  | note | ACCEPTANCE CRITERIA: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated.
label | 4062aa07-685e-40bc-8fe5-902c2e799022 |  | note | All rubbish and remaining coating products shall be removed from site.
label | 0066b895-d962-4a16-b1fc-93d27a9fdda3 |  | note | METHOD: Visual
label | 78e05a62-5b1e-42ef-b750-a10602f2fd45 |  | note | FREQUENCY: At completion of Works
label | 56ab64a6-5226-465e-9f54-91f2c6c6b287 |  | note | CATEGORY: IP
label | f85e6c39-7c9a-42d3-9af4-8b0cd7fa5b83 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 79033d86-3862-4c20-bbe8-bc4663112516 |  | note | VERIFYING DOCUMENTS: This ITP
text | 45429641-65ff-45bb-adfd-a716c0713c36 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Dry Film Thickness (DFT) Testing
label | 9d039958-1aea-4c0b-a4a2-c61bb68ac0e1 |  | note | REFERENCE: 685.12 (b) (iii)
label | 2e9a9ac7-53e4-4c0c-9ad1-ea7be4e546e0 |  | note | 686.14 (b) (iii)
label | 6fd11296-b0cf-47ab-94be-a6b9a272a9af |  | note | ACCEPTANCE CRITERIA: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
label | 42dddc60-94dd-4dfa-9612-76a3023eb4a9 |  | note | i. Anti-graffiti system = 100µm
label | 0d817f81-93f9-45f1-9706-c743fc42298f |  | note | Ii. Decorative & anti-carbonation = 150µm
label | dd097644-9b2d-490d-9f0a-5825589b7fb8 |  | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
label | 9bee955b-d57c-4afd-91a3-4fea27d8477f |  | note | iv. Atmospheric & splash zone (dual protective) = 200µm
label | afeebeb9-99c8-49f5-8c58-b439f0376065 |  | note | No more than 15% of the readings shall be less than 90% of the required thickness.
label | 259ac5c2-3e15-41b9-b58f-611a2911cadf |  | note | Attach: DFT Test Results
label | 042d5c72-577c-4d60-8ef0-b8e6e9a2e262 |  | note | METHOD: Test
label | 84713c0a-ec5c-4186-be6d-fbe724b51364 |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 073fdc39-d446-4ccb-9646-42e154121ffb |  | note | CATEGORY: IP
label | 27170505-aad7-42d7-a7a4-2046e4e46450 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f82ee905-9dda-4ef5-817d-94a9c973a8f4 |  | note | VERIFYING DOCUMENTS: This ITP
text | bf60923c-8e06-4c20-89b6-3f6e9acb89c8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Adhesion Bond Strength Testing
label | ff5a868b-a508-4faa-acb5-ac09dac20c81 |  | note | REFERENCE: 685.12 (b) (i)
label | 677d5a83-a263-44f2-ae52-1e4d03ce40ed |  | note | 686.14 (b) (i)
label | 81427627-1867-4f8e-9e25-117755c5334b |  | note | ACCEPTANCE CRITERIA: A minimum of 14 days after application, the bond-strengths between:
label | b2afe8a0-107d-426d-aefd-8a59105229fa |  | note | i. the coating system to the substrate, and
label | 11b71ce1-8477-4f2c-82cc-963dbd36c378 |  | note | ii. Separate coating layers
label | 01464c33-cac1-4dfd-ba9a-4b18971a5f1b |  | note | shall be tested using 50mmØ aluminium dollies.
label | 1d0653be-647f-4981-8029-9556a3d7ed3d |  | note | The subsequent results shall be greater than 0.75kPa.
label | 48c3a348-5766-4f42-8f3a-82a7c3f9ef0d |  | note | Attach: Adhesive Bond Strength Testing Results
label | 5b5e732c-bc42-4633-9c0c-e8a9ea13e105 |  | note | METHOD: Test
label | 0d2fd252-dcb0-4ef9-aaed-c73337d8df5d |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 5963bffa-65f2-480d-8c29-ceaac7f44f2d |  | note | CATEGORY: IP
label | 6846ebc0-ba8d-4ca9-a9e8-22974b57642d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9419f20b-0fee-4223-a5ea-1f9642cfb45a |  | note | VERIFYING DOCUMENTS: This ITP
text | 7710537e-25ff-4940-8ed4-75a820d78f4f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Penetration Depth Testing
label | 46fd9986-859e-4cdf-a398-8c76a2da19cb |  | note | REFERENCE: 685.12 (b) (v)
label | 619a9e31-dec6-40e8-9610-b20a47454f1c |  | note | 686.14 (b) (v)
label | cb51f0c2-0a7c-4158-ac19-73b323d01b7e |  | note | ACCEPTANCE CRITERIA: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
label | 649e2cd9-b844-4d8c-b461-2dadb2d17b1f |  | note | The subsequent results shall be:
label | fe662260-2bae-40f9-9a09-437455cd2e0f |  | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
label | c65fa072-ae70-432f-bc2d-4e81a1015443 |  | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
label | dec2e6d9-97d8-4e10-81b5-376842929d40 |  | note | iii. Silane-Siloxane or Siloxane = 3mm min.
label | a51cbfe5-1614-482c-822d-369f59294f9b |  | note | Attach: Penetration Depth Testing Results
label | ac96b4eb-145c-4394-94c4-f7a04cda6fdd |  | note | METHOD: Test
label | 0d1c32a0-37df-49c8-8170-fdea97d782c6 |  | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | 19cc549b-db42-4fd0-bf28-fa3743f75c52 |  | note | CATEGORY: IP
label | 7cf71548-778a-4a45-ab5b-2949367c889d |  | note | RESPONSIBILITY: SE/PE/SPE
label | b7739dbb-d744-4bfe-a21c-06ac59d396ec |  | note | VERIFYING DOCUMENTS: This ITP
text | 24a386c8-c256-4270-9f56-c2f9feead84e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Non-conforming Coatings
label | 9cdbe2c7-1c5f-441c-a446-ae232d843dce |  | note | REFERENCE: 685.14
label | e5079f71-1520-4c1c-98eb-60c741349764 |  | note | 686.17
label | 565e9b3e-ce2e-48f0-8351-a5ebe8816853 |  | note | ACCEPTANCE CRITERIA: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired.
label | 4eefffcf-1d60-4db4-b72d-1713aceb5dee |  | note | Such Work may include removal of the coating, surface preparation and re-application.
label | f0da2001-f7d9-45ef-bced-2bfa88b0819e |  | note | Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | 90415fcf-8afa-4b7e-9c1d-e6f5a7d136fa |  | note | METHOD: Visual
label | 4b4c73ca-2a1e-4849-9eb8-b8e9f0dee765 |  | note | FREQUENCY: Where required
label | cb7c3de5-629a-42bd-b926-c19791352a7b |  | note | CATEGORY: IP
label | 7af698a8-a988-44c5-aa3b-4760c3888c1b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1ea259a8-454f-4a72-9d4c-f47a94a685b4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 869f1748-28dc-4b4e-80be-45967da1ea96 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Coating Application Guarantee
label | e25ba8b1-7a4a-4219-9874-a33f27cead0d |  | note | REFERENCE: 685.06 (b)
label | 93edda75-e723-4a3e-9b88-f8018f6b6ed2 |  | note | 686.05 (a)
label | c5c0052a-46f5-4b7a-8aea-79ab034e8dfb |  | note | ACCEPTANCE CRITERIA: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | f564e777-a7ca-4cf8-8500-f2d8380ec36e |  | note | Attach: Coating Application Guarantee
label | a52c6697-8451-43f0-9ba2-f2cd652cb7a5 |  | note | METHOD: Document Review
label | 149bbd75-7030-4e24-8b48-58ecb744d7e2 |  | note | FREQUENCY: At completion of Works
label | 728b5e91-22ba-4d36-9834-65034ca7d660 |  | note | CATEGORY: SP
label | 3c7e7065-5cfa-47f0-89d4-82268acdcf12 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3f83c022-9bbf-4541-ab1b-9bff57b31709 |  | note | VERIFYING DOCUMENTS: This ITP
text | 897f8c41-59e2-42c0-a87c-d3cb3f2f594b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Repair to Damaged Coating
label | eb3e7f63-e4fb-4426-b0ca-e0110cb600da |  | note | REFERENCE: 686.17
label | 3babf7fa-ea48-4a93-9c60-c8c769b0c86e |  | note | ACCEPTANCE CRITERIA: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | 9dab263c-db9f-4fe6-af62-b6c13d252652 |  | note | METHOD: Visual
label | 591d76e5-a744-47a3-a373-636175f47e81 |  | note | FREQUENCY: Where required
label | 9f9de45f-83b2-40a9-a9d0-5ec253154ce3 |  | note | CATEGORY: IP
label | 4ea90efe-cc97-4753-9cea-9cb6c04bb8fc |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4b5b54d1-205d-4562-aeb5-d3699e3f983a |  | note | VERIFYING DOCUMENTS: This ITP
text | 4b66ed4c-f40f-4e7c-9f47-3bc002464a22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Non-conformance Report (NCR) Closure
label | de810eab-e662-4de6-b9d5-c38a85328d26 |  | note | REFERENCE: MRPA Quality Management Plan
label | 8f5f6320-f4b2-4b48-9658-58747d51d55f |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 4bb1f13e-213c-4d43-b8a0-7979064fc477 |  | note | METHOD: Document Review
label | a79e9def-a9bd-4474-be39-eb0e3237032b |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 92f8242b-be71-4b42-8c4c-7281bf52475d |  | note | CATEGORY: HP*
label | e32cbb17-d90d-4f3d-aa67-938196657756 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f97e76c6-e809-4bda-93ff-f9fedb7c3175 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4951259b-9f2d-4b49-ba7e-dd8e1f3d3521 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | a6319194-3b59-49d9-a488-9d95bcc75c5b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 076397fb-9de7-4b72-81ea-dc445c5de87e |  | textbox | Name:
text | 94693b34-0598-4d45-b7ea-ea52f2456494 |  | textbox | Position:
text | 663f2a80-db6a-4462-8f3d-dab995909763 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | Stormwater - Pit Installation Rev0.0 | itp |  |  |  | Yes | Stormwater - Pit Installation Rev0.0 | 99a129f0-0b88-46b1-b102-4fbc471140bd
checkpoint-no-status |  |  | checkpoint | Document Reference
label | 4f8b36f1-28cc-4d8d-9ae5-8b35896477e9 |  | note | VicRoads Standard Section 701 (April 2019)
label | 13be4730-78f2-483d-bb02-0e753d67b7f3 |  | note | VicRoads Standard Section 705 (October 2018)
label | a4966234-94ca-468a-9d21-724dd142a498 |  | note | Revision of ITP template: Stormwater Drainage_00
label | d09919b6-f06b-43a1-ad21-a375a617704e |  | note | ITP template approved by: Michelle Edgar, October 2019
checkpoint-no-status |  |  | checkpoint | 2.1 - Pit Details
select | 60cc15e3-e920-4d98-8826-f9b240f419c1 |  | dropdown | Design detail: | Modify existing pit,New Pit and Line,New pit on existing line
select | 273ed96d-a274-4f41-a7c3-0c665efa5472 |  | dropdown | Pit Supplier: | Aus Pits,Cast in Place
select | 66759763-96ae-4e7e-90cf-5a7582111971 | DataPoint is missing 'select' values | dropdown | Pit Lid Type:
select | dd726015-e7aa-4dfe-94bc-4d897718833f | DataPoint is missing 'select' values | dropdown | Pit Lid Class:
select | 6884a8f3-1161-4466-bcd3-891e57a1b7d9 |  | dropdown | Pit Type: | Headwall,Junction Pit,Side Entry Pit
text | 9c68e6ce-eec0-4507-b230-f66aff13e47d |  | textbox | Product ID
label | 9ef132ac-f9fc-41fb-a82a-6570ea7ed07b |  | note | Record Line Number from IFC Draiwngs (suggest to use in Lot title)
label | d284829a-7a1e-4ed0-a195-68d5c57db067 |  | note | - - - - - - - - -
label | f172cc56-3301-44cb-9e5d-35fdd2f5b23a |  | note | References - 705.05, 705.09
checkpoint-status |  |  | checkpoint | 2.2 - Excavation
label | 77294ba3-00cb-41a4-894e-0e1247b0d4a2 |  | note | Excavation to design depth. Foundation is satisfactory.
label | 333d5675-e1e9-42e3-820d-d334076faa2f |  | note | For precast pits clearance provided to each face of excavation is not less than 400mm
label | 13b78715-daa8-4179-bab0-9a1a171e38f1 |  | note | Bedding for precast pits meet requirements of 701 and compacted to refusal. 80mm for clay and 150mm for rock foundation.
label | 4512bec1-8946-4a41-bc8c-b3463f037448 |  | note | - - - - - - - - -
label | 9a92a88f-09dc-4f4e-b027-80c55bdf4752 |  | note | References - 705.05
label | 93949e53-6838-4310-a1df-8ab6de8975e6 |  | note | - - - - - - - - -
label | ea8c838a-4ba8-464d-be5f-c07f2dcf6e0f |  | note | Verification Record - This signed ITP
checkpoint-status |  |  | checkpoint | 2.3 - Placement of Pit
label | a06565d8-8f64-46e4-8ef5-66e7916b376d |  | note | Survey pick-up to verify
label | 4bcf84f3-03cb-4565-9cff-0a72ac9de9de |  | note | Offset pits to kerb +/- 20mm
label | 3112fcac-e758-488b-a0ec-43b9996e445c |  | note | Plan location pits not adjacent to kerb +/- 100mm
label | e0c91bc9-0e98-46f7-907a-ce273cce3251 |  | note | - - - - - - - - -
label | 39e92d6b-fb32-4fa8-bb22-2829f19d176a |  | note | References - IFC Design, 701.09
label | 246a0386-4f8e-4bf1-881a-ac9687baaa6a |  | note | - - - - - - - - -
label | 3fcca405-e3bb-424b-9002-3a32a6d0e18c |  | note | Verification Record - Survey data included in CAD master file
checkpoint-status |  |  | checkpoint | 2.4 - Pipe drainage connections and jointing
label | dc9d7bea-ed31-4680-ba62-8c4c024c7fa2 |  | note | All stormwater connections to be neatly made. Where nessary, trim ends of drains and finish with cementitious mortar
label | 42604336-90dc-40e1-97ed-b0a70fe79cd4 |  | note | Openings to be neatly saw cut to required size, not to exceed pipe diameter by 50mm
label | 82cf33bc-443b-45bb-ba0f-5f081b0b029b |  | note | Reinforcement exposed by the cutting of holes shall be coated with epoxy.
label | af49cf77-c93d-44d6-b48b-27d78e01fe1c |  | note | - - - - - - - - -
label | e592e6fa-56de-4e60-806a-f666371fc818 |  | note | References - 705.1
label | 98346a30-3a76-4336-870d-d92527b70fcf |  | note | - - - - - - - - -
label | 02ec631a-fcea-430b-a885-ac4aeeb1612d |  | note | Verification Record - This signed ITP
checkpoint-status |  |  | checkpoint | 2.5 - Shape pit floor
label | aa633ba8-f16c-40bf-86a6-979967d899cd |  | note | Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | 246561b1-7704-4ed1-8b2d-a7a99847e458 |  | note | - - - - - - - - -
label | a562fcf8-6dda-4c09-8d55-935e88c4593f |  | note | References - 705.12 VR standard drawings
label | d486994c-ee2e-4201-9f99-6efc52bd91cc |  | note | - - - - - - - - -
label | fe20caa0-7641-41a2-92c9-032f8c61abd5 |  | note | Verification Record - Ths signed ITP
checkpoint-status |  |  | checkpoint | 2.6 - Step Irons
label | ededd44d-955a-4e3f-b0a0-25f24c9c810a |  | note | Requirement TBC.
label | a5a557eb-ef82-49ae-8791-89fff34a37a7 |  | note | - - - - - - - - -
label | fa7fcbda-16b0-463e-abd8-6ec96de8ab5f |  | note | References - 705.11 OR Advise from VicRoads operations team
checkpoint-status |  |  | checkpoint | 2.7 - Fitting of covers
label | 251f6faa-7520-49cf-8ea1-8482953b8e68 |  | note | Cast into top of pit or beddded on fresh mortar 5mm thick. 2 parts sand, one part cement and sufficient water.
label | a972d80d-57e0-45d4-8b5f-5090393281ff |  | note | - - - - - - - - -
label | d4145075-5370-4936-8bc0-77a4bbb47e48 |  | note | References - 705.16
label | 46ac57f5-0a94-4d78-91cd-4172b7aa6a95 |  | note | - - - - - - - - -
label | 28e4ed55-ab01-46f8-a90a-648edebfb483 |  | note | Verification Record - This Signed ITP
checkpoint-status |  |  | checkpoint | 2.8 - Backfilling around drainage pits
label | a01ba5d0-2c56-4a6f-8b6a-356510016a3d |  | note | Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment
label | a5d200d8-87fb-49b6-ba03-1178b7120332 |  | note | - - - - - - - - -
label | e24f8309-1d3d-4a9f-adf0-cd54d4efb987 |  | note | References - 705.17
label | 598f7940-a861-4788-bf8b-91b3116b0508 |  | note | - - - - - - - - -
label | 77c988b4-2ef9-4421-9143-b1f01d0fed30 |  | note | Verification Record - This signed ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1 | itp |  |  |  | Yes | ITP-CIV Type A - Roads (Supply and Install) Rev 2 | 9ae58ec2-a495-4865-ab11-e919fef1e847
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 219d439f-ddf0-49ca-8216-5eda342d520a |  | note | Document Title: ITP-CIV Type A Fill - Road (Supply and Install)
label | 09929009-dcd4-46d4-9752-761ec78464ec |  | note | ITP Description: Type A Fill - Road (Supply and Install)
label | 2d3d2701-1923-4241-a254-8c94bb310c98 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 8afcfe72-198e-4298-adcf-4d9c4f81a175 |  | note | Revision Number: 1
label | 0c899010-3dc0-4247-9b45-c25f6faac4bc |  | note | Revision Date: 8/07/20
label | 0a64eec8-eed2-4eb4-b918-82aa5f48dd1f |  | note | ITP created by: Patrick Cusenza
label | 68f2f666-c2cd-4621-8cd5-8e77d20d5572 |  | note | ITP approved for use by: Josie Pavlou
label | 908d3433-587c-493d-a210-12c86eb49dd5 |  | note | 1.1 - IFC Drawings
label | fb0a7ed8-08c8-4b53-bcb6-306c58b80f76 |  | note | VicRoads Standard Section 176 (Sept 2008)
label | f8d5b79c-76dc-42bd-9df7-379501253d86 |  | note | VicRoads Section
label | a93042c5-ce6f-4dc8-a39d-cb7ea9f53f7e |  | note | 204 (Dec 2015)
label | 167433c3-5c86-41c5-ae8a-d5dbe3945a4b |  | note | Code of Practice RC500.20
label | 9bed7f54-a292-4583-a70d-69eeed77ba4e |  | note | Code of Practice RC500.5
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Material Conformance
label | 42547e9c-c2e0-45d7-8ab6-ab7117d26f7b |  | note | REFERENCE: Section 204.04 b)
label | af1d2486-1bd5-430b-b7aa-893ec48a5760 |  | note | Table 204.041
label | 0cfdab94-781e-4892-9f03-0527319984d7 |  | note | ---------------------------------
label | 0f479c18-23c7-4216-b582-de44b5451e33 |  | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 3b010a35-7542-455b-aaa8-61122a5ac9ce |  | note | Assigned CBR≥%8%
label | 0d36e2fc-dd2d-4f09-965a-28027e2bea4e |  | note | Swell ≤ 1.5%
label | e109b111-2e1f-4be0-be57-9bd5f2983b9c |  | note | Max Permeability = 5X10-9 m/s
label | d589edc4-f996-4716-8c2b-2a064d45c0dc |  | note | Grading: 75.0mm 100%
label | a7fb5b76-f7aa-4e9e-bdb9-56ee007aafe4 |  | note | 4.75mm 40-80%
label | e0349b15-551a-434b-a706-c4806aa48d99 |  | note | 0.075mm 10-40%
label | bf45b632-0091-417c-8a82-e027f6677f3b |  | note | ---------------------------------
label | 4f812e72-58c5-4486-af77-fa6b16c8e40d |  | note | METHOD: Document Review
label | 4973117d-4eef-4b92-96a0-0d5945c92a67 |  | note | ---------------------------------
label | e516d65d-ca74-4580-b5c0-362d9625504e |  | note | FREQUENCY: Once, for each material type
label | beccf82c-18be-4962-a215-d37cb0d2aa23 |  | note | ---------------------------------
label | e5fa5fc0-60b3-4238-b2cb-30bb5e8e3a2e |  | note | CATEGORY: HP
label | 7c2796ec-5154-4357-ba3a-dfb2239d6f1d |  | note | ---------------------------------
label | 9be23f25-ad8c-472f-9f59-814319e0fb1a |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 173bbd53-02df-445e-8398-3cb8a002daa8 |  | note | ---------------------------------
label | 376e1eb2-046d-4505-8bd8-3f090a507fb9 |  | note | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
text | 357c0388-73f1-485b-aa2f-10c33f81a737 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set Out
label | 0df6bffc-e42f-45bf-bf65-915c692f3d30 |  | note | REFERENCE: Design Drawings
label | c66f1132-4e19-4e8d-b210-7b0667695097 |  | note | ---------------------------------
label | 370908e9-2e9f-4ae1-b135-b5c11b190d3a |  | note | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | f334377e-711d-4441-b4c5-0abf32bb17c5 |  | note | ---------------------------------
label | 2d37f062-7696-4d14-8aa1-f6e118f8e699 |  | note | METHOD: Visual Inspection
label | 68d8ad05-8863-4f7d-9e33-c43a06eef07a |  | note | ---------------------------------
label | 18e7b653-916a-47c6-a8dc-8edfb66f8363 |  | note | FREQUENCY: Each lot prior to commencement
label | ab7e4f0b-911a-44be-a9d7-fb8336bc39a6 |  | note | ---------------------------------
label | 6ee20ca2-0579-4dba-af0e-f377a69879d0 |  | note | VERIFYING DOCUMENTS: Signed ITP
text | 061918c1-d092-46ab-8733-7c4afa230b82 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Pre-Commencement of Fill Works
label | f5f19406-993a-4a2b-a530-3f3975aca133 |  | note | REFERENCE: Section 204.10 (b)
label | 4c3b9028-1ca8-461e-b851-0fe44a9526aa |  | note | ---------------------------------
label | a7597711-3e0b-461a-ad90-ded8f4b8e404 |  | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | b6804ac7-b690-4505-b7d0-c7cb00147eef |  | note | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | a3d48aab-365e-40ba-b3cc-acc08278fb6f |  | note | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | 94492296-ca50-48b9-93e6-2040429b1b0f |  | note | Refer to ITP-CIV Subgrade Preparation - Road
label | bdb5e1a5-68e0-4176-913d-3ebf4e905c4d |  | note | ---------------------------------
label | c811fb2a-8d9b-4265-9dd1-680bde18f633 |  | note | METHOD: Visual Inspection
label | b49d7e32-b320-4a68-a11b-8ad22c2257e5 |  | note | ---------------------------------
label | d7043bc7-d23b-4bbf-9cb0-72dd86fe68ce |  | note | FREQUENCY: Prior to commencement of fill works
label | de502fe5-20cd-41b8-8c15-5a4bc9971e66 |  | note | ---------------------------------
label | dfa464d9-d3c2-43b3-a3e6-ea1baadc5977 |  | note | CATEGORY: HP
text | 1a88b67c-f9a2-4d6a-9f8a-2f3aba8fb835 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 4.1 Placing of Fill
label | a44726ad-2ccc-4ac9-929e-6aaf64efef78 |  | note | REFERENCE: Section 204.10
label | 38d95a9a-f1c9-4011-b5df-081bf1104103 |  | note | ---------------------------------
label | 79ae5220-512c-4472-89e7-3f3efe58d5f9 |  | note | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | 2706119b-af09-4ea7-a5d6-08d9e710c11a |  | note | ---------------------------------
label | 2a6cd35e-68cc-48f9-b341-a81756e82956 |  | note | METHOD: Visual
label | 4edfb2ca-4173-4086-b12b-78a5e06fe2db |  | note | ---------------------------------
label | 4b636ddd-320e-40be-a333-a47665ae4079 |  | note | FREQUENCY: Each Lot
label | 87693c2d-4eaa-4ac6-beb0-91e63f942d9c |  | note | ---------------------------------
label | 6366be23-e927-4431-a389-14f20bfaf4d6 |  | note | CATEGORY: WP
label | a65611ca-4993-4628-aa04-98831077e2b0 |  | note | ---------------------------------
label | 2c83d07e-75c8-4b94-934d-df45c4c5c0a2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | a4a46bab-689f-4681-83d3-b5fa721ad979 |  | note | ---------------------------------
label | 2e5bb2c6-366b-4c10-a8da-278d801fec3b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6a1c7457-829d-492f-9177-2dc11f512637 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Test Roll
label | 75d6575f-6329-4392-8906-8630bf9f0162 |  | note | REFERENCE: Section 173.03
label | 678c69b2-1a11-4e1a-b958-535349ceb6a0 |  | note | Section 204.12
label | 4910082d-57b0-498c-8ae0-07c9e4f98216 |  | note | ---------------------------------
label | 057b94e0-13f2-4b22-ae90-2d93df803b0c |  | note | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with
label | 3426f03b-04be-4138-af05-f81e4cf5bb5d |  | note | Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 0378aa55-3b80-4c0c-8eb2-5fc2a61b8a85 |  | note | ---------------------------------
label | ad150cc0-7233-4b0c-a85a-0bfc1cdd110d |  | note | METHOD: Test Roll as per 173.03
label | e7a69b63-6085-42f8-826a-e7a28ace5683 |  | note | ---------------------------------
label | 658300ae-8d8d-46ad-85fe-45a0664e8530 |  | note | FREQUENCY: Each Lot/Layer
label | b070a571-bec7-4dd2-afb0-f16c28558c76 |  | note | ---------------------------------
label | 2ceba451-731c-4799-ba5b-7a305ebb71a3 |  | note | CATEGORY: HP
label | 29d70c61-08b7-4a26-9938-92f53be44b6f |  | note | ---------------------------------
label | d45677c7-dcc6-4823-a324-165248e6fbf9 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 93aa9547-186a-402b-a63b-84c6ed8391a6 |  | note | ---------------------------------
label | ed7504fb-1836-4c72-a103-46d421acf621 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 2bbb7272-3999-45ab-aa8e-ab2ceb1689f9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Compaction Testing
label | 7eba1e98-37bf-472d-aed8-c939b57ab24b |  | note | REFERENCE: Table 204.131
label | 2bbd22de-5da2-4cb8-a376-918dcb1574ba |  | note | Section 204.14 c)
label | d7cc5b20-a948-4b16-9e18-ee3e79081012 |  | note | Table 204.142
label | eafe4e3f-9f03-4ecb-86dd-27a4344192c4 |  | note | ---------------------------------
label | 738e8dec-4e1f-4b42-8b68-22e71ebce8e6 |  | note | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
label | 5a09891b-da46-49b4-be5a-f341a00875a9 |  | note | Standard Compactive Effort
label | eb92d6f8-00d6-4f97-afc0-bbe1c7e9b83b |  | note | Compaction and Moisture content
label | 48bb0c0e-3549-4573-b907-891361acaa92 |  | note | Scale A: Characteristic Density Ratio 99%.
label | 4f0e7d31-42c4-483d-bfef-f1db74d11740 |  | note | Scale B: Characteristic Density Ratio 98%.
label | 0e32aef7-d0e5-4b3f-855c-e1919294ee6c |  | note | Lot size - the leser of one day's production or 5,000sqm
label | 6d67d4bf-979a-45a3-9303-464e01c9d168 |  | note | ---------------------------------
label | 5d218863-1eb1-415d-ab29-ab7d781681d5 |  | note | METHOD: Review Document
label | fd5c9f8b-0f82-49d1-8590-e40fa904ac41 |  | note | ---------------------------------
label | a3592c64-a632-4668-9a77-070153a8b60b |  | note | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | fa9ebe1c-8bbc-424f-a18f-ac64eface7ef |  | note | ---------------------------------
label | b343511c-4505-4e4e-8c8f-ab791f093b4a |  | note | CATEGORY: IP
label | 6421c93f-d98d-42e3-b925-7bebceaa5eb5 |  | note | ---------------------------------
label | 17d6dc4d-7781-4b18-bfb5-2f1d54368239 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4e2e56e8-e1a2-473d-b215-9f52fb2e14b0 |  | note | ---------------------------------
label | 323d7ec9-46ae-4bd9-859e-25f4d92032b8 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Compaction Test Report
text | 734bf24a-1416-4304-a560-1738f3affb13 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Post Compaction Material Property Testing
label | 43f66991-589b-4474-8f26-c5b70e34490d |  | note | REFERENCE: Table 204,041
label | 140b613b-4d4d-4152-b869-d23ba77cc89e |  | note | Table 204.141
label | 5ae143b0-3771-40f3-acf6-080c0cc04071 |  | note | Section 204.14 a) or b)
label | b2d7d8fd-6d1c-4a86-a930-445884d75f52 |  | note | ---------------------------------
label | 0b7a6c39-8751-4d1c-b335-fc388a2231a9 |  | note | ACCEPTANCE CRITERIA: Material Properties:
label | 6426037d-7981-42eb-8648-14204cd5052e |  | note | CBR ≥ 8% and Swell ≤ 1.5%
label | 6494dff9-fc88-4af4-833b-f2b469830f9e |  | note | Max Permeability = 5X10-9 m/s
label | 6973cef3-cda6-4b62-b975-46232743a57e |  | note | Grading: 75.0mm 100%
label | 0971e328-3f80-4646-a3fd-ebdb8ddb2dbd |  | note | 4.75mm 40-80%
label | 648ffd46-4052-42c9-88a4-849fc4b984bb |  | note | 0.075mm 10-40%
label | 2194e04b-4aa7-4e6a-b2cb-a3afd58357bc |  | note | Max. PI x%Passing 0.425mm = 1000
label | c9068f8b-7803-4bf3-a47a-4e2533c16f43 |  | note | PI = 6 to 25
label | 7535fe25-4cee-4f68-a9d0-d96aaa637b8b |  | note | Scale A:
label | f07c7716-3cf2-442d-bc78-a8f621401183 |  | note | CBR & Swell
label | 0f7c3138-f4be-4308-aa2e-2d1bedf44ac7 |  | note | Initial - 1 Lot Test to determine Assigned CBR and swell
label | 9ac73700-d385-4ba3-b600-a331521fb132 |  | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | d83dabfb-c542-466e-bd5d-1f4e549ad218 |  | note | Max Permeability
label | 1495640d-267c-4ec7-8573-64072eb66396 |  | note | Initial - 1 test per 2 lots
label | 8f05969e-6595-46b4-8473-7984abaff49c |  | note | Reduced - 1 test per 4 lots
label | dc3dbf41-273d-47fd-b093-2411f485c33a |  | note | Grading:
label | c06552d9-1035-4b95-9526-f4c98feeda7a |  | note | Initial - 1 test for each lot tested for compaction
label | 28e66ff7-b799-467e-ba53-cb763238ac87 |  | note | Reduced - 1 test for every second lot tested for compaction
label | 4eca4b3b-d631-4234-a083-a5eff33e0fbb |  | note | Max. PI x%Passing 0.425mm & PI
label | f95b4a63-1a40-4e2b-949a-69aaf78e9ae6 |  | note | Initial - 1 test per 2 lots
label | c5d78da3-70b6-4fb7-b394-0f5b6e962da5 |  | note | Reduced - 1 test per 4 lots
label | e4b23851-1b00-4320-bd06-b634573db7ce |  | note | Scale B:
label | 1f15857b-6f92-4ea7-9106-3bb155e3c150 |  | note | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 34c1d0f6-195d-4b65-b1b7-fba1850a3275 |  | note | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | c8f9e8a4-0149-4457-8e21-2bc004e41d7d |  | note | ---------------------------------
label | 94918d22-db18-471b-98c0-91698f66f2ac |  | note | METHOD: Review Document
label | 43820ba7-ea11-4e71-8c85-693c55cb42ed |  | note | ---------------------------------
label | a18458e9-c67f-4a9d-b61c-406a5c87fe10 |  | note | FREQUENCY: Refer to Section 204
label | 1b2909ce-bbe3-4d02-af46-755ec4656f2d |  | note | ---------------------------------
label | cee5c35c-c478-4030-a289-25ca93642c23 |  | note | CATEGORY: IP
label | 5da16fba-9624-4c0a-a118-483967680852 |  | note | ---------------------------------
label | 6ab86650-c57a-48b0-bd87-4b43827feac0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fc63a1fc-e691-406e-b073-6fe805c5fef4 |  | note | ---------------------------------
label | 5b90ed4b-0dab-40b5-ac98-e96416161b2a |  | note | VERIFYING DOCUMENTS: Sign ITP Attach Material Property Test Report
text | 6bf9d139-7947-4542-8d88-d76239e114ed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Preparation of final surface
label | 39518ab9-935f-4969-b2c9-1a047f05b801 |  | note | REFERENCE: Section 204.15, 204.03 (g)
label | f831e189-5275-440a-aac8-e69a33876bb9 |  | note | ---------------------------------
label | 3584ddc1-85fc-4882-bef7-c26d50f7e669 |  | note | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | b7ef2000-be4b-42da-a681-7b95601772c8 |  | note | ---------------------------------
label | 1792068f-871b-47a9-8e62-f10ffa4bb5c5 |  | note | METHOD: Measure
label | c6315073-881f-4570-8544-a8897bb42cad |  | note | ---------------------------------
label | b0909279-f843-45c8-825a-3fdd71cae347 |  | note | FREQUENCY: Top layer
label | 40761473-5969-4d85-b242-a75d010d2460 |  | note | ---------------------------------
label | a5ed9020-fa32-4bfd-badc-5e3de6f6e1ff |  | note | VERIFYING DOCUMENTS: Signed ITP
text | 8d9e6b07-6de7-4081-8235-30b396e82ebc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Survey Conformance
label | 74c733df-da93-4e5f-b0cb-ee72a9a26e34 |  | note | REFERENCE: Section 204.03
label | 08775571-f557-4aba-8276-d6a6b55bd8a9 |  | note | Table 204.031
label | 1ed1f88e-62c2-4144-abb1-9ffa56003850 |  | note | Section 204.16
label | f411fbec-394f-4931-b564-fe3b253b44b5 |  | note | ---------------------------------
label | 645a5aef-5e88-4ff6-b38a-5c4774cf1f9b |  | note | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the drawings within the limits outlined in 204.03.
label | 24f638f0-4536-47d0-8452-f1dffcdfe642 |  | note | Scale A (Princes Highway):
label | d9caf690-74a5-4461-a5ca-a7c9af6ba867 |  | note | Min. 80 measurements per lot tolerance from theoretical surface level;
label | 75cdf1f3-6b78-4fd0-8fa4-e6babb4a2e6e |  | note | x,¯ range (mm) = +5 to -15
label | 8aabb123-f103-42b3-a4ed-6377d013fc78 |  | note | Maximum S (mm) = 12
label | 0471ad4e-f849-4ff7-88b1-ceee9a2c4e4a |  | note | Scale B (South Gippsland Highway):
label | 27b2fb24-8117-4462-9267-a88a50ee75da |  | note | Min. 40 measurements per lot tolerance from theoretical surface level;
label | 1bafcdbb-5905-4d12-b8d3-8081bd72347b |  | note | x,¯ range (mm) = +5 to -25
label | 3028f528-9f66-4aca-8bd0-0796b052ecb7 |  | note | Maximum S (mm) = 15
label | 4517a37b-a62f-4440-8dd3-592c4fcb5069 |  | note | ---------------------------------
label | c54afb63-6b0f-4ae5-9e44-30f83ddd095e |  | note | METHOD: Document Review
label | f0b91cef-7421-4598-b190-92488dcf16f9 |  | note | ---------------------------------
label | 2a26051b-a928-4aad-b5c5-f89a96d6cb7e |  | note | FREQUENCY: Top of Type A/Verge
label | f0549f21-d125-4db1-b9d9-e53c7119a8b8 |  | note | ---------------------------------
label | 563a7d6f-9385-47c3-bae9-2dbe0359e8e8 |  | note | CATEGORY: IP
label | edef4f99-512d-4a26-add1-2df4fa601666 |  | note | ---------------------------------
label | 5084883a-a622-4d8b-8294-1524d8070a1a |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | eca7dcc2-2fd8-4198-a6d2-ea25aac4d178 |  | note | ---------------------------------
label | 18bf0ae1-5091-4574-b885-440281f0442d |  | note | VERIFYING DOCUMENTS: This ITP Survey Conformance Report
text | 5501b81b-11bc-4ced-8226-64bf8e17837c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | 9d107f59-d768-4f8b-90da-d2d373e46967 |  | note | REFERENCE: MRPA Quality Management Plan
label | 366a44cb-e607-4cea-86ac-2dcab5c81ed4 |  | note | ---------------------------------
label | bf30af91-cb89-4ace-8271-3804aa6c4b03 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 6125d760-9dac-43be-ae6b-6a59a60e9c88 |  | note | ---------------------------------
label | 227a6304-fac0-4add-8165-915645ca2c66 |  | note | METHOD: Document Review
label | 35574fce-7fde-495a-95ba-166ef7227904 |  | note | ---------------------------------
label | cc377d2a-d13b-47f0-a639-252b235852c5 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | d03c2671-9ec0-4f66-8d5b-528cc121255e |  | note | ---------------------------------
label | 797d5660-6639-4273-bb4f-16d40e863a8d |  | note | CATEGORY: HP*
label | e0579878-e822-4356-8ce2-56e5426333f8 |  | note | ---------------------------------
label | d3355213-d6df-4f69-949f-1a054a9f5b9d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 00c531ae-393d-43b5-abdc-c0d1d7ce3c01 |  | note | ---------------------------------
label | 346e41b4-7726-448f-a295-523a59d0bcc5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1e9c50c7-ffd0-4792-b441-51376a49ebe7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | d896ee54-cba6-45da-a02c-a1333a4349ee |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 04a8c85a-1a11-4bd6-a85c-e1f721aebaa3 |  | textbox | Name:
text | 2f51d681-8707-4c71-9f17-60935bf9e689 |  | textbox | Position:
text | 50c4749e-d7c9-45a1-accf-842b6fdf5f67 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV CSR - Horizontal Directional Drilling Rev 0 | itp |  |  |  | Yes | ITP-CIV CSR - Horizontal Directional Drilling Rev 0 | 9dbf86ab-17d9-46ab-bf74-604f691e99a2
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 3d74ffc1-3a51-4b97-8e8d-2098612bde69 |  | note | Document Title: HDD - CSR
label | 9f0d6878-3b5d-44f1-b690-992c7051873e |  | note | ITP Description: CSR - Horizontal Directional Drilling
label | cf08b9e8-1d27-4662-86f1-d481831b1962 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | fafa3637-813b-4d9d-9c53-b508152e7a89 |  | note | Revision Number: 0
label | 906f98ac-ed6e-43c5-8130-c14ca28a46a7 |  | note | Revision Date: 15/01/21
label | 4e4bf6b6-f66a-4db9-bf95-f3f8f31ba034 |  | note | ITP created by: Thilan Rathnayake
label | 42e70f21-a2c7-4852-a4cc-2b136ad1651e |  | note | ITP approved for use by: Josie Pavlou
label | ae286f1a-64bd-4b3d-8e90-72e814bd95e2 |  | note | 1.1 IFC Drawings
label | 6795fb58-e256-4b70-b151-3d7dec9c40ba |  | note | 1.2 TS-SP-013
label | bc9fd60d-7910-4ff8-8c4e-19c90ca34551 |  | note | 1.3 L1-CHE-STD-043
label | e9117e31-0650-4e2a-b173-df60bf3cd82a |  | note | 1.4 All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
checkpoint-group |  |  | section | Preliminary Works/ Procurement
checkpoint-status |  |  | checkpoint | 2.1 Check that current revision drawings are being used
label | 05713a1d-42a8-4092-a399-e632bee74976 |  | note | REFERENCE: IFC drawings
label | ffc71a1d-83be-4292-b3e4-eebb72fd100d |  | note | ACCEPTANCE CRITERIA: Drawing revison must be confirmed with the design manager
label | 78dd81d3-d295-4504-9d34-7320fbdfd22f |  | note | METHOD: Document review
label | 52f3fc21-c051-4d1d-bde9-24c9dc50e86a |  | note | FREQUENCY: Prior to commencement
label | 3658a017-5412-46d5-8653-82805a8bc9dc |  | note | CATEGORY: HP*
label | ff6b045a-4039-49d4-9f88-7916b0e9f324 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7d5046ef-e0be-45b7-83d6-c227ab0b1977 |  | note | VERIFYING DOCUMENTS: Design drawings.
text | 46a854b3-36b6-43cd-a72f-e5877de1ff1d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Materials - Draw ropes
label | 229d5299-ae93-4fce-9a7c-9e336ab39ce8 |  | note | REFERENCE: IFC drawings
label | f5c7ba21-6d2f-4efe-9512-d80816f630b4 |  | note | ACCEPTANCE CRITERIA: All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
label | 050eb794-2eba-43f1-a36b-5b2bf9e0b56d |  | note | METHOD: Document review/ Visual
label | 463da566-4835-4061-b62a-79b31011c90e |  | note | FREQUENCY: Prior to commencement
label | d98903ae-c0f1-4651-b6bf-1e0e1533a5bc |  | note | CATEGORY: HP*
label | 09995ed1-5080-4d71-bf30-92c29ec732c2 |  | note | RESPONSIBILITY: PE/SE
label | 1f778d07-cd8c-41cb-9a00-50dc9b4bd6ab |  | note | VERIFYING DOCUMENTS: Material compliance certificate
text | 6672074f-3742-4b5b-8160-1a2148db4fc6 |  | textbox | Team Binder Approval Number
text | b0b8df04-da14-42a5-a79b-2c8260cdfe3f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Materials - Communication conduits (victrack), Signalling Conduits
label | 676d440b-da8b-49b3-aa6a-58edf0b69125 |  | note | REFERENCE: IFC drawings/ TS-SP-013
label | 579c3990-e866-4cfb-b5a9-e717ed688e85 |  | note | ACCEPTANCE CRITERIA: Victrack conduits must be min internal dia 100mm.
label | 14bd3c16-e0b2-41cc-9898-3e12aac0ed14 |  | note | Outside of the conduits must be marked with Communications or Victrack communications.
label | 01b6b852-d83a-4675-9f33-2eec618feb4a |  | note | Bored conduits must be Class 9 HDPE.
label | ac4bd8ec-0a3b-422c-a633-f062e660f654 |  | note | Signalling conduits must be min 100mm internal dia. heavy duty rigid UPVC conduits to AS 3000
label | 4b9be7fd-5539-48fc-b59c-903925b4ca90 |  | note | METHOD: Document review/ Visual
label | 6e8b1b62-2a85-4007-941f-2d403cc910e0 |  | note | FREQUENCY: Prior to commencement
label | d541d7a0-ee2b-4b5e-8eea-ddaa050c7a55 |  | note | CATEGORY: HP*
label | 83baf6c7-e2ef-479d-bda2-83e79dcbbcde |  | note | RESPONSIBILITY: SE/PE/SPE
label | d005a934-a239-4830-abec-5e36dff7ab04 |  | note | VERIFYING DOCUMENTS: This ITP/ Material compliance certificate.
text | 2bb77026-3916-4476-af34-36cc72c4784e |  | textbox | Team Binder Approval Number
text | ea7150c8-1a64-4338-8f68-76c350fcf51a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Materials - Grout (if applicable)
label | 54cd29e1-0387-4a02-8e35-39fd7d530a84 |  | note | REFERENCE: IFC Drawings
label | 53d76d6e-d2ee-4962-848f-505f554a6d43 |  | note | ACCEPTANCE CRITERIA: Grout strength to be 40MPa
label | b0a508df-7390-4582-987a-537130c2c54f |  | note | Grout shall be a high flow, cementitious material.
label | 88f1d735-4524-410d-8a24-75ae25ae5a1b |  | note | METHOD: Document Review
label | 81aea464-84ba-4301-aa36-04fc7bd98b43 |  | note | FREQUENCY: Prior to Commencement
label | 20fe6903-8ad3-45ee-8625-e1e763dc45c6 |  | note | CATEGORY: HP*
label | 9a66934e-f302-436e-a8c2-04887f4b003f |  | note | RESPONSIBILITY: SE
label | 01c4539f-26e3-4245-b01f-025e9483871e |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate and TDS
text | 3199eb9c-de71-4667-a063-6a9ce960a42b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Materials - Marker Post, Plate etc. (if applicable)
label | 3b0c2f17-7a12-4db5-af92-58fc2c0b1b48 |  | note | REFERENCE: IFC Drawings
label | 8db77bfe-b45d-4e4b-b501-6eff9b5d7c6d |  | note | ACCEPTANCE CRITERIA: All steel elements to be hot dipped galvanised in accordance with AS4680.
label | c5036276-772e-43a3-aac4-ff8d7d4423a0 |  | note | METHOD: Document Review
label | 5ce5b1b6-0bc7-4f32-abf7-8d1c3dc3c7a1 |  | note | FREQUENCY: Prior to Commencement
label | ee6ca416-09b6-459b-8514-b9f92c7e2133 |  | note | CATEGORY: HP*
label | 45a49ab4-6c30-4c59-b26f-95a2d0f1238b |  | note | RESPONSIBILITY: SE
label | 6037f19a-0146-423b-ba2e-1f1b98b5944a |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate and TDS
text | 1fd3d29d-1186-4565-bacd-1a7e0756b1f4 |  | textbox | Team Binder Approval Number
text | 91bcae44-8d84-435d-8c78-457378957f9c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | b0e3daba-9c4d-437f-b0eb-6d01bb0f208e |  | note | REFERENCE: IFC Drawings
label | 3ce0f72c-5761-40f3-92aa-e1dbdcbf2dd5 |  | note | ACCEPTANCE CRITERIA: Set out line and level of drilling works.
label | 7e9506f1-4eb7-492c-9f1d-6a1f38d7151e |  | note | Survey to mark out existing services.
label | 713772a4-32f6-4491-8b55-fea018973b88 |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | a62e1315-0d09-48fa-9f78-001e2371a355 |  | note | METHOD: Measure and Visual
label | 637b1468-3beb-4fab-9c9a-8481eaffe86c |  | note | FREQUENCY: Each element
label | 56ce451c-7e87-4c31-aa70-a9bd41282e23 |  | note | CATEGORY: IP
label | f9e15c9f-d40f-4484-9638-91b700370bdf |  | note | RESPONSIBILITY: Surveyor and SE/PE/SPE
label | 58a2da58-c125-4020-bdf1-807a1edeaaa5 |  | note | VERIFYING DOCUMENTS: This ITP
text | eea1409d-fb28-491e-9742-5b09fd97ce60 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Drill rig setout
label | af1d1a76-3314-4859-a729-f76d3fa45ae2 |  | note | REFERENCE: NA
label | b3c217b1-9a92-447a-952c-c8825fd7f034 |  | note | ACCEPTANCE CRITERIA: Location as per current Drill shot plans
label | 55c5a343-cc42-406d-a636-3083634536d9 |  | note | METHOD: Visual
label | e502e58b-f865-4278-a9b6-7c99da30c0fe |  | note | FREQUENCY: Prior to commencement
label | c4ee1707-feaa-447e-aa40-bebc4cf630fe |  | note | CATEGORY: VP
label | 398b6c2a-17fd-4275-95b1-7b8e469aadac |  | note | RESPONSIBILITY: SE
label | a214f85b-9c0a-49a2-969c-c4ec4d36ec55 |  | note | VERIFYING DOCUMENTS: This ITP
text | 76ac7d2b-bda5-4678-8c84-584d864e5a26 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Installation of Pipeline (Trenchless method)
label | bffb8ce1-a7c5-416d-a632-59dd2dd470d0 |  | note | REFERENCE: IFC Drawings
label | f8abba02-e210-4232-8233-8a8e28ef7ac8 |  | note | ACCEPTANCE CRITERIA: Drill to be installed as per the survey setout.
label | 1e51dcf4-92c0-4e91-b7ca-48e8ae64ab05 |  | note | Bore longs to be supplied.
label | 887f9a3c-5852-4f42-935d-0512b4586137 |  | note | METHOD: Document review
label | 4ebedbd8-d83b-4ef5-9382-8e0541fa581e |  | note | FREQUENCY: During pilor bore
label | e8f13bb6-aaf6-45c3-8010-fa89cd480fb7 |  | note | CATEGORY: HP
label | 1a60a1e3-1865-4a2d-9085-3fcd565def85 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | edbf1fc6-f2e4-4c84-bad2-e7194f8f0931 |  | note | VERIFYING DOCUMENTS: Bore logs
text | ada214fd-0da6-4710-88b2-1d4d9f78b6cb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Ground Conditions
label | 5d005ac7-947d-4990-8c5b-2086b70c395d |  | note | REFERENCE: IFC Design Report
label | 5aa0120d-1730-4c27-8d59-8f5dc9cd6f32 |  | note | ACCEPTANCE CRITERIA: Geotech Engineer to be notified if the excavations encounter different materials than expected.
label | 3ea7cefc-978c-4b8d-919f-eb0233b97f04 |  | note | METHOD: Visual
label | e2f8f19d-d8e7-4bc4-9624-0d4cc793f2b6 |  | note | FREQUENCY: Each lot
label | 767ee193-e0ac-4568-8ec1-17a927427f0f |  | note | CATEGORY: IP
label | 653e8b7d-3b5d-4bb2-89bf-171d362cf27f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c1e43a16-bad8-4b71-ae43-f7f2770ee840 |  | note | VERIFYING DOCUMENTS: Photos and Sign ITP
text | e2ea6407-1f36-4c46-85a3-5ed309929900 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Pilot Hole Drilling
label | 59c603c7-899d-4446-8c95-60bfe8eacfaf |  | note | REFERENCE: IFC Design Report
label | d681c4a1-3142-4d69-a855-cd50723d371b |  | note | ACCEPTANCE CRITERIA: Pilot hole to be drilled and rod left inside drill hole.
label | f1efd426-0a30-486a-b34c-01d0d762666f |  | note | To be left open less than 24 hours.
label | 8e129580-73e5-4aa4-90b7-307c7994cedc |  | note | METHOD: Visual
label | 1ef8b2fd-5c54-4749-81d7-132ab3a16281 |  | note | FREQUENCY: Each lot
label | e6e28fbd-a63c-4560-bdca-b95217f08e1b |  | note | CATEGORY: IP
label | 0a72c2cc-d58c-4313-bf68-d0593103c918 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 620fdf46-19b2-4b07-9e97-d59088b878bd |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 233719da-03cf-486a-bdd9-27e9ffdeb531 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 HDD Monitoring
label | 93ad3ca9-12c4-4892-ab29-8ad5e4f2764f |  | note | REFERENCE: IFC Drawings
label | 11a66d19-6e42-438e-9607-3c468b943339 |  | note | ACCEPTANCE CRITERIA: Inclination and path being monitored as per design alignment.
label | c954d4b2-2db6-4b39-ac5d-801a3e839f0f |  | note | Ensure bore hole blockage and fluid losses are detected and addressed by:
label | 7c90b0c9-600d-47c0-95d8-3d330514e426 |  | note | Monitoring drilling fluid volumes, monitoring annular pressureand monitoring cutting returns.
label | 82dfbdb6-f41e-4e65-86b9-5ca2205b5d83 |  | note | METHOD: Measure
label | c183c1ac-9170-41a4-9d23-2f289a3ac1b5 |  | note | FREQUENCY: Continuously through installation
label | 20a4ce33-2a30-43a0-ac59-95a185382c45 |  | note | CATEGORY: WP
label | 731ed356-e242-40b9-be13-e31272f050ca |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 434d2efe-dfa8-4479-8d04-e505f750097c |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9cc23d9b-b7af-478d-b71d-7a05b93163e8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Conduit Installation and Trace Wire
label | 8d7d9c51-4053-4700-868b-c2dc6b430a83 |  | note | REFERENCE: IFC Drawings
label | 00b0c933-0b26-45ff-acce-f590b93fcb5a |  | note | ACCEPTANCE CRITERIA: Min depth as per IFC drawings.
label | 6cb092e7-a278-4ee3-94f9-f8296ed30d43 |  | note | All bored communications conduits shall include the installation of 3mm trace wire.
label | 8cdac922-8ed6-4968-9874-b9866eb951ce |  | note | METHOD: Visual
label | 222e3674-e850-4a98-bcc4-a3200f94acea |  | note | FREQUENCY: All Pipe
label | f062e27c-67bb-4a32-85a9-da96b73cea42 |  | note | CATEGORY: VP
label | 528446d9-687a-4c1d-a44b-ce5079aba4ad |  | note | RESPONSIBILITY: SE
label | 33671a42-5723-4f3d-a0d8-4fa3de548f30 |  | note | VERIFYING DOCUMENTS: Sign ITP.
text | 858587bb-5ca7-4368-970a-f138a5f90e65 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Track Monitoring and Ground Settlement (if applicable)
label | 42dc6032-1b6a-4f8e-889b-1e70d75e779a |  | note | REFERENCE: IFC Drawings
label | e48e3233-f7de-42bb-bf5d-0fac13170ee3 |  | note | ACCEPTANCE CRITERIA: Both tracks are to be monitored at 5m intervals either side of the centreline of the under bore for 10m either side of the bore centreline (20m in total).
label | fb7e2b4f-9e72-44ae-9dcc-bbc62cb82cef |  | note | If movement above the predicted amount (> 15mm) is visible or any tension cracking is observed at the surface or within surrounding areas, then construction must cease, with drilling fluid still being pumped, MTM and the Geotechnical Engineer notified immediately.
label | d85ee8f8-0bc7-4670-8fcd-191d6a8c7e25 |  | note | METHOD: Meausure and Visual
label | ebfaba6c-cbb5-42c3-aaa7-74e727c80dd7 |  | note | FREQUENCY: Continuously through installation
label | 2c5c0b7e-71fd-42a1-827a-63c35368075f |  | note | CATEGORY: IP
label | d405919b-8524-47c3-b9d0-ef21fb6bea2d |  | note | RESPONSIBILITY: SE/Site Supervisor/Survey
label | 04259455-2c83-4ca4-bd0e-229dbdf954e5 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 141e200b-5676-4586-9ae7-c60558408e2c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Conduit welding
label | db93557e-db03-44cc-a2ca-325aebbdf99f |  | note | REFERENCE:
label | 82700a35-d755-4432-a122-d008b1416f3e |  | note | ACCEPTANCE CRITERIA: Joints are to be butt welded.
label | 67af569f-c161-40d9-b8f8-96cda010982e |  | note | Weld map to be supplied and identify unique joint numbers.
label | 2f263914-3436-4d6e-85b5-53f1535a6dbf |  | note | Butt Welding records to be supplied.
label | 2a57b0c2-57b2-4b13-9b04-256da2122137 |  | note | METHOD: Document review
label | d5db1775-9907-4d0b-8729-23b8fb6b543e |  | note | FREQUENCY: All Joints
label | 7abe9a11-90c6-4f40-a261-3dc3336ff810 |  | note | CATEGORY: IP
label | 5dcefe53-bc32-4ef3-b0d9-728dbec3e1eb |  | note | RESPONSIBILITY: SE/Site and Supervisor/Survey
label | e31d07fa-918d-4d3e-baff-f9c3aecfa1a3 |  | note | VERIFYING DOCUMENTS: Sign ITP and Butt Welding Records
text | 6de98b7b-6c47-4bb1-b187-f551e5641852 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Grounting (if applicable)
label | a530463b-0aed-43ec-a105-50455cbe1ffd |  | note | REFERENCE: IFC Drawings
label | 931c1a6f-2d48-41aa-80e6-2697744d9ffd |  | note | ACCEPTANCE CRITERIA: Pipe annulas to be grouted with liqufill with 40mpa strength immediately after installing the pipe.
label | 2c66e5f5-1331-4a70-adba-e74da9fdc213 |  | note | METHOD: Review
label | 7201020d-ad13-4622-b142-232880147dcb |  | note | FREQUENCY: Each lot
label | 1d813f33-0fb8-46f5-92e7-c4263e26a267 |  | note | CATEGORY: IP
label | 37beb463-f338-493f-b51d-bd1180c648f7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | dbeba056-b4cc-4fb9-ad35-09f881da07ab |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 1779f619-3b4e-4056-b447-d7dfd163e7d3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Draw rope
label | 2cbc309a-0886-48ed-8c2c-599edd1a86de |  | note | REFERENCE: IFC Drawings
label | 95eb2514-5d1d-4b14-b088-aea220cc395d |  | note | ACCEPTANCE CRITERIA: The draw rope shall be continuous for the complete length of the conduit run.
label | d628edb9-aa2d-47b3-b0ab-662d6869c16b |  | note | All draw ropes must be continious between pits and have 2m slack in the pite.
label | 80317b77-49a9-46ff-86ab-3ee7dfdc001e |  | note | METHOD: Visual
label | 02f3878f-9c5e-40c4-ab80-9d5ab0fa3eb8 |  | note | FREQUENCY: All Pipe
label | 450fc8f1-f610-48f5-9969-5a8414f93615 |  | note | CATEGORY: VP
label | 0c33ed1f-c037-4cf6-b7fc-a298555142ad |  | note | RESPONSIBILITY: SE
label | 7d0eece7-dc8f-493e-a670-27cc5f1fe50e |  | note | VERIFYING DOCUMENTS: Sign ITP.
text | cb3e7818-a18a-43e5-b86e-d3320aba745e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Mandrelling
label | 09eaf996-4d1a-41bb-8e65-5349d57a4da1 |  | note | REFERENCE: IFC Drawings
label | 6955263a-5a85-4984-bf1a-51355c197ddf |  | note | ACCEPTANCE CRITERIA: Plug with 90% of the pipe diameter to be pulled through each conduit to ensure the conduit hasent been compressed.
label | cc2dbbde-0a88-42cd-a645-309d7a922da7 |  | note | METHOD: Record and Review
label | a998931c-a850-43d4-bdca-aee943260cfe |  | note | FREQUENCY: All Pipe
label | feb364f4-a154-4993-b8be-088eb817fbd8 |  | note | CATEGORY: HP*
label | 8623329e-ead7-490f-8bc6-02c78a194c63 |  | note | RESPONSIBILITY: SE/SPE
label | d895a75f-08ad-4bb3-a314-77e3f2a4d1aa |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 725ad25b-a59c-4afc-bae7-15a3e14c9700 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Reinstatement
label | 00fad391-2af6-4f97-925e-af2bf093c450 |  | note | REFERENCE: IFC Drawings
label | 21162af4-9cec-44af-abd2-b0f523747777 |  | note | ACCEPTANCE CRITERIA: Entry pits, exit pits and trenches within the railway corridor to be backfilled insitu material. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 0622c40c-f2b6-4610-b457-7f03ceb80a89 |  | note | METHOD: Visual
label | 810ecb9a-3c31-4fbd-9100-115dcfee8700 |  | note | FREQUENCY: Each shaft
label | b368de1f-e054-4cb5-bcb9-20c5666c3f09 |  | note | CATEGORY: IP
label | 827b0db5-683f-4635-b152-f72310f123ed |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b8f2eca2-0700-4629-9e43-6dcedaa7654d |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c94122c9-48f9-455a-89db-17424d0d1679 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Marker Post Installtion (if applicable)
label | c65d48c5-019e-4259-87a0-1f0c2b35367f |  | note | REFERENCE: IFC Drawings
label | 6fee5f7a-733a-440f-ac6a-8c1b47f9a533 |  | note | ACCEPTANCE CRITERIA: Marker post to be installed both sides of the crossing.
label | 0456a799-4843-46c6-84a5-742ff6341529 |  | note | METHOD: Visual
label | b898e7a8-7218-4c5e-8b32-5400b2026868 |  | note | FREQUENCY: Each shaft
label | 00babba0-9d3e-4d29-bdec-c54baa8a1bec |  | note | CATEGORY: IP
label | b5925406-a9ab-4fda-aa98-9cf385de4105 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 5ec21442-4cf9-4152-a7c0-6289825d7c94 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ed0fe08c-6a3c-4887-b430-b850ed73bac0 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 As-built Survey
label | 47b561e3-27c4-4795-89fd-2e393b3d42ef |  | note | REFERENCE: IFC Drawings
label | 7ff616cb-5a47-49dc-868c-cbebd96e52ef |  | note | ACCEPTANCE CRITERIA: Survey as built report to be compiled.
label | c1d422ca-2809-4162-8f6a-eda7b89cea0b |  | note | Autocad and PDF reports are to be supplied to: services.applications@victrack.com.au
label | a9968eb3-dfa5-4f68-98d6-2993e18bb86a |  | note | METHOD: Document Review
label | a71daaa0-b081-4c13-8350-677ae5d9ed18 |  | note | FREQUENCY: Each element
label | ba50b926-93b7-4340-9135-3d06172b3b01 |  | note | CATEGORY: IP
label | f9b7c78b-1afc-4797-91a1-c83beabe270d |  | note | RESPONSIBILITY: Surveyor and SE/PE/SPE
label | 9c07dcf4-ef25-4392-ba1d-eda171c7995b |  | note | VERIFYING DOCUMENTS: Survey As Report
text | 9750ad14-5416-4eeb-8331-7cfbfbee5f4c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Red-line / As-constructed IFC Drawings
label | 446db933-ed3a-4be3-957a-65de0618e55e |  | note | REFERENCE: MRPA Quality Management Plan
label | 2cae6335-4ad8-4be4-b408-9f9fa55fd648 |  | note | ACCEPTANCE CRITERIA: All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | d1b4f56b-2955-48f9-9b29-005bd69f0cee |  | note | METHOD: Document Review
label | 28f2515b-1644-4282-855e-4c6401a65cb4 |  | note | FREQUENCY: Once, after construction of the design package
label | b2b649cd-3399-40ea-b29b-cb0c64869b40 |  | note | CATEGORY: WP
label | 8012941b-751b-4474-aa07-368f756a9ccf |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6b7a6093-0824-487b-9eb2-ddb5cfd4cefa |  | note | VERIFYING DOCUMENTS: This ITP
text | 83bdb380-533d-4421-a7d3-80e831c90d48 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 81e0b86f-f369-4db5-9a98-495af0f9e90c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 1ee43f40-5b88-498c-8719-d55a3bac6b3b |  | textbox | Name:
text | cd0524e7-3920-42a4-8ecd-f124443063e4 |  | textbox | Position:
text | e1b1c39f-591a-4206-9551-ce6fe665bfc8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | Conduit and Pit (Roads) - Boring Rev0.0 | itp |  |  |  | Yes | ITP-CIV Conduit and Pit (Roads) - Boring | 9e27bfdb-0786-473d-b33c-12b3a36ebb1b
checkpoint-status |  |  | checkpoint | Reference Documents:
label | a9c895f3-4136-488e-87d5-32ad6f6021f8 |  | note | VicRoads Standard Section 733 (April 2019)
label | 094052b0-a8db-4d76-b0a3-20fa152981d0 |  | note | VicRoads Standard Drawing TC-1220
label | 5e9a362c-821a-4468-b9c4-4d757983cbbf |  | note | VicRoads Standard Drawing TC-2204
label | 1044d9f8-1234-4b8d-adb0-b6204a889959 |  | note | ITP Revision: Conduit and Pit (Roads) _00
label | 57f75664-edbb-4c8a-b8fc-75f8fbffe25b |  | note | ITP template approved by: Romualdo Magpantay(October 2019)
checkpoint-status |  |  | checkpoint | 3.1 - Submission of details for Boring
label | db951065-2a4f-480e-a753-24e6ecc408ce |  | note | Refer to VicRoads standard section 733.03. Details provided to the Nominated Authority
label | 46095446-7e57-4381-abc4-a8afde5569d9 |  | note | - - - - - - - - -
label | 374e9db0-62f7-4ec3-82aa-fadccc6ab23e |  | note | References - 733.03
holdpoint |  |  | signoff | Nominated Authority Hold Point
checkpoint-status |  |  | checkpoint | 3.2 - Depth
label | 98b90e4e-3801-4720-9de3-1bfaf35bbebf |  | note | Unless otherwise shown on the drawings, borings and trenches shall comply with the depth requirements specified in table 733.031
label | 7978b408-ca77-41ca-86c2-3f5bcb4489c4 |  | note | - - - - - - - - -
label | 210b0933-d9a7-44b8-8641-3bea96f4c426 |  | note | References - Table 733.031
checkpoint-status |  |  | checkpoint | 3.3 - Grout the annulus
label | 3d8199df-b4d7-4f90-b285-50eab0965202 |  | note | Before backfilling the bore access excavation, the pressure grouting shall be inspected by the Nominated Authority
label | c50edb77-10fa-4834-8f37-a0daed8fa9df |  | note | - - - - - - - - -
label | 0c226557-1517-41f9-8da1-6a6235ad1b13 |  | note | References - 733.03
holdpoint |  |  | signoff | Nominated Authority Hold Point
checkpoint-status |  |  | checkpoint | 3.4 - Warning Sign
label | f1f637bf-3032-4cfd-8dcd-f1fff98a5ff2 |  | note | An underground conduit warning sign shall be installed in accordance with VicRoads Standard Drawing TC-1208
label | 66d18366-1036-419b-a109-968e870ee0c6 |  | note | - - - - - - - - -
label | 5f491b4e-8dac-4245-b312-f8ceb4347235 |  | note | References - TC-1208
label | 90a7a79a-b19f-43f0-886c-935e0236d582 |  | note | - - - - - - - - -
label | e1af2b65-86c8-4ee0-91e9-2d51bf91497e |  | note | Verification Record - Photo of sign
checkpoint-status |  |  | checkpoint | 3.5 - As-Built Records
label | 8cd7ae3f-3d8d-452f-a16d-3eb797849221 |  | note | Record on As-Constructed Drawings and Survey pick-up for master CAD file;
label | 68e0831a-6ee5-42c3-ba80-f41288cbdd2d |  | note | - Conduit size, Location and depth.
label | b815dc8c-93dd-4b20-a5a6-be10cb65d52f |  | note | - Pit location, size and type
label | 49df1fd3-d8ec-4b24-9815-0e2b68558655 |  | note | Check Works Agreement for project specific requirements relating to stakeholders.
label | 602201a2-c0eb-4bc7-92dd-962b476e7c5a |  | note | Suggest labelling pits with unique IDs for ease of reference.
label | e20dc21b-6f99-422f-893b-8f83c022a7ad |  | note | - - - - - - - - -
label | e07a246b-7b52-408c-8297-4269e78bf8fe |  | note | References - 733.10, 733.11
checklist-flat |  |  | checklist | Stormwater - Products and Material Rev0.0 | itp |  |  |  | Yes | Stormwater - Products and Material Rev0.0 | 9f1510bb-0f1c-40bd-ab46-9c2a524d8de1
checkpoint-no-status |  |  | checkpoint | Document Reference
label | f6b73463-360b-4efe-ad4d-166f3cbe640e |  | note | VicRoads Standard Section 701 (April 2019)
label | 03d37880-bfac-49a6-acd4-178808436fb0 |  | note | VicRoads Standard Section 705 (October 2018)
label | d14bce29-c37e-46b7-8f5c-848a3ce1ff21 |  | note | Revision of ITP template: Stormwater Drainage_00
label | b10d6ced-59f2-42e5-9372-9d6936188485 |  | note | ITP template approved by: Michelle Edgar, October 2019
checkpoint-status |  |  | checkpoint | 1.1 - Drainage Pipes
label | 94875218-aa3f-43e5-8add-16181dc34c6d |  | note | Drainage pipes and culverts supplied in accordance with 701 and AS/NZS 4058.
label | ce277469-1890-469b-8a7f-341be04fcdce |  | note | Documentation as per 701.05 is available in Teambinder Material Approval form
label | b55849e9-70df-47ea-afc0-d3b104a4fdc3 |  | note | - - - - - - - - -
label | 93c7dc05-45e1-4f5c-86db-b74a291bd70f |  | note | References - 701.04, 701.05
label | bcdddd38-500d-4077-8d1e-f3401315223e |  | note | - - - - - - - - -
text | a46b9919-4624-4341-91b3-214fefa433a1 |  | textbox | Verification Record - Teambinder Material Approval
checkpoint-status |  |  | checkpoint | 1.2 - Drainage Pits
label | 02580a92-c0a4-4bd5-b5a6-58406c48896c |  | note | Drainage Pits are supplied in accordance with 705.07.
label | 5c8edaea-27f6-451c-b696-a2c027b556a3 |  | note | Suppliers documentation has been submitted via Teambinder Material Approval form
label | 8981b8ac-42b9-48e1-b6dd-0050d0d2b9ac |  | note | - - - - - - - - -
label | 144b9ab3-8d40-4f9d-90b2-e166995c6b20 |  | note | References - 705.07
label | 917580eb-8a20-491c-b40f-2941f03fcf0b |  | note | - - - - - - - - -
text | bcdf34f7-cdad-4dbf-8996-e031305fd488 |  | textbox | Verification Record - Teambinder Material Approval
checkpoint-status |  |  | checkpoint | 1.3 - Drainage Bedding Material
label | 3defbde9-2d46-49c0-bc07-136ffc273b7e |  | note | Bedding Materials comply with Table 701.081 and 701.082.
label | b85fc77f-a7ee-4dfd-9dcd-dfaaf3aa17a9 |  | note | Material Approved via Teambinder Material Approval Form.
label | e1e6433c-fb28-4eec-b9b6-984241b76d0a |  | note | - - - - - - - - -
label | aac9350f-51a7-4a35-a52d-168dfa30add5 |  | note | References - Table 701.081, Table 701.082
label | 4b58706b-c9bb-4fa5-ad7b-10324792d3c4 |  | note | - - - - - - - - -
label | 80fce6c5-d8f1-4b6a-a0e2-9f7cb1a1607f |  | note | Verification Record - Teambinder Material Approval
checkpoint-status |  |  | checkpoint | 1.4 - Drainage Backfill Material
label | b8369b39-dae0-4f02-be89-8b1c7c0ad07a |  | note | Select and Ordinary Backfill Materials comply with tables 701.081 and 701.082
label | 5daad35a-f0d6-49ee-97cf-66efe2f9ebe1 |  | note | Material Approved via Teambinder Material Approval form.
label | 5ec011a8-5ba6-4613-97c8-a2763fa1bdc4 |  | note | - - - - - - - - -
label | d4b1209d-093e-4333-80c5-df5d610bd06e |  | note | References - Table 701.081, Table 701.082
label | ecd43df2-ed82-4115-a897-78258c5a3a48 |  | note | - - - - - - - - -
label | 44e74f3d-8df6-4fa7-b59c-0171a6637721 |  | note | Verification Record - Teambinder Material Approval
checklist-sectioned |  |  | checklist | ITP-STR-Ground Anchors-Soil Nail Rev 0 | itp |  |  |  | Yes | ITP-STR-Ground Anchors-Soil Nail Rev 0 | 9fc8207e-1855-47c0-a8c1-94d7b1766534
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 56530131-0d1d-57b0-93c5-cf86ea385f22 |  | note | Document Title: ITP-STR-Ground Anchors-Soil Nail
label | 9ca7e88b-aa06-5469-887a-b62a58f85ed1 |  | note | ITP Description: Ground Anchors-Soil Nail
label | 7cae1e11-bfdf-5fae-993f-db3a3f40d1b3 |  | note | Document Number (in Teambinder): n/a
label | 810ea1b3-4aaf-56ae-af6b-9ae1db4ff0ec |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 81806cec-a801-5a80-a921-524836f7aebd |  | note | Revision Number: 0
label | 1e57d0fe-0c7b-528d-a317-0123467066f2 |  | note | Revision Date: 10/05/22
label | 1de899ea-9441-58dd-a665-a0d4fd4f2fe3 |  | note | ITP created by: Furqon Edwars
label | 64c152ef-2c53-5fde-bbce-011de1d2afab |  | note | ITP approved for use by: Romualdo Magpantay
label | d08a97d1-d781-5c55-9fb4-7241add3a29f |  | note | 1.1 - Non Dependent - VicRoads Section 610 June 2019
label | eb591d08-5b51-57b0-ab11-1c370a8a0502 |  | note | 1.2 - Non Dependent - VicRoads Section 611 November 2018
label | 88561fde-68fc-5116-9a48-8f588ce77157 |  | note | 1.3 - Non Dependent - VicRoads Section 683 April 2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1- Design
label | 2f2e2ed2-3e4f-59dc-9a76-72cceaa03349 |  | note | Reference - 683.04 683.04 (d) (i - xi)
label | c70a7aa9-22f9-5cf4-ba00-64bfddb8e578 |  | note | Acceptance Criteria- The Contractor shall submit construction drawings for review by the Superintendent prior to soil nail installation.
label | 0e9d6e66-3bc4-5a01-93d6-e735e42d443a |  | note | Method - Document Review
label | e57e0554-0a53-5a9b-90ae-08a9888112ed |  | note | Frequency - Once, 4 weeks prior to installation of soil nails
label | 67941f00-9da1-5fdb-8095-cd18d3996003 |  | note | Category - HP
label | 379eeb65-4a7e-5f1d-9b58-abffb09f6553 |  | note | Responsibility - Designer/ Consultant
label | bb972116-07a4-5bbd-a3bd-ba22b6640e3c |  | note | Verifying Documents - ConQA Hold Point Release
text | d91095d4-2455-53da-9f31-45c9efbaf8f0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2- Soil Nail Testing - Type I / Design Verification
label | 47d68aa3-0355-5fef-ad4e-bc5c234d8ebd |  | note | Reference - IFC Drawings
label | 7f38603b-efa4-56fd-b4c3-e472c40d20c9 |  | note | 683.12 (a, c - d)
label | b0b9210e-753a-503e-b8de-7d75217b9b70 |  | note | 683.13 (a - b)
label | 7ba2ee7b-c388-5340-8989-ca9707a4941e |  | note | Table 683.161
label | adc068a5-6063-556b-8925-aa451164ae29 |  | note | Acceptance Criteria- 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
label | 5da6b285-be05-53b4-abcc-d5b693488f2e |  | note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
label | 61339e88-ce6d-5fd3-a365-67fc9953f4ec |  | note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
text | e4beca91-1ba3-5315-a9a0-b7c2955505c3 |  | textbox | Teambinder Approval number
label | 88d934b7-7447-56e7-85c7-4f0333452e88 |  | note | Method - Document Review
label | eae9633b-9d00-557f-9c71-ef9f8c934c41 |  | note | Frequency - Once, 3 no. tests per soil/rock type
label | 2ba6d525-2edc-55d7-bc76-1082c38b4a2b |  | note | Category - WP
label | 1de91f20-db00-58c4-9af2-2c1d4616946c |  | note | Responsibility - Testing Technician/ Consultant
label | 9ab725fa-4ae1-5f55-8a1d-26ad0bc87c3e |  | note | Verifying Documents - This ITP
text | 55deeb94-9e38-50f5-bc28-a4fb76988636 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3- Testing - Type I / Design Verification Test Failure
label | eaeb508e-83e9-589d-a252-c8ce38a67ca1 |  | note | Reference - IFC Drawings 683.13 (b)
label | 04ce1dc9-50e4-5763-862d-0aba7a2328c9 |  | note | Acceptance Criteria- Where applicable, if any Type I / Designer Verification Test results fail, Type II / Sacrificial Testing & Exhumation Testing shall not proceed. Where this occurs, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction.
text | 07aa912a-ad16-585b-a6f8-d3f0958b82f7 |  | textbox | Teambinder Approval number
label | 1b00ff9b-e61d-5dcf-be5c-dcdfa21f0c6b |  | note | Method - Document Review
label | 91c1bde7-03d3-529d-8f42-9d4b3ed52397 |  | note | Frequency - Where applicable, per failed test result per soil/rock type
label | fa218a56-1f68-5374-b8cf-56e42dbdb1f2 |  | note | Category - HP
label | 07d44907-3416-5cc3-8b3f-2ef5f24f0e21 |  | note | Responsibility - Testing Technician/ Consultant
label | f691c2dc-2d4e-5715-8d0c-faacef2858dd |  | note | Verifying Documents - ConQA Hold Point Release
text | ef66e57a-ee7d-5f9c-aa34-bc2db7c02054 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4- Testing - Type II / Sacrificial Testing & Exhumation
label | 67683f1a-6479-521e-a82d-45e553685b18 |  | note | Reference - IFC Drawings
label | 3279f80a-d5c3-544d-8495-8877b095d323 |  | note | 683.12 (a, c - d)
label | dcb6664f-e7d0-51ac-bc75-973200ba0565 |  | note | 683.14 (a - c)
label | 217471be-92eb-51db-ba57-e061f66a29b6 |  | note | Table 683.161
label | 8a414645-efde-516f-8bf1-3fab1da3e0a5 |  | note | Acceptance Criteria- 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
label | 5f47c211-baef-5f67-9747-4b5778935a77 |  | note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.161.
label | f2406d7f-0f81-5819-8b7e-34cf9cc7d065 |  | note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
label | 572f17ff-9a34-5640-ac66-9f5d68f11576 |  | note | Exhumation of the sacrificial nails shall be conducted in a manner to avoid damaging the grout column and cut into 500mm lengths with ends photographed to prove grout cover of the nail.
label | b00273dc-900b-5da2-a0da-d041d63d835f |  | note | Note: Dispensation from Type II testing in rock can be requested if:
label | 57db0e4b-e072-54da-a6b0-36820f7da52f |  | note | i. All Type I test results pass in that material
label | 0f935d96-6e17-5b2f-9ace-b7c5aa4bd83b |  | note | ii. The material is not weathered more than slightly weathered and/or less hard than a Rock Quality Designator (RQD) of 50
label | 8bbcf0d7-6c79-5ee4-a20e-4ebb5c4ddc48 |  | note | iii. Encapsulation sheaths are used for steel nails
text | 032feae5-5cba-563e-b486-11e31a2934d2 |  | textbox | Teambinder Approval number
label | 6cc8534b-ea58-5f54-897a-4dbd6b1d8ceb |  | note | Method - Document Review
label | eaf1380f-977d-5d13-bdcc-eb36f9c70382 |  | note | Frequency - Once, 3 no. tests per soil/rock type
label | 31adcd1e-da09-577a-b74b-00d21ceadfc9 |  | note | Category - WP
label | 72649d36-9b13-5db0-aa1d-ff32e4e4b2b0 |  | note | Responsibility - Testing Technician/ Consultant
label | 4c3b14f9-18d0-501a-b924-545b5fa5504c |  | note | Verifying Documents - This ITP
text | 515cda6b-d831-5227-8e25-85931dd36a7a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5- Material Approvals and Certification
label | bbd800fe-bafb-56b4-8eb3-f1cf0bd1bdfe |  | note | Reference - 683.06 (a)
label | 3c10c03a-3294-576d-a7af-3d30eacefacb |  | note | 683.07 (b)
label | 58c83ac7-f446-5264-9dca-fbacfe6efc2b |  | note | 683.11 (a)
label | 29c886cb-e7fe-5824-9d31-e7e551f7cfeb |  | note | Acceptance Criteria- Bar shall not be installed until the test certificates for each batch of bar have been submitted for review by the Superintendent and written approval for use has been granted.
label | a01a59ce-d124-5d65-ac75-cf04b4c6d39c |  | note | Coatings for corrosion protection on all steel materials shall be either:
label | abbb1bb0-3826-5086-98c0-8c2f63923f27 |  | note | i. Galvanised to thickness as per AS/NZS 4680
label | 7f41afb4-4c0b-5bf6-9c29-c7d94b912292 |  | note | ii. Thermo-diffusion coated to Coating Class 80 or ≥80µm
label | 7db095a6-55fd-533a-816c-a28b27bb45d4 |  | note | iii. ≥80% zinc-rich product with ≥100µm DFT
label | 70c4e3fe-a61d-5279-82be-1508314d40fb |  | note | The proposed low shrinkage grout mix design with supporting test results to be submitted for review to the Nominated Authority.
label | ce705479-49c8-5999-b41e-edaba0dae127 |  | note | The following test results and information shall be provided:
label | 1f75f451-5627-5115-a660-69b2a92444e1 |  | note | i. Water cement ratio between 0.38 - 0.45
label | 4e310ea9-23fa-5aea-a809-ad7ec7806dc7 |  | note | ii. The chemical admixture
label | 041b6e0c-041f-54da-8644-f5d7a6cc973e |  | note | iii. 7 day compressive strength test results ≥32MPa
label | d2b14d17-36ff-58be-87b0-60a5390d1dc7 |  | note | iv. 28 day compressive strength results ≥40MPa (Robinson's Road)
label | afe28e9d-0243-5137-9e7f-6918bb69bbd0 |  | note | v. Flow cone test result between 10-30 seconds
label | 0d0e63fc-911b-5f18-b5e1-53b17de68f8e |  | note | vi. Bleed test result ≤2% 3 hours after mixing, ≤4% at any time and separated water absorbed within 24 hours
label | d0da78cd-aa66-50a6-93c9-4de491a123fc |  | note | vii. Chloride-ion content ≤0.07%
label | cba485d8-bc1c-5605-8cc3-dafbbabbc41b |  | note | viii. Sulphate content ≤5%
label | 4cf94c13-1c40-502d-bb2a-34b8dd762ab5 |  | note | The grout shall be made strictly in accordance with the approved grout mix design and in the event of changes, re-submitted for review and approval to the Nominated Authority.
text | 31bc4aa1-fe13-57ec-8211-5d82901ddd3f |  | textbox | Teambinder Approval number
label | d8e79a92-978f-579e-afbe-d711be542a29 |  | note | Method - Document Review
label | 59b9efbf-d107-5252-ad6c-e25f3a91cef8 |  | note | Frequency - Prior to works
label | 3f81c15a-0dd1-5650-9997-999aa0bc5b8f |  | note | Category - HP
label | 6b2fb91a-19aa-5fba-b8b8-ddc74e987cc8 |  | note | Responsibility - Nominated Authority
label | 7e5c5353-edf4-55ae-bf8e-e6c737f09221 |  | note | Verifying Documents - ConQA Hold Point Release
text | cac54736-7a65-53c4-a3c4-abc47e4ad88f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6- Soil Nail Installation, Grouting & Testing Work Procedure
label | f4b1cac7-5605-5665-801b-33c20e826ba8 |  | note | Reference - 683.12 (b)
label | 4b9c4c80-27c5-5b5f-b04f-36b86ae72bd2 |  | note | 683.11 (b)
label | 8f6cd853-de2b-5db2-a1c6-b4b83d137612 |  | note | 683.1
label | 4df7b355-fc00-5ddf-b462-79b406d782d9 |  | note | Acceptance Criteria- Soil nail installation WP, fully detailing the proposed drilling, grouting & testing equipment, methodologies and reporting, to be submitted for review to the Nominated Authority.
text | 9a5c65b9-ab4c-50f9-8c92-049e9ed2c074 |  | textbox | Teambinder Approval number
label | 78d9acc5-4729-5573-8322-2914ff90e7bd |  | note | Method - Document Review
label | a34242b0-6331-5a18-8ad0-51f98ff754ce |  | note | Frequency - 2 weeks prior to installation of design verification testing
label | f7074c3e-9442-543c-a2cf-aa4fb615b3fb |  | note | Category - HP
label | 3ccafb0a-2b3e-5476-9284-7ee015e5f6e4 |  | note | Responsibility - Nominated Authority
label | 1fb47550-1087-59f9-9c0f-19ef6a296da6 |  | note | Verifying Documents - ConQA Hold Point Release
text | 012900ce-b9e2-5ab2-9e91-872a75173819 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1- IFC Drawings
label | e099aa0c-0646-5eb5-b08b-af2b6e1c6d0a |  | note | Reference - MRPA Quality Management Plan
label | 40d0c249-d4ae-5ed3-95ba-1063fc1b96f8 |  | note | Acceptance Criteria- Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 1dae710a-7fea-586f-a30f-d9c312db3990 |  | note | Method - Document Review
label | 253aa012-d77e-51f7-a33e-8f87c0113d27 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 88977e2e-cd66-5cf5-acaa-35aa051098f2 |  | note | Category - HP*
label | a87042dc-03c9-5e21-b26c-c45fdcca4bcb |  | note | Responsibility - All
label | 8099c918-dd12-50cb-bcd1-2e622061da2a |  | note | Verifying Documents - This ITP
text | d60f4d39-450a-5b37-9670-9b1570548242 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2- Survey set out
label | c9298273-dc44-58b6-b627-67d3d7de5a8c |  | note | Reference - IFC Drawings
label | 752c8954-e4df-527b-8466-6f52a40b2d76 |  | note | Acceptance Criteria- Constructed as per Design Drawings
label | d6a75924-fdc3-5d7c-a0b5-8ed9ca4e418b |  | note | Method - Survey
label | aa0cb863-52f4-52cd-9eb7-ab9945c0f8b5 |  | note | Frequency - Every Ground Anchor
label | e5569a6c-d161-52c6-8cec-04a795e3a97c |  | note | Category - WP
label | 09020d3f-701c-51df-8843-29f0180c2d3c |  | note | Responsibility - Foreman
label | 407aea13-c416-57c4-a84f-06532c5d31e7 |  | note | SE/PE/SPE
label | fdd93171-a9d3-5558-9d84-eb886894ca8e |  | note | Surveyor
label | 4b2d8753-2c12-5750-ac56-5d9cc4cb6e15 |  | note | Verifying Documents - This ITP
text | 90d7fe25-d32c-5bc0-b67b-47ba41864149 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1- Drilling of Holes
label | 8cabe298-6814-5cad-bb18-8d6550e3f305 |  | note | Reference - IFC Drawings Soil Nail Work Procedure 683.08 683.10 (b)
label | f49114c1-5ac2-53c8-96a7-c2321d7b0cf7 |  | note | Acceptance Criteria- Drill holes shall be the depths, diameters and angles shown on the IFC drawings using the equipment stated in the Work Procedure.
label | 8579ac6c-c9ea-569d-aed2-0128c98a9fcf |  | note | Where casings are used or sheathing is omitted, the hole diameter shall ensure that the cover to the nail is 40mm min.
label | 69f4a5b7-512b-5a05-bb4e-2fbfd4e0df4c |  | note | Drilling records shall be kept including any observations or difficulties encountered.
label | 0d1ce419-ea48-5cf8-abac-5e7e1e273bf2 |  | note | Only air flushing is permitted, no drilling fluid or water shall be used.
label | 6119d5d3-f1f6-5ec8-b3da-57fc1fc04c50 |  | note | Placement tolerances to comply with the following:
label | bf87e878-e21a-54e2-b38a-70439f4ebab5 |  | note | i. Horizontally = ±50mm
label | 84486e9b-6828-52fd-9ad4-48cde048b31c |  | note | ii. Vertically = ±50mm
label | 19d2b739-7f3d-573f-9dec-60803245e74b |  | note | iii. Alignment = 1:20
label | b1704c62-a5c1-5ff4-ab3b-f6f9872aaeab |  | note | iv. Straightness = 20mm in 3m
label | 46b7ba32-161e-5922-8f14-35a19bd1afba |  | note | v. Inclination = +0° to -3°
label | baa5a1b8-faa8-55d5-bc63-45c28b9716c0 |  | note | Attach: Drilling Records
label | 230b9dd9-aec5-5139-8306-5f3a7cfe46fa |  | note | Method - Measure
label | b8f2854e-3221-5a70-b342-26239e5473da |  | note | Visual
label | d755bb9a-937e-5ac5-96c9-96bf05008501 |  | note | Frequency - Each drill hole
label | 4a7c76f1-bd4d-5e18-a62d-86fedc681126 |  | note | Category - IP
label | 03309bd9-7659-5437-ae74-152bf2ceb0b7 |  | note | Responsibility - Foreman
label | 56eb54fb-7c54-5e20-adf8-1ec4210816ab |  | note | SE/PE/SPE
label | adce3344-a593-5375-8ed0-26b5761d06e7 |  | note | Surveyor
label | e3d79586-7139-573d-8e8f-a521329397bf |  | note | Verifying Documents - This ITP
text | dff4ee81-95a7-5eae-a168-b6f073342e90 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2- Geotechnical Inspection of anchor bore samples by the Geotechnical Engineer
label | 67a1efe4-e013-5a66-955c-2eb0565f3b8e |  | note | Reference - IFC Drawings
label | 12d83136-5d30-5a68-b1e7-d9891371a15f |  | note | Acceptance Criteria- Alliance geotechnical design representative shall record ground conditions. The bore logging frequency will be locally increased to every anchor should any of the ground conditions encountered are different from what is stipulated on the tension anchor schedules
label | 31092d2a-b7dd-5703-bfa7-31b2495efce7 |  | note | Method - Document Review
label | 49cb7e51-ea2d-5003-80a1-f610c154b6bd |  | note | Frequency - All anchors
label | 206755a7-6433-5d99-94c4-80874733591d |  | note | Category - WP
label | c468cd14-56c0-5a2f-bf18-b8b7e43d879b |  | note | Responsibility - SE/PE/SPE
label | a26ff5cc-8ebe-5510-8e02-3ebd7fe5c040 |  | note | Geotechnical Engineer
label | a41a810f-c16c-5e0a-87d2-896b0a1e96a6 |  | note | Verifying Documents - This ITP Borehole Log
text | 6326b7e0-9394-5c17-935c-31a1e89183e4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3- Hole Inspection
label | 41f15ef9-7694-51d5-9bf9-bede34bb3d92 |  | note | Reference - 683.10 (c)
label | fd535a5c-7215-50e0-9618-69813b74d2bc |  | note | Acceptance Criteria- All drill holes shall be inspected following air flushing and prior to insertion of the nails. Drill records shall be made available for review.
label | fb2180a1-9c71-5604-8774-2aab6f3f75cf |  | note | Method - Measure
label | a9844044-4d8f-5230-b908-bd3945cff914 |  | note | Visual
label | 72364837-f7be-5f44-a735-9d24042b3107 |  | note | Document Review
label | fcb8b74d-6faa-5a4c-8dd1-a435b00172f4 |  | note | Frequency - Each drill hole
label | d709998e-8ab9-54ce-bf6d-27c5bdf99ba1 |  | note | Category - HP
label | 328fae18-b6c5-53e8-bcb2-a7c440bd0c92 |  | note | Responsibility - Nominated Authority
label | f4728bc3-2c00-5add-9046-0b6e51b882eb |  | note | Verifying Documents - ConQA Hold Point Release
text | 1eef9106-ca50-5f19-9d09-b57b7bd9f16a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4- Nail System Installation
label | 404127de-9b37-539c-adc4-464bc12d6f38 |  | note | Reference - IFC Drawings
label | e04a6839-b18f-59e9-9870-1540bf34d812 |  | note | 683.07 (c - f)
label | 052b77ad-8e5d-5615-8757-29316d6e7f19 |  | note | 683.09
label | 8cfac155-0e40-5ea4-bb78-190440655daa |  | note | 683.10 (c)
label | 798fa265-7989-5ded-9eae-6718c77cc2d4 |  | note | Acceptance Criteria- Each nail shall be made from the correct material, be the diameter and length as shown on the IFC drawings and be free from defects or damage.
label | 4d77e89d-d95b-58c5-b4e8-3310cb1331e8 |  | note | Centralisers shall be spaced at 1.0m max., ensuring that 40mm min. cover is maintained all around.
label | ce60f792-56be-541d-9909-ae499f2ad8f0 |  | note | Steel nails shall be encapsulated by a corrugated sheath unless previously approved during the Type I & II testing.
label | 17b37a8a-2024-5c1e-86fc-442ded562e9f |  | note | Steel nails shall be isolated 300mm min. where they are to be in contact with the shotcrete facing using tapes or other approved methods.
label | 9757ab73-c28c-5e3a-89c1-f1c70e44f80a |  | note | Grout tube shall be positioned at the base of the hole to displace any moisture present in the hole and to prevent entrapping air.
label | 3740e413-8a0f-58c9-b9f1-46b32289cc51 |  | note | The resulting set up shall achieve the minimum bonding length, projection and be able to resist the forces expected during the grouting operations.
label | 7eb651ce-161b-5a23-b6c6-bd4fd07aceee |  | note | Method - Measure
label | 8b8926f4-dc44-5bdb-aa35-e807d93b1ce4 |  | note | Visual
label | e35f54c6-270e-56ee-a38e-21d563de5b80 |  | note | Frequency - Each drill hole
label | e88ff67a-a586-5779-81de-c292bc1b2e7b |  | note | Category - IP
label | 0ef59fd5-2a35-5b2d-9df7-bf6b2000c479 |  | note | Responsibility - Foreman
label | 0098247f-38e8-5b0b-9243-329b0117d10f |  | note | SE/PE/SPE
label | 55586991-336f-5b2f-a6f9-a679d7acd156 |  | note | Surveyor
label | 8a25a846-12a7-54d8-8b5e-6f84af43d519 |  | note | Verifying Documents - This ITP
text | e8419aa9-1a55-5965-bbd7-d10429e3505c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5- Grouting of Bars
label | d1bf2484-0180-5ce1-897b-3f28bc5c99f3 |  | note | Reference - IFC Drawings
label | f33a90bd-4694-57e9-925d-61c84a6179e1 |  | note | AS1478.2
label | ad9061a2-b956-5c75-b3a3-628341cc2b2f |  | note | Soil Nail Installation Work Procedure
label | f60eba60-c496-514e-a730-0d157f2b9d2a |  | note | Acceptance Criteria- Drilled holes can be grouted up to 24 hours after drilling has occurred.
label | 86d1dbe3-2697-55ea-b116-f7b58dfb161f |  | note | The bar shall be centrally placed in the hole with centralisers at min 1500mm spacing. Centralisers to be used shall ensure a min 45mm grout cover around the anchors:
label | 51baa083-2e79-56fc-9cb4-8b22294b55e5 |  | note | - Internal, between borehole and sheathing and bar: 20mm
label | ed6c513a-a15f-5bec-abca-6fbe269469b1 |  | note | - External, between borehole and sheathing: 25mm
label | c43bca6d-6cd6-518a-bb06-159f0314aba9 |  | note | Method - Visual
label | 5597aa72-40ba-59c8-a5a3-31393036d05f |  | note | Measure
label | 60869c9a-7177-59a4-b4a5-860eabad9240 |  | note | Frequency - All anchors
label | 017d88dc-eeca-5a90-a192-3640ed426e39 |  | note | Category - WP
label | ca4f79c4-6499-5d37-9b86-2faa0554a7bf |  | note | Responsibility - Foreman
label | e04c20ea-ae96-5ff5-8078-cd1d8ff291c4 |  | note | SE/PE/SPE
label | db0e0e04-449c-5114-8388-cc6d67fb8712 |  | note | Verifying Documents - This ITP
text | adba6f95-280d-5cd6-82b0-0330426eae5e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6- Grout Sampling
label | 39bcea55-7802-5841-9003-23d4457f686f |  | note | Reference - IFC Drawings
label | 6b5fe9c5-5094-5397-b469-a3976710cab7 |  | note | Soil Nail Installation Work Procedure
label | b091b4b1-6688-5b01-90ce-b71ff031781e |  | note | 683.11 (a) (iii)
label | b000f8eb-bc80-5cbf-b717-18e91852da72 |  | note | Acceptance Criteria- Each test shall consist of:
label | 5a86c053-44c6-5a6a-8f31-5659b21bfbb7 |  | note | i. 3 no. compressive strength cubes = 2 no. 7 day strength, 1 no. 28 day strength.
label | b6332ef4-2cea-562f-a396-b9f064fd3d55 |  | note | ii. 1 no. flow cone test = result between 10-30 seconds
label | e431733e-85bf-5fee-9bb9-701495e3d6be |  | note | vi. 1 no. bleed test = result ≤2% 3 hours after and shall not exceed 4% at any time with all separated water gone after 24 hours
label | c3815684-c9c6-56d5-9746-19ab070ddb1a |  | note | Record: Required information on the Grout Pour Record.
label | 3250add6-33b4-557d-826d-d8dc04d397a3 |  | note | Method - Visual
label | 409615e7-136a-554d-a336-3d2b09555c37 |  | note | Measure
label | 64a9688d-a2c8-5de1-ac0c-1ad883517b8e |  | note | Frequency - Each 5m³ or part thereof batched per lot
label | 8b74a9f2-f4fa-55aa-9f0a-bb83bdf24a30 |  | note | Category - IP
label | d0bb30f3-3c35-5767-b745-ec837ade663d |  | note | Responsibility - Foreman
label | 12aa9059-4ed0-57dd-b83c-e60c6abb746a |  | note | SE/PE/SPE
label | f2495518-8970-5183-9fe2-c6018e8a7d28 |  | note | Verifying Documents - This ITP
text | b79f6a82-9381-5100-a046-e22df9567581 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1- Testing - Type III / Production Testing
label | 0edbe721-b319-528f-99a7-2999f1b8120e |  | note | Reference - IFC Drawings
label | b2788e07-e312-510e-9ff7-d08b809ee6d2 |  | note | 683.12 (a, c - d)
label | 3c80537b-6adb-5ad7-bbbc-908cc8339006 |  | note | 683.15 (a - c)
label | cf99fb20-ad94-5ba9-b10c-a3c9d6d52643 |  | note | Table 683.162
label | 36640284-16ea-5450-bde7-33083016a6e7 |  | note | Table 683.163
label | 9a619a3a-756f-5f50-b85a-8ff0374ac1aa |  | note | Acceptance Criteria- 3 no. soil nails per soil/rock type encountered on site, are to be installed as per the design, approved methodologies, materials and equipment in locations selected by the Geotechnical Engineer's representative.
label | 0dcdc3f7-45c5-57fc-9a3a-fc9f17418ecd |  | note | Load testing is to be in accordance with the loads shown on the IFC Drawings and the load cycles shown on table 683.162.
label | 442478e5-27f7-5a7b-878d-e0e0f57242f8 |  | note | Testing shall be carried out in the presence of the Nominated Authority and reports issued with valid calibration certificates within 24 hours from completion of the test.
text | 8cc100ad-5db3-5e9b-b0ee-887b6b2e784a |  | textbox | Teambinder Approval number
label | 209ff4f7-6648-5af0-a7a6-fe307142457a |  | note | Method - Document Review
label | cf25a09f-ccce-5da3-ab9b-a1fcf93a184b |  | note | Frequency - The greatest value from, 5% of all nails, 2 no. soil nails, 2 no. soil nails per type of soil, 2 no. nails per installation method
label | f33400c4-0f40-5b50-877f-17a27f966039 |  | note | Category - WP
label | 9bcf5148-9379-5e5e-847b-768e9429872e |  | note | Responsibility - Testing Technician/ Consultant
label | fad5641c-c3cf-537f-9ca8-b92c38b19334 |  | note | Verifying Documents - This ITP
text | dd05c711-406b-5ab0-b61a-de094dd40a80 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2- Testing - Type III / Production Test Failure
label | e4217e35-ce9d-5f21-918c-af8d688b9fcc |  | note | Reference - IFC Drawings
label | 09308d4b-0174-5511-a648-aa8c34be0d21 |  | note | 683.15 (c)
label | d5a212b7-19a2-5fea-a71a-9057de14f012 |  | note | 683.16 (b) (i - iii)
label | 177bd845-426f-5c56-b707-a9717bec9a18 |  | note | Table 683.163
label | 791301b6-1470-5afb-a08f-e75db0ced6f6 |  | note | Acceptance Criteria- Where applicable, if any Type III / Production Test results fail, the Designers must be notified immediately and design assumptions modified and re-issued to the Superintendent's satisfaction. An additional 2 no. nails are to be installed using updated installation procedures, either side of the failed nail and shall pass the load test - note that the loads may require updating.
text | f228facd-1f33-5d94-a6e5-8f8416b7fb8b |  | textbox | Teambinder Approval number
label | 3141d24a-bb29-57e1-96a2-45ad68b79ded |  | note | Method - Document Review
label | 19d633c1-1a22-5f49-b89d-7071b1682074 |  | note | Frequency - Where applicable, per failed test result per soil/rock type
label | 27ef83cd-7227-547c-9476-d31bd62ae5c8 |  | note | Category - HP
label | 21d7b510-94f8-5e3f-ab84-0f66698c7d30 |  | note | Responsibility - Nominated Authority
label | 00b0fef9-6eaf-5c46-a4d3-cd615ba86845 |  | note | Verifying Documents - ConQA Hold Point Release
text | c1368b7c-26d8-550e-8636-ec480d354abd |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3- Acceptance of Test Results
label | 4cfb1011-ffe2-546c-a5db-aee759e94303 |  | note | Reference - 683.10
label | 6222ce3e-ab4f-5d55-8104-e0a13dac2147 |  | note | 683.15
label | 87141265-d46f-5d34-a262-b14b6b909ff5 |  | note | Acceptance Criteria- Installation of production nails shall not commence until the Type I & Type II test results have passed the design requirements (inclusive of any re-design assumptions).
text | 7323e9cd-8987-5720-bca4-4e5cac994345 |  | textbox | Teambinder Approval number
label | 8dd8283b-0e12-5af7-b4bb-f437c883a12b |  | note | Method - Document Review
label | 5bbea7e3-f403-50ab-93e7-a06d5151b184 |  | note | Frequency - Once, 7 days prior to commencing production nails
label | 4a302db8-b93b-592b-b8d2-f388f5414456 |  | note | Category - HP
label | 79a382cc-f006-5fd2-8cc6-b18ad9c89ce4 |  | note | Responsibility - Nominated Authority
label | e2125856-7bda-55ae-a2f6-58acaa28c668 |  | note | Verifying Documents - ConQA Hold Point Release
text | 4d6e3618-2f90-59ed-8f35-23309d04d18d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4- Grout Compressive Strength Results
label | f044921b-3073-56dc-90ce-21a74173851d |  | note | Reference - IFC Drawings
label | 98e5346f-f0fe-5900-8d94-20f8b99987c9 |  | note | Soil Nail Installation Work Procedure
label | b0574c23-fa0d-5905-a03c-9320ce115b53 |  | note | 683.11 (a) (iii)
label | 7063e340-1078-58e0-8b06-f16e71325da7 |  | note | Acceptance Criteria- 7 day compressive strengths to achieve 32MPa min. 28 day compressive strengths to achieve 40MPa min. (Robinsons Road)
label | 4c853d2c-7a76-516a-880c-30aa2879b84a |  | note | Attach: Compressive Strength Test Results
label | e144f58f-b029-5f5b-b4cb-9c7b2609b31a |  | note | Method - Document Review
label | 0d30740d-cbcf-5a89-bc3b-469f8406856a |  | note | Frequency - Each cube
label | 674b21fe-2fd0-57f6-9c39-27914f8ffb21 |  | note | Category - IP
label | afa30bb6-1683-5016-9788-fcb5f3b32b14 |  | note | Responsibility - SE/PE/SPE
label | 086ae7a3-02ba-50be-a550-c0fa728ae126 |  | note | Verifying Documents - This ITP
text | 5df98d08-5eba-5a13-97ba-197acd0e0073 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5- As-built Survey / RLMU
label | fff1efde-641b-5c92-a5f1-e574069504ef |  | note | Reference - IFC Drawings
label | b16b5d03-42a9-51ea-a882-fc89a3dc296d |  | note | 683.10 (b)
label | a36ba2c0-0c6e-588d-a329-c5a69991cd8d |  | note | Acceptance Criteria- Provide record of dimensional measurements to demonstrate nails comply with the following placement tolerances:
label | 67273842-8bde-5593-8dc5-5fc1598ae07b |  | note | i. Horizontally = ±50mm
label | aeffe1b9-324c-59f9-878f-c9b87cd6a0c3 |  | note | ii. Vertically = ±50mm
label | fb465f13-986d-5011-ba23-726687e234b5 |  | note | Attach: Survey As-builts / Survey Report
label | 3c82f3f4-aa42-5e9d-9f10-66574efc3a0b |  | note | Method - Measure
label | de99aeb5-4d25-5006-bbd8-154f0b82c622 |  | note | Document Review
label | 48b1564d-154f-579a-a161-d23221db2cf6 |  | note | Frequency - Each nail
label | c937d055-1e74-5544-9408-1c643a61ee58 |  | note | Category - IP
label | 1b520679-eb83-50dd-bc14-9c676d5553ff |  | note | Responsibility - Surveyor
label | f636330e-114e-50ad-8034-ba5ad7a6e986 |  | note | SE/PE/SPE
label | 3c8a55b4-07be-500d-ad88-36f4ec57255d |  | note | Verifying Documents - This ITP
text | cba390b4-8a54-50ce-a9e2-96bf56b5d9a1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6- Non-conformance Report (NCR) Closure
label | 0ec97811-4ef7-5c8b-9d0d-7cb371ec95b1 |  | note | Reference - MRPA Quality Management Plan
label | d6b82c85-934d-5ce1-a248-42a0cea7472e |  | note | Acceptance Criteria- Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | aa54c7de-f1b0-5e42-9ff3-ffd292a46b8d |  | note | Method - Document Review
label | abfc06da-04f7-50b4-99d1-8bfffbe7f546 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | ff59b9ad-1f2a-58b9-af89-24defcdc0acd |  | note | Category - HP*
label | 5c666fbf-4652-5bfc-8bd6-d2e5976234e6 |  | note | Responsibility - SE/PE/SPE
label | cb94a6fe-cfbb-5bfa-8041-7b76a7d4fc7a |  | note | Verifying Documents - This ITP
text | 8a04626c-698b-579b-a557-a9e374d40840 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2f556e11-dde8-5b11-9cf6-6917af30567c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8eb43fda-ebc2-5483-9984-10eabc69d361 |  | textbox | Print Name:
text | ff1ff423-eb5f-5e95-9e84-ea4aba5c73da |  | textbox | Position:
text | 90a06c65-1637-5932-bc41-5b98026e2d34 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-CIV-Cement Treated Crushed Rock (Supply and Install) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Cement Treated Crushed Rock (Supply and Install) Rev 0 | a0aeb364-7ab6-4e24-9d9c-a5ba4c8af103
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 2728c32a-9d8c-4a9e-820e-390cf1a229ef |  | note | Document Title: ITP-CIV-Cement Treated Crushed Rock (Supply and Install)
label | b94006c5-8005-4d99-b2a0-43b4ff1eb5e2 |  | note | ITP Description: Cement Treated Crushed Rock (Supply and Install)
label | c0823e1b-9c45-4242-b6de-325977e25c21 |  | note | Document Number (in Teambinder):
label | 10935f5b-33e7-423e-8fe0-2c5aa073c571 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 225b50af-ba15-4839-adee-e8340119ffba |  | note | Revision Number: 0
label | 0c40ba5d-d63a-4665-bf18-47faab1abd31 |  | note | Revision Date: 44161
label | e13daa08-5549-41e5-9384-f289847d1927 |  | note | ITP created by: Jadan Halkett
label | 77db2d10-821c-4333-8adb-6cba87c67f99 |  | note | ITP approved for use by: Josie Pavlou
label | cc53e270-1491-40ab-9195-b4c2576b5976 |  | note | 1.1 VicRoads Section 306 Oct '19
label | e72da206-809d-46e5-a494-72fb585194c8 |  | note | 1.2 IFC Drawings
label | ff0d1d45-fbfb-4dcd-9c3b-e81c4d3ea703 |  | note | 1.3 Code of Practice 500.12
label | 283f0714-500c-4c5c-affa-7a40a289be6d |  | note | 1.4 VicRoads Section 815 July '16
checkpoint-group |  |  | section | Preliminaries / Preconstruction
checkpoint-status |  |  | checkpoint | 2.1 Check that current revision drawings are being used
label | e44cd44a-4268-45f0-abad-5b6cef724715 |  | note | REFERENCE: Project Drawings / Drawing Register
label | dd72b72f-7bda-4541-ac6e-a10c5e36a671 |  | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | 8395d893-c2b9-4a46-90e7-8761fce36165 |  | note | METHOD: Document review
label | c3fc3c50-4b45-4310-b3cf-00f5d8a246f2 |  | note | FREQUENCY: Prior to commencement of works
label | e0adde2e-f327-415b-9444-2469b2fda7be |  | note | CATEGORY: AP
label | c07d0ea0-119d-46a1-b9f0-7136a4a8211b |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
label | 5d44232b-2b75-43ad-a0e4-c4b9cbf080d5 |  | note | VERIFYING DOCUMENTS: Latest Revision Drawings
text | 66e251f9-8195-4abe-aa28-5b00c9296c45 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Submit Mix Design - Cement treated crushed rock (CTCR) mix
label | d6aa6649-b2da-4620-9a31-5d08a1734910 |  | note | REFERENCE: VicRoads Spec. Cl. 815.05
label | 93d2b346-c8f8-4afe-b9fa-eaef37df5960 |  | note | VicRoads Spec. Cl.306.04
label | 1dc7abee-23e5-4cb3-8c30-89fb71862957 |  | note | ACCEPTANCE CRITERIA: Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | f54537cf-912e-43de-b686-2e227d358ebf |  | note | CTCR shall comply with Section 815 & 821
text | e0bec2fb-ebb9-4303-a9aa-a9d03f67de66 |  | textbox | Team Binder Approval Number:
label | 65a419c6-4271-404c-9aff-cbdf87f9167a |  | note | METHOD: Document Review
label | 5e48716b-6f13-4ea4-b74b-d24dd747535f |  | note | FREQUENCY: Once per material type, prior to commencement of works
label | bd2013d6-bf4f-4b28-8286-ed0792b8d47b |  | note | CATEGORY: HP*
label | 44e90819-e074-496c-82c5-feafa484bdcc |  | note | RESPONSIBILITY: Site Engineer
label | 49c9c758-32c2-4e62-9bb8-b41e41e8188a |  | note | VERIFYING DOCUMENTS: Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
text | 98b6d478-bbb8-4426-ac55-9284aa6ca98d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Survey Set-out
label | b1e7eeb6-959b-48cb-a8b6-ed0497b51223 |  | note | REFERENCE: IFC Drawings
label | 06ca5bec-ae5b-4507-aadc-e9f4762a3866 |  | note | ACCEPTANCE CRITERIA: Survey to set out works in accordance with IFC Drawings
label | e8d3db0b-7c08-4bb1-aa3c-51b6c58f0eff |  | note | METHOD: Measure Visual
label | 5f8968e3-0c01-4007-a4ff-4ca663756b87 |  | note | FREQUENCY: Each Lot
label | 75545377-285f-42dc-a092-437ba6da840c |  | note | CATEGORY: IP
label | 15d0210c-36a9-4fe1-9b12-5b83a14ba8e2 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | eb87b6ba-da71-4bb3-8f30-9f1735bd6a60 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3dc9c473-e006-4f92-8e0f-e9fce36e629a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Previous Layer Level Conformance
label | 41372cad-80d6-444b-998e-7bea742372c8 |  | note | REFERENCE: IFC Drawings
label | 2083334b-8ea7-4c0b-8895-7193f30c0680 |  | note | ACCEPTANCE CRITERIA: Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements.
label | 0c1f7b05-88ed-4a87-b5e6-bd9b78bb56fd |  | note | Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved.
label | 58ebb9a3-0ab9-4067-bee5-66546f7913a9 |  | note | METHOD: Document Review
label | 74b76423-b4e8-42aa-b5f4-fc17283c6e43 |  | note | FREQUENCY: Each Lot
label | de8b71ff-91ff-4c0b-aec3-87e6631fb9c9 |  | note | CATEGORY: IP
label | 2730f78c-1ca3-4b10-b276-fb0bb9da0b7b |  | note | RESPONSIBILITY: Site Engineer
label | 625f1b7a-2713-4bf5-8dbf-f9f092b60132 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6a837e20-4808-439f-bd46-e81b80612bc9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Lot Size
label | 63538342-270c-4d2d-b926-0fa4f32c60c4 |  | note | REFERENCE: VicRoads Spec. Cl.306.03(b)
label | e46ccc6c-886d-4271-b256-96476df07a8e |  | note | ACCEPTANCE CRITERIA: The maximum size for a single lot shall be considered a single layer of 4000m2
label | b01a344a-ff07-4863-a61b-d9297cfee136 |  | note | A lot shall consist of a single layer of pavement material placed on the same day
label | ece984e6-862f-4378-958a-8b0248043f78 |  | note | METHOD: Site Inspection
label | 0dd8853f-d058-4aca-9f57-d6498039d058 |  | note | FREQUENCY: Each lot
label | eaaef7a4-826f-41a2-8843-36a94430efa2 |  | note | CATEGORY: IP
label | 55b82171-d8e0-477d-a002-c91e0e125fb3 |  | note | RESPONSIBILITY: Site Engineer
label | 33243bac-80ff-4a2e-b1af-9db3242e831b |  | note | VERIFYING DOCUMENTS: Signed ITP Attach: Lot Map
text | 61be7c30-53da-4343-a555-1fe911c58dd4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Hold Point - Alternate Binder (if applicable)
label | 04271575-6a54-4efa-bcef-29cc04dd1328 |  | note | REFERENCE: VicRoads Spec. Cl.306.09(a)
label | 2a8f074f-7dfa-4163-8f44-c9dadc571572 |  | note | ACCEPTANCE CRITERIA: If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method.
text | e7dd218f-32e0-44fd-a48e-3c5114641f3b |  | textbox | Team Binder Approval Number:
label | d690dfc4-013b-447f-8fed-0bfb6ecc0778 |  | note | METHOD: Site Inspection
label | 3aab17ce-9115-42a1-9b3b-9c1a1e63db3d |  | note | FREQUENCY: Once per material type, prior to commencement of works
label | e4f09d5d-8887-4add-b8a5-6b437e37231a |  | note | CATEGORY: HP
label | c6eee93c-16f1-41b4-b29b-a8f5e9139fcd |  | note | RESPONSIBILITY: Site Engineer & Nominated Authority
label | 1c7e0e7c-0ead-45d9-9d8f-2b9c2a533a05 |  | note | VERIFYING DOCUMENTS: Issue to TeamBinder: Test Records
text | ce7a326c-3dd7-43bb-bf96-662254f1df57 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Transverse Joints
label | 167959fd-36de-4dc9-8517-40ed18e5be3a |  | note | REFERENCE: VicRoads Spec. Cl.306.08(a)(c)
label | 4fdfbbdd-81b3-41c0-ac02-d0357f0de785 |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
label | 179f139d-b502-44c4-95c3-b8e48b8e52b1 |  | note | In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m
label | 2a66a615-5a88-483b-b8b8-aad11760b152 |  | note | Transverse joints offset from one layer to next by not less than 2 metres
label | 6dc614a7-a104-4d78-a5af-e3dfc6987a9c |  | note | METHOD: Site Inspection
label | 5f4303e8-b0f1-49d6-b5dd-4fbd36c71e20 |  | note | FREQUENCY: Each Lot
label | e91fae06-2ba0-4a23-b577-9f17e8ea63e8 |  | note | CATEGORY: IP
label | 8f3407c1-3a0c-4107-b1ba-8294e9935a21 |  | note | RESPONSIBILITY: Site Engineer
label | 3dd61d92-ae7b-4537-adf8-a43a2c344c04 |  | note | VERIFYING DOCUMENTS: This ITP
text | abd9b302-3a4a-491d-b918-b199aba28cfc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Longitudinal Joints
label | 553d2830-0f0a-479b-b03d-ee46bd67c0b6 |  | note | REFERENCE: VicRoads Spec. Cl.306.08(a)(d)(e)
label | c477b70e-a352-4ddf-a5cf-86187a43bcd9 |  | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
label | 88c8bdba-94c4-4d02-a519-bf7f495a4355 |  | note | Longitudinal joints offset from one layer to next by not less than 150mm
label | 271ee25a-7c97-4613-852f-b6d8111e798c |  | note | Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | dbc03b76-e8f3-44ef-be59-2310b837ae7f |  | note | METHOD: Site Inspection
label | 9afecc27-7fee-439d-b14a-5d8d303aa3b2 |  | note | FREQUENCY: Each Lot
label | 826007af-f4c5-4aed-83b8-ce5e8846f655 |  | note | CATEGORY: IP
label | b9714283-c4a0-451b-8c33-86312250769d |  | note | RESPONSIBILITY: Site Engineer
label | 0d0b0691-70dc-4c95-84de-ae8f201cf71b |  | note | VERIFYING DOCUMENTS: This ITP
text | bef842fe-97a6-4e20-852e-68a6c1f09775 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Layer Thickness
label | 629f0c74-f5a6-4fe0-80fe-94efd4928ac6 |  | note | REFERENCE: VicRoads Spec. Cl.306.11
label | c1fdb1c8-7839-42df-a048-fd7e54fc4b51 |  | note | ACCEPTANCE CRITERIA: Compacted layer thickness should be not less than 100mm and not greater than 180mm.
label | 59f156f6-6cf1-48f1-898c-52be53496139 |  | note | METHOD: Site Inspection
label | 36f46112-ac0b-4bd4-8b68-e686f96125c6 |  | note | FREQUENCY: Each Lot
label | 77214094-3346-4817-bac9-47a1901b5f04 |  | note | CATEGORY: IP
label | d2a89428-6acc-4c32-b720-3a0aca8c6d4f |  | note | RESPONSIBILITY: Site Engineer
label | a7857a62-35da-4354-9deb-7c9d5c613afd |  | note | VERIFYING DOCUMENTS: This ITP
text | c8b1dd13-e7bc-4d08-84d3-caee8c1c80a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Delivery, Placement and Working Time
label | a487c7ba-57b3-4bc6-b1f4-a9a0ec390f2f |  | note | REFERENCE: VicRoads Spec. Cl.306.07
label | e344c299-4946-4180-b109-f1feaf0f3720 |  | note | VicRoads Spec. Cl.306.09
label | 13c041ab-ee93-4d7f-b20c-5ac76b733748 |  | note | Table 306.091
label | d4ced295-a451-43b7-8689-ec4f14d47454 |  | note | ACCEPTANCE CRITERIA: Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specification requirements.
label | 7227fc32-0ef2-4acb-9dc1-30179f94ce85 |  | note | Working Shall Not be more than specified for each binder:
label | 8b4d7931-470d-4883-bd4d-e8a67b2c2a78 |  | note | Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept)
label | 31c4a79b-7ce7-46d2-ad1f-518b20a38ebd |  | note | Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept)
label | 0f344e0f-3897-4d0d-8d83-795c67400457 |  | note | Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept)
label | 2e261089-6f09-4f08-8f99-180afe7a83e4 |  | note | METHOD: Site Inspection
label | 50feae44-435a-4165-a136-1238101ba7cc |  | note | FREQUENCY: Each Lot
label | 3a01bbac-f743-4c6d-8ed9-854533093416 |  | note | CATEGORY: IP
label | cec13b99-561a-4228-beb4-ffcb7b9b8131 |  | note | RESPONSIBILITY: Site Engineer
label | 33e5b154-79cb-4f75-93bf-e89a44973dfc |  | note | VERIFYING DOCUMENTS: This ITP Attach: Delivery Dockets
text | a69b18b0-32c5-4131-9188-328f464bbebb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Water
label | a6bf891d-0980-49c0-8563-171c94956cf1 |  | note | REFERENCE: VicRoads Spec. Cl.306.06
label | 4f98664e-0878-4ca2-85df-65a5b0706c9d |  | note | ACCEPTANCE CRITERIA: Except for the purpose of curing, no water shall be added to the cementitious treated material.
label | 542381d8-628c-443d-8b15-632fc79ffffb |  | note | Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | dca59e0d-361f-4d17-84e5-bca8d7a8ab05 |  | note | METHOD: Site Inspection
label | 1b5fb575-9730-424a-a643-27a2d32b18be |  | note | FREQUENCY: Each Lot
label | 6a08945f-a12f-4673-b6a7-9e8904209efe |  | note | CATEGORY: IP
label | 00073f44-7b0e-4a14-8f3d-ce7ae62c4723 |  | note | RESPONSIBILITY: Site Engineer
label | c47bb4d5-162b-48b0-bf01-e4c530d23314 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b97d2cc-8b8e-4faf-9095-492dff8fddda |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Cementious binder content & UCS requirements
label | 9d76b1bb-12fc-436a-83cb-bc2f9f543312 |  | note | REFERENCE: VicRoads Spec. 815.10
label | 41eb5000-10e3-404a-8c51-e14d08ade888 |  | note | ACCEPTANCE CRITERIA: Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7days
label | 39563927-8177-4c5e-85f2-a8b57921a4fa |  | note | METHOD: Testing
label | 8422961c-a963-42e6-bff9-7f95d0efa673 |  | note | FREQUENCY: Each Lot
label | ba79eb18-36ab-40ea-b076-350f296ec50d |  | note | CATEGORY: IP
label | bc328067-79e9-4b48-8062-73c39e6262c2 |  | note | RESPONSIBILITY: Site Engineer
label | db02a584-bf89-4bb5-b7d5-d400542ccf74 |  | note | VERIFYING DOCUMENTS: Test report
text | f9293f8d-c13d-4833-a062-c95f9a59b1a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Compaction - Modified Compactive Effort
label | 1fb10397-3979-413f-a0c0-a1d0cba01fad |  | note | REFERENCE: VicRoads Spec. Cl.306.05
label | 35f2ee87-68b7-43f8-963e-88b87fd377de |  | note | VicRoads Spec. Cl.306.09(a)(b)
label | 707c6550-ab91-4a65-8d34-7e2cf11babb5 |  | note | ACCEPTANCE CRITERIA: Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content
label | 8220c73f-e504-42a5-887d-2456e2e872ec |  | note | Scale A:
label | 89036ea5-52f6-439a-a653-427ff3fd8dd4 |  | note | No. of tests per lot shall be 6
label | 97389888-e218-4d2c-a84f-2593a35ea271 |  | note | Characteristic value of density ratio > 96%
label | 28eb5c90-5e73-40dd-b8ca-f8474fcb9981 |  | note | Scale B:
label | 68727f2b-3566-406f-ad9a-8c07d977a425 |  | note | No. of tests per lot shall be 3
label | a08a9748-6a44-4fe0-9a84-dd8f8ccf373a |  | note | Mean density ratio > 96%
label | db4ee612-4e34-4f1a-8dc4-0ae0257d3098 |  | note | METHOD: Document review
label | 7880b474-619f-4c00-9d37-d8e948946f74 |  | note | FREQUENCY: Each Lot
label | 8bac1c2e-08d3-412d-b5f8-16a3d83e9296 |  | note | CATEGORY: IP
label | a564f8af-7d8a-41cf-9fd6-28c7cdc4e8e5 |  | note | RESPONSIBILITY: Site Engineer
label | b6b9bd33-78a8-4431-919e-6e31ad8b5792 |  | note | VERIFYING DOCUMENTS: Attach: Test Report
text | 000bad02-ef61-496b-9bf4-f1ea2d690609 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Test Rolling
label | ea7b1da6-cd10-42fb-af6a-7ac124ac3fbf |  | note | REFERENCE: VicRoads Spec. Cl.306.10
label | ab64ec9e-cbe8-471d-94fe-323ee37c3c2e |  | note | Table
label | 63288f04-d990-46ae-8be6-ace1747b28bd |  | note | 306.091
label | 9c511e7a-b64e-4c27-82cd-412f777360c0 |  | note | ACCEPTANCE CRITERIA: Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
label | cd947135-fba8-4e3f-92ee-624913da8083 |  | note | METHOD: Site Inspection
label | 3b5f5636-ba0b-4c69-b5e9-c2b4688154f5 |  | note | FREQUENCY: Each Lot
label | 562d2bc8-6912-4225-b0bb-c28d65d67442 |  | note | CATEGORY: HP
label | bdcbf170-b543-4021-9255-769b297b4c48 |  | note | RESPONSIBILITY: SE, NA
label | 2a55e6e4-bf94-4e54-a373-81ddb889bb44 |  | note | VERIFYING DOCUMENTS: This ITP
text | fdbe01f8-aad5-406a-a6af-75a037d8c5dd |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post Construction
checkpoint-status |  |  | checkpoint | 4.1 Surface level
label | e827da59-3913-4d03-a746-4544eac31297 |  | note | REFERENCE: VicRoads Spec. Cl.306.03(c)
label | a7708a7d-2d90-425b-aced-52957e3526f2 |  | note | ACCEPTANCE CRITERIA: No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase
label | a512571e-68a7-41a2-b1eb-ceb529c26819 |  | note | METHOD: Document review
label | 6293b549-1356-4d02-bd09-a6ed271454e2 |  | note | FREQUENCY: per/lot
label | 984fa07e-9c92-4af2-8252-b33b31db01a4 |  | note | CATEGORY: IP
label | 34e0fc64-d364-4825-9904-0d3a8ee23657 |  | note | RESPONSIBILITY: Site Engineer
label | a995b1c9-1a61-43ee-9b3a-a2ea81f2db78 |  | note | VERIFYING DOCUMENTS: Attach: Straight Edge Verification records
text | d4c6cb2e-21a1-4d49-ad6d-7645f61d508f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Level
label | 6f6e4ba1-e5d9-4f62-8fff-e94873772cb0 |  | note | REFERENCE: VicRoads Spec. Cl.306.03(b)
label | 936fb76a-19f2-46b4-bffc-9c798ffee127 |  | note | Table 306.032
label | c495b62d-b253-4c18-bd44-01a1842adfa5 |  | note | ACCEPTANCE CRITERIA: Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
label | 551dec16-f21e-4169-9c3b-beaf51f3189a |  | note | Scale A:
label | cb507e82-30db-46ea-a6df-2dadbde099af |  | note | Subgrade:
label | 75119037-0500-4b73-bca2-c574e2a36aa0 |  | note | Mean value of all level readings to range between +5/-15
label | 27695619-e5d3-4be0-b247-84d0befa509d |  | note | Standard deviation of all level readings to be less than or equal to 12
label | 02e97248-b8d1-4efa-a4f3-b6beab6d08fb |  | note | Subbase:
label | df48c307-32b8-4dd6-a59b-5946845ecc1d |  | note | Mean value of all level readings to range between +4/-8
label | a935054f-7865-459e-8511-bbd518b1ecce |  | note | Standard deviation of all level readings to be less than or equal to 8
label | 43c5cd5f-d446-425f-b384-2b23a55377cb |  | note | Scale B:
label | f7c627b9-08a2-4bda-885e-4f9fd8ed2619 |  | note | Subgrade:
label | 211bf883-3256-4976-a664-637491a28369 |  | note | Mean value of all level readings to range between +5/-25
label | 3211777e-50be-4b32-b635-bd4695cb2b82 |  | note | Standard deviation of all level readings to be less than or equal to 15
label | 88a55862-9d49-494b-ae5d-7d5a62ca2a79 |  | note | Subbase:
label | 34d51f82-7531-4e4e-80dd-c3e766edb9ae |  | note | Mean value of all level readings to range between +6/-12
label | 8e5eb8a0-b10f-4f05-83dd-9f6dbe7a8cff |  | note | Standard deviation of all level readings to be less than or equal to 13
label | 399f9c60-73b4-4b5b-9c5c-9a8aefc8d8c6 |  | note | Scale C:
label | 4111c922-9466-4bfc-b5f6-197d9dbfe4a9 |  | note | Level Tolerances
label | aa8077bf-ba1d-4851-a940-71776eb20fe7 |  | note | Subgrade +15 to -25mm
label | 78918539-961b-45c7-b479-66bd6d5ad031 |  | note | Subbase +10 to -25mm
label | 60eda570-ea97-4c66-a6a3-b313cb3a1b6e |  | note | METHOD: Document Review
label | 0c237166-9768-4195-9b99-420300eb4b22 |  | note | FREQUENCY: Scale A: 80 points per lot Scale B: 40 points per lot
label | 2b3ed00f-3949-43e7-8e9f-cea308ad3e2b |  | note | CATEGORY: SCP
label | 8d9306a4-354f-4b71-8c87-23a7708a2b8b |  | note | RESPONSIBILITY: Site Engineer
label | 2600c9ef-46ef-44bf-9086-0b52ba65373a |  | note | VERIFYING DOCUMENTS: Attach: Survey Report
text | 5d91d10a-54ca-4c50-b59f-c6261a561fed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Non-conformance Report (NCR) Closure
label | ee8ef630-1088-4eba-8b4e-428023b491b5 |  | note | REFERENCE: MRPA Quality Management Plan
label | acc3e638-56ec-4e1b-946d-077d038afc06 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder.
label | 4e85cd05-8715-4045-95cd-d1d763499fe4 |  | note | METHOD: Document Review
label | c98df145-a099-457d-af20-e8d77fd2870b |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 0f67e618-377b-40a7-81c5-b434a626f9f3 |  | note | CATEGORY: HP*
label | 5b05ca21-b2d1-4cd0-bcab-b08a09568b1e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 41d5db0b-102b-4adf-889a-aeef3ede2aef |  | note | VERIFYING DOCUMENTS: This ITP
text | 69517db4-d39f-411f-83f6-02aed8fc8f92 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | b4110418-6bd3-4c52-a7b4-866ebbd8bca6 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d4f37320-fe48-4b9d-a3ec-b863495e9346 |  | textbox | Name:
text | 13b513f0-05d9-49c0-8f9b-99bc8ac836f4 |  | textbox | Position:
text | ebbc04ab-127a-441f-88ae-4e3ca2ce31cb |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR Maintenance Walkway - Clyde Rd (Supply & Installation) |  |  |  |  | Yes | ITP-STR Maintenance Walkway - Clyde Rd (Supply & Installation) | a0ea6a58-dd3c-48c3-8cb9-9941b8769f93
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | 1.0 Lot Information
select | e8ae8261-e0c8-5273-bdba-ca989658cd5a |  | dropdown | Lot Status | Identified,Open,Ready for Close-out,Under Review,Reviewed with Comments,Closed-Out
select | 43be4ab2-ffd6-584e-baec-44dc79bd60cc |  | dropdown | Responsible Engineer | Ben Kelly,Brigette Rizzario,Bunnarith By,Danniel Borrie,Danny Gannon,David Chai,Diana Delac,Jack Gascard,Jackson Nunan,Jadan Halket,Jon De Castro,Kia Menchin,Lachlan Summers,Luan PhamMazen Hamady,Mitchel Jacques,Plutarch Deliyannis,Ryan Dsouza,Sanjar Wasil,Scott Paterson,Sebastian Santalucia,Shane Voyer,Shayam Ajjarapu,Ty Qiu,Vince Argiro,Yokanth Ravichandrakumar
text | 95cc1c48-3273-54b3-bc16-2d3fcdc2175b |  | textbox | Design Package No (ex: CBR-0017, AUD-0011)
select | 48624947-ab84-58a9-a2db-e9ace8f59e2a |  | dropdown | WBS Area | Camms Road,Cardina Road,Clyde Road,Fitzgerald Road,Robinsons Road,South Gippsland Hiway
select | f858316e-e4c8-51cb-b57c-3c0272eb5e29 |  | dropdown | WBS Sub Area | Rail - Track,Rail - Structure,Rail - Facility,Rail - Signalling,Rail - ICT/OCS,Non-Rail - Road Authority,Non-Rail - Area Wide,Non-Rail - Council
text | b2c5f7f2-325d-5bad-aea0-65f5030c30fb |  | textbox | Work Start Date (dd-mm-yyyy)
text | b0778344-a313-53fd-8610-b3fdfa507f34 |  | textbox | Estimated date of Lot Close-out (dd-mm-yyyy)
text | 941f44a9-70cb-509a-abae-3ddb570f1d2c |  | textbox | Actual date of Lot Close-out (dd-mm-yyyy)
text | cc85a4bb-2e47-5873-bf1d-9371d870cdcd |  | textbox | Comments
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 21b4a920-c3dc-5037-8d06-43ccdd6c9d16 |  | note | Document Title: ITP-STR Maintenance Walkway - Clyde Rd (Supply & Installation)
label | 18dea407-6dd8-5e83-9f1d-e9ff6f445719 |  | note | ITP Description: Maintenance Walkway - Clyde Rd (Supply & Installation)
label | a1d55882-aefb-56d1-87cd-962beb18a4cc |  | note | Discipline (e.g. CIV/STR/RAIL: STR
label | 7ea014d9-44b6-5fb2-b7a7-265e02c61104 |  | note | Revision Number: 0
label | 74c776dc-a5b9-54cb-825c-3e5abaa2d329 |  | note | Revision Date: 44524
label | 7ab7d9d4-3223-51aa-ae64-7b1f0236771e |  | note | ITP created by: Justin Kreinberg
label | 2534e3e5-7a68-5ffd-932e-d4cf8ba82d13 |  | note | ITP approved for use by: Victor Mira
label | 0b392d58-f111-51b3-a4b1-669177a03551 |  | note | Special Notes to ConQA Team : ITP for Clyde Road
label | 3db59366-9303-5507-a8cd-fc38d84a9f51 |  | note | 1.1 VicRoads Section 610 June 2019
label | 11c629ea-31b3-53bb-b877-2fd0a66270f8 |  | note | 1.2 VicRoads Section 630 October 2013
label | a0d1162b-1cc1-5ea0-af01-759b7b03cfa0 |  | note | 1.3 VicRoads Section 631 February 2009
label | 00526dc4-ec8b-5cf5-b07d-0adabfe8433d |  | note | 1.4 AS4100-1998
label | dcb4fc1e-f249-57de-8ae3-fbba151f04a9 |  | note | 1.5 AS5131-2016
label | 22edd9cc-9059-59d4-a766-6794b4cd0693 |  | note | 1.6 AS4680-2006
label | 43ad8dc5-939e-5056-afc0-d203c82355c9 |  | note | 1.7 AS2312.1-2014
label | bb822264-fec2-5f63-83ea-ba08d0019258 |  | note | 1.8 AS4506-2005
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 846d97c3-bef0-5500-bc9a-913f75fae635 |  | note | Reference: Reference
label | 420e453e-f809-5d97-bf0b-6f2b53055ea1 |  | note | Acceptance Criteria: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. Typically this consists of but not limited to: i. Certificate of Compliance ii. Completed ITP iii. Weld Procedure Specifications iv. Weld Procedure Qualifications v. Welder Qualifications vi. Material Certificates and traceability vii. Quality Assurance check sheets viii. Welding Consumable batch certificates ix. Coating certificate(s) x. Non-destructive Testing (NDT) Reports xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | 3bf1ba5c-ef2b-5bee-87f4-2d8945f90521 |  | note | Method: Document Review
label | f3f2927b-34d4-522a-ac6d-b9e441d23be0 |  | note | Frequency: Each component
label | b896bbc9-b1ce-5eb7-a91d-0c1fba9c7840 |  | note | IP
label | bc1ac9cf-eae3-5092-a588-e15f02ec1f6f |  | note | Responsibility: PE/SE/SPE
label | 4497563b-cc5c-5041-8ff2-5abb054d7461 |  | note | Verifying Documents: This ITP
text | 6aa09c24-609d-59a7-b974-3d2c1a768680 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 2.2 Fasteners
label | 08937038-b3ba-5e31-9291-8b36f29de9ce |  | note | Reference: Reference
label | 1bb8ff81-f66a-5c68-af95-50852dcc3dad |  | note | Acceptance Criteria: Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112 Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252. Enter: Teambinder Material Approval number [free text box]
label | f95429c5-34e2-5fbe-a6f4-1266e241dc27 |  | note | Method: Document review
label | 5fda3e07-3d0c-5f30-8200-bf713553b63f |  | note | Frequency: Where applicable
label | 33079dd8-c50f-5d54-a286-ce39e1b4266a |  | note | IP
label | b43ec95c-bdbb-54bd-81dc-3b91a7730e1e |  | note | Responsibility:
label | 2f83d535-55f9-5bd9-8edd-9111d87b827c |  | note | Verifying Documents:
text | 44eedff3-270f-568a-a43c-251cbb219e4e |  | textbox | Date Completed
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Bolted Connections Using Direct Tension Indicators (DTIs)
label | 67b77103-472a-586b-8a1b-1a2db13507f1 |  | note | Reference: Reference
label | 627379de-9b76-5c9d-babe-11455f141881 |  | note | Acceptance Criteria: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by: i. technical data sheet or information on the product ii. 3 no. min. correlation tests between a calibrated torque wrench and a resentative sample of each bolt diameter/length/grade combination to be used in the Works. iii. a valid calibration certificate of the torque wrench Note: Daily records of use and correlation between a calibrated torque wrench are required, see 6.3 in Post-installation. Enter: Teambinder Approval number [free text box]
label | f21c70e4-9c3f-5bf0-bdf9-18d4baf6cb8d |  | note | Method: Document Review
label | 92153315-51dd-546d-b486-519af2ee289b |  | note | Frequency: Where applicable, once, 14 days prior to use of devices
label | 043ea968-a1a3-5add-b2e6-1e50e2d7ac95 |  | note | HP
label | e1030639-81b5-533e-9d7a-bedf8f161557 |  | note | Responsibility: Nominated Authority
label | d7986415-7911-5f91-b5aa-54e24c95b09f |  | note | Verifying Documents: ConQA Hold Point Release
text | 7f8f61cb-4380-5e8f-b15b-35690c439646 |  | textbox | Date Completed
holdpoint |  |  | signoff | HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.2 Installation Methodology & Works Method Statement
label | 8ade1b0b-4c25-5fc9-bd97-41dd867eba30 |  | note | Reference: Reference
label | 1b322331-ca38-52ac-8a1e-8bc56413128d |  | note | Acceptance Criteria: Details of how the Structural & Architectural Steel will be Installed will need to be provided including the following: - Transported to site; - Handled on site; - Installation Procedure (subcontractor ITP's); Enter: Teambinder Approval number [free text box]
label | e0fa5755-c5c6-5cb2-8c91-0f8e866d415e |  | note | Method: Document Review
label | e46acea6-e293-527e-8108-7739dc6d3aee |  | note | Frequency: Where applicable, once, 14 days prior to use of devices
label | fedb65f6-1a6d-5f06-a33e-041793da28d5 |  | note | HP
label | d2988e94-c713-5253-b536-8594b957ba20 |  | note | Responsibility: Nominated Authority
label | b5301832-f91d-5ec3-a61f-16295301b25f |  | note | Verifying Documents: ConQA Hold Point Release
text | 56f3802b-43ee-500d-9976-af21ee0bfaf6 |  | textbox | Date Completed
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | af177dba-0eb1-5fae-a50c-f447d813e8f0 |  | note | Reference: Reference
label | 953413e4-972f-5932-a2d3-e07d001cf429 |  | note | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 6576c4b6-c60f-5dfe-af83-f0fffba3f427 |  | note | Method: Document Review
label | 1bd77426-d2c9-5a6e-b97f-509e5f13caf1 |  | note | Frequency: Prior to starting Works and at regular intervals
label | 932d2f95-de44-5ed3-81d8-c37d4cac3664 |  | note | HP*
label | c3a36441-47ce-5da2-844f-071ba8ce5052 |  | note | Responsibility: All
label | 10e7f186-ee4e-598d-9ef7-9a35f063bb6f |  | note | Verifying Documents: This ITP
text | 8c1329e2-eef7-5750-b1ce-9a3a93969dd1 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection Checklist
label | 2374a5fe-f00f-5866-9993-5367ccb049e5 |  | note | Reference: Reference
label | c37c3186-8b1e-5675-9cf5-e15ec982d9e0 |  | note | Acceptance Criteria: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion. Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Where bolted faces are sloping at 1:20 or greater, tapered washers must be used. Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects. Complete: Materials Inspection Checklist in ConQA
label | 1ca1383e-2f21-56bb-9c06-fdc2754dc5ec |  | note | Method: Measure Visual
label | cacb64a2-2da4-5031-8449-52c5d210f45f |  | note | Frequency: Each component
label | ed71abff-117c-5cd1-9006-e6e5ee8c192f |  | note | IP
label | 395de7ce-1d90-551a-90b4-fa0bdfa7a302 |  | note | Responsibility: SE/PE/SPE
label | eea15eda-1403-5877-9136-40a567b1a30a |  | note | Verifying Documents: This ITP
text | 3944fd8b-98f6-5e88-9bda-771a8e031b32 |  | textbox | Date Completed
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | 6363a9b2-892d-5097-98f0-b54d92e87430 |  | note | Reference: Reference
label | 1ed21cb0-117a-5da8-af40-4fa90e733394 |  | note | Acceptance Criteria: Ensure the bearing surface clean and free from loose particles that will prevent solid seating of the parts Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
label | 050e8aff-7ef1-551d-892d-ca9ba6fb93f6 |  | note | Method: Measure Visual
label | 01e54c3a-267d-52d1-b423-3db6d04ccf39 |  | note | Frequency: Where applicable, each installation location
label | 7fbfe71b-1bac-53f2-b4be-7c0c63232468 |  | note | IP
label | 234f8b1f-ca97-58cc-ab01-801032a79eb6 |  | note | Responsibility: SE/PE/SPE
label | 8dac8e97-ec7b-5d04-9d45-81205519cb91 |  | note | Verifying Documents: This ITP
text | 5f4393fb-2f82-59e6-9ba0-4fcde3d2d2cf |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | ad32d34e-bdf6-5232-beb9-6e2ed98f7f72 |  | note | Reference: Reference
label | cfab4b12-9f32-53f3-8036-91d793245226 |  | note | Acceptance Criteria: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | 8bf256d9-40a4-5f17-a86f-f2ee2bd6070d |  | note | Method: Visual
label | 01cb4a89-16a9-5ea5-998f-38d1bfff59ee |  | note | Frequency: Each component
label | ad4e0d49-97dd-5691-ba54-73bbca56bccd |  | note | IP
label | ac04b64b-f671-5241-b011-3dee61c8faac |  | note | Responsibility: SE/PE/SPE
label | 8f54bd31-67ba-56b5-b6c5-ac7ee222eb69 |  | note | Verifying Documents: This ITP
text | 271e4c3d-7430-5b99-a4e1-27d5209fbf9e |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | fc414d7e-314f-5d6e-a2f4-f7e0c45e42c7 |  | note | Reference: Reference
label | ab90f623-1255-5ff3-8b54-3a6f965cadf3 |  | note | Acceptance Criteria: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely. Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 5b784de4-1065-547d-ab01-cfb3e25a332c |  | note | Method: Measure Visual
label | 2ed20fe4-8995-5c80-853a-2f368cc54775 |  | note | Frequency: Each component
label | f8a40d7f-d254-53f7-989e-c0fa3aa665de |  | note | IP
label | 79a04845-904c-5300-838a-bcdeb0359bac |  | note | Responsibility: SE/PE/SPE
label | 2d86ae3a-951d-52ae-91d7-22a6e0c7f879 |  | note | Verifying Documents: This ITP
text | 8043e166-c97d-5f46-b00f-c3493a416b0f |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | a50c367a-e2d5-5f62-bddb-edcca3083bd5 |  | note | Reference: Reference
label | da14bd65-50b8-5341-bac9-34c6ad5106f4 |  | note | Acceptance Criteria: Place bolts, washers and nuts as detailed on the IFC Drawings. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 3fa22946-c938-5505-9ad0-0c95940ba33d |  | note | Method: Measure Visual
label | 4eb890d0-cc3c-5bbb-9f4d-c91634379d30 |  | note | Frequency: Where applicable, each bolted connection
label | 4ac82a0b-085a-5d15-bf27-d11a9108a14b |  | note | IP
label | 79d4acf2-38aa-5381-a1c6-d99cbba5e0d5 |  | note | Responsibility: SE/PE/SPE
label | fbc877d5-cdcf-5673-a8b4-d0039da414ac |  | note | Verifying Documents: This ITP
text | 07c6b851-47bf-5c6e-b7a8-61323731e483 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.5 Fastener Tightening - Tensioning Condition (8.8/TB & 8.8TF)
label | 8b6b1075-b5fc-5745-a8d3-dba5b9ab9f08 |  | note | Reference: Reference
label | de69aea2-214c-5745-916a-e810b461f5a2 |  | note | Acceptance Criteria: Nuts shall be either double faced or washer faced type. Place bolts, washers and nuts as detailed on the IFC Drawings with the high strength designation on the bolt and/or nut remaining visible at all times. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tensioned fasteners shall begin with the snug tight condition. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. Mark a datum point that crosses over the static part and the rotating part before tensioning via torque wrench, part turn method, stressing jack or direct tension indicators.
label | aff012cb-7ca7-53bc-85de-922169d58f41 |  | note | Method: Measure Visual
label | be9b7e65-ef49-5260-b821-43b356705749 |  | note | Frequency: Where applicable, each bolted connection
label | 30cf1f42-f5ba-578d-8f53-70f5fdd6db36 |  | note | IP
label | 2359ecc4-1416-5935-99fc-feac9563ecc1 |  | note | Responsibility: SE/PE/SPE
label | 8ec3af18-e102-5025-a316-816834eb7294 |  | note | Verifying Documents: This ITP
text | ae7ab260-e6d5-55d3-88e6-f285740eafaf |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.6 Survey Conformance
label | 1edd4d76-f13a-5860-9d23-a97c66a52d4e |  | note | Reference: Reference
label | 54f92508-28ca-5b4d-850b-7a7b1cd3fd72 |  | note | Acceptance Criteria: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, 5mm Location of beam = ±3mm Location of column = height/500, 10mm max.
label | bb207c2f-28d9-5ce6-8f8e-8cae3f5b9d96 |  | note | Method: Measure Visual
label | 8c58c5b2-d1df-5307-8f8e-db7cd677c818 |  | note | Frequency: Each element
label | 02401212-da98-5128-a083-6d53348800ba |  | note | HP*
label | 36798237-ec8b-5ec7-b49f-ff1898c0013f |  | note | Responsibility: All
label | 60f8e588-19d7-5c66-b492-4022e21f064e |  | note | Verifying Documents: This ITP
text | 17e0d5c9-7676-5f98-af5f-00a56b4c5bf7 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.7 Installation of Electrical Isolation Materials
label | 27991df1-6cd5-5f91-86e7-8f6c6e968856 |  | note | Reference: Reference
label | f6f22278-48fb-5eb1-b3e6-be08fb5864fb |  | note | Acceptance Criteria: Installation of Electrical Isolation Material in locations specified on the IFC drawings - under baseplates
label | 7000b46a-eac2-50f3-9f26-70045d6c68f7 |  | note | Method: Visual
label | f1606bd4-e6d7-5093-9f1b-45753b66f132 |  | note | Frequency: Each component
label | fa2090e1-90da-5298-9c8f-a7a2e28c0606 |  | note | IP
label | 5a1fc1b3-5bfc-5b6d-9c7c-d98b534c04f6 |  | note | Responsibility: SE/PE/SPE
label | 6f5c36cc-f213-5ccf-aff1-2c53630e438d |  | note | Verifying Documents: This ITP
text | 753e813d-234e-5d1a-9c4f-e914b115642e |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.8 Architectural Steel Erection
label | d9109d57-bb87-545c-bac1-5da922114680 |  | note | Reference: Reference
label | 5a4f5d8b-0cd9-5e42-9d20-f4fe68abcb1b |  | note | Acceptance Criteria: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely. Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | a7316706-4c7e-5dac-a153-8cbb26a53282 |  | note | Method: Measure Visual
label | 4fdfb260-6beb-5736-b338-2b0483311d46 |  | note | Frequency: Each component
label | fd40604e-d481-57be-8c71-082fcf1fb838 |  | note | IP
label | a1937175-83cc-51af-ae2c-60c1b06349b2 |  | note | Responsibility: SE/PE/SPE
label | e753afad-6c0a-57a2-80c5-8be78e794811 |  | note | Verifying Documents: This ITP
text | 7f421703-d87b-52bf-8f8d-ee2262852434 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 5.9 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | b63d77ca-e5fd-52dd-806e-133041f1fb35 |  | note | Reference: Reference
label | df983f71-aff6-5e42-b6be-7204e1ac4ad4 |  | note | Acceptance Criteria: Place bolts, washers and nuts as detailed on the IFC Drawings. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | bd135d9d-4415-5cca-9ba0-77be671467c2 |  | note | Method: Measure Visual
label | a51606b9-0ddd-54ae-adba-f90fd0c78db0 |  | note | Frequency: Where applicable, each bolted connection
label | 852565c0-0d0a-531b-a930-6e29234bbc72 |  | note | IP
label | ca15bce5-bebb-5ad2-9075-8e24efcf571c |  | note | Responsibility: SE/PE/SPE
label | fb3754c6-54b4-503b-9648-d27a0793ae15 |  | note | Verifying Documents: This ITP
text | 2f0d9cdd-69b6-5958-a3c3-e73026960817 |  | textbox | Date Completed
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | c2efabf5-de89-58a1-aed4-b96cb48faedc |  | note | Reference: Reference
label | 8711e38e-eb05-5c57-aaaf-0bcc473303d3 |  | note | Acceptance Criteria: After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure.
label | 3e01fa5f-8ff6-5587-9470-a3a7dcd12846 |  | note | Method: Visual
label | b98509a3-57ba-553c-ba47-61ca54f51e4a |  | note | Frequency: Each component
label | 33db655d-58ad-58a1-bf41-f6681683b58b |  | note | IP
label | 657d396d-0fb1-589d-a758-1959dc9066e3 |  | note | Responsibility: SE/PE/SPE
label | 3c403701-a633-5a21-94fb-a6e29c733534 |  | note | Verifying Documents: This ITP
text | 58b82982-96c4-5ba3-b30e-65bbeac4efe3 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 6.2 Direct Tension Indicator Daily Records
label | 199a1557-37e5-5442-84a1-8d840c3969dc |  | note | Reference: Reference
label | fe24ec42-4825-5113-a41e-60d56d275b4e |  | note | Acceptance Criteria: Provide correlation between a calibrated torque wrench and direct tension indicators (DTIs) per bolt diameter. Attach: Daily Record(s) of Correlation Between Torque Wrench & DTIs
label | fecb1064-78fb-5db5-9553-87195457657a |  | note | Method: Document Review
label | a7d51731-e230-58ea-8b17-96e07bb64fc7 |  | note | Frequency: Where applicable, for each day that DTIs were used
label | 1a208bd5-82ff-5166-9b30-91e65709472f |  | note | IP
label | 534c388b-84c8-5610-a3b1-829e339d751e |  | note | Responsibility: SE/PE/SPE
label | b8003b85-acd5-52c8-b741-4fd87a2ac765 |  | note | Verifying Documents: This ITP
text | 44206c7d-6412-5a24-a5d1-bcf4ce103da9 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | 9587c4b5-0c89-5ed0-9bb3-60240deade89 |  | note | Reference: Reference
label | ed091987-9f50-59ff-87fb-defc4d7bb8dd |  | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, 5mm Location of beam = ±3mm Location of column = height/500, 10mm max. Attach: Survey As-builts / Survey Report
label | 613ed62c-a5b0-5835-afc1-cd700972c17d |  | note | Method: Document Review
label | c5e6e0fa-1281-5bd4-830e-c76156d90ab1 |  | note | Frequency: Each element
label | 0e48aa77-7e5f-5280-a2ed-8233c938320f |  | note | IP
label | ddf6932d-709c-5c4e-8bc4-1f05e9cd24b8 |  | note | Responsibility: Surveyor SE/PE/SPE
label | f1a6e1c5-74fa-56ca-a05e-92fc4481cd40 |  | note | Verifying Documents: This ITP
text | b7f53eaf-ce46-53ee-94ff-fa5df10892c5 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 8b210e47-96df-58cd-8a98-b1fbfc9ae21b |  | note | Reference: Reference
label | 87c1405c-3b38-53b9-8fd1-bb3d17035667 |  | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 3e3165e1-d4b2-5f20-8599-2321c8a05447 |  | note | Method: Document Review
label | 6e71077b-43dc-57b2-86c2-836cb2767ad1 |  | note | Frequency: Once, prior to closure of this lot / element / Work area
label | 49bd9db2-7b52-52b0-8874-9628b510a9a1 |  | note | HP*
label | 4080e12d-1715-59fa-ad8e-0e1d4e71c872 |  | note | Responsibility: SE/PE/SPE
label | ad0fc510-5f5d-5c97-a53d-f3bf5cff6649 |  | note | Verifying Documents: This ITP
text | 2433a328-8cdc-5fae-ace8-0e03c40f35b8 |  | textbox | Date Completed
checkpoint-group |  |  | section | Final Inspection
checkpoint-status |  |  | checkpoint | Final Inspection
label | ccb9b4be-1d0d-5d35-96d8-92caed996919 |  | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | 53611894-5691-5477-b396-93590ff5f6df |  | textbox | Print Name:
text | 18956676-06d8-5ed6-af4d-ff409f9b44d1 |  | textbox | Position:
text | 0e186096-ede8-58e8-811a-074d3628d5c4 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-CIV Hot Mix Asphalt (Supply and Install) Rev 2 | itp |  |  |  | Yes | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | a1f26e07-796e-4e39-9745-f46fd1c4bff7
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 0d7c104e-8b4d-459c-80dc-55aed29ff47a |  | note | Document Title: ITP-CIV-Hot Mix Asphalt (Supply and Install)
label | 5b033122-d809-43fd-9379-a13e36524889 |  | note | ITP Description: CIV
label | 63e551e8-9989-4845-9aef-c67baff314ca |  | note | Revision Number: 2
label | 6dbfa83b-9c65-40b0-9d58-76de3d41094c |  | note | Revision Date: 15/01/21
label | 7b579819-2ec0-4836-9821-c80382ef1d88 |  | note | ITP created by: Matt Velcek
label | 4d87f4c9-4754-4432-af38-238eeb3b743a |  | note | ITP approved for use by: Josie Pavlou
label | ee73905a-8cc4-4773-89e3-924794f255b4 |  | note | Reference: IFC Drawings, VicRoads 407, VicRoads 408
checkpoint-group |  |  | section | Preliminary Works
checkpoint-status |  |  | checkpoint | 2.1 Submission of Asphalt Mix Design
label | e9185806-ef44-4bac-bc32-640d3de3cacf |  | note | REFERENCE: Section 407.06
label | 56c990d8-8fc3-4005-9681-2936f3ae8add |  | note | RC500.01
label | 8815fa17-cb9e-4e02-a9be-a6bdd1754c3c |  | note | ACCEPTANCE CRITERIA: Ensure this mix design has been Vic Roads registered and is approved by the Nominated Authority prior to laying mix.
label | ee01d03f-bdac-4a76-992a-1c8bb6e2e87e |  | note | METHOD: Document Review
label | b0ef29cd-6af9-4e44-a01c-90ececa5a9de |  | note | FREQUENCY: Prior to commencing works
label | 28f373e9-2853-485e-9b02-d42bffd31f7b |  | note | CATEGORY: HP
label | 42b0c382-f31e-4cdb-a0d4-857401348dd8 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Nominated Authority
label | aeeec1ac-29c3-4e89-bdf0-c8fd5ea0deb1 |  | note | VERIFYING DOCUMENTS: VR registration and Conformance Certificates Team Binder Approval Number
text | adf61a43-ae35-44f5-99ea-fb4bed300547 |  | textbox | Team Binder Approval Number
text | 64ad8973-78db-438b-aba4-ad44b736f023 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Asphalt Placement and Lot Plan
label | 79c919cf-b2d1-468a-99f1-fcdc8c4f60bc |  | note | REFERENCE: Section 407.17
label | 62745217-0c4d-4e03-a229-87ab662ffbf6 |  | note | ACCEPTANCE CRITERIA: Asphalt placement and Lot plan to be created prior to commencement of works.
label | 3fd1b7b6-17f2-4c38-89e7-53d67a1987c2 |  | note | The location of all joints shall be planned before work commences to achieve the specified offsets between layers and the final position of joints in the wearing course
label | f966e34a-3856-43db-9b1b-abece1c87bba |  | note | Plan to specify start/end chainage, offset/lane and layer.
label | 4b461c4d-57dc-4a44-8061-34d6750794bc |  | note | METHOD: Verify
label | 7e73cda7-b696-4308-ab3f-e8b23563c93c |  | note | FREQUENCY: Each lot
label | f3917ccb-9d84-4e99-8a1f-6ee2f4921beb |  | note | CATEGORY: IP
label | b9fa11bf-ffa9-496d-8a17-8a1045a4f05e |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 883b208c-43c7-4937-9d65-c6ade8473c01 |  | note | VERIFYING DOCUMENTS: Daily Lot Record
text | 2fd521ad-8b91-4b92-be9a-b561f3738259 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Site Inspection and Base Condition
label | fc3d3d15-9141-4291-a333-b47ae7da3a62 |  | note | REFERENCE: Section 407.13
label | e0ee6606-e72d-4557-8a77-f949e5f41d74 |  | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | 7989715e-a8e5-486c-988c-84c667f4743c |  | note | METHOD: Visual Inspection
label | d9dff0eb-3527-461c-9de5-91b4f62d5693 |  | note | FREQUENCY: Prior to commencing paving
label | 46ac559c-3cdb-4686-854f-045ba3c6abac |  | note | CATEGORY: IP
label | b00e4b09-3af2-4c2e-b9a1-ca3de3fdfbe0 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
label | 87a481cb-b851-4b1c-ae59-3a608b9b643a |  | note | VERIFYING DOCUMENTS: This ITP
text | bede4a8c-3eb9-447e-84a8-4ee03c69faaa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Submission of Primer Material Documents (if applicable)
label | 1c9d4b84-dbb9-4328-ac8d-9863c9ec264e |  | note | REFERENCE: Section 408.08 c, e
label | 5d05c682-e7d7-4ec8-9b05-e79a847bd55b |  | note | ACCEPTANCE CRITERIA: The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.
label | 9bfdf18a-839c-4923-951e-39349aa2eb09 |  | note | METHOD: Document Review
label | 1f96c1b5-922e-425a-a9a2-ec0813e6220c |  | note | FREQUENCY: Prior to commencing works
label | 752d8af0-7c42-4873-b625-fc59a66455dd |  | note | CATEGORY: HP*
label | 60171ea9-00fc-4cd5-a1b1-46a3e71a0649 |  | note | RESPONSIBILITY: Site Engineer/Project Engineer
label | ed88e47c-dec5-4b34-b0e4-7f1cb548d4a0 |  | note | VERIFYING DOCUMENTS: Conformance Certificate uploaded to TeamBinder
text | 3983058c-5448-41e7-ae0e-b3013ebed747 |  | textbox | Team Binder Approval Number
text | 376d69cd-a9a2-4972-a7e2-e4ad90d87336 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Application Rates for Primer (if applicable)
label | eab3bbff-8918-443a-ad42-c1af74d5e3ff |  | note | REFERENCE: Section 408.13 a
label | 9f340c37-4128-4abc-b758-cc5bfea33a08 |  | note | ACCEPTANCE CRITERIA: At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent
label | e23d9bf5-c210-49fb-bf44-a2b6ca715787 |  | note | METHOD: Document Review
label | fb649bbe-4eeb-494b-b649-3cf65037277a |  | note | FREQUENCY: Prior to commencing works
label | 563a89ae-37a3-4eb7-b5e3-835e8b5fbb82 |  | note | CATEGORY: HP
label | 9d08db1e-0458-4353-9965-b5ee4626587a |  | note | RESPONSIBILITY: Site Engineer, NA
label | eeea8c7e-2366-4205-95cd-289a1372c898 |  | note | VERIFYING DOCUMENTS: Application Rates uploaded to TeamBinder
text | 6b775d94-1412-44cc-bf77-60bceb399485 |  | textbox | Team Binder Approval Number
text | b5f37a9d-e63f-46bc-91ed-5176fc24b97a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Ambient Conditions
label | 8c1908d3-1aa3-42b1-bcc6-2857a57290c1 |  | note | REFERENCE: Section 407.13
label | ddd32566-ddb9-43d4-8582-a3c4775a37e0 |  | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | 79433f47-3a90-4361-93e1-37b5db1b1c23 |  | note | Base & Intermediate Courses: < 5°C for conventional binders or < 10°C for PMBs & Class 600
label | 6ee21ef8-d022-4608-a927-2f07e781ed25 |  | note | Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | dbb34e8f-62cf-4e99-adfa-0675afce6218 |  | note | METHOD: Verify
label | 8ff8294a-4838-4827-b8d4-64c6a65f4622 |  | note | FREQUENCY: Prior to commencing paving
label | 5473b149-2257-41aa-86c8-1a0af8723f34 |  | note | CATEGORY: IP
label | 5a86bffb-68e5-4155-bda7-daeefafb259a |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | ff31d5b0-4342-451b-9fa2-3e3e4317b622 |  | note | VERIFYING DOCUMENTS: Thermometer Reading Check
text | 18062d41-57ed-4f26-9f30-7f5abc24af65 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Planning of Joints
label | b1bc87f8-bd49-41dc-a58d-007373e5aee5 |  | note | REFERENCE: Section 407.17 (b) & (c)
label | ffd2cf64-925c-40b8-814b-33ed64ed9765 |  | note | Pavement Drawings
label | 86f83b60-07f3-433d-ba8a-5e7bdfe38a9c |  | note | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
label | 681fd1f9-799e-4b76-bd6a-02a689580b46 |  | note | Transverse Joints Offset from layer to layer by at least 2m.
label | b12caf12-dbe2-4f79-a4b0-a6cee709320e |  | note | Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | cff63ee1-9376-49d6-8fff-82e35f8aae86 |  | note | METHOD: Measure and mark out runs by tape measure or survey
label | 632d2a5b-a755-4f29-a2b1-2a1cdc6ba514 |  | note | FREQUENCY: Prior to commencing paving
label | 21d22af4-60a2-4f6f-b7a5-65fb590647fd |  | note | CATEGORY: WP
label | 6cc92fc5-bb4f-4972-9b16-3d0065b8f70a |  | note | RESPONSIBILITY: PE/ Asphalt Supervisor
label | 2c6a2d47-5aa1-4ee3-8603-244b38ffea92 |  | note | VERIFYING DOCUMENTS: Attach Paving Plan
text | 62d9ace5-97db-4308-bcec-76ee07971dbc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Longitudinal Joints with existing Pavement
label | a0f043b4-4fc0-4f68-9551-54bd22fc0cce |  | note | REFERENCE: Section 407.16 (c)
label | bf838d61-c8e6-495e-8563-c842900ed444 |  | note | Pavement Drawings
label | 512ca2f8-533a-44b1-b996-4710e7f05232 |  | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
label | 51dff7ce-8a38-4fee-8f95-32be2464ebd7 |  | note | Depth of step to be cut to the full depth of each individual layer.
label | bbe797ca-323f-4632-8a14-d2cd21b68787 |  | note | METHOD: Visual Inspection
label | 4dd30c75-cc9d-4369-b1b1-95b1a22138f6 |  | note | FREQUENCY: Prior to commencing paving
label | bbbf374c-0d13-435a-aba4-ec2dcf9f7bd5 |  | note | CATEGORY: WP
label | b986d20f-9814-42e7-bc93-480dcfd4c6a7 |  | note | RESPONSIBILITY: PE/ Asphalt Supervisor
label | 2a108a79-52c0-403c-9abf-0df2388d8e57 |  | note | VERIFYING DOCUMENTS: This ITP
text | a471c0ff-f5d3-4a7f-a2ab-881e9d32e7f1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Asphalt placement
checkpoint-status |  |  | checkpoint | 4.1 Tack Coat
label | ad0d56f3-9e07-408f-b6c0-59ac2f286b95 |  | note | REFERENCE: Section 407.15, 407.17 a)
label | d68cf894-2baa-40e9-b82a-6145035c35f0 |  | note | AS2150 11
label | 1cc560c1-ab75-4970-a661-7d9a6c5942d9 |  | note | ACCEPTANCE CRITERIA: A tack coat shall be applied to the cleaned asphalt or sealed surface on which asphalt is to be placed unless the unsealed surface has been primed.
label | 5d3307af-7da8-4486-ba46-480f49300073 |  | note | All cold joints and abutting concrete edges shall be heavily tack coated.
label | f0a48815-81a0-48c6-b464-784b542b6c8e |  | note | Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
label | 78f36138-fbd0-47c1-ba27-8d2e2c919b67 |  | note | Tack coat must be allowed to turn from brown to black before paving.
label | b6dce9af-814c-46f9-a3d9-25b27e8ee4f3 |  | note | METHOD: Visual Inspection
label | f77e4d36-9ed6-4ba9-94ad-401a304b4e0d |  | note | FREQUENCY: Prior to commencing paving
label | b3f62b0c-84ad-4b42-bd39-2c14253d57f5 |  | note | CATEGORY: WP
label | 43406619-e033-49f1-9dcb-b2f07687562e |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | 5eddd275-bf7a-41a2-857a-b87551fa6764 |  | note | VERIFYING DOCUMENTS: This ITP
text | 007c2b67-6abc-4335-a47f-9325f78a57ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Commencement Primer Placement (if applicable)
label | a5c28c9d-44d8-4038-a5b3-f09a7c83e431 |  | note | REFERENCE: Section 408.04 b
label | 508b5cca-4990-4b69-88d5-0d40ce55d17f |  | note | ACCEPTANCE CRITERIA: Work shall not commence until the Contractor and the Nominated Authority have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 hours prior to the works occurring.
label | 926cb8fa-383a-4707-bea6-742fdefb02fa |  | note | METHOD: Visual Inspection
label | 4a124f6f-c060-4258-82e9-6628e485cb79 |  | note | FREQUENCY: Prior to commencing paving
label | 8a690b9a-f799-4d70-a72e-c83628b7e3d2 |  | note | CATEGORY: HP
label | 76df2272-19ce-4f38-a94a-21b6bcf737cb |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor / Nominated Authority
label | 959c7bd1-076a-4009-91d6-11a8874fec2c |  | note | VERIFYING DOCUMENTS: This ITP
text | 6fab13ad-dae8-46bb-9005-e489ce171fca |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 Commencement of Placing Asphalt
label | 5b11f1bf-09b3-4a77-a38e-038d10d2efdf |  | note | REFERENCE: Section 407.18
label | e032dfcf-5af7-4469-a63f-323e33c663dc |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Nominated Authority
label | dda9fab3-877c-405f-9519-286d894f798e |  | note | METHOD: Visual Inspection
label | 1fdbac30-d5ab-4710-bf43-2af7784c0f6e |  | note | FREQUENCY: Prior to commencing Paving
label | be68bb86-6372-4504-9d61-0a562efcc224 |  | note | CATEGORY: HP
label | 5d84bb23-f2de-459e-9bce-da2da839aac2 |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor / Nominated Authority
label | 5d404bca-ab89-4b1d-8016-c24e233a1bc6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 268811d4-ee0e-42a8-9ba8-302cd2dc653d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Mix Design Confirmation
label | 92c28298-7d95-40d7-88c2-ad2ff5ca0e82 |  | note | REFERENCE: Section 407.06
label | ee4eb534-21f8-4102-8636-b8fe5640cc48 |  | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
label | 32459a27-ff09-4da0-8461-aebc4dcc54f6 |  | note | METHOD: Document Review
label | 110aff5d-7d4f-4828-8b7b-cd887b6c87a2 |  | note | FREQUENCY: Each lot
label | 6f0cfa6d-7c8f-46e4-8c91-0ba2691b1d6c |  | note | CATEGORY: HP*
label | 4b654206-86b9-41cb-a6a6-cf3c6bdb7e6c |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | 63acbcaf-8ff0-466f-b20f-b668b65cf040 |  | note | VERIFYING DOCUMENTS: Attach Delivery Dockets
text | c9fa1910-123f-4a37-b296-9c44e9cb953e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Asphalt Delivery
label | c5fc10cc-46b8-48e5-8cf8-a6d9c07904f1 |  | note | REFERENCE: Section 407.16
label | 8a8d190f-7f7e-4e8b-b46b-34a424b0a9da |  | note | Table 407.081
label | a0df6876-a9f3-468f-91bb-dd45307f283e |  | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | 16e8a5f5-0983-441e-8415-8fe1dcd6d115 |  | note | METHOD: Visual Inspection
label | 9d105a5d-06c2-43a7-bd75-e1949c8dfec7 |  | note | FREQUENCY: Each load
label | 8189f412-28ff-4649-94ce-89d4d3c1a9cb |  | note | CATEGORY: WP
label | 9d2b31c5-c706-42a8-b473-0a5448a4e175 |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | a092f1e6-6ffb-4dad-9af2-54c1e3dae6c5 |  | note | VERIFYING DOCUMENTS: Attach Delivery Dockets Thermometer Check
text | a8c92335-2e92-4c04-95bf-78221ae79bed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Layer Thickness and Level Control
label | 33891438-fd8a-4641-8e0b-b5bce7929f62 |  | note | REFERENCE: Section 407.20 (a) & (b)
label | 6623dddf-b733-4a69-91d4-1e14ea13e381 |  | note | Refer to IFC drawings
label | 9c1d6e24-5d7a-4374-8ccb-ed8ed9828b31 |  | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications.
label | ffea584f-9c21-49f1-a928-5c25fe9b3357 |  | note | METHOD: Verify
label | 0d376ec5-911f-455f-9321-d873fffa06c4 |  | note | FREQUENCY: Regularly during paving
label | ed5c5feb-b1a5-4234-83f5-21d045bbcdf5 |  | note | CATEGORY: WP
label | d4a28e5a-945f-4753-9e78-10dc22a25a1d |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | c80dc0aa-96f2-4567-af86-e3c92fd79459 |  | note | VERIFYING DOCUMENTS: Dips using ruler or dip stick This ITP
text | d1f875b8-dc06-43a0-9ac5-f899d6bed07e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Spreading and Stoppages
label | f4a9e4f7-f032-48fd-b8fb-4d5b9fb1f267 |  | note | REFERENCE: 407.20 (c)
label | d9a8c3bc-5d4f-48c7-9784-d97149b8ce34 |  | note | ACCEPTANCE CRITERIA: All asphalt shall be spread with a aving machine to form a uniformly smooth asphalt mat without segregation, tearing or gouging. Paver not required for small areas where use of a paver is not practicable.
label | 4446186d-0931-4448-9b97-c19d14ffabb1 |  | note | Conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised.
label | 90cbba92-102b-4e1e-a150-cd59e693c7ba |  | note | A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | 52651134-36b2-4bbc-bbce-4dfb4bdc2360 |  | note | METHOD: Verify
label | 1540dca2-3dff-4751-9efe-358d83d3015b |  | note | FREQUENCY: If paver stops
label | 7450322a-f42a-4aa0-8b6a-abbf6d4102af |  | note | CATEGORY: WP
label | ae816286-3df5-4b4c-9455-3992c0896e22 |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | 2c36884b-117d-451e-8f7b-53cdc66a6f2e |  | note | VERIFYING DOCUMENTS: Thermometer Check
text | 6e8f2391-ef4f-4c00-a6a3-fa7826f4f8b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Surface Finish of Wearing Course
label | 9f65327f-b648-4038-b50a-1ea499191160 |  | note | REFERENCE: Section 407.23 (a)(I)
label | 550368fb-e601-478f-bd40-0e9df0bcf51e |  | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | 2b4f699c-923c-420b-8182-75541f0211f2 |  | note | METHOD: Visual Inspection
label | dae8a782-839a-4b72-891c-fe385d2c97ba |  | note | FREQUENCY: During paving and after final roll
label | 16379b2a-e028-4480-9a27-f067cea61427 |  | note | CATEGORY: WP
label | 42883967-87cd-4495-9085-bb7276cb8ce1 |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | 4a734d56-46c5-4fec-be40-936afcf0808a |  | note | VERIFYING DOCUMENTS: This ITP
text | a23c1859-3ada-453f-b3eb-28fdb6516f85 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Kerb and Channel
label | 60ed9b1b-de57-4532-85ce-45386cfd554d |  | note | REFERENCE: Section 407.23 (a)(ii)
label | 12ddcfab-ac6c-4827-b9e4-fc9682b6ac27 |  | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified.
label | d19d606e-47c9-460e-8127-cf28da4ca14c |  | note | METHOD: Visual Inspection, Document Review
label | 770c2cf7-f46e-4be3-ae90-0a889c5c24ad |  | note | FREQUENCY: During paving and at completion of work
label | 54466f07-70d3-424e-828b-38f9f64781ad |  | note | CATEGORY: WP
label | 11bda3fb-c828-4806-a721-d78a53fa8415 |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | 47859f3b-8c7d-42cc-b06d-0c63c1f2d79d |  | note | VERIFYING DOCUMENTS: This ITP
text | b45e7652-5213-4c69-b4e3-29ade3d64ab0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Alignment (Asphalt not placed against conc. Edging)
label | fa384a1f-033a-4323-831e-b75f94b9a72e |  | note | REFERENCE: Section 407.23 (a)(iv)
label | e1056164-2d0f-418c-9454-f480670ce817 |  | note | IFC Drawings
label | 4fc99355-8bb2-41f9-a66c-e0987748653f |  | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | 2c148b82-a92f-4bd3-836f-b4e5b2f87630 |  | note | The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | 1a9e2a0e-5403-4af9-8b84-0309ce666646 |  | note | METHOD: Visual Inspection, Document Review
label | b946bcb9-0a6f-4674-bd05-811230190914 |  | note | FREQUENCY: During paving and at completion of work
label | 5b02cc1f-05bb-4edf-95a5-c899e227eb72 |  | note | CATEGORY: IP
label | 7284dc24-6243-481d-af80-91b407650f9d |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | 8891474b-4396-45ce-86f3-eae7756512ae |  | note | VERIFYING DOCUMENTS: ITP Signed and Survey Conformance
text | 08f4478f-ba9b-46e1-99da-0fb6c11e3132 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Width (Asphalt not placed against conc. Edging)
label | aab0079a-ad29-4e96-b80c-9e7bcc4a70b3 |  | note | REFERENCE: Section 407.23 (a)(v)
label | 78b1bd1f-2446-4a15-89e1-a6429596fe90 |  | note | IFC Drawings
label | a174690c-471e-42ab-a9f6-2cba5f98ed55 |  | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
label | a0d1c207-2d8e-40d7-85dc-a76b976eb023 |  | note | The average width over any 300m shall not be less than the design or specified width.
label | e4119082-b5c4-409e-86bd-9a3a35ea4cc1 |  | note | METHOD: Visual Inspection, Document Review
label | 48ebce3e-e957-4896-8c7e-8309768e6183 |  | note | FREQUENCY: During paving and at completion of work
label | f1e33c63-9a1e-46e9-94b2-5195c38bd2ae |  | note | CATEGORY: IP
label | 7e10de79-2cfe-4526-9e48-072922fb95fb |  | note | RESPONSIBILITY: SE/ Asphalt Supervisor
label | 1e5f9e60-1687-4621-b9fa-fce836856515 |  | note | VERIFYING DOCUMENTS: ITP Signed and Survey Conformance
text | 2dd1ca15-dac1-4f5f-abef-b737b326330d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Testing
checkpoint-status |  |  | checkpoint | 5.1 Compaction and Assigned Density Ratio
label | 411248b9-e77d-48d8-ad34-fba5e1f82df8 |  | note | REFERENCE: Section 407.22 b)
label | 2d4dff48-11d7-43f6-8a88-f373f824b302 |  | note | Table 407.221
label | 7de6742d-791c-4453-8d76-c62867aa478b |  | note | ACCEPTANCE CRITERIA: For layers <50mm, characteristic density ratio to be ≥ 95%
label | cf5dc106-e94b-4033-b32e-cd4c0b1b0817 |  | note | For layers ≥50mm, if characteristic thickness to be ≥ 96.0%
label | e8f1a357-840b-4116-af6e-c562306d1ffa |  | note | The assigned maximum density of the asphalt shall be calculated. Should a single maximum density of the production mix vary by more than ±0.5% of its rolling average then a check design or redesign should be initiated.
label | fca12a33-e8b7-41e6-9fcd-2b053145e0e5 |  | note | METHOD: Document Review
label | 3735cefa-5d72-421f-aa9c-e835fc21cf2e |  | note | FREQUENCY: Per Lot
label | c9e20316-d674-4a17-97f9-0f0a5d97d2ef |  | note | CATEGORY: IP
label | c6657f79-2079-478c-b34c-56e5936a4381 |  | note | RESPONSIBILITY: SE/ FH Lab Technician
label | 9252aa49-0bdb-4f2a-802e-3d628494dd49 |  | note | VERIFYING DOCUMENTS: Attach Test Report
text | a06a5ae8-7520-4910-b9c0-72bfd26fb054 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Level Conformance
label | 8391d61d-3dc0-45ad-af40-12422790cfe7 |  | note | REFERENCE: Table 407.232
label | 2857ad51-5aa1-4baf-9fa5-afee98eb7ae3 |  | note | Section 173
label | da5dd72b-c4dc-4aac-9415-3ecbdf8baae6 |  | note | ACCEPTANCE CRITERIA: Scale A (Princes Hwy):
label | dae0a139-cadd-4c14-89a9-a005d92b273c |  | note | Individual departures from design not to exceed ±5mm with a standard deviation of not > than 8mm. 80no. Measurements per lot.
label | 46eecbde-f3f4-456d-b43d-cd605bd3fb28 |  | note | Scale B (SGH):
label | 8a9be03e-5447-4c85-81a8-ad9cf7c662cd |  | note | Individual departures from design not to exceed ±8mm with a standard deviation of not > 10mm. 40no. Measurements per lot.
label | 965b16da-5fe9-4e8a-ba74-6f68a3c289e5 |  | note | Scale C (Beaconsfield Car Park):
label | a60b48fc-2208-4b61-8452-8e7ab2ef5bb2 |  | note | The level of the top of each asphalt course shall not differ from the specified level by more than 15mm for intermediate and base courses and 10mm for wearing courses
label | 2d8ad49a-a2e2-4b2b-92aa-e47f47015f81 |  | note | METHOD: Document Review
label | ee52d244-ec82-408f-8043-b614cc336c5f |  | note | FREQUENCY: Per 4,000m2 at completion of work
label | 7942ea3b-b76d-40e1-a233-71ce4a02a59c |  | note | CATEGORY: IP
label | a9d5e2a2-80a7-4402-a140-5592c9c44efb |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
label | fd5e940b-5d2c-4999-bcab-3b5f487a4c3a |  | note | VERIFYING DOCUMENTS: Attach Survey Conformance
text | dc00edec-16c1-42ef-b190-f7b9aaff0275 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 5774cd11-d47e-42c5-bf1d-067a8e2b30d3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 9bfa8995-46a3-4a13-a82e-ecf01f9284b1 |  | textbox | Name:
text | b91d2e70-7f40-4fd0-ad5e-f252fcc4f1dd |  | textbox | Position:
text | 85b2c223-1861-4fd8-bed3-a470c2adf79f |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-RAIL- Capping Layer (Supply & Install) MTM | itp |  |  |  | Yes | ITP-RAIL- Capping Layer (Supply & Install) MTM | a2598aaf-1029-45b8-aaae-236b8caace14
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | f4ef7b13-24da-5f13-9c90-4b4cbdfec610 |  | note | Document Title: ITP-Rail-Formation - Capping Layer(Supply and Install)MTM
label | a4c63a82-2fe4-502e-8ca6-cf37fb993cda |  | note | ITP Description: Formation - Capping Layer(Supply and Install)MTM
label | e098da63-178b-55bf-9a14-78ee301c87ae |  | note | Discipline (e.g. CIV/STR/RAIL: Rail
label | 379f4fa9-d6d3-5eba-bfdb-1e4bddc8c7e7 |  | note | Revision Number: 0
label | 7fa4f4f1-9b00-5138-a737-36d7b484edc9 |  | note | Revision Date: 6/07/21
label | e03430f0-d5d5-5333-a92f-49b147f73a03 |  | note | ITP created by: Yasna Naicker
label | 3b2ec2ba-0147-58ee-868c-1f8c687ef069 |  | note | ITP approved for use by: Romualdo Magpantay
label | 82762943-3874-56ba-b960-97aac2cda983 |  | note | 1.1 Drawing Pack - Rail Track and Civil
label | b0da9101-5fa9-5865-a15c-03987ea29748 |  | note | MRP-016-C-ACD-REP-03-NWACPW-0001
label | b6932ab1-995e-5ec6-a6f9-5472c28192e2 |  | note | 1.2 Metro Engineering Specifications - Earthworks & Formation Specification
label | 0f6eaf1f-a706-5919-b3ce-86bd4428af13 |  | note | L1-CHE-SPE-178 (VERSION 2)
label | 5c938084-cf7a-5001-a362-410a4fc45b4c |  | note | 1.3 Metro Engineering Specifications - Earthworks & Formation Standard
label | d0923375-1a1f-501f-b51d-5529d459719a |  | note | L1-CHE-STD-029 (VERSION 3)
label | 89677cd2-a2d1-5e29-8b8f-55ab7007d55f |  | note | 1.4 Australian Standard - Methods Of Testing Soils For Engineering Purposes
label | a6f4d8bd-b428-5e08-8bda-3a197cac3c31 |  | note | AS 1289
checkpoint-group |  |  | section | Preliminaries/ Material
checkpoint-status |  |  | checkpoint | 2.1 Verification of Capping Supply Material
label | f36043b8-e770-5fa5-ad97-21d85868ba2e |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 11.2 Table 6 L1-CHE-SPE-178 - Clause 8.8 AS1289 Tests
label | e540c2d8-259f-5431-8192-92f8196125a3 |  | note | ACCEPTANCE CRITERIA: Capping material shall comply with the following grading requirements: • % passing 53.0mm sieve 100% • % passing 37.5mm sieve 100% • % passing 26.5mm sieve 100% • % passing 19.0mm sieve 95-100% • % passing 9.5mm sieve 60-90% • % passing 4.75mm sieve 40-70% • % passing 2.36mm sieve 30-60% • % passing 0.075mm sieve 6-10% The following tests shall be carried out on samples of the capping layer material: • Soaked CBR - minimum 50% compacted to 95% modified dry density • Liquid Limit - 30% Max • Plastic Limit - 20% Max. • Plasiticity Index - 4-15% • Linear Shrinkage - 4.5% • Dry Density - 2.0t/m³ MIn. Refer to AS 1289 for Tests
label | 14c44887-b4fe-54f8-bf26-7120dab1e22c |  | note | METHOD: Document Review
label | 96e0f02a-242d-54c6-b011-5fe5b41b452d |  | note | FREQUENCY: 3 tests per 500m³ atleast 2 tests if < 500m³
label | 28aa2a56-3b7c-5bf7-abaa-c68da5df0c35 |  | note | CATEGORY: HP
label | fe78a039-0811-5df5-b130-4cacc51d5e04 |  | note | RESPONSIBILITY: SE/PE
label | 64ab9f68-f4d0-59bb-a9dc-fa0fda858897 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9e122db6-4a96-5f71-8d6b-9d93ac922632 |  | textbox | Team Binder Approval Number
text | 460b1d0d-0227-5d56-91c5-e86d3326539c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Capping Fill Layer Preparation and Installation
checkpoint-status |  |  | checkpoint | 3.1 Survey set out
label | 6b59773a-2793-5d67-a135-1e3ac8966e47 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 8.2.1a
label | 35bbdbb3-c224-57ae-bedf-a712d54337e0 |  | note | ACCEPTANCE CRITERIA: Survey control requirements for setting out and validation of foot prints, level & slope angles
label | e4865225-5d4b-5051-ad79-f2692344d70d |  | note | METHOD: Visual and Measure
label | cbf9a0cd-4aa5-515f-bdf0-1033f30e6ba5 |  | note | FREQUENCY: Prior to Commencement Each lot
label | e62a0a5d-cc53-5cf2-b20d-83e87cb5e0af |  | note | CATEGORY: IP/SP
label | 59e46b5c-5832-565b-9217-4fd878a2bfe6 |  | note | RESPONSIBILITY: Surveyor SE
label | de93909e-3d27-5760-9a81-64993207187e |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6147d154-3b81-58ca-87e8-b18b0ef823c1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Capping Layer Preparation and Installation
label | 4f7f4bc4-e619-5520-a5a5-0458e0f7e459 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 11.3
label | b1199e77-d423-5d3a-b8ae-760551010662 |  | note | ACCEPTANCE CRITERIA: Capping layer shall be constructed in one layer and compacted to a total compacted thickness of no less than 150mm.
label | a72f6a41-d4b8-5e54-a8dc-05b5844e9036 |  | note | METHOD: Visual Review Test
label | 0f174d33-bd09-5372-85ed-a8cfc3405ab0 |  | note | FREQUENCY: Each Lot
label | ee5a6a49-b1bc-56f5-9b1f-fb30dce51c0f |  | note | CATEGORY: IP
label | 6cc4b082-acab-5836-8144-ff2f00ee7cde |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 68111c49-3e9d-5430-b5de-cd4e2081c849 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 76c0838d-e19d-5191-8f3c-9bdd70bbab05 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Onsite Compaction Testing to specified Density
label | 7b294148-50ac-5660-9519-f5858ae99651 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 11.4 AS 1289
label | d6cb316a-9326-5eb0-abc9-b94936183544 |  | note | ACCEPTANCE CRITERIA: • CBR > 50% • 99% Compaction (Modified Compaction Test)
label | dfafdd96-1af3-51a9-8c3f-7a0e41fa535d |  | note | METHOD: Modified Compaction Test Review Test
label | de031bcf-2f56-50b3-93d8-d332fa37ed54 |  | note | FREQUENCY: Each Lot
label | 54134fea-2faf-5867-be1f-bf13ff2eabd3 |  | note | CATEGORY: HP
label | bcb9a7e8-37c7-52ec-8b76-a8d05e1a6b96 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | 18a3f9ce-f73b-5b68-85e2-9f4aab1013e0 |  | note | VERIFYING DOCUMENTS: Testing Report
text | f565d84c-6a16-59d1-8cbd-0560896e4893 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Proof rolling
label | 6fe88309-baf6-5552-bee8-5132c57adce2 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 9.4.1.a and Clause 8.6
label | 6cf719bd-12eb-5d2e-b2f4-657629b25846 |  | note | ACCEPTANCE CRITERIA: Proof roll as per L1-CHE-SPE-178 - Clause 8.6
label | 93496084-802a-5af4-bf21-69d8daeee7e8 |  | note | METHOD: Proof roll
label | deeb4e27-4e35-5aac-b5d5-d9948bd67e83 |  | note | FREQUENCY: Each Lot
label | 5134ba44-5780-58f3-bdd8-86a9bb6ffbda |  | note | CATEGORY: HP
label | 8e754542-b5b5-58ed-bf65-ef5fbe64940b |  | note | RESPONSIBILITY: SE
label | 93161a75-81d2-5917-8821-ded9f7b5d059 |  | note | VERIFYING DOCUMENTS: MTM /NA representative signoff
text | d44e2133-f8bd-5f84-92b3-37b0c0a33cbd |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Protection proof roll area(Proof rolling)
label | 68e47369-1867-50d4-81ba-cfbcd1c6ca52 |  | note | REFERENCE: L1-CHE-SPE-178 - Clause Clause 8.6.5
label | 8f679c4a-e614-5a3a-a86f-25a94eb4add3 |  | note | ACCEPTANCE CRITERIA: Upon accheivement of a satisfactory proof rolling result, subsequent earthworks layer constuction shall begin with in 2 days. If 2 days exceedshall determine if weather in the period between proof rolling acceptance and construction commencement, or any other activity or occurrence, has had any detrimental effect on the performace and sole discretion, futher rolling mybe required.
label | d723d13c-b51a-55ff-8732-3c57f1a4f873 |  | note | METHOD: Proof roll
label | b1f9e6ea-dfdb-5a63-8dcc-cb110e428ba6 |  | note | FREQUENCY: Each Lot
label | 952d241f-e9b0-5c87-9a51-02f557e98c0a |  | note | CATEGORY: HP
label | 17007508-64a6-5d52-8db2-70c6647af159 |  | note | RESPONSIBILITY: SE
label | 22393fd2-dd74-5b80-9f24-7096a64e4925 |  | note | VERIFYING DOCUMENTS: MTM /NA representative signoff
text | 97f83e41-bd39-5f85-b939-c7e049460b67 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Capping Layer Finishing and Tolerances(Post Construction Activities)
checkpoint-status |  |  | checkpoint | 4.1 Capping Layer Finishing and Tolerances (AS built /Survey report)
label | 40e688d2-d5eb-5e51-a724-9c4abfe3b5fe |  | note | REFERENCE: L1-CHE-SPE-178 - Clause 11.6
label | ee51175f-742c-51f2-8b2f-b0257e5f2202 |  | note | ACCEPTANCE CRITERIA: The finished surface level of capping layer shall: - Be within -25 to +0mm of approved design level - Be within 10mm of algebraic difference of the deviations from the correct level for any two points 20m apart on the centreline - Be within -0mm to +10mm of 3m straightedge laid on final capping layer surface parallel and perpendicular to centreline
label | fddb4c41-b3db-54b2-b0b4-1a9a67bcba09 |  | note | METHOD: Document Review
label | 6654d903-09d4-5db7-934d-ace2d6ddb6ac |  | note | FREQUENCY: Each Lot
label | 273d2aaf-94cd-5469-b61a-ade2ab923e7d |  | note | CATEGORY: IP
label | 17c4522e-19a0-5825-966e-00e82b092a42 |  | note | RESPONSIBILITY: SE/Surveyor
label | ac9403cb-83bc-5be8-b701-448f51503db6 |  | note | VERIFYING DOCUMENTS: Survey conformance report
text | 19c06dde-2f40-5119-a78a-2a7c4cc35496 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Non-conformance Report (NCR) Closure
label | db0b78a3-9ad8-5169-86f8-013b6ffaa893 |  | note | REFERENCE: MRPA Quality Management Plan
label | 773912b6-6812-5f05-ac50-4bdf5ffdac5a |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 3a4f623a-0391-5a3b-b060-0d1aa3fa2122 |  | note | METHOD: Document Review
label | 088a204d-318f-5a22-9aed-a0d9e881b305 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | fbc73537-5888-5c30-ba77-f5b366e973f2 |  | note | CATEGORY: HP*
label | 2faaa401-0201-5d5d-92ca-c6e1cf55c611 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 04332db2-2878-5020-b007-7a6652af1314 |  | note | VERIFYING DOCUMENTS: This ITP
text | 56ea56af-6010-595d-9d3a-2304bb2bacfb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6054b912-13c0-57e7-b97f-df37a217b683 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 506a8244-9d57-5ad4-a318-5e01f8d56949 |  | textbox | Name:
text | 72a1965d-817a-564f-91a8-d512b50e7b41 |  | textbox | Position:
text | dca2ccb8-b680-527c-91b5-ac0779fbd1ae |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Structural Concrete Crack Repair Rev 0 | itp |  |  |  | Yes | ITP-STR-Structural Concrete Crack Repair Rev 0 | a5017b0a-5cb8-47e8-8183-3293c6a46dca
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 94265fa4-3532-46ee-b138-1b6aab23d3b3 |  | note | Document Title: ITP-STR-Structural Concrete Crack Repair
label | 575ec356-8fff-4894-94f6-510a2e9562d1 |  | note | ITP Description: Structural Concrete Crack Repair
label | 78d1c8c7-f19a-413e-a50c-bf74e97da78c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 4eb493e3-f1f8-4482-b5f3-ac545fee579f |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | a0e3a926-b4c7-4c2b-a8f7-0f62e2e40897 |  | note | Revision Number: 0
label | 9cc2e852-e145-4368-9011-b128e7783903 |  | note | Revision Date: 6/11/2020
label | 9dcca10c-d2ad-4448-a536-0e2bf0bd11ad |  | note | ITP created by: Mike Freeman
label | a503ae7e-f05b-4499-9039-40897052a822 |  | note | 1.1 VicRoads Section 610 June 2019
label | 496b90ba-1bad-4f73-84c0-54d3cdf91b41 |  | note | 1.2 VicRoads Section 687 August 2018
label | ef7bd48c-036c-4692-9996-0a8deaa93995 |  | note | 1.3 VicRoads Section 686 November 2018
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 2.1 Assessment of Cracks
label | 289c88c3-cb79-4bb1-be29-135590743903 |  | note | REFERENCE: 687.01
label | 1a6f19ee-5043-4d1c-b60c-0852d6d870d5 |  | note | 610.24 (b)
label | 45f2c8a4-737a-48d9-9022-0694fc2e0876 |  | note | ACCEPTANCE CRITERIA: The assessment of the cracked concrete structure shall be undertaken by a technical specialist with a minimum of 5 years practical experience in the diagnostic assessment and investigation of concrete structures.
label | b983dd3d-c4e9-4b57-8ea1-78685f14cc73 |  | note | Cracks to be determined either as active or inactive.
text | b6d01287-d7b4-42ed-9546-5ca89e1044ac |  | textbox | Enter: Teambinder Correspondence Approval number
label | 069739dc-da8e-4c93-a0f6-3eba0bac586e |  | note | OR
label | 8dfdbae1-5288-43f2-b56c-e79c35f420ac |  | note | Attach: Correspondence
label | 096e33ee-8cff-4979-9ecb-2e129bb70e60 |  | note | METHOD: Visual Measure
label | 9128c11d-7630-4a7b-ba27-7097b8222a6a |  | note | FREQUENCY: For each element, prior to Works commencing
label | 3167e338-8b57-4d76-9822-e42864404e0c |  | note | CATEGORY: HP
label | c25d0dc7-4215-48bc-b57d-dfca08507b95 |  | note | RESPONSIBILITY: Nominated Authority
label | c2822dad-0a85-44c4-8da6-64b05497d954 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e9f52530-6a95-48cb-ae60-7ae397c8a886 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Work Procedures
label | c3ebd756-b0ea-43b6-a2e7-eec10796d9c1 |  | note | REFERENCE: 687.01
label | 93087e7c-9968-496f-a7b8-8716948def22 |  | note | 687.09 (a)
label | 3ddbbacd-c0f0-4fc1-a294-9be7b1962cab |  | note | 610.24 (b)
label | 1c314d4f-48a2-48f3-928d-d6b440a2e21d |  | note | ACCEPTANCE CRITERIA: The Contractor shall submit a crack repair procedure/procedures for review to the Nominated Authority.
text | 9ec6cf01-6b3a-40c5-9a96-c1b981f43727 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 5b9e21ee-8390-4ad9-8186-336baab39b97 |  | note | METHOD: Visual Measure
label | f786a9da-9cfc-4bab-8160-6f663ba5d6bd |  | note | FREQUENCY: For each repair methodology, 14 days prior to Works commencing
label | 6ab9a21c-9c66-4e13-99b4-b65282922cc7 |  | note | CATEGORY: HP
label | ab385755-6668-4c91-966b-506bb1d8fd84 |  | note | RESPONSIBILITY: Nominated Authority
label | b3019f89-3976-494d-aa92-2af0bc9fba94 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e2e7b272-e9b5-4329-bf39-3809d99e7df7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 3.1 Flexible Sealant Selection - Active Cracks
label | 28b9709a-b4af-4e1d-b26e-991443f94377 |  | note | REFERENCE: Product TDS
label | 12aafe24-1605-44ff-903e-28a9c8c0da4a |  | note | 687.05 (c)
label | c5ac0a50-b606-48e5-ae9b-4065a1fded23 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | fcb72c9d-efe1-4510-aa0f-6de92b7f62f1 |  | note | i. provide for a minimum expectant movement of ±25%;
label | 4b0abca2-6f4f-493d-85e3-e0316fbb33da |  | note | ii. Whether or not the repair/sealant is subject to traffic (trafficable or non-trafficable)
text | 3143d0b6-3004-4435-a3ad-c37e2e3b5283 |  | textbox | Enter: Teambinder Material Approval number
label | fa266b36-43cb-42d6-a4c2-5d31b3249b41 |  | note | METHOD: Document Review
label | ac8e5003-774e-4651-a3d7-ee874aba4301 |  | note | FREQUENCY: For each product, prior to Works commencing
label | 98708a78-c3ae-454a-ab63-e44dc2a1af7e |  | note | CATEGORY: IP
label | c86e0bc2-3b29-4a7e-9b56-4875fabc92c1 |  | note | RESPONSIBILITY: Nominated Authority
label | ba773a1d-62dc-4ca3-afd3-eb80802eb22f |  | note | VERIFYING DOCUMENTS: This ITP
text | 3fac8438-7694-460a-adea-d0cacd9489c4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Epoxy Mortar or Paste Selection - Inactive Cracks
label | e0749e26-09dc-46a9-9635-08be97620f0a |  | note | REFERENCE: Product TDS
label | 796b0d29-a7d5-4d2e-9f86-1a86f52eb53e |  | note | 687.05 (b)
label | 05e81675-6e75-4a58-b6cf-a001d34d553c |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | eed24813-189f-4c90-bc59-767ce72ad3cc |  | note | i. compressive strength @ 7 days ≥60MPa;
label | 92582809-733a-4ade-9be4-044d0ad237ac |  | note | ii. tensile strength @ 7 days ≥25MPa;
label | 27332ba3-1f49-4f95-b498-91f8545d34dc |  | note | iii. flexural strength @ 7 days ≥30MPa;
label | aef8fd08-7e8e-49d1-9535-8fd4c6f8caf2 |  | note | Note: For the routing and sealing, injection nipple/entry port placement and surface sealing applications only.
text | b3bf7134-41ca-4286-9627-d566ae07902e |  | textbox | Enter: Teambinder Material Approval number
label | 30bd85fb-0e97-413c-8166-4c84af70b3f5 |  | note | METHOD: Document Review
label | c9bc086c-63de-4209-80ad-d7ef189cb81b |  | note | FREQUENCY: For each product, prior to Works commencing
label | 6b32ef7c-d4ba-49f1-9218-09eb3feca7d2 |  | note | CATEGORY: IP
label | 20c18a15-b58c-4a1e-928e-d207e288ac9e |  | note | RESPONSIBILITY: Nominated Authority
label | 9fa8612b-9552-4a23-8f3e-3d079c80f27f |  | note | VERIFYING DOCUMENTS: This ITP
text | c54ad1ee-5183-49e7-b61a-3b90ac5b5fb7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Epoxy or Polyurethane Resin Selection - Inactive Cracks
label | 4fec2f22-80a0-4afe-9d54-e8d0635e7160 |  | note | REFERENCE: Product TDS
label | 11724934-e137-4178-aa99-eca22148d742 |  | note | 687.05 (a)
label | 9ffad2ec-c318-4f20-b8f5-a67ac2e543fa |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 7e38c5e3-abf6-4aa9-89a7-464f166a7e07 |  | note | i. viscosity @ 20°C - 23°C 650cps max.
label | 976b2c08-2305-4285-ad3b-a73076e6a025 |  | note | ii. compressive strength @ 7 days ≥60MPa;
label | e1e2721a-31b1-4fa5-8ed6-d24b0317e62a |  | note | iii. tensile strength @ 7 days ≥25MPa;
label | cf4e647c-7e7d-441d-8841-f3072ccfc0fd |  | note | iv. flexural strength @ 7 days ≥50MPa;
label | 8cfc90f1-2175-47d9-a4d5-663160f4dca3 |  | note | v. adhesive strength at crack edges @ 7 days ≥2.5MPa (or concrete failure)
label | 67b54ddf-b4f4-41c7-bd04-44c3301fd3f1 |  | note | Note: For the resin injection or gravity fed applications only.
text | fc075260-c05a-454e-99fc-24e46cd41271 |  | textbox | Enter: Teambinder Material Approval number
label | ae29eb3c-bc95-408b-ab3a-c9c515e5c62c |  | note | METHOD: Document Review
label | 86a4d6d0-7aa4-41f2-8934-da90e15da6a0 |  | note | FREQUENCY: For each product, prior to Works commencing
label | e46f8461-c7c6-4944-b713-87763ba8708b |  | note | CATEGORY: IP
label | 33cde6a1-172e-44e8-867a-39871f487c9c |  | note | RESPONSIBILITY: Nominated Authority
label | 7ef3e9d4-6699-4636-b7d2-cab2e1458082 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9b056580-c2a4-4951-8380-8b1ccc4b4690 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Silane Selection - Inactive Cracks <0.2mm Width
label | bdae566e-19ad-4c9a-97fd-be88e6a98ce4 |  | note | REFERENCE: Product TDS
label | 982f7222-c1af-4553-893f-41cf7827a44b |  | note | 687.12
label | 5899b627-7713-4770-8b91-cd533b9a8e20 |  | note | 686.05 (h) (i)
label | e6727523-c43b-41f5-b2eb-62b2e7454467 |  | note | 686.05 (c) (iii) (1 - 5)
label | e889f7d4-d355-4210-a95d-bbee70a06839 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | dc5e116f-2237-41ed-b938-c636d6508098 |  | note | i. active ingredient: ≥95% (penetrant)
label | 791d994a-3959-4d40-920e-d069d6e9c46f |  | note | ≥80% (solid silane)
label | f504ad46-5ab2-4293-a674-ad8db95da868 |  | note | ≥80% (silane crème)
label | 6bbbb97d-bed5-4d09-9496-b69436d0ffe4 |  | note | ii. penetration depth: 5mm min. iii. contain a fugitive dye to enable coated areas;
label | a875676a-38f0-4ea8-8ff4-70d900ebbce0 |  | note | iv. be compatible with a film-forming top coat;
label | c4a61b09-58ac-4c87-850f-a09abf757859 |  | note | Note: For the protective coating of inactive cracks ≤0.2mm in pre-stressed elements and exposure classifications B2, C & U only - 0.2mm cracks are acceptable in other precast elements and exposure classifications.
text | c47f6f5f-23bf-4753-b70f-a9446eb1ead8 |  | textbox | Enter: Teambinder Material Approval number
label | 7d9335ca-3140-499e-9c3e-dab531963415 |  | note | METHOD: Document Review
label | 28eeb6d3-3701-4d57-a9e7-fa48b900e94c |  | note | FREQUENCY: For each product, prior to Works commencing
label | aefd62c6-78e2-4cea-837c-0abd40eef148 |  | note | CATEGORY: IP
label | 5a91e273-6fc3-4aa8-9c0a-0acebb8a0b73 |  | note | RESPONSIBILITY: Nominated Authority
label | 240cc9f9-6d33-4673-9767-b3388b79281d |  | note | VERIFYING DOCUMENTS: This ITP
text | 2ff749f5-d93d-4050-adb7-e97f89eff43b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Contractor Competency
label | 382d3db1-5072-43bd-bd9e-b8a695e226e3 |  | note | REFERENCE: 687.04
label | da7e6a49-f4c6-4c9d-964f-6614a79f1e6c |  | note | ACCEPTANCE CRITERIA: Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application.
label | 050739a7-51d0-48b1-b11f-351579704212 |  | note | Documented evidence to be available.
label | 5a8bbd6a-ccaa-496f-b433-6e873bf09c72 |  | note | METHOD: Document Review
label | b7741e71-4eff-49fb-9a02-fc36174c106b |  | note | FREQUENCY: Once, for each personnel, prior to starting Works
label | a2670dec-22fe-41fc-95d2-f19bf2697ce1 |  | note | CATEGORY: IP
label | 15eb57f1-9b3f-4837-a761-5a7c42e79771 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 20104ba3-7358-45e5-9f59-64bc93b00232 |  | note | VERIFYING DOCUMENTS: This ITP
text | 81ca06ff-83ce-468c-9adb-6ec274d39c63 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Injection Equipment
label | 5fe65c9e-0ec2-483e-b73d-6d7e3ccc3365 |  | note | REFERENCE: 687.06 (a)
label | 009a554a-e2df-4d26-bcf6-d537d0a7261d |  | note | 687.09 (c) (iii)
label | 419cf0ab-6070-4897-bab7-27e326cd2114 |  | note | ACCEPTANCE CRITERIA: Injection equipment to be simple, easy to handle guns with pressure regulation or limitations in the operating range and be simple to clean and maintain.
label | 7c2657d0-5ff0-43fa-8fb3-dd88d5438f11 |  | note | Nipples/entry ports to have shut off valves or at least the ability to be capped to prevent leaks or air travelling back into the crack.
label | 0971117e-6cf5-4253-8557-2b5807461a7b |  | note | Note: This ITP does not cover special purpose, multi-component injection pumps.
label | f54337da-490b-402e-944d-9c1e18db4b55 |  | note | METHOD: Visual
label | 99056ac9-3da2-4c9c-a581-1e2ea3333fae |  | note | FREQUENCY: Once, prior to starting the Works
label | 43d768d3-c53f-48bc-b83b-8f61be9abdeb |  | note | CATEGORY: IP
label | ce760e01-3c29-45e6-9a07-dd75f7386cdb |  | note | RESPONSIBILITY: SE/PE/SPE
label | ece85286-4f51-4db0-a717-62b5f009c437 |  | note | VERIFYING DOCUMENTS: This ITP
text | 45dd5ac8-8269-443d-af0b-d2342e3be9f7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Weather Conditions
label | c5b6e35f-7df5-45ba-bd7d-62048d8b90fb |  | note | REFERENCE: 687.05
label | a893b65c-293a-4362-a2a8-595dcec752ad |  | note | 687.09 (c) (i)
label | 62c7f6d8-61cf-4f28-ba9c-cb90259345b0 |  | note | ACCEPTANCE CRITERIA: Repairs are not to be undertaken when the ambient temperature is below 5°C or 5°C on a falling thermometer, or above 35°C.
label | 625e4a54-5fdf-4da6-b3d4-ffa403489ace |  | note | Cooling the materials is allowed should the need arise if temperatures inadvertently rise during the repairs.
label | 9cb67591-4389-4312-89db-f76fe32fa157 |  | note | METHOD: Visual Measure
label | 98f4557e-dd6c-4043-abda-c3c661a92e26 |  | note | FREQUENCY: Prior to each repair
label | d3f2d222-fae9-488f-b79c-1df40a1181bf |  | note | CATEGORY: SP
label | 0b13b5e1-bc75-44f1-9dc8-876c2e94e056 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b54a8dbd-3dea-4326-b3e6-e46c223ffefa |  | note | VERIFYING DOCUMENTS: This ITP
text | d4b894e3-c99d-41fa-82a5-180c450ca1d1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Surface Preparation
label | ed44c84b-b6a1-478f-8214-ede4f11bbb4c |  | note | REFERENCE: 687.08
label | 214f8b5b-1cdd-4dfa-97a6-dc31ae5c1675 |  | note | ACCEPTANCE CRITERIA: Cracks and surfaces located within 50mm each side of the crack to be cleaned of all loose particles, dirt, dust, curing compounds, grease or efflorescence by appropriate means.
label | d65df8fe-861a-4e0c-9f6a-911b5143507e |  | note | Where cracks and surrounding areas have been moistened during the cleaning process, sufficient time or accelerated drying-out needs to occur unless the crack repair materials are water tolerant.
label | b8f5585c-93c9-4b4b-af74-555ef789b2e3 |  | note | METHOD: Visual
label | 8a2449c9-be23-4915-87e2-9fedec7d1f0d |  | note | FREQUENCY: Each crack
label | 6ff8dd9c-b14b-4b38-9330-4bbf03d75f2c |  | note | CATEGORY: IP
label | e7b79811-b82c-4c1e-a491-a1ea72dd38fb |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1565a177-62a5-4bca-98e8-b064d0bcb334 |  | note | VERIFYING DOCUMENTS: This ITP
text | 26c3583e-aa16-43e0-aea1-e67d9054bf12 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Active Crack Repairs - Route & Seal Method
label | 0170a84a-e839-44ae-9c25-6dfab0e3de93 |  | note | REFERENCE: Crack Repair Work Procedure
label | 69021f1f-3591-47f8-aa6c-ec0d5b5e9e2c |  | note | Product TDS
label | f8a0b38a-27ac-438e-82b5-0cb432b36dcc |  | note | 687.10 (b) (ii)
label | b13c3d33-9dcc-4caf-bdd6-87942fcd4dcd |  | note | 687.15 (a - d)
label | 730441a5-83a1-4b40-a8d9-3aebae2075fd |  | note | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
label | 81e19198-ac1f-42e6-ae1d-26d1770574d3 |  | note | i. All materials in date and mixed as per the Product TDS;
label | a648b976-d964-470d-9f8f-86b5e776f97b |  | note | ii. Saw cuts to be at a width to depth ratio of 2:1 and rectangular in section;
label | e55e6486-4632-4fe5-9766-2294e3d4bd75 |  | note | iii Surface dust to be removed;
label | 8f014470-6e44-488a-aacb-43a41d92f007 |  | note | iv. Bond-breaking tape to be placed at the base of the chase/reservoir to limit sealant interface to 2 no. faces;
label | 1e4edf8c-1907-4474-b080-f2a69d786c17 |  | note | v. Where required, masking tape to sides of the adjacent surface to create a neat finish;
label | 98b712d0-c1e8-4f82-8fc8-9013bce01f23 |  | note | vi. Sealant gunned or tooled into the saw cut to completely fill the void;
label | 8d6bf374-8124-4230-8e74-5736835225af |  | note | vii. Product shaped with a suitable tool to recommended profile;
label | 4c686b5a-64c3-4c2c-8ba6-bf3879ad41f3 |  | note | iix. Repair to be protected from damage or adverse weather while curing;
label | e6602f9e-d56c-4696-a5ff-7401f55b118b |  | note | METHOD: Visual
label | 83e0f314-249c-45e5-860d-586ce3d4f654 |  | note | FREQUENCY: Each active crack
label | 88cbb4fd-ac8c-412a-af84-d876697919d2 |  | note | CATEGORY: WP
label | 04bb8da8-5e46-478c-a6fc-330f67cbee3f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 98fd27b3-790c-4d86-b981-08b19e56588b |  | note | VERIFYING DOCUMENTS: This ITP
text | 87921142-da16-4ebe-9c22-831aa21d5706 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inactive Crack Repairs - Route & Seal Method
label | 0245e576-1078-4a4e-99cf-b3943fbaa458 |  | note | REFERENCE: Crack Repair Work Procedure
label | 70f950c7-d8e3-496e-a90b-72a55b76c7f8 |  | note | Product TDS
label | 3c2ef426-edc6-491c-b696-83f55bd2e409 |  | note | 687.10 (b) (i)
label | 610f6a3b-346c-461a-b409-9fcd267507e9 |  | note | 687.15 (a - d)
label | 0efb70d2-2652-497b-9952-d194a18726e3 |  | note | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
label | b3df6f55-874c-4fd6-8bf8-f21a9cb15c31 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 1e1121f3-8262-436d-b42e-1c265f7a4051 |  | note | ii. Saw cuts to be at a minimum width and depth of 10mm and V-shaped in section;
label | 3d461820-1a91-4508-9369-ea3a056eb467 |  | note | iii. Surface dust to be removed;
label | 0f209285-0da6-45d5-b5ce-86e218ccc0d6 |  | note | iv. Epoxy mortar / paste placed into the saw cut to completely fill the void;
label | 3f8a3909-3247-41b0-87fe-c6220af4db2d |  | note | v. Product finished flush with the surrounding surface;
label | 5f6aea55-d8ac-4770-a883-5cdc80ffb9db |  | note | vi. Repair to be protected from damage or adverse weather while curing;
label | e37206d1-4429-4460-b7f1-54970c68e603 |  | note | METHOD: Visual
label | acab8993-1b74-48df-aced-4a4ddef2a68b |  | note | CATEGORY: IP
label | 89e3730d-75bf-4c48-a61c-78cd89b2b3a4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0ec58da1-8b74-4992-8a79-999d41b35886 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3e3d6199-0238-450f-a12c-8d691323c088 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Inactive Crack Repairs - Gravity Fed Method
label | 1e673559-921d-4840-bcf1-ee9bbe04e77c |  | note | REFERENCE: Crack Repair Work Procedure
label | c8eae499-5a6f-4957-8272-3896632d6f94 |  | note | Product TDS
label | ab4ddc9c-0246-4d9f-924e-f1ad2a83c9a3 |  | note | 687.11 (b) (i - ii)
label | 153d3b0b-1bdf-42c9-82d6-98415261f5ab |  | note | 687.15 (a - d)
label | 84b018e6-069b-4b19-9212-8ed72def21d8 |  | note | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
label | 92707d11-9470-436c-ae9d-d763095b98e8 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 9a9a7f8d-0513-4394-b94b-b67d78f85b93 |  | note | ii. Where required, a water-tight reservoir, to be created with silicone or polyurethane sealant;
label | a831425e-46c8-4532-93b7-f2d143aa64a0 |  | note | iii. Epoxy resin to be poured onto the crack and either sufficient amount contained in the reservoir (if used) or worked back and forth by suitable means (such as a broom) until no more material can be absorbed;
label | 9a9a4bdf-37d4-48e7-8a40-0d740eff6049 |  | note | iv. Excess material and reservoir can be removed as the epoxy resin gels;
label | 8ac22796-6d1d-44cd-bc71-fa1efb9e6806 |  | note | v. Repair to be protected from damage or adverse weather while curing;
label | 2c053c15-9301-480c-b403-7a2022148d67 |  | note | METHOD: Visual
label | 3333b7d8-06ea-4fb3-9ecf-426ae6ba68c0 |  | note | CATEGORY: IP
label | 9020f4b5-77c8-4647-bb47-0483214ee08d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 44a3a7a2-ef44-48a9-ba40-1b40fd29d316 |  | note | VERIFYING DOCUMENTS: This ITP
text | 289c6f63-ccd5-4120-95e6-7591fcf8807b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Inactive Crack Repairs - Injection Method
label | 2e4cd91c-dd1d-4351-8e6f-959f569d8010 |  | note | REFERENCE: Crack Repair Work Procedure
label | 929ef712-cbcd-4b6f-9755-9a2f209726dc |  | note | Product TDS
label | d6e19d87-812f-42ca-8a3f-d64e25fc6091 |  | note | 687.09
label | 08cd1f5f-834c-4b5b-898f-5ebad22d9af8 |  | note | 687.14 (a)
label | d454200d-a8a6-4f67-aba3-bfc7bbe46dcf |  | note | 687.15 (a - d)
label | bba4b23a-942f-4417-87e9-44533c9c0eda |  | note | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
label | f58e036e-3cba-49e7-a5ad-eb80fcf99ae5 |  | note | i. All materials in date and mixed as per the Product TDS;
label | 80538e64-92f8-49c0-bea0-f0d0dab24316 |  | note | ii. Each nipple/entry port coated in epoxy mortar or paste to create a water-tight seal to the entire perimeter;
label | 6b4ff6c5-2937-4789-8e12-0671a842c8dc |  | note | iii. Nipple/entry port placement central over the cracks at 200mm spacings maximum (where cracks are through the full section, nipple/entry port placement shall stagger);
label | 9c3b42cc-161b-40c2-aa58-d738cbeddafa |  | note | iv. Epoxy mortar or paste applied to the surface of the crack in between nipples/entry ports and the full height of the crack if within tolerance to eliminate resin leakage);
label | ab8446b8-798d-4b02-957d-0c8065bfe079 |  | note | v. Once the epoxy mortar or paste has fully set, connect the injection gun to the lowest nipple/entry port (for vertical cracks) or at one end of the crack (for horizontal cracks);
label | 585c7184-d163-4d3e-9c47-9950e59e16cf |  | note | vi. Initiate the injection, applying pressure until resin can be witnessed entering the next nipple/entry port;
label | 5d05ebe7-6c72-44d6-bf12-d8f939c91bed |  | note | vii. Stop pressure and close the valve of the engaged nipple/entry port and connect to the nipple/entry port where the resin appeared, working either upwards (for vertical cracks) or along the crack (for horizontal cracks) until all nipples/entry ports have been filled;
label | c057186c-80c0-4a06-8d26-89321e7b5797 |  | note | iix. Repair to be protected from damage or adverse weather while curing;
label | f47ea97c-19a1-4062-b6da-4ff0e0f9d89e |  | note | METHOD: Visual
label | 71c65faa-7df0-4a8d-816d-508adedd14a5 |  | note | CATEGORY: IP
label | cf8713e3-2db6-4463-9773-16c609ef5032 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 48cbd537-56d3-41e1-ab75-1f1058838e51 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3dc05aec-b804-44a0-902a-8dc5735da97c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Inactive Cracks <0.2mm Width Repairs - Penetrant Coating Method
label | f1d8b37c-3f07-43f5-a754-3e64aca07fd5 |  | note | REFERENCE: Crack Repair Work Procedure
label | b60bd3a5-7eed-4397-ace8-ba75bd5f5e7d |  | note | Product TDS
label | ed90a81d-7641-466a-8b29-528bb86cbc57 |  | note | 686.07 (a) (i)
label | 88423983-3c39-4383-87c9-fb8654eae26a |  | note | ACCEPTANCE CRITERIA: Approved procedure to be followed, steps to witness:
label | 1695dbfe-ce0d-404b-8d45-8a1a8bccea36 |  | note | i. All materials in date and mixed as per the Product TDS;
label | a5a444bc-852e-402f-b335-7e426c40914c |  | note | ii. Silane to be applied with an airless sprayer (for penetrant) or brush (for Solid Silane or Silane Crème) , working from low to high areas and approximately 150mm beyond the extent of the crack;
label | 2a1d7079-a653-4882-bc8c-a29f366a31b9 |  | note | iii. Application rates to be as per the TDS for each type of product ensuring wet appearance;
label | 3b7f40e7-e65c-45b5-9267-c0f25ed6659b |  | note | iv. Re-coating if required;
label | d3481639-dad6-45f7-a1bf-e3571da98765 |  | note | v. Repair to be protected from damage or adverse weather while curing
label | 668fe425-cdf1-4139-9ea2-461a2fa21efa |  | note | METHOD: Visual
label | 2ef21ef5-af57-48aa-9393-f8f67036b48a |  | note | CATEGORY: IP
label | 90021838-ff02-40f5-98a4-e735956797d1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2df65762-93bc-40ec-b5bd-99de538c4599 |  | note | VERIFYING DOCUMENTS: This ITP
text | 765c5953-feaf-465e-b341-afd1dec7ea5b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Curing & Finishing
label | e1b6c1e2-e5ea-478d-a9da-ded8761b87df |  | note | REFERENCE: Crack Repair Work Procedure
label | efa8ac9c-16df-406a-b477-7c2623c48f78 |  | note | Product TDS
label | 20c7007f-e8ae-4e5d-9921-9fe6464730b5 |  | note | 687.15 (a - c)
label | b588dfe6-2f19-4573-8797-6755ab563ab9 |  | note | ACCEPTANCE CRITERIA: After the repair materials have cured in accordance with the manufacturer's recommendations, any surface seal, nipples/entry ports and repair materials can be removed by suitable means.
label | f138eb0b-11f0-4468-ae6b-7d9c3021e8cc |  | note | The surface shall be ground smooth, leaving no traces (indentations or protrusions) of a repair and if the repair location remains exposed, a fairing coat can be applied where not being coated with a pigmented coating system.
label | d27d6db8-2cd1-4b55-89ec-4e788d4fe307 |  | note | METHOD: Visual
label | 5b4cc1a2-74ef-4d88-acae-79e739f2b93f |  | note | CATEGORY: IP
label | 7d840a86-c33a-47d2-8f79-15484629f371 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f285e3db-59b0-4df6-a02e-9d33b3eb4506 |  | note | VERIFYING DOCUMENTS: This ITP
text | 72308daf-6f10-43e3-a3bd-9ba8941faf05 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Repair Verification
label | d3ddb97e-b69c-45de-9644-5de541e1afe8 |  | note | REFERENCE: 687.16
label | 0f89ac12-606b-4169-9860-5afedfe10839 |  | note | ACCEPTANCE CRITERIA: After 7 days minimum, 75mmØ core samples shall be taken to verify cracks are fully sealed.
label | 77539d8e-ef0e-408e-a345-23c0e2ab41d9 |  | note | Cores to be located in conjunction with a covermeter to avoid reinforcement and approved by the Nominated Authority.
label | 97c3b197-fd83-46ca-9f7f-b1a4e7874f5c |  | note | 2 no. cores for the first 25m of crack and an additional 1 no. core sample for each 50m of crack or part thereof.
label | 37a126ac-7dcb-4c14-a934-12eb6bcf36ea |  | note | Core holes to be filled as per the cementitious repair ITP.
label | 2cd11e63-48e0-4e4e-8fe7-fb9952130a82 |  | note | Attach: Photographs of Core Samples
label | 22892494-3036-4bfa-a76d-b1e1cb08b145 |  | note | Complete: Structural Concrete Cementitious Repair ITP
label | 480d7c03-8810-41dd-a6d9-0d43273d6a94 |  | note | METHOD: Visual
label | 9017f0df-5da7-43cd-89f5-6a7c866c8313 |  | note | CATEGORY: WP
label | e740700d-2c41-47cf-ba47-2611e0e98ec8 |  | note | RESPONSIBILITY: Nominated Authority
label | 82a76cf7-085d-4dbd-83a1-4186532b034f |  | note | VERIFYING DOCUMENTS: This ITP
text | b2db52b6-12b8-4966-aa26-5f30c322e8f7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 1a12e3e7-2d51-40ce-9bf1-0677310f23a3 |  | note | REFERENCE: MRPA Quality Management Plan
label | 82254b86-9c8e-439a-92ca-546a9958794e |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 1d4e3e54-0edd-4970-bab0-e00b03c00c34 |  | note | METHOD: Document Review
label | 7856a70e-c44e-48eb-8034-58d187681470 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 328b3252-103d-4416-b3f4-aa5d8c3b8d33 |  | note | CATEGORY: HP*
label | 793cbc1a-7f06-4141-b511-2bb9b772dee4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | ac774976-9cd5-42e6-8514-47e7f718c518 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4b98ac98-27cb-49bb-a857-be08fb57d974 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | e43cea26-af46-4605-b641-6c0c9bc342b4 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b5d1211f-c62c-4765-996a-269f68086182 |  | textbox | Name:
text | f2b08544-0693-4c59-9fc7-527a272d8864 |  | textbox | Position:
text | 10dac392-776a-4730-ad90-6170aa37c2e2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Waterproofing Tanking Slab Rev 0 | itp |  |  |  | Yes | ITP-STR-Waterproofing Tanking Slab Rev 0 | aae23899-be8c-4b50-bf7c-c617d391573b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 9c2da201-6e96-44f3-91b0-89f8f412574b |  | note | Document Title: ITP-STR-Waterproofing Tanking Slab
label | d8da6649-15ee-4147-8e6c-c9b8498ea9f7 |  | note | ITP Description: Waterproofing Tanking Slab
label | 5da3605e-54b5-47ce-be83-5ff7b399072f |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | e218b5e8-f00d-47d1-9979-6e6ec905c813 |  | note | Revision Number: 0
label | 39061894-9e10-4138-af06-92c22ffc4819 |  | note | Revision Date: 21/12/2021
label | 9164d1f0-acc4-436b-aa9d-0d787e0e73b2 |  | note | ITP created by: Nathan Tran
label | 7e908977-867f-4071-9178-afcba8c7cbbe |  | note | ITP approved for use by: Aldrin Guinchoma
label | fbf00d84-c26b-4da0-bd09-de7d1e388ab8 |  | note | 1.1 VR 691 Nov 2018
label | ef32b5f5-d9a8-4768-a704-f5f049197d16 |  | note | 1.2 IFC Drawings MRP-DPK-016-00-CSW-0017-0
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Materials - Waterproofing systems shall be used in accordance with the manufacturer’s recommendations and materials safety data sheets.
label | fb45ed7b-e32f-4dbf-979c-10af695255d9 |  | note | REFERENCE: 691.04
label | b60275fe-0101-42ad-b5ef-81838d335c08 |  | note | 691.08
label | b94a659c-e834-45cf-8c7d-20057edb5063 |  | note | ACCEPTANCE CRITERIA: Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent.
label | a433ba9a-69a1-4ef7-841c-765a79614b8c |  | note | METHOD: Document Review
label | ac5bcd17-6f36-409b-8974-aa0844f0c3a7 |  | note | FREQUENCY: Once prior of commencement of work
label | 3a9f2332-9bd3-4955-82f6-eff259ee3373 |  | note | CATEGORY: HP*
label | 483f8d06-ea1a-4d83-9644-9d2c077907b8 |  | note | RESPONSIBILITY: SE/PE Nominated Authority
label | ea033f7a-5533-48a0-b599-f05d63827bbb |  | note | VERIFYING DOCUMENTS: Material and Surface Procedures ConQA Hold Point Release
text | 1fbe275d-ae9a-4344-bc80-0aab5d183ec1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Work Method Statement and Inspection Test Plans
label | 2589fb2b-1606-4f9b-9ffc-a94e81b4b26f |  | note | REFERENCE: 691.25
label | fee7e926-0200-4d28-91f9-eb126869f76d |  | note | ACCEPTANCE CRITERIA: The Contractor shall not proceed with the trial system application or the permanent waterproofing membrane system installation works until the WMS and ITPs have been reviewed and approved by the Superintendent.
label | 4e0e3bd5-fa63-4195-a998-755b9d918882 |  | note | METHOD: Document Review
label | 30ef74e5-bb88-4e07-83a4-0d12c08b6e71 |  | note | FREQUENCY: Once prior of commencement of work
label | 0bf8335d-2f2e-4638-9453-f4d2b3c08dd4 |  | note | CATEGORY: HP*
label | a2bba018-15ab-4253-8f67-d995f2a717f5 |  | note | RESPONSIBILITY: SE/PE Nominated Authority
label | ca85c172-85de-48a8-96e9-12f4bf8fe79b |  | note | VERIFYING DOCUMENTS: WMS Subcontractor ITP
text | 21ae38e4-479c-41b9-b40f-7d848e8ed667 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Waterproofing Membrane Systems - Waterproofing systems shall be procured from manufacturers/suppliers who have implemented a quality management system to AS/NZS ISO 9001, with third-party certification accredited or accepted by JAS ANZ or equivalent.
label | 9961c165-89ae-490a-8bfd-8216f26c0e4d |  | note | REFERENCE: VR 691.05 (a)
label | a3adf6ed-e9d8-44ee-919f-74a5be17f820 |  | note | ACCEPTANCE CRITERIA: The Contractor shall supply the Superintendent with a certificate from the manufacturer in the form of a guarantee confirming that the waterproofing system and materials comply with the requirements of this section, including a guaranteed in-service performance of not less than ten (10) years from the date of installation.
label | b41b8919-1b49-495c-abbe-be7b8006f216 |  | note | METHOD: Document Review
label | cebb2deb-afef-4b29-962e-e0ad0a8dd967 |  | note | FREQUENCY: Once per Lot
label | 1f814593-5df2-454c-a321-bf874d74ca56 |  | note | CATEGORY: WP
label | a14fd7f8-a9b7-42c2-ae70-3dd6e82bab54 |  | note | RESPONSIBILITY: SE/PE
label | 880b8277-b409-4b64-8dea-60f67e3e2d2a |  | note | VERIFYING DOCUMENTS: Manufacturer Certificate
text | 90e95c13-530e-4c73-a717-81e0a973255d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Waterproofing Membrane Performance requirements
label | 756c7e51-53ae-45be-a8c6-f7e27eebe8f8 |  | note | REFERENCE: VR 691.07
label | 99ce498c-da80-4996-969e-9ce83ab3c4cb |  | note | Table 691.07
label | 288bdb50-7340-4973-b1e0-a236df3b72fd |  | note | ACCEPTANCE CRITERIA: The Contractor shall submit a Certificate of Conformity, including all relevant test results shown in Table 691.071 and Table 691.072, verifying conformity of the supplied materials for every lot/batch delivered. A Certificate of Conformity may be in the form of a British Board of agreement (BBA) current Roads and Bridges agreement Certificate.
label | 104c809d-5b71-4e8f-9374-d6ed40050ff0 |  | note | METHOD: Document Review
label | b0de8f1b-9ecd-4ab3-9966-f27c02b769cf |  | note | FREQUENCY: Once per Lot
label | 72ab7a5a-366f-4823-82e5-c9de4bef8985 |  | note | CATEGORY: WP
label | 7cb2c239-caa4-4d5e-8558-f6b4456e4c3f |  | note | RESPONSIBILITY: SE/PE
label | 977b8554-7d0b-49c8-a8d7-627c26c31188 |  | note | VERIFYING DOCUMENTS: Certificate of Conformity
text | b4bb1d7b-8486-45e3-bedc-37026420ea0c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Inspection of delivered waterproofing materials on site
label | f19cfc06-2405-4543-b00b-8f421a3bcb56 |  | note | REFERENCE: IFC Drawings
label | 06afb86c-c01d-47ea-9ef8-62fbf44c98d0 |  | note | ACCEPTANCE CRITERIA: Materials not damaged during transport or handling and meets specifications
label | eb9cae8e-0946-48c3-959f-1d17b619bb33 |  | note | METHOD: Visual Inspection
label | 8e48ea2a-a036-4d08-b0fc-c7ba43052473 |  | note | FREQUENCY: Once, prior to commencement of works per delivery to site
label | 9617766f-eedf-47b9-ac33-7598762aea1c |  | note | CATEGORY: IP
label | 2f904e8d-a59d-40a2-a23c-3c6fc8bd5125 |  | note | RESPONSIBILITY: SE/PE
label | 9811a354-c82d-4053-884e-ebfd028bff15 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8598ba09-08eb-4b1d-8351-b2b6b4c573e1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 IFC Drawings
label | ffc236e3-284d-4f39-a941-ad02dc951d1e |  | note | REFERENCE: MRPA Quality Management Plan
label | 7ae36f15-3b0e-4848-bfe8-9c343bceabbe |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC Drawing are current as per the drawing register (on Teambinder)
label | f088697d-c56f-4146-b286-69df6f082dc9 |  | note | METHOD: Document Review
label | cd456d93-dad9-4205-bff6-bc931ccb72a3 |  | note | FREQUENCY: Prior to starting work
label | e72e15eb-b8de-44b6-b726-3c6fe0e6cf0d |  | note | CATEGORY: HP*
label | 25d529fa-6422-448b-98e2-66419b50616c |  | note | RESPONSIBILITY: All
label | 4e80349b-cc8d-4d93-8a74-82f59a5c72eb |  | note | VERIFYING DOCUMENTS: This ITP
text | 34a4ee1c-220a-49f5-ad23-593d811eb6bc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Surface Preparation - Surface preparation shall be in accordance with the manufacturers' recommendations for the waterproofing membrane system to be applied and as specified in 691.08.
label | cbf34d50-2f83-4627-8d04-8560c339d079 |  | note | REFERENCE: VR 691.08 (b)
label | 779c262e-dba0-4152-a720-e8b5ab5b9438 |  | note | ACCEPTANCE CRITERIA: Concrete Surface Preparation
label | bbf2bee6-5147-4739-95a6-e0375e696392 |  | note | Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles. Cement laitance, oil, grease, and any remnants of curing compounds and previous asphalt layers shall be removed from concrete surfaces by using grit blasting or bush hammer, scabbler, ultra high pressure potable water jetting to NACE WJ-2/SSPC-SP - WJ-2, or other approved means to provide a strong, hard surface. Areas of persistent contamination shall be removed from the surface by the use of appropriate solvents or detergents followed by washing with potable water in accordance with AS 1627.1.
label | 1d11baef-29bb-42e4-9c51-6c209bd32409 |  | note | METHOD: Inspection
label | b5783eee-7e17-41e1-8592-defc06694c53 |  | note | FREQUENCY: Once Per Lot
label | 927d1ade-0694-4688-842e-f88c8b58d376 |  | note | CATEGORY: WP
label | 9fd0e45e-597a-4afe-9011-921261e44d6a |  | note | RESPONSIBILITY: SE/PE
label | 908e2edd-7431-44ef-a059-21b36a218fcd |  | note | VERIFYING DOCUMENTS: This ITP
text | 9a82ea74-90ce-422d-a552-6b94decf9a0c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Concrete Patch Repairs
label | 00fa1b53-38e2-46ec-b5c3-5b8c3823eb74 |  | note | REFERENCE: VR 691.08 (b)
label | 622eb3e4-acb4-4c04-9949-b50021bddcf7 |  | note | VR 691.21
label | d2a9a2f4-e754-4642-a0f5-a03f1afa09e8 |  | note | VR 691.22
label | 28c12822-74b7-42e5-8aa6-f1438ebb5e72 |  | note | VR 689
label | c2f330fd-4e3d-400c-b5e6-be849fdc6a46 |  | note | ACCEPTANCE CRITERIA: If the surface of the concrete is weak, honeycombed or characterised by loose surface layers more material shall be removed, and repaired in accordance with the requirements Section 689. Shrinkage cracks of width less than 0.2 mm shall be filled with a suitable fairing coat cementitious repair material in accordance with the requirements of Section 689. Such repairs shall be sufficient to result in a strong, sound substrate suitable for the intended waterproofing membrane system. Projecting fins, rough spots and sudden steps shall be removed by light abrasion with an angle grinder to provide a surface which is suitable for the waterproofing membrane
label | 33c0b542-816b-44b6-8e85-c0801f106714 |  | note | METHOD: Inspection
label | e4fa1413-4cf6-4ec1-b9cc-22b3d1c9fff4 |  | note | FREQUENCY: Once per Lot
label | dc21cc19-e9ff-478a-9d5d-68d66845ef44 |  | note | CATEGORY: WP
label | a292e82d-6cc8-44e0-a97d-7a7518ac8a85 |  | note | RESPONSIBILITY: SE/PE
label | fedb1959-6f1e-4d4f-9f32-d3c8a3a74cf9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9106388a-72ff-465a-8573-22ec886872b1 |  | textbox | Date Completed:
label | f12a3e76-fec9-46b2-b86f-2a0d64108534 |  | note | REFERENCE: VR 691.14
label | e5009e64-02ca-4382-a2eb-1d4bdbc90f33 |  | note | ACCEPTANCE CRITERIA: Waterproofing systems shall not be applied under any of the following conditions:
label | bc1e97fd-d040-4984-8b1f-9d63688e9e6d |  | note | a) - windy conditions where over spray and/or spatter may be generated
label | 55ca14c0-f289-474b-a2b1-4da04078eebf |  | note | b) - when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane
label | b048f77f-6989-48c3-900d-5be947d4a4fe |  | note | c) - when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer
label | c3b07bde-a592-4ba3-90de-0cfa9d734789 |  | note | d) - when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period
label | 2bca2c0d-bc6a-4988-a244-9c1a86f00e1b |  | note | e) - when rain spatter or run-off, including leakage through deck joints, contaminating the surface and adversely affecting the adhesion to the substrate, may occur
label | 422cb263-adf9-4917-a592-924c0d9e1bf1 |  | note | f) - when the substrate surface is wet or damp, unless the waterproofing system is specifically required to be applied on a damp concrete surface in accordance with the requirements of clause 691.05
label | b6518b49-33c8-4a94-8476-6b3b0dd9ce5e |  | note | g) - the surface temperature of the substrate is less than 3°C above the dew point calculated in accordance with AS/NZS 2312 (Fig. 8.1) or exceeds 40°C.
label | ba654191-479e-49c4-ae34-41654611e329 |  | note | METHOD: Inspection
label | e8fdeba6-85f2-4040-8c89-7aac75c65814 |  | note | FREQUENCY: Once per Lot
label | 57d3ac4d-d12b-4be8-a72b-1474bd765d2c |  | note | CATEGORY: WP
label | 25cf30c2-5d9e-481c-9881-cd26587176ec |  | note | RESPONSIBILITY: SE/PE
label | d19b6203-6fd2-40ea-b44d-90444dffd4f2 |  | note | VERIFYING DOCUMENTS: This ITP
text | ab9409a1-cced-47c5-9b3b-0ecbd547bce4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Material Handling and Storage
label | 18618fb8-9eea-4d3a-9d15-a4e288e46fee |  | note | REFERENCE: VR 691.15
label | d51e7eac-c96f-4d87-8e4e-125a5d7d874f |  | note | ACCEPTANCE CRITERIA: All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers.
label | 4c5aff60-5038-489e-b665-aa74d39ae2be |  | note | The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming:
label | 650bd221-aa40-4b21-a8d8-15a51e096690 |  | note | (a) - manufacturer’s name and address
label | 09c9e534-672c-4f8d-8a07-0077bfacada5 |  | note | (b) - product reference
label | 77a1892f-4201-4376-a8bb-b2b63119f809 |  | note | (c) - batch number of identification
label | 67ab67f6-f936-4f41-b0f4-2e79fb8e54d3 |  | note | (d) - quantity manufactured in the batch
label | 4f598166-e163-439d-b97a-4ba16db24b2b |  | note | (e) - date of manufacture.
label | 5ac7ab09-15e8-480e-a1e5-18d03ff66ffe |  | note | The Contractor shall maintain records showing which elements were treated with each waterproofing membrane batch. These records shall be handed over to the Superintendent before the Date of Practical Completion.
label | 3061f5f2-92f1-4a1b-90c0-387fa87a4490 |  | note | Materials stored beyond the manufacturers recommended shelf-life shall not be used.
label | b4f5f327-b349-41a7-89f5-66a1a4c8893c |  | note | All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients.
label | d8abf1da-1930-4139-bae4-283ba1f7f477 |  | note | METHOD: Inspection
label | 8eb67f97-ffe7-434f-be6f-c8c2cf824dd1 |  | note | FREQUENCY: Once Per Lot
label | 8ca8160f-c32c-4d8b-85b9-19f34b89f919 |  | note | CATEGORY: WP
label | 5698ab00-92e0-4e7b-9caf-2dd1d5902da7 |  | note | RESPONSIBILITY: SE/PE
label | 82e524eb-bfb0-4274-9e2f-538e70e05d64 |  | note | VERIFYING DOCUMENTS: This ITP
text | ac3fbe35-84c0-4f9a-923c-e9a261c6e378 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.1 Waterproofing Membrane Application (Tanking Slab, Retaining Walls and Pits)
label | 4c5c9762-738e-4dda-8aa7-205443f62076 |  | note | REFERENCE: VR 691.09
label | 586515c0-c26e-4d7a-bfcf-8a83d2e18616 |  | note | VR 691.17
label | 367b535b-98a4-4438-b896-a684de43a53b |  | note | VR 691.14
label | 29a8c314-c7b0-4b23-ad3f-1df97d3d50a4 |  | note | VR 691.20
label | 7b5b6af9-1fee-4081-9dc7-dc04d0d041a8 |  | note | IFC Drawings
label | 1cfb91e3-f6bf-4b04-a9ad-e1caca414ca5 |  | note | ACCEPTANCE CRITERIA: All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application. Sufficient drying time shall be allowed after wet preparation methods to satisfy the requirements of clause 691.17.
label | 5dabf45b-bc47-49ef-9566-79d6d75fade2 |  | note | In addition, the membrane shall not be applied over any previously applied layer/coat which contains application defects or any damage until such defects have been repaired in accordance with clause 691.20.
label | e7747288-bae4-428a-a5fa-b6eb4feaa10c |  | note | Air shall not be allowed to be trapped at the concrete/primer/membrane interfaces.
label | 3f52ae76-003a-4c6b-bd57-f37fa86d9a00 |  | note | The waterproofing membrane shall be applied with minimum side and end overlaps of 100mm and 150mm respectively.
label | 8ffb11f5-7a07-44aa-9dc0-4b47d9ddeaac |  | note | FOR PRECAST PITS:
label | 234d1ec8-f3b8-4381-8d64-9419f160a761 |  | note | Waterproof Membrane 800mm wide to be placed around pit opening bonded to the precast Pit and waterproofing slab with leakmaster gun grade.
label | c732864c-2f8e-4ccb-8acb-281e2d39f999 |  | note | METHOD: Inspection
label | 3b983816-337b-4428-b0db-c7f55da57d29 |  | note | FREQUENCY: Once Per Lot
label | ed23ba40-6708-4d63-9c7c-db24c21a88bc |  | note | CATEGORY: WP
label | ae3b8d9d-5fe5-457f-8c4e-3e0de1fce1a2 |  | note | RESPONSIBILITY: SE/PE
label | b52417d6-caef-4925-832a-47d9a5e7b285 |  | note | VERIFYING DOCUMENTS: This ITP
text | 481247a6-8fc9-4626-9717-ae1aa8129a0e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Welding and testing of double seam weld joints
label | 8e7374ea-5060-498c-bd19-973f7ff5032e |  | note | REFERENCE: Work Method Statement
label | d9d71c24-c056-4a97-b854-36c2440d2c5d |  | note | ACCEPTANCE CRITERIA: The test pressure will be not less than 2 bar
label | d651d21a-7667-4adb-b403-e0f7dbd45e5b |  | note | Reduction of pressure after 10 minutes will not exceed 20%.
label | 3ff63a9a-7fbe-4a9a-bf48-7e67ef45d1d8 |  | note | METHOD: Inspection
label | bfca72bc-864a-44df-a6be-655aaefa479e |  | note | FREQUENCY: Every Seam
label | 4f9be81d-76be-4395-88aa-f918bf3ceef4 |  | note | CATEGORY: WP
label | c8327b9d-dfd6-4d2c-9c8e-e9f7ca4d738a |  | note | RESPONSIBILITY: SE/PE
label | f9f688a1-77f6-40c7-bd39-0dc3cda4e58e |  | note | VERIFYING DOCUMENTS: This ITP
text | d22a0d48-d6c2-4579-b22f-a5510a91fed6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Hand welding of membrane
label | 5f867bed-1b5e-4ad6-bc16-9da88a71da93 |  | note | REFERENCE: Work Method Statement
label | 9c76b4f6-c14d-4d9f-9302-5be656f2cd2e |  | note | ACCEPTANCE CRITERIA: No gaps in weld
label | 879d891f-0a22-444a-9ec5-d3cba00bc53b |  | note | METHOD: Inspection
label | e5dd1607-432a-4a38-8d21-5849b25040a1 |  | note | FREQUENCY: Every Seam
label | f3183a80-d4ba-4f4b-a91b-0616ae895a3e |  | note | CATEGORY: WP
label | cb4e9f6d-0843-443e-8ec5-5fd83be50f30 |  | note | RESPONSIBILITY: SE/PE
label | 51844dd4-af18-4d6f-87d7-9641bccc77f6 |  | note | VERIFYING DOCUMENTS: This ITP
text | abe9a14f-92ec-423d-831b-4d28306ad18b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Installation of waterstops, superstop ,rearguard, hydrotite (Walls, Construction Joints, Contraction Joints and Pits)
label | f60f37ff-ed69-4b90-9c05-c05e09930c70 |  | note | REFERENCE: Work Method Statement
label | 38c4276e-ef38-4fab-8ed9-1719210b5539 |  | note | IFC Drawings
label | 094c206e-52b9-47ba-acc6-73882b58ebe0 |  | note | ACCEPTANCE CRITERIA: Install waterstop infront of the precast wall panel as per IFC Drawings
label | 064e7709-2229-4013-9e3b-5f05d1035400 |  | note | At Construction Joints:
label | 257670a5-293f-4697-9bca-fb9fa5cfa299 |  | note | Installation of Waterstop and Superstop at construction joints as per IFC Drawings Details
label | 6c24d65a-2f5a-43c1-8ac0-4e36a856d4e3 |  | note | At Contraction Joints:
label | 0a406617-07e0-4595-9f50-ebfcbad95915 |  | note | Rear Guard and Waterstop to be installed as per IFC Drawings Details
label | 6e710154-705a-4161-ae3d-17756f94f440 |  | note | For Precast Pits:
label | 1069ea61-9545-4c19-a5a9-28979f971300 |  | note | Hydrotite has been placed around pit cover with a minimum 50mm cover as per IFC Drawings
label | d671472b-3c13-4124-8ebe-b556f411804b |  | note | METHOD: Inspection
label | 92c3b9ef-208a-4453-bba0-f0cc421924b2 |  | note | FREQUENCY: Each Joint
label | 2c192883-2d85-426f-a37d-04db4e2110c2 |  | note | CATEGORY: WP
label | e7990a6a-78bf-4a72-baef-64da5b804dbe |  | note | RESPONSIBILITY: SE/PE
label | 1c4ae8e2-18f9-42a5-a8f3-8d4b6c424ac3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 55f4d298-97c9-4196-b7d6-5096d66cf814 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Installation of Termination Detail
label | dd8f4dc4-96f4-4b7e-864a-71b876c34e66 |  | note | REFERENCE: Work Method Statement
label | e7db41d8-69f1-40be-8eab-e164e096371e |  | note | IFC Drawings
label | 709c1ba3-b7b2-48e8-9418-d97dc685e31b |  | note | ACCEPTANCE CRITERIA: Install of Termination Details on backface of the precast panel:
label | bd529726-d6f8-41fc-b71d-d19eb895f770 |  | note | Termination strip,
label | 38fd4f50-165f-49ca-ab95-199821caa0aa |  | note | PVC Tunnel Liner
label | 27153b74-64f8-4b8b-89b4-39101ceb6607 |  | note | BluSeal AD50 Sealant
label | b6ab41e7-aa1a-40a5-a3c1-53ff2aec7afd |  | note | Installed as per IFC Drawings
label | 80ef333e-f5f7-431b-aae6-410c5ce723c0 |  | note | METHOD: Inspection
label | b87b0cb7-4789-4b07-a1cc-a93295721512 |  | note | FREQUENCY: Each Joint
label | 59bab0d7-1e92-436b-ba8d-a11051685c9b |  | note | CATEGORY: WP
label | db354c55-c0be-45c5-94c7-d81a6605e6b2 |  | note | RESPONSIBILITY: SE/PE
label | 438e4d62-3468-42ea-ba1a-11f4c8c40382 |  | note | VERIFYING DOCUMENTS: This ITP
text | 52044887-188c-4068-a6ed-be5b26c2802f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Final Inspection of installed membrane system including all accessories
label | 787ff79a-98ab-4cdf-8bac-cd84eee3c73e |  | note | REFERENCE: Work Method Statement
label | 44203fec-d799-40bd-9955-33258cdf8885 |  | note | IFC Drawings
label | 147b0a50-1b30-4c4d-bc04-1b90426a8d20 |  | note | ACCEPTANCE CRITERIA: No visual damage to the installed membrane system
label | 45367e64-4b23-4545-a13e-08a6c3acb2f1 |  | note | METHOD: Inspection
label | a5710408-b77b-42ef-a0f1-f48a952a306c |  | note | FREQUENCY: Once per Lot
label | 23c843a6-ea70-4227-9e47-ce9777505816 |  | note | CATEGORY: HP*
label | 7f409a11-1645-4006-a4f1-e23b8ad0c383 |  | note | RESPONSIBILITY: SE/PE Nominated Authority
label | 27ada686-45a0-4f4e-bb0c-518021ede1a1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 98307204-b0b4-4703-be82-26e0b9383dea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Patch Repair for membrane (if required)
label | 93bb43dd-4c35-46d4-8e3e-4f356206d8c5 |  | note | REFERENCE: Work Method Statement
label | f7aab7c2-e5b4-41d7-a4e9-2ad10db4a45e |  | note | ACCEPTANCE CRITERIA: Round out hole
label | 7aeb7135-6ec6-48c3-85e3-873c3b072b98 |  | note | Cut a sufficient sized "patch" from membrane ensuring size for overlapping the edges of the damage by 100mm
label | 677cf7ea-d1b3-43c9-b813-be7ffc12e084 |  | note | Hand weld patch
label | f19bb8e2-e6bb-41a6-9209-8ce9343ea58e |  | note | METHOD: Inspection
label | ae01cac7-578b-42e6-9a1e-31c815d22652 |  | note | FREQUENCY: Every Weld that need repair
label | e0f0ea2f-586c-4a79-a2b3-81c0d3c7ca7a |  | note | CATEGORY: HP*
label | 985f464c-da1f-4765-8460-7b164a835cb1 |  | note | RESPONSIBILITY: SE/PE Nominated Authority
label | d6020bca-99ac-42fc-9726-ffc7b9925cbf |  | note | VERIFYING DOCUMENTS: This ITP
text | 435080d9-591c-40f3-8aaf-a2dbcefcffff |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Copy of Subcontractor ITP/Checklist
label | 0b7d4a3c-b74f-49ff-bece-eefabe6b91eb |  | note | REFERENCE: Subcontractor ITP
label | 1fa7dfdf-b928-4628-bf9c-f60948363a37 |  | note | ACCEPTANCE CRITERIA: Attachment of Subcontractor ITP/Checklist
label | ab5f425d-573b-476f-968f-482bcb26c48e |  | note | METHOD: Document Review
label | c1ff6286-20de-4d7a-87f8-d46ebcbad990 |  | note | FREQUENCY: Once per Lot
label | 9a924a5f-c30a-461f-8f5d-90c31321c5d5 |  | note | CATEGORY: WP
label | 80f18ccc-4210-45e7-9cc1-a1ada526640d |  | note | RESPONSIBILITY: SE/PE
label | 056becd7-f02d-4b6d-8721-58fe86075e2b |  | note | VERIFYING DOCUMENTS: Contractor's ITP/Checklist
text | 0e833604-32de-4e88-be5b-a117dbc061e4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Conformance & Tolerance Verification
label | c5389347-b45b-4387-b719-fae322ad59ae |  | note | REFERENCE: IFC Drawings
label | 18ce9ca4-ff80-46bf-8786-3bf4402210ce |  | note | ACCEPTANCE CRITERIA: Ensure works is within tolerance when compared to IFC Drawings and Details
label | 8e0fcb33-b0f2-4e14-af6e-b907e323bbcc |  | note | METHOD: Inspection, Document Review
label | 625a5cfd-ceab-4e8e-ad07-6deb8cf7344f |  | note | FREQUENCY: Once per Lot
label | 45119cb4-66e1-4ba5-ba2e-cd60819e4eb5 |  | note | CATEGORY: WP
label | 375a786b-545e-4b57-8e27-738e2e09c714 |  | note | RESPONSIBILITY: SE/PE
label | 118d4993-4fcf-475f-ad66-8d768a2b5a10 |  | note | VERIFYING DOCUMENTS: This ITP
text | 002a37a9-1497-4d0f-be6d-19813b049304 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Subcontractor Product warranties obtained
label | 8bf76c11-6ced-4727-8335-b026a10baf09 |  | note | REFERENCE: Work Method Statement
label | 337b06a2-efc3-4c5d-a28f-6b15e3730d7f |  | note | IFC Drawings
label | f9557c8d-5eaa-43b8-b215-c12907e0c475 |  | note | ACCEPTANCE CRITERIA: Product warranties obtained and are compliant with the what is specified in IFC Drawings
label | 80e0dd31-ec31-4725-85d4-50e02ce43ddf |  | note | METHOD: Inspection, Document Review
label | 409ebd4e-ca65-4036-b68f-2ea1f65d794c |  | note | FREQUENCY: Once per Lot
label | cb9a27c4-9271-4b9a-ac09-7f857b761d20 |  | note | CATEGORY: WP
label | d74cdd08-5234-4220-b445-183e191efc52 |  | note | RESPONSIBILITY: SE/PE
label | a8b09447-6479-4f26-948f-46231ca62d35 |  | note | VERIFYING DOCUMENTS: Copies of product warranties
text | 76440f47-0a58-4778-b2b7-b3bb04c85b78 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Relevant RFI's
label | 555612a3-8d8e-4669-a87f-d2d7a8b9265f |  | note | ACCEPTANCE CRITERIA: Design/Construction Queries or clarifications relating to this ITP
label | b8e5fe13-67c4-4746-a848-2794aa4f3879 |  | note | METHOD: RFIs closed out and linked NCRs where applicable
label | 4a577be9-4d65-4c99-bf75-106a32d9c521 |  | note | FREQUENCY: Once per Lot
label | e39498f4-ec77-4aa1-a1e7-9029f951441a |  | note | CATEGORY: WP
label | e2989520-fc38-4751-9010-aee5715d90c5 |  | note | RESPONSIBILITY: SE/PE
label | fcc865a3-251a-4cf7-8d09-60f7775dcbc9 |  | note | VERIFYING DOCUMENTS: RFI's and NCRS linked to this ITP
text | 73888193-1b02-4729-9e48-b67073d73be6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Close Out NCR(s)
label | e125dac6-a42e-46a9-9246-a0aa67e38552 |  | note | REFERENCE:
label | 5a7497fc-4969-4d65-9cd0-69e29845d696 |  | note | ACCEPTANCE CRITERIA: All out pof tolerances notified via NCRs reporting system.
label | d22daf90-82dc-4b26-8c90-f733cad0e4da |  | note | METHOD: Prior to closing and signing ITP
label | 8cabdb6a-3462-48fa-a81c-a437b7946083 |  | note | FREQUENCY: Once Per Lot
label | 80c34b0d-8b70-455b-bd11-e6c9dd072883 |  | note | CATEGORY: HP*
label | 838b10c3-7b2c-46ab-a966-c6dd6506d058 |  | note | RESPONSIBILITY: PE
label | 50e51c28-7743-40cf-a2df-a9ee22164ad1 |  | note | VERIFYING DOCUMENTS: NCR(s) relevant to ITP
text | 75d74a6e-0f7f-48d9-aea2-3678b9e05f70 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 2af9a558-9909-4cce-a053-ac97a217e459 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 75cd90d6-89e9-4491-a59f-523a734d3839 |  | textbox | Name:
text | eea3e71b-c338-47d6-b518-12576ee954d8 |  | textbox | Position:
text | bc96cfd3-4bab-4513-b613-315ba4eeb304 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Line Marking (Supply and Install) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Line Marking (Supply and Install) Rev 0 | b08052b7-4984-4a04-acb7-9b42dc9e0f1d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 55a9e100-b689-4253-ab4f-01e3fd771764 |  | note | Document Title: ITP-CIV-Line Marking
label | e94cf61c-daa6-4098-bfb5-1c25ebe21cdf |  | note | ITP Description: Line Marking
label | 30c779bf-7b18-4e09-a7fd-f243de5f9bb1 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 3b00d9df-5f21-4d35-91f3-c0993a8b03bc |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | cfef6f64-aedd-4d30-9771-62268aadd8ff |  | note | Revision Number: 0
label | f9f251b0-f79e-4828-8085-9da780c7b890 |  | note | Revision Date: 26/06/2020
label | 8e5eef1e-06ac-4dc2-94f2-f677c094fc93 |  | note | ITP created by: Romualdo Magpantay
label | b6a0d4db-f8a0-42ec-850c-cb679c641b93 |  | note | ITP approved for use by: Michelle Edgar
label | c9920fc4-5e08-4541-b154-46af2833b169 |  | note | 1.1 VicRoads Section 721February 2017
label | 07fb4fc2-63c9-469e-92eb-c4337ccf99a5 |  | note | 1.2 VicRoads Section 175November 2019
label | 33e039f9-c3e4-4492-bb3b-1bba4caed655 |  | note | 1.3 VicRoads Section 853 February 1994
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Accreditation to Painting Contractors Certification Program
label | 6bdbfcfa-ea96-4b86-9f7d-bdeb4fce02b7 |  | note | REFERENCE: Vic road Standard
label | bbff891b-e96a-4ea3-969c-5bacf56373f9 |  | note | 721.D01
label | 9bb96dd4-e83c-45dd-8d28-11044a457f33 |  | note | ---------------------------------
label | 4c111545-421a-4529-b931-732aacee43da |  | note | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
text | 89c60dc0-33cd-4e8d-aa62-18deeb17149e |  | textbox | Enter: Teambinder Accreditation l Approval number
label | 157483b3-e31e-4661-8616-131877b32ed3 |  | note | ---------------------------------
label | 8a0076c7-ba1d-4d95-8491-ee1246c3db3c |  | note | METHOD: Document Review
label | 9a2fbdb1-3183-4810-8934-df03355b540e |  | note | ---------------------------------
label | b7e3604e-8b2a-4093-af1a-63b5e9a68ab7 |  | note | FREQUENCY: Once
label | e721f021-aa1b-497e-8731-7112f5a3a940 |  | note | ---------------------------------
label | b94a0db1-eec4-47a5-9b3f-b80aff8ff56b |  | note | CATEGORY: HP
label | 7047b61f-aef7-4106-ae0b-5d973475274f |  | note | ---------------------------------
label | 6380f597-4b3d-4fa7-b619-a1bdc393b502 |  | note | RESPONSIBILITY: Nominated Authority
label | 6fc76b66-de42-4465-822e-75ff0aa3f166 |  | note | ---------------------------------
label | 95e73d17-34c0-49a5-9f8f-f27c31614e84 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release PCCP Accreditation
text | f559e73e-c19d-4b22-b0e1-756198455e95 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Verify type of marking material as shown on design drawings and shall conform to the Standard
label | e83e7b11-a451-4aae-8341-1218c47d32cc |  | note | REFERENCE: Vic road Standard
label | 24411727-3731-45bf-bf8f-f44d529bb49f |  | note | 721.A05
label | d9dd3939-061c-47fb-8cb3-7dd5e8fc1bb6 |  | note | ---------------------------------
label | fc052d56-2870-43e7-86d6-7ff8f25018ad |  | note | ACCEPTANCE CRITERIA: Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
label | 0095c676-2bd6-47f0-b57f-97523fd09a23 |  | note | Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
label | 1b65ef05-5659-430f-ae88-272bda1be301 |  | note | ---------------------------------
label | fcb5d5c1-6cf8-47b8-80a5-7c73d4d65ab5 |  | note | METHOD: Document Review
label | c8be1da6-8655-4825-ab81-32685a21642c |  | note | ---------------------------------
label | 93463829-7e25-435b-9265-17d6301f278c |  | note | FREQUENCY: Once
label | 76e4cf2c-7f2c-4d17-a22a-ae5fea99abf1 |  | note | ---------------------------------
label | f193b1be-cd33-4b93-9950-892891903fda |  | note | CATEGORY: IP
label | fd449e31-a896-46f9-91e8-29b6a8763318 |  | note | ---------------------------------
label | ee17551a-b8b5-4f35-bf3c-9bc65094e4f5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 28189762-f905-4fc1-bd30-e762d7b4ac87 |  | note | ---------------------------------
label | 1f92af44-499d-4171-bf4d-0bda02b51dee |  | note | VERIFYING DOCUMENTS: Material certificate
text | ae9a5582-b47e-487a-a5af-df96778d37df |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Verify Raised Pavement Markers
label | 356d921b-ed17-4a36-ba6c-9481b0dd6581 |  | note | REFERENCE: Vic road Standard
label | 956e9c9a-2c8f-428c-ae5d-dccdf633e938 |  | note | 721.A05
label | 84158f4f-b8e5-4b89-92bc-3a75475fdf25 |  | note | ---------------------------------
label | 3e690e3e-7e46-4eb9-a1cd-7bfd458b2a56 |  | note | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
label | 9f37c45a-eaa3-4135-8030-e6be5cc8d6e1 |  | note | Enter: Teambinder Accreditation l Approval number
label | 55eaf976-90fd-4967-ba16-6aa1e6704686 |  | note | ---------------------------------
label | e98a13fe-c205-4a82-a9ef-a0c28009877b |  | note | METHOD: Document Review
label | f9d68d9b-d675-49da-85de-ec0603163a09 |  | note | ---------------------------------
label | 0740c9ce-30be-4fa4-8a62-efc6ba894906 |  | note | FREQUENCY: Per Material
label | a9947f4b-3879-4a87-8e88-2aca3542d46f |  | note | ---------------------------------
label | 0b4e129a-f371-40f6-9b9e-b823fd5fcc2e |  | note | CATEGORY: IP
label | 2801286a-3190-4a08-b76b-1af4e61e9311 |  | note | ---------------------------------
label | 8c64dc15-5d54-4316-bb5a-b3b848dcaf7f |  | note | RESPONSIBILITY: SE/PE/SPE
label | a108de77-ba53-4489-88f1-885d5d661fcc |  | note | ---------------------------------
label | 291ba244-e7fa-49c7-ac8c-e8ec1ea05548 |  | note | VERIFYING DOCUMENTS: Material certificate
text | 8c3dda98-183c-4a2e-baa7-9bb9f0eeda7d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Verify Adhesive
label | ac934b4d-0c26-4d92-a8ee-cd4e30ab76bd |  | note | REFERENCE: Vic road Standard
label | 5fa7a2c9-16fc-4e9a-b523-406979dacb95 |  | note | 721.A05
label | 0d67df1a-b6e0-4af5-9630-f6c39a82bd6c |  | note | ---------------------------------
label | d930d55f-8b48-4503-af69-fca317895b84 |  | note | ACCEPTANCE CRITERIA: Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
label | ccd25c17-16fd-4dcc-8373-a9ed32ca7210 |  | note | Other types of adhesive materials shall only be used with the approval of the Superintendent
label | 01836004-e8f1-4b33-be6d-68520092842d |  | note | ---------------------------------
label | 914b2394-8f6d-4b9f-b323-dd744346df99 |  | note | METHOD: Document Review
label | c462c45a-e4f1-448c-84e3-b22ac6c956f7 |  | note | ---------------------------------
label | fa5204ce-0b38-42f0-8891-2753389b5e24 |  | note | FREQUENCY: Per Material
label | 1e4f2705-436d-4eb9-b1af-f5885fb3dedb |  | note | ---------------------------------
label | e8b9cd6f-8727-4423-819f-6369425f5cc0 |  | note | CATEGORY: IP
label | e847877b-ad9f-49e3-a593-0d1d9e93e759 |  | note | ---------------------------------
label | 19021242-338d-4ff7-860b-ce474be3c886 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6d2708de-3a0e-4bc5-92ac-4d02826bbd68 |  | note | ---------------------------------
label | 5737a801-d569-4a22-a364-1bf32d8312df |  | note | VERIFYING DOCUMENTS: Material certificate
text | 845e4f0b-3383-4cb7-a288-bef849b6ec07 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Verify Line marking and Road marking Paint
label | 93c22aee-8c74-4b07-94e9-02b02267f8c5 |  | note | REFERENCE: Vic road Standard
label | db1d1945-02f3-43ef-9b45-e25b16f72c3b |  | note | 721.A05
label | b0e48bce-9f36-451e-abcf-868365e294d7 |  | note | ---------------------------------
label | 9dcd4587-55a5-4448-b9e6-432395cb3b47 |  | note | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
label | e11ff625-7bb7-48e4-b8e5-a20a9c0718b6 |  | note | ---------------------------------
label | 8cec277e-58ee-4bda-ad29-9ec910f17b38 |  | note | METHOD: Document Review
label | 6018ba96-49c0-419f-8f7f-d8fe98f88733 |  | note | ---------------------------------
label | ebcb05f5-a21b-411f-b28b-838e6604ce30 |  | note | FREQUENCY: Per Material
label | d383b690-6c7a-460c-bf45-8a788bd33abd |  | note | ---------------------------------
label | 8a2ffaf0-a85e-43dc-8618-1d37b23dcb63 |  | note | CATEGORY: IP
label | 608753b2-74dc-4c32-a848-c8f20351a85a |  | note | ---------------------------------
label | 68dd7779-4544-4841-a200-78d26462262c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2e071350-c7aa-4d4b-8ebc-3636c1d37083 |  | note | ---------------------------------
label | 2c7ac42f-cf58-41bb-96af-97b86ab8b2b5 |  | note | VERIFYING DOCUMENTS: Material certificate
text | e03368e6-d2ab-4399-a0b1-06d351ab914c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Verify glass beads conform to spec. requirements
label | 94e369e4-8fb5-4de1-99f6-228f48c73c30 |  | note | REFERENCE: Vic road Standard
label | b9e7308c-e5e7-4741-a673-ab91543ca5a8 |  | note | 721.A05
label | 85741397-3619-4734-b5c0-9ce77380bcbc |  | note | ---------------------------------
label | b04c872f-f5de-42fa-be2b-abd37639c505 |  | note | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042 as listed in Section 175.
label | 7f2fa8b5-04bf-48bc-ab3d-266e8f19f3d6 |  | note | (ii) Intermix glass beads for use in long life material applications shall conform to AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | 84530fdc-29a1-43ea-9311-5fdab05a39bc |  | note | (iii) The amount of heavy metals in the beads shall not be greater than that specified in Specification 0042.
label | 16a023b1-b558-4c07-a0fb-9724fd83927b |  | note | (iv) Pristine glass beads (Type B-HR)
label | c17b9d03-a6ce-4a4b-9eba-6acf80c862e6 |  | note | Type B-HR glass beads shall comply with the properties of Type B (AS 2009:2006) drop-on glass beads, with an additional high performance retro reflectivity requirement, requiring the delivery of a minimum 450 mcd/lux.m², when tested in accordance with a modified Appendix M* of AS 2009:2006 (described below).
label | a8465232-414f-483a-b0d6-ebb6786e1003 |  | note | Section M4 Apparatus clause a) Dry film thickness of paint will be 200-250 μm
label | e64ddfdd-ee18-44ab-a4b5-a2b07301e662 |  | note | Section M5 Procedure clause b) Weigh 24 +/- 0.5 grams of glass beads
label | a2818fa8-e792-47ea-81e0-04f310335312 |  | note | Section M5 Procedure clause e) Wet film thickness of paint will be 375 μm +/- 25 μm.
label | af966dc8-0c19-439f-a568-fe15618bd814 |  | note | ---------------------------------
label | d628dfc4-00f5-4c0c-a59f-fd702e6167de |  | note | METHOD: Document Review
label | 6da0ada6-c8f4-425a-bf4b-54688da6e5a0 |  | note | ---------------------------------
label | 34934e70-da09-4425-bb4d-cc28a2b9442e |  | note | FREQUENCY: Per Material
label | 75a3ea7c-2b34-4ad0-abb9-b6b2f9698fce |  | note | ---------------------------------
label | cb0fc9ce-0e6e-4678-bfcb-a579f38b6394 |  | note | CATEGORY: IP
label | 5b11dbc2-5515-45d4-a4ad-f798dae45f48 |  | note | ---------------------------------
label | 1af0cecb-05fd-471d-b977-087d73bfe29f |  | note | RESPONSIBILITY: SE/PE/SPE
label | b7566e42-bdcd-4431-a17b-0b7781447190 |  | note | ---------------------------------
label | 4f8a7959-c3a6-402e-901a-58e0778b365d |  | note | VERIFYING DOCUMENTS: Material certificate
text | 6a69484d-2689-47ab-942f-49a8e66238ff |  | textbox | Date Completed:
checkpoint-group |  |  | section | Application
checkpoint-status |  |  | checkpoint | 3.1 Prepare the surface for marking
label | 0c9269b1-f85b-44b5-acf3-2ed362bacbcf |  | note | REFERENCE: VicRoads Standard 721.A06
label | b2a8219b-18dd-4a34-b443-496f8a658813 |  | note | VicRoads Standard 721.A09
label | 947eeeed-e884-498d-bed3-bd16560f178d |  | note | ---------------------------------
label | 9952eb1e-b990-4dda-b6e9-c038a692867a |  | note | ACCEPTANCE CRITERIA: The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | b96777d9-d763-4896-9544-7ce985d55b08 |  | note | The area around making area is also clean to avoid tracking into the marking area
label | 166c2442-58c6-4060-9212-7bafcc763032 |  | note | Removal of existing unsound, obsolete or redundant pavement markings
label | 9dc1779d-fcb8-4888-9790-a1c163daf64c |  | note | Removal of any foreign materials and debris within reasonable limits.
label | 997f8911-c0af-4fab-84e5-b892d600be4f |  | note | ---------------------------------
label | 3bed6e06-3cfb-4984-903e-63b02e9fe361 |  | note | METHOD: Measure, Visual, Document Review
label | 72851b19-c8d0-402e-9388-7a373393148b |  | note | ---------------------------------
label | 01207f17-45e0-4de5-aff0-461ce816b23b |  | note | FREQUENCY: Per Lot
label | 3f5066ed-c59d-4342-ac95-112e2bff3e52 |  | note | ---------------------------------
label | 6e67a4d2-856c-4541-bde0-70db25cd010d |  | note | RESPONSIBILITY: SE/PE/SPE
label | f95b0f81-d25a-4498-8686-bf6b3b3fa468 |  | note | ---------------------------------
label | fd01487a-5c0e-4675-80d5-3f9c36c05d1b |  | note | VERIFYING DOCUMENTS: This ITP
text | 2c73708b-02d0-4351-92f3-fdf84d353d38 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Set out the works for installation of pavement markings / raised markers
label | ad9ed574-9565-424a-ac1c-da38bda5e346 |  | note | REFERENCE: Prior to commencing line marking works
label | d3fc509f-87f1-49e4-8e0f-f0c487afdc1c |  | note | VicRoads 721.B05
label | 3ae9b9ab-896f-41a7-83f3-f78ea31bedb4 |  | note | ---------------------------------
label | 173c8966-e32b-4fa2-b724-5c20c140f9cb |  | note | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
label | a5c9a364-a1ed-4e84-b358-69a24ce9bfa4 |  | note | ---------------------------------
label | 7dacb175-f8e2-48d2-8652-0683a71addf0 |  | note | METHOD: Survey Document Review
label | c8a14f5d-6cb1-4724-afff-f29f7b65237b |  | note | ---------------------------------
label | 5f122e93-3410-4c39-b449-ce919ae20829 |  | note | FREQUENCY: Per Lot
label | 0428655d-f13c-460a-b9af-1cbd5b56e55d |  | note | ---------------------------------
label | 8abfccee-9dc1-4c3e-9471-6632087158d1 |  | note | CATEGORY: HP
label | 26bd21b8-76da-45b0-a40f-4434f9604ad9 |  | note | ---------------------------------
label | 94378594-bdc5-410f-8f02-336b677ec1e7 |  | note | RESPONSIBILITY: Nominated Authority
label | 05c267ff-3f2d-43f8-8b32-c52e3b73fac8 |  | note | ---------------------------------
label | b233f7fd-7beb-4d17-9a4e-74fc331a8c47 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 6033eb9c-759e-40c8-95f6-d0a72b6aab0f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Remove redundant pavement / unsuitable marking markers
label | d792a396-0a20-4f4f-bb9a-be5e4815e5ba |  | note | REFERENCE: Prior to commencing line marking works
label | 504ecd30-d717-44f5-a295-ad88d43f9f5d |  | note | VicRoads 721.A12
label | 01e2e32e-973e-4908-944d-6a922b571b4e |  | note | VicRoads 721.A06
label | 3936de9a-0ed5-4509-be2a-faf679aeb16c |  | note | VicRoads 721.A08
label | 3101d135-5774-4ae3-a6f2-01bb1e3b0cb3 |  | note | ---------------------------------
label | f1b3bcf6-1e08-4147-b512-ecbe31425a64 |  | note | ACCEPTANCE CRITERIA: Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | f79b1108-9ce3-463a-af4c-b7a38536122c |  | note | ---------------------------------
label | 246320bc-acef-4ae3-bb0d-a8b16367b9b1 |  | note | METHOD: Visual /Site Inspection & Document Review
label | 879994e7-9ffb-47ad-b396-3bee07ebcc2e |  | note | ---------------------------------
label | bd95747b-907f-46aa-a147-015f1463466d |  | note | FREQUENCY: Per Lot
label | 0f79c7db-d87d-4318-9857-eb6d66eed621 |  | note | ---------------------------------
label | 02d5e901-6cc0-4342-93f1-494e4b1aba53 |  | note | CATEGORY: HP
label | a41a5186-9be6-4907-92f3-c77b9dd1f16c |  | note | ---------------------------------
label | 66051b71-bed3-44c7-8337-c247cb62adee |  | note | RESPONSIBILITY: Nominated Authority
label | 5c2bee94-a1eb-4786-9609-c4d28727a768 |  | note | ---------------------------------
label | ed5c6172-55ec-4f1c-a803-d924ca64a59c |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 6874359e-d4cb-4991-9d2f-2c0d01936b26 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Supervise the application of pavement marking / markers
label | 0b53fa85-9d82-4ee3-b55c-fb8885d14864 |  | note | REFERENCE: VicRoads Standard 721
label | 70f116ca-55c5-4ce1-af19-eda2acc6f2c4 |  | note | ---------------------------------
label | 55161b09-5b69-4c93-bc9c-4294f762e6b6 |  | note | ACCEPTANCE CRITERIA: Check conditions for application of marking paint & materials.
label | 7b37f5a1-b1a8-4aa9-8c69-c7495187773d |  | note | (i) Paints and markers installed as per manufacturer’s recommendations.
label | 6881a116-6193-458f-9a8c-ba2ec6ece041 |  | note | (ii) The same materials used with those nominated in the certifications.
label | f7dca741-b2ed-4475-aa12-1cd858048127 |  | note | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
label | 6fc3cc2a-30b3-4615-92f1-fdfb4ca9c5b9 |  | note | (iv) Verify markings are straight or with smooth, even curves where intended.
label | 3ce5568b-af1e-46bc-b009-43cb0295ab99 |  | note | (v) Edges are clean sharp cut off.
label | e9e26f2f-4c36-4399-965e-ae10b9f20587 |  | note | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
label | 2da454de-397a-44f2-ae74-73b67b3be9f0 |  | note | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
label | 723f84b1-db40-4888-a847-f4a548a03ee4 |  | note | (viii) Markings are neat & free from traffic damage or other defects
label | 1635c5c4-e360-4b30-9a63-34fd8b18c0de |  | note | (ix) Marking protected from traffic until hardened
label | 6c22a5bd-2ac0-4e0b-ac15-3a4220c449c1 |  | note | ---------------------------------
label | 0954da51-ef0a-46ad-b53b-f99ed4bd04bd |  | note | METHOD: Visual /Site Inspection & Document Review
label | 40d9a586-e902-450e-a8a3-f8e7b0a1d985 |  | note | ---------------------------------
label | e355126e-f773-4ae1-8d5c-2e761e483e6b |  | note | FREQUENCY: Per Lot
label | 0ba992ce-4cf3-4946-b29b-5ea4b5a232c5 |  | note | ---------------------------------
label | 01f6f48a-d569-4adf-905b-67ff9e62a40f |  | note | CATEGORY: IP
label | 0d7bd3ed-7e65-417d-987b-61d801e9da0d |  | note | ---------------------------------
label | 288ee435-3bf3-454c-861b-17196e7f9181 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 701ddf0a-24b5-42cb-8067-8e18a35c1653 |  | note | ---------------------------------
label | a3548e96-4a5b-4884-bd03-546ecf3ab7d4 |  | note | VERIFYING DOCUMENTS: This ITP
text | cf2cd8f6-a4e8-4036-bd7d-bf1934f23092 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Tolerances for new marking/marker installations
label | b803b105-efaf-4ca1-a7ba-1097fef57afb |  | note | REFERENCE: Vic roads 721.A10
label | bb523b0e-f391-456d-9d89-cf82e392b012 |  | note | Table 721.A101
label | fd2c78a4-324c-4b0c-abe6-e3210f7fe235 |  | note | ---------------------------------
label | d7a53896-54eb-4bd0-b166-761876d0b537 |  | note | ACCEPTANCE CRITERIA: Pavement marking :
label | e82ca4ed-2951-4100-87eb-21d15b300191 |  | note | Distance between the centreline of the marking and the centreline of the set out mark-<30 mm
label | a7aa7c9c-c591-4d14-8b41-176db2890d61 |  | note | Distance between the centreline of the completed marking and the centreline of the previous marking-<15 mm
label | b7f4f538-e114-458e-a18f-f29dc35fcdfa |  | note | Width of completed painted markings-±10 mm of the specified dimensions
label | d74d572b-68d1-4a56-8e60-3c1d9dd26aa3 |  | note | Width of completed markings for long life materials0 mm to +10 mm
label | b6545c71-5363-4fc1-b95b-ba8ef42554d3 |  | note | Length of completed stripes and blocks-0% to +10% of the specified length
label | ff9e6275-aa7e-4634-9c48-1526285026ba |  | note | Gap between double lines--10 mm to +0 mm of the required 100 mm gap
label | 308ff071-4b76-4f77-9111-92a8e2aef6d8 |  | note | Raised Pavement Markers:
label | 6393f930-87f5-4e25-9b65-618ef644e7e6 |  | note | (i)Markers in line with broken segments
label | 38278e74-bac5-4f19-b297-00b89efa7e13 |  | note | Transverse position-±25 mm of the centreline of segments
label | dc02396e-6a05-4833-95cd-f1a9bab23a81 |  | note | Longitudinal position-±0.5 m of the specified position
label | 7ab00428-8307-4059-999a-9582edc86abc |  | note | (ii) Markers in a longitudinal group
label | 7563c529-20e9-427b-a55e-ed8f4bd98291 |  | note | Transverse position-±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
label | 7ab866ac-3761-49a3-93cd-29089a65468e |  | note | Longitudinal position-±0.5 m
label | dcbb89f3-3f22-459c-bb2e-f215d112433f |  | note | Spacing of markers within the group-50 mm of specified spacing
label | 643eb35f-3040-4421-8e80-3fd6aa2da7e7 |  | note | (iii) Markers adjacent to an unbroken line
label | 848b49d8-4b1d-48fe-b75a-4215dc114185 |  | note | Clearance to edge line-±5 mm of the specified dimensions
label | 98063422-6508-4626-bce5-efeea25cfe5f |  | note | Longitudinal mismatch between markers in transverse pairs-<25 mm
label | 1414e28b-c37d-4af3-9107-7be0f01cb8cc |  | note | Longitudinal position-Lesser of: 0.5 m or 10%
label | 0f33fd80-bad5-4550-8b2d-e3914cf1e9a2 |  | note | (iv) Orientation of reflective markers-Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
label | f221069b-a702-4ff6-8f75-26c270d4308e |  | note | Thermoplastic profiled lines
label | 3b419878-bba7-4d45-a8cb-11f0c817d228 |  | note | (i) Tolerances on dimension
label | 8d6d9ff7-5cd1-472c-a037-3a492b2f3104 |  | note | Line width-+20 mm, -5 mm
label | 63e06065-af9f-4e87-a863-b7b472aef6c5 |  | note | Line height-+2 mm, -0 mm
label | d99d3036-2084-4d37-9f43-62f969530a93 |  | note | Extrusion breadth-+10 mm, -0 mm
label | 6696d20d-23cc-4017-af10-9c08024e3974 |  | note | Extrusion spacing-±15 mm
label | fb5c951a-2c2f-47c1-8166-88272d50b7ad |  | note | Extrusion shape-±25 mm at any point from rectangular shape
label | 02820957-6851-43e7-867e-83299c458d58 |  | note | (ii) Tolerances on position
label | 45f60550-9674-486a-acbb-4fca48348be7 |  | note | Distance between the centreline of the marking and the centreline of the set out-<30 mm
label | d7d66a82-df44-4d31-98f1-08ca8cc5a191 |  | note | Length of the completed lines--0% to +5% of the specified length
label | 90da85cd-f4e0-46bd-be75-64cc9b839a56 |  | note | Longitudinal position of individual extrusions-±50 mm of any previously applied profiled lining
label | 3baf27ac-b4f4-47dd-8e24-1c9203ae054a |  | note | ---------------------------------
label | c0d01494-5a67-487d-bfd2-df7621e949b8 |  | note | METHOD: Visual /Site Inspection & Document Review
label | 729341c8-75b7-45c8-bf1e-b6b922adfbef |  | note | ---------------------------------
label | f4190524-2f91-4fd8-a4be-05ac16610cd2 |  | note | FREQUENCY: Per Lot
label | 7bfbfbc6-9ea7-46d5-a1f0-d512c1f216cf |  | note | ---------------------------------
label | 21d71f64-99bd-48e0-9172-800384798acc |  | note | CATEGORY: IP
label | a99691f2-2517-4e3d-a7de-70c4a805280e |  | note | ---------------------------------
label | 0e50c782-678e-4149-a094-caed19fceefe |  | note | RESPONSIBILITY: SE/PE/SPE
label | 16f6e9ff-7857-41ca-b63d-cf5736c04d01 |  | note | ---------------------------------
label | 50d41a50-93e2-480e-9f29-f73179922679 |  | note | VERIFYING DOCUMENTS: This ITP
text | f1edc127-cfb3-4c8e-b7fe-0f6c488d1deb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Field test of the paint performance if required
label | 62c9e265-14a5-403a-8c4c-94d13876bf53 |  | note | REFERENCE: Vic roads 721.05
label | eb02d351-4d7f-45c9-b02f-6b5ac34aab46 |  | note | Vic roads 721.A12
label | e5d02ece-ef84-4ac3-b217-a3eeae13e113 |  | note | Vic roads 721.A13
label | 23f2cba5-26e7-45d0-915b-cdcfe7d362d2 |  | note | Table 721.A131
label | 5f0dffac-0290-4c85-8d60-6e378c2c287c |  | note | Vic roads 721.A14
label | ec3dafac-284d-489e-8a27-bd458fe73b81 |  | note | ---------------------------------
label | 5a9df661-6f95-4c5f-9be4-c80c9bca6a7a |  | note | ACCEPTANCE CRITERIA: Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
label | f22ea2e0-79d0-491e-87c4-f0bac0fb323d |  | note | ---------------------------------
label | d26024c6-d30f-473a-b137-1efe91aeac1a |  | note | METHOD: Field Testing
label | 941c12d8-6f77-49ef-9848-d631878ddc56 |  | note | ---------------------------------
label | bc685c9d-6527-4615-95dc-7772156f1c90 |  | note | FREQUENCY: Per lot
label | 6494717f-a82f-48b8-9982-247de0f0b7ba |  | note | ---------------------------------
label | ba664e35-5a15-45c0-9f38-5192d875b108 |  | note | CATEGORY: Testing
label | fbf33c96-a95e-4e47-890e-c8e5d345af34 |  | note | ---------------------------------
label | 62c89bc7-d48d-4a25-a325-6a4aad9f86dc |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6b5338cd-da4e-4ec7-856f-1f9623b2c1ab |  | note | ---------------------------------
label | 764eb769-3bdf-44e4-a28b-5cc495fb0ef0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ec886f82-6fa6-47ac-8d9c-d6abdc61dd93 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 As-built Survey /Drawing
label | 0cccf8c7-80da-4207-b69a-bc476e87a0ae |  | note | REFERENCE: IFC Drawings
label | 26388d16-8c42-46a8-9ee7-39b3f549cf9c |  | note | Vic roads 160.A9
label | 1359c73a-2785-4997-b8c8-fc688847f980 |  | note | ---------------------------------
label | 5cf78a97-9fcf-4d52-8da8-26c915d40e13 |  | note | ACCEPTANCE CRITERIA: As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format
label | 6555179c-76ff-4d85-a621-528f455f7f96 |  | note | Attach: Survey As-built / Survey Report
label | aa8b8381-c504-4cd9-9d69-f40b82fc2a05 |  | note | ---------------------------------
label | 5d856636-0e4c-4649-80a0-1ebaaa3c57cb |  | note | METHOD: Document Review
label | 716a222d-27af-4bf8-a190-3f3e91607eb0 |  | note | ---------------------------------
label | 900ffeec-db12-422a-9f08-27ba5c25f8e8 |  | note | FREQUENCY: Each element
label | c0d48934-1ac0-48b7-b3ee-300cd2a9ad76 |  | note | ---------------------------------
label | ba5bf92a-28f0-4377-b0bc-e3a2a3d492bb |  | note | CATEGORY: HP*
label | b958460a-e106-4427-a6f9-6ba5c933826c |  | note | ---------------------------------
label | 9995a80b-ffa0-42a5-b04c-d06760739ea3 |  | note | RESPONSIBILITY: Nominated Authority
label | 4a4bbb5f-dc47-4637-92bb-4566f11c1a50 |  | note | ---------------------------------
label | 5f96628b-11a3-4ff0-9636-720a8f2e42d2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b60823b1-d8b2-4e2a-b7dd-17a03d009f2c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 Non-conformance Report (NCR) Closure
label | f892aa5c-d4ed-41db-a244-220c3ee79235 |  | note | REFERENCE: MRPA Quality Management Plan
label | 7fb2c686-e5f4-4736-861b-2752d0ac2038 |  | note | ---------------------------------
label | cf8cac14-713c-448e-8a9b-038663b351d3 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 797b3dfc-6632-40a9-8bce-d81cd30ec0b2 |  | note | ---------------------------------
label | c7818cde-5fa8-4c30-bfb9-aa511f817350 |  | note | METHOD: Document Review
label | dcb5ddc4-38b7-492e-8b28-34c199652e95 |  | note | ---------------------------------
label | 2557e5dd-ce10-4833-a471-c3cc08bf4dc2 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e5da5e91-19ba-4dcb-a28d-a59465085192 |  | note | ---------------------------------
label | 9b31f068-fd7f-42ee-9632-6d34311ea402 |  | note | CATEGORY: HP*
label | 8cc70ee2-62bf-4df5-bcb4-cc5b3ceec893 |  | note | ---------------------------------
label | c72beef8-48f4-4d88-9f48-f6d0c1827552 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 95d9863b-dafa-4ed7-b7a8-8de87d6c7106 |  | note | ---------------------------------
label | 898d62c7-4937-494c-a51a-888b64450ef4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 68e9d711-c46e-44f6-8e28-e3f4b82b2681 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | bcd3642c-fbef-46bb-bba9-3e8291ede43e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 70bf3549-4ebe-49db-a2ac-00bdce4554ff |  | textbox | Name:
text | 0183d5a0-998c-4637-9e41-89f16426d415 |  | textbox | Position:
text | 85d6b8ed-ef4b-46a8-bda0-c5572ae82552 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Beaconsfield Carpark Fencing Rev 0 | itp |  |  |  | Yes | ITP-CIV-Beaconsfield Carpark Fencing Rev 0 | b60424b4-3f35-435f-8989-66168837766d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 6e21308d-ddf4-4e2a-8a5b-04ff54060919 |  | note | Document Title: ITP-CIV-Beaconsfield carpark fencing
label | 2f578906-c8e0-45f5-9e69-d08018d5e3a3 |  | note | ITP Description: Beaconsfield carpark fencing
label | 8632e975-e2b2-4f67-9ab6-2b7d208503af |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 47ceb42f-f838-4ed5-8fb3-9f0bf21e64c9 |  | note | Revision Number: 0
label | 8979e62d-0e79-447a-a524-c1d3217a4aa1 |  | note | Revision Date: 6/11/20
label | d62ba542-85fe-42d3-aa35-d9f604051a2c |  | note | ITP created by: Gaurangi Sen / Mathew Velcek
label | 5adc95b7-59e9-408d-b014-24484cd5b72e |  | note | ITP approved for use by: Romualdo Magpantay
label | fcd9d260-38fb-4f50-be20-419aa583b3cb |  | note | 1.1 Vic Roads 707
label | 3a9d9456-ae2e-4da7-a7bf-5da9b063ed1f |  | note | 1.2 L1-CHE-STD-005
label | d95a8255-798b-4433-98fc-62187a05e1d9 |  | note | 1.3 MRP-016-C-AUR-REP-85-BFD-CRG-0001.0.IFC.0.04
checkpoint-group |  |  | section | Materials
checkpoint-status |  |  | checkpoint | 2.1 Submit materials and components conformance certificates by subcontractor for fence, gates and stock grids(Steel Columns, Cladding, Handrails, Chain Wire Mesh etc
label | a8fece93-3e90-448e-b7dc-511a4721ef42 |  | note | REFERENCE: Vic roads 707.03 c,d, g,h & K
label | 70ea6c40-5df2-478c-90fd-740eedd50ea3 |  | note | AS/NZS 4680
label | 10c5888a-2274-455b-845c-f6b966d0f315 |  | note | AS 1725
label | 2c3c66de-af49-43ea-a51a-cb3d4eca984e |  | note | L1-CHE-STD-005 section 14
label | 0055c31a-cb0c-45cf-8667-2cb015bd3c5e |  | note | ACCEPTANCE CRITERIA: Verify supplied materials and components comply with the Specification
label | fa91340f-2af8-4aa1-91d5-c72331e2c5f3 |  | note | Submit signed Certificates of Compliance to
label | b3d20a3c-0353-41f7-a993-5bb9014f7ac9 |  | note | Chain wire shall comply with AS 1725 requirements
label | 624fa47a-cf76-4229-9074-18735f1e263d |  | note | Steel posts (minimum yield strength of 195 MPa)to be hot dipped galvanised in accordance with AS/NZS 4680
label | 1bfe7245-959e-4788-a51d-707cacb11456 |  | note | METHOD: Document review
label | 997eb3aa-2c54-454f-9cb5-9ff14e109a01 |  | note | FREQUENCY: Per type
label | 6c6f6364-671d-46b8-8dd1-3a98cbe83af3 |  | note | CATEGORY: HP
label | c75d130e-dc8f-4e44-a525-a7ced3f68ea4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | dcf10990-e672-4331-bf3f-69c78fc82a8c |  | note | VERIFYING DOCUMENTS: Certificate of Compliance
text | f556d4ee-2710-4a0b-8eb5-fa3f23d61ebf |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Concrete
label | 631da331-6c61-4eeb-9e53-fe8c16080dfa |  | note | REFERENCE: IFC Drawings
label | 3c934330-3025-461d-a06f-f7b8d1e69d99 |  | note | AS3972
label | 4602bd90-d320-4ab2-bd4f-43eb1c781c16 |  | note | ACCEPTANCE CRITERIA: 25 MPa concrete to be used as per IFC drawings. All cement to be GP or GB or SR complying with AS3972.
label | d6dac115-c32e-48e5-8fe6-fe9c93044c85 |  | note | METHOD: Document Review
label | 1224c9c4-dc1d-4ac1-a7b0-7ff3ec57b047 |  | note | FREQUENCY: Each Mix
label | fafeb2c5-8c86-40c9-a11d-b9c17ffd7fd5 |  | note | CATEGORY: HP
label | 13b495f0-6f48-4295-97a2-7be553765590 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4b2ee91b-73a0-40a7-845b-6db8dca4e087 |  | note | VERIFYING DOCUMENTS: Certificate of Compliance
text | 2ac4e5f1-f373-465a-9185-7749125477ca |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Check materials upon delivery
label | b895c99a-36a6-4ba3-967b-61f64108dc4d |  | note | REFERENCE: Vic roads 707.03 c,d, g,h & K
label | 529cf7db-91e0-41b3-9cac-6054e856b9fd |  | note | AS/NZS 4680
label | f80c80a8-c2b5-4ed0-997a-2207400ca567 |  | note | AS 1725
label | 65906e86-1584-4e28-81f7-8f1dbfb7c6ef |  | note | ACCEPTANCE CRITERIA: Components are as per purchase order/s & delivery docket/s
label | 1c602352-946f-4e5e-993e-7c8850438e13 |  | note | Free from damages/defects
label | f6ca7280-429c-41c0-bf2e-ba8b48f2020b |  | note | METHOD: Measure Visual
label | ae782f0e-c33c-467d-ac4b-ec8acba5982a |  | note | FREQUENCY: Per delivery
label | 34f5e11b-4095-447e-ae85-6f151d98f052 |  | note | CATEGORY: IP
label | 77cf2e64-eae2-405f-8d92-6a5df3de77af |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 8f87b5ef-a1c9-4d64-b3ae-c2ad84a68573 |  | note | VERIFYING DOCUMENTS: This ITP
text | 686dafcd-02d8-42b8-a0a1-e6bd0a835b82 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre Installation Work
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 90c33d5f-4ae6-4406-964a-f1ad92d16c79 |  | note | REFERENCE: IFC Drawings
label | 05ddac00-c056-4768-be46-1f66346e6580 |  | note | L1-CHE-STD-005 section 7
label | 46a5bc20-7651-4e9e-9a01-3308d68a6c44 |  | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing contours, levels and features, surface pits
label | 49a9671f-f724-4d08-bab4-7cfe3426a1cf |  | note | Establish Pegs or equivalent to define the boundary of fencing
label | 0db677a9-850d-4297-b527-8f2fded9ea00 |  | note | Fences shall be constructed on the boundary of the infrastructure lease or within the infrastructure as necessary
label | 1b637830-5837-4636-86ad-62e087f7ed9e |  | note | METHOD: Measure Visual
label | d4112acd-9a32-4651-9faa-475a564ddcc1 |  | note | FREQUENCY: Per Area
label | 51172c8f-f2f5-403a-9842-f7f87fd30ac3 |  | note | CATEGORY: IP
label | 9c0c32b5-0800-404f-b5c3-748037736998 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | e9b4fe77-1db4-4951-8f3a-9d1e915a372c |  | note | VERIFYING DOCUMENTS: This ITP
text | 7bb704d8-6907-4b3e-8e6b-e1654e5df1c6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Remove existing fencing (if applicable)
label | d5997d65-6c41-4d5f-9572-eb54e388c2a5 |  | note | REFERENCE: Vic roads 707.07
label | 363337c8-2fb5-468e-b9f1-ee4815ac1417 |  | note | ACCEPTANCE CRITERIA: Backfill and compact all holes left after removal in 150mm max layers to same relative compaction as adjoining ground material.
label | d179eda2-7fab-4068-bb3e-d9ce1cdeed6e |  | note | Total length of fence removed:
label | 0cb39841-bc5f-4b56-b698-8fdc0be3523b |  | note | METHOD: Visual
label | 5fd09b98-3b72-4876-bd6f-3c5874af7be3 |  | note | FREQUENCY: Per Area
label | 140b1e93-0a36-48aa-9f2c-25fb97069d3c |  | note | CATEGORY: IP
label | ab02dc4c-ac46-435c-ac07-22d9d067e651 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9b914d92-9522-4870-9322-dc23d84f2cbb |  | note | VERIFYING DOCUMENTS: This ITP
text | e6a52501-341c-48d5-b489-5f3d2355b782 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Neatly excavate/drill holes for posts
label | 1694725f-8e60-47db-a82e-fa65f407278c |  | note | REFERENCE: IFC Drawings
label | ab2a4ac8-a667-4fbd-9c7d-70f81b3b9c9a |  | note | ACCEPTANCE CRITERIA: All open excavation should be fenced.
label | 26924d79-7e21-4e79-96a8-8b11f2066871 |  | note | Follow asset owners guidelines for work around their service.
label | a7505af9-7276-4c3e-95a3-302add3690a8 |  | note | Post holes to correct dia. and to the concrete footing as shown on the approved drawing see item 4.3.
label | 54a04cc3-cb37-4953-b44f-733d6e2f2b18 |  | note | METHOD: Visual
label | b2156094-89fe-4522-818e-1ced2613c0ef |  | note | FREQUENCY: Per lot
label | 816df3be-93e1-4271-9ad0-db7a8bd6f719 |  | note | CATEGORY: IP
label | cf9b6e80-d861-4c85-9e52-bb86c66f8f44 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 820b1af2-fe6b-4fb4-b3f4-38a3b52a53d6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 138b10fe-1480-467d-a8fc-b8204516ba60 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Ground Conditions
label | 73b54ea0-97ad-4078-802b-ae37510543fe |  | note | REFERENCE: IFC Drawings
label | 4fd171f7-9db3-4738-96d9-8e3f703062f4 |  | note | ACCEPTANCE CRITERIA: All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | 8c2c1f20-a7eb-4015-b186-673d771385d4 |  | note | If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | d9de3301-d5a1-4c0c-9bae-95cbbbcec22d |  | note | METHOD: Visual
label | 4347dd2b-3529-4a9b-bcb9-319cefe8358d |  | note | FREQUENCY: Per lot
label | 00760ad6-a3b4-438f-b63a-1f0fb1713a62 |  | note | CATEGORY: IP
label | 9c37381d-e8b6-4c10-8571-4061a673c319 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 685880aa-96d8-48ea-93e2-b8503872d070 |  | note | VERIFYING DOCUMENTS: This ITP
text | a08871a1-6426-45a6-ac20-75c966294012 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Post Foundation (Weld Mesh)
label | eef2aa3b-1150-4452-b4fb-5f6ef4a7d23d |  | note | REFERENCE: IFC Drawings
label | 5aad412f-5fc4-45ec-88b1-23156e8044be |  | note | MRP-016-C-AUR-REP-85-BFD-CRG-0001.0.IFC.0.04 section 3.2.7
label | bf61cd26-ccf4-4d47-8123-64c8e84c4667 |  | note | VicRoads Section 707.04e
label | 3b488a42-1c39-43ef-ade6-422bf0f0deac |  | note | ACCEPTANCE CRITERIA: Concrete footing shall be set as shown in drawing or to be 600mm depth and 200mm in diameter. Minimum 550mm embedment.
label | 4012c323-3dd8-49ab-a610-5eec620520d0 |  | note | Top of concrete crowned to shed water.
label | 07618158-2843-4b31-96c2-54a83a44890e |  | note | Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete
label | d1b487e9-e207-4451-9316-0e6eea1c1776 |  | note | METHOD: Measure
label | abad76b3-faa2-4a3c-bedf-ab2192a0ee39 |  | note | FREQUENCY: Per lot
label | 13f62254-6f65-4c1e-b702-c4fcf0419be3 |  | note | CATEGORY: IP
label | 93e89ce8-0950-4ec3-a2e3-372a1405f1c6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ddbc0718-9f19-4d0d-96dc-4c63fc109759 |  | note | VERIFYING DOCUMENTS: Post and concrete dockets
text | 8bd7518a-3a4c-4429-8be9-b569efc6cd4d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Post Foundation (Chain Mesh)
label | 19d86354-e6ea-4c14-8bf8-777311ec31ba |  | note | REFERENCE: IFC Drawings
label | b4b8d83d-0d31-41c3-b519-de170ae83d04 |  | note | MRP-016-C-AUR-DRG-85-BFD-CRG-0106
label | 201e167a-e54c-4243-b293-1e878f7a59d6 |  | note | VicRoads Section 707.04d
label | 5dfba7dd-30b4-4706-a732-d92d41e9431a |  | note | ACCEPTANCE CRITERIA: Concrete footing for end post at 750mm depth and 600mm depth for all posts. Diameter of 250 to be used. Minimum embedment of 300mm. Top of concrete crowned to shed water.
label | 1aee1404-f653-462d-bceb-dcfb64676ac4 |  | note | Concrete posts holes must be filled using an approved 25 MPa ready mixed concrete
label | b24737a8-ceee-4f29-800e-8285a810c5ea |  | note | METHOD: Measure
label | d058ffe1-a55f-4132-9a87-3a553bbaf040 |  | note | FREQUENCY: Per lot
label | 67c45bb7-9947-43fa-8a4b-dc5a71eb1f4e |  | note | CATEGORY: IP
label | e254fc2f-9091-49a7-b8a3-7788a1eca541 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 924852f6-fd5e-4364-b5d2-fee5fef73e56 |  | note | VERIFYING DOCUMENTS: Post and concrete dockets
text | e245f1ad-6615-4a1a-ab0a-c3c41eb34e5c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Post Installation
label | edb274b1-c7bf-45b9-806f-649a50b44c87 |  | note | REFERENCE: IFC Drawings
label | 7dbaa1b1-69b1-406b-9f4a-6e9eee4d70e7 |  | note | ACCEPTANCE CRITERIA: Maximum post spacing to be 3330mm for both end panel and intermediate panel.
label | 56aff34b-7604-4bcd-bcf4-16e50ad9aa0f |  | note | Max. post height 1890mm above ground level.
label | 6680f8c8-4549-4658-84b9-78f220240c45 |  | note | Galvanised weather cap installed on all posts.
label | b5e2b036-0125-45b4-a0c3-92bc091c99ef |  | note | Posts to be installed vertically within 1 in 50 plumb.
label | 34510382-efff-4349-92fc-7c049e5ea874 |  | note | METHOD: Measure
label | 42928a75-8298-483a-8c08-0706906e5d20 |  | note | FREQUENCY: Per lot
label | 6254463a-ee76-4301-aa1f-ae0c08c877c2 |  | note | CATEGORY: IP
label | 0fb39ab1-b9bc-42da-b82b-b65eb92ed79b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8ef4e507-ac6a-4f4a-9753-feed77dc67d5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4d245cc6-ec52-4f5a-88d6-db5dff9f4384 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Chain Wire Mesh Installation
label | 3b57cdab-133c-4ab5-9c2a-f91523dcce05 |  | note | REFERENCE: IFC Drawings
label | 5812f483-7a44-4502-890e-efa2563cad30 |  | note | VicRoads Section 707.04
label | 9b3fe083-b5b1-49d8-8363-f0d893d1dc16 |  | note | ACCEPTANCE CRITERIA: Chain-wire mesh 3.15 heavily galv. wire with nom. 50 pitch (W10Z) to be tightened and fastened to post and line wires (Support cable single 4mm Heilcoil and diagonal bracing cable twin 3.15 twisted)
label | 6db288c4-dd20-4fd3-962d-cd5d93477ce7 |  | note | Chain wire to be fastened with 2.5mm dia. galv. tie wire or clips. Spacing to be not more than 400mm intervals on line posts and not more than 500mm intervals on line wires.
label | 8267a304-76e3-49aa-b8ba-11e816fbc5cb |  | note | METHOD: Visual
label | b6497823-bc8c-4a31-a4eb-705cf9a15af9 |  | note | FREQUENCY: Per lot
label | b699d586-a34b-4c68-9d5d-629cb9174608 |  | note | CATEGORY: IP
label | 0a377714-46e3-4038-b2ae-7db3efd92a45 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8b06044a-3565-4bec-a1de-25c7bcf32769 |  | note | VERIFYING DOCUMENTS: This ITP
text | 907d27b4-5169-4580-aad8-25c9ad694a5d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Bracing
label | 4e1fb45d-a6bd-41ac-94f3-f9227613bcc1 |  | note | REFERENCE: IFC Drawings
label | 87ec1633-61c5-492c-9438-5a54a434d2db |  | note | ACCEPTANCE CRITERIA: Tee Clamp T5032 and Cross clamps used on posts.
label | 34c79cbe-3299-4f70-adc2-1f2b7112f8af |  | note | Bracing to be installed on both sides of the fence at the fence corners
label | 22a113ee-3557-46e3-8099-f68d84907707 |  | note | METHOD: Visual
label | ebc6c950-c716-4948-b354-7c86c4dc7daf |  | note | FREQUENCY: Per lot
label | c7cda6d0-4088-44cb-beb3-73e0dd612440 |  | note | CATEGORY: IP
label | 76a0c244-fbd1-46e5-a4c8-3b95bdc5e219 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 540aec35-45c1-407e-9856-a4e60c9af44f |  | note | VERIFYING DOCUMENTS: This ITP
text | 5bf51236-db6f-455c-ace9-206f820724ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Install Gates
label | 80a1652d-1c8a-4ab4-a5fd-35facfbf4b41 |  | note | REFERENCE: IFC Drawings
label | 59c0c4ba-a4e1-40ee-ab63-630c8ca7401f |  | note | AS 4680
label | 9fb4566a-c64b-45c8-b94b-86e950ab35f8 |  | note | VicRoads Section 707.03(h)
label | 7edcb908-a6c5-4e90-bd47-b60ce4805056 |  | note | ACCEPTANCE CRITERIA: Gates shall be standard proprietary manufactured items with galvanized tubular steel frame
label | adf08c97-9a97-49a5-882b-d4ccb252b8cf |  | note | Hinges, catches and other fittings for gates shall be standard proprietary manufactured items fabricated from grade 250/300 structural steel and hot-dipped galvanized
label | ca11525f-9679-4a11-b65c-02788d1c9504 |  | note | METHOD: Visual
label | 94192938-148a-461d-a21d-702ac5beb00c |  | note | FREQUENCY: Per lot
label | 6f4e2679-509b-4ebd-ad83-aefd4e565f78 |  | note | CATEGORY: IP
label | df6aa54b-3e92-44e1-b200-6b001a9b8a34 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1506cb4d-936f-4e9d-9022-2a6ab10db732 |  | note | VERIFYING DOCUMENTS: This ITP
text | 36ea6d42-6049-455c-9815-f8ca42777bbf |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Fence Height and Track Clearance
label | a5c77284-df05-44b0-ae0f-a280e2b8ab11 |  | note | REFERENCE: IFC Drawings
label | 275960fb-3f61-49ba-8aaa-caceefb2e32e |  | note | VicRoads Section 707.08
label | 1b4030e6-b3b2-4c10-b652-e3edc456ebc2 |  | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | f730ec56-6f98-4ed4-9dd8-e6363de2e3d7 |  | note | Vertical tolerance of ± 20mm from the design line, longitudinal line tolerance of ± 20mm in plan view, tolerance on verticality to be 1 in 50.
label | c67006b3-472f-4626-a557-f8374d63d69c |  | note | METHOD: Measure
label | 048933d5-45e9-4735-bbe0-e75fadf57b96 |  | note | FREQUENCY: Per lot
label | 4376117c-e659-4308-b246-c026a3526074 |  | note | CATEGORY: IP
label | 26f22dce-c3a8-4607-9f3e-f974c9b41ab7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b8e074a2-501e-4814-8829-d927ab07e672 |  | note | VERIFYING DOCUMENTS: This ITP
text | de3beaad-499d-474d-af56-1bc4be0c104f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 As-built Survey
label | 7ac4bd9a-4a84-49e0-9802-227c57f9e4d3 |  | note | REFERENCE: As Built Drawings
label | ee5ce52c-6228-4a81-87b8-07c984b0d541 |  | note | Asset Change form
label | 4d9da0f9-3f77-4591-87ac-02ad496c2e14 |  | note | VicRoads Section 160.A8
label | b4dac4c4-ae3c-4f7a-9772-74e51227cd5a |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | 439ebe03-931e-4915-ab64-f93bd89458a4 |  | note | Attach:
label | 61596c5a-39f4-4bcf-86f6-b4ebb6fe5669 |  | note | Survey Report
label | fe23b6c8-0451-4577-98b6-976ad86ee7d5 |  | note | Engineering Asset From
label | 456e3682-b74d-4d3f-b46c-124a7f3f54b7 |  | note | METHOD: Survey Document Review
label | 74c091ae-9d65-4aa0-8c2e-e3f0833a059b |  | note | FREQUENCY: Once
label | 08262966-869a-46e8-bc10-30670c4e4570 |  | note | CATEGORY: IP
label | 86686618-b3c3-46f7-a97a-cbdea9ef7eb8 |  | note | RESPONSIBILITY: Track Surveyor Site/Project Engineer
label | 884d2e37-20b9-40bd-a2c4-315842bfdfbb |  | note | VERIFYING DOCUMENTS: This ITP
text | 26672b96-1e5a-4dd2-aa8a-5073358eb2b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 04f9d34a-7657-479a-b324-93d1f20f6033 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d27341a4-1439-4ed9-8eab-bb66e57ccaea |  | textbox | Name:
text | bb1da862-e6e0-4786-8fc3-e8139d1bdf6e |  | textbox | Position:
text | 8f2cd38d-b407-46c8-8778-aa4737f9cddb |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Clyde Rd Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1 | itp |  |  |  | Yes | ITP-CIV-Clyde Rd Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1 | b75a5423-38cc-4dc3-96e2-e6c1985e9e96
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 28640a43-9b64-5516-89dd-fc30ab77d7d8 |  | note | Document Title: ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding)
label | 0b980ac9-ab91-5bde-a67e-d70724aba92e |  | note | ITP Description: Footpaths & Shared User Paths - 1 (Set-out & Bedding)
label | 55d15169-3f71-5ec6-8413-f2643ef23d53 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ea32ad3b-eb6a-5e1b-b92b-28ff6997f9ea |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | d920c2dc-f56f-502e-81d1-bc3366751308 |  | note | Revision Number: 1
label | 22c3cf16-2ef6-51d7-a4ae-2c33beee2eec |  | note | Revision Date: 20/08/20
label | 3a444fca-be71-5d0a-840c-2b9c5551d613 |  | note | ITP created by: Mike Freeman
label | 1d1b052d-eb74-56c5-ae0c-6d0634c249ec |  | note | ITP approved for use by: Mike Freeman
checkpoint-status |  |  | checkpoint | 1.1 - Reference - VicRoads Section 304 August 2013
checkpoint-status |  |  | checkpoint | 1.2 - Reference - VicRoads Section 703 June 2018
checkpoint-status |  |  | checkpoint | 1.3 - Reference - VicRoads Section 812 July 2016
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 - Bedding Material Placement & Compaction
label | e3bd8287-c67a-58f2-b704-686650a4ed8e |  | note | Reference - IFC Drawings 703.21 812.04
label | 84668ad1-8b5a-5170-9af1-c33b294af357 |  | note | Acceptance Criteria - 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings. Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | 1e27f929-568a-5ac1-8bd2-9ad38c9693be |  | textbox | Teambinder Material Approval number
label | 73c100e8-e642-57d6-ba39-1995c1a6538a |  | note | Method - Document Review
label | 24e46fd3-3933-5239-8976-29d47567df44 |  | note | Frequency - Once, for each mix design, prior to placement of material
label | 4307a4d9-2e74-54d4-800d-efa29db5c6f6 |  | note | Category - HP
label | 118544e7-3b2e-599a-b46a-f941e5264986 |  | note | Responsibility - Nominated Authority
label | 34e1bd75-740b-5ebd-ae71-11427df9e328 |  | note | Verifying Documents - ConQA Hold Point Release
text | 63f151bc-eca9-579d-83eb-4c2e459b390c |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 - IFC Drawings
label | e29c72a1-e70e-5396-91e7-40b0033ce8e2 |  | note | Reference - MRPA Quality Management Plan
label | 3f06145b-eff2-5a51-8aa4-e97d827ad8ca |  | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 29b857d3-6a18-521f-9253-c5a0b27dbadd |  | note | Method - Document Review
label | f5f7527d-3344-54e7-887c-f6a4336db897 |  | note | Frequency - Prior to starting Works and at regular intervals
label | 21bfcce4-7312-5e92-aa6d-2361a72d4651 |  | note | Category - HP*
label | 267bd9d9-e1d6-55ea-98c8-fa5c7f94b00e |  | note | Responsibility - All
label | 8066e730-8c22-528b-a28e-9f197e422f9a |  | note | Verifying Documents - This ITP
text | 9ff84316-86d2-5ea6-94e3-342d4c9f7760 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Survey Set-out
label | ed835166-8b7a-5c08-a9aa-88044d0743ac |  | note | Reference - IFC Drawings 703.17
label | c5f0b5ff-768d-5c68-a65b-9891323dd570 |  | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. The Nominated Authority will review and confirm the set out. Attach: Survey Report
label | 2ae878c2-f37c-520f-a4b2-bdf03af6076c |  | note | Method - Document Review Measure Visual
label | d5c0d6bd-ccc0-5b40-91ec-c9862de34065 |  | note | Frequency - Each lot
label | 82e7eb3a-902d-598f-bc43-dc5ae94e6a94 |  | note | Category - HP
label | ae1f9827-5fa0-5a54-bb80-d083c98eb932 |  | note | Responsibility - Nominated Authority
label | f71b155b-7ba7-55a7-973d-06e7360c39c1 |  | note | Verifying Documents - ConQA Hold Point Release
text | da84a5f3-cd7f-542c-8554-65c17d3510b6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 - Site Clearing & Grubbing
label | 25eecd16-07d7-5ac6-958d-eb89f0657029 |  | note | Reference - IFC Drawings
label | 9e54e82a-2cf3-5b49-a626-16e797267974 |  | note | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed. Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
label | a8f1d74e-cdca-58a7-b02c-0ecf531a6726 |  | note | Method - Document Review Visual
label | 60084d7c-48ef-56d1-843a-ee02b98bc297 |  | note | Frequency - Where applicable
label | 54cb60e6-56a0-54fa-ba86-6b3e46903a86 |  | note | Category - IP
label | eb92128c-00a5-5a7f-92eb-9f9fba0545f0 |  | note | Responsibility - SE/PE/SPE
label | 920a094d-ecfb-5796-95df-a4fe7d8045c8 |  | note | Verifying Documents - This ITP
text | 3747f953-a34f-560d-8bff-05c21c33d0e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Excavation
label | 9dcc0881-1b8f-5c44-89d1-c13f59f1c9b5 |  | note | Reference - 703.2
label | 9ab6485e-930a-5fa6-aea8-4336f62f4d3a |  | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face. Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | 8c075939-85e2-5ade-89d5-a733ac7ee261 |  | note | Method - Visual Measure
label | 999461f2-60ac-5f66-9bef-e1ade0d9f942 |  | note | Frequency - Each lot
label | 1068c700-7525-5889-97f0-d42464873e70 |  | note | Category - IP
label | 0451c5bd-550f-5778-82a7-ddc6b6bc1703 |  | note | Responsibility - SE/PE/SPE
label | a88f4c82-a702-5906-9d5c-ce07b461e968 |  | note | Verifying Documents - This ITP
text | e068d4c1-8f00-58e0-82a3-6aeb5334adf4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 - Pavement Thickness Increases for Crossings
label | c4457e16-9aa1-54c3-9519-f8bc793e1535 |  | note | Reference - IFC Drawings 703.16 703.24 Relevant Council Drawings
label | 1a896b77-a40e-5e99-ab65-6a4452447ea5 |  | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at: i. Pram crossings ii. Vehicle crossings (residential and/or commercial) iii. Established / existing mature trees Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | 17dd9c0f-2e5f-5fe6-8b32-af2e43c970c5 |  | note | Method - Visual Measure
label | 77a2155c-3cdc-566f-902e-c050759a5dd0 |  | note | Frequency - Where applicable, each lot
label | 15ab320d-d0ad-5c0f-a901-7b1decdda4ab |  | note | Category - IP
label | c40f8113-5f9f-560a-8642-a72ef455648b |  | note | Responsibility - SE/PE/SPE
label | 375c20be-fb3c-5c22-9136-75f1b03d47a0 |  | note | Verifying Documents - This ITP
text | b0a4cd5c-3419-5ffe-88a2-2c17515efdde |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 - Bedding Material Placement & Compaction
label | 14bb78c8-8ee8-50fe-8f45-ad2ef581704a |  | note | Reference - 703.21 304.05 IFC Drawings
label | de85fbc7-b77b-5f29-811e-948f236bf50b |  | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings): Footpaths: 75mm thick Shared Use Path: 75mm thick Shared Use Path (with capping): 100mm thick Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted. The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary. All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation. Attach: Bedding Material Delivery Dockets
label | c40f908b-536f-5217-b73e-a39a357835a6 |  | note | Method - Visual Measure
label | ac657b5c-5a59-506f-aa97-22cd9224b8d9 |  | note | Frequency - Each lot
label | 30e41376-a5ff-5d70-9dba-25c69ce90ec1 |  | note | Category - IP
label | 8ddea8ba-21df-5c7b-b3b1-bda41c72b665 |  | note | Responsibility - SE/PE/SPE
label | 4b1a729d-2e07-5759-b77d-dfaa1b2f8d56 |  | note | Verifying Documents - This ITP
text | 2a5fa2b9-effb-5c06-ab76-3bda6e2adf39 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 - Shared User Path - Compaction Testing
label | d4b8c502-4339-57fe-9c92-fd09c28ede56 |  | note | Reference - 703.21 304.08 (a) & (b) 304.11 (a)
label | dae36d19-fc53-5060-886a-51f4dc79756a |  | note | Acceptance Criteria - Compaction shall meet the following requirements: Scale of Surface Level Measurement = Scale B Optimum Moisture Content = ≤85% (1 test) Characteristic Density Ratio = 98 (6 tests) Attach: Moisture Content Test Results Attach: Density Test Reports
label | d90980d7-6e3c-5aa5-8917-ca5fc60f5570 |  | note | Method - Document Review Visual
label | ce86a9b3-bbad-5726-8ae1-18f6e96e3f82 |  | note | Frequency - Where applicable, each lot
label | 6955ddda-479d-591f-bb19-d54396bf0c99 |  | note | Category - IP
label | 14d06910-0ec2-5dad-a9a4-54a0de17c07c |  | note | Responsibility - SE/PE/SPE
label | a6bb88d5-91d9-5de3-b640-61db643d18b5 |  | note | Verifying Documents - This ITP
text | b8d1232a-0555-552c-9753-cea6709883c4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 - Shared User Path - Proof-rolling
label | 73cee252-798f-5e18-abe2-30cef40cae50 |  | note | Reference - 703.21 304.08 (b)
label | 39f3e9ac-7146-5dee-8fb9-150b6e0b5740 |  | note | Acceptance Criteria - Bedding material to be compacted and proof rolled before any construction. Withstands Test rolling without visible deformation or springing.
label | 6b5b0f9f-edc1-5b5d-8902-779c39e4f3f8 |  | note | Method - Visual
label | 4cfe3acd-200f-53ec-a4b4-f15985670ae7 |  | note | Frequency - Where applicable, each lot
label | fd186399-af9b-5900-a073-5359cd5d177b |  | note | Category - HP
label | 7e3db6ea-b57d-5123-97e4-99981a848f08 |  | note | Responsibility - Nominated Authority
label | 601a640a-0691-5038-b9c9-3c3e43e03d62 |  | note | Verifying Documents - ConQA Hold Point Release
text | 38934259-7363-51bd-8b0b-311b3bd9ee54 |  | textbox | Date Completed:
holdpoint |  |  | signoff | REQUEST HOLDPOINT
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 - Shared User Path - Post-compaction Testing
label | e76857e7-b3d1-5b8e-a872-953437d842fa |  | note | Reference - 703.21 304.10 304.11 (a) & (c) (ii)
label | 19bc8a76-9612-58a0-a379-ba9b71cc0d77 |  | note | Acceptance Criteria - Following completion of compaction, material shall be tested for post-compaction grading & Plasticity Index (PI). The test samples to be used for post-compaction grading and PI tests shall be a combined sample made up from six randomly selected increments extracted from the lot of pavement construction being assessed. Post-compaction Grading: % passing 26.5mm sieve = 100 % passing 19.0mm sieve = 95 - 100 % passing 13.2mm sieve =75 - 95 % passing 9.5mm sieve =60 - 90 % passing 4.78mm sieve =42 - 76 % passing 2.36mm sieve =28 - 61 % passing 0.425mm sieve =14 - 29 % passing 0.075mm sieve =6 - 14 Post-compaction Plasticity Index (PI) = 0 - 10 Attach: Sieve Analysis Attach: Plasticity Index Test Results
label | e256163d-1ed1-5279-90b7-cba61a07fd1c |  | note | Method - Document Review Visual
label | 24151009-3994-545d-a44b-f41ef9503805 |  | note | Frequency - Where applicable, each lot
label | fa52ae73-6caa-5aad-899e-113b3bfc9dfb |  | note | Category - IP
label | 80e60191-9eb2-5cab-8a1d-345894ad9392 |  | note | Responsibility - SE/PE/SPE
label | 639d3594-e6b2-5029-b625-7c1a1577d3b8 |  | note | Verifying Documents - This ITP
text | 3eec24f6-2538-5d80-9a92-ae28f5bdcc51 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | 38b93616-edeb-579e-945c-634f2144ee49 |  | note | Reference - MRPA Quality Management Plan
label | 5e00a63e-6058-52c9-a3bd-b22dc14a4817 |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 8507445f-95c8-5737-a19e-693199087aa2 |  | note | Method - Document Review
label | 23710aec-4936-5976-9848-f84f4c7c3189 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | 7293f30d-fa98-517e-bcd2-0d78c7c112eb |  | note | Category - HP*
label | 2af336b1-d616-5076-b724-25c43dd7921d |  | note | Responsibility - SE/PE/SPE
label | 125f75b5-bd34-54d9-9b47-16d00080a640 |  | note | Verifying Documents - This ITP
text | 147b3f27-eda9-513f-9382-e35fb702d45d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 1499b424-1495-5e1a-b009-4984189b61ff |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8b1c14ed-ef69-5149-afb1-c8e34856f169 |  | textbox | Print Name:
text | 39e4bbd5-4106-5ec3-b5ed-cdab2f7f5b56 |  | textbox | Position:
text | ec4969ca-e27a-5bdc-be1e-1369a810a337 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-RAIL-PedeStrail Crossing Install Rev 0 | itp |  |  |  | Yes | ITP-RAIL-PedeStrail Crossing Install Rev 0 | ba11ea26-c4fb-4767-b53d-69892b3670dc
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | a3e63626-2c99-4574-b15a-fb766ae4c835 |  | note | Document Title: ITP-Rail-PedeStrail Crossing Install
label | 2527ee2a-38b1-4f50-8425-c9f3e31929bd |  | note | ITP Description: PedeStrail Crossing Install
label | 1c1d48a2-ebf2-4d0c-8ba0-ef7faa24edbf |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
label | cb07e0bc-3441-4432-9536-e6d3cb724f68 |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | 1cc297e2-3f26-495c-833d-594c99d98046 |  | note | Revision Number: 0
label | 3b9feb62-b757-4902-958b-bd9a24f5c12e |  | note | Revision Date: 6/07/2020
label | 5ce283e8-1bd5-45a8-9a2e-eea95aa28b06 |  | note | ITP created by: Mathew Holm
label | bb979dad-221c-4c0b-a2e0-0c305a705d3c |  | note | ITP approved for use by: Romualdo Magpantay
label | 131b7fc7-c339-446d-8a65-523499a82169 |  | note | 1.1 MTSP 030100-01
label | b81e12a6-595b-4033-83c2-4de5eb87539c |  | note | 1.2 MTST 000002-01
label | 43df928e-1441-41c1-b1c2-6b5b6b243b60 |  | note | 1.3 VRIOGS 003.2-2006
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain and submit Material Certificate of Compliance for PedeStrail Rubber units
label | 3f4390c8-6561-4583-82d4-aff02b00de41 |  | note | REFERENCE: IFC Drawing
label | e9b7fd5d-193a-4b22-8339-cf5101e53c42 |  | note | ---------------------------------
label | 7f6b98ec-ec3c-4c4b-9a43-1ec4373ad252 |  | note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | 8599f469-1592-4ef2-96d8-81cee123a3f5 |  | note | Attatch: Photo Rubber Sleeper
label | 6ce65784-2b5d-4756-af73-2274c304ecc6 |  | note | ---------------------------------
label | f41fd516-d060-43bd-8baa-5b3d773cd34e |  | note | METHOD: Review Document
label | 2b133ca6-885d-4d75-9e8c-7b8c5e20f65d |  | note | ---------------------------------
label | 1caf230e-54c0-4692-aa00-0ca01b3807da |  | note | FREQUENCY: Once
label | 34099a46-565e-45f2-8869-255ec8fd096a |  | note | ---------------------------------
label | d1d4f960-70dd-4710-8c73-50642e7c8bec |  | note | CATEGORY: HP
label | 3f979755-5ca8-4dd4-9a58-91bb66e0140f |  | note | ---------------------------------
label | 6063ab90-0887-48d1-90ed-127c6957293e |  | note | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
label | 49552050-0a9e-4094-9c92-63f91d6c91cb |  | note | ---------------------------------
label | 28efeee1-904d-4dcf-b81c-fde39305114e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e4c614ab-147d-443b-b188-6351cee5ef9f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Obtain and submit Material Certificate of Compliance for all metal components including fitting & uppurtences(Rodding and T-Beams)Strail & accosiated jewellery, Equal Angle, etc.Surface treatment
label | 1b6ffce8-e933-433c-a933-0b7fda8c128d |  | note | REFERENCE: IFC Drawing
label | 29003bb2-25c3-4d4e-bd95-eefb656cdf9d |  | note | ---------------------------------
label | df9e4552-5e44-4157-84a0-5e5dc2025674 |  | note | ACCEPTANCE CRITERIA: No damage or rust on components
label | 738d682c-11ee-48e6-89b3-539a6300e4ca |  | note | Validate total number and type of compoents matches drawing
label | 40962c79-8137-4a8a-9f3b-cdc6f86ea809 |  | note | Attatch: Photo metral components
label | e507a21a-ccd3-406d-8033-e509dc23dbf0 |  | note | ---------------------------------
label | 4bd5d039-285b-44fa-98c3-dc7706b8afb1 |  | note | METHOD: Review Document
label | 1115ac65-b88b-4885-a136-366ad823a807 |  | note | ---------------------------------
label | 5e55fe05-3f1b-4ad4-8f5b-ed17ca2c594d |  | note | FREQUENCY: Once
label | 2a411ed9-da93-4b4e-9271-fa87d92176a0 |  | note | ---------------------------------
label | da6a01ae-147f-4153-95e4-a6ee00d28016 |  | note | CATEGORY: HP
label | a67caaec-5869-40e7-9fb5-95a565a7a601 |  | note | ---------------------------------
label | c96ad556-7132-46f3-a451-641cb5bafc62 |  | note | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
label | 37db5a4a-8e3d-46d9-8c94-3b650326f451 |  | note | ---------------------------------
label | 59c48fd1-55e0-43bb-9e06-0bffde7854d1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 38c8dc62-0b6c-47f4-aee7-d39174769a9f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Inspect supplied items upon delivery
label | 5a159b3c-13e7-4213-a05d-51aba7746fb7 |  | note | REFERENCE: IFC Drawing
label | ac886dea-3bd0-4b2a-ac53-ab85e9719978 |  | note | ---------------------------------
label | 273e79e4-c543-47ae-918b-d8276f990408 |  | note | ACCEPTANCE CRITERIA: No damage or rust on components
label | 8d041753-53dd-4e91-8277-0face6e7db36 |  | note | Validate total number and type of compoents matches drawing
label | c06474f6-3f36-4bed-9689-56a2cac6cd85 |  | note | Attatch: Photo Rubber Sleeper,metal components
label | 16e7024c-9029-4276-abdb-d4ec1fb01264 |  | note | ---------------------------------
label | 092fdd9a-0b6c-4a0a-a0f3-74574c8249ae |  | note | METHOD: Visual Measure
label | 99dbadf1-63b9-49dc-a1dc-93250f9f0bfa |  | note | ---------------------------------
label | dc87e547-b3fa-4ef6-8938-31f25bdb7239 |  | note | FREQUENCY: Per delivery
label | def43b0e-9568-4444-81a3-5eb65086666c |  | note | ---------------------------------
label | 48c9998a-1dcb-4263-84bf-bd36385c586d |  | note | CATEGORY: IP
label | 85758497-191e-4e2d-99d6-4bb2e2c16999 |  | note | ---------------------------------
label | ecfcf9d3-02f0-475e-9b43-edee4b82ab2d |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 3e2b121b-b3db-4770-a3dc-4d3aa2cfb5a4 |  | note | ---------------------------------
label | 7855268d-a972-4997-b443-2585b956ef34 |  | note | VERIFYING DOCUMENTS: Material Inspection Report
text | df31ca48-364b-405c-869f-8a24b843b03a |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Inspection of Existing Track Condition
label | 07e7cd1c-bf8a-45c3-9916-acdbd2eeb75b |  | note | REFERENCE: MTM Product Type Approval Certificate
label | 0a003653-f437-44b8-953c-b7336f459f78 |  | note | MTSP 030100-01
label | c47dad01-a758-4fdb-93c6-3b9ff4734b0c |  | note | Appendix 1 Table
label | a210993a-6fdb-4cdd-bb65-ff7fe1a290f1 |  | note | MTST 000002-01
label | 1842f31f-338c-4006-aab8-b370bb6e46fe |  | note | ---------------------------------
label | 7a74aca2-440e-43bd-b973-2557d14cea56 |  | note | ACCEPTANCE CRITERIA: Correct Rail Weight (60lkg/m)
label | a30bf842-36d6-4649-8076-4d5da4dd35da |  | note | Rail Defect Free (Surface/Internal)
label | 70da5480-a44a-48f8-8c23-930b6063a77d |  | note | Track Geometry Defect Free
label | 35bd4bf3-a874-4081-9236-91d8b56791b9 |  | note | Wide gauge < 12mm from design
label | 7a73e4ec-9847-46e1-8a6e-d3ca63232565 |  | note | Tight gauge <-8mm from design
label | 90fe4ab3-ef71-417f-924c-b47f28329db3 |  | note | Cant <25mm from design
label | 7cc517b1-a0b5-48cd-9c84-547dbac75fab |  | note | Twist (3.5m) < 15mm from design
label | f4f7014c-0d5a-4f14-8a7b-198409f11a23 |  | note | Twist (10m) < 30mm from design
label | 74069552-58ef-4553-bc78-20753196c4bc |  | note | Top <20mm from design
label | 806babc1-7f92-4c60-8dae-bb1490f36963 |  | note | Line <18mm from design
label | 1eda5c1b-0a2d-4d94-899c-edab30b5b081 |  | note | Sleeper Spacing @ 600mm c/c
label | 6151dc5e-9805-44f6-aabe-a5d372db78ab |  | note | Ballast shoulder 450mm wide 1:4 fall
label | 24d63979-e722-4880-b3b8-ac85b08497af |  | note | Top of sleeper free from ballast
label | 1cbdd7c3-aac1-423d-a7ba-41d34423ef81 |  | note | Attatch: Track Measurement Sheet, photo site photo, photo sleeper spacing measurment, photo ballast shouler measurment
label | 0f6709c7-14de-49af-b3cb-3a1e69b1b652 |  | note | ---------------------------------
label | a45b49bc-cff2-485b-a84f-281acf4372c4 |  | note | METHOD: Visual Measure
label | d01a0dba-a272-4727-adbe-6d26e88691eb |  | note | ---------------------------------
label | 1ef44256-0156-44b6-8597-bd829f13a119 |  | note | FREQUENCY: Per lot
label | 8bb21942-b495-4867-811e-9af2428dc857 |  | note | ---------------------------------
label | e817e37f-55d1-4c1a-b858-cd871100fc0c |  | note | CATEGORY: IP
label | ed95c4ce-0165-438a-b130-5ccef69fb95d |  | note | ---------------------------------
label | 2d5c32fe-e7b2-49fc-9dce-f9b95065ed26 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 3603261f-c1c6-42f7-a966-b4a685bacb37 |  | note | ---------------------------------
label | 2365cc00-cb11-4edd-8ffd-51170690b0cf |  | note | VERIFYING DOCUMENTS: This ITP
text | 394a93ad-4082-496c-b59d-14ea01c1c814 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Layout of Rubber Panel Units
label | 235d08e8-0256-477b-a133-91377e5b737f |  | note | REFERENCE: Material Installation Instruction
label | 53090537-e065-41a0-910b-e07d5c1da37f |  | note | Material Standard Design Drawing
label | bcb61512-b7f7-4a24-ad80-9fa1d35b7dac |  | note | ---------------------------------
label | 058a3aa0-09f6-45ae-9771-1998d880762b |  | note | ACCEPTANCE CRITERIA: Survey Check that panels are placed in correct location
label | 49114607-dde1-4125-a416-12e0232ffcc9 |  | note | Validation that components are placed in correct position (I,e outer rail panels and inner rail panels)
label | 6a6d42c5-e80d-4470-a6d5-db4a97835276 |  | note | ---------------------------------
label | 613fdc32-20e8-4572-a332-88440aa1f27e |  | note | METHOD: Visual Measure
label | 0f58c3e0-3857-4900-9978-cdb08de0323b |  | note | ---------------------------------
label | 57f43219-9790-450a-ad49-79dd2812cffc |  | note | FREQUENCY: Per lot
label | 4639f707-1d51-47b9-95ef-5c24d1129aff |  | note | ---------------------------------
label | 56dcad0c-95a3-4327-8252-7b086cb0bca0 |  | note | CATEGORY: IP
label | 0945be36-ff90-44e4-b2c0-ebf3a1214970 |  | note | ---------------------------------
label | 221a3147-6d94-4b22-a69b-7fc2aee46b13 |  | note | RESPONSIBILITY: Track Supervisor Surveyor
label | ac76bf45-275b-46d6-bb8f-dd854e3806c1 |  | note | ---------------------------------
label | 08dba8d8-4b45-45a9-9e72-58d28f7a086b |  | note | VERIFYING DOCUMENTS: This ITP
text | 699cc926-de4f-41f9-ad01-552e228fa272 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Installation of metal rodding and T Beams
label | d3c1c400-9f19-47ca-a1b1-d08d57871139 |  | note | REFERENCE: Material Installation Instruction
label | 68a63d67-4b30-47f1-94e1-d7ebcb7c8be0 |  | note | Material Standard Design Drawing
label | beec7b9b-52f2-4c01-b0e3-97d23658898e |  | note | ---------------------------------
label | 7fd2b9ed-fe3f-43a5-93ee-8274c5f07c0a |  | note | ACCEPTANCE CRITERIA: Correct rodding compoents installed through rubber panels
label | 80c6c63a-3a55-4b56-bb25-e6b224826c01 |  | note | Rodding secured and tightened to rail foot manufacturer torque specs
label | 9e9fa204-e7f1-45a1-8de8-e414e1a30e6f |  | note | T-Beams placed on flat Ballast Surface under out Strail Panels
label | 91928cbf-79bb-4e63-87ab-a4d1f54ce1bc |  | note | Attatch: photol T Beam site layout, rodding rail fastener photo
label | bbdc7417-1769-4de8-b743-3ac01d92f857 |  | note | ---------------------------------
label | 40c7bb94-c42c-4d70-9bc2-ace699d55d6c |  | note | METHOD: Measure Visual Test
label | a3bc9cfc-d379-4a17-a8f4-ae10f62fc307 |  | note | ---------------------------------
label | 0b4f39ba-c9e6-4aac-9214-2fbdc8c9719b |  | note | FREQUENCY: Per lot
label | 2784579e-16a7-4e5d-ac82-e77a52469875 |  | note | ---------------------------------
label | 0340f44c-bad7-4e57-8574-3469ba52c405 |  | note | CATEGORY: IP
label | 6917264b-9e1d-44e9-a5b1-c135615e5208 |  | note | ---------------------------------
label | ba3ae92e-43f8-4a77-8424-55e6cc58d85a |  | note | RESPONSIBILITY: Track Supervisor
label | f14789d5-ee0a-4375-a3b9-bf023428b943 |  | note | ---------------------------------
label | 9440c07c-e51f-4e9a-be6a-27df8994f92f |  | note | VERIFYING DOCUMENTS: This ITP
text | 52c471b2-1d71-4569-942b-2e7bf944667b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Installation of Raised markers
label | 5af19565-9e9e-4189-a5e7-8a5c6be6500c |  | note | REFERENCE: Material Standard Design Drawing
label | 7b54e247-6fa7-4081-9965-d0cce48b98c4 |  | note | TGSI Installation Sheet
label | 06aa8a1d-79ad-4fc8-aae3-5ec370809f35 |  | note | AS1428.4 Appendix D incorp
label | e6eeb294-d8eb-4141-91d3-0b6953516604 |  | note | ---------------------------------
label | a94c37f0-c0a8-4f23-8dea-d2204ed9b823 |  | note | ACCEPTANCE CRITERIA: String Line between pedestrain crib openings either side of tracks for paved marker postioning
label | 3c4f798d-c705-417f-9004-e87953d25e72 |  | note | Paved markers lines layed at 1800mm edge to edge clearance
label | cec7c2ac-ace1-4dd8-86d8-f1cb9d7aa608 |  | note | Clear of train wheel running point
label | d466321b-0ec3-40c7-b039-e0ebc7b74c8f |  | note | Each tile secured with 2x SPAX screws 6 x60
label | 8774c487-12a1-41a6-be9d-16629cb5ceda |  | note | Attatch: Photo Paved marker site Layout
label | 2b741422-f880-4fa4-b7ab-d29e137cc9c8 |  | note | ---------------------------------
label | 62ed2e99-e79c-4f94-b78c-17d9be404561 |  | note | METHOD: Visual Measure
label | fb58991d-94b1-4b7d-8db4-390433a7f69c |  | note | ---------------------------------
label | c7e64861-2bfb-4fc2-b2e3-9e64f773aad3 |  | note | FREQUENCY: Once
label | ed7d4e75-4804-46a5-96f5-455ff8da4636 |  | note | ---------------------------------
label | 17497dee-5745-4c47-8101-8aab5c2aff18 |  | note | CATEGORY: IP
label | 764e451d-6811-4eae-a712-beeb6849ed5d |  | note | ---------------------------------
label | 53e88913-345e-4a41-87f7-3ee7bf48d591 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | a6b97609-a44b-454f-994f-e5306b4be95c |  | note | ---------------------------------
label | d99cbf11-2f7c-446c-b232-62cf9def1e6a |  | note | VERIFYING DOCUMENTS: This ITP
text | 5cdb568a-703c-49cc-ae8b-87350708f7a7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Wearing Course Installation( Geofab, Asphalt Base & wearing couse)If applicable
label | 112cb828-1fa8-4a07-8067-7c69518030a4 |  | note | REFERENCE: L1-CHE-SPE-178
label | 48722c74-6646-42d3-8f0b-d1aa0a122e1e |  | note | L1-CHE-STD-029
label | 156614e7-ee47-4a25-bed0-950359dfaf13 |  | note | VRIOGS 003.2-2006
label | c3e0fb4a-b77f-40b2-9c9b-9cb17c36b9f2 |  | note | ---------------------------------
label | a8e1828d-2cc0-4903-b0cc-3c9d96183e79 |  | note | ACCEPTANCE CRITERIA: Surface Smoothness
label | eb4e5172-94c2-4d95-bf2a-04097f6b5db8 |  | note | The path is to be durable and maintainable asphalt, concrete, rubber or equivalent. It shall be free of potholes with a non-slip surface with levels no greater than ±12mm from the design plane when constructed
label | c0f5fe3c-3f1c-435d-a4ec-1f59cbbd1024 |  | note | ---------------------------------
label | bfaf14f5-4a85-4eb3-bd1b-8685f5ccfd7a |  | note | METHOD: Visual Measure
label | 4fb8b448-2865-4c93-8a6d-809ad414102b |  | note | ---------------------------------
label | b4e9f944-4df3-4be3-94de-5e8049414b79 |  | note | FREQUENCY: Per lot
label | 7f160512-b58c-41a9-a613-af8ee58b1936 |  | note | ---------------------------------
label | b75bf8ef-703f-4f4b-b9d3-97eeae7fc7b2 |  | note | CATEGORY: IP
label | ed1cf580-1d7d-4e8f-bd5a-340f5ea2052f |  | note | ---------------------------------
label | 48e55644-9317-4ca9-a6f7-95ce884292f1 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 0f350910-4aba-4793-bb23-1eac4150e75f |  | note | ---------------------------------
label | 259f33a6-f0ad-42f3-824c-b5c5c807745a |  | note | VERIFYING DOCUMENTS: This ITP
text | 41f6aa36-61fb-4ac3-9cda-40d339ea0d50 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Others Installation if Applicable(Access track,Gates, Bollards) If applicable
label | 5d64e43a-850d-40d9-86b7-3bafd0f952a0 |  | note | REFERENCE: Material Standard Design Drawing
label | 8a2be117-4458-4be4-8dbe-17a8dbb81bbd |  | note | TGSI Installation Sheet
label | 33f7a3a0-5517-4fbc-a2e5-7a91446f716b |  | note | ---------------------------------
label | 15818ea8-0e7d-48db-a964-15574b469d8f |  | note | ACCEPTANCE CRITERIA: NDD foundation or equivalent Design requirement.
label | f9d18658-4f09-4d8c-9704-e61059198b97 |  | note | ---------------------------------
label | 08b016b3-6601-4aa0-a6ad-fb8a1cb92d10 |  | note | METHOD: Visual Measure
label | a4517343-122d-4a73-a4df-b6de1ffea6c0 |  | note | ---------------------------------
label | 0ca9b0ae-4818-4823-b0d5-935fee9065fd |  | note | FREQUENCY: Per lot
label | 89de021d-e9a7-49d7-91b6-8a6b7a497be9 |  | note | ---------------------------------
label | 5326c88b-b499-46d6-92c8-7690ffddf49d |  | note | CATEGORY: IP
label | 99db62d2-75a5-4c35-b9b9-9b866fd83f90 |  | note | ---------------------------------
label | cf6dcca8-3f8b-4c36-917f-988815c15344 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 7ac687e9-4eaa-4c62-a0bd-5571d5cab14f |  | note | ---------------------------------
label | 7f16be8e-7c78-444f-a078-2d39c8ecf2c0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 75d84484-c4f1-4e06-80cc-27999e4a7001 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 As-built Survey
label | 766cabe2-34eb-494a-b831-3826d7caef3d |  | note | REFERENCE: As Built Drawings
label | 9b1e36b0-1dc0-4fbc-9d05-24dd39083579 |  | note | Asset Change form
label | b811b20a-2203-4ad9-a251-6f25917d3b66 |  | note | ---------------------------------
label | 15a8684f-5825-4f6c-a9e1-68c378fcf36d |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | 2f84f2e1-d61c-4807-b291-8058a8b72ac9 |  | note | Attach: Surevy Report, Engineering Asset From
label | 82716862-9974-467b-93d4-d6fe36a0db0a |  | note | ---------------------------------
label | 6c2f9cb6-cc49-455d-806f-de4cf514779b |  | note | METHOD: Survey Document Review
label | 13055a4c-6b3e-42f8-8121-3735590d1cb3 |  | note | ---------------------------------
label | 245e9702-a6fe-45d7-bb15-2527fd4dd6a2 |  | note | FREQUENCY: Per lot
label | 61df7f8a-1231-451c-a106-2a2f5559b159 |  | note | ---------------------------------
label | c339a84f-828b-4720-8f5e-d18f0cbac6ef |  | note | CATEGORY: IP
label | 78d57809-c57d-4f55-903d-2bbc8dd524f0 |  | note | ---------------------------------
label | ef7caed8-8170-4cee-9a32-7777f5d04b3f |  | note | RESPONSIBILITY: Surveyor Site/Project Engineer
label | fcc740ba-ea39-47ba-9275-c999c1a7eaf1 |  | note | ---------------------------------
label | 02a494d0-6c98-431d-b385-59f2b09a81f4 |  | note | VERIFYING DOCUMENTS: This ITP
text | d9685e14-8a22-4c3a-abf2-1dd9d1391dda |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Track Certification
label | ce66f67d-ac27-403b-9348-c86f108eee69 |  | note | REFERENCE: MTMF020000-1 – Track Form A T
label | cde60245-2eb7-4f2f-9469-9de5e10d8b56 |  | note | MTMF020000-2 – Track Form B
label | 0f94a1f6-2e83-4270-851d-855ec65370c1 |  | note | ---------------------------------
label | 13ba5843-9b55-42fe-a090-009db3f6f710 |  | note | ACCEPTANCE CRITERIA: Attach : Track Geometry Conformance Certificate
label | 1b778901-70f6-410f-9253-a4f7c6a8cd53 |  | note | Attatch: Track System and Component Conformance Certificate
label | 01f39226-1db5-44e9-83f4-c7457e17d126 |  | note | Attatch: Before/After Photo of worksite
label | 6624d12c-f801-4081-aa71-972d380e3f2e |  | note | ---------------------------------
label | 27b8ce93-8dff-444f-be14-20b0732fbc6b |  | note | METHOD: Visual Measure Doument Reivew
label | 1472155c-0f08-49ea-89d9-5002a18e57f1 |  | note | ---------------------------------
label | ac048014-bc21-4297-8808-238a4032c62d |  | note | FREQUENCY: Once when all occupation works complete
label | 7ab88241-94d4-4d43-87bc-f2a29748d22b |  | note | ---------------------------------
label | e480f891-86d8-42bb-a529-c7801c4e1314 |  | note | CATEGORY: HP
label | 987a042d-3481-4b7e-bd0e-013edd7031b1 |  | note | ---------------------------------
label | c187e7a5-4359-43c8-ad16-0d10fa72596a |  | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | 0d5c09c1-93f4-46a8-9ec6-3ad15dc0e933 |  | note | ---------------------------------
label | 37bafb36-80c3-43b7-b6fc-bf3dc549584b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c54daa77-816e-4e8b-ab22-fee3567178c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | b4918659-03b1-4311-82e7-f8f60f22158e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 490d516b-be89-4d03-aff6-d9a160be54c3 |  | textbox | Name:
text | cee2ce27-66f4-46d6-ab2d-93b9ad32ea43 |  | textbox | Position:
text | e37f362d-2fa1-4184-a8f1-259ff37fea29 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Traffic Signals - Commission (Supply and Install) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Traffic Signals - Commission (Supply and Install) Rev 0 | bc24e7e6-3365-4194-b2fe-9cd07b766860
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | b4f42382-0db5-401b-9133-805721d940c2 |  | note | Document Title: ITP-CIV Traffic Signals - Commission (Supply and Install)
label | 69d04ac8-4d91-4e94-a88c-47fa16367c92 |  | note | ITP Description: Traffic Signals - Commission (Supply and Install)
label | 65373824-aa90-4213-9a05-1b24825f74c8 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 6bb44810-9f17-46ae-bd97-d39b53e6e9f1 |  | note | Revision Number: 0
label | 219184bf-44c4-4d4e-8454-daac4320c9e2 |  | note | Revision Date: 20/08/20
label | dd83f0d9-b376-40c9-ac66-070c439873e7 |  | note | ITP created by: Saaf El-Zubaidi
label | 48eee85f-f306-45f0-ae31-18936bf03fa0 |  | note | ITP approved for use by: Josie Pavlou
label | d705de5e-50f6-4519-9652-1eca84b8e671 |  | note | 1.1 VicRoads Section 730 October 2013
label | c6f03590-7c5f-43f1-971e-451c4dd774cf |  | note | 1.2 AS3000
checkpoint-group |  |  | section | Signalling Electrical System
checkpoint-status |  |  | checkpoint | 2.1 Point of Supply
label | 93a9e811-b5f7-4999-ab1d-1bb34586a09d |  | note | REFERENCE: Section 730.14 (a)
label | 36ccd713-139a-4aea-a6e3-99a943c43da5 |  | note | SD TC-1207
label | e6d3bd01-68e2-4a0f-9816-45ca5f0b4b44 |  | note | ---------------------------------
label | 8ccaa529-3755-4185-9354-0cab0519aacd |  | note | ACCEPTANCE CRITERIA: The Contractor shall arrange for the installation of the point of supply with the local power distribution company, at the location approved at the pre-installation meeting
label | 50c5b691-6394-4a4b-8bc2-5eeac487398b |  | note | The point of supply shall be installed in accordance with SD TC-1206 and arranged with the local power distribution company to meet the specific requirements.
label | 9fc2f15f-1d02-4830-a609-0d7698927b29 |  | note | ---------------------------------
label | 573f41e0-b997-4bbb-945b-b306790f0efe |  | note | METHOD: Review
label | 09fad812-ed5a-4a2a-aa1b-a8a4f139c24b |  | note | ---------------------------------
label | 6bcfec23-57e2-4c8e-bcd5-de8a6e9ddd5a |  | note | FREQUENCY: Per item
label | be08ad56-bea3-4f41-9fbe-4d9e761909d2 |  | note | ---------------------------------
label | f761429f-9904-49c9-a670-7227d042cbf2 |  | note | CATEGORY: IP
label | 4178d08b-f441-4061-9bf4-a85ebbeeb519 |  | note | ---------------------------------
label | 102c040e-a0d7-4da4-9378-3e48ed7ba5e7 |  | note | RESPONSIBILITY: SE/Supervisor
label | 09a440d2-5d0c-4493-81c3-85ef0325500b |  | note | ---------------------------------
label | f4fa9d78-9e2d-4393-8246-77c1d067806d |  | note | VERIFYING DOCUMENTS: This ITP
text | 512010cd-65bd-481a-ae82-880aa0a837a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Communications Line
label | e1b61b29-cd53-49df-842f-81eeede97175 |  | note | REFERENCE: Section 730.14 (b)
label | 30f71502-2961-409e-9ea8-fdf18d29bc4f |  | note | SD TC-1207
label | 27781ed4-d5fe-4f89-84e7-910293b8595a |  | note | ---------------------------------
label | 9f198c75-c634-4c6d-8765-76ffa6583e46 |  | note | ACCEPTANCE CRITERIA: A communications conduit along with a two pair telecommunications cable is to be installed from the signal controller to the nearest suitable communication supplier's pit as per SD TC-1207
label | 413561ed-d1f1-4398-ba28-ffb1a2d3a88a |  | note | ---------------------------------
label | 64355e1e-d9ea-4fda-a963-684a3fdaafc5 |  | note | METHOD: Visual
label | e2b1625a-e562-4fc2-b1a0-8e8710a26263 |  | note | ---------------------------------
label | e59dfa8f-55fe-4c63-9172-6fc3abf6eefa |  | note | FREQUENCY: Per item
label | af9d4d46-15d4-4537-9e13-fb0486792194 |  | note | ---------------------------------
label | 0f3bf44d-407b-43bd-9a59-91167ab13257 |  | note | CATEGORY: IP
label | e3b45f05-a25a-4c8f-81b7-42873a3dd15d |  | note | ---------------------------------
label | 7f53adf7-7988-473b-a2e5-85dad62549d9 |  | note | RESPONSIBILITY: SE/Supervisor
label | de7b1d57-d512-4208-b0be-ccdc6b5f07b9 |  | note | ---------------------------------
label | 1dce6b06-bfbd-4497-a1c2-65935d181164 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6387ed08-a22b-4d6a-8d44-486099aec7aa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Cable Installation
label | 55b5bac6-0f78-44fc-b558-267ead2b1fa4 |  | note | REFERENCE: Section 730.14 (c)
label | 5bd2dc7f-aa4e-49ed-8a56-b537d622e66b |  | note | ---------------------------------
label | 54f2aa42-f6a2-4343-9c40-e57e37de6146 |  | note | ACCEPTANCE CRITERIA: Site cabling is to be completed in accordance with Section 730.14 (c), ensuring all cables are installed with no damage to sheathing and insulation, restrained at the point of termination (top of pedestal and MA/JUP access points) to ensure minimal stress on terminations, as well as sufficient cable provided to reach 1.5m above the signal controller base
label | ab17a6e9-bd0b-449c-9f1a-9896b296745e |  | note | ---------------------------------
label | 332f4940-c4f6-4816-9599-fc5c60dd6b3e |  | note | METHOD: Visual
label | 30fb375f-d73f-4a43-b022-100ad7b385f7 |  | note | ---------------------------------
label | 09905884-b12b-4c58-a184-32f8811bbfc9 |  | note | FREQUENCY: Per cable
label | 5a674c21-78b4-4f3c-97d3-f253dc53a122 |  | note | ---------------------------------
label | f1639930-394b-47ba-ab43-fd352165b426 |  | note | CATEGORY: IP
label | 34a85070-264f-46fc-b1bf-6e725fb99a6a |  | note | ---------------------------------
label | 4c08c982-663c-4854-9303-e5fa0e8bab30 |  | note | RESPONSIBILITY: SE/Supervisor
label | b76a7651-b81b-4430-991d-788594135d90 |  | note | ---------------------------------
label | 11b7db8e-6788-46f6-907a-0b2760b3d5d7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4c123b25-6145-4ecb-8566-7bd2f44eb7d1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Cable Sizes and Wiring
label | f94439aa-58a1-4261-a38e-1fedd3f4bc78 |  | note | REFERENCE: Section 730.14 (d)
label | c768f08f-7be2-4216-ba3a-55c94f9e5fe7 |  | note | ---------------------------------
label | 9c66f59c-4f7d-4227-a1f5-edf50205b5bb |  | note | ACCEPTANCE CRITERIA: 51 core cable is to be used at intersection traffic signals and its sequential assemblies. 29 (dual carriageway) or 19 (single carriageway) core cable is to be used at pedestrian operated signals and its sequential assemblies
label | 41112382-d4e4-4a3c-9b4f-3e714f54ee60 |  | note | ---------------------------------
label | 24a0a6ed-10aa-42b3-bd1d-b10db6f778a4 |  | note | METHOD: Visual
label | 7fb9229f-ba50-41a6-bf63-19e18637f4e9 |  | note | ---------------------------------
label | b1a04ae4-5c30-4ba7-9e0c-c56c1249b079 |  | note | FREQUENCY: Per cable
label | 4c2519ca-4cee-4bfb-82bc-e108815a2b49 |  | note | ---------------------------------
label | 9143b7b1-8c56-486b-bd70-b1c8ccd0d79f |  | note | CATEGORY: IP
label | 19c31746-4a64-48eb-a310-f14972d96f8a |  | note | ---------------------------------
label | e80be827-9d3c-45d8-accd-85c7e5245adb |  | note | RESPONSIBILITY: SE/Supervisor
label | 9bb36dac-e5f4-409a-91e7-d95751c2845a |  | note | ---------------------------------
label | 669a72f9-2b74-466b-a239-92a14023daf3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6b27041d-1996-4cd4-96fb-abd3f3d9527d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Pedestrian push button terminations
label | a6d2a27e-fd2a-4f70-aff2-075d07218c88 |  | note | REFERENCE: Section 730.14 (e)
label | ac894421-d3c5-44d4-b65f-5f7c7b28ea42 |  | note | Table 730.141
label | 1758b7d2-28c1-41c8-bb39-e298bd850adb |  | note | ---------------------------------
label | 87059a13-0d2b-40f7-a26d-a3548a96c55c |  | note | ACCEPTANCE CRITERIA: Pedestrian push button detectors are to be connected by 5 core cable and terminated at the required locations.
label | 2d4b923f-22c1-4125-9bb7-a1c7c0556c98 |  | note | ---------------------------------
label | 4975f176-69c1-4488-9fd4-6a80495ce714 |  | note | METHOD: Visual
label | 26fd5657-635c-4d7f-9df2-41e87ef5fedc |  | note | ---------------------------------
label | 3e5e4026-bce6-4864-94ae-ceac7cc4d749 |  | note | FREQUENCY: Per cable
label | c27aab80-5bd6-47e2-b015-f577d874df05 |  | note | ---------------------------------
label | 5bf1bf17-c2f6-435e-95a8-453e077ab1ad |  | note | CATEGORY: IP
label | 84ca34cf-083f-4c7d-baae-5fe213a7a719 |  | note | ---------------------------------
label | c5ae4eca-9f67-407c-849f-5bb3c4578599 |  | note | RESPONSIBILITY: SE/Supervisor
label | ad6ad34d-38f6-451d-9ef1-c7029393a1a6 |  | note | ---------------------------------
label | 42ea18c1-2370-4489-bf6d-c13119e2587e |  | note | VERIFYING DOCUMENTS: This ITP
text | b6d1f601-c5ac-43aa-ac8c-091e07301707 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Connecting of traffic signal controller
label | 0c78db1a-23d7-41a3-bb08-3938c3285449 |  | note | REFERENCE: Section 730.14 (f)
label | 6898727c-1137-44f9-923e-10976e66add0 |  | note | ---------------------------------
label | d57674b4-c201-49f7-b165-105ed1c1796a |  | note | ACCEPTANCE CRITERIA: Contractor shall install a 3 core supply cable in a 50mm conduit between the supply point and signal controller base. 1.5m of supply cable shall be coiled in the pit closest to the controller base.
label | cc10ed4d-417e-49fc-b86d-9ba48084c5d6 |  | note | ---------------------------------
label | b013499c-b3cb-4fef-8604-a3bd13620834 |  | note | METHOD: Visual
label | cc3fd7c9-433b-44b0-b910-45ad37b1db1c |  | note | ---------------------------------
label | f751bb04-127a-4a91-88e7-7b8efe564388 |  | note | FREQUENCY: Per cable
label | 7e7bf564-99de-4902-8764-d1b687f92f4c |  | note | ---------------------------------
label | 600bfdb2-8604-4172-aa64-fb24404fc427 |  | note | CATEGORY: IP
label | 67c55c7d-1fb6-43cc-8fb9-54c7c28a6cdc |  | note | ---------------------------------
label | 63685d7c-7696-4378-814e-e707669e4941 |  | note | RESPONSIBILITY: SE/Supervisor
label | 2635a081-3966-456e-992d-16d48bfad36a |  | note | ---------------------------------
label | 7090897a-c8c7-4130-8431-f9db85f84cfd |  | note | VERIFYING DOCUMENTS: This ITP
text | 76f544b9-8fe5-4828-82bf-12f256aaacdb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Testing of Electrical Works
label | 0946999d-66c3-4821-8bba-ba71dc5a257c |  | note | REFERENCE: Section 730.14 (l)
label | 5f689d7d-c4d7-4c58-986d-e22b7fbb754b |  | note | AS3000 Cl 8.3.3
label | 88e04e51-7475-4b87-a33c-0c00d8548bfa |  | note | ---------------------------------
label | 07a33821-ced1-4f87-837b-606e96f4ee0e |  | note | ACCEPTANCE CRITERIA: The following tests are to be carried out prior to the installation of lanterns and hardware:
label | 90d15ab5-0c66-435f-a182-5df4f5540464 |  | note | - continuity of all active, neutral and ELV conductors as well as earthing system.
label | df81adc4-3e78-4bb1-9ef3-97c695b71516 |  | note | Attach: Electrical Test Report
label | ad95ab82-192c-48ac-a6bf-077e96e3317a |  | note | Following the installation of all lanterns and hardware, the Contractor shall carry out a flash test.
label | 08361bce-a356-4046-8a20-00edb447ee83 |  | note | ---------------------------------
label | 65c21046-8f90-436f-8fa4-82017df93d49 |  | note | METHOD: Records
label | 6d65651b-c9ab-4abd-a22a-213659469f0e |  | note | ---------------------------------
label | 01f7da0d-3ad9-4554-bd24-b4134b317c33 |  | note | FREQUENCY: Per installation
label | e960e93d-0762-45c2-83e7-ac8dd164e7b7 |  | note | ---------------------------------
label | 35092b40-e3d1-429f-97f2-cc261dd2c85c |  | note | CATEGORY: HP*
label | 4505540e-0ef2-4ec5-9161-9cb4c8d43ed4 |  | note | ---------------------------------
label | e4750cfc-6b39-485a-a4ee-151804a0d67c |  | note | RESPONSIBILITY: SE/Supervisor
label | 951efd4f-6533-4d8d-b20a-11fe902312ce |  | note | ---------------------------------
label | 80ff0a48-2e1d-4e0e-b084-e2b13cf872fc |  | note | VERIFYING DOCUMENTS: Electrical Test Report
text | 4597058c-ce2d-4d32-ba0d-56d63dbffad0 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Detector Loop Installation
checkpoint-status |  |  | checkpoint | 3.1 Cutting of detector loops
label | 03c659e1-bd62-429a-af42-f574b8cc482b |  | note | REFERENCE: Section 730.14 (j)
label | 79ce4047-9378-422a-9fcf-301a6ff2b2d5 |  | note | VicRoads TCS 054
label | 466dfc84-ed73-444a-992f-dcd26bae0ca7 |  | note | ---------------------------------
label | 15b54908-fd86-49c5-ad20-6b304a83541e |  | note | ACCEPTANCE CRITERIA: Detector loops are to be cut as per the locations shown on the design drawings to the TCS 054 specification.
label | 52a8a47a-c02d-44e5-8d70-5f2e2b53ab4c |  | note | ---------------------------------
label | f231e0e1-fbf3-495c-ab1d-bd1df63ad185 |  | note | METHOD: Visual
label | 988d016c-57a9-45d4-b338-9007ea814e11 |  | note | ---------------------------------
label | 19f28964-ba3c-436d-a3dd-6d7e72ec702e |  | note | FREQUENCY: Per loop
label | ee8a584a-5ef0-45fc-8dbe-7954fdf5de31 |  | note | ---------------------------------
label | 355227d4-453b-4958-aedf-89bbcc832fe0 |  | note | CATEGORY: IP
label | 0d78cc33-016f-4191-913b-7d63d12fbd72 |  | note | ---------------------------------
label | 1c490ae6-f302-4bc7-a993-aa27def1082d |  | note | RESPONSIBILITY: SE/Supervisor
label | 4d947fc0-5b08-41c9-af62-d12be098f4c4 |  | note | ---------------------------------
label | e85618bd-f20e-4e56-a99f-7b525304c5cb |  | note | VERIFYING DOCUMENTS: This ITP
text | 5a4d2a09-f772-456f-8035-b654b67b9e92 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Installation of detector feeder cables
label | c17d7441-8de7-4f6c-813b-3b938670ae57 |  | note | REFERENCE: Section 730.14 (g)
label | 37848ce1-4731-49de-8b48-6d922ce7e991 |  | note | SD TC-1300
label | fb42e704-768d-48f0-ac24-ed896a2917e0 |  | note | ---------------------------------
label | 519b91cf-93cb-4587-b6f1-b24de400c06b |  | note | ACCEPTANCE CRITERIA: Detector feeder cables are to be installed to connect detector loops to the traffic signal controller. Installation is as follows:
label | ae3640d5-f7a0-474d-af67-df82857cd6d2 |  | note | - Install 1 cable per loop and each cable pair shall be clearly and durably marked at both ends to enable positive identification
label | 868a2ce0-e2b9-422b-8d8b-cb4a1ca9f059 |  | note | - Connection of the detector loop cables to the detector feeder cables by soldering
label | 8978ae86-9bb4-4d46-9ae7-9e4c550fd953 |  | note | - 4 wires for each loop (as per SD TC-1300) shall be tied together in a knot close to the conduit end
label | 99874d4d-f779-498d-ad5e-e405e7f3dcc5 |  | note | - Terminations (joined or unjoined) shall be separately insulated and sealed against the ingress of moisture with heat shrink
label | 893429d0-fad0-4381-89e5-7aaa4591cbf5 |  | note | - Detector cables to have sufficient length to allow 1.5m to be coiled in the pit and 1.5m to reach the top of the controller base
label | b1819f5f-554a-4ef6-a2ea-c65541f96fb4 |  | note | - Cable diagram shall be provided once complete and visible to the controller installation contractor detailing the loop cable/feeder cable connections.
label | 9f2bdcf0-94a1-42d9-921b-b82dc10d82a6 |  | note | ---------------------------------
label | 527d7488-0257-453c-8959-08c4dbfeb104 |  | note | METHOD: Visual
label | 4aa4e2e1-8603-4a7c-8c48-161af53905cf |  | note | ---------------------------------
label | f883b997-5176-4521-8a38-4821604570f0 |  | note | FREQUENCY: Per loop
label | 8c652efa-eeff-40da-96c0-f214f748c3c4 |  | note | ---------------------------------
label | 7dfa8a1d-7197-41e8-a2c7-8a469f5dc093 |  | note | CATEGORY: IP
label | 9d3c103d-1647-466a-936a-e518aa7c410b |  | note | ---------------------------------
label | b5aad04b-3e00-4082-bf6d-1409a0d8ca99 |  | note | RESPONSIBILITY: SE/Supervisor
label | 4dceb0ab-b5b4-42e5-931c-c2450c876190 |  | note | ---------------------------------
label | ff09afe0-1652-474b-b4f7-c2ac550ed945 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | b45f21a8-1816-4347-8f17-4e425b447152 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Cabling of Large Sites
label | 28b5e6f8-08e3-4638-a769-9eb8f5b878ab |  | note | REFERENCE: Section 730.14 (i)
label | b3cb4f83-bf53-43bd-a2cf-cc64697bbb47 |  | note | ---------------------------------
label | 392b228a-760e-4f70-b40a-810d67eab8be |  | note | ACCEPTANCE CRITERIA: For large signal installations where the standard allocation of cores as specified in SD TC-1204 cannot readily be adopted, MRPA shall draw up a proposed cabling scheme for approval.
label | 1ac437ae-00fe-47eb-8f90-7d893cbb2ae3 |  | note | Attach: Proposed Cabling Scheme Checklist
label | 1bcade50-d69f-4f54-8da0-aa6378d505da |  | note | ---------------------------------
label | 4a792cdc-82e3-4353-98a9-c18f65b1a4f6 |  | note | METHOD: Records
label | b34a81eb-b729-4680-93a5-9fb1e4c67b82 |  | note | ---------------------------------
label | aae435c0-0765-451e-a594-f4ecdc66a83a |  | note | FREQUENCY: Per installation
label | 1e116e42-2eca-4736-a17d-fe995f73c019 |  | note | ---------------------------------
label | b5525fb6-17ef-47cc-aaf6-872c0526fa94 |  | note | CATEGORY: HP*
label | ecfa98d0-4b26-4bcf-9445-1faa7ab7e99f |  | note | ---------------------------------
label | 658f6403-f424-44ff-b695-f66bb3f035e7 |  | note | RESPONSIBILITY: SE/PE, NA
label | b70c16e5-af8a-4c89-8bf6-58cd52b67577 |  | note | ---------------------------------
label | 116e65ef-8a95-43cd-b187-8be27c6680c1 |  | note | VERIFYING DOCUMENTS: Attach Proposed Cabling Scheme Checklist
text | 0e5319b3-230f-4b2b-9985-88db94b39eba |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-Commissioning
checkpoint-status |  |  | checkpoint | 4.1 Pre-Commissioning Site Inspection
label | 8f629287-142c-45db-9658-8d24fe640be7 |  | note | REFERENCE: Section 730.16 (a)
label | 1fd5b401-9b26-402e-96a8-b8e9fe46b4f4 |  | note | ---------------------------------
label | e03f442f-5ff9-4d94-ba7c-f1c5e4d032a5 |  | note | ACCEPTANCE CRITERIA: Inspection to be carried out between the relevant parties upon completion of the installation works.
label | 5b33632c-9ea4-4215-81c2-8e798c00710d |  | note | The Contractor is to notify NA and VR of the inspection.
label | 27d4d6e7-5544-4ec2-a3ea-02040f255241 |  | note | ---------------------------------
label | 3349f370-962a-4964-8b94-7e9a0bd2d78b |  | note | METHOD: Records
label | ce1bbf47-6ea0-4585-b5b0-6fdf20ea8b75 |  | note | ---------------------------------
label | 2dbde283-0b61-4b80-b4ad-2da21c03c264 |  | note | FREQUENCY: Per installation
label | aa6fba22-4c92-4e60-b98c-106411dd4a20 |  | note | ---------------------------------
label | 6f0b0097-da7b-48dd-9823-b0cbef6f14b3 |  | note | CATEGORY: IP
label | eda53ee4-b274-47e3-808b-511da086462c |  | note | ---------------------------------
label | e26704ae-4281-4897-97f4-11d55c2bcb1e |  | note | RESPONSIBILITY: P/E, NA, Supervisor, VR
label | c4333e71-c52e-4190-ba08-21ef496a48e4 |  | note | ---------------------------------
label | 05066b39-fd82-4fef-95f5-e72088369d63 |  | note | VERIFYING DOCUMENTS: Attach Pre-Commissioning Installation Report
text | 4a70f849-6b1a-494a-b63c-5c6ac38ca0b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Provision of power
label | 4f03b9e2-c325-4dbd-a5d1-e85a989321c8 |  | note | REFERENCE: Section 730.16 (b)
label | 4c251e65-a615-434a-9709-b7b8e2191443 |  | note | ---------------------------------
label | 4f8591c3-1f36-425b-81a6-701392404350 |  | note | ACCEPTANCE CRITERIA: Obtain connection of mains supply by submitting all necessary paperwork and payment of fees.
label | 046aa06f-69a0-4f70-a7f2-a48bea444461 |  | note | ---------------------------------
label | 5c97940c-1a08-42a4-b458-33a115e9f475 |  | note | METHOD: Records
label | 79f8bcf5-c908-4252-8e7f-311ac02be25f |  | note | ---------------------------------
label | 6be4eac5-f9f7-48ea-8a2a-82fa11744744 |  | note | FREQUENCY: Per installation
label | 29985f11-0206-4406-b791-3f7880beb7d0 |  | note | ---------------------------------
label | 4e4dbffb-6747-4fe4-9dbc-3be8195bc453 |  | note | CATEGORY: IP
label | fd15c3d3-325d-4df0-a93e-7be0ef3b9cc2 |  | note | ---------------------------------
label | 6e240770-48ef-49ad-ad5c-6ab7652d7524 |  | note | RESPONSIBILITY: PE, Supervisor
label | 8b662d05-8f42-426a-bbd8-99dd7a9f236d |  | note | ---------------------------------
label | b36d6eed-17db-4a50-a894-38050fa53b14 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e246fff6-f317-49b6-b9f9-89324ee6b5be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Traffic Controller Installation
label | dac012cc-ee09-4bed-a6dc-16c501b422a8 |  | note | REFERENCE: Section 730.16 (c)
label | 053d4e7c-5ed8-443a-882d-26f42d76974f |  | note | ---------------------------------
label | 83295d04-5e0d-4c02-94a6-fa654f5a401c |  | note | ACCEPTANCE CRITERIA: Contractor to notify VR when the site is completed, tested and ready for the traffic signal controller to be installed.
label | 21d2d798-843c-44df-9348-4d83a8e403b0 |  | note | Traffic signal controller to be installed by controller supplier or authorised representative.
label | 62818357-0e17-41cc-b380-09179ec5ae3c |  | note | Contractor shall arrange issuing the Certificate of Electrical Safety and the necessary paperwork to obtain connection.
label | 886e9f80-8ab3-4d10-a722-8d290abcf2b0 |  | note | ---------------------------------
label | bca899be-cc00-42d7-a00b-d484ff759530 |  | note | METHOD: Records
label | 201d3873-77f9-4129-bd1f-b9c21152490e |  | note | ---------------------------------
label | 87b0e782-1974-402b-9966-cb117c13977e |  | note | FREQUENCY: Per installation
label | f8437279-c876-4ff0-b1b6-a51415d92e12 |  | note | ---------------------------------
label | 550a1e14-4690-4502-8706-3fbfc532cbde |  | note | CATEGORY: IP
label | aae131db-9371-4e76-b1e0-52b2049a4a7c |  | note | ---------------------------------
label | 97aab557-daef-4e9b-b52f-0225086338b8 |  | note | RESPONSIBILITY: PE, Supervisor
label | fa21858a-7392-4520-a98b-d7257cad7181 |  | note | ---------------------------------
label | 2eaea7d1-2cbf-4541-84c1-f6f56d7345e2 |  | note | VERIFYING DOCUMENTS: Attached Certificate of Electrical Safety
text | 191462d1-85b8-4c2f-b4dd-a1b98a4cb277 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Completion of Site Works and Commissioning
checkpoint-status |  |  | checkpoint | 5.1 Switch-On
label | d6896169-4b6a-4b0c-9913-c49ad4ad6088 |  | note | REFERENCE: Section 730.17 (a)
label | 0ddfddc0-1d88-43c5-86d0-ed2c753e292e |  | note | ---------------------------------
label | 8b0cb004-3003-4dab-9331-2b624b546bb2 |  | note | ACCEPTANCE CRITERIA: Prior to switching the signals on, a 'flash test' of the installation shall be carried out to ensure that each lantern is connected to the correct cable core. The flash test shall be witnessed by the Nominated Authority and VR and confirmed as acceptable.
label | f2f5ac6c-7d43-4747-ac51-715db866e14c |  | note | The controller supplier is to record the relevant details required for the Electrical Test Report.
label | 7075288a-749c-412e-a9de-ac9c864ef316 |  | note | ---------------------------------
label | e3f6e446-f055-4194-bc1e-a7f68c7ff0a4 |  | note | METHOD: Review
label | af8d7a71-bdda-43ba-87c8-803713e08f23 |  | note | ---------------------------------
label | 73bfd71b-fe15-4170-b834-b75ecd8ad4cc |  | note | FREQUENCY: Per lantern
label | e78e0463-d1c5-47b5-a532-5746a793c02c |  | note | ---------------------------------
label | fc9c3fe6-b573-4f69-82ff-2909558e6ca0 |  | note | CATEGORY: HP*
label | d7268763-6d0d-4e79-958a-7d1b5f65a62f |  | note | ---------------------------------
label | 1ec6eeec-5819-43ec-b41f-0b017199207a |  | note | RESPONSIBILITY: PE, NA, VR, Supervisor
label | 6286f1f9-f549-4dc3-a962-d57671f68b71 |  | note | ---------------------------------
label | b3daeeed-f1c9-4620-8300-42b87dfc5661 |  | note | VERIFYING DOCUMENTS: Attach Electrical Test Report
text | 3bade923-a054-4ffd-b0b0-e4aa8c0129e6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Removal of redundant hardware
label | 9ea72c3a-0ef0-4422-9851-24408cf49c76 |  | note | REFERENCE: Section 730.17 (b)
label | 2116cbd0-443b-4584-ae05-a6a4f8a5f785 |  | note | ---------------------------------
label | 7d16fe51-cbdb-494c-ba22-e2565db2eaf6 |  | note | ACCEPTANCE CRITERIA: All redundant components of hardware and equipment shall be removed unless specified on the design drawings.
label | bda4eb5a-2cb1-4d2f-832a-8c6c42c6308d |  | note | ---------------------------------
label | 54944238-8c6f-41d5-bc86-e30a0cafad64 |  | note | METHOD: Visual
label | 4a0618a6-3dc8-4491-a05e-94d703f85af5 |  | note | ---------------------------------
label | c9cb3be2-691d-4b92-8294-964d0b39eece |  | note | FREQUENCY: Per installation
label | ef312904-1959-4e3b-957f-e65b8fc3c22b |  | note | ---------------------------------
label | 8174d22e-e62b-4cf1-93ae-a3b1cd45d8ee |  | note | CATEGORY: IP
label | 389f5e99-96f9-4455-97dd-31f66a4cbca5 |  | note | ---------------------------------
label | 47a3e5ee-3d9e-4c44-a458-922115803a46 |  | note | RESPONSIBILITY: SE/Supervisor
label | e9f92ebd-0600-4a16-9ffc-aead3b37f256 |  | note | ---------------------------------
text | 701caeaf-460a-4952-9106-439f633d4ea2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Survey as-built
label | e199f544-31b6-4972-ada1-b0be7e4e2c79 |  | note | REFERENCE: IFC Drawings
label | b0a4aca4-8665-4c67-97fa-b9a2450b980a |  | note | ---------------------------------
label | 1681c87c-3ea3-4fc0-a66d-b765adb465c9 |  | note | ACCEPTANCE CRITERIA: Survey to As Built Traffic Signalling works.
label | a5dd9942-6b17-4978-be54-db4d5986e30f |  | note | As Constructed Traffic Signal plan to be submitted to Vic Roads.
label | cbc434e7-61d9-4850-92fc-1aab968bd264 |  | note | ---------------------------------
label | 01fe32b6-d15d-4d22-9394-dc50cb0f1782 |  | note | METHOD: Document Review
label | 581e2ccd-32da-4f32-a293-26d6682b8b98 |  | note | ---------------------------------
label | 90ea23ec-7b6e-49be-829c-b0dfd1b75438 |  | note | FREQUENCY: Each element
label | 58eebaf9-7fe0-470c-b9b2-8e55091e5532 |  | note | ---------------------------------
label | f97aa5ca-8b71-43b2-a5d5-6a38925ed775 |  | note | CATEGORY: IP
label | 41655ee3-d4ab-49e9-a7c9-35acef675ded |  | note | ---------------------------------
label | a065ce7d-6d78-43aa-9dec-5a303f8b2fef |  | note | RESPONSIBILITY: SE/Surveyor
label | 12ea3e87-1a8b-4d75-9c5a-96bb46642a9d |  | note | ---------------------------------
label | 1335be36-da39-4832-af5f-c2264efdf04d |  | note | VERIFYING DOCUMENTS: Attach As Constructed Traffic Signal plan
text | da683118-8008-4c8b-b356-83998870ee83 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 8e26eff6-3c40-4b75-93b0-ee730dd13254 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8cf382f9-4bb9-44b0-a064-34d8f54e7110 |  | textbox | Name:
text | a3372f0a-f7c8-4646-baad-8c07e07037b5 |  | textbox | Position:
text | 0b5051e0-4f06-4330-bc7f-171579949ef2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Horizontal Directional Drilling (V-Line) Rev 0 |  |  |  |  | Yes | ITP-CIV-Horizontal Directional Drilling (V-Line) Rev 0 | c0f433ca-a829-466e-b027-ca6db875104d
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 2b3a785d-40a5-42f8-91cd-56e337823d1c |  | note | Document Title: HDD - VicTrack and CSR
label | 5c2286ea-a659-4bb8-b3d6-a9b6cb883bb3 |  | note | ITP Description: Horizontal Directional Drilling (V/Line)
label | 21909910-0906-4885-9e84-e6bf3bbcf7f5 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 1854f343-0480-4784-9c26-d20711aa2a22 |  | note | Revision Number: 0
label | 6799c731-fc25-4e5a-a49c-e61a2579fb12 |  | note | Revision Date: 22/02/21
label | b66da7e0-7496-4113-a44e-c2c7f0684d36 |  | note | ITP created by: Tom Hudson
label | db3db34a-077e-4660-a575-c511e6b25a2e |  | note | ITP approved for use by: Josie Pavlou
label | 2498eefa-e215-44c9-bd53-7e24c1fcd867 |  | note | 1.1 AS 4799-2009 Installation of underground utility services ad pipelines within railway boundaries
label | bd13dc7a-1f62-461d-b558-e6abfc393ad6 |  | note | 1.2 NIST 2076 Inspection and Assessement - Track Geometry - V/Line
label | 464b21b3-552c-40b5-aea3-429da9597854 |  | note | 1.3 D/17/62901 Design Requirements & Guidelines - Civil Works on, under or over VicTrack Land
label | d6221f2c-370f-4be5-abdf-4ab4d9b6bc82 |  | note | 1.4 NIST 012.2 - Specification for Signalling Supply, Construciton and Installation (V/Line)
label | bf84eac0-20ef-44c5-ae91-5dcfd5df34bc |  | note | 1.5 NIST 012.2.1 - Standard for Construction of Cable Route and Signalling Civil Works (V/Line)
label | ddc602b7-a09d-4794-a418-b41c88960431 |  | note | 1.6 NIST-2706 - Inspeciton and Assessment Track Geometry (V/Line)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Pipe Sleeve
label | 4fd03472-338c-43cf-b2a9-5c6c8188e4f8 |  | note | REFERENCE: IFC Drawings
label | bb4e520f-1ec2-4b59-af0d-7c4bfd8f1258 |  | note | ACCEPTANCE CRITERIA: Confirm that sleeve pipe matches the material specified on the IFC drawings.
label | ce4a56c3-7eeb-4852-b379-f134c1dce64c |  | note | Obtain approval from VicTrack for sleeve material prior to construction.
label | f78d524f-e572-4bc6-b975-dff05aa9d165 |  | note | METHOD: Document Review
label | dde68321-6046-4074-83eb-a6601dc567eb |  | note | FREQUENCY: Prior to Commencement
label | b4b5588c-a3e4-47a5-935f-7827b48440a3 |  | note | CATEGORY: HP
label | 599aae7b-34a3-44de-9865-60b07e6895d4 |  | note | RESPONSIBILITY: SE
label | 4ed1f3b0-2dde-4fac-9dc9-666e68e92a15 |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate
text | 5d8d0f45-f7c2-44f7-87af-07e70cfbbc51 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Materials - Draw ropes
label | e37ab93a-5e0c-42ed-b2d5-1ca18dc1408d |  | note | REFERENCE: IFC Drawings
label | 37b413bb-ee2e-45f2-913b-639f6d3e08b7 |  | note | ACCEPTANCE CRITERIA: All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
label | 63c0f4cc-bcf9-43cb-9cf0-e536ea1373a4 |  | note | METHOD: Document review/ Visual
label | d128f98a-0540-461b-991c-cd14d707df67 |  | note | FREQUENCY: Prior to commencement
label | bb03385e-007c-430c-b4a2-50d3e7af66fd |  | note | CATEGORY: HP
label | da708877-c35a-4444-ba7f-fc45849d92a0 |  | note | RESPONSIBILITY: PE/SE
label | 6d814b0d-bd78-4851-920e-5e867ec8b2db |  | note | VERIFYING DOCUMENTS: Material compliance certificate
text | 8e4e7982-1aee-4592-b610-fabd3b99bc34 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Materials - Communication conduits (victrack), Signalling Conduits
label | c930bbc3-11f1-4d16-bfb8-faa0adbcc0a2 |  | note | REFERENCE: IFC Drawings/ TS-SP-013
label | 72e1c0bc-ccd3-4077-a382-4c72d028eeb7 |  | note | ACCEPTANCE CRITERIA: Victrack conduits must be min internal dia 100mm.
label | 9feb4b14-087a-4c52-af85-91c34ff26607 |  | note | Outside of the conduits must be marked with Communications or Victrack communications.
label | fd86687c-acb4-4134-8ffe-41c42df76646 |  | note | Bored conduits must be Class 9 HDPE.
label | 9822b7dc-42cc-47a9-9d3a-18e1b7445d73 |  | note | Signalling conduits must be min 100mm internal dia. heavy duty rigid UPVC conduits to AS 3000
label | 7776acfc-ca8a-47ab-9ab0-bc30ce5c27a8 |  | note | METHOD: Document review/ Visual
label | 65014103-7ca0-44a3-86a6-4941fd18f512 |  | note | FREQUENCY: Prior to commencement
label | 6bc8d6b4-a7e0-42c0-bbb0-c67376287c08 |  | note | CATEGORY: HP
label | 05ba20dd-58bd-4ef0-a45b-b1bc2f6ac633 |  | note | RESPONSIBILITY: SE/PE/SPE
label | eb245c4c-b6c9-47d3-ae72-3ab9809427ba |  | note | VERIFYING DOCUMENTS: This ITP/ Material compliance certificate.
text | 7610fa5c-d731-4837-8231-d91e3f0028b2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Materials - Grout (if applicable)
label | 2c87fa92-9dc8-4aea-924a-f467d5cbaadb |  | note | REFERENCE: IFC Drawings
label | ecf90f5e-24ab-4cb7-8b0b-b7187d6d9880 |  | note | ACCEPTANCE CRITERIA: Grout strength to be 40MPa
label | 45efe914-daa6-49d3-80cc-2c8c39be2a93 |  | note | Grout shall be a high flow, cementitious material.
label | dc38e1fc-ea22-437d-a252-82187fa84307 |  | note | METHOD: Document Review
label | 9d2575b9-c643-4d11-965c-936e7fbe460c |  | note | FREQUENCY: Prior to Commencement
label | 7264d4f8-2394-4b11-ae61-780079c978aa |  | note | CATEGORY: HP*
label | bfbf11e7-65be-47ef-a4cb-98fb577cd5a7 |  | note | RESPONSIBILITY: SE
label | 6be859b6-91e0-4998-96fc-3b7f61735993 |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate and TDS
text | d618a85f-a016-4109-8d02-486c05f3a626 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Drilling Fluids
label | c5812a86-89f7-4a63-bf9a-bede56d55936 |  | note | REFERENCE: IFC Drawings
label | cce9d10a-e5c8-48bd-bc33-438e84d09a9a |  | note | ACCEPTANCE CRITERIA: Drilling fluids must be of the polymer variety, Bentonite shall onot be used as a drilling fluid.
label | 8272a40d-e6b9-40e8-8c9b-74b369a5801b |  | note | METHOD: Document Review
label | aaafcd0e-f8f6-422d-be48-15902e452b0e |  | note | FREQUENCY: Prior to Commencement
label | 0d92b33f-050f-4eb3-a2ff-a10220b2952a |  | note | CATEGORY: WP
label | 3a1f1ec4-a410-47e5-ab07-65650c5f8198 |  | note | RESPONSIBILITY: SE
label | d1953116-81de-445f-ad78-9f3c7696a246 |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate
text | 282af31b-4cb3-4d2d-8fd7-3c3765b7e1de |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Marker Post and Marker Plate (if applicable)
label | 69328eae-187b-4db1-852f-7323d316651d |  | note | REFERENCE: IFC Drawings
label | a51cfb1c-7292-48b4-8a34-e5fd51ab2384 |  | note | AS4799-2000
label | 9782a501-4203-4466-bdbb-710c3ed1af47 |  | note | ACCEPTANCE CRITERIA: Be of non-combustible material for the marker plates and of at least fire-resistant material for the pole.
label | 3c5201f4-fc1c-4c38-b216-d62e12efd405 |  | note | METHOD: Document Review
label | ec826b89-d1b8-4a11-abbb-c0ebfdec4e76 |  | note | FREQUENCY: Prior to Commencement
label | 672f5452-d8aa-40d2-84d1-83360a600794 |  | note | CATEGORY: WP
label | 6c2a108e-3ec4-402e-b2c1-11f1e73e0dc2 |  | note | RESPONSIBILITY: SE
label | d64d4f3b-4bc8-48fc-910a-1f04e74f6ff9 |  | note | VERIFYING DOCUMENTS: Material Compliance Certificate
text | e5a97f41-21a6-457d-8930-c20bc2bdc3d3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Poly Welding Qualification (if applicable)
label | c354a048-1c6d-4706-a436-5d6dc1ee346e |  | note | REFERENCE: IFC Drawings
label | 9d252a4c-02fc-4f9b-8a99-7982eef42be2 |  | note | ACCEPTANCE CRITERIA: HDPE welder qualifications to be supplied
label | 2196f460-535a-4707-ab28-46d2b754125b |  | note | METHOD: Document Review
label | b467f649-76c3-4884-83cb-e20d4159a73e |  | note | FREQUENCY: Prior to Commencement
label | f3e69d07-ba44-4673-967e-0734901d4ef6 |  | note | CATEGORY: WP
label | 31060c68-a43e-4474-adab-554412d337c6 |  | note | RESPONSIBILITY: SE
label | 9a5812fc-a437-4345-93cc-bf69eafe26c9 |  | note | VERIFYING DOCUMENTS: Welding Certificate
text | d84e74e0-0bd3-4866-a8ae-cab28e76e656 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 2341c582-194a-4cbc-9da2-bc78020ddcb5 |  | note | REFERENCE: IFC Drawings
label | 0cc21995-0865-49c5-9b2b-5fcd2c619868 |  | note | D/17/62901
label | 71341cdd-87ed-4b07-ab8f-f162ad43ef98 |  | note | ACCEPTANCE CRITERIA: Set out line and level of drilling works.
label | 121d95cc-64fb-43b6-8339-b7ea93df5729 |  | note | Survey to mark out existing services.
label | 678ae509-2d3f-425b-a630-d4f5b925bb77 |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | 4b6f48c4-3298-49cd-8aea-6db7d8e9f67b |  | note | Sleeve must achieve a min. 2000mm verticle clearance to tracks. Check FSL of track after lowering works
label | 7a74a8fa-d98e-476a-882d-11828fdfd92a |  | note | METHOD: Measure and Visual
label | 8fb28c85-c304-4b03-8f74-afce474cd3c5 |  | note | FREQUENCY: Each element
label | fd728bc8-3357-4e8c-94f2-6fda04ce6546 |  | note | CATEGORY: IP
label | aec0c1e1-b0ca-4a6a-a181-a33cb8d64976 |  | note | RESPONSIBILITY: Surveyor and SE/PE/SPE
label | f584968e-7964-4979-a23b-42f8bbf84b00 |  | note | VERIFYING DOCUMENTS: This ITP
text | bfb71014-fc96-4507-92f0-1a19b6f65231 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Drill rig setout
label | db0166e2-41a2-413e-b9ee-75e7a02a47d4 |  | note | REFERENCE: N/A
label | a65056ce-b1bf-4aad-94ec-1e86bf774c40 |  | note | ACCEPTANCE CRITERIA: Location as per current Drill shot plans
label | 8cbd7e4f-f0c4-4138-9b2b-60a50c207da9 |  | note | METHOD: Visual
label | 5ef70d38-6ac9-4612-ad32-c5aa3f6b51d9 |  | note | FREQUENCY: Prior to commencement
label | dbf75564-f4db-435b-9fa2-e99668973c98 |  | note | CATEGORY: VP
label | b2e9a40b-5971-4ddf-bf78-e5a24213c2ed |  | note | RESPONSIBILITY: SE
label | 3125d71f-1c3d-49ff-ac0f-24fcff081748 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5b8ae2a7-6894-46dc-97c2-a01a488a9afe |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Ground Conditions
label | 8d4dc07b-5fca-4850-ac7f-d27fc5d3822b |  | note | REFERENCE: IFC Design Report
label | 3b18c569-3a23-44a9-b0f1-665cce489c69 |  | note | ACCEPTANCE CRITERIA: Assumed ground conditions are as per site geotechnical report.
label | 5fef4952-5ffb-48e0-8cd4-f7f999a37ff6 |  | note | Geotech Engineer to be immediately notified if the excavations encounter different materials than expected
label | b7e7f433-754d-4f7e-8d9b-22aaf7de1fe5 |  | note | METHOD: Visual
label | 99c288c0-d076-45b2-9783-fc2e16f1a8ca |  | note | FREQUENCY: Each lot
label | a5324ef6-9db6-432a-8ea0-0662a2889b92 |  | note | CATEGORY: IP
label | 57ed9df4-0c90-49a0-ad97-6e734c1b4d7b |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9d0c34f9-786d-45cd-89af-73995b5c07e5 |  | note | VERIFYING DOCUMENTS: Photos Sign ITP
text | 9dd9c071-ce61-457b-b788-6a8a655a651f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Pilot Hole Drilling
label | 6c824da4-3919-4941-b604-8ca6d330f283 |  | note | REFERENCE: IFC Drawings
label | e34d82f3-2607-4847-a0fb-831648f59648 |  | note | ACCEPTANCE CRITERIA: Assumed ground conditions are as per site geotechnical report.
label | eb4a957e-0837-47f3-bb22-ec1d159ea1f0 |  | note | Geotech Engineer to be immediately notified if the excavations encounter different materials than expected
label | 77941590-3f61-4fd8-9955-cf1f20fd13d4 |  | note | METHOD: Visual
label | 516902c8-372b-4081-ae25-aa82e780e401 |  | note | FREQUENCY: Each lot
label | 18c0fecc-1279-4291-a133-3308d211aa2b |  | note | CATEGORY: IP
label | 3c6b3cea-ca87-4331-810b-306f47eee388 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fe2152c0-9654-4ab9-9bbd-0477673f0cc2 |  | note | VERIFYING DOCUMENTS: Photos and Sign ITP
text | d8aa55fb-10f8-4a46-bdff-f7d74668a8e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 HDD Monitoring
label | e632b0b9-4a73-49e4-812d-f2c99c428322 |  | note | REFERENCE: IFC Drawings
label | f611167c-5b23-443c-9caf-51e6a6108f18 |  | note | ACCEPTANCE CRITERIA: Inclination and path to be monitored as per design alignment.
label | 79d3540a-db5e-4b1a-8f03-734087a23c76 |  | note | Ensure bore hole blockage and fluid losses are detected and addressed by:
label | ee129e2a-f43b-4300-a876-c48c33787bab |  | note | Monitoring drilling fluid volumes, monitoring annular pressureand monitoring cutting returns.
label | f716bb45-f307-4ea7-9875-e99be80c322b |  | note | METHOD: Measure
label | 332a5817-ef1d-4d9d-92df-c481ba77e0de |  | note | FREQUENCY: Continuously through installation
label | 7614a3b0-8759-49ed-8e3d-e2f0bd66c325 |  | note | CATEGORY: WP
label | 3fbaf111-c7a6-4490-8dfa-f0be842ad9d9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1c2c6689-790f-46ce-9db1-2ae4dac3b48a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 02a66371-bd7a-4ef1-9afa-01f86efbc853 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Conduit Installation and Trace Wire
label | aeec6da4-6663-4c3c-a69c-eabd8ac5ad34 |  | note | REFERENCE: IFC Drawings
label | f727d632-e933-457a-a42f-e0ba6a80597a |  | note | ACCEPTANCE CRITERIA: Min depth as per IFC drawings.
label | bcfa0378-463e-4e23-a49c-ea39e8c48d3e |  | note | All bored communications conduits shall include the installation of 3mm trace wire.
label | 7f314166-24c6-41ae-bc45-439764bd6ab2 |  | note | METHOD: Visual
label | 02f59c15-7a3d-467d-bae3-a14f49dbdd3a |  | note | FREQUENCY: All Pipe
label | 4e165543-c321-4052-b57f-4514d980cecb |  | note | CATEGORY: VP
label | 3582d64c-52fe-4e81-a677-738493adc6be |  | note | RESPONSIBILITY: SE
label | 0d0dc3db-24e0-45e2-a78a-20037d2ba15b |  | note | VERIFYING DOCUMENTS: Sign ITP.
text | a364766a-2b14-4b18-8789-1fe5e6510f06 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Pipe installation
label | c9972718-4ba0-427b-82ec-fc2c0eed45cf |  | note | REFERENCE: IFC Drawings
label | 88ad2be9-2e1b-4c8d-8f27-1fbfe9af7cd0 |  | note | D/17/62901
label | 052294b1-1310-4b96-a879-4244a39a58b9 |  | note | ACCEPTANCE CRITERIA: Pilot bore to be reamed, then immediately followed by pipe being pulled through. Bore should remain supported at all times.
label | 8b7a8852-6a5f-47b0-a7af-b5ac09826e80 |  | note | Diameter of bore is not to exceed diameter of pipe by more than 50mm.
label | 568f848a-29a5-4789-ac1e-75592827cc13 |  | note | Pipes to be installed in straight sections with no excessive bending in the pipes
label | 3c664fa6-64d3-4204-8cff-830f94c36f74 |  | note | METHOD: Visual and Measure
label | 1fe0cf39-1e94-4e67-b256-9dccc0250bfd |  | note | FREQUENCY: Each lot
label | 4cb0fae4-b796-44dd-b592-d3cc68361253 |  | note | CATEGORY: IP
label | 4f3bcece-7a8c-4180-bd54-1130799a1cef |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 03c63007-57b0-4728-9309-fe403ad69f66 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | bcff9bfe-b769-4d2c-ba16-8c8f5b8ebb44 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Conduit Installation and Trace Wire
label | 428a27bf-325f-43fb-8655-ce2dcb070ec5 |  | note | REFERENCE: IFC Drawings
label | 48f70c8b-51a9-4957-b5c0-f76a4e9ea9dd |  | note | ACCEPTANCE CRITERIA: Min depth as per IFC drawings.
label | 1a762550-4674-44f4-83f6-67c6aaf4e8c7 |  | note | All bored communications conduits shall include the installation of 3mm trace wire.
label | 28abacef-ec32-48f3-b749-ec6788122cee |  | note | METHOD: Visual
label | 5fa0cfc3-58dd-4a0f-9597-443e4e45aa3b |  | note | FREQUENCY: All Pipe
label | 6f7cec27-0ee1-4cab-be4d-afe46b2d6ffc |  | note | CATEGORY: VP
label | 4ff58ef4-290e-4be3-945b-05f40590f1b2 |  | note | RESPONSIBILITY: SE
label | cda8f9d9-254d-4e15-9607-2b992177252c |  | note | VERIFYING DOCUMENTS: Sign ITP.
text | 3e277406-0210-493a-9b19-c1430de3167d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Track Monitoring and Ground Settlement
label | fe89bf27-1947-40cb-bacd-840b103b0748 |  | note | REFERENCE: IFC Drawings
label | 14336edd-ef24-4376-84c7-5a03af099c13 |  | note | NIST-2706
label | ef48ca6f-65e7-4f3f-b7be-edd5943b3101 |  | note | ACCEPTANCE CRITERIA: Both tracks are to be monitored at 5m intervals either side of the centreline of the under bore for 10m either side of the bore centreline (20m in total).
label | 931e847d-cf56-4381-879b-695c9307997a |  | note | If movement above the predicted amount (> 15mm) is visible or any tension cracking is observed at the surface or within surrounding areas, then construction must cease, with drilling fluid still being pumped, V/Line and the Geotechnical Engineer notified immediately.
label | d50a5838-6545-40e3-9401-5afa00547dc1 |  | note | METHOD: Meausure and Visual
label | c4e1948a-5585-46d0-bfbb-8fcec39e9444 |  | note | FREQUENCY: Continuously through installation
label | d25dfb9b-e196-43b8-a224-790a814c2ac1 |  | note | CATEGORY: IP
label | c51c010c-e966-40d6-b318-5dbe02817c6c |  | note | RESPONSIBILITY: SE/Site Supervisor/Survey
label | 4cd0b483-132c-4456-adb0-4b918852a388 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 78881d54-fa01-4bad-9c49-84305b944919 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Conduit Welding
label | ecc014ae-d283-48a7-90f8-8124c903c1ea |  | note | REFERENCE: IFC Drawings
label | b6bf4c2d-a016-4e39-8456-77dd904ed92e |  | note | ACCEPTANCE CRITERIA: Joints are to be butt welded.
label | 0bbd51d7-c7f5-4046-9140-1cc3427c983e |  | note | Weld map to be supplied and identify unique joint numbers.
label | 26d2e99b-f667-4835-aaa9-237fa581964f |  | note | Butt Welding records to be supplied.
label | 45c4176f-6b79-42f1-98cd-2fa12984863f |  | note | METHOD: Record and Review
label | dd1552b6-4d17-447b-9bd5-bf6c31974c82 |  | note | FREQUENCY: All Joints
label | f3cdf5d4-b571-45c7-b7b9-34fb7e0f93af |  | note | CATEGORY: IP
label | e7b144d5-49c4-4e12-a95b-c0436f89841c |  | note | RESPONSIBILITY: SE/Site Supervisor/Survey
label | add1a7c9-98ef-4854-a1c7-2a88171eb677 |  | note | VERIFYING DOCUMENTS: Sign ITP Butt Welding Records
text | 33ee85be-611e-438f-854f-23b59c61c61f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Draw rope
label | 7cc9790d-db36-4bb6-950a-6c45e617946a |  | note | REFERENCE: IFC Drawings
label | 9d827778-947f-4935-aebe-dfdf61e9494c |  | note | ACCEPTANCE CRITERIA: The draw rope shall be continuous for the complete length of the conduit run.
label | ea7025e7-09de-429b-92e8-a8958e5ef97d |  | note | All draw ropes must be continious between pits and have 2m slack in the pit.
label | 7ff50c2b-d978-4f7d-a4d7-f5d69478743d |  | note | METHOD: Visual
label | 87e6957f-3e6d-4b0a-8b9a-b7dd011606bf |  | note | FREQUENCY: All Pipe
label | 83e48b3b-dc61-48b2-bb4b-c3b4ef60132c |  | note | CATEGORY: VP
label | 7914f23f-4072-4fa5-ba4d-1a75b5c0cac3 |  | note | RESPONSIBILITY: SE
label | 47a33494-5f91-42b6-88d6-c1d23268602f |  | note | VERIFYING DOCUMENTS: Sign ITP.
text | ebc00dfc-47bb-4c75-a51d-f66bdb5bb68b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Mandrelling
label | d12c0a3e-5beb-4bc6-bbfa-80f6db031d79 |  | note | REFERENCE: IFC Drawings
label | a45d2b0b-2083-4a44-b397-f83ed0cc62d4 |  | note | ACCEPTANCE CRITERIA: Plug with 90% of the pipe diameter to be pulled through each conduit to ensure the conduit hasent been compressed.
label | 34827249-73d0-4daf-aa50-71419924826a |  | note | METHOD: Record and Review
label | 636698b7-733b-4836-959f-c17cc847a6e7 |  | note | FREQUENCY: All Pipe
label | 81d508f1-68ab-4bb5-9ea2-477c6cc9bd00 |  | note | CATEGORY: HP*
label | 96695c45-556f-477a-9ddb-dae53741b109 |  | note | RESPONSIBILITY: SE/SPE
label | 487fa76a-bb3c-46de-9f25-8f908b48b6cd |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 221a8bae-40fb-40ad-92c7-b6d741a38187 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Pipe Completion
label | de5c22e8-6d58-4e44-8536-d8834cfda769 |  | note | REFERENCE: IFC Drawings
label | b00515dc-ca39-448b-a6e9-8619c9b06dc3 |  | note | ACCEPTANCE CRITERIA: End of encasing pipe to be sealed at each end as per IFC drawings
label | 9bfbaef3-7308-4215-878d-16e52d3cf58e |  | note | METHOD: Review
label | ba6e635a-fd1f-4eaa-ac0c-58ddfa193d0a |  | note | FREQUENCY: Each end of pipe
label | 341a8b52-e685-4452-b885-b5525a3d7ec3 |  | note | CATEGORY: IP
label | 4b6b0bbf-98c7-4bc5-bbe3-b7721a7cfe1c |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c83de600-ad02-4718-909b-a62af30baa7f |  | note | VERIFYING DOCUMENTS: Delivery dockets Sign ITP
text | e1cd869a-2ce2-4bc2-8e4f-d3db9445cf8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.14 Reinstatement
label | 13cb5a22-418d-40cf-81dd-045af742262a |  | note | REFERENCE: IFC Drawings
label | e0dfc5e5-891c-4c9a-a770-95ffe6761be1 |  | note | ACCEPTANCE CRITERIA: Entry pits, exit pits and trenches within the railway corridor to be backfilled using approved fine crushed rock material. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 0233bc99-62f2-46e3-9368-063ed957fa0d |  | note | Vic Track Engineer to inspect.
label | 23874938-97e9-4fbf-a0ab-d4f0f6084db8 |  | note | METHOD: Review
label | 1bb8bece-219b-44a9-9a8a-1421847bd4af |  | note | FREQUENCY: Each lot
label | 9feb6a9f-79d6-44f4-9260-947ecd473175 |  | note | CATEGORY: IP
label | e0d21c68-e674-4088-a560-106e8cb48fc2 |  | note | RESPONSIBILITY: SE/Site Supervisor VicTrack
label | 536f2b61-93fb-4859-b3af-4bdf8a714664 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ea8c8543-39ac-4c6b-919c-0af6dc674ce2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.15 Marker Post Installation
label | f43d0d9c-dc83-4e36-ba4c-cf118e393d4e |  | note | REFERENCE: IFC Drawings
label | 43fbd636-374a-4659-93a4-72c25270cf3c |  | note | AS4799-2000
label | 1d609af6-df2d-47a8-8278-28cf6f82e633 |  | note | ACCEPTANCE CRITERIA: Marker posts to be installed at every 200m intervals, any change in direction and at the entry and exit points of VicTrack property.
label | 081a4653-7fad-4628-8974-2d324d699d75 |  | note | Marker Posts to be placed facing the rail tracks within VicTrack property
label | 8b5d1c23-bd87-4cd6-b626-1cdfbc608c66 |  | note | METHOD: Review
label | 6da0db10-ccfc-4357-9df6-fdd7fecae1cd |  | note | FREQUENCY: Entry and Exit Points
label | 54834603-b0c7-4518-bf68-4617900aff66 |  | note | CATEGORY: IP
label | a6a5d54e-b35b-4483-8939-ef0fd0166ab8 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6639bdce-bd97-49e4-8fd0-51532846fb28 |  | note | VERIFYING DOCUMENTS: Sign ITP Delivery Dockets
text | b475dffa-0e05-4a37-9c62-26f4cecdf1d3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.16 Marker Plate Installation
label | d021eb6e-904e-4a5f-821d-e289ad812ff9 |  | note | REFERENCE: IFC Drawings
label | 33c8036c-1ccc-41bf-9005-ed037ecafa4e |  | note | ACCEPTANCE CRITERIA: 50mm x 8mm Galvanised Steel Plate Welded to Post
label | cf2cf09b-a398-4bfe-99f1-ac0be4b27966 |  | note | Marker plate riveted to post with 8mm insulated aluminium rivets.
label | be7f67ec-0b82-453d-9544-14d9ee3b45f6 |  | note | METHOD: Review
label | 82610160-2295-40a4-bfab-9f7c04474f42 |  | note | FREQUENCY: Each Post
label | 85b1852c-4378-4003-b7d4-81e40f42233f |  | note | CATEGORY: IP
label | 89700d42-144e-495b-9500-ad01d5a9c8f2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fe081bdb-6767-40f0-8754-8d7577b92dd7 |  | note | VERIFYING DOCUMENTS: Sign ITP Delivery Dockets
text | 921a2a96-bf8b-4acb-859a-e8eb85432121 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 As-built Survey
label | 5287e568-c5c9-4cf4-8604-d3cf891c8dac |  | note | REFERENCE: IFC Drawings
label | d9dc704d-00e5-4add-a0ea-180f34e3688e |  | note | ACCEPTANCE CRITERIA: Survey as built report to be compiled.
label | 1e9b2bec-d2b1-49f5-b933-c77d5e48d1a9 |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | bfc45506-2466-44b5-96ba-bbbbe12ebab8 |  | note | Sleeve must achieve a min. 2000mm vertical clearance to tracks.
label | cd0d00c5-33bb-4dfd-b2a8-b805c7c041f3 |  | note | Autocad and PDF reports are to be supplied to: services.applications@victrack.com.au
label | 41bd171f-14d2-4a1b-ab04-b6cee3499faa |  | note | METHOD: Document Review
label | 3c02a70a-3328-467e-ac74-27de1b0277ec |  | note | FREQUENCY: Each element
label | 140079b1-0819-409f-8c58-f3a22f5a3cef |  | note | CATEGORY: IP
label | b42539c1-d1b2-4156-8f28-4c489152c178 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 3915eaab-0422-43f9-a5b9-95aae1ab8540 |  | note | VERIFYING DOCUMENTS: Survey As Report
text | d6fe7b02-1618-4d40-9124-a8bef597916a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Track Inspection and Maintenance
label | 8313b181-2d3f-4eb4-b22a-171d94bed82a |  | note | REFERENCE: IFC Drawings
label | c23ec351-fd14-41bb-98a8-0fc112b5fd04 |  | note | ACCEPTANCE CRITERIA: Once works are completed, survey to confirm settlement of the track and ground are within the predicted design settlement values.
label | 034dcf0f-d3f1-4c62-aed8-f8412f3b240f |  | note | Not > 15mm
label | 4ece94e5-e356-4ed4-9f07-ec9b1a10da6e |  | note | To be provided to V/Line prior track hand back.
label | 8fcee438-b9ff-4617-997c-034d255853b8 |  | note | Where track has been disturbed beyond the tolerances, realignment and/or maintenance is required by a qualified sub-contractor.
label | da4b8540-c003-43d3-99a4-f0d62ad54667 |  | note | Attach: Track Inspection & Maintenance ITP/Taylor Rail ITP
label | 9c3901d3-3abf-45fb-84a1-09df04df5336 |  | note | Attach: Track Measuring Sheet
label | 5cf68bca-2c9f-4af8-85a0-227a02ebc1d9 |  | note | METHOD: Document Review
label | 3c4f29b3-d6f3-44a4-9f98-2a564eaccfad |  | note | FREQUENCY: Each element Where applicable,
label | 6f247950-0b44-48a0-8fb7-62daf9682d0f |  | note | CATEGORY: IP
label | c86d1110-eb01-4078-8b2b-d46276741995 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 0eb4dc72-4c45-498b-afb5-3dd92a7eebb7 |  | note | VERIFYING DOCUMENTS: Survey As Built Report
text | 4fdd7882-5b47-47db-ade0-4a4c48fe838c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Red-line / As-constructed IFC Drawings
label | e3ddec33-c83d-4cd2-9183-f2f264dbf873 |  | note | REFERENCE: MRPA Quality
label | bb4da678-ae76-44ab-ad1f-920bd47e2948 |  | note | Management Plan
label | d5d94580-9f88-48e4-b763-5217bc1cc42c |  | note | ACCEPTANCE CRITERIA: All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | 8d2840b2-0cb6-4338-9831-d13d77edfb14 |  | note | METHOD: Document Review
label | 2d680d1d-4af9-4aa4-8896-02f325f4b364 |  | note | FREQUENCY: Once, after construction of the design package
label | dd671f63-18dd-4ec3-bd0e-bf5ebe37933f |  | note | CATEGORY: WP
label | ec2c5c3c-3658-4f07-a310-6b6c4074b989 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c9a4f953-583b-4a7a-bc7c-bfbbde787c7f |  | note | VERIFYING DOCUMENTS: Red Line Drawing Pack
text | 8c2ea7de-b4eb-4aee-95e9-311118ede10e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6b04834a-0fb7-49d8-aed3-6a0d5ded01bc |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 09e1dbbc-477a-42b3-a8aa-95d6ff4f9459 |  | textbox | Name:
text | d0081f22-b88a-46cd-a5b6-55938954345b |  | textbox | Position:
text | 5b84ffc7-08f5-45e2-9982-2aaa23323cbd |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Precast Bridge Beams (Supply & Installation) Rev 2 | itp |  |  |  | Yes | ITP-STR-Precast Bridge Beams (Supply & Installation) Rev 2 | c1d87cfe-0a53-4b04-ad01-452908cefe04
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | fb7a3c4f-e206-4842-abf0-20a6a886fcd7 |  | note | Document Title: ITP-STR-Precast Bridge Beams (Supply & Installation)
label | 2e9ae496-2cb8-489d-9554-df9f9993f8df |  | note | ITP Description: Precast Bridge Beams (Supply & Installation)
label | 077d119a-ba01-466f-ab40-12f168af2566 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 23c012cc-e70d-4294-a29f-f00a2d8c7b3f |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 9428cb3a-c30c-46b4-a4ab-11831131fe45 |  | note | Revision Number: 2
label | 79262150-b092-4923-8402-6474c9d7f60f |  | note | Revision Date: 44244
label | c9f3d4c9-f026-4bf2-b283-edc6dd7f34a8 |  | note | ITP created by: Romualdo Magpantay
label | 14a22628-5750-4e74-965a-8f498b0b253d |  | note | ITP approved for use by: Mike Freeman
label | 04461f15-0f3b-4534-895c-e7719ff88049 |  | note | 1.1 VicRoads Section 169 July 1993
label | cf477b9e-2688-4b83-86de-5a92de6b9db9 |  | note | 1.2 VicRoads Section 610 November 2018
label | 02b15237-e83e-44f1-9ea6-f960e1d7ae27 |  | note | 1.3 VicRoads Section 610 June 2019
label | 441749ab-d6a6-479c-a6e0-d221e1a8e7cb |  | note | 1.4 VicRoads Section 613 June 2017
label | 22eb6cc7-0605-4e20-ab4e-17669bc96709 |  | note | 1.5 VicRoads Section 620 May 2009
label | fd9d105a-2d61-40cc-81ea-295e520bd547 |  | note | 1.6 VicRoads Section 622 November 2018
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Precast Elements
label | 0690fbe5-5d61-4220-8035-80decbbc3343 |  | note | REFERENCE: IFC Drawings
label | 873d190a-47a4-4608-9a2a-ba658079fde8 |  | note | 610.46 (a), Table 610.463 (November 2018)
label | da11b6bf-d1ac-4b64-93c1-7f2aaf37d3cf |  | note | 610.47 (a), Table 610.473 (March/June 2019)
label | c4f4aa51-54d6-4169-9dcd-2d7f0716c596 |  | note | 620.03
label | e755a467-1d1a-48b4-b52b-2fb3611ad04b |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 6ca43b2b-19ea-4d2f-9e87-0f946baa2d2c |  | note | i. Certificate of Compliance / Birth Certificate
label | d3ba4b4d-defb-4e6a-a8a0-0dfc0926f62d |  | note | ii. Compressive strength test results
label | 33a82343-38c9-4d83-bec8-c3941665de66 |  | note | iii. Precast Lifting Design
label | 58cb39af-8f69-4542-b0dc-d8a1e424eddd |  | note | iv. Pre-pour check sheet / ITP
label | ffb6d55c-e3b3-4b47-a377-32bf646ae721 |  | note | v. Pre-stressing check sheet / ITP
label | 6e4efd84-b4b4-4697-abe3-340e3c697e17 |  | note | vi. Post-pour check sheet / ITP
label | 31b797ca-c546-4f63-9dcf-b28adac23210 |  | note | vii. Covermeter check record
label | 86894450-c129-4983-8a20-b6da39734967 |  | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
label | 20ba444a-f9c2-4f8f-9ec8-a7f100ce1ce4 |  | note | Note: Different revisions of 610 have different clause numbers
label | 742b3c59-9a4f-4894-8814-1dd67f924596 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | ad77f7e4-af3f-469e-82f8-ea07dc59c224 |  | note | METHOD: Document Review
label | 6f63c467-aca4-4ed3-8116-dd8392ac0021 |  | note | FREQUENCY: Each element
label | f294d6ce-221c-4148-a469-519a29f5fd1d |  | note | CATEGORY: IP
label | 01abf318-aa6a-4c58-8947-937a941b7306 |  | note | RESPONSIBILITY: PE/SE/SPE
label | bf104b48-e4aa-4f83-8805-7c93360611a1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2c00f3f0-346f-49c9-98fe-d800c9ce9fcb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Temporary Works Designs
label | c191bfd8-0136-4327-a8b4-6b79d370216a |  | note | REFERENCE: 610.27
label | 58670df7-d947-4fe3-8d90-ce61e306dc0c |  | note | 613.04
label | f53d00a9-4345-4eee-9958-862a26081c3a |  | note | 613.05
label | 7c733b8b-69ee-4b01-8a3d-76a80451fc4d |  | note | 613.16
label | 9ef3c2bf-19ed-4632-bb9f-2b95102eae49 |  | note | ACCEPTANCE CRITERIA: All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design.
label | a348212f-1b65-494e-a7ff-a35141150601 |  | note | Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority.
label | e6bfa5eb-36c2-40f8-82c8-6cb19b5259c6 |  | note | Attach: Temporary Works Design
label | 71961802-9dd2-4ad1-9ddc-f75e2482e3b2 |  | note | Attach: Attachment A
label | d26771de-86a9-4e13-9082-94290c6d1433 |  | note | Attach: Attachment B
label | 1c9b870b-b389-44d2-a98b-7833a93d2225 |  | note | METHOD: Document Review
label | 0f6254d2-09ca-438b-b5d3-78c6ec14f773 |  | note | FREQUENCY: Where applicable, once, 5 days prior to installation
label | ed96884d-96a1-448c-bb2b-d8c75bc91228 |  | note | CATEGORY: HP
label | 57eab7c7-79e5-49be-b43d-5e2a6612245c |  | note | RESPONSIBILITY: Nominated Authority
label | 85c7f73b-7d52-4f0d-81d8-ac7a73b1e1c7 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | add6ec26-501f-4542-908b-2733c6723dae |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Crosshead / Pedestal Tolerances
label | e1d08ba9-cad9-475f-b481-13131ac3b0d2 |  | note | REFERENCE: Structural Concrete ITP
label | 19a761d7-8043-497d-8860-6c0148fa6ddb |  | note | Or,
label | b3ec6128-bcfe-4771-9ca2-764134c6691b |  | note | Grout Pedestals & Bearings ITP
label | 76f2d18f-9111-4d49-8719-0bc365cdcb7f |  | note | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
label | ece11aa7-c753-4ae2-9337-87f866d2187f |  | note | Reduced level ±2.5mm
label | 35eed8a0-ae6d-4c6a-b591-b44ee42300fc |  | note | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | 7ad695f8-3202-4d15-b1ec-902bc945f589 |  | note | Deviation from flat surface ±1mm
label | 86321399-5e21-4257-ac95-cb2de52a55c3 |  | note | METHOD: Document Review
label | c40d833f-75eb-4331-918f-3fdfd461c94a |  | note | FREQUENCY: Each element
label | 80a87ceb-c85e-415a-a161-a996f494e534 |  | note | CATEGORY: IP
label | 461747e5-57bc-4e75-a510-3fd83e2019da |  | note | RESPONSIBILITY: PE/SE/SPE
label | b8be1276-7213-4bd3-8629-91ae1d3ccde6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0c609174-9d8c-43b7-ae78-fe538da0b5ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Crosshead / Pedestal Compressive Strength
label | a6ded94f-5fa3-4d55-a3ab-fa9c01c336dd |  | note | REFERENCE: IFC Drawings
label | 8712adfa-0984-4312-8357-808a9d6fd670 |  | note | Compressive Strength Results
label | 27afb778-bf41-4413-bcca-0b2f9a0ce990 |  | note | ACCEPTANCE CRITERIA: Re-check that the minimum required compressive strength as shown on the IFC Drawings has been achieved.
label | ac7b9f84-fa9f-42e9-93fe-b21c89f6e953 |  | note | METHOD: Document Review
label | 81b77395-3c48-4b31-a2b1-17a113e873ca |  | note | FREQUENCY: Each element
label | 3bdd0d1a-e57b-4894-8b51-88a778b6f0b7 |  | note | CATEGORY: IP
label | d52280ca-e245-4e18-91ac-4044e3762fb3 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8b158097-ba04-4404-8f6b-3b68788934e9 |  | note | VERIFYING DOCUMENTS: This ITP
text | bf360648-e289-4068-993d-b17d51f253f8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out of Precast Elements
label | de221efc-2c85-4495-ae90-8a2e27ec4a47 |  | note | REFERENCE: IFC Drawings
label | c470ef7c-be8b-4734-8f6b-550ce4149534 |  | note | 610.46 (a), Table 610.462 (November 2018)
label | 880a04c5-b702-4b1e-8c76-5a497779744e |  | note | 610.47 (a), Table 610.472 (March/June 2019)
label | 96c1a189-6783-4c2d-8fdd-1b6dcba64ffc |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element.
label | 5973ff34-52ee-4e23-ad8c-b87c6db19bd5 |  | note | METHOD: Measure , Visual
label | e3b7fa8f-f86d-4486-b1f3-e1c0fe0c3971 |  | note | FREQUENCY: Each element
label | 6d127219-7e9f-4f5f-9dca-26dacd7e4e4a |  | note | CATEGORY: IP
label | 72d4a4ba-a0b0-4c01-af0c-c0511af528c1 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 46d763ee-ca22-4ba2-a0b7-d2323bc73f68 |  | note | VERIFYING DOCUMENTS: This ITP
text | bd34d406-07de-44b6-88ba-25f907b9c680 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Elastomeric Bearings
label | 025cde20-220a-4d39-9fc6-0a334361ed1b |  | note | REFERENCE: IFC Drawings
label | bbeaeae9-b707-4f87-8e4e-b81b40023f27 |  | note | ACCEPTANCE CRITERIA: Where applicable.
label | 4da22861-e707-4fb7-8e2e-cbea62ce6720 |  | note | Complete: Elastomeric Bearings (Supply & Installation) ITP before proceeding with this ITP.
label | 03b1c24d-93c6-461c-9b0a-6a502f6c683b |  | note | METHOD: Document Review , Visual
label | 68de23d0-f6df-4bd9-87d0-1b0591c6f07d |  | note | FREQUENCY: Where applicable
label | 7ef4804f-ec86-4f63-b890-13a8e78f8ad4 |  | note | CATEGORY: IP
label | e2b613c0-105b-431e-a9a3-2b305445966b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 79e1de3b-9819-425e-9949-0a5264cbcc8d |  | note | VERIFYING DOCUMENTS: Elastomeric Bearings (Supply & Installation) ITP
text | ded5fe12-94d5-4e23-8a02-c092bc1b498a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 HDPE Bearing Shim Placement (for integrally cast beams)
label | 23ad20bb-e4ac-4d41-9f66-6176c523b2d4 |  | note | REFERENCE: IFC Drawings
label | 21b5f2c6-5e71-4aad-9290-634694ac720c |  | note | ACCEPTANCE CRITERIA: Place the bearing shims (or variety of shims) to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | 6f4b7b74-769b-42e3-b9eb-6e7cf43847f9 |  | note | Note: The minimum and maximum thicknesses of the HDPE bearing shims as this will determine the product for the grouting activities.
label | 2728dee1-49e5-4cf3-b2b7-5be3bc03f39b |  | note | METHOD: Measure , Visual
label | 40f0e85c-6357-4ac2-9520-b8eaf9bff437 |  | note | FREQUENCY: Where applicable, each bearing location
label | 850881b7-490b-407c-ba34-409705b8a673 |  | note | CATEGORY: IP
label | a6b1bc7b-dd41-4867-a27f-1eb833cc4f9a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4f9f4520-e9ce-41c9-b339-867c0698a8e7 |  | note | VERIFYING DOCUMENTS: This ITP
text | fd599a0d-b35c-49dd-8c48-b6f9ba1e51dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Materials Inspection Checklist
label | 43c7261c-85d4-4d84-b3b3-c3801e215bae |  | note | REFERENCE: 620.06
label | cb64694c-f0ce-4b9b-b8a5-c88cc646b5ad |  | note | 620.07
label | 37dfeb30-2d1d-42f9-8890-859aa0e35b30 |  | note | MRPA Quality Management Plan
label | f2f3f9d0-2806-4930-a631-63fddef723d0 |  | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | 2f93b649-5d96-4250-b350-f87938dea11c |  | note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | 9a190ca5-1b6e-4277-9d03-422190a51f38 |  | note | Elements shall have unique identification and orientation marked (if applicable).
label | 9549e316-dfa7-4527-ad45-87bdd09c99cb |  | note | Complete: Materials Inspection Checklist in ConQA
label | 9026b716-40e8-4d8b-bca8-8e8552e1f75e |  | note | METHOD: Measure , Visual
label | f99325ed-54d6-40d5-922e-4ee7d713b223 |  | note | FREQUENCY: Each element
label | a90e341b-20f4-4a87-8f54-ce404b197dcb |  | note | CATEGORY: IP
label | becf0cc1-cc47-432e-9d4a-a5ece4f4fda4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4dd5d68c-bac8-4fe6-8f36-8332b43ece30 |  | note | VERIFYING DOCUMENTS: This ITP
text | 78764009-af49-4193-a913-d8077dbfefa9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Precast Handling
label | eaa68679-78a6-48b0-8442-6e37483708c0 |  | note | REFERENCE: 620.07
label | 72d60a2b-8869-4090-9358-478f159540f5 |  | note | Crane Lift Study
label | e4547776-c3ba-4db5-9409-0e65a2aa77b0 |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | ad835295-dfc6-4565-939c-b5e5aa5268a8 |  | note | METHOD: Visual
label | bb2e0b5c-5487-48d4-ac60-ced1fa310482 |  | note | FREQUENCY: Each element
label | e39f22d0-b00b-4b1c-85d9-a14d853fd457 |  | note | CATEGORY: IP
label | 4007f828-b653-45d5-b9a5-a2d83b66c285 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e1164f40-bb4b-43b7-a36f-b54c5e3cd830 |  | note | VERIFYING DOCUMENTS: This ITP
text | 65a4a42a-3aa6-40d2-983f-51551f342868 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Precast Placement
label | 26ba6f06-adc1-4ecc-8fe0-9bc8c073f533 |  | note | REFERENCE: IFC Drawings
label | 3105ffa8-266b-4501-81fa-8c72c90765bc |  | note | 610.27
label | 7179c230-7c25-4cd9-84dc-c9b4ca5e61d0 |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | 30312c33-c456-4405-95f7-841790461430 |  | note | The nominal gap between elements is as per the IFC Drawings.
label | 49d0b55b-d63d-4cdc-8de8-32563ba88fc3 |  | note | METHOD: Measure , Visual
label | 449f8975-c6cf-4476-85dd-7b8bdccc41ba |  | note | FREQUENCY: Each element
label | 36c2f882-2487-4827-a21d-f7437d9e6ec8 |  | note | CATEGORY: IP
label | 2375616b-b924-4bd2-a6b2-aa5d77c79ff2 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 086f1177-56f5-4e70-b8c5-455b97cb5db5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8961e475-85c3-4c66-984e-b43ecb9bd52d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Precast Traceability
label | e1b669b8-7162-4299-832f-37259491f8a1 |  | note | REFERENCE: 620.09
label | b7afe35a-fd26-4dad-8042-61a94bb49b46 |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | 6deacd36-6640-448a-85ac-b05523fc161a |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | 03186e31-68c5-47d4-8643-489037e89dd8 |  | note | METHOD: Visual
label | 9f64a834-d80e-470a-ada8-2fae139bc839 |  | note | FREQUENCY: Each element
label | 98ed5ddf-7c25-4036-a7e5-9fcd5cafbe81 |  | note | CATEGORY: IP
label | 37c1ec60-e85c-4827-8020-f78611765c0b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 871a7e5a-8383-4444-a3d6-672692052868 |  | note | VERIFYING DOCUMENTS: This ITP
text | 17593fe5-b306-425b-b330-29ae8d2a7aca |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Falsework Certification
label | 18a152fd-5d1e-41b3-be8f-80bc07bd4206 |  | note | REFERENCE: 613.12
label | cc1b37f2-038b-4af6-8aa8-80d532ff9143 |  | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above)
label | 965a5cb1-b539-443a-bcc4-11a27a2982ed |  | note | Attach: Attachment B
label | e60e9ed5-16ee-4702-824a-a47c9034b53a |  | note | METHOD: Visual , Document Review
label | f9524752-6857-4311-b2ac-ebd3be0d10e2 |  | note | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
label | 56e480b5-1a99-4460-bd9c-78980af8e5af |  | note | CATEGORY: HP
label | b480a6a4-296d-4219-8758-35e1c0810ec3 |  | note | RESPONSIBILITY: Nominated Authority
label | 62126907-0a94-407b-bbfe-ff609aab4fb6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | d3a6ef65-3fa3-42f9-821b-930d908548c2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 Flowable Grout Pour (for integrally cast beams)
label | 0be38ee5-ca35-45fb-ab74-9bf54439c8a3 |  | note | REFERENCE: IFC Drawings
label | 3f57fccd-469d-4bca-9cf0-54371cf8f8da |  | note | ACCEPTANCE CRITERIA: Where applicable, the gap between the bottom of the precast element's soffit and top of the crosshead should be grouted.
label | 4a4a6439-a339-4eb2-8fd1-f4a639a99457 |  | note | Complete: Grout Pedestals & Bearings ITP
label | 5d19deaf-19dd-4172-920c-ab8718e0dda4 |  | note | METHOD: Visual , Document Review
label | 889ab6cb-975b-4bf7-beb5-6efab7d8ca5b |  | note | FREQUENCY: Where applicable
label | a997ed24-fee1-496e-8423-61e19159c325 |  | note | CATEGORY: IP
label | 34208f90-6723-48b0-a834-afa7812cb8ef |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | bb3d12b4-7d20-44cc-9099-71eadf694ae9 |  | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
text | 671c3ebb-11fb-4fb7-9ead-e1840d5da778 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 As-built Survey
label | 4f0725e8-226b-45f8-9e60-251943b35427 |  | note | REFERENCE: IFC Drawings
label | 9ba6a7a3-8ce3-4c2c-a439-0c0f8c620534 |  | note | 610.46 (a), Table 610.462 (November 2018)
label | cab98ceb-8286-472f-9183-41ce8c7d0a83 |  | note | 610.47 (a), Table 610.472 (March/June 2019)
label | 22db37f1-e198-4de1-aa76-2feaad3af13a |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | 5ca6dac8-3e1a-4c89-a387-92811508a707 |  | note | Attach: Survey As-builts / Survey Report
label | 05393345-0a85-49d0-9c30-0f98efdfa87d |  | note | METHOD: Document Review
label | f0203647-794a-4fde-bb30-bd681094bd3b |  | note | FREQUENCY: Each element
label | fd99b60e-deda-4d53-ac93-c35c7960337c |  | note | CATEGORY: IP
label | f7e6e74a-7e05-4342-8e06-efc24be8417c |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | e34dd50a-1420-4c25-939f-3759f60dcb17 |  | note | VERIFYING DOCUMENTS: This ITP
text | a1022ca8-7d89-48ab-a72e-bd677fd2f5e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Removal of Falsework
label | bd4720e9-8917-491d-b44a-2ef12481fe2c |  | note | REFERENCE: Temporary Works Design
label | 3dabd6dc-399c-43f1-8f7d-9a3ac5196a99 |  | note | 613.16
label | e446a8b0-0077-4be3-a94e-66f5f91cc024 |  | note | ACCEPTANCE CRITERIA: Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
label | 770f1211-0736-42c3-bddb-22efd7b8975b |  | note | Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for and repair.
label | ea46a2cd-c2af-4ea6-9c09-c6ee28cda833 |  | note | METHOD: Visual , Document Review
label | 5a4fa5b9-1655-4ac9-b68b-3101b0815cef |  | note | FREQUENCY: Where applicable, each element
label | d5a8cc48-dce0-4c18-974b-19815c93febc |  | note | CATEGORY: IP
label | e8a8dbe0-1584-43a8-805d-59142f052618 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7331bb7b-49e2-4511-b2e6-ae02ee2ace0c |  | note | VERIFYING DOCUMENTS: This ITP
text | 68022e7a-afb4-4d21-9ff4-96c0a6732471 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Non-conformance Report (NCR) Closure
label | d33bc824-cf4f-43e9-963c-ebdccc0b5f1e |  | note | REFERENCE: MRPA Quality Management Plan
label | d6aa81c7-7827-4dbb-b737-35226cf5d9b6 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 806bae95-217e-43ac-b0cc-e1821ce1abb0 |  | note | METHOD: Document Review
label | 7f2a20e8-8533-4b5a-947a-5f6b5fb02a3f |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | b5448290-0311-4e5c-9c81-db3e81ba3f64 |  | note | CATEGORY: HP*
label | a812d4db-cc67-4220-99f6-4efa08bba8ff |  | note | RESPONSIBILITY: SE/PE/SPE
label | 75420ca8-8131-4eee-a6bd-ed58d02ad9ce |  | note | VERIFYING DOCUMENTS: This ITP
text | ab84cc35-0c3a-4b3f-b131-a0c4a6c80fc6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 156a6223-8d95-4070-b5a2-0c0761bcb4c3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d7a6f9c5-923a-46d4-803a-c8e32d14d785 |  | textbox | Name:
text | f99a4a54-7e09-4a65-97f1-66135bb2102f |  | textbox | Position:
text | 074a2b5a-04ea-4081-b563-65f29659d805 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV Landscaping - Ground Preparation (Beaconsfield) Rev 0 |  |  |  |  | Yes | ITP-CIV Landscaping - Ground Preparation (Beaconsfield) Rev 0 | c3ba653e-ec85-4668-958b-0714d688cbbb
checkpoint-no-status |  | checkpoint-no-status must be display normal but was flat Not allowed as a child of checklist-sectioned. | checkpoint | Referenced Documentation
label | 5b011f36-9a2f-48c4-9128-6c3ab49efafa |  | note | Document Title: ITP-CIV Landscaping - Ground Preparation (Beaconsfield)
label | 3b84ce34-ffb2-48c9-a78c-106e1c9abb87 |  | note | ITP Description: Landscaping - Ground Preparation (Beaconsfield)
label | da981f38-e3ca-42cf-901f-703eae2169db |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 95bf2c93-5807-4c1b-acc3-8795cf0dbb97 |  | note | Revision Number: 0
label | 078fb564-68b1-481d-b85c-deb58fa87bef |  | note | Revision Date: 20/11/20
label | 1d99a0dc-cf8d-41a9-8a37-9150b3c123b6 |  | note | ITP created by: Justin Kreinberg
label | 30b5b3e5-649e-4645-9b20-eed234280c4d |  | note | ITP approved for use by: Josie Pavlou
label | 7d56cfab-8ac1-4267-a029-d4dadabbdc52 |  | note | Reference: VicRoads 720
label | 228a21c5-4adc-4ad0-af1e-af505cd28b31 |  | note | AS 4454
label | fdee8f33-7302-404d-a210-959cf34a6086 |  | note | AS 4419
label | 5f652286-643d-4a6a-80bb-5b2db933addf |  | note | IFC Drawings
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Check for correct documentation
label | 2d087c1c-9db6-41c7-a326-4e66026f8cdf |  | note | REFERENCE: Drawings and drawing registers
label | 05f22501-94c0-495a-b11a-cc09cef9bb9e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | ff79af9b-2ec1-4f2d-8eeb-679ffed1eb84 |  | note | Using the correct and complete set of IFC drawings
label | 55968544-6f77-456e-a217-d395d221c379 |  | note | Using the correct and complete set of IFC drawings
label | 6d2c068d-d987-4b16-a463-b46a8dbc797a |  | note | METHOD: Document Review
label | a5cba445-69af-4fe3-a7bb-c33ea2e6a7af |  | note | FREQUENCY: Prior to Commencement of works
label | a34442d0-2b49-426e-aa9d-344b5aa314ed |  | note | CATEGORY: IP
label | f4268cd6-aeb0-4a89-93ae-c96a3ba572f8 |  | note | RESPONSIBILITY: SE
label | 180618c1-7eb5-4fda-8c3c-92a82ab7b942 |  | note | VERIFYING DOCUMENTS: This ITP
label | 5000869f-a3ad-475b-9ae6-7082134fd26d |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Submission and records
label | 81d59678-2bb9-4dd9-8b86-6263fc132bdc |  | note | REFERENCE: Section 720.03
label | 74453bd0-ec75-420d-a821-370e987a40ef |  | note | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
label | 9b44c82e-d33e-4cab-a99e-4c3c5ea00363 |  | note | Following information shall be provided to the NA:
label | ef376096-a395-431a-b203-903d6a01372c |  | note | Samples
label | 2b3aaff8-d1fd-47ce-833d-5a709431fa74 |  | note | -Mulch
label | bbe31ba5-f4ba-409c-885f-75a3fcf204e1 |  | note | -Imported topsoil
label | 7abc74e0-04b1-421c-a371-93c6691b2308 |  | note | Records
label | 3b33947a-9024-4f28-ad8b-6f48113d7a83 |  | note | -Details of suppliers
label | d10820c0-2fa7-4482-90c4-6788633eb929 |  | note | -Soil tests on imported topsoil
label | f3191c06-668a-466a-b1e8-29ba1116f4a6 |  | note | -Copies/Photos of fertiliser labels
label | 72d512dc-3bd3-4b3c-b64a-478f54287a04 |  | note | METHOD: Document Review
label | fe54f4bd-751d-4379-bedc-ab2a708e0887 |  | note | FREQUENCY: Prior to Commencement of works
label | daee4c1c-60cb-45d2-85b2-c23e58c0fa8d |  | note | CATEGORY: IP
label | 75ffd7e4-6798-4e3c-a196-8f0d1adcdc8c |  | note | RESPONSIBILITY: SE, NA
label | c869cc42-fc08-4c4a-a424-201a95ecc1b6 |  | note | VERIFYING DOCUMENTS: This ITP
label | 126def38-6b0e-458c-85d2-caa3ba833288 |  | note | Issue to TeamBinder: Records & certificates
text | 6db29877-2773-4468-99ea-88cd425c0f0c |  | textbox | TeamBinder Approval No.
text | 361e8f05-77c5-433a-8129-bc32ef3f4a07 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Supply of topsoil
label | 6a318c4e-9c02-4236-8037-f691ab3436fa |  | note | REFERENCE: Section 720.04
label | 608a3b3a-2d23-4069-90d1-4a9b5d7892d0 |  | note | Table 720.042
label | 31011607-1680-443f-9031-c60121a8b701 |  | note | IFC Drawings
label | 0d0587cf-688b-4028-aaaa-42abfbaf7296 |  | note | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
label | f5bd8b79-e036-4b8e-88f6-b80507e7c1aa |  | note | Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings
label | e4714302-4642-42c0-9758-de6a72d77281 |  | note | METHOD: Verify, Doc. Review if applicable
label | f06ca7d4-ca0a-4151-9044-98f9adbe2544 |  | note | FREQUENCY: Prior to Commencement of works
label | 60a118f9-6ed2-4c76-b79e-537aaa76b8e3 |  | note | CATEGORY: N/A
label | 3972a734-c96a-42e6-8585-6db8a02078f2 |  | note | RESPONSIBILITY: SE
label | 0b87c5af-eefb-4b11-abfd-8ce79fc05452 |  | note | VERIFYING DOCUMENTS: This ITP
select | 41838f65-3a69-4d6f-8fdf-b90fc584d2b8 | DataPoint is missing 'select' values | dropdown | Issue to TeamBinder: material conformance docs or Test Report
text | 10017a51-d624-48f1-bc98-86f9432cdbd4 |  | textbox | TeamBinder Approval No.
text | 22b50291-5891-4e8d-89c0-ab922179dd4f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Supply of Mulch
label | 7618cb39-2955-4229-91f5-19d7de5af2ec |  | note | REFERENCE: 2.4 Supply of Mulch
label | e17f05b0-5fda-47bc-bb25-d2de1b2a8b57 |  | note | Table 720.044
label | 5d1292b1-4c23-42b5-961a-00cd6f1ab5a0 |  | note | AS4454
label | fe79375b-ff57-46e1-9dad-78d4f81ff39a |  | note | IFC Drawings
label | 95f31599-581c-4ac8-bfad-ec0d10608a80 |  | note | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
label | 93b7335a-7d6c-442e-bc2d-ad1e5d4f5794 |  | note | All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings
label | d7bb21e0-83a1-411a-af13-1279f04fb72b |  | note | Imported Wood Mulch shall comply with Table 720.044.
label | 925f8f4d-b0aa-437c-a48b-01fc201e6139 |  | note | METHOD: Verify, Doc. Review if applicable
label | f50eca78-28fc-4ecb-8d25-cf73ba137e24 |  | note | FREQUENCY: Prior to Commencement of works
label | 407327fb-69f6-4c70-b72a-6fc6566c830c |  | note | CATEGORY: N/A
label | ff7bce48-7952-4821-94cb-8c1d6dc50c1e |  | note | RESPONSIBILITY: SE
label | b56404f5-9ded-4ccf-a7eb-cac612c98432 |  | note | VERIFYING DOCUMENTS: This ITP
select | 901e7157-20a2-4623-a503-40e189aca548 | DataPoint is missing 'select' values | dropdown | Issue to TeamBinder: material conformance docs or Test Report
text | 80467fa1-112d-46d1-ba24-0a94fe6ca3a2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Site Preparation
checkpoint-status |  |  | checkpoint | 3.1 Set Out
label | aa2ac13a-1f8c-42a4-8c05-73533c92c1db |  | note | REFERENCE: Section 720.06
label | 8f512131-d09a-4eee-886b-b8a26fb8bf2f |  | note | IFC Drawings
label | 584626dc-d37b-4063-bde1-86761476bf61 |  | note | ACCEPTANCE CRITERIA: The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
label | f4f1673a-e082-4116-9f07-a65d2e81554d |  | note | METHOD: Inspection
label | 328d18b7-ca31-4db1-868f-a6a8760629a0 |  | note | FREQUENCY: Each Lot
label | 191df9cb-5e55-4e83-b7ef-3a5fb6583370 |  | note | CATEGORY: WP
label | ad7e2ae7-efaa-4023-b7fc-c9978c7723ea |  | note | RESPONSIBILITY: SE/Site Supervisor
label | af5c599f-d5cb-4f9c-a09d-ffb1be7826e4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5950f442-a717-4667-8279-0a15b1007343 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Soil Additives
label | ef118684-7521-455a-91bc-e7db19934e2a |  | note | REFERENCE: Section 720.07
label | cbd5df1e-7b92-40f6-8aac-e4e9d0ddb800 |  | note | AS 4419
label | 8fefefde-2b35-4fc7-8dde-d27f72aa7f9e |  | note | ACCEPTANCE CRITERIA: Soil additives, including any material used to modify the chemical properties of the soil, shall be applied by the Contractor prior to physical ripping and cultivation and in accordance with results and recommendations from site topsoil analysis tests, if applicable.
label | cf10031c-d2d3-490b-ba87-16753946a185 |  | note | METHOD: Document Review
label | dcd8d686-d7ec-45fc-942e-4abf540e101c |  | note | FREQUENCY: Each Lot
label | 287b98c9-494f-41f9-85dd-3798a7f8fc2a |  | note | CATEGORY: IP
label | ebe2bc8c-bcc1-4996-ab11-f3c5a59629a8 |  | note | RESPONSIBILITY: SE
label | e87a920f-3d5a-4096-941b-7985528f5f8e |  | note | VERIFYING DOCUMENTS: This ITP
label | fae93cb2-ad5f-4073-b67c-b6f37d370724 |  | note | Attach Test Report
text | 86bac7d0-46c4-49c1-aa3d-f92a321854e6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Ripping of subsoil
label | 326c9598-3882-49ff-951b-db037425169a |  | note | REFERENCE: Section 720.07
label | 0d935e6c-891b-4141-b3f2-b534ab82302d |  | note | Table 720.071
label | 391b2453-5f16-4ab5-bd3e-bae682a6f3f6 |  | note | ACCEPTANCE CRITERIA: All ripping works shall conform to the requirements of 720.07
label | aa024c37-9557-48aa-90f0-22aec402d959 |  | note | Situation- Ripping of subsoil
label | 0d6d725c-b6f4-4119-9125-a21959de2b5a |  | note | Planting Areas in disturbed areas flatter than 3h:1v= min 400mm deep at a max of 500mm spacing
label | 52dcfe40-e364-4e1c-807f-a265bf91f1b4 |  | note | Planting Areas in disturbed areas flatter than 3h:1v= min 300mm deep at a max of 500mm spacing
label | 1ff6d687-5d7e-45c2-8a6c-deb70ef5c08e |  | note | Planting Areas in undisturbed areas = Min 400mm deep at a max of 500mm spacing
label | 1be4d1a0-6ef9-4c75-8417-b1bdf12de025 |  | note | Grassing in disturbed areas = Min 200 mm deep, 500 mm max spacing
label | 101a506f-9729-4c06-b5b4-9a9389d248bd |  | note | Individual Tree Planting within grassed areas = min 400mm deep at a max of 500mm spacing
label | a850248a-3a7a-4e7e-a16f-a12d3682c5a1 |  | note | Note: Ripping shall not occur within the extent of existing vegetation areas marked for protection or within the drip-line of existing woody plants
label | f801f18d-52e9-426b-a7cb-362e26c8a7cf |  | note | Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
label | c2f64264-1d4f-4c1f-8b28-dd3844f0d69c |  | note | METHOD: Verify
label | af96b4df-0590-4db2-b207-756ffcec64f7 |  | note | FREQUENCY: Each Applicable Lot
label | 7f4c3599-c6a9-418b-80b7-ae89990df10c |  | note | CATEGORY: HP
label | fad026a1-e404-4227-bd58-0a215ca44064 |  | note | RESPONSIBILITY: SE, NA
label | cb74f8d1-5eb0-4d9b-89b1-caca06499235 |  | note | VERIFYING DOCUMENTS: This ITP
label | 0d1f2bd7-415a-4551-ac55-a52cc45dbfe8 |  | note | Attach Test Report
text | e9c409bc-78c2-42f0-b867-63ee848a245c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Edging
label | 75534ddd-4bc9-4862-a4b1-ced6eb08dc3c |  | note | REFERENCE: IFC Drawings
label | cfd435db-6481-45de-9931-aebf0407785f |  | note | ACCEPTANCE CRITERIA: The Contractor shall set out the location and shape of edging in accordance with the IFC Drawings.
label | 6290e8de-a117-41c5-9a3e-30519eded537 |  | note | METHOD: Verify
label | 24a56dee-5b43-42fa-8ff0-07e9383121c3 |  | note | FREQUENCY: Each Applicable Lot
label | 38c116fc-d75d-43c8-a56d-87922f71ea67 |  | note | CATEGORY: IP
label | 5fc2eb46-f73d-4375-8bae-2264f147b7e7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | dcaef3b2-14dd-4dd9-af7a-e263fd22c654 |  | note | VERIFYING DOCUMENTS: This ITP
label | 6f3e609e-9bbc-48ca-91d0-937a85bbcc9b |  | note | Attach Delivery Dockets if applicable
text | 071ad2be-fea6-42b4-8106-98b19d4eede8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Topsoil application
label | e4a6dce4-ab6d-44a8-ab3a-797233b95bb8 |  | note | REFERENCE: IFC Drawings
label | 333ad1cd-f517-4ccf-b1c9-84296a77b784 |  | note | Section 720.07
label | af574534-442f-40f9-8442-1a319acc32db |  | note | ACCEPTANCE CRITERIA: Topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in the IFC Drawings
label | 5db03063-c2c9-4e4d-9cba-20d65306ab0b |  | note | METHOD: Verify
label | a2c99d9a-a2b8-41ad-a6de-ccd843c7cdb2 |  | note | Each Applicable Lot
label | 01922dda-56a4-44fe-97c4-3351288e8f8f |  | note | CATEGORY: HP
label | 94692ee8-0adc-4498-914f-e06cf2910a83 |  | note | RESPONSIBILITY: SE, NA
label | e5061486-331c-4e70-aa1b-a459bb4591e6 |  | note | VERIFYING DOCUMENTS: This ITP
text | d99e0c9a-1817-4a27-a311-41d27383389d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Cultivation
label | 7590489e-fc7f-47c6-b739-1c37591d3189 |  | note | REFERENCE: Section 720.07
label | 79ba4e9f-bedd-4619-99c6-6b74e42187f4 |  | note | ACCEPTANCE CRITERIA: Cultivation will only take place if easy manual excavation cannot be achieved to 300mm or deeper.
label | e127e65e-cf22-4e1d-93cc-49911b03a798 |  | note | If easy manual excavation is not achieved the following will take place
label | b014a5cd-9686-43f1-a5bc-61d373833b98 |  | note | Situation – Cultivate- Table 720.071
label | 51bc56fb-f487-4ba1-8f84-4fbd92664c6f |  | note | • Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
label | ab0d019c-9fda-4335-bc7f-2c1f17c5d72e |  | note | • Planting Areas in undisturbed areas=150mm Minimum
label | 440a1b48-b0f5-4833-866d-112fffe0d057 |  | note | • Grassing in undisturbed areas = 100mm Minimum
label | 3d4b38f1-43c9-4566-95f0-d8fa23793380 |  | note | Note: Cultivation shall not occur within the extent of existing vegetation areas marked for protection or the drip-line of existing woody plants. Hand cultivation shall be used within root zones of trees to be retained.
label | 14657b85-7fb1-425e-ab8a-c9b6228a5606 |  | note | METHOD: Verify
label | f275a966-a952-4210-a155-183161f5f700 |  | note | FREQUENCY: Each Applicable Lot
label | 8041df41-6efe-4381-89de-839d2887831c |  | note | CATEGORY: HP
label | 9554100e-5a5f-4edd-ad24-361b59414875 |  | note | RESPONSIBILITY: SE, NA
label | 56273ed3-835e-49f1-b7a9-f444eb12a66c |  | note | VERIFYING DOCUMENTS: This ITP
label | f85f9598-fc6f-4076-bae5-14d3731ee587 |  | note | Attach Lot Map/Marked Up Area Inspected
text | fd906d3b-44d2-4b5e-8347-39684ddefb1c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Topsoil FSL
label | 20813bc5-22ad-4214-a578-e81a4b87eb1d |  | note | REFERENCE: Section 720.07
label | 48d1c613-83b7-4634-bfef-ce4a3d387708 |  | note | ACCEPTANCE CRITERIA: After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes.
label | 56d912f5-4cda-48e4-a5de-6c17ca06b6f3 |  | note | • Vibrating plates shall not be used.
label | 7ef51c26-9b67-4b3d-9869-fdad614470d2 |  | note | The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
label | 8015608b-fa4d-4bdf-b6e4-f56fa115d073 |  | note | The finished level of grassed areas shall be:
label | be344abd-6923-4136-8f12-6daaf253e468 |  | note | • not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls;
label | d6d9996b-a452-427c-b48d-ea7cc590f8ae |  | note | • level with the bottom of fence plinths;
label | b163af97-d1e8-4ea9-8c1f-82dca1bc6165 |  | note | • level with adjacent pavements, kerbs, pits and other structures.
label | 3b70f84b-aaa7-4780-9cc7-ebceab697768 |  | note | Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
label | f873155e-7a18-474d-90b7-beea8bd6d725 |  | note | METHOD: Verify
label | 76e48f4e-1c29-4b05-8af5-bf6491d62535 |  | note | FREQUENCY: Each Applicable Lot
label | 879ff50f-3471-46ba-aba6-ec8031e34810 |  | note | CATEGORY: HP
label | 5225f6d6-8a82-4311-915e-a67d37eb9562 |  | note | RESPONSIBILITY: SE, NA
label | 658a5eb4-d5e7-4eb7-9ab2-7ab6aced9c6c |  | note | VERIFYING DOCUMENTS: This ITP
label | 0f4538c1-78ca-420b-82cd-3f48ce1f2a9b |  | note | Attach Lot Map/Marked Up Area Inspected
text | a9d8756a-7c50-4987-af4e-7b5ed8636be7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Weed and Erosion Control Mat (if applicable)
label | 7c9fa218-4b7c-44ee-b95b-c0d0731d0e7a |  | note | REFERENCE: IFC Drawings
label | 8157113f-b424-4f70-8c5d-154e94a5c89a |  | note | Section 720.04 i)
label | 16ba6626-59fb-4d36-88cd-eaf72c5ac0e8 |  | note | ACCEPTANCE CRITERIA: Jute or approved equivalent to be installed as indicated by the IFC drawing.
label | 76032764-fd66-4acc-acb3-4148e121bc4f |  | note | Jute mat to be installed where specified on IFC drawings for planting areas steeper than 2:1 and in planting areas prone to flooding or within 2m of waterways, swales, wetlands and sedimentation ponds.
label | 940c5ecd-e83d-43ea-b3ad-55130d2902df |  | note | Mat shall be laid and anchored in accordance with the manufacturer’s instructions.
label | fa09f125-16c7-4fc5-a960-f12fb4c901ef |  | note | METHOD: Verify
label | 707f9fac-8180-4c79-bd69-ae9b29f5acdc |  | note | FREQUENCY: Each Applicable Lot
label | e0d38fb4-1c03-4dd8-86c6-c1a951f331d5 |  | note | CATEGORY: IP
label | d0f281e3-1049-4ed1-b45a-5f1cf194aec1 |  | note | RESPONSIBILITY: SE, Site Supervisor
label | 907c09eb-575f-4cb9-b631-0d15d3ce21a7 |  | note | VERIFYING DOCUMENTS: This ITP
label | 09ce4762-8f2f-4772-8ee9-7cb81dd07502 |  | note | Reference TeamBinder Material Approval No. if applicable
label | 276a79bd-5952-443f-83a0-3c7b796222f9 |  | note | Attach Delivery Docket
text | b9ba5529-8925-476c-8ef2-58ed2b607741 |  | textbox | TeamBinder Approval No.
text | 1d3095f9-25c7-4ab4-a745-6ac3f55a2f77 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Mulching
label | 9ede3646-ebc7-4935-b007-58b11220636c |  | note | REFERENCE: Section 720.08 a)
label | 3f7e64a6-4656-4487-86ff-695dfa8d95ac |  | note | IFC Drawings
label | 0ed87428-24e0-439f-a340-decadd618779 |  | note | ACCEPTANCE CRITERIA: Wood mulch to be placed at all planting areas unless specified.
label | 7af1fa14-33f1-4ff5-8259-619005c00e2f |  | note | Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all planting areas.
label | 115dcb53-a5b6-4914-9d9c-6145afa34eb7 |  | note | If space does not permit this, mulching shall extend to the back of kerb.
label | c882a5da-0610-4680-81f9-45cdf8396510 |  | note | Ecodynamics shall install mulch rings around individual tree plantings.
label | a96801b7-46e7-4900-a22d-470e2ce97736 |  | note | Mulch depths in all situations shall be a minimum 75mm and maximum 125mm.
label | 6c26b4b7-375a-4e5d-b5ee-be1845939a96 |  | note | Mulch shall be raked to an even, neat appearance and kept clear of plant stems to avoid collar rot.
label | c4e57f17-e4cc-4794-8de4-14622334c205 |  | note | METHOD: Verify
label | d6d9e390-eebe-4c64-869a-1f4a3a05f185 |  | note | FREQUENCY: Each Applicable Lot
label | 18ac798b-1109-46c9-be9d-c9e94d9d324c |  | note | CATEGORY: IP
label | dcc82c82-e958-460a-91ab-970b1f21953c |  | note | RESPONSIBILITY: SE, Site Supervisor
label | 9e816f10-c70d-44ec-8b99-047a09a44a0c |  | note | VERIFYING DOCUMENTS: This ITP
text | cfab8966-4a2b-4b2a-b0a6-ed03ff665b43 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6b501847-c50b-429d-8cd3-43b41419d9bf |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d01b63a7-770e-41f7-939c-c03b5789c64f |  | textbox | Name:
text | d37cdd15-379d-41e6-b51a-4c57b795a203 |  | textbox | Position:
text | 4462d132-6d1a-410c-a059-4e08919ae0f6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Grout Pedestals & Bearings Rev 0 | itp |  |  |  | Yes | ITP-STR-Grout Pedestals & Bearings Rev 0 | c45b1079-7313-4333-8fec-9b65371785c1
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 4dd9acf7-0e05-4e7b-a76f-89562db69dc9 |  | note | Document Title: ITP-STR-Grout Pedestals & Bearings
label | 91da737c-46df-42f4-9295-4e74b87f6f54 |  | note | ITP Description: Grout Pedestals & Bearings
label | 09ed3498-ff71-435c-b89d-5e36f45ff31a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | a4055b08-120a-4355-a7f4-f02e5b4cfd6a |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | d09ecc4e-9f8e-4ae0-b33a-0a7792bb00dd |  | note | Revision Number: 0
label | c06879b8-91ce-49fb-9e4d-ec97abe01f17 |  | note | Revision Date: 14/04/2020
label | 1a10f18b-e4c9-43f0-883c-b242fd2ec522 |  | note | ITP created by: Mike Freeman
label | 6d6c1905-7a80-44b1-983a-3d380302accf |  | note | 1.1 Reference VicRoads Section 610 November 2018
label | 642b7ec0-1538-4482-beab-c03828a49e4e |  | note | 1.2 Reference VicRoads Section 610 March 2019
label | 820a3a32-a46a-42f2-9f9a-5ebc967253a8 |  | note | 1.3 Reference VicRoads Section 610 June 2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Product Selection
label | 71431e8d-3bfb-47d6-b10d-0518c3e83179 |  | note | REFERENCE: IFC Drawings
label | b1115e6e-acc5-4fe9-98fc-83dc3d61b4eb |  | note | 610.28
label | 820d30fb-df50-4aec-bf21-21a0b7584041 |  | note | 610.33
label | 79d2c525-023a-44bb-80e8-7b978b60ce4d |  | note | ---------------------------------
label | d79b59d4-1626-4ec1-a645-04a24a930297 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 055f2a9c-2948-4e6f-bfcd-3ad9fc714cf7 |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | 0427a312-f6cf-4117-b7cf-c8069dd059ab |  | note | ii. have the required strength at 28 days as noted on the IFC drawings.
label | 62db0505-9245-4283-b507-525f48b5a393 |  | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
label | 7cfff605-f3e8-4c03-b140-f5116c652932 |  | note | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
text | 7dc68426-bbcf-43b3-99a8-62e3ac798927 |  | textbox | Enter: Teambinder Material Approval number
label | f88966e5-c6b4-41f5-ac93-de343424a079 |  | note | ---------------------------------
label | 88e0f2a1-f479-463f-98d4-6cb7f3155942 |  | note | METHOD: Document Review
label | 93de0e62-186e-424d-a81a-20bcbd3df201 |  | note | ---------------------------------
label | e0e4e433-da96-42b9-99b7-3b9cf341ba49 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | d5e4fa0a-90e5-4677-ab73-b1d799959129 |  | note | ---------------------------------
label | dd15df7f-4c0e-460e-84d5-57ec1cd79a18 |  | note | CATEGORY: IP
label | d5fb30a8-4b85-4589-b891-5c386aae4b1b |  | note | ---------------------------------
label | 10dda394-7fe3-4a32-a828-17fffbee515f |  | note | RESPONSIBILITY: Nominated Authority
label | 19b94f05-1e30-4bfd-b1d8-f172144c5bf0 |  | note | ---------------------------------
label | 3dd9d5db-2d7d-49b2-af8d-01421e0168cc |  | note | VERIFYING DOCUMENTS: This ITP
text | 84025396-e906-46fb-83b4-15a6718d6d92 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Curing Compound
label | 1a4b16f9-23fd-4f4a-b0d6-ece43c3aaab8 |  | note | REFERENCE: 610.23 (d)
label | c2d8ad92-27d9-4698-b693-d6f96bd15c10 |  | note | ---------------------------------
label | 6b85fa59-8b7b-4fb5-bd90-e6eb13106921 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 2c8bd1bc-d98a-42f0-bafb-8d6aa3709aab |  | note | Note: This may be the same product used for the concrete curing
text | 04f34b39-f7af-4e26-af29-051ebb30d615 |  | textbox | Enter: Teambinder Material Approval number
label | 649150eb-04b1-4fa3-b59c-1f3f130177c2 |  | note | ---------------------------------
label | 9b8e6d18-0f02-43db-9618-ec0e37f72d4c |  | note | METHOD: Document Review
label | dd512f1f-70f9-4dbc-85a0-715763b72381 |  | note | ---------------------------------
label | 68f777be-2d12-4e87-aeb6-014844dfd5a1 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | 9d1675b8-1562-4fda-abe7-e473b80f805e |  | note | ---------------------------------
label | 05394268-5732-43a7-92a9-2769e399ab57 |  | note | CATEGORY: IP
label | d8a46715-e48f-40b8-add8-510045bcd3ad |  | note | ---------------------------------
label | 77304e91-b1b4-4334-9d80-b5e222b37cad |  | note | RESPONSIBILITY: Nominated Authority
label | fbffa804-fa6a-49c6-9243-505e2ad779c2 |  | note | ---------------------------------
label | 1a9ac34e-0b74-4026-9c32-5bcebc1a13af |  | note | VERIFYING DOCUMENTS: This ITP
text | 521858d5-0b3c-42d5-a3aa-ca349fcc1b1b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Curing Methodology (for Concrete, Grout and Mortar)
label | 8058aaae-07a0-42ec-ae79-f5d708d40be7 |  | note | REFERENCE: 610.23 (a)
label | 770e4bbe-e539-47e9-aa24-3e4478f8d211 |  | note | ---------------------------------
label | d928d8e0-d55f-4dfc-a7dd-efc5e45e9185 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 75f18139-bcbe-47e6-9427-824bb6056bcc |  | note | Note: This may be the same document used for the concrete curing.
text | b1bf04d8-0245-481f-bdbf-aeb2811cdfe2 |  | textbox | Enter: Teambinder Correspondence Approval number
label | fdd751ae-0d8b-44e2-bf64-1ed18463db1b |  | note | ---------------------------------
label | e8b8b5ea-0d04-4aa3-abfa-8c25367e1cb8 |  | note | METHOD: Document Review
label | b875a025-cde1-4a75-983c-029e5db04bb2 |  | note | ---------------------------------
label | dc023b48-553d-4448-a881-80bf8c383deb |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | 8ee6c76b-47bd-4e89-bf9b-fc762eeadd5f |  | note | ---------------------------------
label | 53ca9c4e-8097-4b8b-905e-86f5ae69fcf9 |  | note | CATEGORY: HP
label | 187cf180-b8e6-4698-b0cf-4e429be1e4d2 |  | note | ---------------------------------
label | 015d471b-4ee6-4d72-8150-b0baf5bb452e |  | note | RESPONSIBILITY: Nominated Authority
label | 530f3c94-f6e2-4ed6-b6a4-7624b3fb8af5 |  | note | ---------------------------------
label | d72f6723-5478-4f7b-bb88-2993099f49c7 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b9960d6f-8e9c-4888-ac15-6239fc9e7139 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | f24f69ac-9dd4-422f-8af2-e5ffd6d95422 |  | note | REFERENCE: MRPA Quality Management Plan
label | 38c9d738-57a5-475b-ae8a-90eb85bc4165 |  | note | ---------------------------------
label | 8e55c4c1-6951-4ef9-879e-26b8322c1556 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 9811b88a-709c-4aec-8694-5ea7e05769e8 |  | note | ---------------------------------
label | b66332b7-586e-4894-a063-a9623d960a7d |  | note | METHOD: Document Review
label | 34c2efac-f7c3-4220-bba6-4e6c48eb40a3 |  | note | ---------------------------------
label | 4a028a95-6009-4982-aa18-db65bd913d3f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 1c6e5cb2-2603-4c42-8153-6201489444cb |  | note | ---------------------------------
label | 3645238f-7808-417b-9bbd-0c86c48f2640 |  | note | CATEGORY: HP*
label | 3b080dd1-3929-438b-bcff-f58925695a44 |  | note | ---------------------------------
label | 416e3b93-a193-4c85-b564-6e093bb940e2 |  | note | RESPONSIBILITY: All
label | 9084c612-273d-4b12-bc29-5a9e424068b9 |  | note | ---------------------------------
label | fe7833a3-1114-496d-901e-e682e5b746f6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3c40760b-0718-41e9-8c0f-acfb21ae77eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 369a6bfe-c6d8-4b19-aa13-0ac081055651 |  | note | REFERENCE: IFC Drawings
label | e07485fa-5aae-4399-9595-17431fe3c841 |  | note | 610.46 (a),
label | 0ce546a3-5d3d-44b9-b1c4-003c4fac0452 |  | note | Table 610.462
label | 816a63d6-dd65-4dac-a14a-38be1aa73003 |  | note | (Nov 2018)
label | 6e68b0f4-e75f-4d7e-b085-bc742cafe447 |  | note | 610.47 (a)
label | ad7fc1ae-7cca-4e0a-a245-84a9550329a2 |  | note | Table 610.472
label | dc6c8cd8-d877-41ca-b438-e117cc3c545e |  | note | (March/June 2019)
label | ef4a682b-e936-4fa1-8602-c38c6114e949 |  | note | ---------------------------------
label | f7111c68-4909-4198-bc37-1f739c3eab1a |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
label | 84fff597-75ac-458b-90e8-a6822c01a6cd |  | note | Note: Different revisions of 610 have different clause numbers
label | ddf9e83a-cc50-4e39-934f-f848118815ce |  | note | ---------------------------------
label | 54a8629d-1f96-43da-b3e6-60ff13705238 |  | note | METHOD: Measure, Visual
label | b6f45b18-eb08-405b-9daa-41867f1c415d |  | note | ---------------------------------
label | 4727c57e-dba6-401f-bf03-479849922da4 |  | note | FREQUENCY: Each element
label | e742afcb-96b2-432b-a72c-5ba24c7098bf |  | note | ---------------------------------
label | 4e0ed584-a54c-4a6d-be6c-b8eb0d81afe6 |  | note | CATEGORY: IP
label | 16cb7157-f016-49b9-86ac-97f34d3e4b04 |  | note | ---------------------------------
label | 73af80e7-5663-46d1-8e3e-d4dec63960e1 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 145b240c-2d56-4142-bdda-8491365b65d9 |  | note | ---------------------------------
label | a8489aac-dbb3-413e-9e5a-3aa9a0dc37ea |  | note | VERIFYING DOCUMENTS: This ITP
text | 1eabbaa1-a894-47c7-949d-67942858e929 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Construction Joint
label | d00fa500-5106-464c-b1fe-f00180d1dc62 |  | note | REFERENCE: IFC Drawings
label | 66eff939-c6d8-4090-b707-ec54c5045ff6 |  | note | 610.2
label | 2b875bb3-7b53-4e89-919c-02469b04e2e6 |  | note | ---------------------------------
label | 701dd2f8-2834-4b60-b0c2-bfacd12882e6 |  | note | ACCEPTANCE CRITERIA: Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
label | 4f09ac85-cbe1-43e6-aa03-675c6eb57880 |  | note | Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | 8e141ef0-746c-452d-a174-6ee7d894a4e3 |  | note | ---------------------------------
label | 64097dec-63be-4eec-b43b-260fd5a319a4 |  | note | METHOD: Measure, Visual
label | 2af66b43-7e91-4e15-954c-1527610fd685 |  | note | ---------------------------------
label | af4a7f8e-e2b8-444a-9bca-8944f1b6f7de |  | note | FREQUENCY: Each element
label | b4a3b8bb-d0ec-4b7c-bdbb-d54eb3edc2b0 |  | note | ---------------------------------
label | d1fcfae1-226e-45c6-a7b8-2d1cf7cc57c0 |  | note | CATEGORY: IP
label | 946ac162-bd26-4e26-9dae-823b20fad9de |  | note | ---------------------------------
label | e4c811ed-0ed9-478a-b9d0-8bc2d39ef950 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e2a6688f-f91d-4abf-8c7d-12c171603255 |  | note | ---------------------------------
label | a25a4fc3-9400-4f03-91d3-a00643645b31 |  | note | VERIFYING DOCUMENTS: This ITP
text | 87c7a8f3-0338-4880-85fc-800cca8bc39e |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Construction & Placement
label | 3468212b-8b21-401d-af18-1535a2a0c5a5 |  | note | REFERENCE: IFC Drawings
label | 5c2f5a61-9812-444f-930c-5400a1db627f |  | note | ---------------------------------
label | 1c36afa1-1df2-4ba7-a4f7-fa8c63fdc8bf |  | note | ACCEPTANCE CRITERIA: Dimensions in plan as per drawings (typically +50mm all around).
label | 0481189a-46d6-4d41-b962-d917ead12f61 |  | note | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | 1193f167-2b55-434e-a7e0-de0a5f66f8c9 |  | note | Any cast in componentry (ferrules, conduit etc.) secure.
label | 6e74d530-042e-46fa-a9bb-c1edcb0acedd |  | note | ---------------------------------
label | 838301b7-6bcc-49b9-aab9-5451917a1f7e |  | note | METHOD: Measure, Visual
label | 8ed14f2c-7f08-49a4-b820-172ac7ca4ad1 |  | note | ---------------------------------
label | f6ff4466-bd9d-40e7-a1b5-bcb7704446df |  | note | FREQUENCY: Each element
label | a27638f5-8f13-46a1-a3d6-b63afeb77e59 |  | note | ---------------------------------
label | 86af0933-cf1a-48c7-b7f4-1d7379624c05 |  | note | CATEGORY: IP
label | 9de4e11e-493a-4409-92a4-662a435a0e66 |  | note | ---------------------------------
label | 19b033ff-8ed9-409b-bf4c-29cde9323411 |  | note | RESPONSIBILITY: SE/PE/SPE
label | aa403202-4afc-4e92-af5c-4bafbc231906 |  | note | ---------------------------------
label | 1cceea89-759c-439a-84b2-472c27e82b75 |  | note | VERIFYING DOCUMENTS: This ITP
text | b34130e2-d731-4af9-b571-c5019033e1ca |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pre-pour Inspection
label | 9d9c3a8b-98b9-4bc3-8227-4283ac1ba370 |  | note | REFERENCE: IFC Drawings
label | 2d8dfbc3-f05e-4e4f-9569-1d20790cca99 |  | note | 610.2
label | 552cd04d-07c5-483c-a1e4-0842f9701de5 |  | note | ---------------------------------
label | 09c89e85-4ea0-49b5-a3f1-2317f31e8604 |  | note | ACCEPTANCE CRITERIA: Formwork location and RLs comply.
label | 5c903287-5aa9-4222-b45c-470bb7e6361b |  | note | Any reinforcement has the required cover.
label | 62c7f6e5-d67d-4105-b28f-9c2f6902e580 |  | note | Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | 0127c21d-f714-4303-b836-f7eb8a60627a |  | note | ---------------------------------
label | 61fa233d-7f7a-4ce0-aca4-ab8e20416762 |  | note | METHOD: Measure, Visual
label | 6fc20ee4-366e-4a09-932c-f599326e0d0e |  | note | ---------------------------------
label | c9f46ffc-6e17-49d5-abf0-c5b91b345983 |  | note | FREQUENCY: Each element
label | f823fbd5-4bbf-45ec-bc16-ef9d408a53e7 |  | note | ---------------------------------
label | 1e250d1b-0813-4c9b-b19c-82d73d215696 |  | note | CATEGORY: IP
label | 11207510-a884-4c01-ab40-180c7df381da |  | note | ---------------------------------
label | 74402b5c-e0cb-4c40-8ef8-1c2f93183678 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4be1060f-1d1e-4da0-95e1-687d963cfe9e |  | note | ---------------------------------
label | 339844c5-7e7f-4c5e-b74c-21ff4536ca1c |  | note | VERIFYING DOCUMENTS: This ITP
text | 48af33a6-1a90-4f8d-a7ad-25ef3151aec9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Weather Conditions
label | 41a12a18-e8f2-4113-913b-7cc312506f4c |  | note | REFERENCE: 610.17
label | 9f669c4d-8908-42f0-99a7-4a3197b09b48 |  | note | 610.17 (a) & (e)
label | d57bce2a-3936-4e86-87b6-39a8ab5c50b2 |  | note | Table 610.171
label | 7a94edbc-b954-4e92-b5eb-3f2cc6f9f7c6 |  | note | ---------------------------------
label | c207b308-5c75-457c-98f9-7e1792fd8178 |  | note | ACCEPTANCE CRITERIA: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 2fd6cde1-b683-4d0d-8f00-b9616754fb54 |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 677f1392-2c6a-422b-bf1b-2376230fc465 |  | note | Record: Required information on the Grout Pour Record.
label | c457433c-ef95-4ebe-b714-0537c84d70b6 |  | note | ---------------------------------
label | 36feec68-867f-4326-8762-cf17f8a7be3c |  | note | METHOD: Measure, Visual
label | b9d8925e-18e0-4b4d-99ab-8c763aee41ed |  | note | ---------------------------------
label | 6df3643b-1d88-4985-b04f-028315c4b3e7 |  | note | FREQUENCY: Each element
label | 4026238e-c681-4fdb-b9d8-3e388b85d53d |  | note | ---------------------------------
label | 7a304177-e340-4ca0-9ce3-c1ba150e9828 |  | note | CATEGORY: IP
label | e3a3d844-5666-4a8a-9406-c43f13b89160 |  | note | ---------------------------------
label | a0934c12-5ed1-4a4c-be9d-5d89a0f88947 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 381b53e9-79fa-454c-80e1-4561fc179c3c |  | note | ---------------------------------
label | 5b6b2837-18cc-43a9-8b53-eb398ee23349 |  | note | VERIFYING DOCUMENTS: This ITP
text | f85f3e95-3070-4635-9c19-8bdf3eb6e799 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Mixing Product
label | 62c5ff2b-db42-461a-ae4a-b13ad9dda418 |  | note | REFERENCE: Product TDS
label | 357983b3-4129-4f31-8d8d-937fee5b1627 |  | note | 610.28
label | 3b1fe7fc-f025-4c30-ac2d-d8d472d8aaf7 |  | note | ---------------------------------
label | 94cd88d2-659d-4b82-b224-40b108b2c7bf |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | d832c4cf-2bce-44ec-95b6-5e349f1f2445 |  | note | Only whole bags to be mixed with potable water.
label | 0d572403-3b8b-42af-a23f-f2c246eeb897 |  | note | Volume of water matches the required amount for flowable consistency and accurately measured.
label | 81fc89b2-6573-4316-bbab-fe04346332b5 |  | note | Product poured into the mixer slowly.
label | 9e8a177d-dd71-44f3-a448-12ac7f8efaf5 |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
text | 9c912128-1cf9-4052-b9ec-79ecf9d96d0e |  | textbox | Enter: Required information on the Grout Pour Record.
label | c465e64f-3a32-45eb-b557-94fa1706b7ef |  | note | ---------------------------------
label | 4abdd61c-7960-4694-9035-d76999e37896 |  | note | METHOD: Measure, Visual
label | 5febf784-f8b2-4e6b-988b-d6672562f8cf |  | note | ---------------------------------
label | 6468d08e-3215-41da-aec3-18fa18568eca |  | note | FREQUENCY: Each batch
label | b5b8cdb5-3bd2-4977-b74d-f14d2a914f30 |  | note | ---------------------------------
label | 6416024d-db80-4047-9bbd-0199baa4bd1f |  | note | CATEGORY: IP
label | fd91dc0d-66f5-423d-a3f7-15fd282ba27e |  | note | ---------------------------------
label | 7413ad29-1413-4ad2-80d3-ee30d9404bc4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | bb267cef-3d75-45fa-b54d-a6a9beeb121f |  | note | ---------------------------------
label | 47621344-61a3-49ee-b33c-569cbd2efc09 |  | note | VERIFYING DOCUMENTS: This ITP
text | 99e3e667-c9be-40ee-afe5-254bd31056f8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Product Testing - Compressive Strength Cubes
label | 3612c556-04c9-41be-b5fe-35007d795004 |  | note | REFERENCE: 610.28
label | 3e15f98e-8d10-4c39-b66b-5051c08acf5c |  | note | 610.33
label | d80bb033-43d2-465b-aad7-cd124e221d22 |  | note | ---------------------------------
label | 9c04fcdb-c6ac-46cc-9edd-8963cc2107dc |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | a25d600a-f89e-48ca-a087-d8e3125a2a62 |  | note | Testing is be in accordance with the following frequencies:
label | 7ff65cdd-7d93-4c1b-9982-f96cb691bf46 |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 0af1fa84-3d87-4f2e-b5c6-4cb55035cf17 |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | 34a73ecb-d34c-4cbb-96d6-625c5c76f1fc |  | textbox | Enter: Required information on the Grout Pour Record.
label | 81800232-538d-4bc0-b888-902ae13947eb |  | note | ---------------------------------
label | 18cec192-7aee-4705-acd4-33a77c86849b |  | note | METHOD: Test
label | 369ff5f4-f8d9-49c8-a803-8797c33deb8f |  | note | ---------------------------------
label | d45de0e0-d29c-45a0-8c6d-c95a131162e6 |  | note | FREQUENCY: Each element
label | 68b7452c-7bf4-4def-bbf4-1d54defca6eb |  | note | ---------------------------------
label | 79e4dd75-8bc7-4390-aa8d-2ee03828280f |  | note | CATEGORY: IP
label | 363d2fe8-707c-4083-a0b1-a2986909dd93 |  | note | ---------------------------------
label | e10e12f3-4845-439e-b0e9-413ba5173c8e |  | note | RESPONSIBILITY: Tester SE/PE/SPE
label | f54b49a7-90b7-4595-960d-c903667438e3 |  | note | ---------------------------------
label | 0cd86247-ff6d-4b17-9dce-ba71508bf4cf |  | note | VERIFYING DOCUMENTS: This ITP
text | ba19677f-1f52-4754-89b1-c9d3c7107ade |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Placement & Compaction
label | 0bdaeece-ac04-4970-8a6d-c9e9c005b74a |  | note | REFERENCE: Product TDS
label | 31d4ae86-cb03-4859-9464-67c8fd90485a |  | note | ---------------------------------
label | 928afe18-ad44-4e68-a688-75c091779126 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | 8f433f4a-8312-44da-a8ee-93c5e9be47b0 |  | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | b3ae9147-78e3-4277-a5ac-f1fc5ea9d047 |  | note | Product should flow to all areas and self consolidate.
label | 9d7cb0dc-c3c0-43d0-888d-746f72a9a272 |  | note | Product that stiffens or is showing signs of stiffening shall not be used.
text | 2e92d58b-6c38-4cfb-99ff-3a35ff4af23b |  | textbox | Enter: Required information on the Grout Pour Record
label | ec075ac1-b6cd-4f56-b1ea-b8f7037ae45e |  | note | ---------------------------------
label | 8891acb0-dda3-47ff-9b5d-b2469ae64aee |  | note | METHOD: Visual
label | 6225fc4c-9795-48ef-89db-26291baf95b7 |  | note | ---------------------------------
label | 4fa24237-0df0-4d18-a41d-cb9918b26795 |  | note | FREQUENCY: Each element
label | 73da03f2-332e-4f1b-85b5-39d8d4f9e1da |  | note | ---------------------------------
label | 3239aecf-4d9e-4596-aba5-915f4e6d3e78 |  | note | CATEGORY: IP
label | 6b18175f-9ce8-41da-9548-ee0b3c76a969 |  | note | ---------------------------------
label | 454f622a-214f-43ee-8868-433ceea8fec3 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | f05f9dd7-7554-4681-b795-addf428ac6c1 |  | note | ---------------------------------
label | 4ae9991c-a337-4ce2-8eb7-4a4e787e99b4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 63d803a1-5bfb-4f63-a3f2-7fa49ad9ac54 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Surface Finishes
label | 77f1bf3f-2bad-4631-a597-ad07a356b543 |  | note | REFERENCE: 610.28
label | 9f5e7d75-ca4f-4039-8230-0e52a3b6fec3 |  | note | ---------------------------------
label | 1c00a77d-4b7b-4930-a694-c6f8345e62d2 |  | note | ACCEPTANCE CRITERIA: Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
label | 79e73d95-f209-4a76-974e-265f65a4841f |  | note | ---------------------------------
label | ad620fa6-f063-4f5f-8d89-455a8c1ed410 |  | note | METHOD: Visual
label | 4a6da960-eee9-42c8-9d6e-321a1ff0e4c4 |  | note | ---------------------------------
label | bc1bfcb2-f329-4c55-9e23-598105ded743 |  | note | FREQUENCY: Each element
label | 9c44c35e-2b8b-4631-8b73-34d297f5b024 |  | note | ---------------------------------
label | e8b4525c-b89a-4699-94f9-f7bca2856d15 |  | note | CATEGORY: IP
label | 707db069-e522-47b5-a56c-91f883ac0170 |  | note | ---------------------------------
label | 7aceaa08-f665-4c51-bc7d-6a61da1f7044 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | cd391b06-4954-4ba1-bef8-1c6f8efaa4ed |  | note | ---------------------------------
label | d10ec90e-aa46-41ee-bed5-df26f842e4ed |  | note | VERIFYING DOCUMENTS: This ITP
text | 1bb8c6c4-2356-4b8c-a011-557c28e78a2b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Curing
label | c5ed8d30-b7d1-45e6-903e-6047e139309b |  | note | REFERENCE: Curing Methodology
label | 2c27c4c7-8c2a-482c-89d8-c90b87d8480d |  | note | 610.23
label | 65f389f2-0565-4dd9-a9af-cd04716ac656 |  | note | Table 610.231
label | fad91218-84fb-44db-9232-9ec27dabb9b9 |  | note | ---------------------------------
label | d106935d-cf26-4c22-9e99-60dab2248fb7 |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | 060bf272-66d6-4724-81d2-d8a077ea48bf |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 7c5828ae-a1ff-48b8-8b53-231b7d50035d |  | note | ---------------------------------
label | 045c5316-c803-418d-b22d-b92f12c7daee |  | note | METHOD: Visual
label | 7b0112b3-a93c-40a8-b91c-230c0d245510 |  | note | ---------------------------------
label | e2c1fe36-ed23-45d4-a72d-ac262254cbdb |  | note | FREQUENCY: Each element
label | 116b88e4-6c65-40e7-a786-7b205ea855f3 |  | note | ---------------------------------
label | a03dcfd6-b813-4fcc-98e4-83cf4fea834d |  | note | CATEGORY: IP
label | 5ea7460f-28d5-40e4-9ae4-65a9099954a4 |  | note | ---------------------------------
label | a139ee3d-332a-495e-a881-1db0dbfebe07 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | ef1f228f-bbd1-4d22-9e92-b8fb7aa00364 |  | note | ---------------------------------
label | a256b742-c8cf-48b0-844f-72067da3cbd5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4e64f0b0-949c-48df-9e81-e4173d68d91d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compressive Strength Test Results
label | 67314c3a-2c22-4f88-ad67-4256fcf52934 |  | note | REFERENCE: IFC Drawings
label | 558e8317-98c8-4574-9880-1e4c6d8609b9 |  | note | Product TDS
label | b486a1be-73e1-4917-ab7d-975ffc0eed23 |  | note | ---------------------------------
label | b7142bb8-4112-4052-83b7-09ff4bcdd05c |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 664a4f04-2152-4946-a35b-987702d6da10 |  | note | 28 day compressive strength per sample comply with the design strength.
label | a708a088-93b2-4949-b3c9-48e44257309f |  | note | Attach: Compressive Strength Test Results
label | f8afb7d3-b82f-486c-9f31-c61642740d28 |  | note | ---------------------------------
label | ef5e5eb6-9898-4cb6-a585-a6e0c2212580 |  | note | METHOD: Document Review
label | 213df565-3536-4283-b1e8-cdf94dc07338 |  | note | ---------------------------------
label | 9539a6c9-abf2-4db2-a2d8-b1483ef8f1be |  | note | FREQUENCY: Each cube
label | b2c1e90f-9f89-4ffb-b42a-56e571ca601e |  | note | ---------------------------------
label | c746d5b9-d05f-4688-bbb7-8a9d12bc888d |  | note | CATEGORY: IP
label | b9389a94-9c89-4862-84fa-73a777cc9fa2 |  | note | ---------------------------------
label | ec0be58e-adb1-47b2-9d45-34780e005e01 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a1f48c90-f95e-4088-9a4d-4e582b918da3 |  | note | ---------------------------------
label | 9d1e84e9-a7df-4d3c-92dd-5e0e29af5894 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1c4fab6d-d3ba-409c-9e0e-3f02ab82b494 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As-built Survey
label | 6b26d005-7be2-46b3-aa03-33ce96dc4a04 |  | note | REFERENCE: IFC Drawings
label | 568c8538-48f1-4abe-8191-806d581d2bc4 |  | note | 610.46 (a),
label | d1a1b92f-2c1d-4403-950e-dd25cfc63f0f |  | note | Table 610.462
label | e9bc4779-157c-49b7-945d-9619ca44a7a1 |  | note | (Nov 2018)
label | f4a6ca3d-caba-4602-ad46-40e27da06dc3 |  | note | 610.47 (a)
label | 0aaf6a87-0c2c-4ab1-8ef3-a4dc4fd86cc4 |  | note | Table 610.472
label | c0962709-f98f-4b64-a44b-ac8af409a2bb |  | note | (March/June 2019)
label | fbf39f1e-1903-47be-9b5d-d29d186bb9ff |  | note | ---------------------------------
label | f0cae71b-40f6-474c-8625-c8205ecdbabe |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
label | 43bb2c1f-69ea-46c0-a28f-cf91782bec6d |  | note | Reduced level ±2.5mm
label | 768ef8e6-3f95-4302-8e43-dea40b852362 |  | note | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | cfb785c8-6e38-48bd-96ce-c7d474b1ed24 |  | note | Deviation from flat surface ±1mm
label | 90eb1208-acf8-4d7d-987f-dbc91cdd75c9 |  | note | Note: Different revisions of 610 have different clause numbers
label | f0ad0355-b9a7-4a62-bb2f-d91820b649da |  | note | Attach: Survey As-builts / Survey Report
label | ec378961-3424-4e7c-952b-740a3359fb74 |  | note | ---------------------------------
label | cf4b198d-1401-4129-ad97-530bb578c634 |  | note | METHOD: Document Review
label | 29a174f8-38fc-449c-821b-306f5cdc771a |  | note | ---------------------------------
label | 7aa76585-5320-432a-a7b2-8144e3f27ed5 |  | note | FREQUENCY: Each element
label | f03b3d2d-db38-4cc1-b750-f507177f0d4b |  | note | ---------------------------------
label | 24e421dc-f3af-4e84-94b6-7b2404deca9e |  | note | CATEGORY: IP
label | 2556907d-f468-48ac-a836-3c6c93dd8b36 |  | note | ---------------------------------
label | 41826db3-717a-474c-b119-02a2bac4937e |  | note | RESPONSIBILITY: Surveyor PE/SE/SPE
label | 55de4665-f8e1-4897-8e29-86815f5e30e9 |  | note | ---------------------------------
label | 164e12cb-586d-43e6-a1b8-7f5a54a7f34f |  | note | VERIFYING DOCUMENTS: This ITP
text | c52accff-af6e-40a9-b803-73b3bf310885 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | d9fb0f0c-7c37-4a1a-aac5-f75050feb686 |  | note | REFERENCE: MRPA Quality Management Plan
label | e5b11fcd-00a0-4f11-a758-e9fbfed2dba0 |  | note | ---------------------------------
label | 760eb6b4-bdd1-49aa-a217-4fed73278992 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 355a4e39-0c72-4c29-805d-80afc1426133 |  | note | ---------------------------------
label | c794aff5-0428-4feb-ab67-261945c2ce7d |  | note | METHOD: Document Review
label | d9dc4d83-8e41-45d0-aa8b-2c905e76dfde |  | note | ---------------------------------
label | bcb90547-784f-4011-8709-d45cb2553059 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e728c138-5dcb-47db-ac5b-012e4f1bfe63 |  | note | ---------------------------------
label | f674bf4e-1ad5-4505-83a6-250f654e192c |  | note | CATEGORY: HP*
label | ed04d055-9b1a-4344-9599-8d737161e066 |  | note | ---------------------------------
label | 330c09ed-5752-4a21-b388-6656ec54c191 |  | note | RESPONSIBILITY: PE/SE/SPE
label | ea014314-f7fa-478a-93c0-ed8f2c1229de |  | note | ---------------------------------
label | efee61d1-7c0f-4320-bf83-b796c36e3d19 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7ee43e31-127d-425e-b713-c0dd53b86101 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 13a47ac7-cf7a-446d-8afb-fd9761741d54 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 059dd5bd-bbcb-4222-9e30-d26a0ad7c0d5 |  | textbox | Name:
text | a2418551-e33c-42ae-9eee-c3cc8ecb2aad |  | textbox | Position:
text | 325bee08-f221-4a1b-8292-d85994bfc486 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Miscellaneous Structural Steel (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Miscellaneous Structural Steel (Supply & Installation) Rev 0 | c6089456-767f-4ba0-a349-1aee5ff52bf5
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | c25c3f49-166f-439b-97fa-1d2ee4a0c37f |  | note | Document Title: ITP-STR-Miscellaneous Structural Steel (Supply & Installation)
label | 93cd5325-e508-41f1-9255-849b5689ea75 |  | note | ITP Description: Miscellaneous Structural Steel (Supply & Installation)
label | b108da0b-15d7-4251-abd0-384f8bf51045 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | f8444de8-c022-4dc4-a4ee-0c2e68469b25 |  | note | Revision Number: 0
label | 4931b9c6-066e-4377-9248-1fa24cfc03ac |  | note | Revision Date: 4/05/2021
label | f774fc56-18d3-4ae7-a895-cad26d116976 |  | note | ITP created by: Mike Freeman
label | c1b57e1b-b118-4dec-b704-3bcfb1d6c1e7 |  | note | 1.1 VicRoads Section 610 November 2018
label | 54de273d-2394-40a3-97e6-12b39f39f7cd |  | note | 1.2 VicRoads Section 610 March 2019
label | ccb161fc-7d91-4d13-b353-02e99f646ac6 |  | note | 1.3 VicRoads Section 610 June 2019
label | 625a542e-4364-4388-87f4-2db753a55ef2 |  | note | 1.4 VicRoads Section 630 October 2013
label | 4ca683b3-f23e-4c06-8e3f-c04cbbc36ed9 |  | note | 1.5 VicRoads Section 631 February 2009
label | adcdacc8-733b-4ff9-b06c-2ea9090916e6 |  | note | 1.6 AS4100-1998
label | ac1d9a7d-e5c6-4617-b64b-2587886af1b4 |  | note | 1.7 AS5131-2016
label | fde9727c-0350-44c5-a5b7-57e9ba736b53 |  | note | 1.8 AS4680-2006
label | 571de948-7f7c-43d1-b451-ff58553e0b1e |  | note | 1.9 AS2312.1-2014
label | f85c26ea-ec4f-4d8d-a658-16e0762062e4 |  | note | 1.10 AS4506-2005
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 3b4fff29-7637-47d7-bdfc-fda5c2717a95 |  | note | REFERENCE: IFC Drawings
label | 6f0d585c-a3ef-4676-b35d-7624eb0a7031 |  | note | MRPA Quality Management Plan
label | 7d7d45cc-6713-4859-8908-0e8e8accb17d |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 9db3b64c-7cf4-439c-a87f-981482d853cd |  | note | Typically this consists of but not limited to:
label | fd2f5f5a-4b42-47fd-9f0c-f4a97b03d648 |  | note | i. Certificate of Compliance
label | 0e0dca0e-3292-4b6b-a891-7ee3349d6627 |  | note | ii. Completed ITP
label | 3989fc75-5fd7-429a-b9c9-11f96687779b |  | note | iii. Weld Procedure Specifications
label | a4fd8777-27de-4c84-9388-ea34cf869059 |  | note | iv. Weld Procedure Qualifications
label | 74797a3b-8c3f-4df4-949c-7de4c215694b |  | note | v. Welder Qualifications
label | d9aa03fc-4db7-4f91-89bc-c545e03cdec2 |  | note | vi. Material Certificates and traceability
label | dd34d510-b327-4b3d-9e6e-74a83aa2ff86 |  | note | vii. Quality Assurance check sheets
label | 01c1b506-d25b-45e4-bada-e836fdfc49a5 |  | note | viii. Welding Consumable batch certificates
label | 81308cfe-7728-42b9-9976-11a61b33779e |  | note | ix. Coating certificate(s)
label | c1168043-152c-4f4b-88fd-0dd79e3ece8b |  | note | x. Non-destructive Testing (NDT) Reports
label | 88a68d9c-2bc1-4c4f-a2a0-e8b427994850 |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 7889ee00-557c-4540-aa1d-6244070532fe |  | note | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | f117865a-d6aa-40ed-b94b-344d179be5ac |  | note | METHOD: Document Review
label | 773c5058-aa85-47e5-94f8-ab37cea4cd9a |  | note | FREQUENCY: Each component
label | 9e2d7e69-41d9-43fa-9ed1-9a93dd2d35e6 |  | note | CATEGORY: IP
label | e5ffb90a-7565-4b94-8203-feb1bf8e9f5e |  | note | RESPONSIBILITY: PE/SE/SPE
label | e6b012e1-fc6a-4307-9fcb-cb0f281d1f07 |  | note | VERIFYING DOCUMENTS: This ITP
text | 15c7151f-cb42-4fbb-84bb-ccd26c8554c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | 28f69d78-b620-4d8b-93c6-0978cf3b8be5 |  | note | REFERENCE: IFC Drawings
label | 08f02dc8-1193-4f4f-8bdb-bcfa93169825 |  | note | 610.33
label | d7b302b9-c611-4025-bcd5-e1041aa0e857 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | ab80eaf2-d4c8-42e3-90d6-755c85a6ee6c |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | 63d82404-3606-47ae-99fa-de42c29d4a30 |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | ea8f984c-1144-4c4e-a258-83f37f37aeca |  | note | iii. have a flowable consistency
label | 1758a85a-e8a2-41d2-8a03-ee0c82ccb518 |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | d0ca6e11-aef9-484a-8059-79fbb5f691d6 |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
text | 213926b9-7dce-40b3-a403-72dc448474aa |  | textbox | Enter: Teambinder Material Approval number
label | 51609451-a43b-4c27-8fa0-c81ee685deba |  | note | METHOD: Document Review
label | ed279f1e-b887-4023-8356-021625e7d7fa |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | ecfe2182-3cfb-4615-8557-d5c1f8aefc87 |  | note | CATEGORY: IP
label | 46030d30-6006-452c-90cc-a99a746df8f6 |  | note | RESPONSIBILITY: Nominated Authority
label | 5ac54356-7249-40ee-99a0-90c2ae289196 |  | note | VERIFYING DOCUMENTS: This ITP
text | df516284-e521-4b55-a12b-4a408dfb1c3b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | 602abd8e-ee5d-4cc1-8e9f-bd34d39e124e |  | note | REFERENCE: 610.23 (d)
label | 4475b65e-084b-4a35-8d60-c0c8885ed439 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 20546251-8018-4cf5-a721-b894ab2e5887 |  | note | Note: This may be the same product used for the concrete curing
text | 85ec795c-e388-4d49-9053-b07f8bf47110 |  | textbox | Enter: Teambinder Material Approval number
label | c9326581-e413-490f-a392-1473316f104e |  | note | METHOD: Document Review
label | 21400609-af44-4350-b429-518a227d2bf4 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | 2c7062e0-a364-4909-817c-eb86b785cbfd |  | note | CATEGORY: IP
label | dd6f9b56-bf85-4705-ba26-ddc724a19246 |  | note | RESPONSIBILITY: Nominated Authority
label | a82cc1bd-5a91-4465-8162-357762ea614f |  | note | VERIFYING DOCUMENTS: This ITP
text | 187e64f6-b6ae-4819-933f-40f3fba52d13 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Curing Methodology (for Grout and Mortar)
label | 909b8d49-25d2-4646-a90c-06a0a6b308c7 |  | note | REFERENCE: 610.23 (a)
label | 44234c52-c977-457a-a330-dd716cc79e73 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 2ff5a7c7-db4c-4888-b40b-6a3146cd177e |  | note | Note: This may be the same document used for the concrete curing.
text | 066cf4d1-8501-4ba4-898c-ca0430acb085 |  | textbox | Enter: Teambinder Approval number
label | 4a25bdd0-896b-4750-8daa-7f12c916c47f |  | note | METHOD: Document Review
label | b2382c58-64ea-409c-99fa-36ec2463e712 |  | note | FREQUENCY: Where applicable, once, 4 weeks prior to placement of product
label | 97998c79-e7e5-459d-afd1-8cabef15537a |  | note | CATEGORY: HP
label | 8549d64e-582a-47b1-9f0a-b6f050cd83eb |  | note | RESPONSIBILITY: Nominated Authority
label | 6a3985e7-5948-4f49-97e1-3eeb0b88259d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b356f739-def9-467d-b094-507747d8c015 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Bolted Connections Using Direct Tension Indicators (DTIs)
label | 12e9ec60-5a1c-4abb-abc7-53fa6af7456d |  | note | REFERENCE: 630.20 (e ) (ii)
label | 42e7feea-9744-4bd4-beff-eac4205e9c53 |  | note | AS4100 Clause 15.2.5.3 (a)
label | e55a8650-ce4d-4fee-92a8-58a19adf46fb |  | note | AS5131 Clause 8.5.7 (a)
label | a9ff77ed-d7c4-49ea-8477-215fccfd5801 |  | note | ACCEPTANCE CRITERIA: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
label | 49838752-509d-4623-8155-db3e07f722f3 |  | note | i. technical data sheet or information on the product
label | b706a787-efe5-4825-b537-ed06759d32f2 |  | note | ii. 3 no. min. correlation tests between a calibrated torque wrench and a representative sample of each bolt diameter/length/grade combination to be used in the Works.
label | 7d1481d4-0a6b-4319-b001-fe36626eff64 |  | note | iii. a valid calibration certificate of the torque wrench
label | 047d18f6-a877-41dd-95cc-90e991aa4634 |  | note | Note: Daily records of use and correlation between a calibrated torque wrench are required, see 6.3 in Post-installation.
text | 5263cf9c-3882-4808-b956-2108cc24fa5f |  | textbox | Enter: Teambinder Approval number
label | 0646dcbd-84d9-44c9-9b01-504b23a91401 |  | note | METHOD: Document Review
label | 6a5c4eeb-9220-4241-bc6b-a96d4f4be265 |  | note | FREQUENCY: Where applicable, once, 14 days prior to use of devices
label | 5df7005e-455e-40dc-a9a0-7485b30f1606 |  | note | CATEGORY: HP
label | e93e4273-777c-441e-aee2-9468f25e0bc7 |  | note | RESPONSIBILITY: Nominated Authority
label | a7848124-79fc-46cb-aa57-d916702d2a3b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 67bab63f-fdb4-43a7-9024-00f2f8c0b712 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 581e1dae-0ce0-4c4e-8fd1-8b92f5887c8f |  | note | REFERENCE: MRPA Quality Management Plan
label | 5f7fa292-1f1d-4e4b-a53d-dcf3859a8959 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | aa0e7acb-28fc-4321-8018-9953830adeea |  | note | METHOD: Document Review
label | e813afdc-9c03-41d1-9eb7-3a278c9caef4 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | e4dc7cd9-3d1f-4fc1-97bb-709b96434a88 |  | note | CATEGORY: HP*
label | ee49f113-463b-49a2-8682-373ef6aa1a42 |  | note | RESPONSIBILITY: All
label | be4ead16-ec7d-4021-b4b3-86209d673c0b |  | note | VERIFYING DOCUMENTS: This ITP
text | 415da6cf-0dc7-4bc7-9d3c-391059c7bfde |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection Checklist
label | 311e71b3-2571-45e8-8bba-8a3c3eece92a |  | note | REFERENCE: IFC Drawings
label | ecf605cd-ad26-4975-a8e6-46c7017fef18 |  | note | 630.08
label | 4bce1b9f-85a0-4c49-8bba-5be2e3991f26 |  | note | 630.09
label | 5632443c-259a-4157-934f-9e50253fbea0 |  | note | 630.20 (a)
label | d730f6f9-f3d4-4bbe-a2ae-555344abf112 |  | note | 631.06
label | a3383af8-e71a-4f74-bd50-c2f1e7832bf3 |  | note | AS4860 Clause 7
label | 452b519b-5458-466d-908b-4e6fbfc4a92d |  | note | 631.11 (a)
label | e7b6d9d1-295d-411a-997e-b7f3f3c928a4 |  | note | AS2312 Clause 9.6.4 (i)
label | 863751fa-39ba-4dc2-9d25-bcaa043b24e1 |  | note | AS4506 Clause 2.3
label | 7c4b1a41-d974-41f3-ac3c-ddd6d956efdb |  | note | MRPA Quality Management Plan
label | 22f79d95-f02e-4182-a599-e734e4ef6bcc |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | 02b13086-d04d-439d-bdac-082c2c2882c1 |  | note | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | 7853f07a-03b8-422b-a6d3-7c1e9d721f72 |  | note | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | e930a392-6eca-4d90-a727-584083e2ce2e |  | note | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | 59a3d4ca-a78d-4275-a867-99c25220e99c |  | note | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | 2b720a71-0492-4362-bfef-be0ee9e8d3b3 |  | note | Complete: Materials Inspection Checklist in ConQA
label | 985c208d-49bb-4767-828c-8da0a1b71e6f |  | note | METHOD: Measure , Visual
label | 64550164-b715-4ad8-a7a4-7336ccec9069 |  | note | FREQUENCY: Each component
label | 0bab2c46-f66a-4ea4-8d23-7f6c20a78f43 |  | note | CATEGORY: IP
label | afdff098-ee24-4cc1-ade8-3c71b5fc1ef9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d0459782-d747-4ade-b11e-5de0286d376b |  | note | VERIFYING DOCUMENTS: This ITP
text | 7fef3d77-7c06-46d8-b82c-1fe0a083fe79 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | 3808180a-18a7-4a1d-b9bd-8df5000e56d0 |  | note | REFERENCE: IFC Drawings
label | 9cbb73bf-0167-439d-9deb-2345d16b8f37 |  | note | Product TDS
label | 15f7be2b-453f-45a1-82b4-3179bf553e0c |  | note | ACCEPTANCE CRITERIA: Prepare the bearing surface in accordance with the Grout/Mortar Product TDS.
label | 1b629bb0-49d6-41c7-98a0-f7cd0acd3f38 |  | note | As a minimum, ensuring that it is clean and free from loose particles such as rust and laitance.
label | be2c8389-f13d-4848-a297-d0b8bb8cd0ea |  | note | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
label | e779d6ea-83b1-488d-b563-aa4dc464525b |  | note | METHOD: Measure , Visual
label | 9af3cba5-1a1c-4d38-a12a-5b96e0421276 |  | note | FREQUENCY: Where applicable, each installation location
label | dce53b92-a7be-4cb8-a168-6fe8c3df90f9 |  | note | CATEGORY: IP
label | 2e0dc5de-f571-4aea-ac74-640847169c9a |  | note | RESPONSIBILITY: SE/PE/SPE
label | e82c33fc-f4a5-4ef8-a12e-c7736f00c12e |  | note | VERIFYING DOCUMENTS: This ITP
text | 843f8645-6bf3-4abe-9de1-af1e3f198ed9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | 42ad72a4-254b-421e-87c5-41354e6edf43 |  | note | REFERENCE: 630.09
label | 7f6b9f00-60f3-4013-9e7b-3d8a0445c527 |  | note | 631.14
label | 582e3723-7efc-484f-9e64-f93a742319d9 |  | note | AS4100 Clause 15.2.2 & 3
label | fc60cf95-c660-4945-b244-aba422325144 |  | note | AS5131 Clause 11.5.6
label | d8618d36-738e-4c28-a22e-b57ab5c3b905 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 94bac920-ebbf-4fcc-a6aa-7981e88c4f51 |  | note | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | e9a5116d-b29b-4504-a007-63b830bc6640 |  | note | METHOD: Visual
label | c8ea75c8-5160-4a75-bdae-ae975fcff661 |  | note | FREQUENCY: Each component
label | 442ae9bc-b405-43ad-a985-30877b6ff988 |  | note | CATEGORY: IP
label | a02858e5-76ce-4da5-ac72-579932ac3f42 |  | note | RESPONSIBILITY: SE/PE/SPE
label | abe1334e-7aea-4d17-bb3a-35033893bd44 |  | note | VERIFYING DOCUMENTS: This ITP
text | 87cd91f3-1245-4ae4-a632-9a89db863bae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | ce76e84b-2307-46c6-81d0-38274e23c8d4 |  | note | REFERENCE: AS4100 Clause 15.2.3
label | 0c362376-540a-4daf-b533-9c80195a9dbb |  | note | AS5131 Clause 11.5.7
label | 679adda8-53e5-4a27-a064-0e3c2ed6159b |  | note | 630.12
label | bd50e908-3124-45cb-aa0d-ec579566ef7d |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | 43f1909d-6136-40ad-a0e5-dfd54fe4a6a4 |  | note | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | fca853fb-25e6-430a-94ec-9b5fecd588b7 |  | note | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | 0bf7dc63-5a9a-485f-bcb1-29bee6d3e86f |  | note | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | e3048d6b-e37e-4448-8df6-dd623214e021 |  | note | Holes shall not exceed the greater of:
label | d7440328-9227-4df8-b99f-08ce971427b0 |  | note | 1.25 x bolt dia. OR bolt dia. + 8mm
label | e64ac5c2-3fa5-498d-afab-d54b4c569444 |  | note | Slots shall not exceed the greater of:
label | a71178fb-da4c-45de-b622-01b1e8a44d65 |  | note | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | cbdc7459-a924-4a6a-97aa-5b7b52d04cbf |  | note | METHOD: Measure , Visual
label | 81e4b34b-b738-45b7-a218-7723cf18b7a0 |  | note | FREQUENCY: Each component
label | 1fa2df3c-6ad0-49e5-8f24-62ce676d3e77 |  | note | CATEGORY: IP
label | 5fd6d943-2027-4065-84d6-5317beb2cd71 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e9c66b92-6e03-4cc7-9f6e-32e6bffb35f9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6d67b88b-0490-4e63-96be-11328f402fb2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | 1a4d03d9-d49c-4f1f-b565-be6aae4325af |  | note | REFERENCE: IFC Drawings
label | 869c0d3c-c110-414d-b694-a08ebc1bdb00 |  | note | 630.20 (a) & (c)
label | 27522a2e-95dd-4d06-a89e-75233b088092 |  | note | AS4100 Clause 14.3.5.2
label | 4550cfa9-10f5-4262-ab7b-5a6bec647157 |  | note | AS5131 Clause 6.7.4
label | c594520f-c03a-4f13-a298-45955db4cf50 |  | note | AS4100 Clause 15.2.5.2 (a)
label | aadda739-6275-4523-8656-bfcdc0d88f00 |  | note | AS5131 Clause 8.3
label | 9bddad2d-2445-4b65-8aa6-0f7a56a7c89b |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 2ad5e823-bc87-41cb-9e11-5e2cd8aa1426 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | 33196f15-036c-4f06-a529-a725a19b0147 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | 72099882-bc10-4643-a343-17f53b9e2aee |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 5f0461b4-e0a4-442f-851f-22064d114fb6 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | b380ffac-63b4-4426-a05b-0cf0b9834e7f |  | note | METHOD: Measure , Visual
label | 5e4f4967-c879-4560-b8c1-7d662cac85c5 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 43f473fe-0b96-4f01-916f-20cf9884050a |  | note | CATEGORY: IP
label | 130f61a1-7601-451f-9a10-542b1f1f9937 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c91374a4-0c57-4ff1-882d-5b5c3006ae81 |  | note | VERIFYING DOCUMENTS: This ITP
text | a588220f-6697-4ba3-8f54-9b3d44c27a8e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Fastener Tightening - Tensioning Condition (8.8/TB & 8.8TF)
label | a1082a95-f2b8-4d35-ab94-1c3c4686cd26 |  | note | REFERENCE: IFC Drawings
label | 598c942e-4ec7-494a-b440-fd82739f63f8 |  | note | 630.20 (a) & (c )
label | 9e3b8c2a-737a-402e-bb72-bcb661759337 |  | note | AS4100 Clause 14.3.5.2
label | 8b96d7c1-9cc5-474b-bbfa-fdf2d54d49dd |  | note | AS5131 Clause 6.7.4
label | ab338e41-ef9d-437c-b97d-c13f139adcb7 |  | note | AS4100 Clause 15.2.4
label | 062a32a6-f4b5-4000-85e6-17596f3d918c |  | note | AS5131 Clause 8.5
label | 711f7057-9b15-4184-99de-796e6bcdf3a4 |  | note | ACCEPTANCE CRITERIA: Nuts shall be either double faced or washer faced type.
label | fe7c7315-1ef0-41e0-8376-8bf8d56d2bd5 |  | note | Place bolts, washers and nuts as detailed on the IFC Drawings with the high strength designation on the bolt and/or nut remaining visible at all times.
label | 98ccdcc9-0f3a-40e4-b4ac-fbd30e5f4a59 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | 593ac2d8-c5f6-4c7d-96c7-0e78ba5d8781 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | cf5213b1-60ca-45c5-8ee5-6122577d305c |  | note | Tensioned fasteners shall begin with the snug tight condition.
label | 1de9f12a-ae23-4e51-ad82-2d07cbc47dc4 |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | 87a110c7-03f2-408c-88e7-a380d66e5db4 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | af06f8b6-0a5c-4a0a-9540-cdcf7e63728b |  | note | Mark a datum point that crosses over the static part and the rotating part before tensioning via torque wrench, part turn method, stressing jack or direct tension indicators.
label | c6298132-1b30-43f0-b07a-2bfeae21ce56 |  | note | METHOD: Measure , Visual
label | e1a8f965-4f1a-4d63-be21-2f0010efba9f |  | note | FREQUENCY: Where applicable, each bolted connection
label | 20af66f6-68da-4b3f-95a4-ba5b4ace0e53 |  | note | CATEGORY: IP
label | 195752e0-2279-4f41-825d-9984e5519cc8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b02e9824-441c-4b0b-9d82-a52063a3337a |  | note | VERIFYING DOCUMENTS: This ITP
text | 8e5fa99e-b7a6-4b45-be27-10070144a5af |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Survey Conformance
label | d3f78b56-1fd7-4926-af5b-e95c12f37c42 |  | note | REFERENCE: IFC Drawings
label | c225bf58-4d56-4021-a041-15bf4e74f1da |  | note | AS4100 Clause 15.3.1 - 7
label | 0244dbf2-15e7-4e05-ac7f-f99c30a13a19 |  | note | AS5131 Appendix F, Table F3
label | 3a21713b-47ef-4a54-b7bd-8dd72eafe985 |  | note | ACCEPTANCE CRITERIA: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | 2a3d9d13-b706-4ec4-b2a3-8a993d1884c6 |  | note | Departure from RL = ±10mm
label | 9a1f3102-9bd0-4d33-91ae-bce2a6a509c0 |  | note | Departure from plan position = ±6mm
label | c0fd9639-ce24-4ab5-a05b-417e4e35c3d7 |  | note | Departure from alignment = ±6mm
label | 09ba30a2-3064-4159-88b9-ca4fe665094a |  | note | Irregularities in alignment = 25mm in 30m
label | e70fd4ac-be3b-48b4-b565-d8cca54e20d9 |  | note | Projection of bolt = +25mm, 5mm
label | 5df01675-4a29-4c61-af49-6548e994989b |  | note | Location of beam = ±3mm
label | 26b99e2f-d77c-4513-ba09-c7d4e487bdf1 |  | note | Location of column = height/500, 10mm max.
label | 60669d2a-2f9d-4d82-bc91-bcb5d795d288 |  | note | Attach: Survey Report
label | cd43a0d0-89b6-4d3f-b871-a9785573339c |  | note | METHOD: Measure , Visual
label | 5c93720c-00df-44a8-99c8-0853b43bad10 |  | note | FREQUENCY: Each element
label | 87898743-6040-4a8d-b37d-a2b8e568cd57 |  | note | CATEGORY: HP*
label | 19a5b8cc-da7d-49fc-853d-aef073c3e994 |  | note | RESPONSIBILITY: All
label | 88ad6938-ed78-4285-bfab-8c13de7cb317 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3d2f9326-fe9d-4603-8c39-60807444d0f6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Base Plate Formwork Construction & Placement
label | 1f2c8f6d-8734-4836-8590-deec12f71013 |  | note | REFERENCE: IFC Drawings
label | 2f6b9c79-f29a-4cb3-9099-ca8cac2d24fd |  | note | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
label | ba295afc-cf22-4401-adbc-426b9734e5cf |  | note | Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | 59892eac-7f0c-4e18-b01d-91f5d28a5d23 |  | note | METHOD: Measure , Visual
label | d552e37f-3af4-404f-9013-34f320b3393d |  | note | FREQUENCY: Where applicable, each bearing /mounting location
label | ceeab0f9-e3e9-41d0-b760-888e54c819ae |  | note | CATEGORY: IP
label | ae72dca9-c3dd-4b06-bdd8-63ac4ee19c6c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2b397c39-9d42-4886-94ca-334baaf2c003 |  | note | VERIFYING DOCUMENTS: This ITP
text | f082515c-b9c8-43a4-a410-9bd21d54552d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-soaking Concrete Surface
label | f58f5545-ee9e-45b3-a97f-4ae5bafb1ca2 |  | note | REFERENCE: Product TDS
label | c188b1f0-b583-409a-bc65-867a37bd4ba8 |  | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | 81090973-aa3c-48a7-8c0f-caf2e39321a2 |  | note | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | 0e270d30-ee5d-4984-b44a-db344fa4656c |  | note | METHOD: Visual
label | ff2bbbdd-5828-41ea-9430-9c9358f4e777 |  | note | FREQUENCY: Where applicable, each bearing / mounting location
label | 5d182fad-43c8-473b-b003-d0e4a7528753 |  | note | CATEGORY: IP
label | 7c930c19-fd92-4ec4-b84d-4017c709cee0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 57c5cc92-42b9-4cc9-a481-b8fd8acc2c58 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1a205ea4-4d0a-4b36-91b7-a36cbee44b85 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions
label | 5b530019-e5f5-4bb6-bf20-9a996557d596 |  | note | REFERENCE: 610.17
label | 383a0ea7-47bf-44bb-860a-2be493e885c4 |  | note | Table 610.171
label | ba9ce201-bc82-4d58-be17-15625c5c909e |  | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | c0a5d365-b9da-4c9a-af20-fdeec31daf10 |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ca63852e-a972-4da6-b32f-bbd52e556563 |  | note | Record: Required information on the Grout Pour Record.
label | 2b176324-e5d7-4d2f-8512-358fd895247d |  | note | METHOD: Measure , Visual
label | 98092497-b9fb-45d5-9853-1ced54605cce |  | note | FREQUENCY: Where applicable, each lot
label | 8dc1df78-f907-4440-8a98-d7233213d654 |  | note | CATEGORY: IP
label | b9719302-9b7f-4ad0-8e49-5762d753e7be |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | a8372df8-6b27-463c-b0be-d1502b930c0f |  | note | VERIFYING DOCUMENTS: This ITP
text | 2645b627-bab5-4a38-bde1-cc2cfae5c797 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Mixing Product
label | f7a80305-dea2-44a7-936e-d16cea203b0e |  | note | REFERENCE: Product TDS
label | 86a05a12-3405-4db9-8d08-c471688700ad |  | note | 610.28
label | 956326c9-ddc5-452b-832f-de01d49ee141 |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 9130195f-be0e-4166-a9c4-b3ffdc93207b |  | note | Only whole bags to be mixed with potable water.
label | 95f979ce-edf8-485c-84c2-6aa1d3a490e4 |  | note | Volume of water matches the required amount for flowable consistency and accurately measured.
label | f5d59bf8-7799-4fb2-8188-accb15d38ff3 |  | note | Product poured into the mixer slowly.
label | 6c25cc8c-fc30-457a-a11e-d1130c824d4d |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
text | c9c3296d-5a1e-4fc5-821f-2d539f0a4b68 |  | textbox | Enter: Required information on the Grout Pour Record.
label | 3dd107f9-3bf3-427b-8247-dee2c5a21e15 |  | note | METHOD: Measure , Visual
label | 21ae2cbd-b567-41d1-a1e4-9a6f9ef7ae9e |  | note | FREQUENCY: Where applicable, each batch
label | 5edda109-1fe0-4208-8cb6-8138d4ff227d |  | note | CATEGORY: IP
label | 2a051336-d5f9-425b-b841-915ef2d95439 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4f130d71-5117-4d63-8224-daf974c63f53 |  | note | VERIFYING DOCUMENTS: This ITP
text | 57032edb-cd5e-4685-b9c7-758244f8703d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Product Testing - Compressive Strength Cubes
label | f2ed5e9d-11d8-4256-a6c5-406c63991dce |  | note | REFERENCE: 610.28
label | 1d40364e-c096-4f89-80ee-762744faffdd |  | note | 610.33
label | e35b1d14-351d-419b-b701-42d2858da7fd |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | f15b8caf-8cc6-41ae-b9ef-758c7e8d78bc |  | note | Testing is be in accordance with the following frequencies:
label | ecd3a6c5-462b-45c6-b9b2-2e55258df11e |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 4f84b609-0074-4aad-a362-b5f0713e536a |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | e1877871-806c-4163-9763-ce97756bdd22 |  | textbox | Enter: Required information on the Grout Pour Record.
label | 44b1f8d5-cb94-4938-9928-5fb4c6606de6 |  | note | METHOD: Test
label | 58f7c55e-cc65-4149-8d80-74b7a4b5cfc5 |  | note | FREQUENCY: Where applicable, each lot
label | 413785b8-2b03-452d-b37e-d712b3b288fc |  | note | CATEGORY: IP
label | 5ee24395-b25b-4845-a7cd-9e15d314b0b6 |  | note | RESPONSIBILITY: Tester , SE/PE/SPE
label | 22e8e6ea-509e-4fbe-bfc5-dafdc8102975 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0d6bcced-efa0-4d32-8b3b-981fda1ca68f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction
label | 5efdf2a5-f257-4247-b352-c145afbe43e2 |  | note | REFERENCE: Product TDS
label | d473bf00-19c8-4d65-af70-1c2d29c216b8 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | 83cdf689-855c-4d47-93af-8261a36be9f3 |  | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 5ffad3a1-9083-42bb-8452-66732fa2cb8b |  | note | Product should flow to all areas and self consolidate.
label | 3a65b1a3-eeca-4691-96e0-51e38f586c24 |  | note | Product that stiffens or is showing signs of stiffening shall not be used.
text | 2b34fae6-a285-42cc-acaf-05fde9c45be0 |  | textbox | Enter: Required information on the Grout Pour Record
label | e6e9cf34-7368-42c8-8864-26d2e2106183 |  | note | METHOD: Visual
label | bd2ed9ad-b78a-4c82-98dc-794000ba39f1 |  | note | FREQUENCY: Where applicable, each bearing / mounting location
label | 591f21fd-28fc-4d08-890b-290cd03059ca |  | note | CATEGORY: IP
label | aac0f7b0-7ce3-4f1c-8931-62ec52774755 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | a08d1e5b-1d76-48bb-a07b-d12d5eb70c2d |  | note | VERIFYING DOCUMENTS: This ITP
text | 2c010ffe-ddfa-4e1f-89c4-b53cc18909e6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes & Protection of Works
label | d0276e3a-9f0c-4ba1-854d-6b4a474ad0b9 |  | note | REFERENCE: IFC Drawings
label | 6649348c-44a8-47c7-88e2-ba923190c155 |  | note | 610.17
label | f275ee7f-eb8d-48d1-b0f7-c036cc936ae2 |  | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | 75bd23bf-3bc1-4318-aa3d-b6c2ad788ef2 |  | note | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 4f476e9b-58aa-44c4-8cf9-9315d47c6907 |  | note | METHOD: Visual
label | bbdf9c93-8a15-4741-a365-ddafd4ce4ebe |  | note | FREQUENCY: Where applicable, each bearing / mounting location
label | 307cf3e7-006b-482e-9703-653960bc5561 |  | note | CATEGORY: IP
label | 6b704b58-367f-4e1c-98fe-ec805c33f52b |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | d20847fb-4dde-4273-89a1-a3dcbc14b2ea |  | note | VERIFYING DOCUMENTS: This ITP
text | 346fe335-daab-49f7-a80b-c39489b16c66 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Curing
label | d9d9361a-990d-4575-a75d-631cb1292cbd |  | note | REFERENCE: Curing Methodology
label | 81b6e0e3-40d1-43e9-bdc7-53eab83cd184 |  | note | 610.23
label | fceaa769-48e7-49bd-a19e-41a1d648ac32 |  | note | Table 610.231
label | 3d284d99-4739-477d-af65-6372a4d3ff5d |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | f77a7439-ca3e-4e43-8557-25e0bcd1fe38 |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | c5c0c5cc-1fff-435e-abe0-b71918c926e2 |  | note | METHOD: Visual
label | 6360da12-6616-4b4f-b384-51417d3a810e |  | note | FREQUENCY: Where applicable, each bearing / mounting location
label | 36582c6b-c4c6-4798-af93-12473d758d6c |  | note | CATEGORY: IP
label | 5686f897-d856-4d89-9d6b-59142455f72c |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 08ad49cd-671d-4495-bcef-b7a910f4920c |  | note | VERIFYING DOCUMENTS: This ITP
text | ec33e771-77c7-4eb7-b3d4-551678d9f25d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | 2a815ae9-ccc7-4ddb-af65-2730749af199 |  | note | REFERENCE: IFC Drawings
label | e4120a2b-d862-486c-b743-727c9b4b0ec0 |  | note | 631.15
label | 1ec479d7-3837-41c4-afeb-8779ebd14a81 |  | note | AS4680 Clause 8.3 & 8.4
label | 837c475c-4950-4500-aa06-763162e8215a |  | note | AS4506 Appendix E
label | a23ba831-4568-4c5c-9cb0-31278eaac045 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
label | 592fc17f-bc70-462e-ad80-4aca27a31624 |  | note | Where damage exists, it shall be repaired using an approved repair procedure.
label | 88d7e518-8e15-49e2-934e-f32339f1dc52 |  | note | METHOD: Visual
label | 032e4274-becf-4e69-8a33-e439be8e5b4b |  | note | FREQUENCY: Each component
label | 52c827e9-dc25-46b1-acdd-6fe34c9155f1 |  | note | CATEGORY: IP
label | 2990748a-7da6-4152-af96-4bd3f352dbad |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0157ba57-9106-45ff-bd72-67f3e939c11a |  | note | VERIFYING DOCUMENTS: This ITP
text | f6116a2a-12b6-439d-bef9-74a5b61db5cc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 6919b41f-ef3f-408a-b5bc-2dd7631af1d6 |  | note | REFERENCE: IFC Drawings
label | 0c7a91d5-f271-427c-969d-ed6b6034e3e8 |  | note | Product TDS
label | a0ffad05-8438-4648-8dd1-bf7c6a873cff |  | note | 610.28
label | 533857d1-d6c0-4b71-bb94-af8d1a469511 |  | note | 610.33
label | db0c511d-fb8a-427b-b6cf-d87a7f74eaa2 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | eb58b437-8c2b-44db-81a8-d38444a58612 |  | note | 28 day compressive strength per sample comply with the design strength.
label | 1c067763-de94-48fd-bfd4-2a28c8ca217f |  | note | Attach: Compressive Strength Test Results
label | ef2518b2-cdbe-4960-9e3e-dfa808146d43 |  | note | METHOD: Document Review
label | 30c9101b-d4e8-4d57-b262-3b562c55a8a0 |  | note | FREQUENCY: Where applicable, each cube
label | 5e37e0d0-1ac9-45b3-88d9-46fc369dcb4b |  | note | CATEGORY: IP
label | 9b87c536-87bc-485c-9aff-2721970ea761 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3e0830ea-3e1e-46ca-8b7a-31ad2ba695cb |  | note | VERIFYING DOCUMENTS: This ITP
text | b6373208-ebe6-430b-bfaf-90df709c4253 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Direct Tension Indicator Daily Records
label | 30d660e7-0a3f-47d7-9988-80a9ce5184da |  | note | REFERENCE: 630.20 (e ) (ii)
label | 690137ed-c8d6-4f0f-9935-24d4781c4504 |  | note | ACCEPTANCE CRITERIA: Provide correlation between a calibrated torque wrench and direct tension indicators (DTIs) per bolt diameter.
label | e96a2fd1-714d-4530-bc68-7a965be4f922 |  | note | Attach: Daily Record(s) of Correlation Between Torque Wrench & DTIs
label | fc8cb42a-059f-468d-9ab8-17ed9aee7167 |  | note | METHOD: Document Review
label | f2ef6f60-9605-4745-b31d-a0303381a079 |  | note | FREQUENCY: Where applicable, for each day that DTIs were used
label | 11ad34ce-3ab9-4c6e-b6ec-9780e402dd7f |  | note | CATEGORY: IP
label | fc8a3571-e93b-416c-9ca1-261b105f0747 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dfae3a49-1a4e-4b7f-b1af-3a56fbfa49a0 |  | note | VERIFYING DOCUMENTS: This ITP
text | f4dba9b9-0fab-45ba-9925-8c48c63d1ea3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 As-built Survey
label | cc56364e-4139-4450-a6bc-ac00d2ca0035 |  | note | REFERENCE: IFC Drawings
label | f17f2dfb-8f7d-49ff-95b6-1fe2d54fe96f |  | note | AS5131 Appendix F, Table F3
label | 142a85e5-a30d-463d-8fa5-01827187ff75 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 91febc03-3fc1-47c1-831e-2b4ba5efefe5 |  | note | Departure from RL = ±10mm
label | d086c7eb-a9c4-403b-babc-56e4a55d0e68 |  | note | Departure from plan position = ±6mm
label | 67c9aa09-12bc-49af-ad45-fcc5ec403cd2 |  | note | Departure from alignment = ±6mm
label | 2c918c54-f4ca-4dba-9b20-a3ed51f582a1 |  | note | Irregularities in alignment = 25mm in 30m
label | d5292736-35e7-4db2-b1a1-42da8269a69d |  | note | Projection of bolt = +25mm, 5mm
label | c5144215-a990-4b92-b79a-e2e2ac2f8307 |  | note | Location of beam = ±3mm
label | 909b0b0b-7b1a-424b-b851-886ffc762aac |  | note | Location of column = height/500, 10mm max.
label | 2e118106-9f41-4ace-b304-6b396187eb97 |  | note | Attach: Survey As-builts / Survey Report
label | 4d69d334-e298-4233-8a50-59c8d5f9530c |  | note | METHOD: Document Review
label | c7529fb8-644c-4970-ba7d-135e31325a89 |  | note | FREQUENCY: Each element
label | a1068cd4-e19d-4f40-8d83-2a4e70e92509 |  | note | CATEGORY: IP
label | d6c651a7-9f87-4d63-a3f5-4b29e4eb3105 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 82e5e0c1-2ccc-4f0e-8b59-e618375b7fa7 |  | note | VERIFYING DOCUMENTS: This ITP
text | bf7b888a-ba16-4a4b-a2ea-852d6bbb43af |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Non-conformance Report (NCR) Closure
label | a8ad49f0-1f83-4d7f-b27c-cf2b96a17f6d |  | note | REFERENCE: MRPA Quality Management Plan
label | 8990526b-27af-4e91-9cb3-78cfbc82c32d |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 2e7b59fe-8759-473e-9c88-401bb6dcd1b7 |  | note | METHOD: Document Review
label | 11e404bb-7ef0-4aac-bc67-8346d89fc026 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 0bafc7a9-63b9-4c2a-8f9c-ee77074f405f |  | note | CATEGORY: HP*
label | df054180-fcf2-471b-9e47-556e6dfc8180 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e48c5f29-dad3-4c98-b429-597bcc92ed0d |  | note | VERIFYING DOCUMENTS: This ITP
text | 0602302e-c7a1-4b01-a230-3fc553b19dd6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 2259d6a7-99cd-480c-af5f-2a0d05f57414 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | e1edc905-e914-4521-ba11-dc44b8a66120 |  | textbox | Name:
text | 343fd0c6-af61-438d-9507-cca0ed8da24b |  | textbox | Position:
text | 54dd1e38-9387-46cd-9433-f9168697485e |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Temporary TL3 Barrier (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Temporary TL3 Barrier (Supply & Installation) Rev 0 | ca97a186-1ae0-431e-87a5-9281919cfa02
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 74d089bc-35ac-4477-bb4b-ad763516daa4 |  | note | Document Title: ITP-CIV-Temporary TL3 Barrier (Supply & Installation)
label | 6ea8e4e1-835f-440b-b9e2-068b612f32f8 |  | note | ITP Description: Temporary TL3 Barrier (Supply & Installation)
label | 71e08336-65b5-463a-8142-ea83eaf840c5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 66f15aca-919f-48d1-8520-48dc0997a65e |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 95a34853-b8a6-4a9d-b624-b7c18986083e |  | note | Revision Number: 0
label | b3763420-8a01-401e-b6f1-85261f7e61c6 |  | note | Revision Date: 7/07/2020
label | 658dab78-2042-48c2-a6b7-d3a2a85e168a |  | note | ITP created by: Demson Manafi
label | 2e3aa0a1-3435-4e59-ac14-b9461938c598 |  | note | ITP approved for use by: Mike Freeman
label | 12c6fdbf-7139-468f-9e77-25de0874890e |  | note | 1.1 VicRoads RDN 06-04 March 2020
label | c75baff3-ae1d-4e61-8051-ec044a85c71c |  | note | 1.2 VicRoads Detail Sheet HighwayGuard Safety Barrier - Temporary April 2020
label | 3e12db82-7269-45fd-9bb5-b032a33d9448 |  | note | 1.3 VicRoads Detail Sheet QUADGUARD-M10 Crash Cusion April 2020
label | 18210929-e3e7-41ef-9c5d-b44e107f38a7 |  | note | 1.4 HighwayGuard LDS Australia & New Zealand Product Manual September 2019
label | d2615551-7fba-4249-b395-5aebafb0b05f |  | note | 1.5 QUADQUARD-M10 Product Description Assembly Manual November 2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Barrier Component Approval
label | a851d34e-bb86-4da4-8f6c-ec604e5f2a42 |  | note | REFERENCE: VicRoads RDN 06-04 March 2020
label | 117f4c69-54ee-443c-bb9f-5cc99a8dc77b |  | note | ---------------------------------
label | 2448180e-9f0d-4172-8fbb-3429b13b4fbf |  | note | ACCEPTANCE CRITERIA: Barrier components and end treatments are on the Accepted Safety Barrier Products list.
label | 65d98602-2096-4597-9e0e-677c1892a72c |  | note | ---------------------------------
label | 16677731-c2a4-4e1d-ad1a-36d2ffe84c05 |  | note | METHOD: Document Review
label | fcb91a5f-96df-47ae-98a1-c59f81b03048 |  | note | ---------------------------------
label | 3afe8b68-e777-49d0-bc86-b56fd39c7eab |  | note | FREQUENCY: Prior to starting Works
label | d3bd860a-7402-402f-b32e-d77fcb919d73 |  | note | ---------------------------------
label | 0e931a23-2c12-478a-98db-a65afceafe57 |  | note | CATEGORY: HP*
label | 34086385-5abc-452d-bcc4-3dc8d2f2bc4a |  | note | ---------------------------------
label | 0705cd2e-9fda-4b4a-ac65-e3f1ce4039c4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2cc0ac5e-995a-4a74-926d-b4fc48b701a4 |  | note | ---------------------------------
label | d844caef-915e-4775-81c2-98a6f65865e3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3ecf0bca-0e36-4332-a309-3ed3c24e33e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Chem-set Epoxy Material Selection
label | 4b10a171-ea64-4a7f-a885-253b7b457df7 |  | note | REFERENCE: Product TDS
label | d50593b4-1c2c-4f94-98b5-249f8d61b57c |  | note | ---------------------------------
label | ce1299ea-d5da-4571-9369-815e63c9673a |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 8ecfa8a0-675f-4e6f-87d2-13e23d76c166 |  | note | i. able to be used to secure M20 & M24 threaded rod into asphalt and concrete
label | 1cbd5be1-886b-4694-8485-b86e7c80feb6 |  | note | ii. able to be applied within the temperature ranges applicable to the site conditions
label | 66821a5e-d5a8-4d64-9a0b-88f6c8a4e88a |  | note | iii. able to be cured within several hours to allow for testing
label | dc4f38b1-9761-4244-9972-2abd174750b1 |  | note | Enter: Teambinder Material Approval number
label | e7e5b3c0-2892-49b1-9edf-7807d02fca29 |  | note | ---------------------------------
label | 6fdafbb8-65f3-4885-bc86-b350ac71a5fe |  | note | METHOD: Document Review
label | 9d7fd951-c90f-4246-bf7b-d8fc782b5156 |  | note | ---------------------------------
label | f97b74ea-493a-48c3-b5d8-6989bb965c5a |  | note | FREQUENCY: Prior to starting Works
label | 8f2bb1dd-164e-4388-a6ad-bdecef969982 |  | note | ---------------------------------
label | 546dd7b6-27a0-4a9b-91dc-a17ba72170b6 |  | note | CATEGORY: WP
label | 4857258b-27c7-4939-8ef5-71963302afbc |  | note | ---------------------------------
label | 4da6e3d6-f0f7-419f-9649-d1c3cda2b7ff |  | note | RESPONSIBILITY: Nominated Authority
label | 3ddfab32-11a3-4fd6-91bb-374f2c1c60d0 |  | note | ---------------------------------
label | 0074f687-a723-4497-b2e0-d54e1a058148 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2c1352cf-623c-456f-8267-5de790390014 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Threaded Rod
label | 0a32c8c4-5e15-4a52-bd86-f67e27cc43e0 |  | note | REFERENCE: HighwayGuard Installation Manual Page 17 of 23
label | 64b61b41-013b-49bc-b2b5-342643707a3c |  | note | QUADGUARD Installation Manual Page 16 of 43
label | 4c152882-b6cf-4975-a4a0-c8c51adccd24 |  | note | ---------------------------------
label | 08c46512-b1a3-4609-92f7-0c0904e8a318 |  | note | ACCEPTANCE CRITERIA: Threaded rod must be 8.8 grade.
label | 99e97f28-b830-4870-8a79-84fe1d821feb |  | note | ---------------------------------
label | 159b3826-0c06-4e5c-9a7f-626713769aeb |  | note | METHOD: Document Review
label | 4269e1c3-f5a6-4969-8e1c-da82d8fbb5dc |  | note | ---------------------------------
label | 4c3c1fd3-fb11-4b9b-9a1d-e201f79440d3 |  | note | FREQUENCY: Prior to starting Works
label | 57659a16-fec5-4c2e-9cfb-389e8558d322 |  | note | ---------------------------------
label | 2771c70b-9e6c-4b7a-b72a-aa306e780efc |  | note | CATEGORY: HP*
label | d8e3bb3b-94cd-4ec4-90ec-9c0062afb395 |  | note | ---------------------------------
label | e3d428d1-3bf9-4929-ab77-df384618e64a |  | note | RESPONSIBILITY: SE/PE/SPE
label | e271a38a-4f75-40d3-8247-c449ddfbd050 |  | note | ---------------------------------
label | 7feb3cb0-5830-4cf0-9e32-a961a84ad488 |  | note | VERIFYING DOCUMENTS: This ITP
text | 23e0eee4-5d0c-4e82-8aac-0cb24b88acec |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 IFC Drawings
label | 4bcf45bf-883e-481e-b428-761cd7272374 |  | note | REFERENCE: MRPA Quality Management Plan
label | 9bef8eb6-1049-4042-b143-971ef658ed07 |  | note | ---------------------------------
label | f610065a-84ed-4341-acdc-e4b5960de5ce |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current
label | e22d9bd6-83b2-45ce-afff-3432e55721a1 |  | note | ---------------------------------
label | df16f89e-d294-4ca9-8aa3-e6141788c396 |  | note | METHOD: Document Review
label | 2d6e7c77-dde4-4903-b7dd-d7d5ff6e5d6b |  | note | ---------------------------------
label | 1aa94d84-330e-423e-bb4e-271b51c82c3c |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 8dabb4ec-052c-4af5-ba06-773a1c6bb5e2 |  | note | ---------------------------------
label | b3a9ebca-7650-4134-a0bc-c9738ef77219 |  | note | CATEGORY: HP*
label | 1cb02543-617e-43a2-b704-d18c6ac07554 |  | note | ---------------------------------
label | 01352bfe-9270-46c3-9d3b-52c8208780f1 |  | note | RESPONSIBILITY: All
label | 45b2b497-0f15-43b2-b913-4eed05a798ed |  | note | ---------------------------------
label | 1188137e-dd94-4a3c-b32f-d3c38f8610ca |  | note | VERIFYING DOCUMENTS: This ITP
text | 442dd413-befc-42fb-b715-e1b61d0a6637 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Survey Set-out
label | 050ff5f2-9e0b-4336-8fc3-7614dc1b9ea9 |  | note | REFERENCE: TMP / Alignment Drawings
label | 401a7018-da1a-47ca-b8f4-7d2f895d9bf4 |  | note | ---------------------------------
label | 3e9c014a-c4d6-46a7-99ec-e36a6a483b60 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location and alignment requirements as per IFC TMP drawings.
label | ffabe19c-bbcb-4fd0-ab8b-37ab2f12b43d |  | note | ---------------------------------
label | 14d600df-87f3-42a9-9607-8004d73834cb |  | note | METHOD: Measure Visual
label | fab9a505-838b-4dcd-88de-295be7f80823 |  | note | ---------------------------------
label | 9265b3c1-138c-4721-ba46-e78cf3b7c712 |  | note | FREQUENCY: Each element
label | 361bebab-dbe3-4cd4-a1d9-531687986dce |  | note | ---------------------------------
label | d8bc19b5-9425-4b0a-b941-7df73f081398 |  | note | CATEGORY: IP
label | 1ed20bf2-c79b-495b-b20d-756f50f8489c |  | note | ---------------------------------
label | a91e17a4-ab20-4e32-bebb-b48bff368017 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 1b117f9f-3cb4-4c34-8d7b-4fc16a04f715 |  | note | ---------------------------------
label | e7fe25ea-7e92-4353-9c3a-1be0265d4fbf |  | note | VERIFYING DOCUMENTS: This ITP
text | deaf865e-9544-4d63-a916-70c1935d8de2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Site & Substrate Conditions
label | 37e24ff9-0125-45df-98cb-fe42669c0ecf |  | note | REFERENCE: HighwayGuard Installation Manual Page 10 of 23
label | bae15fdf-eab9-49a0-bf8e-9133ab1cd3aa |  | note | QUADGUARD Installation Manual Page 15 of 43
label | e59910bf-2d76-492c-b957-6f7d9220f91d |  | note | ---------------------------------
label | 40ec09d8-f48e-4fc5-9c19-1edbe1206e58 |  | note | ACCEPTANCE CRITERIA: Barriers & end terminals shall be placed to the following requirements:
label | dfba19ef-4376-48c1-b419-4fedfbd5b11c |  | note | i. Foundation = 150mm minimum asphaltic concrete over 150mm minumum subbase, or
label | 725627b2-c3be-4edb-81c4-b379750b7361 |  | note | = 250mm minimum deep lift asphaltic concrete
label | 2523f75a-98dc-4ad9-bdb2-8f3a74b8d5b3 |  | note | ii. Cross-fall = 8% maximum
label | 3e3fa330-0fc3-4761-847f-61c43a8afb82 |  | note | iii Differential cross-fall = ±2% maximum along the length of the QUADGUARD system
label | b6d40e66-6619-4db3-a3ff-bd0c45e0fec9 |  | note | iv. free from obstructions within the deflection zone
label | aff165e1-3f84-4dc9-a612-91eb9bc04fb5 |  | note | v. have a minimum 60m length between end terminals per barrier run
label | 1195adc3-2b63-4a30-ba4d-2d1ce7c46dbe |  | note | ---------------------------------
label | 93ad0c42-de43-42fd-b21f-cfb57929a2ec |  | note | METHOD: Measure Visual
label | 255a2b89-1982-444d-b957-e7218003af0b |  | note | ---------------------------------
label | 146303d3-de51-4808-b393-01012b3465c4 |  | note | FREQUENCY: Prior to starting placement of elements
label | d24237fd-f53f-454e-9e8f-64c818e26b36 |  | note | ---------------------------------
label | 22482559-3b8b-4aa9-86e7-5e8b38b9fd47 |  | note | CATEGORY: IP
label | c0a09766-efd4-4ab4-b2bf-819d2d705351 |  | note | ---------------------------------
label | c20be202-3ee9-4dbc-a5e3-5ba020e13c7e |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE Foreman
label | 55e43d54-a633-41b5-82da-12df002365d5 |  | note | ---------------------------------
label | b25b41b1-a636-433d-9e45-4cac193f6a8c |  | note | VERIFYING DOCUMENTS: This ITP
text | bf3a2953-a919-437c-a83d-d31147261fb7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Materials Inspection Checklist
label | 0b1789d6-23a9-4515-a405-485d30831e2d |  | note | REFERENCE: MRPA Quality Management Plan
label | 3fcc36ae-a6ee-48e9-8acc-6c2265854b05 |  | note | ---------------------------------
label | 2c871546-6f12-4b27-b1a3-d90202ecad13 |  | note | ACCEPTANCE CRITERIA: General inspection to ensure that all components match the requirements for the system, all parts have been received/deployed to site and are in a workable manner.
label | 13091af6-67ab-4713-8acb-f97b3f1211cd |  | note | Complete: Materials Inspection Checklist in ConQA
label | df5bb86e-768d-4e04-97d5-d9d9189ccf65 |  | note | ---------------------------------
label | aa67ca07-92c5-4042-b5ec-6ccd97d4adfb |  | note | METHOD: Measure Visual
label | ae233011-ead7-431f-b2a1-5d283f0e2a63 |  | note | ---------------------------------
label | bba808a3-50e7-4ea8-8e6f-51674b03a4ff |  | note | FREQUENCY: Each element
label | 21bc5515-8d8a-42c2-b70c-e0bc3e913007 |  | note | ---------------------------------
label | 279f23e7-bf59-4a9e-9cf0-f3c6d1ade6a7 |  | note | CATEGORY: IP
label | 31df8e26-f575-4150-a3bb-12c903d19146 |  | note | ---------------------------------
label | e45cd6aa-659c-4c6c-87f4-0c180a8b3e00 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | e6b20f6b-815e-4ae3-bca0-e4a99745cff9 |  | note | ---------------------------------
label | 8a437f57-41b8-4943-afab-972b38a5af45 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4d2644ea-8da3-4193-95cd-759b757c5add |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Barrier & End Terminal Handling
label | 84823770-86b5-4a5b-94ce-7c084bd63c0b |  | note | REFERENCE: HighwayGuard Installation Manual Pages 11 - 12 of 23
label | 07b789aa-c15a-4154-a644-0b9503d56395 |  | note | ---------------------------------
label | ae98fbff-347b-4cde-a711-7e0470f6e543 |  | note | ACCEPTANCE CRITERIA: Handle barrier components by nominated lifting points only using suitably sized chains or slings to prevent damage.
label | 1fbed4e2-1584-433f-8741-0d71a01ce17e |  | note | ---------------------------------
label | 0f86ecc9-192c-43d7-ae15-4eb82c9685b4 |  | note | METHOD: Visual
label | 059b68b8-c77b-4618-8aee-2ce1a782d652 |  | note | ---------------------------------
label | daa181a3-b194-44d3-9ac5-84718f5b4d62 |  | note | FREQUENCY: Each element
label | e4375d7c-8e9b-4d5a-b0d2-5143ceca3817 |  | note | ---------------------------------
label | 7fbe8efc-8ecd-41d0-9eb3-9a24c44f3dfd |  | note | CATEGORY: IP
label | f4800877-a793-48b8-8cc7-e78d0e6537b8 |  | note | ---------------------------------
label | a254089a-e395-4425-917c-5610e532b297 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | 7cac279d-73d8-45d5-bb2c-23b3d84bce65 |  | note | ---------------------------------
label | 23bc8bf2-dd8d-4341-9765-c02dae6979b6 |  | note | VERIFYING DOCUMENTS: This ITP
text | cb6e66ed-1382-4882-bd36-fecb4b33c1d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Barrier & End Terminal Placement
label | 48afbeee-2b81-41a3-b073-50c61e657ad4 |  | note | REFERENCE: TMP / Alignment Drawings
label | 5820bd87-043b-4a0a-ac5b-27e3a8081439 |  | note | ---------------------------------
label | 7e1cb111-4b73-4f39-b716-51dca6a33ff2 |  | note | ACCEPTANCE CRITERIA: Locate barriers as per survey set-out.
label | 99c45c74-91c5-4e04-bc15-d1dd9cfa59e0 |  | note | Minimum 300mm offset from edge line of adjacent trafficked lane.
label | 7a3dce29-e370-4259-8b82-e1b60d5297be |  | note | Selected barrier T-connector and/or angled barrier for required horizontal/vertical radii.
label | 21463bcd-4a30-4d80-89e2-f5401e485462 |  | note | ---------------------------------
label | ec832092-814e-42ec-b1d9-76118310a338 |  | note | METHOD: Measure Visual
label | 91c8d2b9-fdb2-4343-891a-72e1fcbce184 |  | note | ---------------------------------
label | ed1e1757-7efe-4798-9b58-60ebaba275c4 |  | note | FREQUENCY: Each element
label | 7b336dc8-a2d2-484e-98e7-81d7a6b6e76a |  | note | ---------------------------------
label | ebb6d8eb-5cce-4a0c-8223-2c5ff7095caa |  | note | CATEGORY: IP
label | 727fb534-5732-4d7c-a80d-5332cebf078e |  | note | ---------------------------------
label | 265910e8-3438-4b73-834f-7afe1759aff2 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | 80199790-e5e6-44c5-bea7-5dee1b094a25 |  | note | ---------------------------------
label | 1a1f802d-6ff4-4bc0-ad05-493ce17c17d9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 390a0423-9f47-434d-890d-960e9f8c24e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Barrier Connection
label | 49f14ff4-0650-4be9-8149-43ba1dc47f11 |  | note | REFERENCE: HighwayGuard Installation Manual Page 13 & 23 of 23
label | a31f0eab-15b7-4b77-a579-4e1f15c79516 |  | note | ---------------------------------
label | 2d9943ed-0719-46fc-be8a-475d61bed83c |  | note | ACCEPTANCE CRITERIA: Secure the Quicklink security nuts to connect T-connector to barrier length to snug-tight condition.
label | 2d96917b-8cc3-4711-a2b3-9b188ec2b094 |  | note | 10mm maximum mis-alignment to prevent snag-points.
label | 00fb89ff-17b5-4fce-9fee-3abeb44bea63 |  | note | ---------------------------------
label | 63ab7dee-df25-4199-9f89-e11afa3a444b |  | note | METHOD: Visual
label | 52611153-275c-408f-8d3e-f7682c409ac6 |  | note | ---------------------------------
label | 4e985033-27c6-4a43-8e7e-7da06bf620bc |  | note | FREQUENCY: Each element
label | 37cbf905-f052-4ca7-89c8-c846272a2b38 |  | note | ---------------------------------
label | 1cb57c96-098c-4cc8-adba-de8cd366841a |  | note | CATEGORY: IP
label | 7a1d2037-a34f-408b-967a-d6b5b0863e73 |  | note | ---------------------------------
label | 5498b10f-4fcf-4a13-8feb-3b6ad69f3219 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | 8f8f21a5-1897-49c5-84f6-1865713515ed |  | note | ---------------------------------
label | 34de8c5b-ebb8-494a-babb-654eecb3cba2 |  | note | VERIFYING DOCUMENTS: This ITP
text | c9eab3c8-3896-4e11-a469-6f8b44e1d8bd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Installation of Anchors - Barriers
label | c59aa8ab-4b9c-4e98-b8d3-c05fa3748017 |  | note | REFERENCE: HighwayGuard Installation Manual Pages 14 of 23
label | c9bdb679-39ab-4cb6-b526-f22ce247b76e |  | note | VicRoads Detail Sheet HighwayGuard Safety Barrier - Temporary
label | bf6461ec-abb0-4dd8-8ce2-b0cc779eb7fd |  | note | April 2020
label | a46e4a0d-d235-40a8-9632-0640c03a74df |  | note | Epoxy Product TDS
label | 96fc16f6-f5ac-441e-9165-1dcacb19bc72 |  | note | ---------------------------------
label | e351e3d9-dbb5-4d44-af60-5c14679fa3f5 |  | note | ACCEPTANCE CRITERIA: Position 330mm long M24 8.8 grade threaded rods:
label | c2092879-4af8-4e97-8570-67a922eb5c4d |  | note | i. 6 no. at the start and end of the barrier run (3 per side, per end))
label | 200c54d5-ce53-48c0-ab48-7ce218c1c23c |  | note | ii. 2 no. at 12m maximum spacings, staggered across each T-connector (1 no. per side, per 12m)
label | e574855f-e13b-4386-b3bd-6934e3e21ac7 |  | note | Using an 28Ø masonary bit, drill a 300mm minimum depth hole into the substrate.
label | f2d730ba-7cc9-4270-822b-be657da51792 |  | note | Blow out the holes and inject/pour the epoxy into the hole.
label | 2068e2b4-c5fe-492a-8160-488101c20eae |  | note | Wind a nut onto the threaded rod, making the end flush with the top of the nut and place a washer underneath the nut.
label | 8644be85-6462-42e0-9683-1284e8f772af |  | note | Place the threaded rod into the hole, rotating as the rod enters to ensure full coverage of the thread until the washer has made contact with the barrier base-plate.
label | cc8b0d4a-fa3c-4616-9836-ecfc97096814 |  | note | Note: Threaded rod lengths above are based on an asphalt substrate - see the installation manuals for required lengths into different substrates.
label | 79d557b7-f329-4664-ab7e-dabf702b1fc9 |  | note | ---------------------------------
label | 2f1aad99-6fcb-4a61-b64e-8d4500b14231 |  | note | METHOD: Measure Visual
label | 97fee2dc-6fa5-48f2-b005-2459f3c82d8c |  | note | ---------------------------------
label | f199ff4f-995b-4f86-8ab2-5461ad1a3d46 |  | note | FREQUENCY: Each lot
label | 7f54b2a0-eb3d-4d9b-a21a-80e41e4092a6 |  | note | ---------------------------------
label | 16ffd941-36ea-44a6-a871-50541edf219c |  | note | CATEGORY: IP
label | 2b0018dd-e4e4-4ee7-ab3f-b082bc4f3174 |  | note | ---------------------------------
label | 2f8d99b6-b145-4308-84eb-c66253bf2ad1 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | ef32e509-e0e7-4a3f-b158-208c22a315ea |  | note | ---------------------------------
label | 5ddd03fb-64f6-474d-bd7a-60d6ae118d66 |  | note | VERIFYING DOCUMENTS: This ITP
text | 00db3020-9016-4ff3-a51d-57acd386529f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Erection of Gawk Screens
label | 6ad3ca8f-6766-4bad-8d10-049d4d12a542 |  | note | REFERENCE: Product Drawings
label | 9b885c87-045d-4c6d-9e77-8d6966500205 |  | note | TMP / Alignment Drawings
label | 090f01af-e384-4e97-ab19-7e8a850da29c |  | note | ---------------------------------
label | 3789e461-88b0-4191-ab53-e8c9a4a6bbe1 |  | note | ACCEPTANCE CRITERIA: Where applicable, erect the gawk screens as per the standard drawings.
label | 63b4ec9f-bb05-4ce5-baef-dfcda9376031 |  | note | Securely fasten the bolts to snug-tight condition.
label | caa96aea-ac9e-419f-a431-8e52170b55c8 |  | note | ---------------------------------
label | 7aa90f0b-1a59-45a0-a566-cdcead54628d |  | note | METHOD: Visual
label | 656280ee-cef3-443a-bbcd-29f70987b552 |  | note | ---------------------------------
label | 09f3a39b-8b07-49d5-af12-39120877f107 |  | note | FREQUENCY: Where applicable, each lot
label | c1e8efb8-386b-4766-91b4-8b61b451974b |  | note | ---------------------------------
label | 562422f0-36eb-435d-aecd-d180a3b9a8d6 |  | note | CATEGORY: IP
label | 2d35474d-1073-466c-847f-6d7240a2e70b |  | note | ---------------------------------
label | 26690ba4-5b91-4684-bd3c-58862321a381 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | 470cadf3-1b54-41f6-8aed-89dc411ff06f |  | note | ---------------------------------
label | 8b7b0a7e-cce4-41d0-878b-f9e70d358a72 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6743fe12-a8db-4739-bc3a-d3de6adffda8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Delineator Attachment
label | c626cad7-4710-4d31-926f-a47348aee6ca |  | note | REFERENCE: Product Drawings
label | 0036e7b0-2c51-4e45-8082-4cc66e9c7eb5 |  | note | TMP / Alignment Drawings
label | 69bb7c25-1520-434e-8ceb-89225bd183e3 |  | note | ---------------------------------
label | dd1ba250-9b36-426b-b4e9-6f43227970d5 |  | note | ACCEPTANCE CRITERIA: Where applicable, attach delineators so that the correct colour is shown in accordance to the traffic direction of travel and ensure that they are fastened to a snug-tight condition.
label | 9419fbdd-d341-466b-8c68-e74d7ed52a45 |  | note | ---------------------------------
label | 85ad9110-5bb6-4952-9e33-fef5808b773a |  | note | METHOD: Visual
label | c7dbf7b5-1490-41ec-8a67-5b4c8d9af636 |  | note | ---------------------------------
label | 1008794f-a6d2-4f9c-860f-c0c009175e3d |  | note | FREQUENCY: Where applicable, each lot
label | 31c6349c-d956-4ff2-8baf-1c661bf13e45 |  | note | ---------------------------------
label | cf63b40b-66d6-4e3f-82ce-f40921e5ccb2 |  | note | CATEGORY: IP
label | 9d7e571f-ae50-46f9-b9df-43daf0accea5 |  | note | ---------------------------------
label | 30a72f55-5678-4432-9be6-207af5015edc |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | 92d6596a-2522-4e0e-a0cb-0eb0350c4bdf |  | note | ---------------------------------
label | 8f12072c-9f12-4912-adc0-dfac2575d852 |  | note | VERIFYING DOCUMENTS: This ITP
text | b50e18bb-aac2-4b09-a282-c566144db65c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Installation of Anchors - Test Anchor
label | aca3b39d-67f2-480c-a2cd-9cb9cb5cc880 |  | note | REFERENCE: HighwayGuard Installation Manual Pages 17 of 23
label | c6cb7af9-0d2b-44c8-aa02-4ba2fa47cd78 |  | note | Epoxy Product TDS
label | f76149e3-b29d-49a9-a8b2-cc70de44667e |  | note | ---------------------------------
label | 467abbae-6c52-4c52-8a37-2a362bb2f60e |  | note | ACCEPTANCE CRITERIA: Position 1 no. 330mm long M24 8.8 grade threaded rod into the pavement behind the barrier defelction zone.
label | d569c4ab-516c-483a-941f-ba5e723a69c3 |  | note | Using an 28Ø masonary bit, drill a 300mm minimum depth hole into the substrate.
label | edda8efc-0769-41fd-904d-a1a751c8c83a |  | note | Blow out the holes and inject/pour the epoxy into the hole.
label | ec112ef2-212c-406b-abee-09f647921a6e |  | note | Wind a nut onto the threaded rod, making the end flush with the top of the nut and place a washer underneath the nut.
label | 7cf857df-3285-4550-bb74-66d5aaa3bc85 |  | note | Place the threaded rod into the hole, rotating as the rod enters to ensure full coverage of the thread, leaving 30mm minimum projection to connect the pull-out jack.
label | 7d14cf2b-17bb-4ee7-9c66-0632f46a315b |  | note | See 5.1
label | e598b99b-a4ed-4a8b-94b5-14b4c8ee4d9a |  | note | ---------------------------------
label | bdeda22a-0f54-4156-abdb-563ffc45c1a0 |  | note | METHOD: Measure Visual
label | ce03b695-eaca-4dd8-9325-5988b941403a |  | note | ---------------------------------
label | 4eea58c3-ec6e-4dab-bb08-d3638bc6ea12 |  | note | FREQUENCY: Each lot
label | 915d761e-9e87-4008-b6df-63666d51866e |  | note | ---------------------------------
label | 02bb6bcc-1ffb-4b6e-a29e-426f76c85fcc |  | note | CATEGORY: IP
label | f47b5524-c1c9-4f4a-8a41-89712a348e28 |  | note | ---------------------------------
label | d60fbe0d-3802-4ab5-8b2a-5ee159657a1f |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | c5555201-cba8-42cc-8e51-9a1383b3cead |  | note | ---------------------------------
label | 61d4802c-fbb0-4bde-9b54-910867aa4b82 |  | note | VERIFYING DOCUMENTS: This ITP
text | f45e49db-4abc-4524-be55-463be6045894 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Installation of Anchors - End Terminals
label | 54cbc5ac-4431-4b37-a409-083264573764 |  | note | REFERENCE: QUADGUARD Installation Manual Pages 16 - 19 of 43
label | a67405dd-166c-453d-9b61-247ae161267d |  | note | VicRoads Detail Sheet QUADGUARD-M10 Crash Cusion
label | 210da89d-e8ec-46bb-a475-f2849a0c7f4e |  | note | April 2020
label | 738cb7e4-a811-428e-8e75-03fb67580902 |  | note | Epoxy Product TDS
label | 2bcfcafd-d024-4769-a8a7-ba0c460bee80 |  | note | ---------------------------------
label | 49c33fb9-d41f-4999-960a-2d6ebaf9e32c |  | note | ACCEPTANCE CRITERIA: Position a 460mm long M20 8.8 grade threaded rod in each monorail hole.
label | 8d456ffa-0954-4b99-8637-77de0da3be16 |  | note | Using an 22Ø masonary bit, drill a 420mm minimum depth hole into the substrate.
label | 19964340-d4c3-412b-8f20-80907a0a91c8 |  | note | Blow out the holes and inject/pour the epoxy into the hole.
label | bdb1b99d-3317-4c1c-849d-fab3a99940f1 |  | note | Wind a nut onto the threaded rod, making the end flush with the top of the nut and place a washer underneath the nut.
label | d0c85a6d-8482-4f10-a39f-4c09ccf5f68c |  | note | Place the threaded rod into the hole, rotating as the rod enters to ensure full coverage of the thread until the washer has made contact with the barrier base-plate.
label | ec11f11e-7fd3-42a7-a444-bd42437f80bb |  | note | Note: Threaded rod lengths above are based on an asphalt substrate - see the installation manuals for required lengths into different substrates.
label | cee6f9f4-de0a-4224-9d4d-4993fc12a477 |  | note | ---------------------------------
label | 663378f4-cbfa-427b-a27d-e9e2b82fc4e5 |  | note | METHOD: Measure Visual
label | 6cbc2dac-0fee-496c-84f9-4d5ceb47550d |  | note | ---------------------------------
label | 48edddef-c835-4f1d-b1a1-a625bf2405dc |  | note | FREQUENCY: Where applicable, each lot
label | 483e3fc7-d968-4a46-b279-d02e505eb514 |  | note | ---------------------------------
label | f5da1ac9-9be4-4926-bc65-9390bf198b9d |  | note | CATEGORY: IP
label | fba581bb-738b-457c-a4c1-c75931d29e8c |  | note | ---------------------------------
label | b04fe2c6-698b-4417-ac1e-d1ff8dac45d9 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | 768adf52-03cf-48a5-aa7a-d251e102ef30 |  | note | ---------------------------------
label | 0cf8ee01-453e-4ee5-b6f4-94d4bab292cb |  | note | VERIFYING DOCUMENTS: This ITP
text | 07b0b262-cfc8-4e34-96e8-eb5821d16818 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Torque Nuts - End Terminals
label | 0968d4e9-dcbc-478b-b50f-b95b3ebdef7f |  | note | REFERENCE: QUADGUARD Installation Manual Pages 17 - 19 of 43
label | 709eaf8f-935c-4b40-9f93-1b1ce9ac54e6 |  | note | Epoxy Product TDS
label | 298a2b42-ab6e-4587-a9a2-ebf7670400c4 |  | note | ---------------------------------
label | 0d2e522d-9a65-4c9a-aa96-7476d94b77fb |  | note | ACCEPTANCE CRITERIA: Once the epoxy has cured, torque the nuts to 15Nm.
label | caa9f553-1079-4c62-bcb8-4bb3b9c2a9a3 |  | note | ---------------------------------
label | 60449b05-17ed-41bf-9d34-4cabd4379263 |  | note | METHOD: Measure Visual
label | a708a640-e375-4844-adf0-512b5bb38e85 |  | note | ---------------------------------
label | 0d4bc98c-a79b-43a7-b99c-7a013cdafa0d |  | note | FREQUENCY: Where applicable, each lot
label | 184696b7-41fe-403d-90c3-0e579754e387 |  | note | ---------------------------------
label | 72ff5ac8-13b5-472a-a01f-6a6c97d30176 |  | note | CATEGORY: IP
label | 2f214706-380a-4b7f-8df7-a8ef797a8101 |  | note | ---------------------------------
label | 7edc8577-e187-4119-8230-7890ca2af340 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | 7848fd3e-22e1-4555-b607-e80bb3a95459 |  | note | ---------------------------------
label | 8fcf828f-2258-4097-8659-97e23dbde78e |  | note | VERIFYING DOCUMENTS: This ITP
text | 52881b95-aace-43bd-835c-05a7e955de26 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 End Terminal Assembly
label | a2f2dcc6-b9bb-40ff-aa92-5f16fc689e00 |  | note | REFERENCE: QUADGUARD Installation Manual Pages 20 - 34 of 43
label | 286ebedf-f7eb-4c1d-9c78-800dbf94d322 |  | note | VicRoads Detail Sheet QUADGUARD-M10 Crash Cusion
label | 3670931c-8012-4fd6-b791-40995b24cca4 |  | note | April 2020
label | c0f9106c-b973-4e28-ab28-04860d23bee2 |  | note | ---------------------------------
label | 5e371a74-c510-4298-842b-358eacbe94cf |  | note | ACCEPTANCE CRITERIA: Complete installation as per the installation manual.
label | cbc33b12-b8bb-46b3-ae85-df00c1f0d22d |  | note | Replace any parts that are worn or damaged.
label | daa6a117-b057-4566-94af-111cd8300dde |  | note | ---------------------------------
label | 97177030-b89c-40fc-a5ce-11c62b852f0e |  | note | METHOD: Measure Visual
label | cc534fef-22b4-4faa-aff4-974f1a82d90d |  | note | ---------------------------------
label | 68074bc7-2d38-4e00-9f4d-9c3ec545bdbe |  | note | FREQUENCY: Where applicable, each lot
label | 4d33fd25-484d-4364-b846-ab2b153cb24c |  | note | ---------------------------------
label | 38c0d5d5-2f5a-45d1-b5cb-906e03d90243 |  | note | CATEGORY: IP
label | 682019bd-920a-4a29-8ba9-a2ae80474c5d |  | note | ---------------------------------
label | d7b47e0a-2f9a-4ee9-978d-ba471d2110f8 |  | note | RESPONSIBILITY: SE/PE/SPE Foreman
label | a7d17924-4742-47ba-8142-9e9068168fb2 |  | note | ---------------------------------
label | 95514fa5-59f0-4e79-b5b3-a2effe3b3d50 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4d06ff70-0265-4045-abce-3cea5eb4969d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Anchor Pull-out Test Results
label | b769060d-bf20-42ae-9c3f-207d95f9654b |  | note | REFERENCE: HighwayGuard Installation Manual Pages 17 of 23
label | f9da5fd6-c602-4db4-9570-a431623a4f96 |  | note | Epoxy Product TDS
label | b514ed37-7b32-4407-8218-02d0f7799e79 |  | note | ---------------------------------
label | dac8d88f-2e81-483f-a63c-53dca30dadc9 |  | note | ACCEPTANCE CRITERIA: Conduct a pull out test on the test anchor to confirm ≥95kN strength has been achieved.
label | c5f7f8e5-521a-49d6-8f11-794d617a496c |  | note | Attach/Photogragh: Anchor Pull-out Test Results
label | 3a90a45a-bc91-4a4e-b27f-7d74364b2ddf |  | note | ---------------------------------
label | cbee8db7-d3c8-45b8-b45f-da55e61b33ad |  | note | METHOD: Test
label | f6d0d539-ee70-4efa-a3d8-682e5c97d34d |  | note | ---------------------------------
label | 8b88bebe-629f-48af-99cc-6f8fc6f7badb |  | note | FREQUENCY: Each lot
label | 48896ed5-8e12-4cb5-9b26-9e5f99891ba7 |  | note | ---------------------------------
label | 2f341a95-d87a-41fe-9e5c-dda07fc911e2 |  | note | CATEGORY: HP*
label | cbd99586-bfac-493a-8296-20d6539cee19 |  | note | ---------------------------------
label | 70d42592-ae96-421b-a600-a2447de61a7a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1d579162-0fc4-4073-8a27-c519c12c7c8e |  | note | ---------------------------------
label | 45acd1f4-69a9-4e13-a762-5d9bb745f54c |  | note | VERIFYING DOCUMENTS: This ITP
text | fc5fb8c9-b613-4593-a8d6-d05c2a5c3d59 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Installation Certification
label | 175c8c36-f36e-451b-91a8-31c51025f0cb |  | note | REFERENCE: Subcontract
label | 340ef415-9595-4e13-abd9-8e2340bff7d9 |  | note | ---------------------------------
label | 8294159c-3099-45f9-9ed3-691e2247f877 |  | note | ACCEPTANCE CRITERIA: Installation subcontractor to issue an Installation Certificate, confirming that the installation has been performed in accordance with the manufacturer's product manual(s).
label | de2450c4-3606-47ab-8cfd-47324a43f1f1 |  | note | Attach: Installation Certificate
label | 19f69166-ab73-44ce-87f8-d153cd1e3fcb |  | note | ---------------------------------
label | 2e849961-b6f5-4337-8451-1a07a263ced6 |  | note | METHOD: Document Review
label | d82e1742-53ca-4a41-84a3-eba45c7b1fd8 |  | note | ---------------------------------
label | 3c13967f-0dc5-4039-89f2-046b54f73a78 |  | note | FREQUENCY: Each lot
label | a17ef476-ec1e-4ce5-8040-8f2faffaa648 |  | note | ---------------------------------
label | a26b0fd3-292b-47c3-98a9-10923dfc2323 |  | note | CATEGORY: HP*
label | a894b2dc-00b8-4a60-b849-e1b66ca1454d |  | note | ---------------------------------
label | 4b7aeb3b-315c-4943-9f0a-9d0f342b4c0c |  | note | RESPONSIBILITY: SE/PE/SPE
label | bc216b13-9ca8-4455-9736-d76ff648d14c |  | note | ---------------------------------
label | 607617c4-6baf-4038-8669-56374ac17649 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4883c7af-68b2-4533-91f2-9f11b743e888 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | b94ff300-e02b-4348-8455-c102cad5ec3c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d23868f8-a108-49a2-9341-4ebec97a5813 |  | textbox | Name:
text | e4f50156-5cd9-417c-bcc6-5092585475b1 |  | textbox | Position:
text | 2e61555c-320c-48ae-9803-a3a2d533f6a8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | itp |  |  |  | Yes | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | ccccfce1-b452-49f5-912e-7e192921ca51
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | adae9d4d-b67e-4c8c-aaaa-ca344a1cd214 |  | note | Document Title: ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3
label | 1d36f9ac-c9e7-4e17-aaeb-017851de1a0b |  | note | ITP Description: Structural Steel Barrier Rail (Supply & Installation)
label | 792bf003-8c59-4d58-9178-795580743704 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 5c6256de-ad4f-49d2-8146-fb0565543594 |  | note | Revision Number: 3
label | 4d780a5f-9ea4-4460-b3ca-6b6a9768570b |  | note | Revision Date: 4/05/21
label | 65f36246-429d-45a5-ac16-f2cbef85a2db |  | note | ITP created by: Mike Freeman
label | ad9a9a91-dc9f-4891-b621-cb6fc84ef27b |  | note | 1.1 VicRoads Section 610 November 2018
label | 0a57e4bc-0928-44d3-b036-66fad85d22d8 |  | note | 1.2 VicRoads Section 610 March 2019
label | 793e5c6e-9454-405e-90bd-1c89f1cfc756 |  | note | 1.3 VicRoads Section 610 June 2019
label | b47fa068-1e1d-47bd-9539-332bc982f002 |  | note | 1.4 VicRoads Section 630 October 2013
label | 894e378f-d39b-45b1-b9d0-8adc79b0929e |  | note | 1.5 VicRoads Section 631 February 2009
label | 35352c9e-4d3e-460e-9e06-b32e1e3e3d35 |  | note | 1.6 VicRoads Section 671 October 2013
label | 0e0e1850-379e-4faf-ba67-4b5af4125e13 |  | note | 1.7 AS5131-2016
label | e3deb57d-08e9-4b83-adf3-a9cbdc230d8b |  | note | 1.8 AS4680-2006
label | f40c4561-1199-4964-9817-c758f7ce7d51 |  | note | 1.9 AS2312.1-2014
label | 45a9e833-3a9f-4d31-a5be-f375892c1c5a |  | note | 1.10 AS4506-2005
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 24ba9873-986a-43b0-aebd-66aa8b6eb822 |  | note | REFERENCE: IFC Drawings
label | 8ba2419d-0b76-419d-9889-bfdea3e350cc |  | note | MRPA Quality Management Plan
label | b0a2ac9f-a8d8-4c49-9fb9-96783a34faf8 |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 2ae71416-f8ef-4432-a408-ec83d4b18a73 |  | note | Typically this consists of but not limited to:
label | a2f9837b-9e96-4511-a404-e61bf5295532 |  | note | i. Certificate of Compliance
label | ed1b38b3-5435-46a7-84f0-fce5a02994bf |  | note | ii. Completed ITP
label | 22a5d432-acef-44cf-bddb-8ea601fccb84 |  | note | iii. Weld Procedure Specifications
label | bae44cca-3c88-47bd-895e-3f0dafd8dc4a |  | note | iv. Weld Procedure Qualifications
label | e507cd92-82f5-446c-90d1-5684a8406b73 |  | note | v. Welder Qualifications
label | 675423c6-468f-431e-ae36-daee189c87d5 |  | note | vi. Material Certificates and traceability
label | 8cc03af0-098c-47e9-86e7-f544929d8f11 |  | note | vii. Quality Assurance check sheets
label | b4620a60-120c-4f60-bdfb-f99cff3a1b1d |  | note | viii. Welding Consumable batch certificates
label | ce8b8200-9d6a-42c6-bec2-de110e7b5c11 |  | note | ix. Coating certificate(s)
label | 47eb347b-4c8a-461b-8f5e-f59fb88217c3 |  | note | x. Non-destructive Testing (NDT) Reports
label | ccfd3af2-4f85-403b-ba3e-a5e0cce102fa |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | b5e9c16d-2956-4563-84c3-c4664686b5dd |  | note | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | e2cc4b4b-469e-4234-9617-2c5c06f0a781 |  | note | METHOD: Document Review
label | 7ef3e7e9-f596-4baa-88f6-10d30556176f |  | note | FREQUENCY: Each component
label | 1cf1b100-e5c1-4da4-b1c4-fe6a58c7001b |  | note | CATEGORY: IP
label | 44939e93-ab3b-4801-ac4e-f471ed49f1da |  | note | RESPONSIBILITY: PE/SE/SPE
label | be6db382-36bb-4886-9b97-f7e8ac6dca64 |  | note | VERIFYING DOCUMENTS: This ITP
text | 338e1872-e604-47ff-949b-ca0a82af5e7f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | 65824a36-7567-4d6b-bd1e-1fa3ee29cb72 |  | note | REFERENCE: IFC Drawings
label | 7116611b-467f-43af-ab67-33bb9724afe5 |  | note | 671.04
label | 0d7a902d-718c-48ce-a64f-fbd6a8b5c7c1 |  | note | 610.33
label | cebe679f-ed7c-483e-b269-9948b18544f3 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 29944583-3750-4d34-88ff-e8bc1515a4ed |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | 9888b049-32a9-48df-82dd-3a4fd1be21e7 |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | 88b793b5-64a7-4898-a1a8-9c654573ca2b |  | note | iii. have a flowable consistency
label | e2c5158c-dfef-44d9-a446-fdeab7c1a6b7 |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | f4caa0b0-dc8e-4a27-99f2-e034e8b6b9de |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
label | edfd52bc-fc37-4373-a36c-f366e3d8ddaf |  | note | Enter: Teambinder Material Approval number
label | 2a962a0e-f026-49a5-ba2a-b14365fcdcf2 |  | note | METHOD: Document Review
label | 186aa31e-7efd-48a7-a04c-33ad8d746167 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | d2ecd355-d8cc-4cc7-8ce9-3e2a1013b650 |  | note | CATEGORY: IP
label | fc8086bc-1325-417d-bd7b-972ba9ffdabc |  | note | RESPONSIBILITY: Nominated Authority
label | 9e5cb82d-16f2-4610-afc9-3a192c6bbe74 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9288a082-f3b9-497d-ad5d-1698bc6f99ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | f397e5b5-d1cc-43c5-8820-486924d0ef27 |  | note | REFERENCE: 610.23 (d)
label | acc70afb-f477-4742-b58f-eb0a3f0196ff |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 1aadd829-bb9d-41d0-bc5b-5d23a1d1e37c |  | note | Note: This may be the same product used for the concrete curing
label | f715a5cb-917a-47ac-ab17-d8b8c3d3bce5 |  | note | Enter: Teambinder Material Approval number
label | fc27712b-b114-4925-9cb6-1be2100d2bdf |  | note | METHOD: Document Review
label | 28c57106-de44-4019-adc3-4751326396e3 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | 338b68b6-4f77-4cf3-8773-4f62cacdfc35 |  | note | CATEGORY: IP
label | a5908c82-5e52-49b0-9f61-41008a791fdd |  | note | RESPONSIBILITY: Nominated Authority
label | 589f62e8-a15a-4725-84b2-281d15ba0d62 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2708e1e8-41ac-4384-b0dc-5dea0b5884e5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Curing Methodology (for Grout and Mortar)
label | 875562d7-cf5b-44ef-b984-1a9a89ad1857 |  | note | REFERENCE: 610.23 (a)
label | 9de6b0a4-657a-4b36-9ef6-f3870500e030 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 16fbf39b-38de-4c45-9579-37504d435ca3 |  | note | Note: This may be the same document used for the concrete curing.
label | 857647c4-ce33-4ad6-8a59-816bc48c377a |  | note | Enter: Teambinder Approval number
label | 5685c014-f7bd-4675-8a4a-2bcca30b89b3 |  | note | METHOD: Document Review
label | c4756361-759b-4322-bd29-dc8e4641eebc |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | 5a1d76af-9235-4766-8b12-3ae103e9e915 |  | note | CATEGORY: HP
label | 2a8e3c44-94ba-49c5-a05c-733abc27e4e0 |  | note | RESPONSIBILITY: Nominated Authority
label | 2037a5c7-67d3-4bf1-b408-cdf83e575bf6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1ac4ee65-76e1-4910-b8fb-8071dfca6091 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 97ed0588-be40-4a21-9caf-918ee83815f0 |  | note | REFERENCE: MRPA Quality Management Plan
label | 89566f2a-79ec-4a28-a359-defd4f9a224c |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b0c36f0d-68c4-403b-af54-1eaf01f98423 |  | note | METHOD: Document Review
label | 49122914-9b98-4f71-aa7d-913d898dbdb1 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | df60dee1-ce17-446d-b5ca-d1e47b2c246f |  | note | CATEGORY: HP*
label | 9a21a790-9e27-4477-bb0f-96f6727e69c3 |  | note | RESPONSIBILITY: All
label | 7ac017c5-882a-4b26-8789-8ca42e517b4e |  | note | VERIFYING DOCUMENTS: This ITP
text | 1adc9dc0-393f-4c9e-95c3-3e80b7d58ab7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection Checklist
label | 1cf5630f-1230-4b4b-8daf-987804c1b3d4 |  | note | REFERENCE: IFC Drawings
label | 59a0543f-60ac-47ab-bca5-74e5e9ba0d79 |  | note | 630.08
label | fb657cbf-8ccd-4140-a143-e5178064c86f |  | note | 630.09
label | 2a328178-fb1a-48f3-b49e-9e4798c6d365 |  | note | 630.20 (a)
label | 141e21ec-e84c-4731-91b9-cf75a3b2b587 |  | note | 631.06
label | b5d9a857-6cb8-4e8b-a098-4f5a40cb0d4f |  | note | AS4860 Clause 7
label | 276eaa04-056b-4656-9daa-eb5c0dafa100 |  | note | 631.11 (a)
label | e58e3859-1fef-4f07-9ed2-15403201efaa |  | note | AS2312 Clause 9.6.4 (i)
label | 4ef2e693-b97a-495a-b14e-e842389a055d |  | note | AS4506 Clause 2.3
label | 17ab2c08-2c14-410e-9334-8734e2e4b28e |  | note | MRPA Quality Management Plan
label | 06c9fd94-1f36-49c7-8a8c-e8d6622accea |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | e37b0f04-c69a-490b-817e-d10772720fe9 |  | note | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | f4f265d3-5472-4da6-ac27-12e326be5d16 |  | note | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | 96e914ce-886d-4f8c-bcad-31ad9c638a6f |  | note | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | 1129b51b-7334-4cac-8d23-175a8217c628 |  | note | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | 8a33a754-efa3-492d-875d-196c481a939f |  | note | Complete: Materials Inspection Checklist in ConQA
label | 489b6819-8178-4da9-84a1-038359e65079 |  | note | METHOD: Measure , Visual
label | 66fef421-af83-4432-bc30-4d3a08ef178e |  | note | FREQUENCY: Each component
label | 5c3c3df8-5621-4ede-9387-1d0159be7d5b |  | note | CATEGORY: IP
label | bc1a3b08-cfbc-4ac3-867f-c4cbedcf6f46 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 393ee02a-37a4-4a34-8640-6a99143a4087 |  | note | VERIFYING DOCUMENTS: This ITP
text | d411b96d-dbda-4bb1-ad46-aed53ad127fa |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | a8979a74-ff16-4eea-ba26-7317c934bb90 |  | note | REFERENCE: IFC Drawings
label | 2c15f710-8366-4526-abf3-f6f44992378b |  | note | Product TDS
label | 206fc1d8-3811-4a79-a2bd-077d5706af66 |  | note | ACCEPTANCE CRITERIA: Prepare the surface in accordance with the Product TDS.
label | c6873c17-7a74-442a-9d6e-d45803caba3d |  | note | As a minimum, ensuring that it is clean and free from laitance.
label | eefd6b77-2659-434e-975f-1aabace684de |  | note | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
label | 8523ccff-4dbe-4831-91a4-fba87c5f6cc6 |  | note | METHOD: Measure , Visual
label | aed6f142-6089-41ae-a8c3-89adb4f7772f |  | note | FREQUENCY: Where applicable, each post location
label | e39ae37e-b065-4c0b-8adc-ae0b6bc18bab |  | note | CATEGORY: IP
label | 51046109-2670-4d69-880c-52d7e9a48171 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0cdd815c-bace-4560-82d3-6feb55cd05e0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2368695a-90ae-4a46-8ff8-993d3589eac0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | 023aa73b-c30e-41ba-a333-efec6f1bb697 |  | note | REFERENCE: 630.09
label | c5f2670a-bc64-4680-8029-a65df01c04f6 |  | note | 631.14
label | a72b0939-f202-4486-a4bf-ce496a0c114b |  | note | AS4100 Clause 15.2.2 & 3
label | ce7a3207-0e28-4836-8887-8a5fa0d8c97c |  | note | AS5131 Clause 11.5.6
label | d2493af3-9a12-4387-b663-a335ecf81be1 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 0d948f38-5989-466e-9369-cfdc17f6ad3a |  | note | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | 7e55525d-2211-46e2-99d8-5d17e2ef6c95 |  | note | METHOD: Visual
label | 20ef1ef2-40f5-4c36-8944-f84b7fd8bbd4 |  | note | FREQUENCY: Each component
label | edc1eb4d-cb65-4711-94c7-314c7f5075aa |  | note | CATEGORY: IP
label | a8234679-0256-49d8-a3ca-693648bf65ff |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9a14190e-51d0-42cb-b9d7-174a9c7885eb |  | note | VERIFYING DOCUMENTS: This ITP
text | 0ea1d0f7-01c0-4cec-b63a-542603443b9d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | 2a801d1f-9bd7-4b85-9f6a-741a03a82262 |  | note | REFERENCE: AS4100 Clause 15.2.3
label | 4395999b-416f-4e96-8b82-8ee4b595a663 |  | note | AS5131 Clause 11.5.7
label | 1ec78c75-2854-4ce6-aed8-0f2b6a86847d |  | note | 630.12
label | 58359ad3-8bc5-42b1-81fb-9749d4dd4183 |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | ba91d928-b985-47c7-a345-bfb3ce5837f4 |  | note | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | 5c988e39-a283-4d9a-88d0-9dda9eff8424 |  | note | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | c50898e0-732b-4dd4-8dec-7ffdb8f825ce |  | note | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | 96571110-58c0-47ec-b24e-dc1ed3de9dc5 |  | note | Holes shall not exceed the greater of:
label | 2c2a3685-2cbc-4203-b05f-077ffe43914d |  | note | 1.25 x bolt dia. OR bolt dia. + 8mm
label | 31a129ad-e8c2-46b2-8122-023d587b4025 |  | note | Slots shall not exceed the greater of:
label | 20a282cf-7e19-4d9a-a023-885c68dd4c36 |  | note | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 078d055c-3a8e-4a98-a92a-e201aa795131 |  | note | METHOD: Measure , Visual
label | c6a02271-dfe7-4817-ae19-324a0d770007 |  | note | FREQUENCY: Each component
label | 09cb488b-ffe1-47f4-9e43-1a1484c72cb9 |  | note | CATEGORY: IP
label | a8823ece-c9a1-4ec3-8b99-d4c4fa33caad |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ec10c4b-6da0-4a17-bff5-0344165f8a11 |  | note | VERIFYING DOCUMENTS: This ITP
text | d4ba7532-1a8d-47b8-b3b8-2b01fe6a6930 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | bc34da90-b9e0-4ab4-95c7-c50038a2fad7 |  | note | REFERENCE: IFC Drawings
label | d2ec75a0-e0e1-45e0-9b8b-295ed2a9ddff |  | note | 630.20 (a) & (c)
label | fda4fa86-81c1-4040-93e7-8c5e7626edc4 |  | note | AS4100 Clause 14.3.5.2
label | fd3a7455-8e65-40ab-951e-754ac258c7e6 |  | note | AS5131 Clause 6.7.4
label | 770780e0-3143-43a8-a71b-10a4cb87c994 |  | note | AS4100 Clause 15.2.5.2 (a)
label | f9ed3133-bad3-4494-87a4-39b67344e28a |  | note | AS5131 Clause 8.3
label | 9a49125d-ec7d-4097-9699-c99892b4db09 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 6db9d23e-70cf-4664-81d7-0591aa177073 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | 17cbcd94-fcb6-4540-b3b2-0b680d40c073 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | b845b681-a234-4f90-b7b3-3150d6cdb266 |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podgier spanner.
label | b4dbe196-1fb2-4902-bddd-fccee394d272 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 9deade1a-63f5-4701-bdc2-021172775b94 |  | note | METHOD: Measure , Visual
label | 148a2e8d-e241-4886-825d-a9061e857670 |  | note | FREQUENCY: Each bolted connection
label | 15026e97-81eb-4b80-8b94-7bc71125b8b0 |  | note | CATEGORY: IP
label | bfc87069-62fa-4821-aab2-092cfc102538 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c5516ecd-3b78-402e-9926-c67eb62646be |  | note | VERIFYING DOCUMENTS: This ITP
text | 1b284228-e681-4a56-8146-4f5ad4e3887e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Survey Conformance
label | 83ae5c26-8740-4c86-8d60-bde5dc3d1b26 |  | note | REFERENCE: IFC Drawings
label | 1866abde-26a1-46bc-9f1a-413ce8eabc52 |  | note | 671.06
label | 52c2e729-f399-40a6-85f1-44530f5cbbe6 |  | note | AS4100 Clause 15.3.1 - 7
label | d996070c-84c5-444e-b0c9-dac3331d4d5d |  | note | AS5131 Appendix F, Table F3*
label | 5dbf100d-a253-4845-be6f-582f342dbf6d |  | note | ACCEPTANCE CRITERIA: Railing posts shall not be grouted until verification that the Works meet level and location requirements within the tolerances below:
label | 2c1c6756-9e02-4a8a-8952-6752395d28c7 |  | note | Departure from RL = ±10mm*
label | 9b3cee75-90c5-451e-b6db-8b2d19ef35f2 |  | note | Departure from plan position = ±25mm
label | 6e72b565-d14e-4dc8-831c-ac9be196877e |  | note | Departure from alignment = ±5mm
label | 31b6a611-676c-433d-997d-679b07a227dd |  | note | Irregularities in alignment = 3mm in 3m
label | 9b8e385b-d372-4f1b-899c-8aa3eae29688 |  | note | Variation in joint gap width = ±3mm
label | 17c4710c-eaaa-416c-9175-4f1be5b1c42d |  | note | Projection of bolt = +25mm, 5mm
label | be539dff-513d-477f-bb4c-0a79eb5fefb2 |  | note | Attach: Survey Report
label | c6b68eca-dd20-49d5-9d6c-ebe71cf3975f |  | note | METHOD: Measure , Visual
label | 923e4b58-16aa-48c9-887e-d61aff74c7b0 |  | note | FREQUENCY: Each post location
label | b9c591d0-f182-4f7b-8d86-961459d76c01 |  | note | CATEGORY: HP
label | d691a511-f7d0-4873-a157-c8707740a66b |  | note | RESPONSIBILITY: Nominated Authority
label | 8ca25511-2a96-44af-b16d-496a0c6e82e6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 73f82146-01f0-4f19-8027-ea8120884931 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Base Plate Formwork Construction & Placement
label | 9ff622d8-ff24-46af-9ccd-f415969a1754 |  | note | REFERENCE: IFC Drawings
label | 5f4f80d6-bd60-4d79-a509-d32e8209eef6 |  | note | ACCEPTANCE CRITERIA: Dimensions as per drawings (typically flush with base-plate sides and underside).
label | ddffbf4e-b81d-43d8-94ed-ad45f6373607 |  | note | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | 4433e25a-4eb6-4909-b5a3-40c12c29228d |  | note | METHOD: Measure , Visual
label | 95244109-caec-424a-a40e-f2b6f805aa4c |  | note | FREQUENCY: Each post location
label | 4b0c7391-4b91-4d1f-9315-bdcb839a07b0 |  | note | CATEGORY: IP
label | 59759c1a-51b2-4cd3-b2fe-fd2268044a63 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 493c896f-06b6-4522-9956-88352074473b |  | note | VERIFYING DOCUMENTS: This ITP
text | e23648d8-cfcc-43f8-9c63-5243c9b2d3e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-soaking Concrete Surface
label | 68bafdeb-10a1-440d-b091-b45f0aa7dd15 |  | note | REFERENCE: Product TDS
label | 27bce66a-0c40-47d2-b397-0bb50cd2222f |  | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | e36a7c5f-422b-48b3-aa06-222e2399d13b |  | note | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | 0af2f6a7-dc1d-4928-97e8-f1686ebd078e |  | note | METHOD: Visual
label | b315d835-2983-42e3-86ff-28932cbf0f8d |  | note | FREQUENCY: Where applicable, each post location
label | e8ae89f8-6a41-4041-b266-a3aa444bbf4e |  | note | CATEGORY: IP
label | 1e07cfce-9e7d-43cc-aead-aab159abe444 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4f52e84f-f981-4614-8aec-7c9d66a251a9 |  | note | VERIFYING DOCUMENTS: This ITP
text | d074d7fe-dc26-42fe-a7a4-555da426a8d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions
label | 1c99cd6f-048e-4a3d-bfa7-795e3e48aaa4 |  | note | REFERENCE: 610.17
label | 5892b3cf-9551-4b08-a266-91aae9d18c4e |  | note | Table 610.171
label | 67239f9c-c2ea-46df-9e40-058e30b04f46 |  | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | 8420ce35-f614-4164-9d61-ef74b6a796d3 |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 73a43a26-ff86-4842-b858-65975704725b |  | note | Record: Required information on the Grout Pour Record.
label | 16539809-ade1-4884-a09c-e9186db136fb |  | note | METHOD: Measure , Visual
label | d9e5dc6a-4d78-4ece-8157-e29e713eb967 |  | note | FREQUENCY: Each lot
label | bf44f8ee-5dbe-482f-8edf-a02f52cc47fd |  | note | CATEGORY: IP
label | 4599fbab-5d65-491c-9cc8-01ccfd66854d |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 789a01a6-4bde-443b-ae51-4886374e309b |  | note | VERIFYING DOCUMENTS: This ITP
text | 2482e769-6792-49ff-9f91-1caa4e8733b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Mixing Product
label | c8281654-1654-44ee-a762-42abb3e078fc |  | note | REFERENCE: Product TDS
label | ab723bf7-25c7-4aa7-8eab-1fcdb1e17bf0 |  | note | 610.28
label | b6aa5e1d-9f8e-4dd2-b5ca-1c156c1b0241 |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 50e89f1a-1a75-45b9-a619-3ffdc46f7c21 |  | note | Only whole bags to be mixed with potable water.
label | fa0ec530-fe15-4f57-9b19-867842b2ef7c |  | note | Volume of water matches the required amount for flowable consistency and accurately measured.
label | 5884cd4e-57eb-41bb-99b2-689c989d9df4 |  | note | Product poured into the mixer slowly.
label | 25f18c00-269c-4199-b411-4ba881f6cb3a |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
label | c734638b-c38e-4165-b384-8e752c845bcb |  | note | Enter: Required information on the Grout Pour Record.
label | b0448c43-08f8-4b1f-8e4c-fa0006315cab |  | note | METHOD: Measure , Visual
label | a808b417-be61-495e-9dc8-d5130d01da93 |  | note | FREQUENCY: Each batch
label | 211ee0d3-10a5-4355-b4e2-52ededdfb695 |  | note | CATEGORY: IP
label | 1b27dbf0-f6ca-4118-8b4d-be6e86253309 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 58f1f11d-ed80-48aa-b069-7de13e885c7d |  | note | VERIFYING DOCUMENTS: This ITP
text | 21d910d4-8d2f-4f89-93a7-4028be6ba927 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Product Testing - Compressive Strength Cubes
label | 42ba2d43-d3ae-4032-8957-14210aa0203a |  | note | REFERENCE: 610.28
label | b68ffb99-bc47-4ca9-a306-1255fbbe91ad |  | note | 610.33
label | af9ef3d6-e74a-4aeb-9293-25b6cda1bd02 |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | 31996608-fde6-4acb-966d-41d1d7438333 |  | note | Testing is be in accordance with the following frequencies:
label | 64b095bb-6b41-453a-8761-be7a152735d4 |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 853d8362-6d83-4548-95b0-51df3509c9e1 |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | e361237f-83bd-41a0-8eb3-50a84673690a |  | note | Enter: Required information on the Grout Pour Record.
label | 50308706-ee6f-45dc-9b40-efe0181f8d23 |  | note | METHOD: Test
label | 6dc91826-d0d4-4bbe-bb88-6b63dc583b38 |  | note | FREQUENCY: Each lot
label | 41931124-c56c-4e4b-badd-1d681a5a87c1 |  | note | CATEGORY: IP
label | 751a5a0c-d77b-4eb9-9813-79ad6e14e74c |  | note | RESPONSIBILITY: Tester , SE/PE/SPE
label | aac092ba-e9dc-4c89-846f-1db9523a7b91 |  | note | VERIFYING DOCUMENTS: This ITP
text | 94cb63e0-3ee0-46ab-b53c-e8ce72790bba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Placement & Compaction
label | f088ebed-3592-4123-b778-2f4339758e6d |  | note | REFERENCE: Product TDS
label | 32a8ba10-88ef-4e04-aeb4-773155b8ae53 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | e307c596-bdf3-4b81-922d-61177e910df2 |  | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 6dc7bf3d-1f07-4779-bf45-7ead629ae744 |  | note | Product should flow to all areas and self consolidate.
label | f6ed13cf-37a8-4f3e-8dbf-4b7a0f29cfd3 |  | note | Product that stiffens or is showing signs of stiffening shall not be used.
label | d5f40cf5-7a4f-4ae7-8258-04d6ec50c6af |  | note | Enter: Required information on the Grout Pour Record
label | 9f921ce9-3908-4a45-a912-e815caa65802 |  | note | METHOD: Visual
label | 0cca327e-9a83-4402-b536-45cf328717c4 |  | note | FREQUENCY: Each post location
label | 2e55a8f2-3d38-4ad6-9f07-036ae57ee547 |  | note | CATEGORY: IP
label | dd266388-858b-4627-884a-cf6cc7d6ea2e |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 48b23b17-2c5a-4c8a-9ccc-b0391c5330e7 |  | note | VERIFYING DOCUMENTS: This ITP
text | d214f6ac-ddbe-4d31-9486-278e908a312b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Surface Finishes & Protection of Works
label | ace981c0-07f1-4357-ac1a-1f810793a9d8 |  | note | REFERENCE: IFC Drawings
label | 246f5d7e-4fbd-48ee-9fff-9c1995b18414 |  | note | 610.17
label | 0721160e-7900-49d2-b369-d8754776e541 |  | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | 4baa4a75-421c-43f1-bee3-a6ad0787420c |  | note | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | fd39a96a-85d5-4e1f-8ea3-126018406586 |  | note | METHOD: Visual
label | c670e816-5998-40a3-88c0-d135ad1cf990 |  | note | FREQUENCY: Each post location
label | b8da96f8-61e8-4044-a583-7fbf70518957 |  | note | CATEGORY: IP
label | 5dac41dd-90cb-47b9-9e63-eef4e12f022f |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 3dbb4239-3f39-44e9-92ed-a2b2803e20f5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 36ebf752-32bf-4a01-87ca-478cd3c8c735 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Curing
label | 543bc34f-8995-4266-a5d1-f2561747c121 |  | note | REFERENCE: Curing Methodology
label | 4602c0ff-f3fa-4683-859a-1b5285619890 |  | note | 610.23
label | eb6881bf-0770-4be3-be48-1cc8b2da4f65 |  | note | Table 610.231
label | 3ac877eb-d0c4-48c6-a824-4a8f22991b0d |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | fdc579c2-f455-46eb-9465-908c0984118f |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | e8fe8da4-e5a2-4507-bd5b-a4383d96e274 |  | note | METHOD: Visual
label | 433253a6-d757-42d3-9683-77a8fd31b7b1 |  | note | FREQUENCY: Each post location
label | f9fb252d-d4cf-45b1-b0f9-b357ee6b6f85 |  | note | CATEGORY: IP
label | c05f1761-92ae-4f2d-a2c8-2a94acfa3b80 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 6173bb2b-7cca-412d-940e-6498f3afcc38 |  | note | VERIFYING DOCUMENTS: This ITP
text | fcc969ec-16d8-43c6-9a3f-3f34be053f1d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | 0a1f3085-4550-4e42-8797-9974bcaed756 |  | note | REFERENCE: IFC Drawings
label | 712bc534-7327-466b-af20-6f4ba9620d01 |  | note | 631.15
label | d9429056-7e61-478a-9812-fa876c8f42a1 |  | note | AS4680 Clause 8.3 & 8.4
label | a12326fd-5862-40f3-ad73-a4677169e5e7 |  | note | AS4506 Appendix E
label | d9f77c06-a6e9-48ee-8e69-0b2298e00003 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings .
label | 7069ac07-8f96-4831-8aae-43c2de4629ff |  | note | Where damage exists, it shall be repaired using an approved repair procedure.
label | f6c8743f-baf7-4add-9ac9-c6f3ebc0e5c7 |  | note | METHOD: Visual
label | 93956f1b-4a0b-4695-9628-a13eea5b3bac |  | note | FREQUENCY: Each component
label | b47be97c-71d6-40ec-8818-5ef2593a0bfa |  | note | CATEGORY: IP
label | 39d80471-79c9-45e1-bf39-665695d2055a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8e10dcc6-f5c5-488e-a6a7-41fd888ea76c |  | note | VERIFYING DOCUMENTS: This ITP
text | 3e52737e-5713-4f68-bae9-485a050aa00a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | b7347ea4-383d-4d30-979a-eaa90dec6f81 |  | note | REFERENCE: IFC Drawings
label | 0ed92d9c-26a8-4848-88a7-1f0fa3b9e6b8 |  | note | Product TDS
label | d7d4688b-c8fb-4bba-87b9-f926f591cc82 |  | note | 610.28
label | fceeca48-001c-4c33-9b55-9d63d208e177 |  | note | 610.33
label | 7eea0992-1749-476e-b72e-92fdc1f6ff90 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 28ebbd6c-5bb7-49b7-8584-263901aad96f |  | note | 28 day compressive strength per sample comply with the design strength.
label | 76188b2a-219e-4728-a861-d897ae4adf78 |  | note | Attach: Compressive Strength Test Results
label | 7c7123a5-8db1-440b-a091-7a625f6e3808 |  | note | METHOD: Document Review
label | 4fd0907f-3b38-4a58-8199-e204aa3fb353 |  | note | FREQUENCY: Each cube
label | 0c158708-7996-423f-a5e4-a6ff65a55045 |  | note | CATEGORY: IP
label | 574382e9-8f84-42c0-8363-66dbc1f49580 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dd98eef6-bfd9-4386-a9cb-db7bf277318e |  | note | VERIFYING DOCUMENTS: This ITP
text | 6ac54f55-2784-4a37-8fb7-974fa13f19ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | 5059e770-687f-4211-b884-b7bbec704616 |  | note | REFERENCE: IFC Drawings
label | 606114f0-1f95-4e33-a5c6-b11fbb55e1f5 |  | note | 671.06
label | 9baf6b69-5a44-4cbd-988c-e58254687485 |  | note | AS4100 Clause 15.3.1 - 7
label | a514014c-6ab5-4b08-9c2f-e7f87d21b63d |  | note | AS5131 Appendix F, Table F3*
label | 516e7563-152c-4774-b38c-2dfa7a4cce29 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 7c07e500-5502-4c90-99f3-f71c84db5c01 |  | note | Departure from RL = ±10mm*
label | e5c23d32-179c-4bce-a5e8-b40eb1d7b7b2 |  | note | Departure from plan position = ±25mm
label | ed2aff12-7f2e-4b03-9a91-6b970443feed |  | note | Departure from alignment = ±5mm
label | bd7eadf6-72be-4982-92c7-3b749529b4cb |  | note | Irregularities in alignment = 3mm in 3m
label | 78d670b2-e8a6-4331-ae4b-b60f9806dc6d |  | note | Variation in joint gap width = ±3mm
label | 88886655-a112-465a-955f-0a2d101b3499 |  | note | Projection of bolt = +25mm, 5mm
label | 3e733762-e86f-467e-894c-f4f91fe008d2 |  | note | Attach: Survey As-builts / Survey Report
label | 3ea5bb83-505c-40db-96f2-45d9f1ebecd8 |  | note | METHOD: Document Review
label | a281d4c8-fe33-41ae-b257-8ea894a58b5c |  | note | FREQUENCY: Each post location
label | 90f70d61-ea87-4266-838e-bba064d6badc |  | note | CATEGORY: IP
label | a373a05e-5efa-4b4c-a491-fbf5aab92190 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 252e35f0-9c17-41c1-bdd0-1ad38e1070af |  | note | VERIFYING DOCUMENTS: This ITP
text | fddf4fbd-5aed-402e-9aa4-4e239874c64a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 87e9b031-15c3-4aa7-8b59-b80bdd347a89 |  | note | REFERENCE: MRPA Quality Management Plan
label | 86e3ad6b-bea2-4858-916d-a8fb91570e7a |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | aa14db83-f6e2-4641-ae89-4f4f8a29a0b1 |  | note | METHOD: Document Review
label | 8988be7e-5a6d-4c5a-a144-4e215efeeba4 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 3406899d-5b87-4d62-8859-487e24e556f2 |  | note | CATEGORY: HP*
label | 23ac5cdf-5f1c-4cc6-8fdb-c4ec6b55b367 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1b8119c7-bec1-47cc-942e-a9e48e094a43 |  | note | VERIFYING DOCUMENTS: This ITP
text | 23b28d35-c858-4c58-9fc5-5b22bd250857 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6ad4a7d4-ddfe-4d26-8cef-b362e7ef1e66 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 39e74f11-9794-4284-8e50-a948fccefc9f |  | textbox | Name:
text | 5c2170dd-7a7d-4a8c-8d2c-68082e6cb0c8 |  | textbox | Position:
text | 57649ec3-a8e6-40f5-9c95-cf56ba425236 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-Rail-Overhead Wire Works |  |  |  |  | Yes | ITP-RAIL-Overhead Wire Works Rev 0 | cd0d3856-c3aa-4da0-a1f0-5bea9f0ca0b0
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 4ace5bfb-a7ea-4010-888b-eec89888c8f8 |  | note | Document Title: ITP-Rail-Overhead Wire Works
label | 3731cc96-afea-446e-a921-dbb9b9910cc6 |  | note | ITP Description: Overhead Wire Works
label | d74dc73b-5be8-499f-b041-b0380cdf1f48 |  | note | Document Number (In Teambinder):
label | 0911d5da-cea9-431d-bd15-5bf8e00cc11b |  | note | Discipline (E.G. Civ/Str/Rail: Rail
label | e2c53782-a5e1-448a-a20e-0d48af64dd3b |  | note | Revision Number: 0
label | 4446d0f8-137b-4116-a41f-5311b4e668e5 |  | note | Revision Date: 44211
label | 2595a819-1b30-4670-8dae-1e844958eb10 |  | note | ITP Created By: Ravinesh Mishra
label | 0eb1562c-3188-44fc-95b6-6ca9466b1da9 |  | note | ITP Approved For Use By: Romualdo Magpantay
label | 1f7b5411-deb1-484a-af8e-a8e3f4041b13 |  | note | 1.01 L1-CHE-STD-011 MEST 000002-02 (1) 1500VDC OVERHEAD WIRING SYSTEM
label | 9045fb11-033c-4b59-87de-dbeee3124c39 |  | note | 1.02 L1-CHE-GDL-001 Infringement of the Absolute Minimum Structure Gauge Clearance
label | a135719a-d8b7-4c70-8597-a877b5b19b26 |  | note | 1.03 L1-CHE-INS-029 (1) 1500v Auxiliary Side Feeder Location
label | 9da748f0-c01f-4b16-8d07-98cc2b0a8692 |  | note | 1.04 L1-CHE-INS-037 (1) Overhead Wiring and Signalling Structures
label | 1cb56a76-4cf3-4e45-9a53-80580265ec88 |  | note | 1.05 L1-NAM-INS-015 (2) Relationship between overhead airgaps and signals
label | 5d4f0fe8-0399-434b-ba77-d63c454ea9ec |  | note | 1.06 L1-NAM-INS-039(1) Maximum span length of new mixed tension airgaps
label | c5969079-ac86-4338-9ccf-a10987cb16db |  | note | 1.07 L1-CHE-INS-038 INSULATING COVERS OVER OHW MASTS
label | 7b110172-f535-4770-804e-70919cc8c353 |  | note | 1.08 Clyde Road Package 65 Design Drawings
label | 92316475-17e6-4d68-9075-4c0913f62dfc |  | note | 1.09 Clyde Road Overhead Waiver SWXXXX
label | 6a1fba53-3563-453a-ae56-d75cbc2e341f |  | note | 1.1O L1-CHE-STD-058 OVERHEAD WIRING AND SIGNALLING STRUCTURES STANDARD
label | beb47dd8-5304-4e86-b035-f651bb819aeb |  | note | 1.11 MRP-DPK-016-00-ETN-0005-0 OVERHEAD WIRING PACKAGE (RLMU)
label | 293c4b91-3fb8-46bf-b1cd-0eb214840a4e |  | note | 1.12 MRP-DPK-016-00-CSF-0018-0 OVERHEAD MISCELLANEOUS STRUCTURES Package
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.01 Obtain and submit Material Certificate of Compliance for Overhead Materials; Structural Steel/OHLE Jewellery/Contact, Feeder, Auxiliary Feeder, Catenary, Jumper, Guy & Dropper Wire -Small Part Steel
label | a6d45b4a-0d8e-4d04-b528-3e6410b498fb |  | note | REFERENCE: IFC Drawing
label | 60f758bb-948f-42c5-862b-0ff78586de77 |  | note | Bill of Materials
label | b7dcbc21-2aa6-463c-adbe-c01165d8afb4 |  | note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | 1888fb13-680a-44a3-bb5f-9a93a9539eef |  | note | Attach: Manufacture Certificates of Compliance
label | 97bd6505-4fd9-471f-8fb3-19c0107fc484 |  | note | Manufacturers document record
label | 2d8c02a4-b2d8-476e-b7ba-f28e1f8f8efe |  | note | (WPS,Welders record/Surface treatment record)
label | e42e3d71-43ca-430c-be1b-24407dd4166d |  | note | METHOD: Review Document
label | 3de95fd7-9552-466a-9893-cece46d57121 |  | note | FREQUENCY: Once
label | f3910874-c089-4cc1-b4fb-d15373a6d5fb |  | note | CATEGORY: HP
label | 9704bf3d-785d-48cf-959f-5c1e7f07c99d |  | note | RESPONSIBILITY: Overhead Supervisor and Project Engineer
label | 47bbe57e-4253-42cd-bc1a-6f19b2d256d7 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1127a973-9607-43fb-a92b-b9173c5e88f5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.02 Inspect supplied items upon delivery
label | 337af3c5-c9f2-4148-81e3-e19fbde31dff |  | note | REFERENCE: IFC Drawing
label | 03e4d736-c99b-4616-94cc-501b029c702f |  | note | Bill of Materials
label | 8909e983-dece-44cf-9d58-3e911e9cfa3c |  | note | ACCEPTANCE CRITERIA: No damage or rust on components
label | 77094171-1b6c-4012-b489-efff3c89466b |  | note | Validate specification, total number and type of components matches drawing
label | eb69eb29-57b9-4e5f-9837-aa91c9565f2d |  | note | Attach: Photos on site;
label | 8e155ccc-c2d4-4aa5-8b7f-f74d7ee84026 |  | note | Structural Steel
label | 5f5780cd-82b1-4a3d-bf29-57ca4c180341 |  | note | OHLE Jewellery
label | 2e076a1a-fc51-443f-9b8c-4c11be398cee |  | note | Contact, Feeder, Auxiliary Feeder, Catenary, Jumper, Guy & Dropper Wire
label | 50c101e4-effd-44c5-84a3-8fd63cc4de95 |  | note | Small Part Steel
label | b45b1d1b-8ac0-4cc1-aeac-e23f6b058c20 |  | note | METHOD: Visual Measure
label | 77324b1a-9f4e-4e46-9a92-69b86299f629 |  | note | FREQUENCY: Per delivery
label | 1901db5e-5041-4062-a082-52a7c53eeb98 |  | note | CATEGORY: IP
label | 52e626b0-3983-42bc-8248-af397f9d7343 |  | note | RESPONSIBILITY: Overhead Supervisor and Project Engineer
label | b75c029e-19a8-469c-be50-75931185a96e |  | note | VERIFYING DOCUMENTS: Material Inspection Report
text | 1b5e9399-aa02-4427-8b1e-f934cfa6e3f5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.01 Removal of existing overhead wire
label | 41988c8f-a227-41d8-9b4d-352440fdac41 |  | note | REFERENCE: Design Drawings:
label | 505a5fae-df0e-43b9-91af-e540e8b26a50 |  | note | TBC
label | 5ce6f4b7-b36c-44f2-9b42-ba07ed8425f4 |  | note | L1-CHE-STD-011 MEST 000002-02 (1)
label | 3466d897-95f5-4bca-b252-245c1e26a9b6 |  | note | ACCEPTANCE CRITERIA: Anchor overhead wire as required at structures as identified in waiver
label | ab1c2451-8aed-4385-9203-0647c534c863 |  | note | Remove and roll wire for storage clear of site
label | 92ddcf31-04d6-4812-baa2-133216e72656 |  | note | METHOD: Visual Measure
label | cdb4f327-5e8c-4155-b80b-4748d02854f4 |  | note | FREQUENCY: Once
label | 41633545-bf5d-4b98-8225-87d42be827c0 |  | note | CATEGORY: IP
label | e05e5ca4-ae3f-459b-88f8-2dcc10ce2d61 |  | note | RESPONSIBILITY: Overhead Supervisor Site/Project Engineer
label | 5e09316d-812e-41c7-bc73-079854503277 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9eacaebd-c12f-435f-a13c-d3dbc60e7fc2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 Jewellery Installation
label | 15e234e5-f70d-4a20-bfef-0d6b499b20ff |  | note | REFERENCE: Design Drawings:
label | 10ba8ad0-a703-4d4d-933e-c74caab897cd |  | note | TBC
label | 66e4431f-13d5-4a01-a025-ed26a5cd1c10 |  | note | L1-CHE-STD-011 MEST 000002-02 (1)
label | 18700123-0863-4228-a61a-695823608666 |  | note | ACCEPTANCE CRITERIA: All overhead jewellery installed as per IFC drawing and relevant standards
label | 00164390-0af6-4ab7-9cb8-24d162d2e65a |  | note | METHOD: Visual Measure
label | 41998600-7ac5-405e-aaaa-e9784a9c9ecd |  | note | FREQUENCY: Once
label | 3a458b35-4ae1-41e0-9bcd-7e2fe1752cc5 |  | note | CATEGORY: IP
label | c037e010-c408-402c-b8c0-5d4794d0933a |  | note | RESPONSIBILITY: Overhead Supervisor Site/Project Engineer
label | 032bc592-d9b4-46da-9697-32ac43f42057 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9e12b3b4-f631-45de-98f3-8d4114c11144 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.03 In-Span Equipment Installation
label | 960e3f56-ad92-406c-852f-2ea7d3527fb0 |  | note | REFERENCE: Design Drawings:
label | 53f11579-3e6b-45f7-b4ce-1593e9d75cac |  | note | TBC
label | a3c96014-a082-44bf-850b-6a3ebe5c7dde |  | note | L1-CHE-STD-011 MEST 000002-02 (1)
label | 5df315a1-4720-4721-8513-0e733dfd63f4 |  | note | ACCEPTANCE CRITERIA: All in-span equipment installed as per IFC drawings and relevant standards
label | 3a4e1bfb-2570-42b8-9e2a-54fdb2fce1dd |  | note | METHOD: Visual Measure
label | a1586588-ac66-4988-bc50-81dffd1c05d4 |  | note | FREQUENCY: Once
label | d92b8826-8bc3-4e97-b0ed-116bf19f5bcb |  | note | CATEGORY: IP
label | c39c928d-5660-4bb6-83fe-456c6482a250 |  | note | RESPONSIBILITY: Overhead Supervisor Site/Project Engineer
label | 8b1565a2-1506-48ed-af38-415c7d8366d4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2abdfc02-1a5a-4cb0-81ce-bacc6b9d6ee3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.04 Overhead Wire Installation
label | ac3bc9bd-84d7-4665-adac-1b4c36c7f729 |  | note | REFERENCE: Design Drawings:
label | 20278b71-1ac4-4008-a7c2-352e1e7da6cb |  | note | TBC
label | 156210bb-cdfe-419d-b509-aef8ca53a039 |  | note | L1-CHE-STD-011 MEST 000002-02 (1)
label | c77e22e4-d2e9-4b4d-85c7-e82ac0897937 |  | note | ACCEPTANCE CRITERIA: Overhead wire installed as per ICF drawings and relevant standards
label | d04ddd7f-a501-4174-aad7-77386ae2c42b |  | note | Height & stagger measurements recorded and confirmed within allowable limits
label | c7dec2a3-d912-4ad5-bb49-997be2b8ee17 |  | note | METHOD: Visual Measure
label | 7aba9c45-a5da-4dec-b898-e3bb1f925252 |  | note | FREQUENCY: Once
label | 8838ec9a-2d25-4164-8921-af85108055d1 |  | note | CATEGORY: IP
label | 5e04a3be-6c98-4842-b7d2-f4f00e22bfc9 |  | note | RESPONSIBILITY: Overhead Supervisor Site/Project Engineer
label | 61cba058-08d9-4cbb-bdb3-55ff17a13e21 |  | note | VERIFYING DOCUMENTS: This ITP
text | a43a1880-7cbf-4672-8172-9ab112551680 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.05 Complete Clearance Checks
label | fa0b3b8f-efcb-4507-a1ad-c8e4f8cfa699 |  | note | REFERENCE: Design Drawings:
label | c8e0e5ea-af47-4cc8-b16e-a294aa82fc45 |  | note | TBC
label | 9d963a32-ca52-4161-b1e8-e63874519b53 |  | note | L1-CHE-STD-011 MEST 000002-02 (1)
label | 3712cb64-45d7-4f24-87d8-7697206ab1b7 |  | note | ACCEPTANCE CRITERIA: Visual inspection for clearance and wire staging from Hirail EWP
label | 338fcd5d-3a3c-4440-9177-aa674fc5d701 |  | note | METHOD: Visual Measure
label | ca2d848d-32f5-49de-bfe3-84be36805f0d |  | note | FREQUENCY: Once
label | dea5899c-b457-41d4-8ac3-19dac2fc4402 |  | note | CATEGORY: IP
label | 982b56c6-8fdf-411c-89ae-c1849ea8b54f |  | note | RESPONSIBILITY: Overhead Supervisor and Site/Project Engineer
label | 382a86d7-b5b4-4cb5-8c1e-f213eac23f53 |  | note | VERIFYING DOCUMENTS: This ITP
text | 668d79d0-89f1-4fad-a4e7-890ba0625150 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.06 Complete Pan Run Test
label | 320fdca2-99f2-4a2f-ab9f-84073f2a4780 |  | note | REFERENCE: Design Drawings:
label | ad435706-864e-4033-b192-094085baa7fa |  | note | TBC
label | a4c3a7e8-ce03-49dc-8f27-1ca1d5c58620 |  | note | L1-CHE-STD-011 MEST 000002-02 (1)
label | 51dab84f-f1e2-4dae-ae9e-c2fb8b00adfe |  | note | ACCEPTANCE CRITERIA: Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
label | e53d0ab5-9990-411d-9619-fa982d30518a |  | note | METHOD: Visual Measure
label | cfd004ef-5235-4aae-8f63-2b2ab9042a40 |  | note | FREQUENCY: Once
label | 391864b3-c19a-463b-9428-148bb6a41003 |  | note | CATEGORY: HP
label | b41c3b2e-afc6-4ae5-852d-81774fdda7c4 |  | note | RESPONSIBILITY: Overhead Supervisor and Site/Project Engineer
label | cdbe8d8b-5674-4c6f-9ead-cd2a49b285a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 17836927-bd10-434b-abf2-51332f5b35ac |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Final Inspection
label | f9b3bf82-bcc9-4f81-b1b9-c317e27b37a6 |  | note | REFERENCE: IFC Drawings
label | 032fd0ee-fb29-4e98-a51e-2875bb7eba73 |  | note | ACCEPTANCE CRITERIA: System in a working state to allow passage of trains with pantograph applied
label | d8ac0279-3519-4be8-a20d-555f59c5d8ca |  | note | Sign-off SAR
label | 1732955d-acc7-4e3f-9897-24c412540f1a |  | note | METHOD: Visual Measure
label | 6775d706-17aa-452e-997d-2e5fe1b7c84a |  | note | FREQUENCY: Once
label | bb9f4b38-0d25-47a8-8fe3-302965aa481b |  | note | CATEGORY: IP
label | 3df73583-03ff-445f-b5f4-67e3cd953d3f |  | note | RESPONSIBILITY: Overhead Supervisor and Site/Project Engineer
label | 8c912441-525c-4c23-b976-c40afd8e2210 |  | note | VERIFYING DOCUMENTS: This ITP
text | e5472fe8-7696-4ab8-9504-77ecbca947a8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Overhead Structure/Wiring Survey/As built
label | 3402e0b1-19cd-4bb8-8cf9-00dad3babe87 |  | note | REFERENCE: IFC Drawings
label | 4761d4bd-65b1-4b67-be39-ff4d7903e907 |  | note | ACCEPTANCE CRITERIA: Attach: Overhead cross section relines
label | b6c6f769-e07f-41c4-9b66-8a1a5d2e82da |  | note | METHOD: Visual Measure
label | eb2ea10f-9875-490e-82b9-3406bfcbe987 |  | note | FREQUENCY: Once
label | 1443496a-a5b3-4c97-b071-84ee7b7f5ae3 |  | note | CATEGORY: IP
label | 1b70d978-3be4-441f-bd8d-f6f8cd14af94 |  | note | RESPONSIBILITY: Overhead Supervisor and Site/Project Engineer
label | 6ad25566-882b-44c0-b66b-0c1feee11993 |  | note | VERIFYING DOCUMENTS: This ITP
text | 614293b0-58c7-40d2-88f1-f80a35752ef6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Track Certification
label | c8de41d0-90f4-4d88-befe-077ef3048b72 |  | note | REFERENCE: Overhead Certification Doc #
label | cce640be-ef1c-4193-9ef5-133798c13af4 |  | note | ACCEPTANCE CRITERIA: Attach: Overhead Conformance Certificate
label | 427f80aa-0a2d-4adf-b5a9-9c726a32b0dd |  | note | Attach Site Photos: Before/After Photo of worksite
label | 6f4dfdb8-f049-4687-ab4f-726d761f3c6f |  | note | METHOD: Visual/ Measure/ Document Review
label | a4d52ced-9779-4aab-bb3c-01ba5d7fa895 |  | note | FREQUENCY: Once when all occupation works complete
label | 4eaae94a-f52c-4fef-b358-7445f759c444 |  | note | CATEGORY: HP
label | 9b0f2aa8-1635-4bd3-ba65-4166d7d16826 |  | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | 86493105-2153-4729-8fbe-28194af643d4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4e4a7968-43af-4fb4-bc9a-06a704b9caef |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 81cbf72e-95ce-4e9b-a566-953589aeaeba |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a4d25a16-6b3e-416e-aa96-046f06c9aa69 |  | textbox | Name:
text | bcb05302-50d0-4bcf-bd5d-6d09a6870e06 |  | textbox | Position:
text | 53634080-eed1-4739-b6c6-65b3d0ac3a5b |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-Rail-Track Construction Rev 0 |  |  |  |  | Yes | ITP-Rail-Track Construction Rev 0 | d3e2b5a1-622b-46ef-bafd-f1bd3775d214
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | bb020dff-ea34-52e6-9994-38debcf84acc |  | note | Document Title: ITP-Rail-Track Construction
label | 5649d91e-28f8-5a96-bd11-e29aafab21da |  | note | ITP Description: Track Construction
label | 479fba19-abd3-5e5b-8c27-2db39c68c214 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
label | 32503da6-3ca2-5b90-841a-d39ed72d14f3 |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | db33951c-284c-5d87-a83c-483d0411b589 |  | note | Revision Number: 0
label | fbef440d-661b-5436-8977-b5177d9b8e81 |  | note | Revision Date: 1/10/2020
label | 84efcb21-a89f-5d59-a74e-b3e4c4f4b260 |  | note | ITP created by: Mathew Holm
label | 2a00b226-18f4-5177-b541-6b81a6279535 |  | note | ITP approved for use by: Romualdo Magpantay
label | 80372e6e-61ed-5660-ad35-44ee8ef6a161 |  | note | 1.1 L1-CHE-SPE-316 Concrete Sleepers
label | 227806c8-5eab-5dd7-b099-2ba5956b386a |  | note | 1.2 AS 1085.1 Railway Track Materials – Part 1: Steel Rails
label | edcd7411-6fc9-5b84-99cc-3ee92b8e5a4f |  | note | 1.3 L1-CHE-SPE-003 Heavy Rail Construction Tolerances
label | 23657f6b-2738-553a-a6b2-a3a120c1ebc1 |  | note | 1.4 L1-CHE-SPE-064 Ballast Supply
label | 4a07d96b-17f7-557e-aa0c-6b6fc00ca82f |  | note | 1.5 L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | 7828a9a3-8070-5077-a6e5-0bcb03411cb6 |  | note | 1.6 PTC Heavy Rail Track Construction Standards Drawing F598
label | 3e4efb5c-6e32-5023-b50e-d4ad61b9d6ae |  | note | 1.7 AS 1085.20 Welding Rail Steels
label | be2a13f4-dccd-5ec9-8038-e5b8786957aa |  | note | 1.8 Evans Road Package 70 Design Drawings
label | d8fb5bd2-1816-5678-aacd-0a7501b2b434 |  | note | 1.9 L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan
label | 3ba629f8-4ab8-5597-a184-032700c2cb4d |  | note | 1.1 L2-TRK-PRO-028 Requirements for Welding Track
label | 63d1af6b-517a-588b-bbeb-a5f933670a28 |  | note | 1.11 L4-TRK-FOR-074(2) New Weld Return Form
label | faafa03a-949e-568c-b5b0-12eb00d42dcf |  | note | 1.12 Welded Track Management Chapters 1-16
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain and submit Material Certificate of Compliance for Track Materials; Track Rail, Track Sleepers, Track Jewellery, Geofabric, Triax, Class 4 Fill 19mm Aggregate, Ballast 60mm Aggregate, Welding Kits, Welding Crucibles
label | 7e3ef657-387a-54cc-b152-88fa31e767a2 |  | note | REFERENCE: IFC Drawing
label | a27efc22-029b-5a0f-b062-24858112fce8 |  | note | Track Construction Site Mudmap
label | 47146058-2816-514a-9bbb-8b738b6fa542 |  | note | Bill of Materials
label | 7325d0a8-7bfc-540c-aa9e-806321849858 |  | note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | 9e72fc95-6791-55a4-a19e-fce26bbdabc1 |  | note | Attach: Manufacturer Certificates of Compliance
label | c46abedb-f13b-571e-9446-7d6d9f2db4db |  | note | METHOD: Review Document
label | f9d0a084-0359-5249-85f9-b317e2db63ea |  | note | FREQUENCY: Once
label | 659f8a9f-2cba-59ff-9e89-5af9ba37e33c |  | note | CATEGORY: HP
label | 03de1f8c-8df7-5a1c-ba0b-e829934d9181 |  | note | RESPONSIBILITY: Track Supervisor Project Engineer
label | 356a8402-8e23-5b0c-943b-b6df42ec8502 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e9050fb6-7063-5cfc-a086-c717ee12adc4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Submit Welding Procedure/welding qualification welders Record
label | b75d3dd5-185f-5e4d-bf82-adf46b34a871 |  | note | REFERENCE: L2-TRK-PRO-014 Welded Track
label | f4461339-c198-5196-afdf-b17befb55148 |  | note | AS 1085.20 Welding Rail Steels
label | 6835fa2f-0033-5f78-8fff-200466f3533f |  | note | ACCEPTANCE CRITERIA: Qualified personnel & welding accordance with manufacturers specs.
label | 4aa0254a-15a2-59f8-88ee-cfbce2d1f4c9 |  | note | METHOD: Review Document
label | 3155ec44-b136-58dc-bab9-4f436586c72e |  | note | FREQUENCY: Once
label | b00c9348-00b8-549c-ab4c-d98225e20d76 |  | note | CATEGORY: HP
label | c36b28d0-1c19-500a-97c1-e94b1bd2bfac |  | note | RESPONSIBILITY: Track Supervisor Project Engineer
label | f3982b3b-561d-58d1-92ea-8b624860d53e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | d604b772-5d3c-5073-9a28-9d1f21ae4f91 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Track Tamping Travel Network Path Circular
label | c0733544-72ef-5efa-9a17-c145655c45ea |  | note | REFERENCE: MTM Access Resource Management System (ARMS)
label | c4243bf8-825a-5862-aab5-2959c34d90a1 |  | note | ACCEPTANCE CRITERIA: Approval of Travel Path
label | ceeeb8d1-7fcf-53cf-b8e3-ed60a201f267 |  | note | Attach: MTM Approved S'Circular
label | 8d6d66be-3919-5269-b418-30185d38a8ce |  | note | METHOD: Review Document
label | fd692c38-5c11-5f0a-8ea7-7492b2d8af4f |  | note | FREQUENCY: Once
label | 977bd409-2c51-5e41-9092-cfd48b3df794 |  | note | CATEGORY: HP
label | d7acd0cc-df45-55fb-b782-6366b3166580 |  | note | RESPONSIBILITY: Access Planner
label | aa6bae4b-b46f-588e-8a0a-77fa4d6d54c0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9ac7077c-7538-5ce0-b53c-694d31ef0691 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Inspect supplied items upon delivery
label | 60dac500-fd60-5077-94ad-5ba75052dc54 |  | note | REFERENCE: IFC Drawing
label | 45fd3897-c48f-5957-b983-0a4dd5081acc |  | note | ACCEPTANCE CRITERIA: No damage or rust on components
label | 6b155f3d-e9e4-59d3-90dc-7dc48166713c |  | note | Validate total number and type of components matches drawing
label | 75229a46-3352-5be1-afb3-74f5d1be9033 |  | note | Attach: Photos on site;
label | eb322edf-1208-5029-bd86-ae88caff6310 |  | note | Track Rail
label | ddd1dc95-7288-5976-b52e-c7e86382aa9a |  | note | Track Sleepers
label | 1dcc0cfd-ddfc-5dd2-8a09-ca56e20f3f54 |  | note | Track Jewellery
label | a85d1190-3ec3-5bc7-9592-dac53d5c133e |  | note | Geofabric
label | a034ff56-997d-5626-bb15-1ef74dbb73b9 |  | note | Triax
label | d01a2456-36db-5b53-af75-ddf33172e535 |  | note | Class 4 Fill 19mm Aggregate
label | 8dde5893-1890-5a8c-9c2f-3f3ce0dc1a28 |  | note | Ballast 60mm Aggregate
label | 080f577a-948e-5bf5-8f14-4569921ca1d2 |  | note | Welding Kits
label | 55d34a4b-345a-5909-b990-f28fbcdc45e5 |  | note | Welding Crucibles
label | 1a9ed0e8-479d-5cc5-b6cf-ab81403e2e1e |  | note | METHOD: Visual Measure
label | 543c4791-e6b3-5b9e-bba9-de0e02481f99 |  | note | FREQUENCY: Per delivery
label | b1e31b49-e1de-595f-b7d3-13b8ba2522fd |  | note | CATEGORY: IP
label | 3821c5d5-0801-5185-99d1-1dc6712266f3 |  | note | RESPONSIBILITY: Track Supervisor Project Engineer
label | b6ad6661-37a0-5748-a906-38ffee94ad3c |  | note | VERIFYING DOCUMENTS: Material Inspection Report
text | d6a505f5-59ca-51f5-80ba-b6620e72919b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Earthworks ITP/Formation/Ground improvement/capping layer
label | bb41c16c-e16a-5edd-8372-bd1f02db87b5 |  | note | REFERENCE: L1-CHE-SPE-178 Engineering Specification Earthworks & Formation Specification
label | 44fec51f-7152-51bd-97b9-0d7b8c5e224f |  | note | Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
label | f8085aa5-a2f6-5055-930c-9ddd10fe467a |  | note | ACCEPTANCE CRITERIA: This Item will be completed under the checklist Earthwork/Ground improvement
label | 46bb9ed7-1cf8-5ca3-ac3e-5211d416e4d2 |  | note | METHOD: Visual Measure
label | 2f5a549e-e220-5e41-a05a-cae777613e6c |  | note | FREQUENCY: Once
label | 17f52b9b-34c4-5fb7-ae89-c48e3d228260 |  | note | CATEGORY: IP
label | a0ceb5c7-1a57-5604-ab60-4ddaf23d7951 |  | note | RESPONSIBILITY: Track Surveyor Track Supervisor Site/Project Engineer
label | 99c76983-f683-51a2-aaab-6b632d833d3b |  | note | VERIFYING DOCUMENTS: This ITP
text | 857b7628-eeba-5fe2-94a3-293252875f2e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Installation of Bottom Ballast
label | 2ac6f5e8-e0f3-532c-a071-6d8440e7a9b2 |  | note | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
label | 5c43cf91-6d58-50cc-bb6f-0b5923edce97 |  | note | PTC Heavy Rail Track Construction Standards Drawing F598
label | 04abda49-1f18-5ec2-bb9d-10451024a22b |  | note | ACCEPTANCE CRITERIA: Overall Minimum 300mm bottom ballast depth
label | f36d08bd-56d0-50f3-9ea6-f03258dc25da |  | note | Ballast to be placed in 150mm max layers.
label | ae198c92-6868-585c-8c76-f9fcf69434fb |  | note | Bottom Ballast to be left 20-40mm below final design level – Tolerance (under sleeper) -0mm, +25mm.
label | ce5c1a69-ab30-5e10-97e3-28ee9a7eb8ad |  | note | Layers rolled 10 tonne smooth wheeled vibrating roller with minimum 3 passes
label | 48e9c52e-2caa-5d1c-9a1f-bd6613e102fe |  | note | Attach: Survey Measurement
label | 8d74f344-e769-5da6-9ad3-dbfbe51bd97f |  | note | Attach Site Photo: Installed Bottom Ballast Layer
label | 34982b31-c88e-5d56-ac16-b8d3b3d32490 |  | note | METHOD: Visual Measure
label | a423cca0-0b2f-5802-ba28-e92150fa66bf |  | note | FREQUENCY: Once
label | 1e65978d-fc91-5e3f-b318-c9c2d883d563 |  | note | CATEGORY: IP
label | 4b19656d-791f-5469-bd3c-d16556a7a2bf |  | note | RESPONSIBILITY: Track Surveyor Track Supervisor Site/Project Engineer
label | 0e45e2d0-065c-5c21-87f7-7175a28f951c |  | note | VERIFYING DOCUMENTS: This ITP
text | 7d6a48b7-6a75-5f19-8890-dd88eded71d1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Laying of Sleepers
label | 2c5add99-d9e6-5715-871b-51ddb294cc48 |  | note | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
label | b8f18d3e-fcc4-52dd-aeea-69eadea6661e |  | note | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | fcfd854f-5eba-5023-92b7-dddb2858a0e6 |  | note | ACCEPTANCE CRITERIA: Sleepers Square at nominal 685mm ±25mm for open track
label | 7bdab8d3-e9db-52a5-891c-4334834411cc |  | note | Sleepers Square at nominal 600mm ±25mm for under RRV pad
label | 311e27e2-b5a7-5c7a-9117-da529a8d8920 |  | note | Attach Site Photo:
label | ea916252-ed8b-5221-b30d-4c152bfcf617 |  | note | Laid Sleepers
label | 567c70e5-7de7-51ab-a4f9-6013d801916c |  | note | Sleeper Spacing Measurement
label | 42a51278-5761-5db4-bce8-5bbe0b5422b8 |  | note | METHOD: Visual Measure
label | cdc71a62-e365-507c-83b5-a833ef35a3f1 |  | note | FREQUENCY: Once
label | a7aed53c-75d3-5806-aec9-80097578e44b |  | note | CATEGORY: IP
label | 4caa292a-fcf2-554f-b0e1-9eba7535dd00 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 352e25bf-2e22-50f5-a46a-1b384064234d |  | note | VERIFYING DOCUMENTS: This ITP
text | 1dccbd22-9d10-5548-889f-59702a5f1376 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Rail Installation/Clip Up
label | c88f6d1e-3052-5c79-953b-ac304ed7d4d4 |  | note | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
label | 80bcaeec-8430-5a25-9659-70f41afb8b54 |  | note | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | 43c09f28-5a44-5957-b7e9-2974a941071c |  | note | AS 1085.1 Railway Track Materials – Part 1: Steel Rails
label | 383c8331-1655-54a9-ae47-07ea495cd337 |  | note | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators
label | a36881b0-6164-5b3f-8cb1-04bbba533789 |  | note | All rail fastenings installed
label | c23ad812-55bf-54da-9250-b76a1dcba2e5 |  | note | All Rail Ends, positioned midpoint of sleeper bays +-25mm
label | 18403e1f-e749-5f8b-92e6-22b12170f1e8 |  | note | New Rail lengths minimum 20m
label | 69a59288-8bce-535e-b849-f46052337502 |  | note | No Existing Welds Within 4m of new rail tie in point
label | f49d9af7-2474-5810-b8f7-3191e4e9dca6 |  | note | Attach Site Photo:
label | b6b1aa8d-2e57-5723-9608-ce2324ba04e7 |  | note | Laid Rail
label | b1f486a0-74d4-57a8-b667-bd76ffaa85a5 |  | note | Rail Joint to existing weld measurement
label | 18661506-6d92-580a-9773-ce25480ca3d0 |  | note | Weld joint between sleeper bay measurements
label | fdca1ffd-3346-54e9-8532-6a9788d0ad7c |  | note | METHOD: Visual Measure
label | 9d75d5a5-7222-5945-80f2-66280c9a9777 |  | note | FREQUENCY: Once
label | 075d2ff1-95b1-5a66-8a74-290b8fa0d69a |  | note | CATEGORY: IP
label | 250473a6-9b79-5743-b4db-497d90730533 |  | note | RESPONSIBILITY: Track Supervisor Site/Project Engineer
label | 35abaa99-6571-5f78-9ef6-46562864b22c |  | note | VERIFYING DOCUMENTS: This ITP
text | 86d73930-8fbf-5109-affd-5ac7c49447e1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Track Tamping
label | 4c10cb1f-4bee-579f-ba9d-9c835c2394dc |  | note | REFERENCE: Track Tamping Design Drawings
label | ee95f3e9-a4c1-52a9-a591-a0e33d2e4ae0 |  | note | MRP-056-C-AUR-DRG-70-LBK-CPW-0025
label | 54add3bf-0a2a-58af-8387-43c9b117e280 |  | note | MRP-056-C-AUR-DRG-70-LBK-CPW-0027
label | 6b39fac4-260e-5a09-be5b-41724bce0735 |  | note | MRP-056-C-AUR-DRG-70-LBK-CPW-0028
label | df44eeac-3f18-5c3f-8c3f-8bef807aba0e |  | note | L1-CHE-SPE-003(1) Heavy Rail Construction Tolerances Table 1
label | 2906243c-0bd8-5d94-869b-444af37f97d5 |  | note | ACCEPTANCE CRITERIA: Tamping Ensures Track Geometry Tolerances are not breached;
label | 4294c7d1-88f4-5105-b5c6-a7dceba73ff3 |  | note | Gauge +3 / -3
label | 5ceb767a-4579-549e-8bf2-72f5596d3e06 |  | note | Gauge Variation in 2m 4
label | 30e400ee-9f0b-53fc-b32f-5f41fa6b3719 |  | note | Line (10m Chord) +4 / -4
label | 36ceeb46-3e07-5be1-b1e5-0b0d603482e7 |  | note | Twist (3.5m Chord) +2 / -2
label | f2f849b5-328a-54a2-8bbd-527515c2bcd3 |  | note | Top (10m Chord) +5 / -5
label | 63db3d5d-a8cb-5374-b61d-d6ba7ed963c3 |  | note | Cant +5 / -5
label | d2253ccf-91f7-5d0e-b995-520c6b221ceb |  | note | General Alignment +15/ -15
label | e9aed65b-3b6a-538a-8955-701f222c1fd3 |  | note | Survey measurement of RL of top of rail head
label | eae220a3-65ed-5367-87be-fef430a5c27d |  | note | A minimum horizontal clearance of 3.0m from track centreline to structure.
label | 0ae83682-11fc-5710-9e40-7bf5614cbda3 |  | note | Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
label | d7d43f01-fd70-524b-b049-c0cb7f0f53b6 |  | note | Attach;
label | c62da28f-aced-5668-82db-46fabe319e5b |  | note | Tamping Geometry Recording
label | f24fcd35-8f78-59d0-9c19-758cca07b41d |  | note | Survey RL measuring sheet
label | 2a452119-1408-5d7a-9006-c2c0e3b33147 |  | note | Height and Stagger measuring sheet
label | 0b331a31-0bec-5782-bb8d-d899d89c0aef |  | note | Attach Site Photos:
label | 6a27316e-72ff-5f4e-8d32-86351b6bb4df |  | note | Tamping Activity
label | e789aa1a-4816-5296-8539-2d54e3ba7707 |  | note | Overhead measuring Activity
label | d587c77b-d0ca-51d1-8279-a4413f58ca2e |  | note | Structural Offset Measurement
label | 1c5be56a-eae2-5f75-a4b9-7d2acba8b36b |  | note | METHOD: Visual Measure
label | cffba125-31f7-59dd-8997-512750ac3900 |  | note | FREQUENCY: Once
label | b2d17ff4-31f5-539c-a1ec-ac77788878a1 |  | note | CATEGORY: HP
label | 0ecffac4-02f0-518e-a2fb-86ad3c144736 |  | note | RESPONSIBILITY: Tamping Operator
label | 99741c61-7642-573e-99e4-64a5070a1cc8 |  | note | Track Surveyor
label | 843fd8b4-ce0d-5eab-a1b3-4a1428f74320 |  | note | Overhead Engineer
label | e69ee16e-155a-5f3a-a0c9-4c1bfa953780 |  | note | Track Supervisor
label | 470f88b5-e388-5b54-8ded-8e87e5f52e1a |  | note | Site/Project Engineer
label | a1171fa2-82bc-5633-b388-bfa67f6ea7e3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 60249e0e-6a42-55b5-8e72-605cd499daeb |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 Regulating and Ballast Profile
label | 1509c2f9-936e-54b8-8d97-0df83af5f69f |  | note | REFERENCE: Design Drawing MRP-056-C-AUR-DRG-70-LBK-CPW-0011
label | 48ff639e-24cc-5519-ba10-df87ba0c98aa |  | note | L1-CHE-STD-029 Earthworks and Formation Standard Section 13
label | 5b91bbdb-6d50-509c-a2e4-77a5c5a87b60 |  | note | PTC Heavy Rail Track Construction Standards Drawing F598
label | ad0ae1a3-5ce9-5728-a60c-77893e1ec390 |  | note | ACCEPTANCE CRITERIA: Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter
label | 4f07fef3-729e-51af-abc2-21b39451a45b |  | note | No Ballast to be on top surface of sleepers or around rail Fastenings
label | 595cecf2-939e-5329-ace2-4514a170e306 |  | note | Attach Site Photos:
label | e765f295-3513-5dd7-bf42-8fb9c3bedbb3 |  | note | Ballast Shoulder Measurement
label | cb4116c2-f91f-542b-989c-2e0069233bb7 |  | note | Rubber Panels free of ballast materials
label | c7c118c5-151b-5f96-a62c-3c5a7b815f66 |  | note | METHOD: Visual Measure
label | 50913525-5cbf-56ce-9d4c-1f354cb157a8 |  | note | FREQUENCY: Once
label | fabcccbf-815a-5a1d-94dc-7f6829c0f6b4 |  | note | CATEGORY: IP
label | b543bfbd-2b6d-5d03-8288-de7628164ea9 |  | note | RESPONSIBILITY: Regulator Operator, Works Supervisor, Site/Project Engineer
label | 7d6db747-5bf3-571e-b11a-3eec0538c867 |  | note | VERIFYING DOCUMENTS: This ITP
text | ecaade82-a182-5e5a-b2cf-382c473f0b2f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.10 Aluminothermic Welding
label | 05646785-29a3-55dc-a7c7-3507b9c31b51 |  | note | REFERENCE: AS1085.20 Railway Track Material Part 1: Steel Rails
label | a9b72330-ca4a-50b2-88a1-5746946a10ff |  | note | L2-TRK-PRO-014 Welded Track Management Manual
label | d0de6a9a-2a71-5475-8891-81680b33bc57 |  | note | Chapter 11 – Rail Welding Process Section 4.9
label | cc9057c0-ae36-5899-ab2f-fb7885091659 |  | note | L4-TRK-FOR-074(2) New Weld Return Form
label | 544cdaf3-2b84-5292-84e3-6c5d322f595d |  | note | ACCEPTANCE CRITERIA: Alignment inspection shall be carried out on each weld and record results.
label | 7a423981-8768-509a-a007-f5458a6ddc6f |  | note | Horizontal Alignment ± 0.5mm
label | 3ca9a5f0-7d86-5772-a95b-b0a832d472f9 |  | note | Vertical Alignment + 0.5mm, - 0.0mm
label | 1a9f7d2e-1f86-52fd-9cd9-92ced9283de0 |  | note | Verify Aluminothermic welding carried out in accordance with AS1085.20
label | 0ae8458f-3814-5866-b88e-d0f0934c1970 |  | note | MTM New Weld Return Form Welding Section Completed
label | 0ad65fda-88a7-5f5d-bca6-8cc79e510cdf |  | note | Attach
label | 8e40b4c1-accf-5570-b491-77b419836de0 |  | note | New Weld Return Form (Weld Section only complete)
label | 5e348ec5-36cd-58ff-8ad7-73a3db70e1f6 |  | note | Attach Site Photos:
label | df6dfc62-304b-5f1a-ad79-edf0c4ed5b38 |  | note | METHOD: Visual Measure
label | 85bf5137-c911-5890-a8a7-3c8643b9f681 |  | note | FREQUENCY: Each Weld
label | 4cce1dc2-6d67-5e7f-9889-4314cb921d02 |  | note | CATEGORY: IP
label | 3f553937-4d29-53ef-aa9e-5c374f4e485a |  | note | RESPONSIBILITY: Track Welder, Works Supervisor, Site/Project Engineer
label | b1d22140-fb50-56c0-9f8d-48a16f86a92d |  | note | VERIFYING DOCUMENTS: This ITP
text | 29ab9239-b8a9-5266-8208-d3f94751305a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.11 Track Stressing
label | f1b9fcc6-32c9-507e-b0ac-790039bd3fed |  | note | REFERENCE: L2-TRK-PRO-014 Welded Track Management Manual
label | e123fc88-35da-578b-81dd-8132d86af6da |  | note | Chapter 11 – Rail Welding Process
label | bfe9a823-e0c9-5e59-bc4f-b704210c6167 |  | note | L2-TRK-PRO-015(4) Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail
label | 57abf3c2-3583-5c72-a144-d30fa704a86d |  | note | L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan
label | 07cdc8aa-1df1-5861-b5b0-b39b3f91f666 |  | note | ACCEPTANCE CRITERIA: Stressing Rail in line with MTM Chapter 11 – Rail Welding Process
label | 8b29230f-b32b-5723-8ed2-a60e45c729b8 |  | note | Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
label | 1f2c2780-0087-52a7-90a7-c117a44bd123 |  | note | Under Rail Roller Configuration: 1:10
label | e67d837c-b8d5-5994-b437-d53b3f38a694 |  | note | Maximum pull length in one direction not exceeded; 900m
label | 6e10c5a7-b42f-5f28-ba37-bee89f87ecbf |  | note | Reference Marks recorded pre and post tensing of Rail
label | 0f95e744-b1e4-5894-b8f3-e66c576c31ed |  | note | MTM L4-TRK-FOR-130(3) Track Form C Stressing Restoration Plan Completed. Validation that SFT 38 degrees is achieved
label | 38c8648f-8cd5-5089-a6f5-493346bd565c |  | note | MTM New Weld Return Form Welding Section Completed
label | 1e92f97e-5f57-538e-8414-b1c9aa9ecccd |  | note | Attach:
label | 795e6a3e-edda-538b-a58f-3ac10380e298 |  | note | New Weld Return Form (Weld Section only complete)
label | 9bbacb09-7d63-51e2-ac33-21c67d71443c |  | note | Stressing Restoration Plan (Fully Complete)
label | 52aa9bab-09b7-5867-a846-201f3b8f18af |  | note | Attach Site Photos:
label | 5d43fbd2-b57c-58b3-926b-e5c3570d6042 |  | note | Stressing Activity
label | 23e718ee-ac70-54c4-b7de-9251eaa7d113 |  | note | Under Rail Roller Spacing
label | 513e5936-da50-56ef-8a81-f83ded930f0c |  | note | Before/After Reference Mark Measurements
label | 29abb954-c11d-540e-8190-3bce7b0e8dc2 |  | note | METHOD: Visual Measure
label | c8e9fe82-0da0-5bf6-bd0c-91518a8676af |  | note | FREQUENCY: Each Restress module
label | fc7d2696-41e8-5116-a97e-af63ec56ea86 |  | note | CATEGORY: IP
label | 04d00318-c7e3-56b8-8d5a-82ec14670b63 |  | note | RESPONSIBILITY: Track Welder, Works Supervisor, Site/Project Engineer
label | 949bc7bc-ed24-58bf-852d-604eb3119d2d |  | note | VERIFYING DOCUMENTS: This ITP
text | 6549dce7-d920-5a87-8608-c6ba85f71d34 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.12 Weld Ultrasonic Testing
label | 210d7a17-2ee8-5d1a-9b12-c87f865a3472 |  | note | REFERENCE: MTPR 031000-01(3) L2-TRK-PRO-049(3) Non-Destructive Hand Testing of Rail
label | 9b876563-d96e-5ed8-9548-e38b1cb30622 |  | note | AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
label | 4eadb14b-5702-5b11-b806-9288fcf16601 |  | note | L2-TRK-PRO-014 Welded Track Management Manual Chapter 11 – Rail Welding Process Section 7
label | 81236436-26b7-5968-b0d9-2707b224a9a8 |  | note | ACCEPTANCE CRITERIA: Ultrasonic testing to be carried out within 14 days and in accordance with MTPR 031000-01(3) L2-TRK-PRO-049(3) Non-Destructive Hand Testing of Rail
label | cfd0d7af-d064-5e98-9397-cdbb5c5bb7c4 |  | note | The cross section of the area of the head and web shall be completely scanned;
label | d21099c0-1e19-5fdd-94c2-2dee0361f006 |  | note | The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
label | 603a68d5-fc17-503b-b4e3-4f74e3215423 |  | note | Welds shall be scanned to both directions.
label | b85a7293-5505-52aa-b113-e7004361bded |  | note | No classified internal defects found
label | bc6379a5-1bfd-54c0-b8ac-a16ea7071761 |  | note | Geometry of rail head does not exceed 1mm peak 0mm for dip
label | d1f3da56-2256-5512-92fe-682cef06ef13 |  | note | MTM New Weld Return Form Testing Section Completed
label | 495fdf96-834d-5bfd-8b73-0bedd51828b9 |  | note | Attach:
label | b1b52019-bb17-5ee6-a827-644cebe5aa92 |  | note | New Weld Return Form (Fully Completed)
label | 521a22fb-1b11-5be4-9a68-f7c4d167da66 |  | note | Attach Site Photos:
label | 291df0d8-cc2f-502a-85f8-dd89809bc3d7 |  | note | Welding Aligning
label | 88f7b4c0-8bf0-5845-9113-652e7eec6eba |  | note | Welding Process
label | 98da9298-ae77-5de6-86fe-875844fe9d10 |  | note | METHOD: Visual, Measure, Test
label | 5a0a7aa6-5490-5184-be45-fb669eec6c78 |  | note | FREQUENCY: Each Weld
label | df286567-7733-5b17-af0f-39d945a2d15a |  | note | CATEGORY: HP
label | 1b5bda94-4db7-557c-9404-4501c5aef4f4 |  | note | RESPONSIBILITY: Weld Tester, Site/Project Engineer
label | 009e6a11-d958-5573-bfd9-dd509ceeb540 |  | note | VERIFYING DOCUMENTS: This ITP
text | d3544acb-1cd0-5402-b45f-40f8b9ba95bb |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 As-built Survey
label | 239ca6a0-445c-52c1-9529-6f4ad7c401d1 |  | note | REFERENCE: As Built Drawings
label | 33315f26-b0c9-55e8-b658-fd88d035f50c |  | note | Asset Change form
label | 6ec4f07f-b629-59ac-943a-a339ae72aa54 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | 191a84f1-79c7-5cfa-90cc-a6e28679f80c |  | note | Attach:
label | 53a75d42-4107-52a6-864c-a4dc82e2cb44 |  | note | Survey Report
label | 87eb216c-6f35-5094-96ae-37fc5e56238b |  | note | Engineering Asset From
label | 47ad9756-f887-53da-aa48-46a517113373 |  | note | METHOD: Survey Document Review
label | 2a09abeb-451a-50d2-a000-46eb419fcec4 |  | note | FREQUENCY: Once
label | 70243d34-3986-55cf-8965-65364d324899 |  | note | CATEGORY: IP
label | f277f132-0573-5307-9afa-f4b7d25916fb |  | note | RESPONSIBILITY: Track Surveyor Site/Project Engineer
label | 7c7724af-b0ed-5fc7-9d37-fdb55a4e8ef9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2d747116-c47b-52d9-be79-07abe7171741 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Track Certification
label | b204255a-6c16-50f9-80a2-612d17b837b5 |  | note | REFERENCE: MTMF020000-1 – Track Form A T
label | 36887c9a-ecab-5a5d-95ea-9cdc11b77254 |  | note | MTMF020000-2 – Track Form B
label | 2020d412-c545-5cd0-a9e9-b8def84d62dd |  | note | ACCEPTANCE CRITERIA: Attach:
label | 863aa03c-aa6c-5af7-a08c-4915ce98d89b |  | note | Track Geometry Conformance Certificate
label | 3f437f98-6c58-53a1-9385-dc03364e9023 |  | note | Track System and Component
label | cda704a2-050c-5aae-ad29-eea522032419 |  | note | Attach Site Photos:
label | 2486d522-d963-52fe-8905-7b8660dce53a |  | note | Before/After Photo of worksite
label | 823f4780-0b64-5054-b9f5-b50cf3790117 |  | note | METHOD: Visual Measure Document Review
label | 3338e7b1-e5c1-548d-a789-10ea644f9964 |  | note | FREQUENCY: Once when all occupation works complete
label | e66841d3-b7b2-5fe5-a530-13c449cbe71a |  | note | CATEGORY: HP
label | ba604a01-3c60-5502-80eb-5e672e1d611c |  | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | 476a4866-36a3-5ac4-8df9-def905ca9b0e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b395cc8a-e9b2-5736-b792-3662f1714518 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | e2d42f3d-98f4-5bed-9482-669b518e8562 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0eee8ac4-d7e9-5dfa-96bc-9dde2e179819 |  | textbox | Name:
text | 59ccf6c1-38a7-53a3-9052-8fb9de4c3309 |  | textbox | Position:
text | ecbe9a4a-390f-58c0-a48a-98da6d928785 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-RAIL-Supply & Cable Installation (Signal) Rev 0 | itp |  |  |  | Yes | ITP-RAIL-Supply & Cable Installation (Signal) Rev 0 | d43c299c-fb1c-49e2-b7f7-88b8099057a2
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 15e1cd42-85ba-4b1a-9762-ea24cb5bbf72 |  | note | Document Title: Inspection Test Record – Supply & Cable Installation(Signal)
label | 763916b0-ce3e-4e91-92b6-e87026ae595c |  | note | ITP Description: ITP Checklist -Supply & Cable Installation(Signal)
label | f80ccbc7-10ad-4e4f-8b0d-971fbc579dd5 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 8baf71f9-5c3c-4953-9201-6f448d185ceb |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 5a41bc43-8d23-409f-b610-bb4721a68c1b |  | note | Revision Number: 0
label | 24b438dd-58e6-45b3-a085-bcf8388b9aed |  | note | Revision Date: 13/07/2020
label | b5bd0b76-9317-4874-bcb5-061adeca559a |  | note | ITP created by: T.Zhang
label | ae777232-cba3-4318-bd61-ddd140d84bb1 |  | note | ITP approved for use by: Romualdo Magpantay
label | 4d0e85a7-8275-459e-bfa6-a5549c07524d |  | note | 1.1 LE-CHE-STD-070
label | ddc6d491-ffef-41ca-b582-e8c94644f720 |  | note | 1.2 LE-CHE-STD-070/VRIOGS 012.2
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain and submit Material Certificate of Compliance for Cable Drum
label | 26ef1a63-2c73-4174-9813-6add99ea7b87 |  | note | REFERENCE: IFC Drawing
label | c2f02668-5c80-484d-adb9-226e32dabf96 |  | note | Supplier Specification
label | c94523a5-f68d-4e20-b568-a5e01da7e463 |  | note | AS
label | 8b48132f-3a26-4679-b98d-d0de28dadd3d |  | note | ---------------------------------
label | 5bb3b19e-341d-4a7d-bf7b-8758df8f25c3 |  | note | ACCEPTANCE CRITERIA: No damage to Cable, Cable has undergone pre tested and has been identified with a cable drum Number
label | effc3b9c-e3fb-4d55-aa7c-ed2aea5b7162 |  | note | ---------------------------------
label | 79d2acee-691c-4f70-ac03-2b2d20e66711 |  | note | METHOD: Visual
label | 307a792a-d99d-4c72-9200-d6daafeca733 |  | note | ---------------------------------
label | 9000c0d7-efe4-4878-b21e-92aceec36fbb |  | note | FREQUENCY: Once
label | a2bc2042-21b1-419c-8460-8645e140601d |  | note | ---------------------------------
label | 49881df5-8764-4250-8fcd-474ebfa2c7ba |  | note | CATEGORY: HP
label | f53ac410-779e-4caa-b0d5-2d2464e11aaf |  | note | ---------------------------------
label | 7bb29f20-83ad-42a8-b74d-c51c560d100f |  | note | RESPONSIBILITY: Nominated Authority Eelctricians Site /Project Engineer
label | 6d3e17b6-0dc9-433d-95b4-5f22ae26b8b1 |  | note | ---------------------------------
label | 3d541436-e5d1-4a4d-ad9d-348afd2d4a4d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 63d06e94-a777-4585-8d70-226c0ff24aef |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Acceptance & Testing of Cable Drum
label | b39a7715-ec5d-43c1-beac-5239d3eeb0d4 |  | note | REFERENCE: IFC Drawing
label | d41f95f5-9c58-4170-807a-960e723df47b |  | note | Supplier Specification
label | bd275b77-b9f4-420e-b023-135616cb7461 |  | note | AS
label | 32621ade-747a-49bd-93a7-09c02973ab86 |  | note | ---------------------------------
label | 188b384f-ec86-4d20-b4f9-653364b29be0 |  | note | ACCEPTANCE CRITERIA: Megger test the cable drums to ensure, there are no damages to the cable
label | e353e357-05fe-47ff-a99c-19653b7130ca |  | note | ---------------------------------
label | ea335521-c235-4805-8119-7a8197987037 |  | note | METHOD: Testing
label | e96855c3-9f24-4b12-9524-712a60c2ec9a |  | note | ---------------------------------
label | 506939c7-a2ed-4376-8561-f940d7cd6721 |  | note | FREQUENCY: Once
label | 7255b84b-efa9-4928-bd65-77510475eb85 |  | note | ---------------------------------
label | 2a9eef2a-8c4b-45a9-974f-850fb08b14a8 |  | note | CATEGORY: IP
label | 72da6562-217d-4e20-86a8-9708546fbe31 |  | note | ---------------------------------
label | d54f64b3-8bc2-495c-8972-283d61af81c5 |  | note | RESPONSIBILITY: Electricians Site /Project Engineer
label | 48aac82c-545d-431a-b8cd-ed58107a4183 |  | note | ---------------------------------
label | 09ca56f8-de47-4aa7-8563-bcdb42c7961f |  | note | VERIFYING DOCUMENTS: This ITP
text | 0b6401e3-f4ac-4eb3-819a-2d0223ca7795 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Acceptance & Testing of installed CSR conduits
label | 7e70f008-820f-4180-aca2-eb10b423a8ba |  | note | REFERENCE: IFC Drawing
label | 8d3000fb-dbd3-45de-883a-498e0304c924 |  | note | Supplier Specification
label | b42e852f-b0eb-4d09-9108-889fdf9495a8 |  | note | AS
label | 7da8b1e0-3b22-4d77-aa28-223e192abbad |  | note | ---------------------------------
label | 5e6fabaf-e2f2-468f-8661-75dd0bb492b2 |  | note | ACCEPTANCE CRITERIA: Cleaning and Mandrel testing Complete
label | 699b7fe2-8420-4081-befd-ad25b73d4651 |  | note | ---------------------------------
label | fd46c5bb-eadc-4caa-831f-6103de28b573 |  | note | METHOD: Visual
label | 70e732c7-8921-47e7-9523-8e1f08026fe1 |  | note | ---------------------------------
label | 53e339b4-25ea-421f-82c8-41d14f099604 |  | note | FREQUENCY: Once
label | 8f9308eb-e6f5-4b13-b7d0-01bee05f744f |  | note | ---------------------------------
label | 93265d84-ca0a-4298-8f01-d8559cc511e3 |  | note | CATEGORY: IP
label | ed0a5233-0f78-44dd-b7dd-27cba67cbb3f |  | note | ---------------------------------
label | b15a53cd-6981-4aba-b67c-1bb387efd3e8 |  | note | RESPONSIBILITY: Electricians Site /Project Engineer
label | af97a921-7cf4-499c-baf7-007acad76931 |  | note | ---------------------------------
label | 35cd1b98-cbf6-4ff2-a2ac-ffb256884f7f |  | note | VERIFYING DOCUMENTS: This ITP
text | 33fe4ab5-e877-4cf1-ab6a-748fb3907e76 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Hauling of Cable
label | 3f5e140b-54f3-43f2-b0a4-fcd936e2bc2e |  | note | REFERENCE: IFC drawing cable running plan
label | 5f81043b-26c0-4f48-b84b-734f55b8aa7b |  | note | ---------------------------------
label | 9883671b-0b69-4f99-9816-4025a660bb13 |  | note | ACCEPTANCE CRITERIA: Confirm the correct number of cable being install is correct to Cable running Plan
label | 96fdeafa-1cd8-448b-b0d9-44dcbcfa9b68 |  | note | ---------------------------------
label | 29f8cc1e-8201-443f-8532-83c63e380070 |  | note | METHOD: Inspection
label | c1663ba5-42bb-4add-81f5-dfcf434e963f |  | note | ---------------------------------
label | 98509f59-17db-47fb-b0c3-cbb1da7c0a2d |  | note | FREQUENCY: Once
label | 80bd4a73-ebec-431b-9ad4-3457e954eda4 |  | note | ---------------------------------
label | 54cce035-247b-4d3f-9a52-c6b8eb657942 |  | note | CATEGORY: IP
label | a2430a66-9bac-40f1-8647-f2dfedb850fa |  | note | ---------------------------------
label | 5a68f108-a338-4b36-8bd1-b1e09d687f33 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | 2cdd26dc-e374-4340-9362-9128175f6df6 |  | note | ---------------------------------
label | 6affcf79-c3b9-4719-8a3d-2e8a30152023 |  | note | VERIFYING DOCUMENTS: This ITP
text | 691443e5-5f8b-46b6-82cb-0b42f4644601 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Laying & positioning of cable
label | 99869d4a-760d-470d-8bb1-1585701e009f |  | note | REFERENCE: IFC drawing cable running plan
label | 167e98d2-bd06-4039-ad17-ee8a5d6dddb5 |  | note | ---------------------------------
label | 3935afbc-ac63-476a-bbb7-a005b81e0d78 |  | note | ACCEPTANCE CRITERIA: Correct cable installed as per IFC cable running Plans
label | d19eee6d-8b4d-4217-b917-e3e3424b7dfd |  | note | Supervisor to confirm the correct cable is being installed
label | 17fd9a1e-71b6-4949-a538-298e17c9aee7 |  | note | Confirm the correct number of cable being install is correct to Cable running Plan
label | 685ed11c-b240-47e6-973e-489db6e7c775 |  | note | ---------------------------------
label | c00c3de8-f866-45b7-ba76-a4bd7a181194 |  | note | METHOD: Inspection
label | ac34c241-a84a-4cf3-bc47-b6c3eb349201 |  | note | ---------------------------------
label | 37eddb87-5e9e-4b59-a574-8a38f15ef0fb |  | note | FREQUENCY: Once
label | 9e53a27e-ead0-4e10-aaae-c5e80099495f |  | note | ---------------------------------
label | 8d6c309a-688b-42f3-a9ba-a86e80b4e378 |  | note | CATEGORY: IP
label | 8c21f4bf-38c6-458f-a382-1e16091cdbc2 |  | note | ---------------------------------
label | ba725afa-27db-46d1-9ec9-87bd0189b497 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | 789d15c2-34c5-4252-9c82-0a6baf7335a8 |  | note | ---------------------------------
label | c3c05c56-5822-4d78-83ed-44559a632017 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8f7e9030-98a7-4a43-b9b4-fde3d724aa94 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Installation of cable to final position
label | 54f6e0ad-a686-4714-93a6-aca7712e170b |  | note | REFERENCE: IFC drawing cable running plan
label | 9f9cfbb2-f8b3-4eb8-9c1d-e8d94499cc1e |  | note | ---------------------------------
label | 8a232245-f4c0-40bc-bc32-bf0b7875d183 |  | note | ACCEPTANCE CRITERIA: Do not exceed minimum bending radius
label | 09f719ad-8da6-4cb4-b043-db0e93b589b5 |  | note | Loops in Pit at ends and change of direction
label | c903579f-de4e-4222-a685-14eb16dea36c |  | note | If cables not in final position and terminated ends to be sealed with amalgamating tape
label | ece161ab-268c-497a-beea-0a497233a1c6 |  | note | Cable to be extend a minimum of 5 meters beyond future termination point
label | 8675b480-e92f-4ec7-8ba7-95f9a5629474 |  | note | ---------------------------------
label | 5bf844ec-1683-4fd5-b931-8139aecc079d |  | note | METHOD: Inspection
label | 9e9317db-ac55-45b8-b206-8ec27a8fe0f9 |  | note | ---------------------------------
label | 16949997-9170-43f8-b972-25edbf9d6e6b |  | note | FREQUENCY: Once
label | 34454383-9dee-4f83-a3d6-ca20f78431f2 |  | note | ---------------------------------
label | 5c5a7bbe-56a4-416a-95f7-9033ec9aed73 |  | note | CATEGORY: IP
label | 825053ed-246d-47ef-986a-86b3a80458b8 |  | note | ---------------------------------
label | 4732e68c-9e11-49b5-9366-9c74b868467e |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | 850e72a9-3c89-485c-88a9-2c1c8fd709ba |  | note | ---------------------------------
label | 40c2c6c0-f424-4ff2-8ed6-e255f907747f |  | note | VERIFYING DOCUMENTS: This ITP
text | 48632177-04ee-4e2a-a22d-add9bde4970d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Jointing of Cable joints in the pit/handhole
label | cee95fac-1eb5-44e0-92f1-9fbb63225e38 |  | note | REFERENCE: IFC drawing cable running plan
label | d7dd29d1-e9b1-43df-a63c-5206b5675901 |  | note | ---------------------------------
label | 72b096f5-3305-4911-9a55-d82b0c2013d2 |  | note | ACCEPTANCE CRITERIA: Chainage to be recorded on checklist
label | 8b861b6c-2d99-4d61-a4b1-d53dea44e0a3 |  | note | Joint to be done as per the joining kit instructions
label | 54ad0904-4511-42df-9281-565cf7d5be78 |  | note | ---------------------------------
label | e285b034-e727-4424-9e01-fc3836a0b1d2 |  | note | METHOD: Inspection
label | 85f6bfe1-56be-46d5-a36b-b239707f3a88 |  | note | ---------------------------------
label | 22012871-79e2-4550-b704-014e637639d0 |  | note | FREQUENCY: Once
label | 4c020a52-cb93-4753-86b1-7f6570edb071 |  | note | ---------------------------------
label | efb76d49-a38b-409f-bfb2-e4cfa82d7858 |  | note | CATEGORY: IP
label | b1bcc9db-aa8a-4d55-851f-4fa4896f4a2a |  | note | ---------------------------------
label | 0c54bf47-b540-449f-a288-a4ac97df0ac6 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | 2df80f45-77e3-434d-87d7-58aa64e851ae |  | note | ---------------------------------
label | 68e83d1e-74db-4845-8a0a-9b8c16687932 |  | note | VERIFYING DOCUMENTS: This ITP
text | b821ee29-86dd-498e-9af3-08ccde94c5b6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 As-built Site Walk (if required)
label | 7ef987ea-0a8c-49ef-94db-ba7f25bc0116 |  | note | REFERENCE: As Built Drawings
label | 4b1179c8-41a0-4fd9-82f2-e19f177aef0c |  | note | Asset Change form
label | 92afe0d6-07f8-4a49-aee5-3e712c82fb88 |  | note | ---------------------------------
label | 11540d87-8319-4cc7-8278-d4841f6be0d4 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction Method
label | ffab11cb-5130-40b1-9d37-cccfc0af493b |  | note | Attach: Surevy Report, Engineering Asset From
label | 76693d77-ee2d-4eb0-b9c3-1c74088fc28d |  | note | ---------------------------------
label | 428e9ea5-c552-4da0-b71e-6962cbf21275 |  | note | METHOD: Survey Document Review
label | fb6c1b29-b271-4778-a58c-1e0965868d86 |  | note | ---------------------------------
label | 6d8f57ad-673d-4306-90db-0befb9e8d9b0 |  | note | FREQUENCY: Per lot
label | 246e3a6a-c589-4297-9c3b-ca2271c6dae4 |  | note | ---------------------------------
label | c440f63d-76f3-46b2-b301-c63475c74a73 |  | note | CATEGORY: IP
label | 09a671fa-cb6a-45ea-991d-fcc3043f5d3a |  | note | ---------------------------------
label | bf1b7163-27e6-43ef-84aa-a2b5fe60a7a8 |  | note | RESPONSIBILITY: Supervisor /PE/SPE
label | fd9ffea3-9783-43f0-b0ed-9f62f174b216 |  | note | ---------------------------------
label | d0dac3dd-42f9-4431-aef9-857d06792359 |  | note | VERIFYING DOCUMENTS: This ITP
text | 30bc19b9-a2f5-4e1d-a8e1-ebe1d64ba87b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | f5da221b-2160-4986-bf1d-7b4218e9142a |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | a62be1a3-48bc-47cc-962f-9ae16dccd539 |  | textbox | Name:
text | 7aacf086-02f3-434d-98a1-5dfe1ce124eb |  | textbox | Position:
text | 42456ace-81aa-44a4-9c0f-0c3753bc4390 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Structural Steel Posts & Screens (Supply & Installation) Rev 2 | itp |  |  |  | Yes | ITP-STR-Structural Steel Posts & Screens (Supply & Installation) Rev 2 | d56f8668-327c-4d48-9c4e-53d548957ec4
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | bb4097ea-2cb1-4f83-ac89-5bee0c07acd3 |  | note | Document Title: ITP-STR-Structural Steel Posts & Screens (Supply & Installation)
label | 756079e5-d786-4723-9baf-078e5798c117 |  | note | ITP Description: Structural Steel Posts & Screens (Supply & Installation)
label | f68ea9e5-70b7-41bb-a66e-a11119c44975 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | c02e7950-0752-4ed7-96b5-345c091ee1fa |  | note | Revision Number: 2
label | 95c99d0c-6e4c-4cdf-a3f2-06a095fc3521 |  | note | Revision Date: 4/05/21
label | 0a79d60a-8151-4325-acc9-1022cff2eb79 |  | note | ITP created by: Mike Freeman
label | 9f1b7248-c493-4706-a565-b46695fde042 |  | note | 1.1 VicRoads Section 610 November 2018
label | a46f5f67-dab1-4b55-a9bd-7b9455800e3f |  | note | 1.2 VicRoads Section 610 March 2019
label | 6e24c483-f6c0-4b4f-a5ff-5f86b6ef5bcc |  | note | 1.3 VicRoads Section 610 June 2019
label | a7fbd5b6-91f1-4e31-915c-caa1ff94e7e8 |  | note | 1.4 VicRoads Section 630 October 2013
label | cec09a61-63b0-4cf8-9899-226d5f1a62e8 |  | note | 1.5 VicRoads Section 631 February 2009
label | a20f00f1-757c-4ae3-958f-0baa08f6b6f0 |  | note | 1.6 AS4100-1998
label | f693c218-c2dd-460d-af27-a4305bc055f5 |  | note | 1.7 AS5131-2016
label | 6c3724f3-0d09-4079-a82b-d25e15029485 |  | note | 1.8 AS4680-2006
label | a914761c-d45a-45e5-9ae9-63bb261099b5 |  | note | 1.9 AS2312.1-2014
label | 811f4d00-2b3f-4ccc-9236-8905b7d7f254 |  | note | 1.10 AS4506-2005
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 1672f1e5-95a1-45f3-b17e-f117a4a0ca41 |  | note | REFERENCE: IFC Drawings
label | f146bce4-e715-42de-b3ef-f753fca214a5 |  | note | MRPA Quality Management Plan
label | 5f94b32d-06e6-4878-bceb-3c6589e80aab |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | d7fcad22-2252-457e-bc1f-5d4667933d5a |  | note | Typically this consists of but is not limited to:
label | 9c4ab67d-cfbc-451a-881a-66ac6858ee4d |  | note | i. Certificate of Compliance
label | 0863675d-ae65-4cef-bff4-d4aae5ad4c6f |  | note | ii. Completed ITP
label | 7adef496-97e7-43ef-abe8-4f69e6b178f7 |  | note | iii. Weld Procedure Specifications
label | 93b01f4d-218e-4392-abbe-63b16e513afc |  | note | iv. Weld Procedure Qualifications
label | b4230ecc-ef9d-4253-bc97-4689ff370f14 |  | note | v. Welder Qualifications
label | 343363b3-c881-4710-9d49-1c97f8ed6282 |  | note | vi. Material Certificates and traceability
label | 61071fa8-4981-4e03-9676-a4cba5086aba |  | note | vii. Quality Assurance check sheets
label | 7a375703-4911-4542-a009-d73bdf1e62f7 |  | note | viii. Welding Consumable batch certificates
label | 3e73b3fb-c1c4-43d6-86de-f67357411178 |  | note | ix. Coating certificate(s)
label | 45792b38-a808-4619-be9f-4f1ee8759522 |  | note | x. Non-destructive Testing (NDT) Reports
label | c4998c9d-9b05-4868-b708-f0a564d3731b |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | 7c74064d-c1fe-4002-897b-831fc5443f5d |  | note | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | e79ac34a-112b-45fa-b395-090b3003ae13 |  | note | METHOD: Document Review
label | f081436d-b90d-4fe0-9bff-aa71359f9495 |  | note | FREQUENCY: Each component
label | 94322b50-15be-44c8-abf2-229ded5be1d1 |  | note | CATEGORY: IP
label | 11999c15-d8b0-4eb8-9ed0-c0dd05b60b0d |  | note | RESPONSIBILITY: PE/SE/SPE
label | 83722d90-13b8-46dd-adee-d24e72cca6fd |  | note | VERIFYING DOCUMENTS: This ITP
text | c05ca299-cd25-4e0e-b414-605cac3aff96 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | 800739c7-8505-4c22-b5e4-66f6a6532938 |  | note | REFERENCE: IFC Drawings
label | 1622c23f-8248-4467-85af-a6e3a38144b1 |  | note | 610.33
label | be98f0e0-3215-4941-8548-7128a408938c |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 9a20ae19-7794-41db-941b-47a07d80064f |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | 4efaec96-f831-4be9-84fe-4d3d5173eb5d |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | bd4c9987-6efa-4603-994b-f78a3783b878 |  | note | iii. have a flowable consistency
label | f64876f1-92a0-4b51-a5da-a8faf004bf71 |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | 41e585e1-7f93-46ad-89ce-6d1c04b143bc |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
text | d92e8546-7831-4d47-952c-9124e8c43e17 |  | textbox | Enter: Teambinder Material Approval number
label | acc2531b-f22d-4b7a-ac92-7d3d097e1198 |  | note | METHOD: Document Review
label | 24b45667-decc-42b8-8a18-56e41e55ea01 |  | note | FREQUENCY: Once, for each product, prior to placement of product
label | ec230b39-e7fc-4e96-af80-b24eb1eb917c |  | note | CATEGORY: IP
label | ed5297b5-6d24-4adc-9e0d-ff83b9ffaa8a |  | note | RESPONSIBILITY: Nominated Authority
label | f0018154-4aaa-4a8f-bc19-e8d6071d5c84 |  | note | VERIFYING DOCUMENTS: This ITP
text | e70e188f-7cb1-43f0-a8cf-b3720d2ae12e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Base Plate Structural Grout or Mortar
label | 0b24e46a-3464-4091-b3ae-4ed9a83b30b5 |  | note | REFERENCE: 610.23 (d)
label | 328e7b46-124a-4cc9-82a0-771dc6926eb3 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 644ce439-165b-43d7-ae4e-4456027d518a |  | note | Note: This may be the same product used for the concrete curing
text | 0a146950-359b-4ac7-bd09-a15f359a52e1 |  | textbox | Enter: Teambinder Material Approval number
label | 9386da2a-713b-41fa-807f-ebfa1889d28c |  | note | METHOD: Document Review
label | 639aff42-0c21-4c83-beaa-9b7bd27e9c38 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | 19639b2e-c725-4882-8add-94963dde3b84 |  | note | CATEGORY: IP
label | 59d67a58-35ee-4e93-9ff7-ef2fc971ed40 |  | note | RESPONSIBILITY: Nominated Authority
label | 40176d5a-f81f-47f8-bc52-2ee897af4592 |  | note | VERIFYING DOCUMENTS: This ITP
text | 29891c0f-4c6b-4752-8e77-7d586be5434c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Curing Methodology (for Grout and Mortar)
label | 4824af60-4718-4816-9de9-9d58a11a0279 |  | note | REFERENCE: 610.23 (a)
label | deb62aca-1864-4af5-970c-008cd3ee755e |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 2a577662-5aaf-495e-b200-233b35d984c1 |  | note | Note: This may be the same document used for the concrete curing.
text | d56a4aa2-95b4-4efd-8125-31e5ed5e13a7 |  | textbox | Enter: Teambinder Approval number
label | 26b3199a-747a-4b51-931f-209fac25dc84 |  | note | METHOD: Document Review
label | f2af46db-8fcc-46d2-bb59-5375e54aa6a1 |  | note | FREQUENCY: Where applicable, once, 4 weeks prior to placement of product
label | 7e2c7050-dba4-4e04-bdeb-70bf5c58f176 |  | note | CATEGORY: HP
label | b2ae6cde-1cdd-45f0-a196-8dcea567872b |  | note | RESPONSIBILITY: Nominated Authority
label | 2471093e-cacc-485f-a73c-4cfd602ffda2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | dd46f5d7-2e63-4bd3-9c5f-2648f5da6ff9 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | d9e53300-42c4-4ff4-a3d6-f012b04edcd9 |  | note | REFERENCE: MRPA Quality Management Plan
label | 0c69a4a5-c1ae-4dba-b2df-12b904152f5a |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b4e888bf-b771-478a-8c8a-b9f454d0cb8b |  | note | METHOD: Document Review
label | 23ccb97f-cb36-415c-b9d3-cc8176ac6da0 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | b2eb69da-6638-471f-92b6-526b69c73efc |  | note | CATEGORY: HP*
label | ea785b5a-b03c-425a-8421-a7188560150b |  | note | RESPONSIBILITY: All
label | 5aa7bbd9-164d-469c-a393-bd9a74ff17b5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 52fb1ee7-9451-4045-9774-ebf5699ad9b4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection Checklist
label | c24dc098-46a6-4aa7-9587-c0fc3042e36e |  | note | REFERENCE: IFC Drawings
label | 82cdb75f-7f11-42e5-9cea-abbf56baec77 |  | note | 630.08
label | 8c93d5f7-316c-4ed6-b309-de6a1e0e24ce |  | note | 630.09
label | 16c5e450-f1d7-46ec-b6e2-1304adab5241 |  | note | 630.20 (a)
label | dc68a1c3-d06d-4098-a1d6-47f74cac6f99 |  | note | 631.06
label | 9e77baa2-548e-4c30-8827-05258b2fcf6c |  | note | AS4860 Clause 7
label | a49f9bce-06a2-4693-b2b0-301de52064f0 |  | note | 631.11 (a)
label | def1df43-8ffd-49fa-97d8-456512ed35f0 |  | note | AS2312 Clause 9.6.4 (i)
label | 9597abbb-0c82-4cf7-a3a1-11c168b04f46 |  | note | AS4506 Clause 2.3
label | e73d71d4-a161-4019-a568-8a39b0f3f07b |  | note | MRPA Quality Management Plan
label | 384271b4-d65d-483e-90df-d3b2ef92bc04 |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | bf504bf6-a12f-4c53-9629-9711e119489b |  | note | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | 4a77ca20-50cf-4ffc-857f-c38bf88b1992 |  | note | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | b6714980-944c-493a-8ae4-8a4b4784424c |  | note | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | 230fbbe8-40f6-4fd9-8070-5db335fe6417 |  | note | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | 2c1d5ce8-d121-475e-ba37-5f23e927917e |  | note | Complete: Materials Inspection Checklist in ConQA
label | ebde7eed-e96e-48d2-a300-ffdf76459b1a |  | note | METHOD: Measure , Visual
label | cdf5cbe4-80e7-43ee-a2b8-ef8e2c66423a |  | note | FREQUENCY: Each component
label | 801e2559-8603-4a53-a794-dbcdb42e9e9b |  | note | CATEGORY: IP
label | 77034ed6-fd46-4b00-8979-d6137fc43563 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 41d2b49b-5d7b-4bdd-b4b2-f083bb0f71f4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 91d3ddf7-2dce-4a8c-bb34-5d1a9f1d0802 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | f630eafa-9a35-405c-8e8e-575fc40c404e |  | note | REFERENCE: IFC Drawings
label | 1c951e10-6cf2-4054-aef7-e63bc225cb5d |  | note | Product TDS
label | 96b77534-7120-48b9-a054-839d1cdc4336 |  | note | ACCEPTANCE CRITERIA: Prepare the bearing surface in accordance with the Grout/Mortar Product TDS.
label | 127720dc-28f2-475b-97db-232a6d1ed234 |  | note | As a minimum, ensuring that it is clean and free from loose particles and laitance.
label | 88346354-bf86-4d73-8921-9c3080b34a7a |  | note | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
label | 8d04e995-ba6f-49d7-b91f-70375fc6493c |  | note | METHOD: Measure , Visual
label | 8d69d680-5a4c-4fbe-8c9b-8bfe2eb73639 |  | note | FREQUENCY: Each post location
label | a27ed554-f825-4483-af4c-f4c2212af547 |  | note | CATEGORY: IP
label | 3316fe84-d6d7-4d3c-8f2f-31da32833543 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 56aac7d8-a535-4b94-aa53-924b2bb12942 |  | note | VERIFYING DOCUMENTS: This ITP
text | e4d49ce0-2b4b-4ef8-a4ab-3fbb996fab2b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | 3e3b7ddf-706c-493e-a80b-7ae2945cec1b |  | note | REFERENCE: 630.09
label | 52de7b2e-ef10-4117-b61d-ec8443676da8 |  | note | 631.14
label | f333ae28-aa8e-42f0-ae39-4fb9eb39fd0e |  | note | AS4100 Clause 15.2.2 & 3
label | 1d055495-3578-4835-9494-295a84a74500 |  | note | AS5131 Clause 11.5.6
label | dfbf3047-68e3-4498-86b2-6a2e694493f5 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 1ebffe96-d05c-48ce-8e16-483aa684f0d3 |  | note | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | f6a65ab5-084f-4625-87dc-5880603e73ee |  | note | METHOD: Visual
label | 95dadbd6-dc6c-4388-b3ec-eb14b3292ee7 |  | note | FREQUENCY: Each component
label | f4c9c198-773e-4fc0-8ee8-a97f2eb815ab |  | note | CATEGORY: IP
label | 9c1bf365-6f71-436f-aef0-de3f174d07e8 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 889b2503-a8c3-49e6-8934-e8ff4484e330 |  | note | VERIFYING DOCUMENTS: This ITP
text | da2ad7f9-9473-4487-814e-272a9eaeb4b4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | 5802bffd-16c5-42f8-a4e9-bd5d52cbe55c |  | note | REFERENCE: AS4100 Clause 15.2.3
label | c947c50a-93b0-475b-baa9-a20acc64caa7 |  | note | AS5131 Clause 11.5.7
label | ef8398e3-8476-4987-b02c-5963c846e91a |  | note | 630.12
label | dcffa110-7e9d-4551-aba2-b8df84ddf3a3 |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | 5205e140-138b-4b77-beef-2efe33df6f82 |  | note | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | 37ec64b7-decc-42a1-ac98-79bf2957bee4 |  | note | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | 35561209-e919-4d18-965b-dbc40fb59478 |  | note | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only rheaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | c35fd37c-8e4d-408f-8d05-a5ff6b7c2f1d |  | note | Holes shall not exceed the greater of:
label | 5da1173c-e050-4fbc-9cfa-e8555150dab2 |  | note | 1.25 x bolt dia. OR bolt dia. + 8mm
label | 845190a1-7d53-459d-9428-d9c5526ce272 |  | note | Slots shall not exceed the greater of:
label | 15f2ac21-ca48-4240-a611-937b856f979c |  | note | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 41fc4355-6435-44e7-aa0a-5e8441637bfa |  | note | METHOD: Measure , Visual
label | 100320bb-1eb7-457e-968e-f21241b19ad5 |  | note | FREQUENCY: Each component
label | b118b2e6-b85b-4dab-91c0-e2d1f489608f |  | note | CATEGORY: IP
label | 73650c11-3733-43cf-9420-b8b43649d4e0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a5f37da5-6baa-4328-8c9c-6918fc4b3525 |  | note | VERIFYING DOCUMENTS: This ITP
text | bf8e5360-37a2-44ed-852b-d906b465eb01 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | a4588316-e7e7-4e0e-9758-f543cc46a5c7 |  | note | REFERENCE: IFC Drawings
label | 58ec3b65-10de-4a65-b654-7f01056a3c97 |  | note | 630.20 (a) & (c)
label | 71105a60-94bb-42fc-8992-18de0517ea52 |  | note | AS4100 Clause 14.3.5.2
label | 38ce5ae0-25ea-4dc4-b242-2cb4bacca7a1 |  | note | AS5131 Clause 6.7.4
label | 05901694-0af4-4c87-a9f6-24f59739f2f1 |  | note | AS4100 Clause 15.2.5.2 (a)
label | ee546a5d-7392-4aa9-b6d8-203b7517d68e |  | note | AS5131 Clause 8.3
label | 7bcec74d-4877-4adc-873e-9c4504ca3799 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 00093cb6-f661-4aab-884a-945c2cc0d881 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | e7eaa6c1-ddde-4ec4-a60c-7c2814758ed0 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | db0e179f-8025-4f45-a614-7e36a10dd096 |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podgier spanner.
label | e4b4f664-7620-4047-a5f9-72caf8684ea7 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 28075769-b146-4282-838f-e097930aea83 |  | note | METHOD: Measure , Visual
label | fb3f4ae8-cb4a-419b-b198-84ab7fb35ee4 |  | note | FREQUENCY: Where applicable, each bolted connection
label | 3eccfffa-a015-4276-8618-e639403468a6 |  | note | CATEGORY: IP
label | 82269d07-b2a5-4fe3-b8e3-bbbd92e9bfb5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0f7dfe10-20d9-454c-aa71-cc9fcd1c5dbc |  | note | VERIFYING DOCUMENTS: This ITP
text | 28523c9f-04a0-4ab3-bf11-76e9515e3315 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Survey Conformance
label | ffa152d3-b9dd-48bb-a555-c7d39b3f8631 |  | note | REFERENCE: IFC Drawings
label | b06bb7bb-75a6-4c03-baa2-43f5ed472581 |  | note | AS4100 Clause 15.3.1 - 7
label | e7570648-3f4a-41bb-897b-f69254b4eccf |  | note | AS5131 Appendix F, Table F3
label | f8bc8dd0-d25e-4b72-902b-98be65287983 |  | note | ACCEPTANCE CRITERIA: Grouting of base plates shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | f6f4c7d5-7ee4-476b-818e-ee6be1f9c8ee |  | note | Departure from RL = ±10mm
label | ff67e23e-0635-450b-8add-f7df74215aab |  | note | Departure from plan position = ±6mm
label | 179892fc-5558-47e9-b0fd-2ed35e1432b4 |  | note | Departure from alignment = ±6mm
label | 33fdfd6c-6223-4161-bc39-6b697fa4e11e |  | note | Irregularities in alignment = 25mm in 30m
label | 2b024547-c3a1-4b3a-9e57-c436449b4dcf |  | note | Projection of bolt = +25mm, 5mm
label | c0b330ad-d5ea-4a75-99c4-333e29e710ab |  | note | Attach: Survey Report
label | c9acbafb-867b-449d-8c61-f315bbfc9afa |  | note | METHOD: Measure , Visual
label | 9abf329b-cb27-4625-a9eb-2d902e87cedc |  | note | FREQUENCY: Each element
label | d839da26-eef9-403d-8e17-21d6f6359c66 |  | note | CATEGORY: HP*
label | d6cd8f24-60f0-4a9f-9a3b-8d6d62cec3e8 |  | note | RESPONSIBILITY: All
label | 27f83a43-60cf-43f0-9b1b-3338a493f5c8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7773ac24-cacc-4077-b6d4-3f3ba236c826 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Base Plate Formwork Construction & Placement
label | 1f4f9cdd-1dd8-40fb-9630-e897a783e780 |  | note | REFERENCE: IFC Drawings
label | 82c6807e-9d8f-4ff9-876f-e7d35262913d |  | note | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
label | 9e1f53fb-556b-483b-b7a6-1f44e37668cd |  | note | Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | 12e4ff12-656f-49ec-a8f8-42f24c614b58 |  | note | METHOD: Measure , Visual
label | 974ee752-f834-4a20-974c-f8fc48ae8b1d |  | note | FREQUENCY: Each post location
label | e6640c4b-2060-4213-90c0-e619c6c46258 |  | note | CATEGORY: IP
label | 202c3e81-e6f2-412b-85be-a54f5ce79eed |  | note | RESPONSIBILITY: SE/PE/SPE
label | d36cd19e-e7fe-4443-81b7-654d382a6589 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4a662266-3e4c-4472-ba33-41e2c2a0c588 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pre-soaking Concrete Surface
label | 4fd0a6cd-9c4b-44d5-a6ab-38b74ed4de49 |  | note | REFERENCE: Product TDS
label | 3a37830a-7ab6-4a36-bfc7-cc17a9325fb1 |  | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | 26c3cd9a-e604-4edc-8468-ec88eeb5d99e |  | note | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | 45ad4eaa-b26b-4474-a1c7-f94ce51c6471 |  | note | METHOD: Visual
label | b20ef7aa-47f6-4a55-9d88-c2d21ad073c4 |  | note | FREQUENCY: Each post location
label | 90666063-6e4c-459e-83cc-57d9d2cb2d83 |  | note | CATEGORY: IP
label | 7248cc14-03b1-47e8-ab1a-c9b90c276a75 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d0e29884-329f-4281-a0a0-3ae4964fe48f |  | note | VERIFYING DOCUMENTS: This ITP
text | 6c0ded39-49b2-4657-9cf1-e0b85b4a8da4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Weather Conditions
label | 24398fef-113e-4d4b-bab6-6265b4b79107 |  | note | REFERENCE: 610.17
label | e4d9dff4-e4dd-454c-982b-12cd1b888b2b |  | note | Table 610.171
label | 60aeae9e-8fc8-475f-bb7a-bcfcc0023ff3 |  | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | dada6e82-1ff1-4e14-97f2-8e9ba2248bde |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 2c731c6e-8831-4666-bef9-6b6f7448c07b |  | note | Record: Required information on the Grout Pour Record.
label | dee41597-2e09-4511-b62e-179d342cd8f1 |  | note | METHOD: Measure , Visual
label | e2a0150a-275b-4b5f-a3c1-72a022a8c99c |  | note | FREQUENCY: Each lot
label | d50bd689-2d3d-41d5-b49d-9e44a06bdcd5 |  | note | CATEGORY: IP
label | 5ae14bbc-041e-412a-9a87-7b7eb9c12b1d |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | eadb2f6a-7a39-4f9a-b339-7d5ab5fadb95 |  | note | VERIFYING DOCUMENTS: This ITP
text | fef6a832-c6ef-45dd-a745-b77b2c09fec0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Mixing Product
label | ced613d0-5d6b-4792-8ede-bc6ee6ed3a99 |  | note | REFERENCE: Product TDS
label | 0cc36bd5-c312-4324-8adc-31ee06933de0 |  | note | 610.28
label | a315c873-325f-42eb-a7ad-ab0ff57ecf1b |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 99455467-c8c7-4819-bd49-157e184aa441 |  | note | Only whole bags to be mixed with potable water.
label | 678adb58-7e14-4ff8-b5f2-be0191e6f6b9 |  | note | Volume of water matches the required amount for flowable consistency and accurately measured.
label | f7089b05-dd6d-40b2-a7ec-bbefc313b0a9 |  | note | Product poured into the mixer slowly.
label | fe5ef11c-844b-4017-baa2-0bf99f3b5f36 |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
text | 8ceefeec-032d-4b62-b361-279482cad88e |  | textbox | Enter: Required information on the Grout Pour Record.
label | 43b62a04-0bc0-4e4a-ace6-85599cf6393e |  | note | METHOD: Measure , Visual
label | b45070a2-ae1a-40b4-8fff-8367d83ca91b |  | note | FREQUENCY: Each batch
label | 10d5e4e2-8a36-4c8d-a4d0-a76df762b9b0 |  | note | CATEGORY: IP
label | a4c1b5e7-84a0-44ed-9971-3e720b57286e |  | note | RESPONSIBILITY: SE/PE/SPE
label | c94b37c3-c9f8-4b9d-a6fc-f39e4d8ac28c |  | note | VERIFYING DOCUMENTS: This ITP
text | 4b840c61-4619-4c98-93d1-2a6ad87fdee3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Product Testing - Compressive Strength Cubes
label | 4e511810-6457-45ba-8985-cc268bbaba79 |  | note | REFERENCE: 610.28
label | 5569b194-f28c-41bf-9547-75538f64043b |  | note | 610.33
label | fc553a89-0129-49c2-b0d8-899229381157 |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | 4c0ba25e-d119-4d1b-983d-229b577371a8 |  | note | Testing is be in accordance with the following frequencies:
label | 203b88ef-5635-4e8c-8c49-3b59fb5e98ac |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 4a10477a-a7c7-4746-b70f-a9d1c0a3080e |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
text | f17fca04-b912-4d83-957c-6125b31ddda4 |  | textbox | Enter: Required information on the Grout Pour Record.
label | 51b1fe0d-e3db-4b5c-951f-553f58644e6f |  | note | METHOD: Test
label | b77e8a2f-a805-4ddf-b84f-7ecff99362e7 |  | note | FREQUENCY: Each lot
label | 190bd450-6dac-4d4c-8efd-fe7b61ebcfd8 |  | note | CATEGORY: IP
label | bd8fbfd8-92fa-4a67-8f38-21b767c445e6 |  | note | RESPONSIBILITY: Tester , SE/PE/SPE
label | 5810b942-1194-488c-90bd-d6bcfc55db4f |  | note | VERIFYING DOCUMENTS: This ITP
text | 12e5620c-b051-4910-a6a8-4d89017f087a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction
label | 83a61ec2-7250-4a3f-85c7-5e39e3d7383c |  | note | REFERENCE: Product TDS
label | bcd8f00e-bdf8-4250-8e97-51dfd1f863a6 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | 746cbc9c-0f22-4b3e-a9ad-6d78119037c8 |  | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 25bdfcf7-5b4b-4fb1-b5bd-bda9bc8729e7 |  | note | Product should flow to all areas and self consolidate.
label | 57fe0e5b-6c1d-4186-9b1d-b767a8f86334 |  | note | Product that stiffens or is showing signs of stiffening shall not be used.
text | 511b4317-11a7-4f25-95ec-6e6b38b99b05 |  | textbox | Enter: Required information on the Grout Pour Record
label | f7b9e2da-5a9f-4e4a-9ea9-c85b87685152 |  | note | METHOD: Visual
label | fc516a80-123b-48a6-8724-56e0dee0898a |  | note | FREQUENCY: Each post location
label | 7dbe1ed0-29a8-4738-acae-5e52bac71610 |  | note | CATEGORY: IP
label | fd90bad4-32f3-4dc7-9ccb-9537f3796204 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 8a65ad17-fc15-4d29-89b1-8559331248fa |  | note | VERIFYING DOCUMENTS: This ITP
text | c81b2aff-e09b-4fc0-8887-8ac56c9f8e76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes & Protection of Works
label | e54a5b9c-66e0-4f60-b58c-fad83bef383d |  | note | REFERENCE: IFC Drawings
label | 96abad4c-0f48-49e3-8780-698a05d49cd4 |  | note | 610.17
label | e5c78e79-6355-4e53-b196-56fab92129ef |  | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | a0d6e886-76cc-4e3a-b114-45b31474eb03 |  | note | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | c1867d98-f70c-4d94-8671-a3e9682d1be8 |  | note | METHOD: Visual
label | 6e27b76d-bc6a-4755-bfb1-a5ef4744c386 |  | note | FREQUENCY: Where applicable, each post location
label | 35ea3131-7192-475e-9013-b0f53cd43545 |  | note | CATEGORY: IP
label | cb7a028f-4936-43e0-883c-808c20bddea1 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 753fc37e-1e39-42ca-a07d-3b35049ba1a8 |  | note | VERIFYING DOCUMENTS: This ITP
text | e992803c-ca76-4941-8fe4-8f35162f4965 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Curing
label | 1bfce4ed-b107-491f-a8e7-34d017c0507a |  | note | REFERENCE: Curing Methodology
label | 7e1d9c01-6afc-4c23-98ef-ad57e6d6ff1a |  | note | 610.23
label | 1f4255f5-a3e9-41fc-ad59-06eea9a4e7bb |  | note | Table 610.231
label | 6749d7ca-5cab-4145-9ffe-19225e4e34e2 |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | 7284c75e-493e-4406-8d9c-1a135bca05bc |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | e6e17fb5-35f0-424c-9ca0-fc693678895d |  | note | METHOD: Visual
label | c4fe6458-28de-4fc8-8550-9af05c402b8e |  | note | FREQUENCY: Where applicable, each post location
label | 7e7c5434-34dc-4af7-9bbf-fbd33143a376 |  | note | CATEGORY: IP
label | 59f6a714-c4f2-4f38-8d67-72399cc0262f |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | a34018b1-fa10-4982-8c12-3bc721f59eb2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 937b123c-f8ab-44bd-8968-ac4a8a8f33ed |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | 213936e6-0a06-4c37-a922-bf67b0584600 |  | note | REFERENCE: IFC Drawings
label | dbb05612-f41e-420a-9c29-14d068b3b520 |  | note | 631.15
label | 2ed195c2-85dd-4181-9c4d-c9a7f25ee2b2 |  | note | AS4680 Clause 8.3 & 8.4
label | 0b61ab8c-947b-4b5f-8ddd-31278834a927 |  | note | AS4506 Appendix E
label | dccf4c7a-0e57-4e5f-8212-a7e6c550c064 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
label | 3d9c3138-8256-4309-966d-e6dba2e53d98 |  | note | Where damage exists, it shall be repaired using an approved repair procedure.
label | 7b0b5179-bc34-4ea2-83fe-addf9df1b270 |  | note | METHOD: Visual
label | 56c08ef7-c725-4937-b0d0-a8e994039bbf |  | note | FREQUENCY: Each component
label | 9b7f9fe2-f4f7-4818-b3e0-1d78bebad5a3 |  | note | CATEGORY: IP
label | 21cdc7e2-afb8-42c3-a205-0dc8bace87b4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 173c857f-bbac-44a9-8805-12439d9e7a3c |  | note | VERIFYING DOCUMENTS: This ITP
text | 47ed5d09-7f04-44b9-b1ac-1f9c2280b3d1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 2ffdc8d3-77a7-4d54-ae0a-48bca07fe650 |  | note | REFERENCE: IFC Drawings
label | f356efa1-0e66-497a-af05-a9a48c03286d |  | note | Product TDS
label | 69a25348-97ab-431c-ae36-7ad1e39c8d93 |  | note | 610.28
label | 7bfd29fc-ee77-4fc1-bf9e-669d68c35e83 |  | note | 610.33
label | 9384f06a-5b52-44ad-bc75-dea7d5e59e58 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 468e10a7-519e-47d2-80e3-092a650e8da8 |  | note | 28 day compressive strength per sample comply with the design strength.
label | 2828f966-b019-41de-af43-c245e7b1fa2e |  | note | Attach: Compressive Strength Test Results
label | e76d0715-8daf-4bbb-8e42-3c77062a385a |  | note | METHOD: Document Review
label | 9cf66461-d2e9-470e-b2da-faa9f0b95513 |  | note | FREQUENCY: Each cube
label | eefe7d4b-a2cf-427a-8b46-a4268af00bcf |  | note | CATEGORY: IP
label | 09e4c91c-7f91-4cee-8201-69d1e565d4eb |  | note | RESPONSIBILITY: SE/PE/SPE
label | 70276942-cf00-4341-a036-6e41656b6803 |  | note | VERIFYING DOCUMENTS: This ITP
text | d9aff1a8-2731-4f05-9859-11b3201a9817 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | 16d61ab5-1eee-45d7-8b64-70e2143e14e8 |  | note | REFERENCE: IFC Drawings
label | 3c4e3767-417d-43d2-a39c-2e0d999679e2 |  | note | AS5131 Appendix F, Table F3
label | 76ae3ee5-1507-4cef-851c-da248bf6a001 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | b2a3ae15-d70e-4ff0-8c94-b0d7018f28a1 |  | note | Departure from RL = ±10mm
label | f7704619-9b6c-47fe-8d3b-07f73491669c |  | note | Departure from plan position = ±6mm
label | 95992f92-7e5f-451b-9b5f-5e9669fef870 |  | note | Departure from alignment = ±6mm
label | d198f458-39b9-4c9f-a4c3-ec79e5aaff75 |  | note | Irregularities in alignment = 25mm in 30m
label | e3f98857-30ff-4004-a3fa-78cb87f2d89d |  | note | Projection of bolt = +25mm, 5mm
label | 8eb091db-d7eb-4e6d-96ba-45a4751560b1 |  | note | Attach: Survey As-builts / Survey Report
label | cd2aa57c-fb9c-4d2d-993e-f81a3250ee3f |  | note | METHOD: Document Review
label | 45f57da0-0515-41e3-b8bf-722e3067dde2 |  | note | FREQUENCY: Each component
label | d0f606e8-0d07-40dc-a30e-81e55e840150 |  | note | CATEGORY: IP
label | 3a261aa1-4457-4925-90a9-ab0a944cca2c |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 977253a1-4e14-4c1c-adeb-4ebd4370e2c0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 549cd720-adc7-4dcc-b2b3-1abc59976a69 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 00277e52-48c1-4d7e-99d2-2be2a4ec4095 |  | note | REFERENCE: MRPA Quality Management Plan
label | a460d892-5a41-4740-a45f-ec672ea7d71d |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 3669a539-a89e-4409-b01c-865e82883a72 |  | note | METHOD: Document Review
label | 978b7baa-34a8-4caa-806d-c99c8022fb85 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | f6edbb19-fa87-4ade-b048-953872bd205e |  | note | CATEGORY: HP*
label | a72e06ce-f9e6-40e6-a95c-1ddf0c8a24fa |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2b100151-a54a-4a1c-8f84-d116c9406b64 |  | note | VERIFYING DOCUMENTS: This ITP
text | c66ed83c-578d-4305-bb9b-6a3c624f80b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 9bfbfdda-eadf-45de-aa83-f3a470af1b7e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8e436256-2dbc-4aab-9cce-f9f5617c020e |  | textbox | Name:
text | b8ce35a2-aec9-4799-b00c-c239df110564 |  | textbox | Position:
text | 578f4c00-786f-4520-8443-ae8a5f8bd9f1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-RAIL-Rubber Modular Units (Supply & Installation) Rev 2 | itp |  |  |  | Yes | ITP-RAIL-Rubber Modular Units (Supply & Installation) Rev 2 | d7cc3a78-e3a7-4465-a3fe-a1578a7598fd
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 66953186-43c5-4092-b82b-09b6f361112a |  | note | Document Title: ITP-Rail-PedeStrail Installation
label | 2937c47a-c0e8-4916-8e39-a04b912cd1fa |  | note | ITP Description: PedeStrail Installation
label | 6d1af35e-52ce-4abe-8e28-5b3222e522a9 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-CLD-ITP-00
label | bdaf2ca9-dfe7-4384-96d8-1c20ef8b743f |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | 0c908b4b-1c00-476f-aa11-ef16f24deb7c |  | note | Revision Number: 1
label | a9dcac9c-0859-4698-9a74-0c74c30eeb58 |  | note | Revision Date: 15/02/2021
label | c022af0a-8af6-4008-9eae-83ca20af1ae6 |  | note | ITP created by: James Porteous
label | 23409b59-a7d7-4d92-ad8f-b97b84016568 |  | note | ITP approved for use by: Romualdo Magpantay
label | 10e66d62-1ca8-4bb0-bfd5-a8142ac9c01c |  | note | 1.01 L1-CHE-SPE-316 Concrete Sleepers
label | 9e2203c9-536c-432d-befc-90811eb51f3d |  | note | 1.02 L1-CHE-SPE-003 Heavy Rail Construction Tolerances
label | a7bcc69f-3d45-4331-9c89-212cad3015ec |  | note | L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
label | bded482a-7d5e-44d1-b9e5-ea8044acda00 |  | note | PTC Heavy Rail Track Construction Standards Drawing F598
label | ca5e2abc-f245-481a-89c2-f07083cd1cae |  | note | Clyde Road Package 29 Design Drawings
label | 993a7cda-ef04-487b-bb50-a7ee94ad8a74 |  | note | pedeSTRAIL Installation Instructions
label | 62c829c7-54ba-462f-9966-a1c9bc3dcd16 |  | note | STRAIL Installation Lever Operating Manual
label | 7620a3c0-50fb-49db-b3cc-928e5518d2bd |  | note | STRAIL Removal and Transport Tool Operating Instructions
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.01 Obtain and submit Material Certificate of Compliance Strail components: Rubber Panels. Concrete Kerbstones, Metal Rodding/Fastenings
label | ce0b516d-5c41-4c55-a30a-3636092f452b |  | note | REFERENCE: IFC Drawing
label | 1c0aaec3-bf6b-46c3-b6e6-9652e73c0f25 |  | note | Track Construction Site Mudmap
label | e7866928-52a7-4789-957a-4ec715a2f94e |  | note | Bill of Materials
label | 4a95e3b1-8fb0-4d91-8ef7-2e95fe2bc58a |  | note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
label | af8d1c3c-8636-4414-bd78-428275c120b4 |  | note | Attach: Manufacturer Certificates of Compliance/Material Test Certificate
label | fe90827a-ad11-43e4-9553-d9ce63097dd8 |  | note | METHOD: Review, Document
label | dee7b79c-a96c-48cc-8a69-e03de209dcd0 |  | note | FREQUENCY: Once
label | 24830d82-7775-4835-b2b4-f22816e03916 |  | note | CATEGORY: HP
label | c3b4caab-f865-4b8c-b484-c51292014e20 |  | note | RESPONSIBILITY: Track Supervisor, Project Engineer
label | 59e92606-eb3c-4ed4-8b5c-cdd27007b24a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | dfbc0b55-3894-4bb7-81d8-64fe4265a40e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.02 Inspect currently supplied items upon delivery
label | 6b09945c-7356-4253-bc05-8dd992ce3374 |  | note | REFERENCE: IFC Drawing
label | b9ed7bf6-1f2b-4f0a-a948-aa0cc9352f22 |  | note | pedeSTRAIL Installation Instructions
label | cc523ada-8c28-4080-9631-0ad7364f1981 |  | note | ACCEPTANCE CRITERIA: No damage or rust on components
label | 941ef1b4-966f-4b5a-8c02-a3aa4d7bc9a3 |  | note | Validate total number and type of components matches drawing
label | c69c28ef-f2c0-465b-b454-1f36369e0f55 |  | note | Attach: Photos on site;
label | 2101333f-4078-4f1b-a9a9-5097fe077b4c |  | note | Rubber Panels
label | 11076cc0-09f1-43c5-aad7-94e93d1f601e |  | note | Concrete Kerbstones
label | 0d0d3b6c-eaf7-4592-9c92-eb8b59213f29 |  | note | Metal Rodding/Fastenings
label | d5e175bc-1622-430a-b6a6-dfdde1b450df |  | note | pedeSTRAIL Installation Lever
label | 5f705a96-de9e-43dd-9828-b1b9f994d114 |  | note | METHOD: Visual, Measure
label | e607f832-45e0-40a2-aa89-72a598c9b17d |  | note | FREQUENCY: Per delivery
label | 7246eff3-7512-44a1-a671-7c0cc0b56a85 |  | note | CATEGORY: IP
label | 9ead2dcd-0212-44ec-97f1-e69afd923a9a |  | note | RESPONSIBILITY: Track Supervisor, Project Engineer
label | 640676bd-e9db-46a0-8bef-ea23158cc26d |  | note | VERIFYING DOCUMENTS: Material Inspection Report
text | 70a3268b-f24a-4024-b001-49a9a32850d1 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 3.01 Inspection of Existing Track Condition
label | 004e60c3-2246-459f-aec3-4adf7b6a9cc2 |  | note | REFERENCE: MTM Product Type Approval Certificate
label | 19f2ba1b-2de3-4f8b-8f8b-dc46bcf2d818 |  | note | MTSP 030100-01
label | 2f5f759d-d7d3-41eb-8543-3136fd4079cb |  | note | Appendix 1 Table
label | e381bf2b-641a-4777-9c77-ab8a1019eb68 |  | note | MTST 000002-01
label | 819ddbdb-8952-440c-9d54-a1a34c2f8093 |  | note | ACCEPTANCE CRITERIA: Correct Rail Weight (60lkg/m)
label | 0ef09eb2-a653-45df-a85e-a573aa9fbd8c |  | note | Rail Defect Free (Surface/Internal)
label | 81565caa-2938-49c2-9e62-e51c35ae470c |  | note | Track Geometry Defect Free
label | 6c07459c-6895-4ffc-bdea-ffc5fe58616e |  | note | Wide gauge < 12mm from design
label | db5714af-5322-4f49-b3be-75f7b52c50fb |  | note | Tight gauge <-8mm from design
label | a1808dbd-7d06-4904-9f25-2aa1699dd6aa |  | note | Cant <25mm from design
label | bd2d2355-89be-4a6c-85c7-349f9c38689a |  | note | Twist (3.5m) < 15mm from design
label | 20bf933f-3ab0-43a3-b686-d20ba5087e8b |  | note | Twist (10m) < 30mm from design
label | 8c670673-abcd-40f4-b84d-9d1254b620fb |  | note | Top <20mm from design
label | 0d9cc624-74c0-4930-9d46-ae5fb9c85f17 |  | note | Line <18mm from design
label | e549e1c6-fc8d-46a4-939e-e652fe66ebad |  | note | Sleeper Spacing @ 600mm c/c
label | 8a446ffd-a9bf-4b81-8840-5344a27f04b0 |  | note | Ballast shoulder 450mm wide 1:4 fall
label | 658ff17a-d832-4dda-abbf-4bf34b1a63e2 |  | note | Top of sleeper free from ballast
label | 442b97f2-cfff-432e-86db-e277faf5285e |  | note | Attach Site Photos:
label | a53eddd9-72ca-4f64-9e1f-1cd3d22d2c76 |  | note | Before Track Layout/Condition
label | d79bb921-0c77-45ac-9475-07f0a044e0d1 |  | note | Track Measurement Sheet
label | 6e289bdb-99a1-4197-bc6e-896b4841cb40 |  | note | Sleeper spacing measurement
label | 521c0236-c27d-445e-a96e-1902e5cda63a |  | note | Ballast shoulder measurement
label | c43e5261-f129-4719-b21d-d5f70849c777 |  | note | METHOD: Visual, Measure
label | ff005eeb-7e13-4bf2-947c-5dff6804abc6 |  | note | FREQUENCY: Once
label | dbeaaa0f-5476-4e5f-85ca-f75285fb9d44 |  | note | CATEGORY: IP
label | b86d8fdb-c399-4456-ba93-d553ceecfff9 |  | note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
label | 19f48ec0-3942-4f87-aa45-8088236232c5 |  | note | VERIFYING DOCUMENTS: This ITP
text | c8a1e3cb-e990-4284-ad49-ba77d364e390 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.02 Excavation of Granular Footings/Bollard hole Foundation
label | e66d91e8-9b58-4b0f-bc7f-c2ac9e4b5464 |  | note | REFERENCE: Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
label | 21e07f80-6b7d-47d1-954b-c211fa3adca5 |  | note | ACCEPTANCE CRITERIA: Survey Check that footings are placed in correct location and offsets to track;
label | d69e0679-bd2a-4ab0-ab1c-adbd352080d9 |  | note | 50mm offset edge of sleeper
label | c933004b-809b-44fa-bf96-4ed90750187e |  | note | 100mm below bottom of sleeper
label | 109ae35a-d04f-4fa6-bb5f-c5b51f0795fd |  | note | Asset Search no underground assets
label | 183f7692-fea7-4a10-ba80-f1df5d7bae73 |  | note | Minimum Excavation Dimensions; 600m wide x180mm deep x 24300mm long
label | 16e57b57-8e17-4093-81d0-9d5fc17ab2d0 |  | note | Attach;
label | 37e6f4a8-6c41-4858-bf04-c72f160a6ae9 |  | note | Survey Sheet
label | 691fce9b-c426-48f7-a2c3-c6dfca2078ce |  | note | Asset Locator Readings
label | 3fba01de-37e9-42b5-8583-c7eb65b3fffa |  | note | Attach Site Photos:
label | cfe5e867-7c83-430c-a9d3-9d7ce37b3ecd |  | note | Survey Checking
label | 2cf642e0-c4ff-46c9-92e9-bb65a5ade1b4 |  | note | Asset Location Checking
label | f1fbb67b-ca75-43b5-a24f-429cc6d19de5 |  | note | Excavation works
label | 37c41930-3bbe-466a-9722-7261a363451b |  | note | Sleeper Offset Measuring
label | 5118b083-feb6-4ac2-a716-2d606ff2092a |  | note | Excavation Dimension Measuring
label | 11947376-7c30-4508-97b4-2da2a3f3131f |  | note | METHOD: Visual, Measure
label | fd91240c-85cf-47a8-a660-2c074101ef1c |  | note | FREQUENCY: Once
label | 139f0945-c2fe-4ade-8335-cf973085c52b |  | note | CATEGORY: IP
label | c04b8217-e7b7-4352-9ee9-b3cf85a435d4 |  | note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
label | 8be47af2-f504-4957-ae8f-45f0ac3c9c2f |  | note | VERIFYING DOCUMENTS: This ITP
text | 2c9faade-ca85-4718-a6f7-e0f8c28e2720 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.03 Footing foundation placement (Geofabric/Cement Treated Crushed Rock)
label | e5ca47a8-e16d-4a25-9842-015a5381c522 |  | note | REFERENCE: Material Installation Instruction
label | 0845bec6-b31b-46ce-b4f0-51a888b0a2bd |  | note | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
label | 318a0c48-6325-403f-8989-a4789661605c |  | note | ACCEPTANCE CRITERIA: Compaction of CTC to 5MPA
label | 59d5a3eb-6f40-4461-93aa-91c851be93b3 |  | note | Minimum Footing Dimensions achieved ; 600m wide x180mm deep x 24300mm long
label | 009a2f4d-2712-4fa5-91c3-21eaf72c311e |  | note | Attach;
label | 48c2a504-83f5-4f96-a522-bbba4e29e55e |  | note | Certificate of Compaction
label | 2d181d01-91c2-4571-b361-371eb93f81b7 |  | note | Attach Site Photos:
label | 06c27487-d985-417e-a293-cafec99825ff |  | note | Compaction Testing
label | 0b3b9229-3d2c-4372-bb3f-c3ad4cffb805 |  | note | Footing Dimension Measuring
label | f43982b7-4196-4078-a874-a883b1bba18f |  | note | METHOD: Visual, Measure, Test
label | 79de741f-cc45-40e3-b067-83f5b341bee8 |  | note | FREQUENCY: Once
label | 6f4763b4-c85d-4bb3-b00d-af79b03f51da |  | note | CATEGORY: HP
label | 64621ab8-10cd-41b5-9d67-3cc236f1ca68 |  | note | RESPONSIBILITY: Geotechnical Engineer , Track Supervisor , Site/Project Engineer
label | 3fdfb2b8-d6a4-47a9-8070-143228812980 |  | note | VERIFYING DOCUMENTS: This ITP
text | 90ccdc54-7e80-4560-89d3-6a5d48b82040 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.04 Installation of Bollards, Concrete Kerbstones
label | 164dd812-41d5-41da-b4b3-36b3126fc6bd |  | note | REFERENCE: Material Installation Instruction
label | 6e16df5e-5dd0-4567-80c2-9833c5034a85 |  | note | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
label | e98b4e0d-3a7c-4636-858b-deaea3ea37aa |  | note | ACCEPTANCE CRITERIA: Bollard
label | 86b14265-eacb-41f5-b879-bfdbe5f8956e |  | note | Concrete 25MPA with N20 Grade
label | f0bf6d89-0256-4104-8993-31a11e0cb0b5 |  | note | 100mm Concrete below base of Bollard
label | 5998cb87-168c-46e5-b44a-f456a9b97a4c |  | note | 1200mm protruding above ground level
label | 1602d8eb-d43e-4c81-bf24-bb08b89ac73c |  | note | Kerbstones
label | 9dbc2acb-fb9c-4937-b130-ae0f86e19f51 |  | note | Installed so inner top lip is 713mm offset to outer edge of rail
label | 837a14ee-da9b-485d-9b1e-43022b212882 |  | note | 7mm screening used on top surface of footing to adjust height so that top of kerbstone in line with top of rail height
label | 1e170ad4-1761-48e8-80dc-5c3ddc9bf2de |  | note | Attach Site Photos:
label | a3b7e74a-b08f-401e-ab4c-853ce4bc6bef |  | note | Hole Depth Post Bottom Concrete mix
label | 2e4d337e-d365-4bc6-8187-2442ace5cf6a |  | note | Height of Bollard above ground
label | 5d633a7b-b9fb-4af0-956a-78744ebabd46 |  | note | METHOD: Visual, Measure
label | 82a11552-da09-4f3d-8ab9-ce31e919952c |  | note | FREQUENCY: Once
label | 423201ff-4dcc-4fa2-a634-bdb459315b5e |  | note | CATEGORY: IP
label | b1dc1d86-da4b-4a1f-9a9b-82b975abbbcb |  | note | RESPONSIBILITY: Works Supervisor , Site/Project Engineer
label | f9e9b9b5-785e-47d9-b466-6cbba57a7abd |  | note | VERIFYING DOCUMENTS: This ITP
text | e575b565-cfda-43c5-bfc7-5f217e4c46ca |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.05 Installation of Rubber Panels with applicator and metal rodding /Fastener
label | e708cc7a-5e92-4d6e-b406-c334a5e1a9f9 |  | note | REFERENCE: Material Installation Instruction
label | 12d1d757-da89-4726-ba36-958250207b3f |  | note | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
label | df8448b3-311d-4eba-afc0-09d51ada3ec0 |  | note | ACCEPTANCE CRITERIA: Correct location and sequence of Panel Install
label | 44c3a8c9-9d74-4f16-9a01-dc4fd4836c3c |  | note | Panels sitting within rail profile, no dip on outer panels
label | 5082048b-5575-4f87-b4db-7bd129507828 |  | note | Attach Site Photos:
label | 9d310408-6841-4f4a-a68a-2072e0ccee3a |  | note | Rubber Panel Installation
label | 32c6f57b-7da0-43f8-86a4-e2ebda6d39bc |  | note | METHOD: Visual
label | 6a8f2642-cb5c-4a2a-b775-db7efbe536b1 |  | note | FREQUENCY: Per lot
label | 5e82377b-4e6a-458f-83f2-07c6addd1ecb |  | note | CATEGORY: IP
label | 3bcd9713-3c01-4204-b997-50723ef5d783 |  | note | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
label | 018f6bc2-f46c-4676-bd51-975309cdf482 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9da6be1d-bda4-4ce6-9a78-01b05434d868 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.06 Installation of Ballast Shoulders on Kerbstones
label | 2ba0a751-61e4-4061-8b23-f086255402eb |  | note | REFERENCE: Material Installation Instruction
label | 6635f474-e64c-4856-b7ff-9f53346efcb9 |  | note | Design Drawing MRP-016-C-DRG-09-NWA-CTW-9009
label | 8e9c181f-c9f5-44be-ad13-19d7bc71f8e7 |  | note | ACCEPTANCE CRITERIA: Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter
label | 0d7961f6-3548-4e86-be48-1cd191bcd3c7 |  | note | No Ballast to be on rubber units/within gauge grooves
label | 620dd3ab-69f0-418d-89d2-7fd615bb197d |  | note | Attach Site Photos:
label | 64cfaf0d-29a7-47a5-9a50-95f9c46c326d |  | note | Ballast Shoulder Measurement
label | a1b99c1c-3781-47be-b174-4b28f3ba5209 |  | note | Rubber Panels free of ballast materials
label | 826efd03-2e26-428f-83fe-6830a8151dd1 |  | note | METHOD: Visual, Measure
label | 5a0c525c-adce-4747-bf47-09ba68c0498a |  | note | FREQUENCY: Once
label | e2e9f4ec-ec2b-4770-8f1a-3f1da72be799 |  | note | CATEGORY: IP
label | 3f80c977-9cd3-45fb-bd8d-321caf556f73 |  | note | RESPONSIBILITY: Track Supervisor , Site/Project Engineer
label | 5090c6f2-833e-4d08-9696-1f7cee8f6513 |  | note | VERIFYING DOCUMENTS: This ITP
text | 150407ee-f72b-48f7-a161-6a44917e57bb |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-Installation Activities
checkpoint-status |  |  | checkpoint | 4.01 As-built Survey
label | e538fcf5-8d9f-41bd-8571-fb56aee99734 |  | note | REFERENCE: As Built Drawings
label | eb02a535-7cdf-42f5-a01c-f1be90c31faa |  | note | Asset Change form
label | 72d1ec49-16a9-4592-9570-d849124427bf |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | c7cb059b-0494-41a3-9ce6-a2e303b4cd82 |  | note | Attach:
label | dacb60ca-ab52-428d-aeb0-8c13fc6174a4 |  | note | Survey Report
label | 280ab864-0042-4f5a-87f7-960686ac3508 |  | note | Engineering Asset From
label | 05b1344a-eab6-4184-858b-aec26d04f056 |  | note | METHOD: Survey, Document Review
label | 2ca37068-55e0-42c7-a82a-f71027b91228 |  | note | FREQUENCY: Once
label | 548d5fa3-6667-4281-a9c7-bf481987c1d9 |  | note | CATEGORY: IP
label | 9521b3c6-3728-427d-9219-6e1814f1d14d |  | note | RESPONSIBILITY: Track Surveyor , Site/Project Engineer
label | f5f06b1d-024d-418d-9324-1aeb113fea02 |  | note | VERIFYING DOCUMENTS: This ITP
text | aeb11516-1f64-4a99-a26c-ac9644ca6298 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.02 Track Certification
label | 7a27c5ee-4029-488a-86dd-011f9eedceec |  | note | REFERENCE: MTMF020000-1 – Track Form A T
label | bffc2acc-c4a6-4cc7-8769-b0a079baecae |  | note | MTMF020000-2 – Track Form B
label | b094c369-985c-4470-a02e-a93262b6509c |  | note | ACCEPTANCE CRITERIA: Attach:
label | 7970dc95-69f7-43e1-87e4-8eb1a1f06e34 |  | note | Track Geometry Conformance Certificate
label | a75187eb-5707-4288-a603-f99a952d52a4 |  | note | Track System and Component
label | bd520470-9b1c-40d6-a5ae-a6a589a003df |  | note | Attach Site Photos:
label | bcf519e9-a06d-40f0-bfef-0613b4df5b85 |  | note | Before/After Photo of worksite
label | 033e8c34-0d08-4f47-a27b-009bd56244b5 |  | note | METHOD: Visual, Measure, Document Review
label | e663e65b-0811-4977-bda3-381248560de9 |  | note | FREQUENCY: Once when all occupation works complete
label | dee31732-6314-4989-9b29-0765c31de5f9 |  | note | CATEGORY: HP
label | 6f2e91cb-8792-452e-9474-48b24be52e45 |  | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | 2733b7bd-4d43-4b6b-aea8-f150320340e8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 976dd494-5d90-459e-8405-ad3f7d75f9a8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 10bfed29-a9cd-409b-9b3e-08b6e342c27c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 8cc3c356-1b38-4766-bea1-722bd2ddb55f |  | textbox | Name:
text | faffcc54-5986-42a0-88fb-ae61bb17fa85 |  | textbox | Position:
text | a0bb76d2-5d9b-4542-99ee-f30ea41e1800 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Elastomeric Bearings (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Elastomeric Bearings (Supply & Installation) Rev 0 | d9883a22-cfec-4d70-800d-756d3d9a36c0
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 59008c4a-f7c7-4e18-b379-ee428699e157 |  | note | Document Title: ITP-STR-Elastomeric Bearings (Supply & Installation)
label | 924f58c8-6f9d-44e0-b004-db60dcc1340b |  | note | ITP Description: Elastomeric Bearings (Supply & Installation)
label | 26d47787-c2ba-401d-bb60-8a8d3fe1fc6b |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 175e233b-0e46-49f7-92cc-8387b67d62d3 |  | note | Discipline (e.g. CIV/STR/RAIL: STR
label | 17011fa6-564b-406e-be96-14efeabb5ab7 |  | note | Revision Number: 0
label | d618756e-0809-4ed9-bc04-a3486fe00451 |  | note | Revision Date: 15/04/20
label | b37fe88e-7323-45f5-8202-bc2a5aabcee9 |  | note | ITP created by: Mike Freeman
label | 0e0c68ac-f120-43fd-a9a6-5ea30d009e66 |  | note | ITP approved for use by: Mike Freeman
label | ff5faeb1-81de-40db-904d-0ce3251c1b84 |  | note | 1.1 Reference VicRoads Section 610 November 2018
label | 58cf305b-7e41-4e48-8f12-3713258c345d |  | note | 1.2 Reference VicRoads Section 610 June 2019
label | de532c4b-af53-4c95-b2f6-800c2400bfab |  | note | 1.3 Reference VicRoads Section 620 May 2009
label | 0a82f41b-7837-4062-a367-3f0d6cef4cca |  | note | 1.4 Reference VicRoads Section 622 November 2018
label | 89ddd0de-ac64-4588-8bb9-a1a37558d7c0 |  | note | 1.5 Reference VicRoads Section 652 June 2010
label | 1989bd02-5f56-497e-8900-867845430b97 |  | note | 1.6 Reference VicRoads Section 656 June 2010
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Galvanised Bearing Plates
label | 127b2a63-03dd-49dd-9202-0627f6fc4a19 |  | note | REFERENCE: IFC Drawings
label | 1b2892a1-5bd1-4c31-b2af-ffe899c6262f |  | note | 620.05
label | 6813f18f-7ec0-48f9-b367-4aabdbfc5fec |  | note | AS5100.4
label | 269e3859-df1b-481c-b9c0-8dfc9d948398 |  | note | AS/NZS4680
label | 5f2e677a-a194-4d28-9ee3-b49a336f55a8 |  | note | ---------------------------------
label | 2dd8d213-c767-47f7-a338-5c66f0d293fa |  | note | ACCEPTANCE CRITERIA: Steel bearing plates (top, bottom and tapered attachment plate) are to be manufactured to the requrements of the IFC Drawings and AS5100.4 and galvanised to AS/NZS4680:
label | 441f3496-c5c3-4987-819f-030e120f6656 |  | note | Tolerances:
label | cb07e706-2094-4d6e-a8e8-6b3ba69f4b8e |  | note | Length/width = +2mm, -1mm Or;
label | a689ed71-5cdc-4ca1-a5c0-728b4be405cd |  | note | Diameter = +2mm, -1mm
label | 48f6dfeb-157b-431e-928d-ddd98ab413c9 |  | note | Twist = the lesser of 1% or 1.5mm
label | 6c6f0687-254d-48b0-92b9-4325198aed21 |  | note | Galvanised coating thickness for material >6mm:
label | 97a9c121-cbfd-41f3-9d04-167eacbccaff |  | note | Average = 600gm/m² or 85µm
label | d0b8e89d-37c5-405b-9d4f-e79f4e527b3f |  | note | Localised minimum = 500gm/m² or 70µm
label | fcaea127-79a7-4369-ae30-60bc62621c23 |  | note | Attach: Dimensional Records
label | b4af9b02-89e1-45f7-8523-acb82ae5416b |  | note | Attach: Galvaniser's Certificate of Compliance
label | b9bed28f-9278-4a25-ab64-44dd2842158a |  | note | ---------------------------------
label | d7f69e85-4fbb-4a18-a1a3-10c64725f2d6 |  | note | METHOD: Document Review
label | f30fc6df-799a-4d27-b548-b4bc54b499db |  | note | ---------------------------------
label | 83253240-d155-44f6-ac42-9da7f1d5cf87 |  | note | FREQUENCY: Where applicable, once, for each component
label | 8ee8cb67-2c97-42a6-98ec-37fa9451ea0b |  | note | ---------------------------------
label | dfa423ff-f198-44b1-ba6f-b25024fd396a |  | note | CATEGORY: IP
label | 53d13a88-1fe6-43b5-816d-4da1022d329e |  | note | ---------------------------------
label | ca300428-d508-4a2b-85ad-9bc280a098ec |  | note | RESPONSIBILITY: SE/PE/SPE
label | 342d4073-ca4e-4b78-96da-3038f4e1637f |  | note | ---------------------------------
label | 15491499-21f3-4266-80f9-d56d76d5e820 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7ebb3dcf-8cbc-4960-9567-24c776eaeece |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Epoxy Bedding Mortar Product Selection
label | e924f9c2-a099-44c2-b49d-444334fa148a |  | note | REFERENCE: IFC Drawings
label | e619d7b3-4ed1-45b1-ba95-d7bf30c76d9a |  | note | Product TDS
label | 456fb15a-489f-47f4-bedc-3a40a797e7d6 |  | note | ---------------------------------
label | 346b85eb-ae5b-4d00-83da-d172d69fb64a |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 99e28909-9ce6-41c7-b3b4-40bcf7370c07 |  | note | i. dual component, thixotropic epoxy resin or adhesive
label | be0e6ef0-ef96-4e49-a086-0213f993e152 |  | note | ii. Have a minimum compressive strength equal to or greater than substrate
label | b8bc2365-f53d-4278-8087-e522f1663667 |  | note | Iii. have no minimum thickness requirement
text | 5903d67b-6f33-4734-b353-5b3c84643099 |  | textbox | Enter: Teambinder Material Approval number
label | e4c5cff5-8116-4541-9d61-8a5d9c29ed75 |  | note | ---------------------------------
label | 31d767f0-18a7-4305-81de-4b8ce89064c0 |  | note | METHOD: Document Review
label | cc8e7f6d-1e48-47b5-ab11-ff700392e9a5 |  | note | ---------------------------------
label | 92238f47-d14b-4df9-b9c9-67633de3c63a |  | note | FREQUENCY: Where applicable, once, for each product, prior to use
label | 40b55b1e-2b54-478b-ae15-921ed8e7f5fc |  | note | ---------------------------------
label | 9d71a8c5-170d-422d-9437-3765113578ae |  | note | CATEGORY: IP
label | 45ffe70f-eec9-407c-b51f-00d880e1ee22 |  | note | ---------------------------------
label | 38cfc1ad-152c-4b3c-9cd5-eff70ddf6a76 |  | note | RESPONSIBILITY: SE/PE/SPE
label | beda265a-18ac-4fb2-ba76-ca796cc9501f |  | note | ---------------------------------
label | a06c0288-bed9-4cba-af71-776116830db7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 423b46b3-bd01-4efa-b4ec-a4b3d977a973 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Elastomeric Bearings
label | 3cc8ee98-2859-4aae-9c1a-e064de1755a1 |  | note | REFERENCE: IFC Drawings
label | c0fd4067-1877-46f1-b3e3-4cd1f66a17e7 |  | note | 652.02
label | 4f96c0a7-2ae9-4ac2-bd2c-b7e76adc1c3b |  | note | 652.03
label | 9eab4ad8-de98-4c6f-8d92-9ddfbc50e75e |  | note | 652.04
label | ca7406c3-031c-4708-b042-974736e3a643 |  | note | AS5100.4
label | 5c41863e-4bda-47a7-8ed8-f42bccc17b68 |  | note | ---------------------------------
label | 5c3eea1f-b585-4e3f-ba4a-3fb5df570c9f |  | note | ACCEPTANCE CRITERIA: Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
label | 72b52c77-25cd-48a4-9f67-2b8be9ef8b8c |  | note | Tolerances:
label | 72980c54-9f84-4506-a56d-a463295367a0 |  | note | Dimensions in plan = +4mm, -2mm
label | c5c67d64-cf5b-4313-a4fe-3bc3d4ef200e |  | note | Thickness =
label | 05c694de-ff6b-47a8-9470-3a73e6bb81b6 |  | note | ≤100mm = ±2mm
label | 9e3094d6-196d-4571-bdac-003c399a8e1c |  | note | >100mm ≤ 150mm = ±3mm
label | 9a80be62-c661-4da4-99cf-d3fb6b43d9e9 |  | note | > 150mm = ±4mm
label | f55bc5e1-c2c1-4aaf-bd7a-09a9b6c50c68 |  | note | Testing:
label | 6b929043-a26b-4fa8-9a11-01ff9c704e57 |  | note | Each bearing tested under compression
label | 3987dd0b-03f8-42db-8ec1-7e4c5a3330ca |  | note | Batch tested for shear stiffness
label | 3d4fea6e-fd2f-49df-b847-95c48c5bee5c |  | note | Attach: Elastomeric Bearing Test Reports
label | 1e8d30a2-740a-4c60-9add-4d8658c8ad3f |  | note | Attach: Elastomeric Dimensional Records
label | 1eb77bda-428d-4f13-a2e8-ee8faaf82dbe |  | note | ---------------------------------
label | 664247be-7b26-4794-a138-255d5404d571 |  | note | METHOD: Document Review
label | c16f7bd5-3994-429e-8a3f-dfaad2a41847 |  | note | ---------------------------------
label | 318d6a5f-e7a2-47c7-a2cf-ed430178aa59 |  | note | FREQUENCY: Where applicable, once, for each component
label | 4415cfe7-90b6-45cf-a9fb-1cf968646b4c |  | note | ---------------------------------
label | 4a2356d2-aeca-4187-9f03-3c92d4247ecb |  | note | CATEGORY: HP
label | ab063c39-25d3-433e-a94e-a9dfe01abb0e |  | note | ---------------------------------
label | 632e2e21-aa34-4dfa-9166-c17c8b7d0365 |  | note | RESPONSIBILITY: Nominated Authority
label | 478341cd-f7b8-4802-94ed-a0c3b19aedc7 |  | note | ---------------------------------
label | e26a3b8d-4b6c-4e6e-8476-f7ba8ef0b9ae |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 298086f1-9b15-4711-bf20-f730cc789f99 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Crosshead / Pedestal Tolerances
label | 1b576d89-9883-4277-aa6b-aa5f8505a9e2 |  | note | REFERENCE: Survey As-builts / Survey Report
label | 690d3b50-0f8f-4a76-8a89-21d13f61d964 |  | note | ---------------------------------
label | 49278be0-63fb-406f-95eb-59b2e8275268 |  | note | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
label | c0d528b4-8f0b-4fb1-a35a-28cc3b1414a3 |  | note | Reduced level ±2.5mm
label | 2e752141-ffde-4c0f-91be-7791d130d42a |  | note | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | f7e448e5-60bc-49ea-844f-7bd4e51e48d3 |  | note | Deviation from flat surface ±1mm
label | 6ee3b78a-bbf0-41eb-b7d4-c45ff401fb99 |  | note | ---------------------------------
label | d7bc29b6-7388-4c14-a95c-70a464df6cc8 |  | note | METHOD: Document Review
label | 94fecb61-f407-4935-b5e2-6ec2163b1270 |  | note | ---------------------------------
label | 1ed867e2-deff-4709-bea2-4ad338ecc888 |  | note | FREQUENCY: Each element
label | 3e01878f-e2d6-4812-ab9c-796352460156 |  | note | ---------------------------------
label | 0a66fa41-f902-42b7-99a6-6f4f751556c0 |  | note | CATEGORY: IP
label | e230a966-7228-4323-97ed-e4ce438d749a |  | note | ---------------------------------
label | a9b65756-9443-4160-b2e8-1bd310307493 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 6011bb2e-a0e5-4243-a882-3f5ffafb22dd |  | note | ---------------------------------
label | db577336-9a6e-4468-a27a-fe00bdeaaf0f |  | note | VERIFYING DOCUMENTS: This ITP
text | 8e905d99-b5aa-4bb6-a0eb-ab13f8b101d3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Bottom Bearing Plate Installation
label | 6695adb9-b048-4bba-8fc2-32f8a0222933 |  | note | REFERENCE: IFC Drawings
label | 343b3dc7-821b-44ad-bce7-8a06d8145fbe |  | note | ---------------------------------
label | e0025809-eac2-449d-9b29-e86edd048dd4 |  | note | ACCEPTANCE CRITERIA: Bottom bearing plate to be dry-fit into the correct location and orientation as shown on the IFC Drawings.
label | 01144a6e-9262-4402-97b2-9a0ba26ce32a |  | note | Mix the epoxy bedding mortar as per the manufacturer's TDS and apply a 1mm thick layer (approximate) evenly to the full extent of the plate.
label | f8e9ae6a-64c9-4061-a817-fd34bbda9266 |  | note | Bolt the plate to the pedestal to a torque setting of approximately 175Nm.
label | 77130ad1-ee02-40ec-abea-6f7714bce04b |  | note | Record: The bearing plate ID onto the Red-line Drawings or Survey Report
label | e7244285-50e5-4b9a-bfd8-60885f7aabaf |  | note | ---------------------------------
label | b083d71b-85cb-4663-bc88-962136397ac2 |  | note | METHOD: Measure, Visual
label | 24416c14-5943-4805-bae8-df3ca940f0d5 |  | note | ---------------------------------
label | a7343121-9d55-46b9-9a97-bcf542462394 |  | note | FREQUENCY: Where applicable, each bearing plate 4 days prior to loading
label | 8c4b6858-3bd1-4aaf-b3d8-be62894fd24f |  | note | ---------------------------------
label | 55722217-9c75-4ad6-9624-30ce293214e1 |  | note | CATEGORY: IP
label | 0024e0d2-c929-4cdf-be3a-d3a7d73a661c |  | note | ---------------------------------
label | 70a77d79-6492-4712-ad6c-8e4efe3e8a11 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 3a11ed39-6525-4610-b9a6-30cbfa0fdb14 |  | note | ---------------------------------
label | 4751da7a-147d-41de-b278-c1b68a723e40 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0f139417-a051-4fef-8d9d-050eb37391ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Elastomeric Bearing Placement
label | c514a182-58ca-45ec-863e-b7e7b25784a2 |  | note | REFERENCE: IFC Drawings
label | fb7cd916-8663-4516-a96f-8a4936f2935a |  | note | ---------------------------------
label | dd1fbf4d-c8c0-4be1-a78b-146397ef34f8 |  | note | ACCEPTANCE CRITERIA: Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
label | 4458a147-02ea-4e2e-b073-ac5656d519ad |  | note | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
label | 48070236-09e1-4bdf-8348-3a91d6cab0c2 |  | note | ---------------------------------
label | b602878c-1c15-4e96-a117-7c62a03f2bf0 |  | note | METHOD: Measure, Visual
label | a80a7cdf-78d7-4828-b34f-a2ffccc521f0 |  | note | ---------------------------------
label | a219ba3c-5c65-4524-83c8-84e48c6defcf |  | note | FREQUENCY: Where applicable, each bearing location
label | c59afd3a-8a08-460c-9ebc-cf4fc3d05e08 |  | note | ---------------------------------
label | 159f59f1-616d-4540-a959-57b96b2bb288 |  | note | CATEGORY: IP
label | dac84c59-ad36-4194-8d53-2aa7a2389833 |  | note | ---------------------------------
label | 372c8333-61de-4d59-a4d4-a6765741aefd |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | dfe76e49-a0bf-4db3-90ad-981a99766aea |  | note | ---------------------------------
label | 5e2ab4c5-e1db-4a57-94b8-8e5af0022a7f |  | note | VERIFYING DOCUMENTS: This ITP
text | d866fa24-d06f-4582-99f8-a945a044df4a |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 As-built Survey
label | b2b124b9-68da-447d-872a-8a6c1de46bd5 |  | note | REFERENCE: IFC Drawings
label | 5a1fa171-b1bd-48a0-a68e-1ecdd71ad49f |  | note | 610.46 (a),
label | d7313879-24fb-42f6-9502-d2607808c375 |  | note | Table 610.462
label | a7c5dc49-0152-44ef-ad63-507ae1902a7c |  | note | (November 2018)
label | 9818cdac-6db1-452c-b2a2-d7512067575c |  | note | 610.47 (a)
label | 649ac770-8ade-480b-b8e8-07474ae0ea0d |  | note | Table 610.472
label | 338fdde5-e225-458d-8da5-b2e3bb807941 |  | note | (March/June 2019)
label | fd747b2d-c572-4121-896f-72d9478c0d83 |  | note | ---------------------------------
label | 3d7f60b5-fc8a-47ad-a4c5-202853f39c35 |  | note | ACCEPTANCE CRITERIA: (March/June 2019)
label | 7d70c487-d041-41bf-85d0-0f211897c5ac |  | note | Attach: Survey As-builts / Survey Report
label | 1c1fd7db-9e1c-4464-8b75-e443f2bb721f |  | note | ---------------------------------
label | 2639b90d-cf07-476f-91e6-5434da2aae5a |  | note | METHOD: Measure, Visual
label | 62b27a27-1348-47f7-b09c-092b1b22877b |  | note | ---------------------------------
label | 50784edb-663d-4881-b85d-d818ad8e853c |  | note | FREQUENCY: Where applicable, each bearing location
label | 29e9e421-2ccc-4e2f-aa2e-9f458ac9300b |  | note | ---------------------------------
label | 87c24a83-0685-4caf-bb8e-9d30c7650dda |  | note | CATEGORY: IP
label | a322f0d9-5fdd-4c3d-b8a5-8153daffdb47 |  | note | ---------------------------------
label | 5f28b67a-a907-4d17-85c1-a8cd965eecc3 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 3062564c-cd34-4fff-bfe7-6f47c49fb530 |  | note | ---------------------------------
label | d526174c-58e2-4bed-ac5f-933c2eae575b |  | note | VERIFYING DOCUMENTS: This ITP
text | f886cc60-032f-4e45-8a3a-c5aeb32b483f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | a46fdc35-bd42-41d7-a55c-30756a41745c |  | note | REFERENCE: MRPA Quality Management Plan
label | 031e2efb-7436-4710-be2f-5152df035ea9 |  | note | ---------------------------------
label | 1e7b9776-691e-41ae-92e1-984a616fc789 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | bd5ff4ae-723a-42cf-b9da-b0c13f71e12b |  | note | ---------------------------------
label | 7496a464-6d8d-42de-9345-3514efd299a2 |  | note | METHOD: Document Review
label | 42131a6b-f638-444f-ad7b-af56d8bce328 |  | note | ---------------------------------
label | 06b4bfab-34c6-42c3-9389-5d8e36c885a6 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 88cbc5b4-9309-4b14-bc08-cb4d92a15d00 |  | note | ---------------------------------
label | 1cf2f0bd-7e4c-486b-acd8-d678d086b55c |  | note | CATEGORY: HP*
label | 2b9e17cf-ae27-4ce9-8fa8-5b2027cdce7b |  | note | ---------------------------------
label | 638ff192-8e81-49eb-b7bb-7b0d2c398dfc |  | note | RESPONSIBILITY: SE/PE/SPE
label | 533dfda9-cebf-4ca6-8b45-8398e8f4f790 |  | note | ---------------------------------
label | 754eacdd-0d09-43f0-965f-8144bb6d1c65 |  | note | VERIFYING DOCUMENTS: This ITP
text | fba40602-adf4-48f6-911e-781168a12582 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 3b7593e9-a831-4abd-a23f-d417b0fddcb3 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 18a389cd-3aa4-4002-8080-d5fcc3b31deb |  | textbox | Name:
text | 3304468e-26d9-4736-b35b-6961a306f7d3 |  | textbox | Position:
text | f65a6f28-d5e1-47dd-bc80-23a33ed4d962 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Pits & Conduits - V-Line (Supply & Installation) Rev 1 | itp |  |  |  | Yes | ITP-CIV-Pits & Conduits - V-Line (Supply & Installation) Rev 1 | da396eb6-b592-4bad-97b7-21fb83fb0e2f
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | e41f7184-2e7d-4f8b-92eb-f97e4be23c40 |  | note | Document Title: ITP-CIV Pits & Conduits - V-Line (Supply & Installation)
label | 396b8a47-341f-4854-a6a2-12a7f9a25b0b |  | note | ITP Description: Pits & Conduits - V-Line (Supply & Installation)
label | 1d8d5227-2b68-4302-a6dd-af67efe000b5 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 93623c56-ed2b-4b86-85cd-aaf59bc53235 |  | note | Revision Number: 1
label | b2e77acd-0fc5-4ba9-9c2b-ab16a5917ee6 |  | note | Revision Date: 26/04/21
label | 75cfe026-1169-42af-a9c8-cc16e15c9257 |  | note | ITP created by: Michael Daly
label | efe43dd4-1e41-4312-a781-a5029a40d637 |  | note | ITP approved for use by: Josie Pavlou
label | bd3937c9-3bf3-44b6-8f31-6364437e251b |  | note | 1.1 IFC Drawings
label | c392f232-bd26-4e54-8096-839e65e7f1e4 |  | note | NIST 012.2
label | ac727707-2e8c-402e-8c67-549b09b33c60 |  | note | NIST 012.2.1
label | 0f88190a-118c-4ebe-a62c-0ea1833adbbf |  | note | Australian Standards
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Conduits
label | 23bfbc0a-2836-4a46-9e8b-3f2462833c13 |  | note | REFERENCE: HV Conduit: AS 2053
label | 3314cada-70e1-466a-b19f-c59ddea11b89 |  | note | HV Conduit (boring): AS 4130
label | ba6bae6b-77f2-46d0-b1bb-02ba0d0061ce |  | note | Comms Conduit: AS/ACIF S008:2006
label | 7b94c62b-dc5a-4e9b-bb5a-622813f07bd1 |  | note | LV Conduit: AS/NZS 3000 - 2000.
label | fed6d4ec-7c35-465a-86b5-4a5568390fce |  | note | NIST 012.2
label | 01b75df8-aef6-41eb-ab8e-b8efefd43b02 |  | note | NIST 012.2.1
label | 3776b8af-9be4-47d4-b26e-45b63dd42dc0 |  | note | ACCEPTANCE CRITERIA: 22kV Conduits: 150Ø (160mm OD), orange electrical heavy duty 8.8mm wall thickness, greater than 1.65x cable diameter for single cable
label | f57216b5-2886-4a00-aff2-d5ce297dc860 |  | note | Comms Conduits: 100Ø (114mm OD), PVC White comms conduit 4.6mm wall thickness
label | c23d07b6-2766-4ba7-9753-62a7da4d402a |  | note | LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | cd465f4b-8c1c-4047-a91a-1aafaeeadc23 |  | note | LV & comms conduits to have a min. 600mm bending radius
label | d408c316-b9a2-4310-9f3a-f2449fa22c30 |  | note | HV conduits to have a min. 2000mm bending radius
label | 7c026868-facd-4e74-acc7-c13f1ed33596 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | e043a620-5435-464a-a1a7-0e2601e41a50 |  | note | METHOD: Document Review
label | fa5dffe3-0b83-4f70-acff-f732bea697f6 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 641eaad3-5bd9-4c36-9de0-45f9608c2b71 |  | note | CATEGORY: IP
label | 7b2f7c37-d866-4355-8740-7479f4e30bac |  | note | RESPONSIBILITY: SE/PE
label | 36785d60-6ec6-4670-b8a4-83f6c04fceae |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
text | 9d5deb4f-a4ac-45a1-8fef-d9df413e2f7d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Pits and Pit Lids
label | 89ee0e29-0109-40e5-83e4-e6eec7d6580d |  | note | REFERENCE: IFC Drawings
label | f7d8cd8c-7815-40b8-a5c6-b2f644e8cee4 |  | note | NIST
label | 4e8f5094-445d-4dc1-9608-8fdadf5c2d80 |  | note | 012.2.1 Section
label | ccc933d5-6d43-4e39-8580-7694e5edecc5 |  | note | 6.15-16
label | a767c262-a5d4-4545-b753-37979afe6e11 |  | note | NIST 012.2.1 Section 6.9
label | 829aff51-87b8-4d2f-a39d-9cdb9c0ec537 |  | note | NIST 012.2.1 Cl.
label | 5215de08-f40a-4c02-82d4-f071415d5871 |  | note | 6.7 (c)
label | 70b50f9e-353d-4006-8f50-ae8d213c9556 |  | note | AS1289
label | 70011c94-f6f2-4325-9096-2ea4c35efd44 |  | note | ACCEPTANCE CRITERIA: Pits: located within 1.5m of nearest rail, pit to be 300LA Railway loading
label | 0352c935-0ecf-4a7a-8ab3-12fadb1bf3a9 |  | note | Pits 900x900mm or greater, multipart pits lids to be used.
label | 7ce6be36-cc8d-4e92-a52e-86a74fa1e983 |  | note | Concrete Pits to be made as per AS 3600
label | 72adaf1d-8e03-4919-ae3d-4d7eb793d6c0 |  | note | Pit lids: Covers shall comply with AS3996-2006
label | d756764a-85af-45c9-bd3e-8d804a3763d8 |  | note | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | dfac5b89-81fb-451c-b46d-4c5971f0738b |  | note | HV Pit Cover: pit covers shall be labelled with the words “DANGER - Railway High Voltage” (L1-CHE-SPE-070 13.4)
label | 6382e073-a281-44c9-bd85-a3539ae158c4 |  | note | LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | dc869616-60cf-455b-ade3-b90f3f3160cf |  | note | Inspect materials upon delivery and attached delivery dockets.
label | e10b2ccf-34c6-41d6-93ed-68e0809e8112 |  | note | METHOD: Document Review
label | 1ed40f3c-b870-42d8-9fce-685883ab5d7b |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 9464e792-30e2-4b50-b41e-2e7902fd80f4 |  | note | CATEGORY: IP
label | db148af4-ac18-4a39-b3f6-12eac1315978 |  | note | RESPONSIBILITY: SE/PE
label | bc811172-5c98-4363-98ef-2dfb99f668b7 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets , Attach Precast Birth Cert
text | a73316c9-cf0e-457f-85e9-a0e72d1de9fb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Warning/Marker Tape
label | de41f661-904d-4bb5-a97b-7fc551e44ff0 |  | note | REFERENCE: IFC Drawings
label | 2c88f87e-c35e-451f-a6c6-b9dc568ffbc6 |  | note | AS/NZ 2648.1
label | c31e32b2-147a-4ee5-b361-ca14c6d0bff6 |  | note | TS-SP-013
label | 0ddc128a-2787-4c6a-b740-e74541c6bee2 |  | note | L1-CHE-STD-043 6.4
label | a8a56caa-421b-4d67-90ad-32176ee0aaaf |  | note | ACCEPTANCE CRITERIA: Warning/Marker Tape:
label | 1495b5d9-8722-4917-8e4a-dd46da042119 |  | note | Above LV: 150mm minimum wide orange coloured PVC
label | 462fd5d3-9dcf-46f0-a51c-b8d00232cd9e |  | note | ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 734dd97e-8634-4812-909b-21f8f38d4a25 |  | note | Above Comms: 75mm minimum wide white coloured PVC
label | 25db3de8-1a8e-4f50-a247-9d897d6dbf3f |  | note | ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
label | 9893dbb5-7e29-469b-b54d-9f0463bb98ff |  | note | Above HV: 300mm minimum width orange coloured PVC 'Danger - Electrical Cable Below'
label | 570a8f44-ad29-498b-8294-2aa351b97566 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 42d2a336-0665-40d0-b6bc-92cdf6cc4c17 |  | note | METHOD: Document Review
label | 4ad849a3-f697-41d0-b594-31cd1fc5519f |  | note | FREQUENCY: Each Material Type, Each Delivery
label | b3ae2562-626b-4f33-bcda-36d95fc45c7f |  | note | CATEGORY: IP
label | ddc7ad9b-7455-4a94-af8f-f3e3d75367e6 |  | note | RESPONSIBILITY: SE/PE
label | 27cbd160-a21f-416c-a6c0-c9ad172507d4 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets , Attach Precast Birth Cert
text | da81c633-0442-4d7c-b5ba-862b71d958f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Protection Barriers
label | 2147606e-b55f-47db-b849-95ce127dbecf |  | note | REFERENCE: IFC Drawings
label | 2a2ca921-4805-4f3b-88d1-57326ec334b7 |  | note | NIST 012.2
label | f1bce9e3-db39-4e43-abf7-5af99825a9e0 |  | note | NIST 012.2.1
label | 192d0c55-bd0f-4fb4-80ed-67f3564af078 |  | note | AS4702
label | 45844938-d586-4f8f-a11e-13f488a9fdc2 |  | note | ACCEPTANCE CRITERIA: Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
label | c790d09b-a9a2-4cfd-a33a-c2ebe685b045 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 51291e77-270d-4a9d-8bc4-1140f82e64a3 |  | note | METHOD: Document Review
label | d1e91d63-76e1-4501-9df8-7d4ac2aeea2a |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 97d1353c-32e3-49db-b334-2d448c42b183 |  | note | CATEGORY: IP
label | 0dc44a96-2e94-47dd-ad19-e1ecb55063a3 |  | note | RESPONSIBILITY: SE/PE
label | 5703e82c-b827-4f2f-b14d-3f121e9397f0 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
text | 6f75dd19-d7c1-4284-9793-c8f8cd133816 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Backfill Material
label | bcd17a72-12ae-4ccf-872d-4a3609829344 |  | note | REFERENCE: IFC Drawings
label | 89bb1a4e-a756-418c-9e18-9ab6243fc451 |  | note | NIST 012.2
label | 7ac397c2-e5a6-4dfd-9024-b5a3062f121e |  | note | NIST 012.2.1 Section 2 Table 1
label | c319573f-5865-4ed4-bac4-8636fe3b2877 |  | note | ACCEPTANCE CRITERIA: Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could damage the conduits.
label | 1213ddba-ebc8-4173-b82e-df46d9478dcc |  | note | Inspect backfill material.
label | 7d82396f-419f-4cb0-9028-dbbb756e9303 |  | note | Attached delivery dockets (if applicable).
label | 0834fc5a-1d9d-46a2-b0dd-fcdc35e96d43 |  | note | METHOD: Document Review
label | 96c5fe01-5c72-431c-a68f-9b9bfee45dad |  | note | FREQUENCY: Each Material Type, Each Delivery
label | ff7df895-655d-473c-968c-09b60f13ffa5 |  | note | CATEGORY: IP
label | d8d4e58b-7947-41ec-9cc9-64706789d523 |  | note | RESPONSIBILITY: SE/PE
label | d7b1d41d-f7fa-425c-9b7b-77b7a08a1545 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets (if applicable)
text | 7223c796-a9cb-4397-813e-5d0ee69005fa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Bedding Material
label | b1bd1e89-5115-472c-a923-4d7637bdcca6 |  | note | REFERENCE: IFC Drawings
label | c44c84b7-fb9d-4a9f-a1a0-0337e5b277b8 |  | note | AS2758.1
label | 27d69fb3-284c-45ae-897c-7e4db2024626 |  | note | ACCEPTANCE CRITERIA: Bedding Sand shall be a clean sand and/or Crusher Dust that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
label | 37858d8d-56e6-49f9-8d5c-41a003fd2c1e |  | note | METHOD: Document Review
label | 8824cf19-cd28-4848-8006-4f54b8f6b63e |  | note | FREQUENCY: Each Material Type, Each Delivery
label | f497bb1a-555c-4f8c-9649-319003eead67 |  | note | CATEGORY: IP
label | 0cbd1802-b5e2-47d8-993a-f90fa4569748 |  | note | RESPONSIBILITY: SE/PE
label | 042b5695-88c3-446b-9805-e846200511c3 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
text | f04b1e54-7736-4010-8861-80e1ccf4f0eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Draw Wirer
label | 1fe19a24-561b-40ce-beea-d60ecc543985 |  | note | REFERENCE: TS-SP-013
label | 0d63971a-c306-4272-93eb-bc5dc679b8b6 |  | note | AS 4142
label | de048a50-d098-40bd-b73a-42c66fcd3d8a |  | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
label | f0c23281-978a-4cde-b931-5ce464e3f36f |  | note | METHOD: Document Review
label | f15e4884-5541-417e-9204-897f3a36c167 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 2656a63e-c30f-45e9-92a6-887d690d6a4a |  | note | CATEGORY: IP
label | 6e59f149-2180-4e6c-bbc8-4a98107e761b |  | note | RESPONSIBILITY: SE/PE
label | 3b40e3ad-beb2-4b5a-8cb8-ebd248046075 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
text | 39c2f988-5e1f-4392-8c54-71fdf8dd1ddd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Concrete Mix - Trench
label | c3cb281b-9e44-49b5-8228-dc8c7b1d35fd |  | note | REFERENCE: NIST 012.2
label | e7a99f91-f30b-4cdc-8f9f-2b95b6ebd789 |  | note | NIST 012.2.1
label | b9efd187-c2e3-4def-857c-7bde5868a37e |  | note | ACCEPTANCE CRITERIA: Concrete strength at 28 days shall be not less than 25MPa.
label | bda25d6f-e6d6-4fcc-876a-7233d3ff8129 |  | note | Chemical admixtures or fly ash shall not be used
label | 481e09c0-447f-4829-95c5-acfeec8290b9 |  | note | METHOD: Document Review
label | 051824b7-9dbf-4f4b-8f82-cd4fae646b6c |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 0544e265-3770-48bb-8797-c8b03b85740d |  | note | CATEGORY: IP
label | 60dcd84c-71d3-49de-ad75-6fdd07a36a28 |  | note | RESPONSIBILITY: SE/PE
label | ee6c3628-7b1a-4270-9793-e3eebb7710d7 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
text | ac8887ff-f41f-4352-8d85-001d993e488b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 Markers and Marker Posts
label | d5882551-b22f-45d5-aac0-e55b8c743675 |  | note | REFERENCE: NIST 012.2
label | 06523b00-8c1c-42e6-83a1-6752a6581f01 |  | note | NIST 012.2.1 Cl13.2
label | 51591dcd-8946-4e8f-a1c2-b939d9d3f308 |  | note | AS 4799
label | 3f433f67-c258-475b-95a2-9ece2df69e47 |  | note | ACCEPTANCE CRITERIA: Markers and Marker Posts are to be manufactured in accordance with AS4799.
label | e877e2b5-1ff3-41f5-a885-5649e6633623 |  | note | METHOD: Document Review
label | 06a59b40-712f-4258-8510-adaf27757227 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 43b7ad10-551a-4bb4-b04e-6b9a07bee4a2 |  | note | CATEGORY: IP
label | c5ea8c5f-ff39-4214-8caf-7daca80430e7 |  | note | RESPONSIBILITY: SE/PE
label | b6a5f526-24a3-4bf4-835b-2883a0eb1921 |  | note | VERIFYING DOCUMENTS: Attach Material Conformance Certs, include TB Approval No. , Attach delivery dockets
text | 039247c8-5c90-4489-8084-571785e0bb04 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | a55ff193-1d8e-401f-b741-d6ced1f9a8c0 |  | note | REFERENCE: IFC Drawings
label | 49cbc8d0-baf5-42d2-9c5f-26e17b92d0d9 |  | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | 2d8979c8-b0cb-4eff-824a-b4dd15f77f60 |  | note | METHOD: Measure , Visual
label | 87d477b7-ed44-48d1-8075-e6252f07bd6b |  | note | FREQUENCY: Each element
label | 177199a4-04d5-4939-9887-73b3b3ada94b |  | note | CATEGORY: IP
label | dbc3b158-60a3-4783-9524-e1c4588340d1 |  | note | RESPONSIBILITY: Surveyor , SE/Site Supervisor
label | 1d2210ab-d029-4e29-a732-7b219a20e8d1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 13c04529-d8be-4d81-999f-05328d5cbe52 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Permits
checkpoint-status |  |  | checkpoint | 4.1 Services
label | 45738035-d281-41e2-8184-82e9715890a0 |  | note | REFERENCE: Services CAD file
label | 00824d1c-195b-4d1f-96f1-836034eddb06 |  | note | ACCEPTANCE CRITERIA: All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
label | 9fb65a50-989a-4db4-b0b7-6ab5c3ac233a |  | note | Survey to mark out existing services.
label | 70c6ff84-f543-46ee-a52f-2b85d2ce8d94 |  | note | METHOD: Visual
label | c94eb207-b2c9-48cf-aa0d-27c8b5afd15d |  | note | FREQUENCY: Prior to commencement of works
label | 3c580d5f-2a3b-4e8c-9621-bfd453f8cd62 |  | note | CATEGORY: IP
label | 5eebbb38-f1d7-48e3-be70-3f6cbff16b7e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 9af205d5-69cd-48ae-8737-3823e543a953 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | efc9d016-e279-4939-a808-638498ccf57f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Excavation Permit
label | b676a942-e43f-424c-b77a-488ca094fc00 |  | note | REFERENCE: MRPA Excavation Permit
label | bc57515d-7dbb-41eb-b4f9-988385f810f3 |  | note | Ground Penetration Permit
label | 4b68b925-e924-4f6a-ba44-ca2f0138b87f |  | note | V/Line SAP
label | 2cc7eaaf-8ca2-4d48-8b0f-015c191e9c33 |  | note | ACCEPTANCE CRITERIA: Insert Permit No.
label | 855348bf-b46f-40c2-99ec-1202eaef7f2d |  | note | METHOD: Document Review
label | 53bc7e5d-b87d-4087-99e2-ecbf0fa95dc0 |  | note | FREQUENCY: Prior to commencement of works
label | 011727a5-33a1-47e0-8a16-4dab51d6dc5e |  | note | CATEGORY: IP
label | 093275c8-2d9d-49e2-a9c2-8136373d595f |  | note | RESPONSIBILITY: SE/PE
label | 75828901-5339-4fc2-8292-60734adadeb4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | f4b7a98b-6097-4ccd-9e6b-4994aa0294e8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 VicTrack PTW (if applicable)
label | d7a4c936-f4e5-4122-8ff9-86089fbd4312 |  | note | REFERENCE: MRPA Excavation Permit
label | 47fc7c22-295d-4770-ad07-b1aa75a3dfe8 |  | note | VicTrack PTW
label | e9c02cbf-57a0-4f40-8a30-427581aa63bb |  | note | ACCEPTANCE CRITERIA: Insert Permit No.
label | 17cc0df5-23da-430a-8b8c-9656ecadce62 |  | note | METHOD: Document Review
label | 8ceb13c4-e365-468c-8954-5fee497a65b5 |  | note | FREQUENCY: Prior to commencement of works
label | 65b27990-5de0-4391-a231-9f20f3976451 |  | note | CATEGORY: IP
label | 0cc3ea80-91ad-4373-b7b3-85a8596d501b |  | note | RESPONSIBILITY: SE/PE
label | 5eefdc7f-5ea0-4496-89ae-fa1956d6e240 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 757c1840-2791-48fe-8a5d-91bb2a81ff34 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 V/Line SAP (& Monitoring Regime)
label | 14431445-4275-4c5f-944e-b959e86b8b0b |  | note | ACCEPTANCE CRITERIA: Insert Permit No. or Notification Email
label | 90934e7b-744d-4223-b0ea-9ace36de5b8e |  | note | METHOD: Document Review
label | d50fbd15-9b34-4df0-b20f-a0b655ee4b69 |  | note | FREQUENCY: Prior to commencement of works
label | 3e08cb46-04ce-4a2a-8b3c-6bfab62cbc1c |  | note | CATEGORY: IP
label | a584b8e4-f69f-4877-814a-f99c6eec91c8 |  | note | RESPONSIBILITY: SE/PE
label | 42912388-c679-425b-aebd-1d394075e1f9 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 7f68ad29-ac5a-4519-b25d-956f10394118 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Excavation Activities
checkpoint-status |  |  | checkpoint | 5.1 Trench Excavation
label | 5e494f03-a309-4f4c-bca2-796bfe182a83 |  | note | REFERENCE: IFC Drawings
label | aef4e26f-84aa-4d03-9032-79c525dffc21 |  | note | NIST 012.2
label | e4b21b0e-6cfe-4097-b6ba-351bc48b1f35 |  | note | NIST 012.2.1 Cl7.1c
label | 87887441-279c-4d5e-89b2-a4e07242cf2c |  | note | NIST-2659 Cl6.3.3
label | c2bf3bac-184e-49c2-a47c-e7c0292df8b6 |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | 5ddd2a42-e9ac-4ea8-83b3-8603bbaa8607 |  | note | Edge of trenching to be a min. 2m from structures/pile foundation (unless it is mounting the structure) and a min. 4m from edge of rail for LV, HV & Comms
label | 9c1f2b0c-e314-4825-8615-61f4f0d2d70f |  | note | The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
label | 968335f4-4e51-4abf-8f3d-c460fb798a37 |  | note | The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 10850fdb-48e6-43c6-9651-054407a3faeb |  | note | Level and compact base making sure no low points exist. Soft earth should be replaced with a suitable fill material.
label | b8725b6e-7a1d-4897-8959-6700b60a22e6 |  | note | METHOD: Measure, Visual
label | bf343bcb-b0b8-4779-9a45-1b2c2e66efaa |  | note | FREQUENCY: Each lot
label | 924f4d4c-5527-4422-8ec5-ab0e22a3a8c0 |  | note | CATEGORY: IP
label | 71c3e960-4323-490c-a206-7ce54e7d3076 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 14a5968e-fb99-42c3-9bb9-859f7588dd8a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 15378231-9a88-48ac-9b88-8eba653995af |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Trench Stability
label | c60dc44b-4a5a-4d57-b84e-d3043a7e6b90 |  | note | REFERENCE: NIST 012.2
label | 928e7c37-92aa-419b-b4fb-6fca826f9cf7 |  | note | NIST 012.2.1
label | cd1c5548-78b9-4684-80d4-357f20c6d7ba |  | note | IFC Drawings
label | 1662f7d8-b8e7-4c1d-bd96-ea921ab6d942 |  | note | MRPA standards
label | 7f736d73-a612-4632-81ac-0a9a68aa47f0 |  | note | ACCEPTANCE CRITERIA: Trench stability check:
label | 329047b7-2a99-4c0c-9341-9fb86f11bbed |  | note | Shoring,
label | 1aed3396-91b6-4de1-9811-c84222d7d6f7 |  | note | benching
label | 5d39f7bd-8ff3-4dc8-b8db-7e4b414ae6e2 |  | note | Geotech signoff
label | 6a13724b-c694-4b34-b760-e82f5bd996d8 |  | note | METHOD: Visual, Document Review
label | bba555ff-a9c9-42b8-8f4a-810d01ac9782 |  | note | FREQUENCY: Each lot
label | caa04300-ae91-423d-809a-4c6ae0ea627d |  | note | CATEGORY: IP
label | dc6b9e63-8cb7-4c08-ad0f-83cf3aa51555 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 001aa2e3-7673-467d-a3c6-2ed2fe74aa99 |  | note | VERIFYING DOCUMENTS: Sign ITP, Attached Geotech Report
text | 77b37abc-ed1f-426c-b388-1a2560f90fd2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 ULX Trench Excavation
label | 72e47914-58f9-4cbe-865f-85fe2b11d888 |  | note | REFERENCE: NIST 012.2
label | b86af846-a13d-4825-a441-f824c88a34ee |  | note | NIST 012.2.1
label | f0a25601-45f5-4692-8cef-40f5fe975309 |  | note | IFC Drawings
label | 2d4a7b00-4684-4bc0-972d-9c44411c5fd3 |  | note | TS-SP 013 Cl7.3.1
label | b84b8264-2bdb-48d7-a9b9-392d59ec292c |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | 2da13690-6c53-4952-b5c9-8bb1c63e1ac0 |  | note | Trench alignment to be perpendicular to the tracks and extend 3m past the edge of rail on both sides of track.
label | ec485b91-4400-4ba7-af34-13d34f5c8189 |  | note | Top of conduits to be 1.2m below top of rail.
label | e72ca423-8dfc-486e-b4f9-53a6acb1e908 |  | note | METHOD: Measure, Visual
label | 36064cd1-9fc4-424b-b437-05970b49cb0c |  | note | FREQUENCY: Each lot
label | 0099e0fb-e97b-4d25-a529-c7b2f7d4715d |  | note | CATEGORY: IP
label | 4d6ba660-ff7e-4e66-a04f-1155847922e2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | eb323020-27e7-4f54-832c-c436cc45bfcc |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ade710be-24ef-460d-9808-0730ab4b4a13 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Conduit Placement
checkpoint-status |  |  | checkpoint | 6.1 Bedding Sand
label | ed6a54c9-c890-414c-9449-95a16842bc73 |  | note | REFERENCE: NIST 012.2
label | dbf96bb3-f556-4b7a-bd6d-ba9667fa6cf2 |  | note | NIST 012.2.1
label | 0c65aec2-18fb-4292-be32-f82c574f79d9 |  | note | IFC Drawings
label | 17629cd6-f8d2-46ae-8082-3bbb24efa190 |  | note | TS-SP 013 Cl7.3.1
label | e3137343-1fb7-4440-90e6-5fdb339c3f38 |  | note | ACCEPTANCE CRITERIA: 100mm of bedding sand/crusher dust to be places at the base of trench.
label | 544dc319-0079-4be1-9d2e-e85a05f2f2fb |  | note | METHOD: Measure, Visual
label | 65ff79b5-5d8e-4c7c-b7cc-05c02a87e6f2 |  | note | FREQUENCY: Each lot
label | 5153db19-2911-4d47-8b70-523ebf7f7393 |  | note | CATEGORY: IP
label | 3cd68c55-48da-469e-9da2-c40a18c649ad |  | note | RESPONSIBILITY: SE/Site Supervisor
label | a2e53ee6-25d1-42c1-9f5c-205ad7d6e10a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | f93d618a-2fa8-4906-a217-7ebfdf7c352b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Conduit Configuration
label | 9fd237e5-15db-4029-becb-fb2312fd274d |  | note | REFERENCE: NIST 012.2
label | c3eb2709-bace-43f6-856d-dcaee4faa6d4 |  | note | NIST 012.2.1
label | 487361b8-7ce6-4f7b-a8cf-255af6d4a0bc |  | note | IFC Drawings
label | 7a71341e-cdca-496a-972a-1fe1c545e3b9 |  | note | NIST 012.2 Cl7.3(f)
label | 96cac7ae-69fa-4c25-be45-a48f2024461c |  | note | TS-SP 013
label | 8ab98420-8788-48f0-9cf7-2051f9cfe1a6 |  | note | ACCEPTANCE CRITERIA: Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | b9c92e5d-7bf5-4eae-96f8-28611b050b8a |  | note | Min Cover
label | 6116798b-9e97-4b5d-b4cb-d8356d7818da |  | note | HV: 1000mm
label | a1edd39e-4b73-4d55-91ee-d2e4e2de396f |  | note | VicTrack: 650mm
label | 1d7e7ff7-a95a-4ffa-ad21-ed53f014c515 |  | note | Signalling: 800mm
label | 0ffe8c76-c3d2-4a25-b425-572367b02b1a |  | note | LV: 800mm
label | bf4701a1-f3c1-4314-a838-2ecb6ff8ca19 |  | note | Electrolysis: 800mm
label | 9ef5deaf-4721-4cbc-b9c0-12939a7a76d1 |  | note | SCADA: 800mm
label | 539e283c-9c61-42a7-a70b-da3a6b04fadb |  | note | Where Water Courses encounted: No less than 1000mm below water course. Conduits shall be covered to a minimum depth of 300mm with porous bags filled with stabilised sand and the remainder of the trench then filled to the top with approved heavy grade fill (vline req.)
label | 6e8c8cd2-4348-4274-b897-0c3ca3a72134 |  | note | 1200mm Under VicRoads Roads & top of Rail
label | 6bb72222-231b-4408-ad24-bc559addcfa1 |  | note | 900mm below council roads
label | 95db045f-0cf6-4afa-90ac-87879a72582c |  | note | METHOD: Measure, Visual
label | 74ba2908-dd09-498b-aabe-163b128184e5 |  | note | FREQUENCY: Each lot
label | 8dd8ec4f-d80b-4b14-984f-722886bcc38f |  | note | CATEGORY: IP
label | eca2caff-a1cf-4fc2-9ba4-3719be19ea23 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f58a249f-f6a2-4586-9741-7347aebd963a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 0e471b48-8067-4758-a3f5-c1336cfeb7d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Separation of Services
label | af98ad75-3b48-4726-b910-81afd00b7272 |  | note | REFERENCE: NIST 012.2
label | 301645ef-c703-42f8-beac-56d22afc5d4c |  | note | NIST 012.2.1
label | 8702ad89-24d4-4e25-bc78-5d33296226fe |  | note | IFC Drawings
label | c2548dcd-8153-4d65-acae-84754bfb073d |  | note | ACCEPTANCE CRITERIA: Separation of services
label | e96408e4-e37a-44d9-8574-4cc6c61313b3 |  | note | HV: Min. separation distance between HV conduits at least 50mm
label | abcb64c2-eb8c-4f21-b3b0-f9ac7d2a7676 |  | note | VicTrack: min 300mm from HV
label | c7d96f42-c6de-4737-adf0-17291a7b68f7 |  | note | Utility: 300mm to utilities
label | 378d8793-8829-4887-9839-89509d39574f |  | note | METHOD: Measure, Visual
label | 680cb3c4-35b7-498e-8e52-d841bdca0d21 |  | note | FREQUENCY: Each lot
label | 565717f4-8c80-472a-9b82-666d3c907d0d |  | note | CATEGORY: IP
label | 8d66fa60-e3e4-4ce1-bd47-6e00474320c7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 91627d09-f1f8-4445-b5e1-7ead1b389cec |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c41d83b6-20d4-4b16-85a7-b944421cbe6c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Joints
label | 7bf44024-1b46-4496-95c9-6cf40c111ed1 |  | note | REFERENCE: L1-CHE-SPE-070 (MTM)
label | b61c53a7-0b17-4bfa-bd18-4d78e6616294 |  | note | L1-CHE-STD-043 (MTM)
label | a3b5b401-bb8f-48a1-89bb-8295047c4895 |  | note | L1-CHE-STD-070 (MTM)
label | 0d04a54f-d785-45ed-a51e-49ce7b4591eb |  | note | IFC Drawings
label | acfad146-efbe-4405-8a5c-121ff230a434 |  | note | NIST 012.2 Cl7.12
label | 48f07e8e-46da-4283-bf12-feae88ce0b0b |  | note | TS-SP 013 Cl7.3.5
label | 5d1bc766-34df-40f0-9d7c-c263825accf3 |  | note | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigot;
label | e1feb276-6e81-4325-89ee-e3d70dca78d1 |  | note | The ends of the conduits, both spigot and socket shall then be coated for the full length of the spigot /socket with a conduit-manufacturer approved adhesive and connected together for the full length of the socket.
label | 9ad710c9-7a59-4be2-bd03-c68a28269f92 |  | note | Spigot type or bell mouth fittings shall be used on all conduits to ensure that cabling is not damaged during installation.
label | a805cffe-90d3-4d92-b64d-0b4d46324c20 |  | note | Internal spigots must not touch one another. All spigots must be flush to the pit wall.
label | 14a9bf90-508b-4d4e-bb6d-b3338c9e9fa7 |  | note | METHOD: Visual
label | 3c2fd0b9-5fb0-4538-abc5-0061eecd9e48 |  | note | FREQUENCY: Each Joint in each trench
label | 9a2d8fd3-6230-4005-b3a8-d68e94d4e57c |  | note | CATEGORY: IP
label | 5df17752-6bf6-47f3-beec-eadfda1e04d7 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | d5cf2ef1-2572-446c-abfb-12b0484e6a52 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 9e9ebc64-ac79-4d0a-ac32-f91a58fd00d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Conduit Inspection
label | 8e95d514-8725-4787-a64f-d263abb6dc2e |  | note | REFERENCE: NIST 012.2 Cl16
label | bd1205d9-4f20-4f4c-bd2a-7b0a46401a85 |  | note | TS-SP 013 Cl7.8
label | 94e953b4-88fe-4248-957d-9d140d2c9570 |  | note | ACCEPTANCE CRITERIA: Provision shall be made for inspection of cable routes by NA, V/Line/VicTrack representatives prior to backfilling.
label | 42bed759-842d-4a7f-b6ad-965808924ec9 |  | note | VicTrack will witness the first layer of backfilling of trenches with clean fill material, compacted to minimum 50mm above the top of the conduits.
label | 934d3dc2-27fb-4e72-ac23-4dc0e54e5f5e |  | note | METHOD: Visual
label | d7e75a4b-1e4d-404b-9aa5-df848fd9ee4c |  | note | FREQUENCY: Each lot
label | 9568c24a-fd1e-45c2-ae9c-5907abe02767 |  | note | CATEGORY: HP
label | d7a85952-b08c-48f9-9cef-2d78596accc3 |  | note | RESPONSIBILITY: SE, NA, V/Line/VicTrack Rep.
label | 46ba08d7-ba9f-4dbc-9458-09446fef1f64 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | da2586d4-cfdb-40eb-84cf-04105de32bc7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.6 Survey As Built
label | a4705820-8c76-4077-b3bd-3ac87fd32fdb |  | note | REFERENCE: NIST 012.2
label | aca8d735-21bc-439f-840c-d9e1f3b78de1 |  | note | NIST 012.2.1
label | 62677189-e53d-4d46-98d8-c4e19359d3d4 |  | note | IFC Drawings
label | 773557e6-76d3-4e2a-8fb9-c6b404a5792d |  | note | ACCEPTANCE CRITERIA: As-Built survey to be completed and recorded before backfill
label | e458fc1f-b9dd-4e8d-994f-f71d26ec8987 |  | note | Cable joint locations.
label | 2b29baaa-f598-42a8-a87b-12906429b694 |  | note | Cable pit locations (Corners)
label | 319486c9-c835-472a-8bea-eb5d30502ad0 |  | note | Pit dimensions & pit lid type
label | 55a4df86-cff1-42ed-b545-b9bce511cc49 |  | note | Under line crossings
label | ea99411a-d8bf-4848-b82e-10967923b026 |  | note | Under road crossings
label | e0cefcc6-53b5-4680-be8a-bef720ad517a |  | note | Changes of direction
label | f7fcc38f-2dba-454d-8136-121c3d7223eb |  | note | Spare Conduits
label | ae81b35d-f1ef-4aaa-a4e1-b87dabae9e68 |  | note | Conduits labelled as per trench profile
label | 2c43e659-44c0-44b7-8eeb-6d0ee4c38b8e |  | note | every 10m
label | 81c81da5-5769-43c9-861d-9f98e030f8ab |  | note | Other significant points of the cable route
label | 49632754-1f2f-46a6-821a-6053b59553d8 |  | note | METHOD: Measure
label | 2e533107-f832-463c-8dea-1ff3913b9344 |  | note | FREQUENCY: Each lot
label | faf37ae2-be58-495b-9ef8-6a049eff7ce1 |  | note | CATEGORY: WP
label | 82ee2c73-4c70-402a-a0e8-a8a5bb584b28 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2dea24e7-2b12-45d6-840b-4da05b6c9507 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6d69906f-cb63-4300-b5b5-b0d394d22507 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Bedding Sand Installation
label | d780eb16-177c-4880-8708-60e780af6826 |  | note | REFERENCE: NIST 012.2
label | 9ad830cd-7fa3-4634-9b21-512823b559c7 |  | note | NIST 012.2.1 CL13.1
label | c738a797-512b-46f8-a8b1-cbf71fcc0d3d |  | note | IFC Drawings
label | 46f10956-5f0a-44c4-9bf0-662095962998 |  | note | ACCEPTANCE CRITERIA: Bedding sand/crusher dust extends 100mm past edge of conduits.
label | 7fac4506-9218-4411-b561-af449228063f |  | note | Bedding sand/crusher dust extends 100mm above conduits.
label | b90854e9-dcf0-4b80-bbfa-18f256ed5f24 |  | note | Conduits shall be laid on a clean bed of sand 100mm thick
label | 719c12e3-925c-405e-ab7a-e2d7ef80fcda |  | note | METHOD: Visual
label | c799cc4c-c72a-47f7-bc26-bb3861a71702 |  | note | FREQUENCY: Each lot
label | 1a223b03-f0cf-42f2-a7ae-b30c50b40ef4 |  | note | CATEGORY: IP
label | 0aa190c3-2a32-482e-8a74-b43725450779 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cb754180-c61c-414c-abfa-de3e100f16cf |  | note | VERIFYING DOCUMENTS: Sign ITP , Attach Delivery Dockets
text | 9bb5f168-0f5f-4b0f-883e-8e3140def16a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 HV Protection Barriers
label | 233a8f44-c81a-4f02-8bf3-e980ae1789df |  | note | REFERENCE: L1-CHE-SPE-070 Cl10.3.3
label | 346c1019-a540-4381-a313-45e85e838849 |  | note | ACCEPTANCE CRITERIA: Top of HV Protection barriers installed 150mm above and 50mm beyond vertical line of any HV conduits
label | 6d73a3aa-376e-4e7a-955e-4b699652dd8e |  | note | METHOD: Visual
label | dabb8d46-d54f-40f2-a295-266b4308ebfd |  | note | FREQUENCY: Each lot
label | 8b2910c0-09c5-47e2-a7e9-8ec1096a33c3 |  | note | CATEGORY: IP
label | c62847e3-b6bb-4017-a5d7-638f5ebc77ec |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 832fd556-b38f-4ac4-9d8c-9f208d17a045 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 2a7dd8e0-af76-4524-a1c1-dd450e0c1847 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Marker Tape
label | 5dd74616-2289-46c1-8852-99cfba7abb15 |  | note | REFERENCE: NIST 012.2
label | c9c015c7-1bf9-4ddb-aeff-16a0be3feab1 |  | note | NIST 012.2.1 Cl10.3.3
label | e43a963a-2f0e-491f-9da3-80389c4221c9 |  | note | ACCEPTANCE CRITERIA: Warning Tape installed a min. 300mm from FSL.
label | 3682daf4-d6a7-4886-ba0e-3c179e84e7f8 |  | note | Tape to be one continuous length.
label | aac8ec6d-3e88-4ee5-9a8d-59a885e327ae |  | note | VicTrack to inspect the Marker Tape placement..
label | 6359c8fc-3168-4cc8-b823-f8efe9a6d2a6 |  | note | METHOD: Visual
label | 0e38bf0b-8820-4d19-8be8-8dc9a42de5a7 |  | note | FREQUENCY: Each lot
label | 40646308-7c95-46e9-8ee1-df631dabf7cf |  | note | CATEGORY: HP
label | 45201f76-8ebc-45d8-9294-4e17abe8faf5 |  | note | RESPONSIBILITY: SE, NA, VicTrack Rep.
label | 786bd856-e48c-4d2e-a8b7-ee26fb578052 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 44061ab8-e6ed-4e97-a2e2-60b9511b44a2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.10 Backfill Installation
label | 6552288a-feba-4e02-a43b-c2b7d1359992 |  | note | REFERENCE: IFC Drawings
label | 47dfb5b3-a5e6-4cb9-b0fa-69e164bebc31 |  | note | NIST 012.2
label | 8b4e8d8d-a279-4c73-b0ba-d2fc48efd708 |  | note | NIST 012.2.1 clauses 6.15 and 6.16 and 6.5
label | 6d3d0821-92b1-4002-84b5-2f83a79add09 |  | note | ACCEPTANCE CRITERIA: Backfill per trench profile
label | 7491ab54-bf17-4ca3-9d28-13bccb471e6a |  | note | 150mm layers
label | f6cfb5a9-5c2e-4018-8407-8c0740a16aca |  | note | CBR >3% for existing material to be used
label | d1c962bd-3682-44b5-97ef-843ab83e37d2 |  | note | 95% compaction
label | eae9ba5c-6896-4076-8f78-c16581c4a76a |  | note | conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
label | 1d498a9d-65fa-4229-8de6-97e2807471f2 |  | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | e518e532-9a04-4e49-a446-6fde756bea16 |  | note | Trenches under road pavement - backfill to be same material as the road formation material.
label | 7a6ca838-8559-49a1-a733-49aa4ed434f2 |  | note | Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
label | aba5d36c-1d51-4b6f-a847-6c982dbe221e |  | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
label | 24bfdb5f-db9d-4679-82ee-47ff37ac42d8 |  | note | VicTrack to be notified and witness the first layer of backfilling.
label | 000246d0-0f49-45bb-bf18-546af8cb0ba7 |  | note | The final 150mm of fill of trenches in rock areas shall be stabilised sand, or concrete (minimum 25Mpa) if in vehicle access roads.
label | 5a1d71b6-d828-4a86-a64e-6e7b39f1f5c4 |  | note | METHOD: Visual
label | 39b26aa4-65ea-45d7-8a40-0c78df3f9826 |  | note | FREQUENCY: Each lot
label | cad1162d-fa40-4634-b841-e3f509b2dbef |  | note | CATEGORY: HP for first layer only, IP for the rest.
label | 6545489f-9bc2-4200-9547-b5f00b2ec7e6 |  | note | RESPONSIBILITY: SE/Site Supervisor/NA/VicTrack Rep
label | 76f30f69-c2f5-4f36-93ea-97c282598148 |  | note | VERIFYING DOCUMENTS: Sign ITP , Attached Delivery Dockets
text | 9cd26cce-fef5-4296-bcd0-df5005b5c5b6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.11 Compaction Testing
label | 8f4cf778-634d-4212-a166-d6d74ae53a8d |  | note | REFERENCE: NIST 012.2
label | ae527268-f464-4e2c-a5cc-c051c09deaa0 |  | note | NIST 012.2.1 clauses 6.16
label | e2d6ba93-e0be-49f7-8583-dd797e13edca |  | note | AS3798 Cl 5.2 table 5.1
label | 9e0532bd-e126-467d-90ac-7230ba4473c8 |  | note | ACCEPTANCE CRITERIA: Compaction to achieve 95% Standard Compaction using an approved Mechanical Vibrator.
label | 45cc4cb1-0807-4d5c-b939-86032b47f65e |  | note | Under no circumstances is the cable trench to be compacted by driving excavating machinery or other vehicles along the trench.
label | c32f3443-7980-4268-97b0-51813079df64 |  | note | The tests shall be taken on a frequency of one (1) test per 200 linear metres per layer or one (1) test per area per layer where any area of excavation is less than 200 metres long.
label | 33453c5f-7070-411a-b735-4e0fde6ca9dd |  | note | METHOD: Document Review, Visual
label | c3619c80-3399-4a87-835f-f5317e840ddb |  | note | FREQUENCY: As Per L1-CHE-STD-043 6.16
label | 6c2e4e41-67ba-462b-91c2-0a5aceec4bdb |  | note | CATEGORY: IP
label | cf67d87e-047c-48fd-a568-d39695c8c6bb |  | note | RESPONSIBILITY: SE/PE
label | 12477f87-b5af-43ad-ba07-d7a458494f80 |  | note | VERIFYING DOCUMENTS: Sign ITP , Attached Test Report
text | edc74160-eb7d-480d-840e-828796537dea |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Location
checkpoint-status |  |  | checkpoint | 7.1 HV Pits
label | 3efa0466-442a-4e39-9580-391b21cf5e3e |  | note | REFERENCE: NIST 012.2
label | eb82fde8-4c86-47e7-9fa4-e72cbd122746 |  | note | NIST 012.2.1 (Cl 7.21c) CL9.2,9.3
label | cc183b54-f169-4fa4-8569-352f6cba824d |  | note | ACCEPTANCE CRITERIA: HV Pits intervals no greater than 400m
label | 5415f8b4-6431-4674-aff1-27f379eb39f8 |  | note | 3m from rail
label | 5b078365-1c13-45c6-afbd-dd0e230cbefe |  | note | Access Roads, Class D lids
label | 6c159667-e14f-40ba-85e3-f38881517ea1 |  | note | Footpaths and non traffic areas, Class C Lids
label | 49b96844-89f7-47e2-9d42-f51623128723 |  | note | Alignment of square pits parallel to property line
label | c3376f5d-4b9d-43b5-8958-c8e814ddad69 |  | note | Pit size as per L1-CHE-SPE-070_9.3.2
label | dfa3108e-35dc-4f23-b11b-bab0601df6c9 |  | note | METHOD: Visual
label | ab4d3ef2-e4f4-4600-be52-d044ede9552c |  | note | FREQUENCY: Each Pit
label | 697d82e7-c0df-499c-b19b-71e811281997 |  | note | CATEGORY: IP
label | 61cc844d-cc31-49fc-8e76-ea2ec9dc6f40 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f7b8c7a8-9be8-4a80-b509-e8438f5b7af4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 23ebd4d4-50a3-4b10-9087-fff680cfa6d5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.2 Sand Pits
label | 33a26724-d15f-4c42-bed6-60ffaf473bab |  | note | REFERENCE: NIST 012.2
label | 9e44568a-0b20-4b14-a89d-39e57af241b5 |  | note | NIST 012.2.1 (Cl 7.21c) CL9.2,9.3
label | 131c2c06-9b6f-47d9-a0fa-6ef2b37b341d |  | note | ACCEPTANCE CRITERIA: Min. clearances from:
label | 7fb6c402-2b45-430c-9481-4a84744da064 |  | note | 5000mm CLEAR OF VICTRACK ASSETS
label | cf4c28d5-5684-4b0a-867d-fd0cc5e230a3 |  | note | 2000mm CLEAR OF V/Line SERVICES
label | 2a5df54f-a6e3-4375-8f5c-c1662fceca44 |  | note | 3500mm FROM NEAREST RUNNING RAIL
label | 6236df3c-a3ad-4d2a-aaa9-8cd1af458fe1 |  | note | Sand pits shall not be used within paved areas and access ways
label | 4fc1bfb6-c354-4d95-a32d-c95e79435a6e |  | note | Not to be deeper than 1500mm
label | 8d73c611-b387-48b5-8b69-d2dd3f740c93 |  | note | METHOD: Visual
label | 254014fc-1b52-4486-957f-47cef59b56c5 |  | note | FREQUENCY: Each Pit
label | 7ce17764-b09b-407b-a8e8-88ca61c6409c |  | note | CATEGORY: IP
label | d8c42c6c-a5b3-4657-a1c2-267701b8a4f9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 04e9ff6a-28cc-4a7e-8900-cfbb5a16a0c9 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 8a4338f5-b426-4c90-bcc8-1b2506d28696 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.3 Vic Track Pits
label | dd5af289-2af1-40ac-8dcb-f75aff677b56 |  | note | REFERENCE: NIST 012.2
label | 7ba1b351-8bd3-4a8b-9a5b-dfd24e32fd90 |  | note | NIST 012.2.1
label | 0777bec2-8d02-4700-b4c6-f03bbd1d7bc4 |  | note | TS-SP-013 7.2.2.vi & 7.3.7
label | 7e628150-d52c-4548-a4ef-6e88871c5f6b |  | note | ACCEPTANCE CRITERIA: VicTrack Pits:
label | 57302754-9d1a-4c9e-85d6-17e52f152032 |  | note | intervals no greater than 380m
label | a806550a-2cd1-450e-9b53-f4eb45a7ac24 |  | note | no lateral deviations of conduit from the straight line between pits greater than 2 metres over the nominal 380 metre pit spacing not all at a single or several distinct points. If this cannot be achieved, then the pits need to be at a closer spacing;
label | bd063064-52aa-4042-8320-1a7558311ad2 |  | note | 4m from rail (if within 4m a physical barrier at 3m is required)
label | 04c80209-5a7d-472e-bf64-5d6d6b97548e |  | note | Access Roads, Class D lids
label | 519ecd5f-9d83-4298-b67c-ccc4363be6bb |  | note | Footpaths Class C Lids
label | 8c99da98-dde6-4f04-8140-5dfe15c8cfe0 |  | note | non trafficable areas Class A with bollards
label | d215d07d-43a3-45b7-b118-3ac20db6252c |  | note | conduits to enter from ends of rectangular pits
label | b82547c0-8027-4e9f-894f-4f2e9087edcc |  | note | METHOD: Visual
label | e995cddb-91d5-4648-a860-fc8e1180cd82 |  | note | FREQUENCY: Each Pit
label | 437b8530-c42d-4b14-8efe-4fc87d388a60 |  | note | CATEGORY: IP
label | d791f03f-64f1-442b-96c3-5e3dfb65ca96 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6e97f3d9-81a4-4aa2-9bf5-f579a8050993 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 8d50dffc-d1ce-488a-93d9-221fa4b64384 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.4 Signalling Pits; LV Pits; Electrolysis Pits; SCADA Pits; V/Line Comms Pits
label | 68daa169-ddc6-4936-abd2-33baa41faf80 |  | note | REFERENCE: NIST 012.2
label | 09aa171a-544d-44ea-af28-08c29a84dc8e |  | note | NIST 012.2.1 Cl7.14.o, Cl7.14.g
label | 2e39cede-15b5-4a02-bc74-520b743f664a |  | note | ACCEPTANCE CRITERIA: intervals no greater than 400m (electrolysis 190m)
label | ed6bdaa9-28e3-4652-a8cf-2221f5dd9051 |  | note | 3m from rail
label | 95b3b781-9f57-4943-8689-ccdb44f66b56 |  | note | Access Roads, Class D lids
label | 578b8b8f-7bdb-4635-80fe-50e7467e9ade |  | note | Footpaths and non traffic areas, Class C Lids
label | cb6adbd5-6e2f-4145-9920-0b24b16df597 |  | note | METHOD: Visual
label | ceafc6f6-fd89-46d5-9629-1183aec283ce |  | note | FREQUENCY: Each Pit
label | c22e2378-8ffe-4908-8509-cb3c54d9f1e4 |  | note | CATEGORY: IP
label | e975d6c3-c055-48e7-bca1-2855ea37f9c4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | aa53ee5a-bc37-4515-92c6-5a32d6d9b221 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e193b0df-405f-43a3-b6b0-5e2092ae79ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7.5 Additional Considerations
label | e9291e57-f555-492a-bda5-344fe1009cdd |  | note | REFERENCE: IFC Drawings
label | 1e22a626-6a61-4ccc-8cb0-70949090a53d |  | note | ACCEPTANCE CRITERIA: Access tracks to pits
label | c9dd1d5a-67f5-47fc-bfce-014dfeb837d7 |  | note | Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
label | cd661119-7665-4a98-a3b0-471dd9106a87 |  | note | Hand rail & retaining wall installed as required
label | 3d163121-c97b-4445-9b45-d46580abc106 |  | note | METHOD: Visual
label | f55f18af-f484-4dfa-9bd7-dee5167b11f8 |  | note | FREQUENCY: Each Pit
label | 730643d1-893d-431b-94b7-6d49d7cdb5cc |  | note | CATEGORY: IP
label | 99aab169-bd0d-4c7b-9489-0558ab2c1084 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1c35544e-5464-4097-a8a6-aec5e74a3d29 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 60735713-6be6-4a7a-ba84-51f8656d158d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Installation
checkpoint-status |  |  | checkpoint | 8.1 Bedding
label | 427b08e1-a525-4c13-930d-4ab1cec1c6a9 |  | note | REFERENCE: NIST 012.2
label | 67c747c0-c76f-4938-9e16-780ae53687da |  | note | Cl 7.21.u
label | 311eb256-31c1-438d-a46d-07052c716b09 |  | note | NIST 012.2.1
label | ac2fa6f7-b234-42f3-923a-29e2d14c235c |  | note | ACCEPTANCE CRITERIA: 150mm of compacted crushed rock under pit extending 500mm past the pit
label | 463993b8-6e91-4508-b9f7-e8bda391af97 |  | note | Drainage arrangements shall be provided at the base of each pit.
label | db3b50a7-555b-49ef-9555-ac7ec47afc97 |  | note | METHOD: Visual
label | d20e29f0-6ac6-415e-8fc8-ba7d5e1a0e6b |  | note | FREQUENCY: Each Pit
label | 2225e9f8-a5eb-44f7-9bae-0ff55da48400 |  | note | CATEGORY: IP
label | 2af28a12-1a55-4b12-a3fb-a34b7fca2345 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6fd4465b-dee0-4d89-b962-35feec02eda6 |  | note | VERIFYING DOCUMENTS: Sign ITP , Attach Delivery Dockets
text | b48e7869-6bc8-4c7b-ae38-aa6b7ae645bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.2 Pit Orientation
label | 6005cb16-825f-41c8-a903-fe9695541875 |  | note | REFERENCE: IFC Drawings
label | 382b11ed-6c2b-4822-82f3-fa5e88b6058c |  | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
label | da60bbbc-8ee4-4550-bcc2-2299bd4518f7 |  | note | METHOD: Visual
label | 4489a212-6dc5-4ac5-b763-89bd68db661e |  | note | FREQUENCY: Each Pit
label | b042cf51-2ed7-4ad1-82a5-6ba69303acdc |  | note | CATEGORY: IP
label | a285d050-b539-4d1c-9189-93f733629b8d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8bf44f81-f579-41bd-a86d-5a81c5c971d8 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 89959920-573e-4f53-86c5-7f5271bb9ff2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.3 Pit Installation
label | 9adc493f-c951-4b77-9f8f-66f3c490ef7c |  | note | REFERENCE: IFC Drawings
label | 21eb5c19-f0ad-4140-b473-222235331e2b |  | note | ACCEPTANCE CRITERIA: Pit installed to design specifications
label | 24d045eb-b98c-4099-8d5c-2760552fbdc6 |  | note | Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
label | ad5ce0df-30a5-4230-85b0-10d537bb676a |  | note | METHOD: Visual
label | fff2ddc4-197c-42b9-bcfe-c4217ca664d7 |  | note | FREQUENCY: Each Pit
label | 2160e400-c590-4b6a-bbd1-799220cd478a |  | note | CATEGORY: IP
label | 5721d2d0-5efd-4a94-8767-684e3f2f9775 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f897ac1d-c74b-42f6-9e8a-8f3287c03054 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e3e079d6-6d67-4120-8cea-aa729b88d65c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8.4 Pit Greater than 10ft
label | 50f82ed1-0701-496c-b355-b4b962778893 |  | note | REFERENCE: MRPA Procedure
label | 65a5a5db-a1f6-468f-b4f0-859131134532 |  | note | ACCEPTANCE CRITERIA: Each pit if non standard lift (greater than 10t) the following is required:
label | fc6ec7b6-5d2d-4ecb-8571-419c657987ff |  | note | Certified Working Platform
label | 89f910d6-d22b-40b0-97e7-0b3b4d2087bc |  | note | Certified Lifting Anchors
label | d682b4d8-314f-4c94-8521-18c968eb2a71 |  | note | Approved Lift Study
label | cf114b75-6e22-4f07-b4a3-2849138274bb |  | note | Check Birth Certificate
label | a88dd273-7ff9-457c-8ad2-fea464d05f2f |  | note | METHOD: Visual
label | e60720ed-68ec-4ef2-ad6a-d9b604599b07 |  | note | FREQUENCY: Each Pit
label | a5eb4775-3615-47e4-8a85-0bd14c053860 |  | note | CATEGORY: IP
label | f5ac9f06-8333-483c-97bb-b435eb81de16 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 904e36cb-1f60-4918-9da4-0a572c419ec5 |  | note | VERIFYING DOCUMENTS: Sign ITP , Attach: Geotech report, lift procedure, shop drawings
text | 5c4d974e-9a0d-49af-9b7a-785fdfa9f36c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pit Fit Off
checkpoint-status |  |  | checkpoint | 9.1 Conduit Entry
label | 769eaed2-b267-422b-9129-6ce816ad99f6 |  | note | REFERENCE: NIST 012.2
label | ab5e6073-d047-4679-8158-f2c20dedf6ef |  | note | NIST 012.2.1
label | b04ef8f5-12b2-406d-822d-82a6533fea54 |  | note | IFC Drawings
label | 0c085676-6ac7-41ad-b46d-0f1864eb0e3f |  | note | ACCEPTANCE CRITERIA: Conduits entering pits shall slope away from the pit such that water does no flow into the pit with lowest conduit 100mm from the pit chamber floor.
label | 4361c72b-3c3a-4189-99fc-07292f66f2a2 |  | note | The exterior entry points for conduits into pits shall be sealed by mortar (ratio 4:1 sand/cement) or both externally and internally using an approved, expanding silicone based or similar type sealant
label | 6bbc7c0e-37e4-4757-b7ca-9b4ad8c11062 |  | note | Penetration holes through pit walls shall be 1mm to 5mm larger than the conduit outer diameter and created by either:
label | 09ce778d-773b-4267-a66c-1732fdab7da5 |  | note | a. Preformed (cast) holes
label | 45f6d199-18c1-4ef9-965c-6e9e05764aa3 |  | note | b. Hole saw cut (or diamond drilled in the case of concrete walled pits)
label | fcb1af88-4286-4622-b361-9de921bb1aed |  | note | c. Comms conduits entry into concrete pits shall be via drilled holes only
label | 6fe219fd-d629-44f9-8091-6f29b9a6b84a |  | note | METHOD: Visual
label | bb55913d-2eb7-41a4-b0d1-dcc70312c6a4 |  | note | FREQUENCY: Each Pit
label | 4fc1410c-0a9d-4203-bd0b-c0593421ed09 |  | note | CATEGORY: IP
label | edc4f111-bd33-4893-82d2-9ae87bcffb23 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2ca25bba-1a78-47d0-8040-9bdf07a87ae1 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ee7e6ee6-e43a-415b-a2b0-405360b1a26b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.2 Tracer Wire
label | 33db5c2d-cb27-40e8-b03b-95714b1fc749 |  | note | REFERENCE: NIST 012.2
label | 99744e7a-30cd-4f4a-ab21-165bfc1d9341 |  | note | NIST 012.2.1
label | 78b5be5f-f3ee-4e02-a47a-1132e6af8c9a |  | note | IFC Drawings
label | 723dd26b-68a7-4860-93cf-6e4a611ec1af |  | note | ACCEPTANCE CRITERIA: Warning tracer wire for Vic Track routes to be drilled into pits and crimped off.
label | d8449411-5b77-4a2c-90e1-2aed1dcd21bc |  | note | If tracer wire broken needs to Crimped
label | 7db5ff5e-1aa2-4694-ac79-425450659cd0 |  | note | METHOD: Visual
label | f5102461-6b90-4c2d-9ace-4fe0f48d0f50 |  | note | FREQUENCY: Each VicTrack Pit
label | c2e3086a-ce3e-4a95-b288-4fddf2135017 |  | note | CATEGORY: HP
label | 0f18af91-cce0-4303-a296-550236742996 |  | note | RESPONSIBILITY: SE, NA, Vic Track
label | fc84e7e1-8fee-48b8-a1fb-543ae38475f6 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 3819ade1-efa6-46f4-86cf-52d4ca927af0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 Spigots and Bell Mouths
label | 5685eb74-cc8e-4260-b9a0-66d56d21f987 |  | note | REFERENCE: NIST 012.2
label | 3a813338-d928-4df1-a330-756d05e2cf18 |  | note | NIST 012.2.1 _9.3.4
label | c01e74a2-4a51-4b19-8edc-5e91cd546bde |  | note | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush (if conduit type isn't mentioned below) with the pit wall and not touching any other spigots.
label | 6e97814c-eaed-48d2-8ca3-1c0cd1943356 |  | note | HV Conduits entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
label | 50775579-b395-422c-9b1c-93646e698da6 |  | note | Comms conduits are to be correctly fitted with Comms entry spigots mounted flush with the pit wall to ensure no damage to the cables during installation.
label | 2aa25575-1475-4e8d-9ca4-dfcd62955b05 |  | note | Signals conduits must protrude into pits by a minimum of 10mm and a maximum of 50mm and are to be fitted with a spigot to ensure no damage to the cables during installation.
label | d194f26f-c0fe-4821-a415-00bdf338c7a8 |  | note | METHOD: Visual
label | bc5c43b4-a6b1-4f53-8896-41cff0d83064 |  | note | FREQUENCY: Each Pit
label | cef145cd-bf9b-4020-84bd-8e55cefb6fbe |  | note | CATEGORY: IP
label | 0b7e664c-d458-4795-bcee-9c261a0f13b8 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | c40ad348-9275-49cf-ad7a-50ec9a38b5d4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | daf67065-269a-4824-a2d2-73f4b7cd1fbc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.4 Draw Ropes
label | 1bd89ba9-8525-4054-8c2c-d16f0a08142a |  | note | REFERENCE: NIST 012.2
label | 8178d9f0-cb40-4dca-a767-b9cda927cea4 |  | note | NIST 012.2.1
label | 40bc63e8-1cda-419c-bf63-8a19d8d12b26 |  | note | ACCEPTANCE CRITERIA: The draw wire shall be continuous for the complete length of the conduit run.
label | 45db4b7d-d836-4eb1-842a-0738cbd736e3 |  | note | The draw wire shall have a minimum of 2 metres of slack within every pit.
label | 7708af2e-4fd3-47e3-a242-e83c892ccb67 |  | note | METHOD: Visual
label | 8f69d9e8-1e35-43bd-854f-867a0b7cb63d |  | note | FREQUENCY: Each Pit
label | e9687708-2183-45d5-a36b-0254ea203e8e |  | note | CATEGORY: IP
label | 89f5733c-d318-4bb1-ae10-64ac25896306 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 60388f01-b2d0-4896-8b86-c4a6ab9aa7c7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 79d2fe6f-6383-401a-b187-0bf61958c2e6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.5 Backfill and Compaction Testing (if applicable)
label | ae63433a-4fed-42ed-bf94-cc64118a277d |  | note | REFERENCE: NIST 012.2
label | 9ec36e73-b860-4200-8b0a-d13ee539fd08 |  | note | NIST 012.2.1
label | 33c5b2c3-4bf1-4a3e-ba48-79c840425c85 |  | note | IFC Drawings
label | 83345b6a-3616-41f6-ba4a-67bfdf5d7b1e |  | note | ACCEPTANCE CRITERIA: Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
label | 6967fd96-74ae-49ba-8380-401324463a6e |  | note | Sand within sand pits to be compacted in layers no more than 250mm layers
label | c8f09a1b-0ae1-4e31-b796-140eb254c3a9 |  | note | Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
label | e0edf96b-4501-4aef-aafe-4ba2e6b651b8 |  | note | METHOD: Document Review, Visual
label | fe66c7ca-3059-4f83-a184-d83a6955f23f |  | note | FREQUENCY: Each Pit
label | 3eb8b3ca-a940-43b8-abe9-3cd59cef40c6 |  | note | CATEGORY: IP
label | 32beb8ac-9abc-4be4-82c1-41083a6e7785 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b0fae444-98e6-4b9e-a084-7e87f531fd01 |  | note | VERIFYING DOCUMENTS: Sign ITP , Attach Test Report
text | 4da12824-2b4a-4674-9faa-e107ae7c6d0f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.6 Step Irons
label | 02848c68-fe0f-4857-ba6a-2e90eab7c011 |  | note | REFERENCE: IFC Drawings
label | 35a4bb80-f6a0-4f11-afe7-7a873db3f267 |  | note | NIST 012.2.1 0_9.3.7
label | fe66646f-9d60-40fb-92e1-fef50a4c0b65 |  | note | NIST 012.2_14.2
label | c6adb3a8-3340-4313-a918-f7b868ca2c77 |  | note | AS1657
label | fdd26088-f6a1-46c8-8297-41b1a41de248 |  | note | ACCEPTANCE CRITERIA: Unless otherwise noted on IFC drawings, the below is required:
label | 0b76e2f1-93ed-409f-985b-243a0a3aa10b |  | note | High Voltage Pits: Step irons/rungs to be installed if pit is greater than 1.0m in depth (including lid thickness)
label | e242979d-6a4f-454a-bfa3-42526ca8b282 |  | note | All other Pits: Step irons/rungs to be installed if pit is greater than 1.2m in depth (including lid thickness)
label | 0e34e506-f8f4-4e63-ba14-fb7ec2e08aeb |  | note | METHOD: Visual
label | 613cde81-3f69-4dc4-bbc1-e41fe99a2855 |  | note | FREQUENCY: Each Pit
label | b082aa98-6224-4cc7-8749-192094a1004e |  | note | CATEGORY: IP
label | b8a436d0-ce61-4ee6-b0a2-8316cc35099d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0bb81efd-5fa8-478f-8715-b499c2e6f2ab |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 153fb56c-fa98-4ba9-be2c-52257979ecc1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.7 Spare Conduits
label | 1abbb044-7f9c-49f8-b9bc-30c876c1cebc |  | note | REFERENCE: NIST 012.2
label | ac6e3ed4-0c0e-41a7-8a87-b3cceb4be8ee |  | note | NIST 012.2.1
label | 46d5610d-11d5-4474-8acd-85b67d609cd5 |  | note | IFC Drawings
label | 8c850df1-ccce-4171-9258-76cf18668c0d |  | note | ACCEPTANCE CRITERIA: Spare conduits to be sealed with a tapered polystyrene plug and to be included on survey report.
label | 061c9c47-38ce-45f2-a91e-5b55b669a683 |  | note | METHOD: Visual
label | 4cfffb1b-91bb-4564-997a-6663de55db47 |  | note | FREQUENCY: Each Pit
label | b5fc70ff-a717-44f9-843a-01cf9615251a |  | note | CATEGORY: IP
label | 2fa5eb30-1f3f-4b1d-83a6-e95cad8ee624 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1a235a3d-4ae7-4db5-9535-3d5bac8d3b81 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c7bba506-9c8d-4739-8b8b-247130020ae8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.8 Pit Labels
label | cee6ab31-d0c1-4365-96ba-7d6c9ef80a93 |  | note | REFERENCE: NIST 012.2
label | 14db544f-e83f-4d5c-9e3c-855195bd4288 |  | note | NIST 012.2.1
label | 07214b12-8d53-4285-8d64-9ed2fc379de0 |  | note | IFC Drawings
label | 061de332-062d-4ed7-aafc-d72cb0e282a1 |  | note | ACCEPTANCE CRITERIA: Pit labels Brass Label (30mm x 150mm)
label | a26e1360-dcf7-4115-b16d-25f5218da549 |  | note | HV: DANGER - Railway High Voltage
label | 559dfdef-7d0f-4b0e-b4ca-8b963ec900b1 |  | note | VicTrack: Victrack Comms
label | 775b94d8-c867-46dc-ad52-ed30a308f5f2 |  | note | Signalling: Rail Sign Comms
label | 3c0fcf8d-c853-43ff-b5b0-20bda4a4fdab |  | note | LV Pits: Electrical
label | 2a0800bc-5ea9-4fcf-ae63-23541b5ca8d5 |  | note | Electrolysis: Electrolysis
label | b481c644-8825-4ee3-9d1a-eadb345c3298 |  | note | SCADA: Rail Sign Comms
label | bbc52363-f332-4eb4-81fa-5c7bb9504364 |  | note | V/Line Comms: Rail Sign Comms
label | e3f3d4d6-f0b6-4778-b7dd-e5cc01cb20b8 |  | note | METHOD: Visual
label | 32c1b77b-6e24-4ee5-a568-4bb2939545bb |  | note | FREQUENCY: Each Pit Lid
label | 3f6b1854-20e9-43fc-9dbd-8793929a3e51 |  | note | CATEGORY: IP
label | 72d6c40e-03c9-48ab-8e30-5571eb76e523 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 45a27ecc-191e-4a76-9496-2c4a30068776 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | b00e0d64-9e1d-4fed-9eaf-ae0124bec8c3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.9 Pit Numbers
label | 02ba594f-7c6a-494f-b1e8-fc2097931314 |  | note | REFERENCE: NIST 012.2
label | 8ad32636-c5ff-4ef1-9e1f-b3183ac09cce |  | note | NIST 012.2.1
label | f2dfa5a0-9179-43dc-9c84-ae7133f3da3c |  | note | IFC Drawings
label | fd51c4f8-c290-42ec-97fa-91f15e86701a |  | note | ACCEPTANCE CRITERIA: Pit Number Brass Label (30mm x 150mm)
label | dbcdc5a7-f1c5-4e66-aeed-4037d8acce0e |  | note | HV (22kVV Feeders): ###HV
label | 1a03c5c8-a4b2-4fe0-b92e-4eb58f6939a4 |  | note | DC (HV Feeders for OHLE): ###DC
label | 14870288-5121-42e0-9ce5-32877039503d |  | note | VicTrack: ###C
label | 8377d771-ce15-488f-94e4-aef5d11abc3e |  | note | Signalling LV: ###SL
label | b675f193-3c72-42d4-8898-ff9bd825cac7 |  | note | Signalling HV (2.2 or 3.3kv): ###SH
label | 1ce1b96e-06ac-4ec1-bd7f-85c64a801143 |  | note | LV Pits: ###L
label | e78df3f0-f43b-4bb5-8887-a442f9501e5d |  | note | Electrolysis: ###E
label | 9d4e480c-9877-42ee-9f21-49a550fe93a1 |  | note | SCADA: ###MS
label | a65d482f-b923-4ca7-9788-957a5875e7a0 |  | note | V/Line Comms: ###M
label | 2c7e7ab2-3e4f-4bc7-bf97-abf848c38abb |  | note | METHOD: Visual
label | 12a4cd5a-00b2-4875-8702-32dc19edd1ce |  | note | FREQUENCY: Each Pit Lid
label | 5aab0bb1-9e90-4e48-9632-f2ec15160c3c |  | note | CATEGORY: IP
label | fb3cbc76-1564-466c-9dc3-95eb2326e572 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 5403458e-4f26-440b-8f27-3eaffd508cf7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ed3220e8-7a83-4541-bf93-d974eae3eb22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9.10 Mandrelling
label | df85469e-cc01-4f28-ba2a-936454bfaaab |  | note | REFERENCE: NIST 012.2
label | 28b726af-6aff-4a3b-9235-aa23f73e9d3a |  | note | Section 16.1
label | 3d529fa7-e72d-41f9-be0d-471a123272e4 |  | note | ACCEPTANCE CRITERIA: The mandrel shall be solid, have diameter not more than 12mm smaller than the internal diameter of the conduit and be a minimum 230mm in total length and 130mm in flat length. It shall be pulled through every conduit in both directions by hand or with a machine to ensure their integrity.
label | 7cc0bf78-a67f-4aa7-988b-0ce59c694f41 |  | note | MTM/Victrack Witness
label | 527b4412-751b-4c1e-8612-bef77c9aaff3 |  | note | METHOD: Visual
label | 6d4587a3-2d0f-4420-8b60-8f8cc902988d |  | note | FREQUENCY: Each Conduit
label | 2d7912e3-41f3-4093-a52f-d33d241c1779 |  | note | CATEGORY: HP
label | 8c80aa78-6a9b-43a9-92d4-954df982ff45 |  | note | RESPONSIBILITY: SE, NA, V/Line/VicTrack Rep.
label | 1e7e60ad-761a-4bc6-b06b-2374c598127e |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 26ffcfd4-fff4-4fa0-8e1c-1228228f9874 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Protection and Labelling
checkpoint-status |  |  | checkpoint | 10.1 Non Trafficable Pits
label | 3cb8d862-b784-44f8-b877-cfced91f8564 |  | note | REFERENCE: NIST 012.2
label | 5d93b4c0-931b-4cba-b876-eca001b6123f |  | note | NIST 012.2.1
label | 16b70b14-0aff-41ac-9d17-de27f5759e6d |  | note | IFC Drawings
label | 94ccf78d-5a14-4b3d-8cbf-9506ca813301 |  | note | ACCEPTANCE CRITERIA: Non trafficable pit lids to be 50mm above FSL and to have 2 x white bollards installed at the corners of the pit.
label | 837fd1fd-0ab1-40d2-98d0-082a4a5e4f4d |  | note | METHOD: Visual
label | 2b614ed9-410b-4e69-b55c-87bc91f138a5 |  | note | FREQUENCY: Each Pit
label | 23cffead-22bf-4539-bb7a-130d3b5df645 |  | note | CATEGORY: IP
label | 03c6df97-cfa1-4d14-ad78-3438308c81c0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 272d043d-65d2-46df-8345-1b6249b041ce |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 3ff2aa03-888f-4711-bc1e-4c06b66b6b79 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.2 Sand Pits
label | 3d35b51c-5007-451d-a757-e614ad3206cb |  | note | REFERENCE: NIST 012.2
label | 6e1f0133-e3fb-4872-87ca-5d93b31c195d |  | note | NIST 012.2.1 Cl 9.4.3
label | 620a9fd8-e35f-4167-93be-0915d3018a6e |  | note | IFC Drawings
label | a0133873-e5ad-4a10-8671-970de46798b8 |  | note | ACCEPTANCE CRITERIA: Sand Pits (HV)
label | 81273f85-aeac-49da-aaed-3134ed06cd9b |  | note | 4x yellow posts installed at the corners of the pit and 2 of which shall have cable route markers attached
label | 9e3e317c-e5e3-4430-ab16-1bc69d691cc0 |  | note | If posts are impractical, 4x monuments with cable route marker plates affixed and a cable route marker nearby indicating position of the pit
label | b4347702-b410-41b7-80ef-c996823a8968 |  | note | METHOD: Visual
label | 4738d428-5e25-47bd-bd9c-4f4ebc932646 |  | note | FREQUENCY: Each Pit
label | e60f074b-5f56-4908-82e9-c668ae6b152f |  | note | CATEGORY: IP
label | 9911d309-2ef2-4e2b-aac3-fc22d47cfae4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b459e014-be98-4103-90eb-a45343bf85fc |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 27cde6a1-2718-4240-858e-59f26eaaf261 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10.3 Cable Route Markers
label | 4e8f24b9-4f04-4273-a12c-c284a27c8fc0 |  | note | REFERENCE: NIST 012.2
label | 9ab8f74d-5ee2-4f9e-afb8-6575b5a04aaf |  | note | NIST 012.2.1 Cl13.2
label | a6f1ba99-758d-4701-accc-1816b6b6c901 |  | note | STD_E0169 and STD_E0170
label | 742bf9e1-f010-4b99-93ee-b6e09c0a9ca1 |  | note | AS 4799
label | bd168bdb-1912-4347-bffe-967bae15a664 |  | note | STD G0003 and STD G0004
label | 01c99150-6e54-4986-b6c0-a9f2137508b5 |  | note | ACCEPTANCE CRITERIA: Cable Route Markers
label | 7125f739-320d-4748-91fc-95f8e6733d5c |  | note | points entering & leaving the rail corridor
label | 564add37-4565-4712-a21d-6c57ff84ccbe |  | note | no greater than 100m spacing
label | fb515b6f-b15b-4f9a-85c8-4cb0e4d1fbe9 |  | note | Change of direction (more than 5 degrees)
label | 3e7a274e-0110-46e9-9dff-6499326151e5 |  | note | White posts with marker plates for conduit runs
label | 49f24223-b75f-4211-8b96-7878b2afc361 |  | note | METHOD: Visual
label | 820d3899-d5fd-4795-9c40-701f1168d7d6 |  | note | FREQUENCY: Per Cable Route
label | b9f7c8b2-9e10-4729-9332-20081fa44bbe |  | note | CATEGORY: IP
label | 832a2c7e-4f61-42a3-8ff7-8a488613b0e5 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cf8d43ea-0942-4b91-895f-195a0ede68c5 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 0f5b0d1c-289e-4ab9-a43a-0124082699d2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Cable Route Handover
checkpoint-status |  |  | checkpoint | 11.1 As-built Survey file
label | 3ad31385-12bf-4092-9b0b-2858cbc4860e |  | note | REFERENCE: NIST 012.2
label | fffb4572-8428-4c85-83f0-d2fa10759591 |  | note | NIST 012.2.1 Section 13.1
label | 1d2e3cc5-5819-4dc4-9ae7-c37d44755237 |  | note | ACCEPTANCE CRITERIA: Survey report to include but not limited to:
label | c7d030b9-b742-44be-a35b-b126628fa44a |  | note | Cable joint locations.
label | fb0ecc90-34a2-439c-b9c2-b2fcfc7925d2 |  | note | Cable pit locations (Corners)
label | f0992457-80ee-4d4b-b7de-87a0ceafcc08 |  | note | Pit dimensions & pit lid type
label | 4adcb18b-d90d-4260-822e-978c2208ea7f |  | note | Under line crossings
label | 475ae567-50ac-4ec8-b9e0-fe8846e5cda6 |  | note | Under road crossings
label | 790da2de-d0bd-4337-b81f-95e63c656315 |  | note | Changes of direction
label | 53f709a9-9f07-4f3f-bfc0-e8c4472c001c |  | note | Spare Conduits
label | bdf0ffe9-f0d6-40f8-b891-c6ff241116e7 |  | note | Conduits labelled as per trench profile
label | cff3fe90-517f-4d9b-ba3b-b8967cb51ca8 |  | note | every 10m
label | a68586fe-10da-429c-b307-f03e6f120fb4 |  | note | Other significant points of the cable route
label | a5806a93-ad66-4765-bd3c-5dcb95426bcf |  | note | METHOD: Document Review
label | eb881245-077d-47d6-89f1-eeeb643f27ff |  | note | FREQUENCY: Each Design Pack
label | d0c19f04-93c2-4b90-af3b-7cb52bfb000f |  | note | CATEGORY: IP
label | bce788a9-8560-44f5-9d61-4394da39579b |  | note | RESPONSIBILITY: SE/PE
label | 66c257af-1fcf-41a8-be23-97883190709b |  | note | VERIFYING DOCUMENTS: Sign ITP , Attached Survey Report
text | dd6829fa-0261-404a-a06e-832a0f022bc2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11.2 Engineering Redline mark-up
label | b6aea00e-3e18-412d-8a8c-e14ccfc8af1a |  | note | REFERENCE: IFC Drawings
label | dd58bad8-ca6a-4913-a7a7-6e529f9b472d |  | note | ACCEPTANCE CRITERIA: As constructed cable plans shall be provided for the entire cable installation and in accordance with AS 4799 and the PTV Infrastructure Drafting Standard.
label | ca02366e-43a2-4380-a4da-4fbd43291018 |  | note | METHOD: Document Review
label | 70c109cc-5457-421f-a651-0802b98d7f63 |  | note | FREQUENCY: Each Design Pack
label | effd60a1-490c-46be-a279-b18e6aad9d67 |  | note | CATEGORY: IP
label | 1b6c7a90-d62a-4de8-869a-f97eef548aaf |  | note | RESPONSIBILITY: SE/PE
label | 470522a0-15a3-4f5c-9f52-c6b244a4285c |  | note | VERIFYING DOCUMENTS: Sign ITP , Attached RLMU
text | f563e1e8-2785-4627-8b9a-64dd0a94d1bc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Cable Pulling and Terminations
checkpoint-status |  |  | checkpoint | 12.1 Cable Pulling
label | 366f109c-83b6-44ae-b8db-b8c4084104a9 |  | note | REFERENCE: NIST 012.2
label | a49a6096-1e02-4f13-b67e-430e87450c57 |  | note | NIST 012.2.1
label | bd8c3633-0f02-4217-81ed-340dcb97d725 |  | note | IFC Drawings
label | c77a58a1-c617-4ba1-be63-3809c385d374 |  | note | ACCEPTANCE CRITERIA: Cable pulling to be witnessed by V/Line/Vic Track and to be signed off.
label | 0aec241a-b4a0-4714-8bf4-bce7d2b55d99 |  | note | METHOD: Visual
label | 98c72e0c-abc4-4578-99a5-2c0278033efc |  | note | FREQUENCY: Per Cable
label | 48bc00dd-f6a0-491b-ab7e-ea46090c9ee1 |  | note | CATEGORY: HP
label | ef6ad673-4fbd-4526-b68c-2c302da0da1a |  | note | RESPONSIBILITY: PE, V/Line/VicTrack
label | 3276b038-3af0-462d-a738-254e1017e4fa |  | note | VERIFYING DOCUMENTS: Sign ITP
text | febe3f20-1665-48e3-86be-dcb024e35ccd |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.2 Cable Labels
label | 24b53930-2dcf-4c4d-ad4e-6579f34579d7 |  | note | REFERENCE: NIST 012.2
label | b3f91929-d947-4cae-96d2-728d875f4a16 |  | note | NIST 012.2.1 Section 13.3
label | a032e91a-48cb-418c-8d7e-b9fa7ee92959 |  | note | ACCEPTANCE CRITERIA: All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
label | 2b849c39-403a-4233-ad4c-b74f4da88eb1 |  | note | The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
label | 17ed9dc8-2a62-44b4-9fae-f1721e450015 |  | note | METHOD: Visual
label | 8cc08c5f-c79f-4473-ba3c-aabc452417b7 |  | note | FREQUENCY: Per Cable
label | a1ac9781-708a-4858-8e71-9ceed9f8c02a |  | note | CATEGORY: HP
label | e343df0a-d38b-444b-a9e6-62d0cee1eed0 |  | note | RESPONSIBILITY: PE, V/Line/VicTrack
label | bda8e9fe-cd92-4d94-b22d-ba1b576d32f7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | abb94d22-c059-4455-aadc-c392d0154267 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12.3 Cable Joints
label | 620734a5-a8da-48be-a259-11ff8e1e7910 |  | note | REFERENCE:
label | 614ab40b-0dc8-41dd-8d6d-3aadae2dff6e |  | note | ACCEPTANCE CRITERIA: Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
label | c6eeed25-2aa7-4c24-b778-a302624581b1 |  | note | METHOD: Visual
label | 1fb2352f-d044-44c7-814c-46c02a0cb3ff |  | note | FREQUENCY: Per Joint / Termination
label | 1aaf6693-0a3a-469b-b223-a010ff1c642d |  | note | CATEGORY: HP
label | 5413b90a-ecb7-4346-9df8-22ced67da211 |  | note | RESPONSIBILITY: PE, V/Line/VicTrack
label | d819db89-59a7-48e4-8c1c-f2aa1eee7fe4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 78a674a6-e531-4f07-843c-52a45505e94c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 13.1 Handover Check
label | e0576fb1-da84-4918-b911-0b1ad050ec14 |  | note | REFERENCE: IFC Drawings
label | 0bdc409b-fd2f-49b6-ba63-ec368c9e3634 |  | note | ACCEPTANCE CRITERIA: Handover check completed for Testing and Commissioning.
label | e417dea1-7922-4380-97d3-3a6f66a09991 |  | note | METHOD: Document Review
label | 4f6f1f87-7e25-40ce-a74b-1db4066fa0c6 |  | note | FREQUENCY: Per Lot
label | 00bcd09b-6168-4b1f-b9f8-d5007150410e |  | note | CATEGORY: HP
label | 660b96cc-627b-46ff-9740-9713f34aee0a |  | note | RESPONSIBILITY: PE, V/Line/VicTrack
label | 7f7b7318-c16e-41c4-aa52-a94cebd0894c |  | note | VERIFYING DOCUMENTS: Sign ITP , Attach V/Line/Vic Track Check Sheet
text | 8b573af1-f1ec-4297-ad5f-514be41970bc |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13.2 Testing and Commissioning
label | 1b7deb4a-3b3f-4762-8e5f-2872e0fd74ae |  | note | REFERENCE: IFC Drawings
label | 1ade78fc-da5e-43f4-b070-f27e48462b75 |  | note | ACCEPTANCE CRITERIA: Testing and Commissioning to be completed
label | d3ccfe62-6d55-4ba0-9645-b497999eccde |  | note | METHOD: Document Review
label | d97cb813-4d43-4415-ae63-eb65c05409b4 |  | note | FREQUENCY: Per Lot
label | 89d76a46-3810-483c-b8e5-98eb294b6877 |  | note | CATEGORY: HP
label | 35693f83-7a56-455c-932d-c5bf1de1a1ae |  | note | RESPONSIBILITY: PE, V/Line/VicTrack
label | 4aeec143-09bc-45d9-8c8f-b3d3c00611f5 |  | note | VERIFYING DOCUMENTS: Sign ITP , Attach T&C Report
text | 29637765-d00f-4cbe-8394-b7e25352e4b7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 4d5c75ce-7771-4691-af4e-bd9b353acf23 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 867364db-3352-4fdf-99ff-aacc2c35a128 |  | textbox | Name:
text | 54edd2a9-3b6c-435c-8d94-18c4d5affea1 |  | textbox | Position:
text | 8784eb75-0059-4632-a704-a98491518140 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-General Concrete Rev 1 | itp |  |  |  | Yes | ITP-CIV-General Concrete Rev 1 | decbbcee-d8e9-4f26-b8f1-fe4abff8ffc0
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 236057f7-78b9-48d5-8a0e-0ba3fd308043 |  | note | Document Title: ITP-CIV-General Concrete
label | 923c9a7c-70bc-4727-9ec1-bdf20437fd76 |  | note | ITP Description: General Concrete
label | fc97af16-e905-48ca-8a9f-4abdb030fc43 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 998352df-0b6b-40df-8453-9c2234446c1d |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | cf78fdcc-8dc7-4e4f-a2d4-d720f44acca0 |  | note | Revision Number: 1
label | 57f7e590-1646-40b5-8382-f05e9bf92a5f |  | note | Revision Date: 27/08/2020
label | ab8c7edb-247a-408e-a0ba-441ae0734567 |  | note | ITP created by: Mike Freeman
label | cf2639d0-5835-40a3-9707-63c262ae2b59 |  | note | ITP approved for use by: Mike Freeman
label | c2492f58-549c-4238-bcf6-2f15c6dfeb17 |  | note | 1.1 VicRoads Section 703 June 2018
label | fa40065f-826b-4b20-921b-86fc88032b07 |  | note | 1.2 VicRoads Section 812 July 2016
label | 3c58c4d0-3f80-497b-a034-d81ef6343662 |  | note | 1.3 AS1379-2007
label | c4983e60-8d41-473e-9f1c-118d611f413e |  | note | 1.4 AS3610-2018
label | 4252e416-8496-495a-b1d6-457ceb0f3d0e |  | note | 1.5 AS4671-2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bedding Material / Base Layer
label | 0a0b9b9d-8e58-4602-855e-5c415160fd63 |  | note | REFERENCE: IFC Drawings
label | 661b97a7-dca4-4086-be87-de4dcbe41b20 |  | note | 703.21
label | 20ec4e99-e366-4fcd-9212-2913568812be |  | note | 812.04
label | 7e0090b0-956a-4948-8942-1d0ac541da8a |  | note | ACCEPTANCE CRITERIA: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
label | 4552748f-1a4c-4086-b1c0-baa0b4009bb8 |  | note | Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | ae98c1fd-a593-47a3-9746-480b749ee6a8 |  | textbox | Enter: Teambinder Material Approval number
label | db02aa02-2883-4790-a939-a1154014dda9 |  | note | METHOD: Document Review
label | b5f05a1f-21d4-45f5-af15-a369ab19257c |  | note | FREQUENCY: Once, for each mix design, prior to placement of material
label | 2bb5a963-de15-4708-9aa0-a8a8e6cb2526 |  | note | CATEGORY: HP
label | a5f5a2ff-f456-43c0-95f7-ce0edace3c58 |  | note | RESPONSIBILITY: Nominated Authority
label | 49e16f1e-8240-43ff-bb5a-26a1a37a349b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 860127f3-0b06-4352-b26d-fcb764750ebe |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Concrete Mix
label | 2188672a-813e-41a4-9a78-ef9e86466958 |  | note | REFERENCE: IFC Drawings
label | 60fa596e-8862-4649-be53-8d32d917a81e |  | note | 703.05 (a)
label | 28047f72-33de-41b6-ab8f-eca7ae957b11 |  | note | 703.07
label | 83d86be5-cc90-4430-aa0a-b429c9af0745 |  | note | MRPA Quality Management Plan
label | ec1be236-302f-4712-8a1a-c5c62394bd46 |  | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | 4ef1d0bb-5626-4961-94ea-ee82e7be4c3e |  | note | Paving concrete mix conforms to AS1379.
label | 5792d91a-921c-4731-9735-3b178d766c9a |  | note | SUP concrete mix is registered with VicRoads.
label | 55a2bd03-c416-4105-96a5-a7788ef4f2f7 |  | note | No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | 0642c9cf-ebce-43a0-bb4b-c023f42428a8 |  | textbox | Enter: Teambinder Material Approval number
label | fa4a723a-5f77-4406-8123-f747e8681341 |  | note | METHOD: Document Review
label | 11e996e3-8d1e-421d-a2b3-3d2af450af6b |  | note | FREQUENCY: Once, for each mix design, prior to placement of concrete
label | eb71c380-3960-4079-9721-b9c609c0c9c3 |  | note | CATEGORY: IP
label | e5afd62b-f556-497f-897d-5eb232bc7693 |  | note | RESPONSIBILITY: Nominated Authority
label | 59999453-7d4d-426b-836a-32737bec3d83 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 8d118270-35db-4320-b6c2-3b5548933a23 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Reinforcement Certification (or ACRS Certification)
label | 93385016-7cae-4911-9972-3381c038eaed |  | note | REFERENCE: 703.13
label | 47d67e99-6fc8-4d37-aa49-c03767a798d9 |  | note | MRPA Quality Management Plan
label | 48e632bf-30c0-4485-9271-9ba529d71ea4 |  | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | fff3e681-5a58-409e-a05f-3e785632d45e |  | note | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
label | ea91f5b2-3d30-4da6-bc0d-083b35e541ad |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | dfee8fb8-3baf-4233-a712-8683d0cc8016 |  | textbox | Enter: Teambinder Material Approval number
label | cc43ba74-a31a-4e75-b02a-816fe8c9d354 |  | note | METHOD: Document Review
label | f3b59e78-9f2c-405b-b700-500da2d0c3f5 |  | note | FREQUENCY: Once for each supplier, prior to placement of order
label | 85419bec-932e-4d45-b9bb-aedb5fafe737 |  | note | CATEGORY: IP
label | 435fed6e-9784-43ae-a3fd-6e6aad781888 |  | note | RESPONSIBILITY: Nominated Authority
label | dca41e06-03d9-433b-bc4b-7858a41bad93 |  | note | VERIFYING DOCUMENTS: This ITP
text | 81508367-972b-45f5-9720-36a873545ae3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 8a5618af-aad5-4452-b6d3-38b34d30cb81 |  | note | REFERENCE: 703.09
label | 24e9f6a5-15eb-4ab2-9f67-317f39b48bf2 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 4b64c320-e365-4a3d-805c-7a02d3c65335 |  | textbox | Enter: Teambinder Material Approval number
label | 207678d3-0240-4d98-8307-57b4ad36c7fc |  | note | METHOD: Document Review
label | 987da46e-905c-438e-b4a9-34c09818df5c |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 60360bd1-e8b0-4a55-b04f-328c0417361a |  | note | CATEGORY: WP
label | a06e51e2-936b-424c-af5c-c184139b765c |  | note | RESPONSIBILITY: Nominated Authority
label | ff7c5b12-6465-4fe9-aafd-cacbd5f131eb |  | note | VERIFYING DOCUMENTS: This ITP
text | 9b02e033-f87e-4f56-9aee-1167cdf0ba1c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 00fa6bcd-66e4-4bfb-8a80-5ae2a67294d7 |  | note | REFERENCE: 703.10 (a)
label | 349f5e6a-42d5-457d-a8ec-860803e9f3fd |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | cfff6db4-1224-4af8-b84d-570cb9a99899 |  | textbox | Enter: Teambinder Material Approval number
label | e18d1a13-9bd3-4893-aa27-f27dfa3ddd80 |  | note | METHOD: Document Review
label | 9b23e603-9910-4932-8682-5ba16082d9e8 |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | dd10bfa1-084c-44ee-ab8c-39eda2014c32 |  | note | CATEGORY: IP
label | b953b83c-e893-4883-8e7f-25a92dfa07b4 |  | note | RESPONSIBILITY: Nominated Authority
label | d1f488aa-a57b-4626-9148-f06b439fe5f7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 633608b4-026f-4f17-8767-f2aa3f82679b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 IFC Drawings
label | e5900af1-9ec5-4c43-a9dc-27648cd59fc6 |  | note | REFERENCE: MRPA Quality Management Plan
label | 9fd1f4eb-00eb-4a10-8260-f64a0631d4fb |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 151f49f9-1cde-4f26-a491-1b5ddce9a9f2 |  | note | METHOD: Document Review
label | c7d61c57-d4e1-40d3-a9f6-3f0c36b2b358 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | d9e37283-914e-4a21-903f-f08a604cf015 |  | note | CATEGORY: HP*
label | 8886c57b-c04b-4822-8062-d74f62740d39 |  | note | RESPONSIBILITY: All
label | e763f38d-a6f5-44da-8f3a-971af90cd8b3 |  | note | VERIFYING DOCUMENTS: This ITP
text | faf32203-df43-43d5-87f7-1b31f2fb561c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Survey Set-out
label | a7838c25-6c0d-4114-ab37-cf722f3fea54 |  | note | REFERENCE: IFC Drawings
label | 09b35e83-dec6-410f-a73a-6a6c022fe057 |  | note | 703.17
label | c4a9f68a-a585-4674-b624-d7f416979a29 |  | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | b78a9c25-56e5-4fad-8766-df1068a7210c |  | note | The Nominated Authority will review and confirm the set out.
label | 4e5ae1a3-9d95-40d0-a260-1e620414fd2f |  | note | Attach: Survey Report
label | 03719059-4101-48ff-9bc5-1182f1a58cf1 |  | note | METHOD: Document Review, Measure, Visual
label | a4eb4665-4acb-4ce8-a76b-162d3691d740 |  | note | FREQUENCY: Where applicable, each lot
label | 03244323-0854-400d-be82-4c356740530e |  | note | CATEGORY: HP
label | 025b6ca0-545d-4da9-98d4-a769673e1d79 |  | note | RESPONSIBILITY: Nominated Authority
label | 01f8ab2f-8b70-4db0-9d33-964836c455fe |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4214e0f8-d7c4-4e6d-b78e-faaa5aef23df |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Excavation
label | 142b42e8-b381-4d48-b5f9-aeaf588547e5 |  | note | REFERENCE: 703.20
label | 56147b04-b92a-4d03-8bd8-d4b287a798c0 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | e223968d-d742-4fa5-b262-66e8ebd2ffbe |  | note | Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | 764ec928-c6a7-4f55-9706-c450a13f4ec4 |  | note | Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | 40badd41-4399-4e5c-82e0-6c20894e59cf |  | note | METHOD: Visual, Measure
label | 958d5f42-2d0d-4dd6-92a5-dd5e234785c8 |  | note | FREQUENCY: Where applicable, each lot
label | 2de75dcc-e024-4830-b70e-febd227c618a |  | note | CATEGORY: IP
label | 49b3f3c3-d3bb-4fef-93ad-ceff81c2cef9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2bceef36-d99c-4e4f-b31c-fa4f304c2e3c |  | note | VERIFYING DOCUMENTS: This ITP
text | 718034fc-9425-4757-9883-aa52bbf78bb3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Bedding Material Placement & Compaction
label | bc7a9204-8cfb-4908-a782-6b400a0607b8 |  | note | REFERENCE: 703.21
label | ae6eb902-e6d5-4017-8aef-e148609ac4ba |  | note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings).
label | 457cd01c-b9cf-41f7-92f3-8b5308d519ea |  | note | Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | d91b9d9c-e093-43d2-bec1-52bd0f05c18c |  | note | The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | f1f3bff4-0e3a-4eb1-ad36-dc67a136aa53 |  | note | All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | 3c1675b0-d476-4b65-afe1-ecf85608c80d |  | note | Attach: Bedding Material Delivery Dockets
label | 73a47b3f-0100-4281-bed0-90df68d48511 |  | note | METHOD: Visual, Measure
label | 72248299-c7ed-4750-ba0b-7d2f2923080c |  | note | FREQUENCY: Where applicable, each lot
label | 4daa3b7a-5a3f-4752-807a-e70d2e4c2240 |  | note | CATEGORY: IP
label | 6bb98be8-74e9-4a17-b744-90d58011a9de |  | note | RESPONSIBILITY: SE/PE/SPE
label | d40b1af2-6c14-4d47-8821-b1a49624a9b3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0db89b33-f857-4df1-b59f-ad835fa18dea |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Formwork Construction & Placement
label | c0da65d1-22be-44da-8ff0-2afa26e08ce4 |  | note | REFERENCE: IFC Drawings, 703.12
label | f38f9eb2-5be7-4249-b33e-f946a48412b1 |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | e1dc3451-ff00-444b-8271-adf7d99a1db7 |  | note | Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | 94053d09-488c-4e9c-a501-5a0e2c71972c |  | note | Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 89f5c656-9477-4a0e-972c-28dd5defeeec |  | note | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 08990272-ab54-4f95-9f78-270a905e1dcb |  | note | METHOD: Visual, Measure
label | a454c1a6-e164-4564-ac1b-c63461135b99 |  | note | FREQUENCY: Each lot
label | eb0abea3-d652-4079-aa23-221966aa0681 |  | note | CATEGORY: IP
label | 09d02a1d-71cd-4672-a152-38103b7038d7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 5a80dde6-9a62-410a-b7a9-967a9fb8dd3a |  | note | VERIFYING DOCUMENTS: This ITP
text | 488f295a-649b-44c3-a865-76306b8b0dca |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Construction Joints & Matching Existing Surfaces
label | 303a56f9-eb25-4da0-bc75-7f92895960fa |  | note | REFERENCE: IFC Drawings
label | 1be4c3bd-56bf-4008-8c72-b439346aa564 |  | note | 703.24
label | 94d1dace-2b72-4ce5-b6e7-d86a0e3ee816 |  | note | Relevant Council Standard Drawings
label | 94f1d077-7694-4694-a6fa-d63960ab4099 |  | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | d021fc90-295e-45e2-96f9-70bea3d12ea3 |  | note | Consult the relevant Council Standard drawings for the joint detail, these may require:
label | 54b11ebc-f254-49c8-8ace-b7a2bbcb45c3 |  | note | i. Concrete cutting of a shear-key
label | 98a117d7-e30c-45a7-92d2-c81c10e9d45b |  | note | ii. Surface roughening
label | df2e6e26-f9bd-4ccd-affe-434c8e5db5d3 |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | 001ad01b-14b2-4545-b720-fc7cef57a45c |  | note | iv. Cutting a groove for sealant
label | 152de112-e74c-4283-9b8b-82eda802de5f |  | note | Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 8c4fd5ce-dff3-4f22-b5c6-381662d3abd9 |  | note | Transitions between different profiles shall be made in accordance with the drawings.
label | 9f78dec5-4ba6-4320-8c07-fe96a2ff8e66 |  | note | Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | 17c8bc9b-5f68-4d23-a3cc-02ccf463cedc |  | note | METHOD: Visual, Measure
label | 230f0890-f3b8-4b80-8d43-9479d66b579e |  | note | FREQUENCY: Where applicable, each lot
label | 6c412799-4c5b-4a56-91eb-0461d71bee12 |  | note | CATEGORY: IP
label | f983ae79-70c3-47ce-a998-50484baa226b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8a7dfedb-96d1-4a79-9c58-c18e22c43649 |  | note | VERIFYING DOCUMENTS: This ITP
text | 92397bbd-83c6-476a-9218-296159b4e70f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Isolation Joints
label | 7f918859-f4eb-4837-9a12-84d5de548fc1 |  | note | REFERENCE: IFC Drawings
label | 55dcf850-5b29-4722-aea1-122eb5494ede |  | note | 703.26 (c)
label | 96beb1de-8d52-436c-b269-752bc740a2e8 |  | note | Relevant Council Standard Drawings
label | 67038975-b927-4fc4-895f-f56fc952f9e8 |  | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | b440fe90-e517-4343-b361-abc937bfcf76 |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | 50c83f32-d753-4285-b35b-e94eee30a534 |  | note | ii. at any location marked on the drawings
label | 8c9522d2-b14e-4b5f-b6fe-22cb6cabf25b |  | note | The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 50bd0db4-1493-4846-934a-d2630a9f3149 |  | note | METHOD: Visual, Measure
label | 1067e70a-718e-448b-aeb6-3d7a30affc81 |  | note | FREQUENCY: Where applicable, each lot
label | 9ae558a7-ba20-4a27-a643-5ba71f8359ef |  | note | CATEGORY: IP
label | 03074616-c18d-4ff4-a8d5-12468d30b918 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e4e72195-af24-4565-a16c-e5e3e25abf29 |  | note | VERIFYING DOCUMENTS: This ITP
text | 06115ccc-3103-41c9-b595-247c3a648bf3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Reinforcement Placement
label | a59e409d-0594-4dbc-a7be-1d67dce6cad9 |  | note | REFERENCE: IFC Drawings
label | 9cf582d5-d1f2-4afa-96c8-53a1f75817ec |  | note | 703.13
label | a5f1ce24-2fbf-4ac9-a133-4026269ed1ab |  | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | b39a0c49-71a1-49e5-ba4a-e5df5c8569ab |  | note | Any splice lengths achieve the minimum length and are in contact for this length.
label | b03c507a-aedc-4abc-82ef-cab3ce182e7f |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 221001da-0f32-4be1-a382-dc8cb6d0599f |  | note | The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | fa6116f9-b255-40eb-b599-131ba6835c2f |  | note | Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
label | a80ef737-ed02-48f5-8c68-86fb2b5dcb7a |  | note | Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | 66accac7-285d-4695-95cb-947c0d0e8301 |  | note | METHOD: Measure, Visual
label | 5192121f-82ad-4b1a-9dbe-e1fad1d43119 |  | note | FREQUENCY: Each element
label | 30e6767c-a1ac-4ac9-8089-bf979ff0fc08 |  | note | CATEGORY: IP
label | ecebbfcb-6f8b-4b0f-97da-c1c7c69cfde5 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | bdfd63a4-ae5f-4b47-a008-06895e0a02a1 |  | note | VERIFYING DOCUMENTS: This ITP
text | afc5cfe7-4d69-4b21-b185-de0a3ea85cf6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Pre-pour Inspection
label | 26edddfa-c2aa-4a3a-b461-348ca22e3f20 |  | note | REFERENCE: IFC Drawings
label | 5780def2-0f21-40d7-98ed-49bb516a072b |  | note | 703.15
label | ed3e4965-d975-40d9-93a8-a0cb58efe45b |  | note | 703.21
label | 1347af33-52a5-4361-9279-be26ba5f2373 |  | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
label | e3ea64c6-0fd5-4ea8-b1ba-966594ae0bc5 |  | note | METHOD: Measure, Visual
label | 913df962-5adb-42f8-a967-4c9675e5601a |  | note | FREQUENCY: Each LOT
label | 2c440574-bb3f-4c6c-8262-918ee577890e |  | note | CATEGORY: IP
label | 916473fd-cc98-44c4-90d1-53a8e62a9a9e |  | note | RESPONSIBILITY: SE/PE/SPE
label | ec11d88c-9b10-46d5-833a-fdf5459d662a |  | note | VERIFYING DOCUMENTS: This ITP
text | 86aac8e7-f520-41a3-b9a5-d80e84f80233 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Weather Conditions & Evaporation Limits
label | 995f4cb6-e4d8-4889-810a-09efe9cfcda7 |  | note | REFERENCE: 703.09
label | 6bce248f-6b0e-4918-8219-3aa6b66f3a6b |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | 09b04a62-41eb-4550-8f67-4d26f6091694 |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 496c4311-ddcf-4ace-8524-5db5ef4cfb86 |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 379d2758-8d19-48dd-a404-a726c0d492f9 |  | note | When the evaporation rate exceeds 0.50 kg/m˛/hr apply evaporation retardant at the rates specified on the manufacturers TDS.
label | c9b9f98a-a0f0-4105-baac-af307b6b1985 |  | note | Record: Required information on the Concrete Pour Record.
label | 29622ef7-76e0-4f7e-9ef0-e782988d03f4 |  | note | METHOD: Measure, Visual
label | 6661cc9a-8ff1-43ab-9ab4-ceadbffc450b |  | note | FREQUENCY: Each LOT
label | d7f62ce8-fec1-49c3-ab1d-d48aef02d05f |  | note | CATEGORY: IP
label | be7f8173-7e72-47a4-a6d9-52a6bdc9ab1f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 64186e49-d058-48a8-86d0-5f05b55683a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9b9a68ce-7e11-4d5c-a2a9-ff5631a4a911 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Concrete Testing - Sampling Frequencies
label | bf038c02-cd08-4bb9-a172-1de4650d47d9 |  | note | REFERENCE: 703.11
label | 7a8a12a4-93fc-487b-90b2-87d7ee094376 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | c8b89f65-6107-44ab-bbae-54f127cf0bef |  | note | 0mł to 50mł = 1 sample
label | c0bfe94a-b65b-4b02-9cfa-b0d356f280b6 |  | note | Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | 5de94cd1-1911-4da9-b8f6-ea7907601f11 |  | note | Compressive strength cylinders = 2 no. 28 day strength.
label | 2a490486-f576-4fd2-ac4c-87b5f9d53b86 |  | note | Record: Required information on the Concrete Pour Record.
label | 70ed3ba0-89dd-454e-8abb-439bf12e9c99 |  | note | METHOD: Test
label | c6bf53a0-5f79-48e5-ba7e-782633a0b68b |  | note | FREQUENCY: Each lot
label | 1d2e57a4-9c8f-4174-9959-dde83c5cbe54 |  | note | CATEGORY: IP
label | 8a18bee0-8152-4568-a93d-8c5a34fe3279 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | 5c58a97a-4440-447f-8a92-5c5cf3f42643 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1e2bcc33-4327-431c-b339-90a1ff6324e5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Concrete Testing - Slump
label | c6f6948a-cf32-4f28-8836-c1436c1a6da1 |  | note | REFERENCE: 703.11
label | 0e48c4b3-08fd-43e9-bcd4-5e838d333fa4 |  | note | 610.16 (c)
label | 17745ac2-4b59-4e95-a906-6788da696466 |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | 90e12499-fd62-4678-8a9c-be13ea322f08 |  | note | <60mm = ą10mm
label | 148020b5-db17-49c0-b401-f008150528d6 |  | note | e60mm to d80mm = ą15mm
label | f91baeb4-910c-4ae3-b9a8-167eba6ebb00 |  | note | >80mm to d110mm = ą20mm
label | 1db1f62c-ea63-4b83-8ef4-cde80785b798 |  | note | >110mm to d150mm = ą30mm
label | 5a007382-7ddf-4a12-9420-67865aa5bd1e |  | note | >150mm = ą40mm
label | d842e9f1-cddd-4e21-a011-f2708191691f |  | note | Record: Required information on the Concrete Pour Record.
label | 10560cf5-310a-4300-8dc6-e70af86078a1 |  | note | METHOD: Test
label | bd2d5865-7104-4ca7-99ef-3c713d3fdce9 |  | note | FREQUENCY: Each sample
label | 92d03f77-ac5e-4a4a-8007-91f7ddf7651c |  | note | CATEGORY: IP
label | 153d8a1b-9b6f-4d66-b079-e18e94d271d9 |  | note | RESPONSIBILITY: Concrete Tester
label | 79b87962-c62f-4dde-b920-419d5fcf5fc0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4458bedd-12b7-48d3-9576-59ccdd1770b0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Concrete Testing - Compressive Strength Cylinders
label | c930d419-bffb-41cd-96cf-26a181674b3e |  | note | REFERENCE: 703.11
label | 4a5ae845-a2c5-4bd6-a1a8-08e8cc082b3e |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | a949b6d2-86d2-4467-8d5b-752b378c3246 |  | note | Record: Required information on the Concrete Pour Record.
label | d3a96772-469d-49a0-9b4f-effeb9adae69 |  | note | METHOD: Test
label | d8c0f504-0580-4d83-a5c7-887e02c65d8f |  | note | FREQUENCY: Each sample
label | 88af0125-1dff-4c52-b4db-a0813242af2a |  | note | CATEGORY: IP
label | a4135241-86bc-4b23-884b-52f74473ffa6 |  | note | RESPONSIBILITY: Concrete Tester
label | 958f1565-1e65-4909-b127-dd49c0b75968 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0546dfbe-a0a5-4269-96b6-d27eccf467e9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Supply & Discharge Rates
label | c24f4f3e-8ee2-4e11-9d38-ea131799860f |  | note | REFERENCE: 703.08
label | d13d0320-7465-4516-8aa2-9a4b86b4be34 |  | note | AS1379 Clause 4.4.1
label | da70c1a8-232c-4675-8c29-1c02853ea225 |  | note | AS1379 Clause 4.2.3
label | f1523113-bdab-443c-9a36-1bfaae119fb0 |  | note | AS1379 Clause 4.2.5
label | 55684a67-b94b-4f8a-9b77-b97036899271 |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | b82c21ff-5df3-4638-b991-2ad5bbbca93d |  | note | Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
label | 9f34c6b0-c212-4960-8e68-5250e93a08c8 |  | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | f7b7a674-9fa9-4a08-b3a1-52d2ee80dc46 |  | note | If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
label | bcf81ce0-bcdc-40a3-89dd-d384f503484e |  | note | Record: Required information on the Concrete Pour Record.
label | a2743538-bbe3-44a2-a360-207dd8ceb8e3 |  | note | METHOD: Measure, Visual
label | 7f12b089-2e42-4d45-a5e2-99ed804f082d |  | note | FREQUENCY: Each load
label | ba288490-551e-43be-8d0d-b03997e6ed16 |  | note | CATEGORY: IP
label | 4c7d5fef-a709-4ee6-b464-3bc46c706631 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | e96a0c83-b2bf-4027-ae03-dd36be4b4b53 |  | note | VERIFYING DOCUMENTS: This ITP
text | 83be8063-f35f-42f0-97ae-4ae64d7c6046 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Placement & Compaction
label | 686e0b3b-2654-4888-b6bf-f77d66ff8eab |  | note | REFERENCE: 703.08
label | da043dd6-8b16-42b3-a8b4-04f7e2624183 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | c3cf066a-aa59-44a7-87ce-ace31820a177 |  | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | fd57d912-a84e-436c-a3b1-5d9e793e32f5 |  | note | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | 92b08960-ac68-457c-8cbb-bab999e4ed26 |  | note | Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | 83824815-dfe8-4c65-bf14-3139a7304f67 |  | note | Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 7ccdb67d-f293-4ba8-b696-7b41c26b1f1b |  | note | Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | 1b986a6e-cbe0-4904-b362-7072010393b6 |  | note | Record: Required information on the Concrete Pour Record.
label | f548db4e-33fd-4408-b429-3c872a212c34 |  | note | Attach: Concrete Pour Record
label | 618c3191-52a1-4dcf-87a8-5004a897dbe4 |  | note | Attach: Concrete Dockets
label | 054d4dac-ace2-4797-b3d5-3e29b1b92ede |  | note | METHOD: Visual
label | 6a5d8f39-c702-4ede-bb5b-0ecb29ed81de |  | note | FREQUENCY: Each load
label | bc871f77-8da9-4e97-874f-ebf9408e0325 |  | note | CATEGORY: SP
label | 5c7e8fe4-338f-4b18-8ea0-42bb4cfd75f9 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
text | 13e5ba35-15a4-4d69-872d-aa313b5dc1bb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.14 Surface Finishes
label | 02e731d2-fa00-4f58-b4c7-bb2c8270d417 |  | note | REFERENCE: IFC Drawings
label | 22b4bc1c-f718-4c56-8039-6e2ea477dd8f |  | note | Relevant Council Drawings
label | 66ab382c-087f-478d-ac3c-bb6d05483c34 |  | note | 703.25
label | 5bb651f2-a1c7-4fa9-a2e1-b3fded488cfd |  | note | ACCEPTANCE CRITERIA: Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
label | 45e034df-23c1-4e74-beb1-cf720d533217 |  | note | All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | b4f2cbd6-9aa5-4d11-9a23-17a896145e3a |  | note | METHOD: Visual
label | e8f4fc70-6cf9-405b-846c-11857e53bc13 |  | note | FREQUENCY: Each lot
label | 76c87c6e-ea81-437c-897c-078c3aa1e119 |  | note | CATEGORY: IP
label | 11310d72-63f2-4292-8618-8eda0d9df821 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | d143bbdf-7318-4f28-99f1-d470d165b6f5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7d8fc359-2d6a-41a2-a8e6-4ce1dae08bf0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.15 Marking of Conduit Locations
label | d3eaeb62-de60-420b-8f25-1c5ce9938947 |  | note | REFERENCE: IFC Drawings
label | 56cf9e2f-695b-4406-9a55-de279ca92b1e |  | note | Relevant Council Drawings
label | 63e3de5e-c57c-46b2-93ee-abf0dc4ed4e5 |  | note | 703.28
label | 47177bff-040c-4fb0-a25c-1af0187d56bf |  | note | ACCEPTANCE CRITERIA: The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
label | 3d7d9cf1-45a9-419c-b6e2-e939dfebfe04 |  | note | METHOD: Visual
label | 7f821acc-2ceb-4159-a757-50bfd43c41f7 |  | note | FREQUENCY: Each lot
label | 8cb1d564-55a4-4079-bab4-ded6e547f9c2 |  | note | CATEGORY: IP
label | c5561e2e-19c2-46dc-a044-3240ab0c172d |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | e663a2cd-55fa-4540-9a33-eba87ce314ac |  | note | VERIFYING DOCUMENTS: This ITP
text | 20cc596e-1f1e-4330-846d-2924e48e3cba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.16 - Crack-control Joints / Weaken Plane Joints
label | 3e69a23a-4462-4bc8-a8ae-97e49c8efc3e |  | note | REFERENCE: IFC Drawings
label | 7542eca8-64d3-420b-ba51-d5af8f7ce79c |  | note | Relevant Council Drawings
label | ad0fa10c-feca-4c5b-b8b3-d9bebd329e93 |  | note | 703.26 (b) (ii)
label | f16f992f-fbf6-4d25-86bd-77c299cab644 |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | 6b594f57-a7cb-4871-952e-69fb22a1a2ab |  | note | METHOD: Visual
label | 5a805a79-6bea-4dd3-9e9a-b3ae70471861 |  | note | FREQUENCY: Where applicable, each lot
label | ea76be95-2d11-45cc-a706-550ee79cc49e |  | note | CATEGORY: IP
label | 837aaddb-4d5e-483f-b3b1-3fa707a11427 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b56b2e74-620d-46e6-a6b1-b803fd254bc0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1c318a2e-a900-4d32-b524-eae5982e0f1e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.17 Curing
label | f664f196-4304-401b-9a6d-cf4fc8338579 |  | note | REFERENCE: 703.10
label | 5a87490e-7108-4a75-9545-e62f6883b188 |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | e981229b-cca7-4861-bbde-1c02a035fe03 |  | note | Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | d86970d2-fc99-4369-bb7b-8134639fbcb8 |  | note | The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | d977bcd0-771e-4efe-8c1d-3eabb96e8a1f |  | note | Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | 8156d31b-254a-42cd-899e-41f865210288 |  | note | Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | 3b550acd-e903-4f42-8bdb-226db3b68602 |  | note | METHOD: Visual
label | 10768512-6081-43fd-9149-9491bfb233b9 |  | note | FREQUENCY: Each lot
label | b100188f-81cd-4da8-be55-2a319c2c6a78 |  | note | CATEGORY: IP
label | 815d3ddc-a5d2-47e2-80cd-d279b662de48 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | e73e6247-ae6f-4f65-b83c-27cdfe195adf |  | note | VERIFYING DOCUMENTS: This ITP
text | 6a734ce5-4f32-459d-8db7-436470ac469c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Protection of Newly Poured Concrete
label | 9ffdc576-6b3e-4350-9111-d2d1255e221e |  | note | REFERENCE: 703.27
label | 39dc6114-0062-4354-8212-1f764eb3d1c6 |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | 4962ddbf-821d-4186-9527-627e2201df59 |  | note | Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | ed43468f-b681-4972-ad37-de75b00c199a |  | note | METHOD: Visual
label | 78e244a4-b093-40fe-ba09-bdac71f0f516 |  | note | FREQUENCY: Where applicable, each lot
label | b11e04e6-199a-4be3-b6b9-597e2ed867e2 |  | note | CATEGORY: IP
label | d1d10943-0387-49a1-b352-65419d2af103 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | d4528f44-671f-489c-8542-f34e572b196b |  | note | VERIFYING DOCUMENTS: This ITP
text | 15734b90-e18d-4351-b89b-7e1168ac0ecc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Stripping Formwork
label | 4a21cc65-d331-4040-a4af-acadc82bd328 |  | note | REFERENCE: 703.12
label | f3c2317f-3937-4761-8591-fc8d4339c58c |  | note | AS3610 Table C2
label | ddf320f1-9a20-436b-97d1-fcaa134e5785 |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | 92d864ca-f83e-4a02-8a03-5179ec4c023d |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 511ba437-5e8c-4c70-a900-abb30c9d166d |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | 921a52db-5acc-4e48-a053-84d3b1078807 |  | note | METHOD: Visual
label | fa6206e5-600a-4abe-8e61-2633380a0610 |  | note | FREQUENCY: Each lot
label | 2a0ee069-f83d-4e4a-9173-4683af7880c1 |  | note | CATEGORY: IP
label | 30ff9760-4be0-4040-93c0-bd05ca956d7a |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1a018ecf-c4f1-4d55-a56b-9835bd1ebda4 |  | note | VERIFYING DOCUMENTS: This ITP
text | ff69ed61-854f-45b0-aa6c-41f030e8f838 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Backfilling & Pavement Restoration
label | 6f9c0f46-b316-44a3-bd97-439f67bf7fad |  | note | REFERENCE: 703.29
label | 37504a29-09e0-475b-86e5-04dd86785576 |  | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | 793d5008-af04-4f05-a9fa-2f41899dc450 |  | note | METHOD: Visual, Measure
label | 63e0cd06-04bf-46b3-a609-fe66ae567391 |  | note | FREQUENCY: Each lot
label | 2d68a0e2-a0df-4640-99bb-1a9a8e7fcad1 |  | note | CATEGORY: IP
label | f9144373-373c-4531-8369-70e48c41e78e |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b938333a-16d0-4287-abab-30fc81d037dc |  | note | VERIFYING DOCUMENTS: This ITP
text | 48d13244-8320-458e-9aff-3bd0b663e374 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Surface Inspection - Cracks
label | 1008cad6-4e9d-45a3-a05e-6365835ab4b4 |  | note | REFERENCE: 703.3
label | 0a71989a-54a0-40dd-bbdc-f75bb577dc86 |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | 1de9da6d-8ade-40d2-a2a6-81008247d6ef |  | note | If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 4b2714ec-6c81-447f-bbc1-e1f382264135 |  | note | METHOD: Visual, Measure
label | ed645c06-705a-4716-a850-78ec151e9b3d |  | note | FREQUENCY: Where applicable, each lot
label | 1f9a495b-7411-42a1-9685-8acd3b1cf84b |  | note | CATEGORY: IP
label | 0cb62020-fb40-4b95-833e-f3168d51d46c |  | note | RESPONSIBILITY: SE/PE/SPE
label | 42a19ecb-4c0f-40a9-bc8a-796c37a0b2a5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5198e088-5deb-409b-b46a-f04689bb2ab1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Surface Inspection - Surface Finish
label | c8caf445-e998-4b83-a0d4-b608bb59a78e |  | note | REFERENCE: IFC Drawings
label | 895f9fb1-60b8-4988-a03c-35295529b9e3 |  | note | Relevant Council Drawings
label | 4db0ad57-8b07-4b0a-9b33-7a68660202d9 |  | note | 703.25
label | 878ac47e-f942-4ae3-81cc-7eea0b3e9b66 |  | note | 703.10 (a)
label | 99ccf68a-3bcc-47d2-9c79-fd2a9903591d |  | note | AS3610 Clause 3.2
label | 920db7c3-9db7-43dd-844b-39a3d25ba842 |  | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | 55ce3ad3-9cba-4fac-b9e2-abf64b9a752f |  | note | All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. Class of finish:
label | 13d6790e-7b7b-4b92-ae41-b045aa4bb775 |  | note | Permanently hidden surfaces = Class 4
label | 53b90c30-ca8c-4842-a428-e74c774c5c65 |  | note | All other surfaces = Class 3
label | 9fea2619-3d77-4d30-b0de-e96f241d51b3 |  | note | At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | 05d9f868-85a4-46e7-a816-01de26bdaf4d |  | note | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | ba508032-afb3-49e3-b3bd-a6ca9fe3f903 |  | note | METHOD: Visual
label | 4170468c-df20-476d-94b0-f1b2a13dcf5f |  | note | FREQUENCY: Each lot
label | 30a6384c-7dbc-488c-b31f-95012cb90661 |  | note | CATEGORY: IP
label | b065f2d9-a74d-4ed2-bfbd-99557b7ca5a0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4d04266f-03d2-4a75-80fa-189d2c0ffc08 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6eb454d8-abaa-49a7-a19c-2a2cab22750e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Compressive Strength Test Results
label | 3e962578-a5e7-420b-8af0-686d38fb86f8 |  | note | REFERENCE: IFC Drawings
label | 1baeedff-e090-4751-8c13-bf870702bbc9 |  | note | Relevant Council Drawings
label | 2f91f96a-a1b5-4209-8bbf-9c99dd44dfeb |  | note | 703.11
label | 09b331dd-af45-418a-90a3-b1b21d6ec48d |  | note | Table 703.111
label | d11da278-ff70-4426-bc51-2b7ace7a4745 |  | note | ACCEPTANCE CRITERIA: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 598f5524-f9e7-4a96-b087-5bcd58e3af3b |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 185b4fa6-6441-45ea-b73e-ec2056740f1b |  | note | Attach: Compressive Strength Test Results
label | f25efa24-f2fa-4a23-9f39-05f26677087f |  | note | METHOD: Document Review
label | a6805ae1-706c-42b6-b2d7-c79a27797f6e |  | note | FREQUENCY: Each cylinder
label | aae93d42-8792-4125-96d2-dbc4020c8e8b |  | note | CATEGORY: IP
label | 18b0173c-27d7-44cd-96bc-2329450ae517 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 12bc6167-ddd7-492e-a032-fc707160bbce |  | note | VERIFYING DOCUMENTS: This ITP
text | 20ea4801-d8f6-47c4-9ae6-448a5b6eb68a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 As-built Survey
label | e8afef9d-bcd2-4b32-acd7-e13d05ba78fd |  | note | REFERENCE: IFC Drawings
label | bdd483aa-a8aa-4cdc-a34a-5b7a5d3bd893 |  | note | 703.15
label | 19efa59e-fdd2-4a50-a2e3-e575a5c4d29d |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 44ebe256-f5ea-4acb-aef3-3732fcdf1fc9 |  | note | Departure from RL = ą10mm
label | 2a9609a5-c502-43b8-a322-5ef1bd4dbba4 |  | note | Departure from alignment = ą10mm
label | a6a295c8-b9d5-41a5-b684-fff3228d49c1 |  | note | Rate of change of deviation from RL or alignment = 10mm in 10m
label | 29916bd3-e8bc-4389-a161-358632eb5309 |  | note | Irregularities in alignment = 5mm in 3m
label | a746f96a-91b8-4103-baf3-ea38879561c2 |  | note | Section dimensions = ą5mm
label | f6059265-6188-4ce9-a872-69683eacc038 |  | note | Section dimensions (less than 25mm) = ą3mm
label | 2c7a8d57-94d8-4fca-bd94-781fa355e29b |  | note | Width of pavement = -5mm, +15mm
label | ee7f4a51-0aa0-47c7-9d4c-d4817730dcc1 |  | note | Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
label | 68afdbfb-b1f8-4220-9831-1c6cb74a3429 |  | note | Attach: Survey As-builts / Survey Report
label | 3365698e-35da-4582-904c-e281ed79d792 |  | note | METHOD: Document Review
label | c4869b62-f854-41d0-8cc4-ee02c488f071 |  | note | FREQUENCY: Where applicable, each lot
label | d4ce7545-4f5c-45f1-91b9-74a1c220e2dc |  | note | CATEGORY: IP
label | c05a36d2-b8dd-4ed7-a449-b6fa6e330d91 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 392864dd-ef46-4b72-bc17-b0f2642cc616 |  | note | VERIFYING DOCUMENTS: This ITP
text | d989132b-7c3c-4202-86cb-97176b3ce1bd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Non-conformance Report (NCR) Closure
label | edcf176f-5c84-419f-85bc-0a0b5b76c530 |  | note | REFERENCE: MRPA Quality Management Plan
label | bccbca5e-8477-4f68-b7cb-a2c8dbf289de |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | f06c0393-ea11-4247-918c-c9bfe3ab5aa9 |  | note | METHOD: Document Review
label | 195a2d1e-cf15-4215-ab5c-77324e4fca7f |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e4f423de-62b0-47b7-83bc-21d2158b3b08 |  | note | CATEGORY: HP*
label | fa076dc2-095e-41ec-976d-f224923aa600 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f870407a-d71c-4af1-9429-67dddbf9a70f |  | note | VERIFYING DOCUMENTS: This ITP
text | 4e37935c-603c-4609-856c-2561a9a50bd5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 13a724da-26b8-4bce-ad3d-7469b6ea2834 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 4d035ed5-cce6-4db7-b878-be8fed9b83ca |  | textbox | Name:
text | ae5deb4f-bca1-4540-b743-514bc1b2a5e9 |  | textbox | Position:
text | f866a540-8f33-4a4f-b9ab-22e262c99f2e |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-Rail-Ballast Conduit Install Rev 0 | itp |  |  |  | Yes | ITP-RAIL-Ballast Conduit Install Rev 0 | df44e481-dc18-4fd3-a14e-34b28ac55a13
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 97a9bad6-a4c1-4634-b4e3-d48c8a39b153 |  | note | Document Title: ITP-Rail-Ballast Conduit Install
label | 558354c4-387b-4ec0-941e-33f8224de155 |  | note | ITP Description: Ballast Conduit Install
label | 21b6c39f-3e42-428e-b4ab-a61bc310e30a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
label | f4cdb780-7000-4c53-8fe8-79219ff4a9db |  | note | Discipline (e.g. CIV/STR/RAIL): Rail
label | 75d2ec08-5b41-4c68-beef-987925863134 |  | note | Revision Number: 0
label | 02e4ff52-c056-4c76-a569-8dc795c49e9d |  | note | Revision Date: 23/06/2020
label | 7b601a7b-3c8b-4a25-86d1-562b92eb76d4 |  | note | ITP created by: Mathew Holm
label | 2bc0ee3f-fc4a-4ef4-a4fe-7037e6a9558a |  | note | ITP approved for use by: Romualdo Magpantay
label | 5b00dc35-7371-45ce-9243-13ddd2c63d35 |  | note | 1.1 MTSP 030100-01
label | da9a610e-0844-4522-897b-e72c9c4e6847 |  | note | 1.2 MTST 000002-01
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | 2.1 Obtain and submit Certificate of Compliance for the Electrical supplied Materials
label | 71192f11-0d14-484f-b579-ca403714ce4e |  | note | REFERENCE: IFC Drawing
label | d4c67bfd-beb4-44c0-88ef-4ca47a2e1a9d |  | note | ---------------------------------
label | 537835ae-b8da-43b6-b458-915a4dbf2386 |  | note | ACCEPTANCE CRITERIA: Verify supplied Electrical materials components are in accordance with AS/NZ standard & design drawings.
label | 722e2652-b1a3-45dc-85ea-225095560890 |  | note | 50mm Galvanised Pipe
label | 8fea203d-d4d7-42e1-95d3-805a8314dcfa |  | note | 63mm PVC Pipe
label | e65320e4-c0f1-4672-8967-14f5a165c351 |  | note | ---------------------------------
label | 8dc1ab27-650e-44dc-bc98-16bcc5331467 |  | note | METHOD: Review
label | 2bb0da82-ce59-46d2-9027-e7a3fc2186df |  | note | ---------------------------------
label | d1af8c37-a849-4e54-bb83-3b296fc0fe08 |  | note | FREQUENCY: Once
label | 50e68fd9-34c5-4c6d-8609-666901fe4145 |  | note | ---------------------------------
label | 0c8a5a30-ddb1-4d98-be9f-a808c89c29e2 |  | note | CATEGORY: HP
label | 7dbedda9-d376-4cfd-9f14-047ee1ce050a |  | note | ---------------------------------
label | 3159dd35-6c01-4437-84a0-2710ac88dbbe |  | note | RESPONSIBILITY: Nominated Authority Track Supervisor Site /Project Engineer
label | 0cae7225-12ca-4426-86cb-09fb0fc006b8 |  | note | ---------------------------------
label | f4167d2c-085a-4b00-9181-2bc5a50bbb4a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | c87855fa-fbbc-4001-9cc7-a09a324dde89 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Inspect supplied items upon delivery
label | 4b8fe71f-c36d-4bba-abd2-3c4992b37cd5 |  | note | REFERENCE: IFC Drawing
label | 4b9aee38-6c86-44a0-9f34-aa2f7bff3d90 |  | note | ---------------------------------
label | 7b55cdcb-6efb-4dab-b3d2-c3000681e53a |  | note | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
label | 37ef2e64-a90c-4657-987e-039925d9d1cb |  | note | ---------------------------------
label | a571958e-7670-41cf-882e-8e2c93ff2916 |  | note | METHOD: Visual
label | a10c00a6-415b-4c80-91fd-d01ba17012ae |  | note | ---------------------------------
label | e5c45951-785e-4dc7-a821-0aa012240d2e |  | note | FREQUENCY: Per delivery
label | cdadf134-f80b-4d77-8d52-d40ec953124a |  | note | ---------------------------------
label | b63692d2-5749-4bc2-8974-21281b5091c9 |  | note | CATEGORY: IP
label | 293eb289-20cf-403e-8cb0-22b767b8f0e4 |  | note | ---------------------------------
label | 649e6b7e-ed64-4d4d-9213-eca227d0a476 |  | note | RESPONSIBILITY: Track Supervisor Site /Project Engineerr
label | 66653b80-c3a1-4c80-b220-965f594d782e |  | note | ---------------------------------
label | 8ca6735a-28bc-4752-95db-1ca9c5eeacc6 |  | note | VERIFYING DOCUMENTS: Material Inspection Report
text | f5dd179a-5258-4d79-8086-95bcbe8d47fc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Ballast Trench Excavation
label | fd03ae39-938d-47b9-8153-426125959ddc |  | note | REFERENCE: MRP-016-C-ACD-DRG-09-NWA-CTW-9013-A
label | da932c3a-520a-4938-91e1-860a904876a1 |  | note | ---------------------------------
label | dfa1be5d-aa18-4eef-b538-d625aa2ed824 |  | note | ACCEPTANCE CRITERIA: Excavation midpoint between sleeper spacing 685mm
label | a4bdad1f-7221-4530-8f76-1213ca76007d |  | note | Ballast Trench does not exceed 150mm or base of track sleeper
label | f35b3402-6602-44ef-985a-5d95887ea139 |  | note | Attach: Photo Site Excavated Trench
label | 12dafb56-9f0e-430c-a819-8123a3a6e97e |  | note | ---------------------------------
label | ca8c0b95-2371-4480-81fc-d228f2e12272 |  | note | METHOD: Visual Dimensional
label | 659e7a78-6ad2-4e62-b67a-2b32ca34ad0f |  | note | ---------------------------------
label | f24e85f2-d5df-43ca-874e-d6c4f8419e7d |  | note | FREQUENCY: per lot
label | 33bf7a09-972c-421f-b74c-925ace663269 |  | note | ---------------------------------
label | ac523259-2965-40c5-89ae-f096148fabb1 |  | note | CATEGORY: IP
label | e6dc1b05-3c47-4062-a7c7-36aee910c534 |  | note | ---------------------------------
label | ae5940b2-661c-49f5-835d-3f6127351d99 |  | note | RESPONSIBILITY: Track Supervisor Site /Project Engineerr
label | 71173a73-6d74-41f8-9294-e9f5167e7ff9 |  | note | ---------------------------------
label | 6e93a9f2-7b42-4fd3-ba59-a27b86399a11 |  | note | VERIFYING DOCUMENTS: This ITP
text | e4886aff-9a4c-40b2-8ff4-17d2e34e7eaf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Conduit installation
label | 59e13790-e418-478f-b7fe-4fcba0dcaea2 |  | note | REFERENCE: MRP-016-C-ACD-DRG-09-NWA-CTW-9013-A
label | 6d26d192-47ef-410f-a276-29cbf5385e47 |  | note | ---------------------------------
label | f4f1e6f4-f8e3-45a6-8847-247b9246597c |  | note | ACCEPTANCE CRITERIA: Galvnasied pipe is sleeved inside pvc pipe
label | 4541f9a3-a228-4b34-84a3-66d0a4a1c92a |  | note | Top of pipe is 50mm below foot of rail
label | cffe23ed-fa59-44d4-8a93-6e6b1b75874e |  | note | Pipe placed midpoint between sleeper spacing 685mm
label | 2099653b-c6d7-4bfa-9f17-55363b7bdd5c |  | note | Attach: Photo Conduit site layout
label | 6cfdf2b9-6735-4b13-b452-7f416873774f |  | note | ---------------------------------
label | a9cebadd-1da1-41b0-8326-bd8b5e80babd |  | note | METHOD: Visual Dimensional
label | 22cf8034-3269-4fe8-86d2-4aac8971a6dc |  | note | ---------------------------------
label | 50a84176-63c8-423d-8a8a-50a2f271554a |  | note | FREQUENCY: per lot
label | 9a95127e-12ad-486f-b707-9638b8b2d26a |  | note | ---------------------------------
label | 9f602796-9efe-406a-8aa0-5a9dbefeddfd |  | note | CATEGORY: IP
label | df9dcf32-08a4-47b1-ad5a-dfe5705fed8d |  | note | ---------------------------------
label | bc9daa9e-4827-4da3-a5cd-222fa2af2472 |  | note | RESPONSIBILITY: Track Supervisor Site /Project Engineerr
label | fde0ba37-1f18-46a9-a00e-bf271efe645b |  | note | ---------------------------------
label | d8802b6f-7b26-4b74-b3fc-b2e00f3add63 |  | note | VERIFYING DOCUMENTS: This ITP
text | cc36a696-fc0c-44a4-8338-58014641677c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Ballast Backfill/Tamping /Boxing Works
label | 3a39f6c2-09d3-4392-bff1-98121758ed3f |  | note | REFERENCE: MTSP 030100-01
label | 76a17a43-4a64-451c-8cb4-a46311dd00aa |  | note | Appendix 1 Table
label | 66d269e0-81e8-411b-a139-06e8eb8ef665 |  | note | MTST 000002-01
label | eb89dfe5-f6c1-4799-91fb-373ccb3fe387 |  | note | ---------------------------------
label | b206094b-eef0-484d-8fd3-6b7f6e8c030b |  | note | ACCEPTANCE CRITERIA: Track Geometry
label | 9068774a-db60-4d9c-ad40-567a47a7b1ab |  | note | Wide gauge < 12mm from design
label | b389a406-ea61-4614-b2fd-412c6ae21e01 |  | note | Tight gauge <-8mm from design
label | aeec721a-7d93-4645-872a-6fc63c43d7b4 |  | note | Cant <25mm from design
label | a498bdd0-4096-4457-8b77-1289ba0a06a5 |  | note | Twist (3.5m) < 15mm from design
label | 3f21fca7-4a3f-4ba1-8eb9-bbc6645f56ed |  | note | Twist (10m) < 30mm from design
label | 8a73420d-f5f7-47e9-91b7-ef57170e2cf8 |  | note | Top <20mm from design
label | 0123d7d2-de30-4326-8627-cb66d8863012 |  | note | Line <18mm from design
label | 00f6cc36-ea62-47cd-be3b-d41dc660c2b4 |  | note | Ballast shoulder 450mm wide 1:4 fall
label | 3ee1c5bd-1837-47e4-9c37-e517d5ff1733 |  | note | Top of sleeper free from ballast
label | 00505422-2dc9-4d55-8e3c-c071c8415c1f |  | note | Attatch: Track Measurement Sheet , Photo completed ballast profile
label | 3fe2eb06-e428-4b40-9678-9c823ad358c8 |  | note | ---------------------------------
label | e2aacde2-e451-4c1d-a2d8-899acd4ea427 |  | note | METHOD: Visual Dimensional
label | caadbf66-e662-4cd9-880d-c5bb35789a39 |  | note | ---------------------------------
label | 119ae477-7337-413b-9595-cb9b56353ccd |  | note | FREQUENCY: per lot
label | ea0ee356-e857-4f6f-90e7-3d7849aa8b9a |  | note | ---------------------------------
label | bda39461-9676-4612-8391-51f478b302ff |  | note | CATEGORY: IP
label | f22e07b5-03c6-43ca-bc55-ac41c0816d89 |  | note | ---------------------------------
label | 3713e5bf-750d-4fd8-9321-b0fb57323814 |  | note | RESPONSIBILITY: Track Supervisor Site /Project Engineerr
label | da3668f6-eea4-42dd-b8af-16e926512761 |  | note | ---------------------------------
label | 3d5a0e42-8844-4f73-9fb0-72052eb79478 |  | note | VERIFYING DOCUMENTS: This ITP
text | 37b740b8-60c9-41c7-b1f1-5881e770a9a5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 As-built Survey
label | b44f50fa-bc14-4adf-841d-3853f2f133fc |  | note | REFERENCE: As built Drawings
label | f071509d-419e-479d-9dae-cc22e80f467d |  | note | Asset Change form
label | bc9a219f-6f9c-4c5c-abaa-f0c4ab8be047 |  | note | ---------------------------------
label | 54fd62ca-c191-4cf9-b22f-8a24b9e1d897 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | 6bfc730f-e94e-46e6-ba50-30228293c56b |  | note | Attach: Engineering Asset Form (signals)
label | f2afe7ff-d687-4565-9956-974cdddb25e2 |  | note | ---------------------------------
label | fc68d56d-2522-4958-b973-6a3602161a27 |  | note | METHOD: Document Review
label | 59079ca3-e988-4ca5-8c3a-a893599ca47d |  | note | ---------------------------------
label | 3769c561-f904-42e3-a6e6-e7374bd12f4f |  | note | FREQUENCY: Once
label | 294058db-7257-473a-99f5-4623a68a7dad |  | note | ---------------------------------
label | 0139a86f-674d-4a9f-87a0-b1cf32553979 |  | note | CATEGORY: IP
label | 76f88a60-268c-4773-8f5c-a15596fe08bf |  | note | ---------------------------------
label | dafbd480-1925-4da9-873b-b7efa8a3fcdb |  | note | RESPONSIBILITY: Surveyor Site /Project Engineer
label | 6a5a19ad-0672-42b7-a797-fe40e9489ba1 |  | note | ---------------------------------
label | 66c50924-89ea-48ba-ba6d-66c3db61d2e2 |  | note | VERIFYING DOCUMENTS: This ITP
text | dcabee45-87db-4da0-9508-e78272aea350 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Track Certification
label | 30dc84c8-f6cf-48c9-9285-fb29cc9ea67c |  | note | REFERENCE: MTMF020000-1 – Track Form A T
label | 54c9b3ba-033c-41cd-a0d8-0bc9eea24f9c |  | note | MTMF020000-2 – Track Form B
label | 817a0947-e2dc-4676-9367-e722dc18b87d |  | note | ---------------------------------
label | f2b63746-89ca-4a1e-8d7d-1f4e7cd0fd10 |  | note | ACCEPTANCE CRITERIA: Attach : Track Geometry Conformance Certificate
label | a270ddc5-17ad-4af0-885a-206eb2f9bc0a |  | note | Attatch: Track System and Component Conformance Certificate
label | d8b72e5e-eaac-4f43-b547-573b2e930886 |  | note | Attatch: Before/After Photo of worksite
label | 097a7f51-d779-47c9-a6f1-4c9282eb0bcc |  | note | ---------------------------------
label | 7be81d07-e716-4f3a-8a66-d591917590cd |  | note | METHOD: Visual, Measure , Document Reivew
label | 3ff7e2f4-f35f-4118-af9c-762c5964c129 |  | note | ---------------------------------
label | 409bcdf0-9ebc-42fe-a809-cfc03fbaa239 |  | note | FREQUENCY: Once when all occupation works complete
label | 64011117-e912-4c85-a1e2-48bf11eb43e9 |  | note | ---------------------------------
label | 213120b2-be36-43db-86c8-57f3c16850fa |  | note | CATEGORY: HP
label | 4d7f6509-2297-4449-82a6-0dd410c9956e |  | note | ---------------------------------
label | cb264836-f4db-4799-a01c-25875474493c |  | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
label | e5b54776-c277-4ef7-8013-0b5a4ef95790 |  | note | ---------------------------------
label | 1f0ac554-56f8-4bad-8c17-0594c946f683 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 7313cde4-3f81-44f0-9adf-eaee568122e1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | a9de3651-696c-4e9d-93fc-5ebdcb04b96b |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 97ef9260-f7e3-4898-b826-509ac1d8222b |  | textbox | Name:
text | f1286689-ff47-4c8c-9cc8-357687b7e29d |  | textbox | Position:
text | c7429dad-d84b-4f37-a4d0-64ed19036cb8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation) Rev 1 | itp |  |  |  | Yes | ITP-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation) Rev 1 | e0e42da3-ba55-45e0-a195-5ff409134cd8
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 8ede6b47-ffd8-4441-80e2-152b5650e782 |  | note | Document Title: ITP-STR-Precast Barriers, Parapets & Kerbs (Supply & Installation)
label | 87473659-9c5e-4384-a0b1-ed81c267404b |  | note | ITP Description: Precast Barriers, Parapets & Kerbs (Supply & Installation)
label | 7fe17885-137b-4086-8a9e-36384d72a755 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 9addf9f7-67eb-49eb-aa28-a63771b4a200 |  | note | Discipline (e.g. CIV/STR/RAIL: STR
label | 0b9aead4-4496-466e-8baf-755b40b64d59 |  | note | Revision Number: 1
label | eaf6be81-76d4-44fe-892e-db0b8015a56a |  | note | Revision Date: 44244
label | a5cea546-35a9-41ac-990f-931f74aff013 |  | note | ITP created by: Mike Freeman
label | 457d89f9-0c06-4544-9af5-726615f1c761 |  | note | ITP approved for use by: Mike Freeman
label | 25beb783-335d-413b-97ff-15311742055d |  | note | 1.1 VicRoads Section 610 November 2018
label | 56280ccb-7d4b-441b-af80-8263c7fc3af8 |  | note | 1.2 VicRoads Section 610 June 2019
label | 30d05fa4-b47a-43d7-bddc-6367bd17c5af |  | note | 1.3 VicRoads Section 620 May 2009
label | a329697f-fb9c-4558-be48-a5b3ea2c329d |  | note | 1.4 VicRoads Section 630 October 2013
label | 7a1932bc-e218-4b5a-9d7f-bd59075f3a6c |  | note | 1.5 VicRoads Section 671 October 2013
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Precast Elements
label | fb487248-950e-493e-a9fa-1cd74e554cd4 |  | note | REFERENCE: IFC Drawings
label | 05ffc3a8-0a3a-41cd-819d-ca3457c9bd4c |  | note | 610.46 (a), Table 610.463 (November 2018)
label | a524b044-c51c-4d95-9dad-0521e7d9ae48 |  | note | 610.47 (a) Table 610.473, (March/June 2019)
label | 6c7db008-b96d-4058-bf00-d426a343edc4 |  | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | 8c34195d-17e4-4eff-b815-757395ac0c33 |  | note | i. Certificate of Compliance / Birth Certificate
label | 1f971707-6515-4539-9c33-c796b535ef6d |  | note | ii. Compressive strength test results
label | 2683f76b-d537-480f-8076-a20697d0f191 |  | note | iii. Precast Lifting Design
label | 33783c4a-053e-44d8-bf97-e3b51e7a3907 |  | note | iv. Pre-pour check sheet / ITP
label | 3eb68920-c5a9-4ec4-944d-e19dc0641a2d |  | note | v. Post-pour check sheet / ITP
label | 6aecfa78-ab7e-49d9-8da8-7bad01be8a67 |  | note | vi. Covermeter check record
label | ac8c560f-bc97-4255-9cc4-0d72f76d0de9 |  | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
label | 29344d33-ad3a-44d4-8486-82842007c56c |  | note | Note: Different revisions of 610 have different clause numbers
label | 4fcb6394-a40b-48c5-8580-2cabff7baf54 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | eff8f0e7-c171-4f5c-b753-7792d1af20c4 |  | note | METHOD: Document Review
label | 328cd4a2-ed03-49b6-85b1-168f0efe98ee |  | note | FREQUENCY: Each element
label | e65ce6f6-ecfb-47cf-b5ba-4bd6e5f08551 |  | note | CATEGORY: IP
label | 990f99b1-3a49-4ab6-9666-718dd9454899 |  | note | RESPONSIBILITY: PE/SE/SPE
label | 4b00e388-10b8-464b-97ab-59641e953d75 |  | note | VERIFYING DOCUMENTS: This ITP
text | c12bb393-9946-4ac5-ad5d-7eb348c48281 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Epoxy Adhesive
label | c2c132d8-1f02-4360-8d44-922cdd7010c8 |  | note | REFERENCE: MRPA Quality Management Plan
label | 90421646-8b4c-4b7c-b7b1-c9f10254dbe4 |  | note | ACCEPTANCE CRITERIA: Details of epoxy adhesive used to install steel bearings to bridge deck/foundation to be submitted for review to the Nominated Authority.
text | 52f846a8-c746-438b-bd8b-59d5ed0a36a7 |  | textbox | Enter: Teambinder Material Approval number
label | 8c1d0a6a-11a8-4de9-a27d-10c1bdc52329 |  | note | METHOD: Document Review
label | 3e59daad-8c17-4339-ba5a-eb6963d0094e |  | note | FREQUENCY: Once, for each product
label | c73c114a-9623-4c3f-afb9-486e84050646 |  | note | CATEGORY: IP
label | 1eb19b9b-a947-4b5a-b743-4fb53bc8a3b7 |  | note | RESPONSIBILITY: Nominated Authority
label | 10b1e8d9-18ea-4476-9610-abf5de894cda |  | note | VERIFYING DOCUMENTS: This ITP
text | 1367eea9-981d-4599-9272-3bb53eac12d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Joint Sealant
label | 8156cbb9-c3b7-408a-bf06-e0ec12c37c96 |  | note | REFERENCE: MRPA Quality Management Plan
label | d6f5be35-af67-4149-8d5e-38a4a90e3ce4 |  | note | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
text | f2cb8bd6-5b12-4266-8520-3d549072d1fe |  | textbox | Enter: Teambinder Material Approval number
label | 0fbcda0c-f25b-418f-8f86-782089fe292f |  | note | METHOD: Document Review
label | 97f00367-72aa-4a3c-94c9-4ccd336c222b |  | note | FREQUENCY: Once, for each product
label | 50e0608e-4ece-4be5-b777-cb7dda9683d0 |  | note | CATEGORY: IP
label | 801391a7-1c68-40f4-85b4-e4e3fcfcc972 |  | note | RESPONSIBILITY: Nominated Authority
label | 02e2f839-884c-4d6b-a6d2-8a08aca4572b |  | note | VERIFYING DOCUMENTS: This ITP
text | 5db579a3-833e-4f5b-b98c-5d9370c61974 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Bridge Deck / Foundation Compressive Strength
label | 1758131e-eea1-484e-87ff-fd758b9b0df8 |  | note | REFERENCE: 671.03
label | cd0b80db-736f-47d7-ae4a-92673f9ffb0f |  | note | ACCEPTANCE CRITERIA: Check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | b71adb75-7c8c-42f7-9861-aca85782b406 |  | note | METHOD: Document Review
label | bfb68e06-88e5-48e5-ba01-a0df845d72c8 |  | note | FREQUENCY: Each installation location
label | 43c3db53-07fb-45e5-bcea-ad00cabd705f |  | note | CATEGORY: IP
label | 4f9da36d-9f31-471c-8d18-5ea166ba7ed9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2dd18357-7481-464e-acea-b34fff96ce1f |  | note | VERIFYING DOCUMENTS: This ITP
text | e02445cb-3f25-4d5e-9588-45b05b8830d0 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out of Precast Elements
label | 84ecbcaf-d225-472a-b917-d781a6a9fcb8 |  | note | REFERENCE: IFC Drawings
label | a6a62b89-961e-4815-b8cf-a907faa015fd |  | note | 610.46 (a), Table 610.462(November 2018)
label | f815d1b7-bd3c-415e-b4ab-7c79183a581b |  | note | 610.47 (a), Table 610.472 (March/June 2019)
label | fddf2862-4bb2-4618-9120-aeb0fa1dba61 |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
label | fc9f177e-18ca-4cb1-ab9a-b1b5bacfc9e5 |  | note | Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | 4af29c6a-ec4e-48c1-87a1-6c4832f22e0f |  | note | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
label | 3049b3e1-5551-442e-b2d0-575e5ae4333e |  | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
label | 5ff1a3d1-eae1-45ca-8e78-d3a65b9c3594 |  | note | METHOD: Measure , Visual
label | 5712bb11-181e-402a-86a5-e39288f77ced |  | note | FREQUENCY: Each element
label | d71e7e35-ec48-48c1-b71f-dc7a1a60fb95 |  | note | CATEGORY: IP
label | 41f93565-518a-4abf-856f-027e64e8c2d7 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | f39c7137-313e-4456-a824-53a3b9bada1e |  | note | VERIFYING DOCUMENTS: This ITP
text | 095f2235-f077-4ccf-b2c7-0bdb563667a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Hold-down Bracket Levelling Bolt Bearing Plate Placement
label | 4f0944e9-84ef-4205-8b89-d7357dc6d814 |  | note | REFERENCE: IFC Drawings
label | 3eee0aeb-7c5c-4397-a437-25fb9063d8c7 |  | note | Product TDS
label | 35751ca0-29f3-4547-8422-cfef454f6a72 |  | note | ACCEPTANCE CRITERIA: Mix the epoxy adhesive in accordance with the product TDS and apply to the back face of the steel bearing plates.
label | b53e9b3b-9964-4f90-b51e-6175e4daaee2 |  | note | Place the epoxied plates onto the survey marks and ensure that the area level.
label | 3650b979-b1c5-4792-ad1d-e42455a6e6cb |  | note | METHOD: Measure , Visual
label | 36e7a25e-c10c-4d74-8802-46c672e4d852 |  | note | FREQUENCY: Where applicable, each installation location
label | f64392f7-d12d-4109-be72-59c935c7a391 |  | note | CATEGORY: IP
label | e8efb6de-72e1-40dc-8d8f-7652c745f58b |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | f1eb5fe8-4208-45ee-be58-571c79f8133a |  | note | VERIFYING DOCUMENTS: This ITP
text | 1803a694-a1ca-46c5-97e4-e016424b2fa8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Bearing Shims or Bearing Strip Placement
label | 7d0f2618-eb38-477a-a70c-b5152f5fe2a1 |  | note | REFERENCE: IFC Drawings
label | 9c64d658-c7ae-491e-9ee6-f51c7deb0503 |  | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | 947b3248-5742-46cf-8447-c37122cd0f34 |  | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
label | fafa3b78-e0ff-42f9-8a86-f4bc7001a4bc |  | note | METHOD: Measure , Visual
label | b6629526-2df7-4648-874e-941ae354eb41 |  | note | FREQUENCY: Where applicable, each installation location
label | 6e110be3-a02b-4ca6-b344-b9c92934a77d |  | note | CATEGORY: IP
label | bd58ae68-7c31-404f-9825-64efb81dbbcf |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | f0bc8a44-568e-4ee9-ac3e-6ff35aad6c9a |  | note | VERIFYING DOCUMENTS: This ITP
text | 43b31f0e-56dd-4dfd-9e50-05a8944e80b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Sealing Strips, Backing Rod & Bitumen Board
label | b39207e6-a1c5-41d4-b8c7-7984e9bef4e8 |  | note | REFERENCE: IFC Drawings
label | f67b11ca-0740-4632-863d-da1c98b4a6f5 |  | note | ACCEPTANCE CRITERIA: Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits).
label | a635cb26-8f55-4c48-8795-36749758e9c3 |  | note | Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities.
label | 32d08adb-16e5-49ae-ba55-45aefc2643c7 |  | note | METHOD: Measure , Visual
label | 26d7701e-b4e0-40da-b94b-30f921c27961 |  | note | FREQUENCY: Where applicable, each installation location
label | 877b79ac-ba52-41d3-95a3-51e686e232e8 |  | note | CATEGORY: IP
label | c9c169ed-fa3f-4cd5-abd3-66661f0dde9c |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 9a701397-c81b-4b58-84c7-edc0ee66ad1a |  | note | VERIFYING DOCUMENTS: This ITP
text | 99e0181c-5312-4791-a682-bf1e42332b2b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Materials Inspection Checklist
label | ac7f746a-0caf-4307-ac0f-e53398c7953b |  | note | REFERENCE: 620.06
label | 3cb519a2-c8c5-47d7-bff9-c252dce60261 |  | note | 620.07
label | 617914fc-2df3-4de6-9f61-0aeac0dd4f6f |  | note | MRPA Quality Management Plan
label | d7fdfb92-c3b7-490b-87f1-e202c318b9f5 |  | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | 526f0351-1402-462b-8589-b0c14811ed89 |  | note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | 8c256ca9-ef69-4a28-a408-d9df691ae23f |  | note | Elements shall have unique identification and orientation marked (if applicable).
label | b7b89cad-3c65-48f6-a71e-48fcf7419c32 |  | note | Complete: Materials Inspection Checklist in ConQA
label | a6253fc1-be10-4e83-b0b4-94897db80be3 |  | note | METHOD: Measure , Visual
label | 35f03387-418e-4124-86cd-27d61b8bb175 |  | note | FREQUENCY: Each element
label | 13ff1a42-8d07-4549-a1ad-d4c0b7188112 |  | note | CATEGORY: IP
label | c8402afb-6910-48ee-a362-82a720db22e6 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9a17ffb2-23dc-4aba-b74f-a47ae05f3e5c |  | note | VERIFYING DOCUMENTS: This ITP
text | c47325e9-66f0-4af0-9f41-f0ee22f2225c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Precast Handling
label | 56c8f5d1-cd94-4a57-97ab-ba57fc08fb98 |  | note | REFERENCE: 620.07
label | da173067-6807-4e0e-abf0-0db1eee34f70 |  | note | Crane Lift Study
label | 6bcda74a-6dbd-4d89-9d38-1e45a2b54d2b |  | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | 6d03c8ef-9780-44d7-b280-f6caca67b7b3 |  | note | METHOD: Visual
label | 0366f45d-9b76-485b-90d9-f29ab424bb6e |  | note | FREQUENCY: Each element
label | e2b5a8b2-6d64-42a6-913b-59cd9ee05ea8 |  | note | CATEGORY: IP
label | 6b2af405-2aba-4b09-813e-629ab92eca03 |  | note | RESPONSIBILITY: SE/PE/SPE
label | be93eb31-b639-4d8e-bd50-80c2784eceee |  | note | VERIFYING DOCUMENTS: This ITP
text | cf2e0213-1ad9-4966-b233-2f336fe34759 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Precast Placement
label | 747cc2d4-c560-4062-b272-20310383e4eb |  | note | REFERENCE: IFC Drawings
label | 323bbbf7-9f9e-4649-a817-3bac7fc5f742 |  | note | 610.27
label | 5247a269-0149-4767-9509-1c6a6c6ecd7e |  | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | af96cc99-8708-4d07-a238-3cde337c4cab |  | note | Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance.
label | 18d42539-3739-43ae-99c9-8ec976eb58bb |  | note | The nominal gap between elements is as per the IFC Drawings.
label | c674c4d3-da87-45db-ac3e-186ca8ce3b90 |  | note | METHOD: Measure , Visual
label | 5531af84-af6f-4019-be9f-0ebe924bf8da |  | note | FREQUENCY: Each element
label | 4fb7b035-c41f-4720-bff1-9532768bd903 |  | note | CATEGORY: IP
label | 4b9944f7-1805-4514-96ec-20f80b8a091a |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 31e28146-e2a8-4300-b759-709aeca77f17 |  | note | VERIFYING DOCUMENTS: This ITP
text | 900e4ff2-9b9e-4847-b1eb-80b95c57fcdb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Draw-string in Service Ducts
label | 8c9ced96-d36f-4149-a45c-b59b6a2f41fc |  | note | REFERENCE: IFC Drawings
label | 679b566f-36eb-49be-ad9b-f21c6ce83dd7 |  | note | 671.03
label | 83a54270-83b9-428f-99ad-b07c93204b34 |  | note | ACCEPTANCE CRITERIA: Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes.
label | 9a10f9c6-3801-467c-9d8b-af6be0524953 |  | note | METHOD: Visual
label | e3d9d176-61b0-4418-9a69-bbf2c4a2ec65 |  | note | FREQUENCY: Where applicable, each element
label | 40dc8e7f-16c9-4a83-9d75-2fd9128e2db2 |  | note | CATEGORY: IP
label | 7c40b37c-f5cf-4f05-bd16-a36458743ecf |  | note | RESPONSIBILITY: SE/PE/SPE
label | aa2f3d8a-b1fa-4146-b0e7-a8ab0b0e2c6e |  | note | VERIFYING DOCUMENTS: This ITP
text | 3e574b6f-8fd5-4a2b-8904-88aec70f4808 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | 20dec3f3-d260-4cd4-a856-8972aaf48ab4 |  | note | REFERENCE: IFC Drawings
label | 9301d110-9b05-463c-a24a-6ded0be3d4e4 |  | note | 630.20 (a) & (c)
label | 387d4c33-3b28-4d0c-afd6-d714b3606e35 |  | note | AS5131 Clause 8.3
label | 0411ce98-7f70-46db-b6cc-7c1af1c36f4e |  | note | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | f7bc39f6-bfe2-4b65-8f03-959c4396982a |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | 493e14be-22ee-4621-8bd8-fbf86a90dde6 |  | note | Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | b43e297a-d048-4a62-aeae-46b51879c4ba |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 563580d1-6916-4daf-961a-c9d29680045e |  | note | METHOD: Visual
label | 56d754d4-cded-4886-b1ca-674f2bf1c1cb |  | note | FREQUENCY: Where applicable, each bolted connection
label | ee7a9caf-cd7e-4453-bc65-70cfd18cbbb4 |  | note | CATEGORY: IP
label | 301bc668-7388-409a-9c31-57d07859bc85 |  | note | RESPONSIBILITY: SE/PE/SPE
label | de184c96-9ecc-4f67-b32b-9a5159bc6dc9 |  | note | VERIFYING DOCUMENTS: This ITP
text | c7db1f55-d9c9-495b-9dab-0ce42523e47e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Precast Traceability
label | 98d73917-b9ac-417f-a63c-f4fe8a05f98d |  | note | REFERENCE: 620.09
label | 4ddb9e59-4a57-4ebb-a549-2d301787d668 |  | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | a06ed561-0429-4e7a-9238-72d316e83af5 |  | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | c79c18e2-fac2-4d1a-af76-74650138ae57 |  | note | METHOD: Visual
label | 9cdc74d7-05be-4d4f-ac1f-0dde6a2ec2e4 |  | note | FREQUENCY: Each element
label | 8a358b29-6722-4d07-a88b-091baa9f0999 |  | note | CATEGORY: IP
label | 22005b90-63d4-430e-b345-a77c7e38481e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 697606ad-f554-4f5b-81c9-cbee63913f73 |  | note | VERIFYING DOCUMENTS: This ITP
text | 08ec3846-469e-45b9-8080-4b53951ab682 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Joint Sealant Application
label | 6ee6c5bf-d30d-4ff1-8426-696ad1102143 |  | note | REFERENCE: IFC Drawings
label | bf57ff79-e2d7-44c8-b8ba-9a022962e501 |  | note | ACCEPTANCE CRITERIA: The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
label | a56988ba-96c5-4da7-a3de-cd5de53fc6da |  | note | METHOD: Visual
label | 14d0b5b3-ffdf-4aed-af90-b242fffc752a |  | note | FREQUENCY: Where applicable
label | 881f2894-e916-48f3-be09-14c89526f3a2 |  | note | CATEGORY: IP
label | b69e06a5-e06d-4254-813f-4d1608ecfffa |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | d9f54d4c-09ca-4d3a-86de-4636ff9bcab4 |  | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
text | 5cfc5f11-c697-4052-9586-3b9bd6e69d4a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Flowable Grout Pour
label | bf1417cd-9140-4060-8713-e46cd2c15c6d |  | note | REFERENCE: IFC Drawings
label | b2f931d3-41c6-4a41-80c9-4591e75b7ebc |  | note | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
label | 5e78ff50-8842-4d6f-8571-bebf8b699c3f |  | note | Complete: Grout Pedestals & Bearings ITP
label | dc99047c-d464-45e0-940c-3592bb47b3bb |  | note | METHOD: Visual
label | acf5ea63-49ee-4529-b1c0-0dbac3e90cd6 |  | note | FREQUENCY: Where applicable
label | 75a6342f-1559-47bf-b4f2-54088754e26c |  | note | CATEGORY: IP
label | 65d3b85a-20a0-407b-97c4-b7a768748a31 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 8fef52fe-684c-44e6-8dcc-d802e03bc49a |  | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
text | 6443ae18-3250-4637-9dfa-5e9b8246f2bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Barrier Railing
label | 8f84ccd5-b2f8-443d-a345-be2545f422e9 |  | note | REFERENCE: IFC Drawings
label | 04bbf3c1-5820-4857-a5b9-e28a06e680b6 |  | note | ACCEPTANCE CRITERIA: Where applicable.
label | 561c0ace-cafd-458a-b9fc-a65d0b7b8702 |  | note | Complete: Structural Steel Barrier Rail (Supply & Installation) ITP.
label | fff1ab4f-7079-4f99-a600-969199f81957 |  | note | METHOD: Document Review
label | c1105d87-70c7-478c-9bef-a463940950cd |  | note | FREQUENCY: Where applicable
label | d0f6ecef-6373-4322-a1ac-358232f97d72 |  | note | CATEGORY: IP
label | 637377a7-0733-4138-8394-d881bce7d867 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 3e8e769b-b4f0-47a1-9d60-d6619c04a1fd |  | note | VERIFYING DOCUMENTS: Structural Steel Barrier Rail (Supply & Installation) ITP
text | 75e8ee38-b8c2-4eb7-8b3f-f790004c4af1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 As-built Survey
label | ebc5ddaa-aa6a-40f9-abb8-8992cb675c95 |  | note | REFERENCE: IFC Drawings
label | e373c5ce-581f-4326-bdbc-dc522c1381a7 |  | note | 610.46 (a), Table 610.462 (November 2018)
label | 81649270-ecbc-4e36-ad3f-afaa1773d0b9 |  | note | 610.47 (a), Table 610.472 (March/June 2019)
label | 43816a6f-e4af-4746-934d-cf9549542fc9 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | 3ad97e17-3cf3-42e5-b803-fd00af5808f7 |  | note | Attach: Survey As-builts / Survey Report
label | b99055e3-262a-4c74-9ac1-8b424c5c575d |  | note | METHOD: Document Review
label | 542c0365-c4cf-4b4c-ac8f-b413f1a589ac |  | note | FREQUENCY: Each element
label | 050dfd73-3238-4a1c-be5b-0fd7398b3b45 |  | note | CATEGORY: IP
label | c1766aa5-c537-4c71-9f84-1be15cf99c55 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 71563986-729b-4c39-a982-8f7e7b464b29 |  | note | VERIFYING DOCUMENTS: This ITP
text | 823beb11-1bd0-45b4-8c7f-547bf7151b42 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Non-conformance Report (NCR) Closure
label | 7b53ffff-bd7c-440e-adfe-e04b7420cec8 |  | note | REFERENCE: MRPA Quality Management Plan
label | c9887733-40cb-4192-8c87-c542d318d30a |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 8bbb91fc-2ff5-4aff-b1aa-8fc7b0c0dd0b |  | note | METHOD: Document Review
label | 159ab3b8-a08c-415c-a9f2-435a62960f0b |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 9f3d4c30-8050-4105-83bc-38cbf3f0661b |  | note | CATEGORY: HP*
label | dfd583fd-6d56-4ba1-bdfc-3ce80c64a735 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9fc42244-0c3a-49ef-a8f6-d9fee92e91eb |  | note | VERIFYING DOCUMENTS: This ITP
text | 8774619f-19a0-4b7e-89b6-f4f665a8effa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | d953a48a-f236-45af-8101-8611f8bfce23 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 4380f54d-4728-4a6d-9599-5e3f596bc2b8 |  | textbox | Name:
text | fa7f3d04-783e-45f2-950e-0d2a5e2783eb |  | textbox | Position:
text | 94d046bf-3783-4df8-a5d4-aa5ff30b977a |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 1 | itp |  |  |  | Yes | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | e3a540bf-5955-4cbd-9059-4691fcd68f04
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 0423d365-6e94-4673-873d-a8c846a8b5a9 |  | note | ITP Description: Unbound Flexible Pavement (Supply and Install)
label | 8f46c7d1-435b-4244-992d-627159d5fb0b |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 32a46778-098e-4a20-b91f-02042dd4de5a |  | note | Revision Number: 1
label | 930f11f8-77de-4797-b071-bdc6804d664d |  | note | Revision Date: 28/08/20
label | 8edeffe1-4c90-4b68-99f0-cca571afcf8f |  | note | ITP created by: Matt Velcek/Hiruni/Saaf
label | 720d3b42-9395-421b-949e-55da032f9813 |  | note | ITP approved for use by: Josie Pavlou
label | aaa4076d-721e-459f-bd53-6fd683a6558e |  | note | Reference Documents:
label | 23c20d3c-ba01-4d24-ac10-cdfbcced727b |  | note | IFC Drawings
label | 952bed3e-4ea3-4c87-99b8-f1c23b5164d0 |  | note | VicRoads Section 173 (10/9/2008)
label | e906efb7-17fa-4304-941c-7cae17c4424b |  | note | VicRoads Section
label | c1e3acbe-b8c0-42a4-b78a-68858191c202 |  | note | 304 (13/8/13)
label | 76160cd5-fab2-41d6-8e38-86b2f6752946 |  | note | VicRoads Section 801 (19/07/18)
label | 2c5f36ac-d01e-4d4d-acbf-ff133a2c435b |  | note | VicRoads Section 812 (13/07/16)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Crushed Rock Mix Design
label | 3dfa9cd5-85de-4106-bad7-da154475293d |  | note | REFERENCE: Section 304.03
label | 8b2c788d-ff1d-4998-a215-a1a6e16969f5 |  | note | Section 304.05
label | c446d393-0ef6-4839-82e3-e40503fdab50 |  | note | Section 801
label | ba46c39d-e29b-45b1-9eb3-183bc75d9ad4 |  | note | Table 812.121
label | b0c38fbb-3ee0-4f33-9367-9a0ea09f3f1e |  | note | ---------------------------------
label | c184507e-44c2-4063-9305-84faf5554d22 |  | note | ACCEPTANCE CRITERIA: All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
label | d9b25c1b-4612-4da3-9592-55ea7fcbd29b |  | note | Material properties to be tested in accordance with Table 812.121
label | c8635976-5a66-45e3-908f-a3144556d13b |  | note | ---------------------------------
label | 659bcbad-fd52-435b-baee-47dd6d9cce22 |  | note | METHOD: Document and Docket Review
label | ca8c8f49-4ed0-4058-a418-a56e9c177cf4 |  | note | ---------------------------------
label | 148c132f-83a9-43b4-bd8f-fe287a436b91 |  | note | FREQUENCY: Material conformance as per Table 812.121 Delivery Dockets to be checked each lot
label | e6635f2e-918b-4409-ad80-0ea324e5d62a |  | note | ---------------------------------
label | f48818f6-bf58-424a-8ed0-98c2f46952c3 |  | note | CATEGORY: HP
label | 18e5f9e4-749b-4f67-b9f4-9740045c592a |  | note | ---------------------------------
label | 570121c0-2c94-46ff-b055-07805f1d8b5a |  | note | RESPONSIBILITY: PE
label | c22e468e-73e7-49d5-829c-77bae47933e1 |  | note | ---------------------------------
label | f14f0596-8ba7-4fda-8656-641f273b3f12 |  | note | VERIFYING DOCUMENTS: Manufacturers Compliance and Test Certificates, and Delivery Dockets
text | a9159ea5-bfdd-4ea2-98dd-d0f22169a0e1 |  | textbox | Team Binder Approval Number
select | 1e7d0cc4-9187-4aea-872e-07d045598a07 |  | dropdown | Specified Design Material Type | 20mm Class 2,20mm Class 3, 20mm Class 4
text | d7da51c2-d918-4f8d-bc5d-a0c6771fed2b |  | textbox | Specify Design Layer Thickness
text | 764755c2-2f75-419b-aa56-629718d0008b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 66b3f565-174e-4f1c-9412-b1fc60654921 |  | note | REFERENCE: IFC Drawings
label | f0907a9b-f0f4-45de-abbb-ae20dc0292c0 |  | note | Section 304.06
label | 9eb7d0d5-2ac3-4293-9e5f-0abc7f6d3fdb |  | note | ---------------------------------
label | 57ce0950-81e2-4f1e-a4e2-4a13dca18b41 |  | note | ACCEPTANCE CRITERIA: As per IFC drawings and within stated tolerances in 304.06
label | 0a454c73-3f60-426c-91a4-1e61285ac5d6 |  | note | ---------------------------------
label | 5b1274d1-f6f2-4679-a24a-a7df7d29d279 |  | note | METHOD: Visual and Measure
label | f340b707-38a3-4d46-8781-0a7c0a7a8a29 |  | note | ---------------------------------
label | d712574d-52e3-4fb3-af1c-3ac5e7750d65 |  | note | FREQUENCY: Prior to Commencement Each lot
label | 79f21474-8960-4392-b6e7-4c72105aa501 |  | note | ---------------------------------
label | b81d6bf2-cb35-4813-95ab-ee6e85515215 |  | note | RESPONSIBILITY: Surveyor, SE
label | 43702e37-dc72-487b-a3cf-740744b167a2 |  | note | ---------------------------------
label | 781a8276-77b9-4525-881c-af299ba278c2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | be2e913b-cc51-4eb6-bdc8-7b731206386e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Previous Layer Conformance
label | 3c8d6ab5-7d63-4514-83f7-874980c29b4c |  | note | REFERENCE: IFC Drawings
label | c434446b-e0a8-4a63-b068-d5f2fadde82a |  | note | ---------------------------------
label | b4b413f3-22a6-4efa-b8f7-95892c98a60e |  | note | ACCEPTANCE CRITERIA: Previous layer to conform with IFC drawing requirements and closed out prior to placing pavement.
label | 7b88b5ee-3941-4d7c-8a0a-04eac25a1589 |  | note | ---------------------------------
label | 1c1ca827-c5b4-45fb-b445-91eb8012d042 |  | note | METHOD: Review
label | f440bbfd-0cf8-4bf6-931e-bcf10eb09716 |  | note | ---------------------------------
label | 7721d3c4-594b-45ee-8da5-ee718f1b2a98 |  | note | FREQUENCY: Prior to CommencementEach lot
label | 4fd5e2cc-c7d0-48c9-bb1b-d5aa4ff94084 |  | note | ---------------------------------
label | 38ecf7f5-0a23-4c20-bba1-c7b91c023a52 |  | note | RESPONSIBILITY: SE
label | 0bfda55c-8666-4684-ae67-dd833daff347 |  | note | ---------------------------------
label | e1b3f9f1-4185-482d-ba98-00c8818a3ee7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 3c6ebb70-751c-4bcb-8a36-efbbfe6c7217 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Select Scale
label | aab88595-eb8e-4f20-86b5-265699561cfb |  | note | REFERENCE: Project Requirement Specifications
label | 31527a13-7e30-4144-8c96-129a4be05ce2 |  | note | ---------------------------------
select | 6212f7c0-8aa2-4798-b257-a985c6f5c12e |  | dropdown | ACCEPTANCE CRITERIA: | Evans Rd - Scale B,Cardinia Rd - Scale B,Princes Hwy - Scale A,South Gippsland Hwy - Scale B,Beaconsfield Car Park - Scale C,Clyde Road - Scale B
label | 4ffa7609-4e1e-464b-98a9-1129053411ca |  | note | ---------------------------------
label | 20aaa6d1-eeaf-44b3-90b9-70e8356e61b6 |  | note | METHOD: Review
label | 7fcd4b13-71e9-435a-8769-a007e275c65e |  | note | ---------------------------------
label | 31f5a740-be4b-4fac-95e2-17c6da52afca |  | note | FREQUENCY: Prior to CommencementEach lot
label | 44e77636-cb40-4871-97d0-2a5fa656830d |  | note | ---------------------------------
label | e84233d0-df25-4baa-93d9-91cc188b343d |  | note | RESPONSIBILITY: SE
label | 2847e91e-5f77-4807-9e97-fa39359b8492 |  | note | ---------------------------------
label | dd3990cc-9a13-441a-85c8-7c85c600161a |  | note | VERIFYING DOCUMENTS: Sign ITP
label | d6947f4f-5974-4ab4-9775-357e5dd76aaf |  | note | Specify site specific scale
text | 025278e7-3b0e-4447-a4c2-abe0a752b712 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Placement of Material
label | 88919c94-edfe-47cf-ba38-f588342ff0bb |  | note | REFERENCE: Section 304.03
label | df4cbae1-b19f-4650-b82c-6e1d59bc4f83 |  | note | Section 304.06
label | b616e4c8-dddd-4414-ad6d-b9fce214ffa2 |  | note | Section 304.08
label | ba54c3f3-c4de-48ec-be8a-68fbd16d2281 |  | note | ---------------------------------
label | 9ae0508a-33aa-406d-9d8d-86b1d44f3401 |  | note | ACCEPTANCE CRITERIA: Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas. Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | d23209df-af65-4b7c-b1f9-382b259de29c |  | note | Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | 5bae6c2b-97eb-4b15-a1e9-74c0d59ad374 |  | note | At no location shall water pond on the surface of any pavement layer.
label | b5d1ffc4-a2d2-4275-a3ab-6ef410cc1d31 |  | note | Lot size shall be the lesser of 4000sqm or a days production.
label | 06d4415f-7230-4f7b-9415-8bfa45117e0d |  | note | ---------------------------------
label | 5c0d10c8-35ef-4f98-9a08-969b856e797d |  | note | METHOD: Visual and Measure
label | a0181385-7e13-4ac4-99bd-b24aa4cb59f7 |  | note | ---------------------------------
label | 686fb05b-6a7a-4010-86df-09c64085dffc |  | note | FREQUENCY: Each lot
label | 3b961c7b-3d67-4ee9-a6db-8868df620699 |  | note | ---------------------------------
label | f8fb1f44-33f8-4b46-90e4-dffed4db6479 |  | note | RESPONSIBILITY: SE
label | 8a16a6ed-730e-4c42-b329-6855e0dbfd60 |  | note | ---------------------------------
label | 085db1c8-f57c-4aeb-acc5-f60847ae8852 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | be36e974-532a-41c2-befe-edd4ca801c39 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Placement of Material
label | dbc818b2-df30-4720-ab6e-2cb8b18ed350 |  | note | REFERENCE: Section 304.06
label | c51789be-c9ab-48d6-bcc5-efa042afcbf0 |  | note | ---------------------------------
label | 3213f040-6b7b-4e77-b2df-a92ebd732375 |  | note | ACCEPTANCE CRITERIA: Lot size shall be the lesser of 4000sqm or a days production
label | a9a774f1-9269-432a-a74a-7891f74ebb83 |  | note | ---------------------------------
label | 79861889-0dfe-4e89-b019-05c6bf631200 |  | note | METHOD: Measure
label | 3efd4021-f0da-49bb-9163-c4bce35658af |  | note | ---------------------------------
label | ca57706e-1129-42e5-8856-971475186534 |  | note | FREQUENCY: Each lot
label | 0cae3f2d-7f76-48bf-a1c1-630ebdcc426f |  | note | ---------------------------------
label | 2cb8f416-ca8f-439c-8f15-d446a38eb888 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6ee1dfe1-8499-4ae2-9017-d6d0d676722f |  | note | ---------------------------------
label | fa1bfbbe-6d1a-4c63-9bc7-fc4e8bedb1d0 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 1cda2b8c-2c5a-4b9a-bfb6-2db659ffff3d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Construction - Jointing
label | d6e9545f-ef1f-4123-aae9-d00c3ea5bb0b |  | note | REFERENCE: Section 304.07
label | 6d71b067-aad1-4eab-b29e-96e2152ef14b |  | note | ---------------------------------
label | adaa1bc7-bae2-40a5-8945-b524e50fe309 |  | note | ACCEPTANCE CRITERIA: Material shall be spread in a manner to minimise joints.
label | f6c05974-bb15-4dc1-8b1e-732dd980229d |  | note | Transverse Joints in adjoining pavement runs and in any underlying layers shall be offset not less than 2m.
label | 204fdf7e-05eb-4757-8e56-718cdd72989d |  | note | Longitudinal Joints to be offset by not less than 150mm to any underlying pavement layers. To be located within 300mm of the traffic lanes or within 300mm of the centre of a traffic lane.
label | 30fa1cab-8c99-44ff-9f3a-f7ca0eb4616b |  | note | ---------------------------------
label | 0303d9a9-a06e-41b5-ab28-140a2251b2b2 |  | note | METHOD: Visual and Measure
label | af4d78cb-cbfe-4aad-b543-d7563f0287c6 |  | note | ---------------------------------
label | 60ae4423-ac87-4044-9489-a66cf5441eec |  | note | FREQUENCY: Each lot
label | 810b0e2a-357e-4914-b6b3-0a057851f548 |  | note | ---------------------------------
label | 9dc14894-c3a7-4de3-8ffb-dfa9f95af6a5 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3e56f9d0-ba8d-4a65-a048-add94849a90a |  | note | ---------------------------------
label | 55066877-4825-41c5-a612-7e83eb50934a |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 77229458-1318-41ce-8665-f00b4956cacc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Compaction Testing
label | 4a8b26c1-767c-4713-ba14-1aa980186df4 |  | note | REFERENCE: Section 173
label | feac58f8-7415-4d38-9c17-5985f0acb83e |  | note | Section 304.08
label | 20ac7db6-e9ce-4357-952b-cd45bbc1e83d |  | note | Table 304.081
label | 0277547d-8724-47b0-8407-60b2904842e5 |  | note | ---------------------------------
label | 06d08192-8b5c-45cf-90ec-4b0ed8c7e84e |  | note | ACCEPTANCE CRITERIA: During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | 791ce747-ae3a-4b12-92a1-63319bcf625a |  | note | Density Ratio to be based on tests performed with Modified Compactive Effort.
label | 9fe12672-4dc5-437a-a493-97f5a97f0264 |  | note | Scale A:
label | e8a6a27c-bbf9-4d1c-b0d6-7f6d20b8167d |  | note | Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
label | d24f2f91-ce07-4fc3-b020-7a72e941064c |  | note | Base Layer CDR ≥ 100%
label | 14d663bf-7036-49df-a0da-34725595f18e |  | note | Scale B:
label | dfb98c7a-f519-404d-87d1-2466eabfeef1 |  | note | Subbase Layer Characteristic Density Ratio (CDR) ≥ 97%
label | a302720e-394f-4342-967c-4618a535be55 |  | note | Base Layer CDR ≥ 98%
label | 484cbb5b-bb52-459b-97fd-e1a58e34938d |  | note | 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | 7e4299a8-711a-42ed-a1e5-6bfa0b2b1f57 |  | note | Scale C:
label | 85fe5f8e-0cda-4def-82c3-f0830dc80af7 |  | note | Mean Value of Density Ratio (3 tests):
label | 09af8035-ff5f-4475-b438-029cbca51b72 |  | note | Subbase Layers >98%
label | 8ca1c8b8-5dfd-421e-9283-cd88e08fff97 |  | note | Base Layers >100%
label | d70daa4e-5401-4274-8366-110c6f460006 |  | note | ---------------------------------
label | 9e79c093-a6da-4a59-aeaf-a7549e6d490b |  | note | METHOD: Review
label | c13202b8-31d3-4ab4-86fa-3604e16e31a9 |  | note | ---------------------------------
label | 7e0313c8-15ed-493b-8ec8-a9a36fe7a3d6 |  | note | FREQUENCY: If the lot is < 500sqm , test every lot. If the lot is > 500sqm, test the first 3 lots. If they all pass then can reduce testing frequency to every 2nd lot.
label | d5309d0c-c776-42bf-9186-958ca3ddd4e0 |  | note | ---------------------------------
label | c5c42edd-9963-4fa3-812f-f1e070f5dcb9 |  | note | RESPONSIBILITY: SE
label | 7d123f04-b30e-4e89-981f-d7209e3c1b65 |  | note | ---------------------------------
label | 32701567-a021-4bef-b538-db8c20195c1e |  | note | VERIFYING DOCUMENTS: NATA Certificate
text | c8b78f71-8ff7-4acb-a120-f7166a2d4500 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Post Compaction Materials Testing
label | 8e250412-cee0-4b10-af4e-770bb0682890 |  | note | REFERENCE: Section 304.10
label | 36b9f3b5-79a5-4c83-95d7-ff44d2a14fb5 |  | note | Section 304.11
label | ce1cd2ab-51e5-4a74-b53c-07aa2367db96 |  | note | RC 500.02
label | fcedd652-0da4-49ae-bd46-9f5b633ed9f6 |  | note | ---------------------------------
label | b3370008-9bde-431f-991f-d49311f01a1e |  | note | ACCEPTANCE CRITERIA:
label | 63e89545-c260-4fb4-8913-ec556f0b5112 |  | note | Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | 9ced1a5b-d336-492e-83c3-a3d4de620320 |  | note | 20mm Class 3:
label | 94c83d7a-6227-464d-8087-c162a46a6c7b |  | note | Grading
label | c928132c-2756-456c-b3b0-da971f10d859 |  | note | 26.5mm 100%
label | e264593a-f4ed-4cb2-82e6-7d1e62fe7814 |  | note | 19.0mm 95-100%
label | 8a95f2a5-f8e3-4f4e-9410-d0514ce306cb |  | note | 13.2mm 75-95%
label | 184585af-d7c8-48aa-9088-d9a4d34dd861 |  | note | 9.5mm 60-90%
label | 1c8bc12a-3fab-4142-b7c3-ea5c9a6b670e |  | note | 4.75mm 42-76%
label | 7daf81ac-cdc3-4913-95b4-0bf191624cb8 |  | note | 2.36mm 28-61%
label | 13fffe3a-ff1c-4d8f-afc4-1182db8df0c8 |  | note | 0.425mm 14-29%
label | 389a9ae2-b0a4-4ef0-8e7a-6baccdf2cdf3 |  | note | 0.075mm 6-14%
label | 91710542-dd16-4e88-8211-f78b1b8f2d52 |  | note | PI between 0 to 10
label | ab67fba8-c033-43b8-9984-038bc77baff0 |  | note | 20mm Class 4:
label | b0c6264c-63f8-4ffe-a5d9-d8b83107a0cc |  | note | Grading
label | 8f7f48e0-39f2-4d33-a7d6-2f1feac814c4 |  | note | 26.5mm 100%
label | 322be881-6a3a-4dba-bd2b-8340e58477fe |  | note | 4.75mm 42-76%
label | ac2b23ca-f1b8-4207-9640-3be4f3b8ef0e |  | note | 0.425mm 10-28%
label | d408cf5d-f294-46c1-8240-9e002ab0f82a |  | note | 0.075mm 2-14%
label | 1b57cf0e-8e3f-435b-840d-37467ce3250f |  | note | PI between 0 to 20
label | 23763422-cbd0-4300-9a34-1db2a66723c0 |  | note | PI x % passing 0.425 mm sieve (max) 450
label | 0e5008db-cf70-4f20-8361-20cc1e40e457 |  | note | Scale C: Post compaction material testing is not required.
label | 1ccef1ba-715f-4b5a-b26f-c2c08deb76e9 |  | note | ---------------------------------
label | 3ba4aa0b-4977-4e31-a125-dbaa475d1a68 |  | note | METHOD: Review
label | 76105467-0743-44d6-9513-39ef52fd6427 |  | note | ---------------------------------
label | 546ed0aa-5433-4d82-876b-fec6bde15fe3 |  | note | FREQUENCY: Scale A: PI and grading to be tested in the first lot. Reduced Grading every 2nd lot, reduced PI every 4th lot.
label | 28dbdb0e-3b0a-4a41-9592-4a1f86db4067 |  | note | Scale B: PI and Grading to be tested once post compaction
label | 85d5df03-b392-4a73-bfa1-11b05d2082d3 |  | note | ---------------------------------
label | 284b290c-c7b9-4fe1-97df-f50fe681739f |  | note | RESPONSIBILITY: SE
label | 604330bd-d92c-4e9b-8550-229b5c5ba674 |  | note | ---------------------------------
label | 55f01914-f977-42c6-8231-4146477efda9 |  | note | VERIFYING DOCUMENTS: NATA Certificate
text | 5dab1638-5dce-4c8d-a342-2df69bbdeddf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Proof Roll
label | 03279df2-b03e-4eb6-a0c8-7598292ce0c3 |  | note | REFERENCE: Section 304.08
label | 8e071b3e-7a44-4dfc-ad69-28ed89313819 |  | note | ---------------------------------
label | ee63cbb8-6988-4a50-9afa-8b691535e918 |  | note | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | 75bebf53-d45d-498d-9f71-24d911f21399 |  | note | ---------------------------------
label | 75c4b52f-5a2f-4aad-b6e2-6faba3598f4a |  | note | METHOD: Visual
label | b1cd6e3e-327e-4ff8-8565-512eda9db15a |  | note | ---------------------------------
label | 241cb291-e907-4a05-a7f6-87398a4aea73 |  | note | FREQUENCY: Each lot
label | 643a2a60-ea87-41f5-9482-6dda178e90d4 |  | note | ---------------------------------
label | 993faa15-4d95-40ea-b5c3-9e03f9f9d21a |  | note | CATEGORY: HP
label | 3385667f-cf7c-4574-8aca-2ba24cc27581 |  | note | ---------------------------------
label | 785de631-3523-4a26-bc52-7ce31e51de07 |  | note | RESPONSIBILITY: SE/Site Supervisor, NA
label | 16799bf7-5035-4623-98fc-44fb63129d9c |  | note | ---------------------------------
label | 3a8d2d50-56f8-46d5-b25e-d21d674052ae |  | note | VERIFYING DOCUMENTS: Sign ITP
text | bfb03805-4b2b-4f52-b0bf-e387ac677772 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Protection of compacted layer
label | 4872cae3-6652-4819-9881-4e2ce1da7f01 |  | note | REFERENCE: Section 304.09
label | c26c76d8-2f96-489f-b230-e1986ee61208 |  | note | ---------------------------------
label | daef5a66-9a7c-449d-89bf-c7b495f5c5fd |  | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | ecb30a0a-bd34-4062-8b47-eb0c17e77b81 |  | note | ---------------------------------
label | 667ee6d0-f5cb-43da-917a-f11773d0f637 |  | note | METHOD: Visual
label | 5ccbbc6b-74a8-4610-8a1d-0b11f8e47899 |  | note | ---------------------------------
label | 20808f41-b4da-4386-951d-6dc620113e7c |  | note | FREQUENCY: Each lot
label | df67de5c-60ba-47b4-a2cb-760d5d034ace |  | note | ---------------------------------
label | 85b2173d-7b6e-4859-a34a-452e2de16198 |  | note | SE/Site Supervisor
label | 2b20d753-32ab-4ad6-b0e6-bb4e87fe669f |  | note | ---------------------------------
label | 104c56db-6862-4c3f-ab19-519304055370 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a4858f6e-d36b-48e7-abb0-c658c6f7a848 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Survey As-Built
label | 745d1600-23b0-46f4-b9e3-2f767f86175b |  | note | REFERENCE: IFC Drawings
label | 5b9da010-c6c5-4246-9f03-00f2798a16a4 |  | note | Section 304.06
label | f691afbf-aa12-4047-aa8b-2237efb6cc77 |  | note | Table 304.061
label | 9618ae89-9f65-4d77-a97d-b4f7d0e85ddd |  | note | Table 304.062
label | 3f2240a8-d5eb-4b7a-933f-01dd457602cc |  | note | ---------------------------------
label | dc82d9e4-4af2-455b-95a2-89a8397a04c6 |  | note | ACCEPTANCE CRITERIA: No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge palced in any direction.
label | c3e56306-e8a2-4169-aa35-dd3988e7657b |  | note | Subbase course shall be not < the specified thickness by more than 15 mm.
label | 5807b58c-9b4b-47e8-86bf-d51f4f5ad626 |  | note | Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | 661dc121-21a8-4531-a61e-c78f1378551f |  | note | The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | 7b77707b-b283-411b-bf24-fe148ba4ffd2 |  | note | Scale A: A minimum of 80 measurements per lot
label | 99f67faf-6ad6-4449-b87a-258b412b6841 |  | note | Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
label | 94212aaa-4ed0-4e6c-9c35-6e9bf54ddd71 |  | note | Base: mean range ±5mm, maximum Standard Deviation of 8mm
label | 26ce9fe4-1334-48e2-8f5a-65a127f94b2b |  | note | Scale B: A minimum of 40 measurements per lot
label | 75bf313d-bc1a-4346-baa9-2bde4f9a2f8b |  | note | Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | 97ed783e-ed44-4825-a0ac-501f51f85fb8 |  | note | Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | a6992b59-7039-414a-83c6-801f66b56d1f |  | note | Scale C:
label | f8f8e360-23d2-4688-b086-072e30a66e24 |  | note | Lower Subbase (mm) +15/ -25
label | af4a1c1f-5889-4c3c-8d14-76d617a22dd1 |  | note | Upper Subbase (mm) +10/ -25
label | e089238c-a93a-461d-81e9-6964ca25816b |  | note | Base (mm) +/-15
label | 84ff8680-ad28-4d08-bc95-e156a1dd29ce |  | note | ---------------------------------
label | e573ed1e-eb7f-4a35-b6f8-f07a95e67067 |  | note | METHOD: Document Review
label | 2543d9ea-3727-415e-af56-386285a7d913 |  | note | ---------------------------------
label | b6ad12b3-87e8-45a2-83ed-04f997670b97 |  | note | FREQUENCY: Each lot
label | 95cfd08f-533c-40a1-9861-00780b265c4b |  | note | ---------------------------------
label | 3673bd28-6d0c-4dba-baae-527f3e836539 |  | note | RESPONSIBILITY: SE/PE
label | 0223e34f-d17a-4e60-8da7-288a834ab57b |  | note | ---------------------------------
label | 700428d4-7018-465d-ae1c-6e6f7e2ea310 |  | note | VERIFYING DOCUMENTS: Survey Conformance Report
text | 2947fa40-a353-47d0-9313-218dc3b937fd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 5dca4a54-6245-4f8b-b840-304176a7f282 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7db7b7e2-c933-41d2-8d49-2501a22cf423 |  | textbox | Print Name:
text | 32b576ef-d2b7-42fd-839a-1535bfaac2af |  | textbox | Position:
text | 72fea557-6137-4769-a6f2-fcc2a85b6ab4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1 | itp |  |  |  | Yes | ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1 | e442b910-27e2-4051-85f5-cab6bd381803
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | e71f872c-42f6-4315-bf43-a59c5e2efe53 |  | note | Document Title: ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling)
label | 55a51843-4cf4-48d7-8d1f-30957bc8c66e |  | note | ITP Description: Footpaths & Shared User Paths - 2 (Concreting & Back-filling)
label | 5bc962ac-9198-43b5-ac10-d77ff857a59a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 213f91a8-a9f9-40cd-a90c-a4469c3ab2cd |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 904df985-89d9-4f99-bc6a-9a2ba3ef12f0 |  | note | Revision Number: 1
label | 553ecfd4-52f5-49ea-bfc0-004329112e97 |  | note | Revision Date: 22/06/2020
label | 40e21d9c-b909-4b91-98d7-3ead6557896d |  | note | ITP created by: Lachlan Macready
label | 07ee7027-0659-45ed-a9f0-3a84944819da |  | note | ITP approved for use by: Mike Freeman
label | 07e878ca-c294-411a-8b63-949f2e2ccb45 |  | note | 1.1 VicRoads Section 703 June 2018
label | 2233c260-6c54-46c0-8364-5471dc738b22 |  | note | 1.2 VicRoads Section 610 November 2018
label | 94367ae2-7731-4cbb-a21b-72da8a58825d |  | note | 1.3 VicRoads Section 714 April 2018
label | 8d87672a-6d47-4180-a1cb-7dbc255111b1 |  | note | 1.4 AS1379-2007
label | b262a28f-8a77-4f37-93a5-ff10377a003f |  | note | 1.5 AS3610-2018
label | 168a7d46-7e60-47bd-b49e-16711cb0969d |  | note | 1.6 AS4671-2019
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | eed12136-4071-43c1-97fc-de474eab3987 |  | note | REFERENCE: IFC Drawings
label | ba8e8aff-a7ab-4a38-837e-ddaddcb1153e |  | note | 703.05 (a)
label | a9724505-858c-4c35-897a-74171562ef50 |  | note | 703.07
label | 0ef98ff4-794d-4710-8deb-7c833e24eb17 |  | note | MRPA Quality Management Plan
label | 6e1b59dd-a3bb-4c3e-81e4-07a30c57e6f6 |  | note | ---------------------------------
label | c2f0cf2b-3f9a-42d9-bf4f-979d7ae91ea4 |  | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
label | bd3f7e78-55c6-4f32-b52e-f7d9e7fd5c0a |  | note | Paving concrete mix conforms to AS1379.
label | d14895ad-d615-445b-9a34-922d35554c89 |  | note | SUP concrete mix is registered with VicRoads.
label | e7e3fbe6-78d2-49e0-a4cb-8370f072ad18 |  | note | No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | 25c4eecd-dcd6-41a3-9984-a7989e1a2a22 |  | textbox | Enter: Teambinder Material Approval number
label | 6430a9fc-48eb-4d58-bc7b-82a959784726 |  | note | ---------------------------------
label | 9f99c46a-9398-40fd-af51-0bbe1ed22f08 |  | note | METHOD: Document Review
label | 4a389d24-e3f3-4390-b457-9472fc4e2a8a |  | note | ---------------------------------
label | ecfb8415-d1f6-4f3e-9367-565bfaed2308 |  | note | FREQUENCY: Once, for each mix design, prior to placement of concrete
label | 233e294a-5d74-4ed2-b851-81142ed5e3ae |  | note | ---------------------------------
label | d87045b5-8dd8-47e5-8744-62044f6acf6d |  | note | CATEGORY: HP
label | f43c312b-ebbc-4161-9fd2-9df5106907e2 |  | note | ---------------------------------
label | 5258b811-04e5-4d61-b3cb-f6fb9ee02a1b |  | note | RESPONSIBILITY: Nominated Authority
label | ac77d9ae-0da3-41b8-b0a6-38ab3368fcd0 |  | note | ---------------------------------
label | f7471dd0-3d4f-4c51-a751-3b8e56ce38c1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 667e967d-5ecf-4a92-b45e-0577a0fc2eeb |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Reinforcement Certification (or ACRS Certification)
label | 98562499-983b-45fd-9f66-c00c3bdbaaa9 |  | note | REFERENCE: 703.13
label | 9c39bdba-942e-4342-af49-3c1ca99faa46 |  | note | MRPA Quality Management Plan
label | 3c7c3087-9d1a-48c6-831d-37e9dfe73ab9 |  | note | ---------------------------------
label | 5da98cf3-29aa-4dfc-a218-088faba99a25 |  | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | 3761f9fb-e59c-4a4a-9b14-023d31f78d1d |  | note | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
label | 7c5a204f-26ad-486d-9bfb-e5474b981b63 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 6b4c6ac9-ff43-4de9-887f-8d1d9b03d603 |  | textbox | Enter: Teambinder Material Approval number
label | 2ae7c1d5-3168-47d8-9e0d-834b015038a7 |  | note | ---------------------------------
label | 4c0ad25b-644c-42c6-b62c-8160d4b98b70 |  | note | METHOD: Document Review
label | de0dd9ef-2a67-4617-a71e-60735efa3f17 |  | note | ---------------------------------
label | d5e18b32-0a27-4d24-a337-6ee41d13db8b |  | note | FREQUENCY: Once for each supplier, prior to placement of order
label | 84257bad-34b5-43d2-9bff-3d87e70ae5dc |  | note | ---------------------------------
label | 53bc7105-57fe-4a2e-b49b-3cedf6feed06 |  | note | CATEGORY: IP
label | 4e89890f-d4c9-40a9-ba22-995db2ff10fc |  | note | ---------------------------------
label | 78b3c47d-826d-4a02-9980-9f29336fdd1e |  | note | RESPONSIBILITY: Nominated Authority
label | 83bcc8e9-d052-472e-8a3d-3541ed001b68 |  | note | ---------------------------------
label | 8f30a65c-5ef2-4fb6-b781-723d332c6481 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6ddfc44b-d165-4aba-9452-b1ffc6001fe8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Evaporative Retardant
label | 7e4eac05-6ccf-4d24-aeb0-0a2505e1da19 |  | note | REFERENCE: 703.09
label | 0edd46b1-9685-4b67-b278-1c66d2e13338 |  | note | 610.17 (f)
label | 7d97429f-b5dc-4931-847c-a1bf96ff9162 |  | note | ---------------------------------
label | fd543eba-e73a-41f1-9eeb-c31a5b32cd16 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 27fa5683-3c34-4073-9f7e-fcc7520f85a8 |  | textbox | Enter: Teambinder Material Approval number
label | d90848d8-6c6c-4fee-9fb7-aa0e50de3cda |  | note | ---------------------------------
label | 02f501ae-db5f-4089-8827-db0c0daefd47 |  | note | METHOD: Document Review
label | de915b78-1843-4033-83bc-a39df991da57 |  | note | ---------------------------------
label | 9fef0073-70ba-4833-b631-058a1e72be8f |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | af16a79d-662c-47a0-834c-4e6146991f49 |  | note | ---------------------------------
label | 997a7cb6-0d66-4c99-9e0b-3c30db3484eb |  | note | CATEGORY: WP
label | b8ded91e-d66e-4240-832c-9bffa7b06083 |  | note | ---------------------------------
label | 674577e4-ae65-4774-a8e9-1c8081898120 |  | note | RESPONSIBILITY: Nominated Authority
label | aee89f52-e4be-405f-a680-4cb351ce879d |  | note | ---------------------------------
label | 94bf6b8a-2773-487a-9135-474a1e3354d6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7a7ee111-51af-4320-8c82-e4b2c1ab1532 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Curing Compound
label | 8c311983-fd06-4d26-b5e6-e2c2aa81b494 |  | note | REFERENCE: 703.10 (a)
label | bf38ad26-ccd1-4bdf-ab16-beddc1a0c4c0 |  | note | 610.23 (d)
label | 209e4d52-a41a-43e1-8320-26eb4349029b |  | note | ---------------------------------
label | cf6f737b-5fd7-411c-b825-d8d2daa2eb27 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | 088b4614-0aeb-4431-84d6-0717c166ea1a |  | textbox | Enter: Teambinder Material Approval number
label | bd003248-94e1-4ce2-977d-2869ce38f2bb |  | note | ---------------------------------
label | 792b7124-7316-4a4d-8c9d-fee2d48695d8 |  | note | METHOD: Document Review
label | 785f59fd-90d8-4e7b-acd7-8167f02a6537 |  | note | ---------------------------------
label | 36e94589-9d5a-42a7-960a-72c29b69208f |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 41568339-4479-429d-8bb6-6cfee53243c8 |  | note | ---------------------------------
label | bc3b7d2f-13e7-4d9a-9814-3ee5eeb4969a |  | note | CATEGORY: IP
label | 17cd1623-d512-4bc6-9fcb-1214cf0e6d01 |  | note | ---------------------------------
label | c27354cf-f07d-43a0-aa02-b2c2ef5abcfb |  | note | RESPONSIBILITY: Nominated Authority
label | b172b885-be91-4382-b581-87687d365812 |  | note | ---------------------------------
label | 08e469a8-651c-4489-b45c-f9df40c376c4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 294edcd0-54d2-4137-8a69-11c812df0450 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 IFC Drawings
label | 7c8d5d66-7327-46d6-93b4-8c10ec6ed52f |  | note | REFERENCE: MRPA Quality Management Plan
label | b4d7feec-8921-4cf7-a99e-9bfe907f2e2b |  | note | ---------------------------------
label | 134ce982-9b9b-4d9a-ba0c-b7cb072ac3da |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 33066f4a-c0da-427c-aac6-4865d1343b0e |  | note | ---------------------------------
label | 5cab495a-b35e-4f8a-83ef-a51a2aed8f23 |  | note | METHOD: Document Review
label | bbb24b57-3382-4961-ad80-b4485c0ed057 |  | note | ---------------------------------
label | be09dcac-689b-41d2-b55d-d706107eea72 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | acaf62fd-7040-4233-b916-8d01edeef282 |  | note | ---------------------------------
label | 56a3b33b-b9af-4cba-88ac-5efd1707acd1 |  | note | CATEGORY: HP*
label | 751a8f4d-5c55-44ed-992b-1f0c2ead51fe |  | note | ---------------------------------
label | 23ede68d-d2a5-4cb1-84e9-666e17d6ba4a |  | note | RESPONSIBILITY: All
label | 98ef2bde-f849-4ec9-a699-89bc02630c03 |  | note | ---------------------------------
label | 525759d6-1aa6-47a9-b48c-504002947367 |  | note | VERIFYING DOCUMENTS: This ITP
text | 40fdcbf1-f24f-41eb-9f7d-807e0f45d520 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Formwork Construction & Placement
label | 408f780b-84a7-48e9-bc8e-041b2ab50fd7 |  | note | REFERENCE: IFC Drawings
label | 6aa6da5a-1f39-4761-9728-427729ffc3a2 |  | note | 703.12
label | 53f974fd-b30c-4d66-a02a-86556cf20ff3 |  | note | ---------------------------------
label | 962857e4-50ec-4ece-9ff9-bd8247e9ec56 |  | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | 9c23e6f8-9cfe-4cd0-97d3-eb89bf7c8bfc |  | note | Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | 96db35d4-17ce-4763-8ff5-32e916aec90f |  | note | Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 0e32a58b-8518-499f-b511-0d6174f6e47b |  | note | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 013efbc8-7584-47a9-9e23-65c01a1fedfc |  | note | ---------------------------------
label | c4bcfa7a-d416-4bad-ad6c-9a4a967d810e |  | note | METHOD: Visual Measure
label | a1df013f-b89f-4c99-913e-78b9cf1dde1a |  | note | ---------------------------------
label | 6b851ef0-e3b1-4b71-bd5e-6fd4b51336b7 |  | note | FREQUENCY: Each lot
label | f966ffa9-7b60-4203-a1b8-ffd7341e24e8 |  | note | ---------------------------------
label | 6d147b2c-7df7-41f6-b38d-94dfde857666 |  | note | CATEGORY: IP
label | 0fc131de-3515-4937-a3bb-4d1cf7d50424 |  | note | ---------------------------------
label | b37451a6-8a55-4b22-84df-2fabc7be78b9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 737c48f7-7e48-47d6-99e6-739dac8e82d7 |  | note | ---------------------------------
label | e3b27bbd-b7f4-4c78-8a15-43ff7957e324 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6045c473-8683-4986-92db-7c1cdf6bd944 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Construction Joints & Matching Existing Surfaces
label | 621561c6-e59f-4487-b854-acdb76920af6 |  | note | REFERENCE: IFC Drawings
label | 4104d43c-d53a-428d-b41e-ea5668b19b42 |  | note | 703.24
label | 8a72140a-bc8a-4f51-9d55-afad4ae73329 |  | note | Relevant Council Standard Drawings
label | daeb6929-6c11-4c67-b209-67e287d17a02 |  | note | ---------------------------------
label | b253670b-c644-401c-824d-6564ce1833c9 |  | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | ed913ffb-810f-454b-85a2-80aef67a2aa0 |  | note | Consult the relevant Council Standard drawings for the joint detail, these may require:
label | 2b37ec34-e812-4fb0-afcd-94c6c54a9510 |  | note | i. Concrete cutting of a shear-key
label | b1f3f8fb-63e0-416a-8f49-50bf98f2ac6c |  | note | ii. Surface roughening
label | 74bd569b-3e4b-4b22-a0ac-502fa2316326 |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | a9857c27-c51c-49c6-b5c0-51ed15f3a0f5 |  | note | iv. Cutting a groove for sealant
label | 97312197-68cf-4864-a668-450e3dace83a |  | note | Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 24907ddb-5ee7-491d-bb2f-b7ddac153928 |  | note | Transitions between different profiles shall be made in accordance with the drawings.
label | bc640a47-fac6-4428-be29-e0a0808d5073 |  | note | Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | cd78a15b-77e6-44ca-9319-4d04f1d765ce |  | note | ---------------------------------
label | 93e7d189-4906-45f4-a9c5-1bb3c167986f |  | note | METHOD: Visual Measure
label | e3540f0a-c81d-4fe3-80e0-91d019347021 |  | note | ---------------------------------
label | 88722b7b-7742-42eb-ad5f-5464ed406ecd |  | note | FREQUENCY: Where applicable, each lot
label | 3173408f-0a84-419b-907c-68dd3a034fae |  | note | ---------------------------------
label | 9cf73a11-f16c-4659-91c3-6283ecca863c |  | note | CATEGORY: IP
label | 2ec20f4d-fc0b-445a-a4fb-0ad0a0f5df92 |  | note | ---------------------------------
label | 7e8a1ace-d6fe-4837-8cba-a1bd321adcd4 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4416e791-efce-4572-ad1b-47f5b7599504 |  | note | ---------------------------------
label | 217edd6f-8a8f-4f70-8b6b-43b65dccd072 |  | note | VERIFYING DOCUMENTS: This ITP
text | f20308cc-79d7-4ff2-ab24-0f841e7bfca6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Isolation Joints
label | 7981e081-6023-49dc-959a-78f0d777ed76 |  | note | REFERENCE: IFC Drawings
label | b5a9e92d-a718-4774-a259-2370297dd792 |  | note | 703.26 (c)
label | 92923679-eb7e-4213-989c-c8313db7dbb7 |  | note | Relevant Council Standard Drawings
label | 0deebdcb-0e4c-491b-b227-65777156ac72 |  | note | ---------------------------------
label | 35a8af22-f2e1-4ddf-9f51-d36ce1a4c7ba |  | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | 7d2ee1ed-4075-47f7-8d8a-08d04ef67a1b |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | e3b36e99-cd6d-4072-8256-5d01f35ceb0b |  | note | ii. at any location marked on the drawings
label | 29bd45ae-6104-41ce-b617-0503dff59aee |  | note | The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | bb66aaa6-74bd-401c-9f69-62afe9e4c0d1 |  | note | ---------------------------------
label | 1e1de7af-c131-43f7-ae71-39d9a7f3ecb0 |  | note | METHOD: Visual Measure
label | 1a4dcbad-7bfe-445a-9ef3-d20b5981cd4d |  | note | ---------------------------------
label | 7a500430-a666-4b0d-beee-fc22ed182041 |  | note | FREQUENCY: Where applicable, each lot
label | 354bd5df-214d-470d-9167-c424d1f5cc07 |  | note | ---------------------------------
label | 0b04e346-6555-4c33-a4ec-79e879105d62 |  | note | CATEGORY: IP
label | 4e6fcff7-1408-4b27-a0f4-bd03095baa8d |  | note | ---------------------------------
label | d70f6367-0ba0-4b94-a928-542783e60f3b |  | note | RESPONSIBILITY: SE/PE/SPE
label | e81e5e1a-1868-484d-8979-76097d040e66 |  | note | ---------------------------------
label | 66ddec3c-cdbd-458a-9ee4-fe42e409e6cd |  | note | VERIFYING DOCUMENTS: This ITP
text | ec9f6824-c86c-4973-89a7-c2090816a636 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Expansion Joints
label | 3a08c80a-a64c-46f7-9b11-3ff81702cee7 |  | note | REFERENCE: IFC Drawings
label | fe1fbf80-3db8-40d5-895a-7dd223e35f67 |  | note | 703.26 (a) (ii) & (b) (i)
label | 8104cd54-9144-4d77-8d9d-d10d4af55bbf |  | note | Relevant Council Standard Drawings
label | 918c0b77-74bc-482e-a3e5-36956ba24da3 |  | note | ---------------------------------
label | 52423121-fb2c-402f-9b56-14dff3505c4c |  | note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
label | 17c0926d-945c-48af-bc29-ed67b5d86bcf |  | note | i. on either side of vehicle crossings
label | 3728ff95-44e2-4472-b768-66f5262a0e07 |  | note | ii. at junctions with existing footpaths and shared use paths
label | 1adff3b5-1ecf-4e63-bf7c-87f36d367a10 |  | note | iii. at junctions with bridges
label | 24b0a45d-9aba-484b-a7d2-b261bd39d579 |  | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | ae8528c6-1dbc-4647-822b-e60b75841890 |  | note | The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 16e4ae46-db4f-4d25-a81c-27203732e850 |  | note | Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | c845caf8-6662-44b7-81da-8a8fa41611fd |  | note | Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | 438346d0-701f-4c9f-91c9-bedfea5b644c |  | note | ---------------------------------
label | 30c9eab1-5493-409d-b6be-0e263b7d5ced |  | note | METHOD: Visual Measure
label | f2a948db-aabd-41f8-b806-a5bdbbf45e58 |  | note | ---------------------------------
label | 084c92fc-7eea-49c5-b781-3e213d2a66e0 |  | note | FREQUENCY: Where applicable, each lot
label | 56ed41cf-91d7-4ec1-bde2-8cbc45618e36 |  | note | ---------------------------------
label | 5f3cfa5e-7b6e-4b06-8903-0ef41e9c2dd2 |  | note | CATEGORY: IP
label | 82448220-8287-4a9e-9098-9a634ddcd317 |  | note | ---------------------------------
label | 3d3346a2-5dd3-4084-8276-0a194b3c9256 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 881e174b-e96c-43d2-bed8-02938dd128c3 |  | note | ---------------------------------
label | 22d33661-e0bd-4ea8-9813-4364aaa6bfa6 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2e5289d4-1d35-4ef6-94d5-5403cb1fcac7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Reinforcement Placement
label | 1ecedffa-a65c-4af9-abc5-adf130aac21e |  | note | REFERENCE: IFC Drawings
label | 24891543-ce76-49f2-b700-e0b7cf8ce65c |  | note | 703.13
label | 31e95e70-39db-4b56-9bcb-7fed3f47534d |  | note | ---------------------------------
label | dd803453-ecda-4700-835e-a41612c25151 |  | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | 33da0349-32db-479e-b9ae-7d1e41b6cb84 |  | note | Any splice lengths achieve the minimum length and are in contact for this length.
label | 5adb8bc6-55a9-436b-adf1-4756263e3591 |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 60cc5baf-338b-4be4-a531-6ce01084503a |  | note | The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | 9133d4d7-6b73-468d-965e-832f3968e587 |  | note | Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
label | fee73fe3-6c1f-405b-92ba-a21361bf9a69 |  | note | Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | 88c2f8e5-b36e-4200-b125-a8a47302a298 |  | note | ---------------------------------
label | e29eef73-c5af-43e7-b464-a97540c56113 |  | note | METHOD: Measure Visual
label | a7519396-8263-475d-940d-3bf183186959 |  | note | ---------------------------------
label | 0a839a40-bd59-40bc-8246-ce821245fa37 |  | note | FREQUENCY: Each element
label | 15f3c5cc-b207-43c9-9ca6-b0beda8db3a0 |  | note | ---------------------------------
label | aaaab1c8-07e7-4cbe-8060-df139ea6e245 |  | note | CATEGORY: IP
label | c86fdece-5a2b-47d0-a55e-f53f08993709 |  | note | ---------------------------------
label | 553a4f0a-925c-44f2-85e8-a5b5c38bcfc1 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 1fdb0bc6-b36b-4946-b1c6-11e0491d2dc9 |  | note | ---------------------------------
label | 9e6f03bf-21d5-441a-a88a-40d0e527290d |  | note | VERIFYING DOCUMENTS: This ITP
text | 5979296c-47b8-4055-9148-523ea0b7ae4e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Pre-pour Survey
label | 53bed2c4-c84a-4ccb-94fc-caedfd203b33 |  | note | REFERENCE: IFC Drawings
label | e939ed62-0528-458c-9e4d-fde72979e756 |  | note | 703.15
label | 5d93b411-dcd1-414a-a81e-86f25582d5be |  | note | ---------------------------------
label | 17eea297-9015-4a87-8662-12806a94f814 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | 342025a4-235f-4a14-8266-d66a5bf0497d |  | note | Erected formwork and base layer within the tolerances below:
label | 32c72aa6-7c41-4bc4-88ae-9b662cddf787 |  | note | Departure from RL = ±10mm
label | 13121b8c-95fd-4dc0-9ab1-14bc5bf39820 |  | note | Departure from alignment = ±10mm
label | fd7234be-7440-4e7d-83c4-65585949df73 |  | note | Rate of change of deviation from RL or alignment = 10mm in 10m
label | 5fc14115-e500-4ac5-b870-573b48fa4048 |  | note | Irregularities in alignment = 5mm in 3m
label | a70ebdf2-6202-4a4f-8783-dd50c4129e72 |  | note | Section dimensions = ±5mm
label | 53ce4daa-87f0-4f44-94d2-9c3b26bb5fc7 |  | note | Section dimensions (less than 25mm) = ±3mm
label | 7a5f37ce-470f-49dc-a5a5-d79984e82c9f |  | note | Width of pavement = -5mm, +15mm
label | 1cfea96c-1a93-45d4-a38b-b141cefd5ec3 |  | note | ---------------------------------
label | 10b294e8-42f3-4dac-886e-ea0a35f69905 |  | note | METHOD: Measure Visual
label | 0c12db5f-2dc7-4f61-836e-feb0397446b0 |  | note | ---------------------------------
label | c21276c4-ee81-4dd5-a05e-389c9372cfca |  | note | FREQUENCY: Each lot
label | 330ae596-0387-4e97-874d-3fa106dd1e44 |  | note | ---------------------------------
label | f29c781c-35f9-4d33-8d79-c748ead57038 |  | note | CATEGORY: IP
label | e9a3a3a8-71d2-4e14-ad7a-0481f81db558 |  | note | ---------------------------------
label | 0ad533b7-26f0-4258-ac0f-82392bf7c062 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 66ae16dd-ca1a-4087-b91c-a98090db5123 |  | note | ---------------------------------
label | 2a1dfecd-99d3-4849-b53d-1df635046efb |  | note | VERIFYING DOCUMENTS: This ITP
text | 51ba7965-5308-4a73-98ac-d7d050f2e646 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Pre-pour Inspection
label | cd1e33b1-cc66-49da-919f-8886669bf004 |  | note | REFERENCE: IFC Drawings
label | 4d83324e-11fc-41a5-b50e-a87455a10087 |  | note | 703.15
label | 9a6ba483-ec47-4cdf-a2c6-cffd0e4d0141 |  | note | 703.21
label | d54901e4-7106-42a7-b9da-94fd6e2ae711 |  | note | ---------------------------------
label | d1067965-a639-432a-a5ea-003252d480fa |  | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | 47f535ab-5622-4e81-bd0c-6df2f1e76e16 |  | note | Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | 83d5f037-2464-4b98-8420-95e1354df293 |  | note | ---------------------------------
label | 964d117f-bac9-4857-8166-32f137f9d82d |  | note | METHOD: Measure Visual
label | fb4cf554-1994-415c-a820-f8734f450dd6 |  | note | ---------------------------------
label | 17655191-b942-4a56-83f1-c975e0c1ebd1 |  | note | FREQUENCY: Each lot
label | 46ab8c32-223f-401f-8823-547f316b278d |  | note | ---------------------------------
label | ef16bb95-3479-46b5-94ac-3ff0004d78e3 |  | note | CATEGORY: IP
label | 9e2ddcea-a09a-4fab-86d3-57f0bf1f38bc |  | note | ---------------------------------
label | a33f2ee2-37da-4000-be23-922346264565 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 39c95412-62d0-431c-9548-966c0b3a3bdb |  | note | ---------------------------------
label | 0157cf52-20b9-4774-a742-65a935d5516b |  | note | VERIFYING DOCUMENTS: This ITP
text | fdb1dc6b-8b1f-492a-9022-bcbe2588e76c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Weather Conditions & Evaporation Limits
label | e38c734d-c24f-4b7a-b2ee-a1d78406dc49 |  | note | REFERENCE: 703.09
label | 1bae9ab3-7cd1-4b35-a4d8-19265c9f33be |  | note | 610.17 (a - f)
label | 63d28faf-1604-491a-aab1-502108057e2a |  | note | Table 610.171
label | bd78a19f-534c-4669-a4e8-d4a0a31b6202 |  | note | ---------------------------------
label | 8e6f888d-2fb3-405a-b6e2-d2e1fc62001e |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | 93bb96c7-e193-4e17-8a78-87251526bc61 |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 7a6d2cfe-eba9-417f-be36-1916e7e8c94d |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 2dfed09f-ec4c-4719-b563-a9dedf843797 |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 6bc46892-79e8-484e-a5ab-61ae008f5ab1 |  | note | Record: Required information on the Concrete Pour Record.
label | 277f7640-03c7-406a-8521-92bf6129e336 |  | note | ---------------------------------
label | e0cbe1bc-daca-4d92-8ebe-1d0a19aaba93 |  | note | METHOD: Measure Visual
label | 9983f6fc-bed1-49bb-aeae-0383ebbdcf8c |  | note | ---------------------------------
label | 65972df2-efdd-4cba-8f8a-7ff901d76dc4 |  | note | FREQUENCY: Each lot
label | 63dc228d-7635-4e98-b9c9-9b5d0615c057 |  | note | ---------------------------------
label | 5c72c765-b6eb-4fdb-a1f7-8b800588e6d5 |  | note | CATEGORY: IP
label | a69fb8c5-33eb-41cb-9117-d16a8b2ee2a7 |  | note | ---------------------------------
label | 21ed0d3c-e736-4ae4-98f8-3b4058bfa64a |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 397ec0bf-b966-493c-8822-cb24ccd4af25 |  | note | ---------------------------------
label | 64aada0e-7bf7-4bf7-a5d9-0952d36e0f9a |  | note | VERIFYING DOCUMENTS: This ITP
text | 28b7d9ec-6b74-423c-abec-7bb9b946917a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Concrete Testing - Sampling Frequencies
label | f2dab0c6-69c5-4988-b591-63c49f2b8e56 |  | note | REFERENCE: 703.11
label | bffbe978-9049-42c5-913b-67121931e2a9 |  | note | 610.16 (b)
label | 7240eff6-e589-4ee2-bed6-b59c422c81ba |  | note | ---------------------------------
label | bd43e53e-613c-40a6-a679-2381d4afe208 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 101105e6-8948-4191-8fd2-a2a37d059cc6 |  | note | Shared User Path:
label | 51cd49e8-e2d3-4f4b-b614-52493be37baa |  | note | 0m³ to 10m³ = 1 sample
label | e25d8d4d-a249-4065-9e4d-23ac488677d9 |  | note | 10m³ to 25m³ = 2 samples
label | 62e03843-15eb-4e4f-9deb-9d7d72dad360 |  | note | 25m³ to 50m³ = 3 samples
label | ed722dd4-e820-44d1-b4a7-8969b9ca88bd |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | e6e8d9de-7cb6-42b9-80a3-fdac16d42287 |  | note | For each additional 50m³ and additional sample shall be taken.
label | 228622a5-b68f-4eb2-a06e-ca4f43e9f5da |  | note | Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
label | 37e6d5ad-2a7a-4b19-a2dc-eaca63a58550 |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | b82c7ae8-b0c0-430b-8bde-324f823b9724 |  | note | Footpaths:
label | 6ec473d9-358f-4493-9e18-0bdc96432720 |  | note | 0m³ to 50m³ = 1 sample
label | ab291b4f-8837-4a7b-adc8-12774c947f00 |  | note | Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | 9a212bfb-024e-4510-8164-12e0a2b72e83 |  | note | Compressive strength cylinders = 2 no. 28 day strength.
label | 0d5e5179-b2eb-4747-aef2-f452135f41df |  | note | Record: Required information on the Concrete Pour Record.
label | f408bac7-d94a-4aec-afbd-d021ba7533cb |  | note | ---------------------------------
label | c770adcf-b1c2-444e-bf42-06e9adf5d07a |  | note | METHOD: Test
label | 86b14379-d21e-4fa9-af4f-d8dd0e076d35 |  | note | ---------------------------------
label | 151e5cc8-2b61-4998-a158-c162de196948 |  | note | FREQUENCY: Each lot
label | a7d8deac-b54b-43dc-ac06-e7b708cab5f6 |  | note | ---------------------------------
label | 45b1ef30-96c9-4d2d-a957-2924620ee11d |  | note | CATEGORY: IP
label | d64ae04e-003a-4fb1-b100-02af9b6ad71d |  | note | ---------------------------------
label | 6f04b8fe-a330-4301-a1ac-dfb48d59cee3 |  | note | RESPONSIBILITY: Concrete Tester Foreman SE/PE/SPE
label | a1b17c0d-3da5-42ba-a617-78856db9cd74 |  | note | ---------------------------------
label | 3a22b43e-fc18-48b7-9363-1780a7251890 |  | note | VERIFYING DOCUMENTS: This ITP
text | be893ca8-37dd-4762-853d-c46b7750b635 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Concrete Testing - Slump
label | 44d77a05-a0ba-40c3-8152-4045c70414fb |  | note | REFERENCE: 703.11
label | 473f40e9-f359-445a-a9ea-c1806cfd6894 |  | note | 610.16 (c)
label | 53ade6aa-6914-41c0-9c2d-15b3b74ed8df |  | note | ---------------------------------
label | f7ea99a9-3268-4e3c-bac6-e9448ead3312 |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | bd9b972a-d7d6-48e7-9faf-bbc8456e5088 |  | note | <60mm = ±10mm
label | 01400972-cae8-4beb-9d46-6682be2a3037 |  | note | ≥60mm to ≤80mm = ±15mm
label | 176a1a5a-0bb4-4804-a24b-491b130f7c88 |  | note | >80mm to ≤110mm = ±20mm
label | 5bb18462-28a3-4351-9323-2c166de0bca3 |  | note | >110mm to ≤150mm = ±30mm
label | 0cd0cdec-0454-415d-b69b-709791051dd8 |  | note | >150mm = ±40mm
label | ae487e24-1166-4c96-aaff-be957b89eb44 |  | note | Record: Required information on the Concrete Pour Record.
label | e38e0645-c5f9-4207-887a-33be5f26eb29 |  | note | ---------------------------------
label | aedd1c10-3702-4ee5-9394-3f93d48443e0 |  | note | METHOD: Test
label | 07a8e808-1bdb-4bd8-9eb9-aa5734ca5489 |  | note | ---------------------------------
label | d9f3dd9d-5165-45ae-b09d-acf9be6b978f |  | note | FREQUENCY: Each sample
label | 1e498cf0-5b61-4811-a060-ae04e8963d87 |  | note | ---------------------------------
label | d058f09f-421d-4163-817e-3cdf72498887 |  | note | CATEGORY: IP
label | 0497ebf8-bac7-438c-8490-004b969d3fd5 |  | note | ---------------------------------
label | e87e8945-edf6-4e71-aed5-0b851b7e679a |  | note | RESPONSIBILITY: Concrete Tester
label | c80f0519-3378-44f8-bdf4-b2608e034996 |  | note | ---------------------------------
label | e0133e5a-9a01-4d1d-bb63-531702c4a593 |  | note | VERIFYING DOCUMENTS: This ITP
text | aa050043-6a5a-4464-9d57-849b59556d0a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.11 Concrete Testing - Compressive Strength Cylinders
label | 4c8817ab-b1ee-4a6c-8511-3af8ed081b00 |  | note | REFERENCE: 703.11
label | c595d52a-5a46-4cea-b576-654c9eca6d12 |  | note | 610.16 (d)
label | d30e07a5-196e-4354-b908-5d9da50b5952 |  | note | ---------------------------------
label | b25e76b1-38f2-40ca-b232-3bc0c5cc9814 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 17f0190f-fa31-41cb-be70-b502690047d2 |  | note | Record: Required information on the Concrete Pour Record.
label | 9f696cfd-5808-4448-a6b3-606491fa3b2f |  | note | ---------------------------------
label | 11684d28-952d-4276-b170-dadd58164591 |  | note | METHOD: Test
label | de53c331-2f1a-4f68-be64-510f30340dd7 |  | note | ---------------------------------
label | 3db6d44d-fc69-48b8-aa7b-a9ba7ae4b749 |  | note | FREQUENCY: Each sample
label | e4f22d2e-f12d-40c9-9619-b26c22063e61 |  | note | ---------------------------------
label | 43050026-1d22-4267-8109-ac48ebdd99b0 |  | note | CATEGORY: IP
label | 65481a0e-7425-4310-9926-9ec0b2b483e2 |  | note | ---------------------------------
label | 98c68c37-40d4-4c92-b6a9-9b6e53c39047 |  | note | RESPONSIBILITY: Concrete Tester
label | 3ab7597e-185a-43c2-b3da-04aaccbe5cc5 |  | note | ---------------------------------
label | 99ceec44-16cd-4d46-b70c-d43b8c6b659d |  | note | VERIFYING DOCUMENTS: This ITP
text | bcfbc617-c711-44b8-b403-1a9e9525edcf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Supply & Discharge Rates
label | c9a0a382-21d0-4c99-ac8d-4bb58abf04a1 |  | note | REFERENCE: 703.08
label | 91a46640-c3d8-4775-94e4-7626bb9b99e4 |  | note | AS1379 Clause 4.4.1
label | 2b4bbc1b-8b31-4ddb-8eae-3caa2adef505 |  | note | AS1379 Clause 4.2.3
label | 61bbea6a-88f2-415b-87cf-763f9c14701e |  | note | AS1379 Clause 4.2.5
label | 62fca4e4-4f76-418e-b340-9f7d528ed350 |  | note | ---------------------------------
label | ddd37e8c-0bd6-4400-84f0-10f6e993f73a |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | 68ea05b1-0cab-42f4-9cd5-83ebc4f21944 |  | note | Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
label | 40434d21-46c0-486f-95a5-b66dc81f8aae |  | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 66cb32dc-be09-4213-9b9c-08363586d1e8 |  | note | If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
label | 4db4d4dc-42ed-4456-89d1-144de20ea5c0 |  | note | Record: Required information on the Concrete Pour Record.
label | df02c409-bd73-477f-9ad1-72c023197929 |  | note | ---------------------------------
label | ce28f967-0eee-4181-a22c-177cd243f3a4 |  | note | METHOD: Measure Visual
label | fbb432d9-be41-43fb-92cc-8136bf0842a4 |  | note | ---------------------------------
label | 93ef5980-9661-445f-aaba-9966e157bf9a |  | note | FREQUENCY: Each load
label | cfad3968-e219-4c57-8934-9de174543cd6 |  | note | ---------------------------------
label | d8ad15ee-559b-43c4-8370-6941f560280a |  | note | CATEGORY: IP
label | a9157d63-87c7-4230-aea3-7df07d9b3f49 |  | note | ---------------------------------
label | b5c0d04f-9ea7-46ca-9c71-f10ff6f59e31 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | a32736e3-7d8a-4ca6-8cbf-f2a73076d8cf |  | note | ---------------------------------
label | bd06073f-d0e7-4bae-92c3-bf2b57eabaaa |  | note | VERIFYING DOCUMENTS: This ITP
text | e853733c-2c99-4806-bd93-0c6e4eeed230 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Placement & Compaction
label | cf25eacd-f513-4d3c-b748-d6fc8b0264be |  | note | REFERENCE: 703.08
label | 98143921-faa3-45d1-bf75-d81b45688863 |  | note | ---------------------------------
label | 90102c7f-e0c7-4fb5-af37-f4c0df6f8157 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 062b12fa-8da4-4bfe-865e-9e469001468b |  | note | Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | 509285a4-58fa-42c8-b2ee-8649fef2c0c7 |  | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | ff21763b-91f3-4367-a839-efa9f7d128e6 |  | note | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | 9aecf439-ad08-4e7f-94e6-afab7103a1e9 |  | note | Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | f77c0bd5-0035-4bcd-9549-b1e81457bb07 |  | note | Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | b32bd32d-572c-440b-8ab7-381d176a393d |  | note | Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | e31478c2-d2e1-4ce7-9d20-5046e870e658 |  | note | Record: Required information on the Concrete Pour Record.
label | 5e78809e-7506-4b11-b025-26a72c761fcd |  | note | Attach: Concrete Pour Record
label | 94eb13f8-c7e4-4abb-b6aa-8d2d0dffe72d |  | note | Attach: Concrete Dockets
label | f58175ef-74f3-4001-8020-439cd0dc838f |  | note | ---------------------------------
label | a5b5f2f1-d1ab-4a69-8c66-171c72e5cd89 |  | note | METHOD: Visual
label | eb07a0ca-a792-4433-97e1-50d02e9d2496 |  | note | ---------------------------------
label | 6109d760-13c1-4f53-a900-57cd77537c0b |  | note | FREQUENCY: Each load
label | 0abdb091-5ca3-43f6-948d-941ae5ba0b6e |  | note | ---------------------------------
label | 4ee4dc13-8573-4475-be51-e3719b59a69e |  | note | CATEGORY: SP
label | bd0630e9-c10a-401a-be64-7ddea16efb91 |  | note | ---------------------------------
label | cdffd630-994d-4772-9dee-d073d9ee237a |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
text | 169d8b5c-632d-4f75-8000-07c092a155d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.14 Surface Finishes
label | e57e3c33-2593-4bd3-9222-633ac0c32424 |  | note | REFERENCE: IFC Drawings
label | 610aeda1-db57-4240-91a6-76b92f6d0341 |  | note | Relevant Council Drawings
label | a59d0a7f-9528-4ea3-856a-b663e4468b13 |  | note | 703.25
label | bf837333-7a9c-4ed3-86de-2f64f40da12e |  | note | ---------------------------------
label | 74b86858-96bc-40bb-8893-ba8142eba2a4 |  | note | ACCEPTANCE CRITERIA: Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
label | 16fb5260-9ea1-4f4e-903d-26b53abbb76b |  | note | All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | a67bee43-401b-4f9b-9de9-d995e31afa6b |  | note | ---------------------------------
label | c4576ffd-9930-4acb-b363-49ac63f67d0a |  | note | METHOD: Visual
label | ecb1a0e2-0c7c-4b06-a933-df63a76443d3 |  | note | ---------------------------------
label | e0d0398b-a6f9-4ff1-96f0-5b0383e0f65b |  | note | FREQUENCY: Each lot
label | bee071f8-36d5-41b0-9159-8f29fbf3ce5a |  | note | ---------------------------------
label | 0a589212-9b2e-4ef4-b2c2-53830dfa1521 |  | note | CATEGORY: IP
label | 35c3f347-cd20-4535-ae4e-9394605841a4 |  | note | ---------------------------------
label | ef4905eb-d21f-4e4c-8b24-2302ea0dbda2 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 7ccf6cfb-4eef-471d-97cc-bfd8300bb89b |  | note | ---------------------------------
label | 65e49aa8-19a8-462f-a200-dc45db3b293f |  | note | VERIFYING DOCUMENTS: This ITP
text | 7e56597e-cad9-4320-bbed-bd1257cfe3da |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.16 Marking of Conduit Locations
label | a598c20f-1b12-43a3-9904-ec7b02dc0730 |  | note | REFERENCE: IFC Drawings
label | fab6f630-f268-4495-ad60-37ec83ab68d0 |  | note | Relevant Council Drawings
label | a768163a-0161-4704-9677-c9a18cecf539 |  | note | 703.28
label | 8a72475c-9a37-4518-9bac-bbf47be34c42 |  | note | ---------------------------------
label | 6ba11b5c-79c1-4c63-b2bc-c9ed2b30bd9b |  | note | ACCEPTANCE CRITERIA: The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
label | 263f46a0-168d-4cbe-94a7-bd71f4af92a1 |  | note | ---------------------------------
label | c78510d1-3b37-41c6-a52b-3d89be61d0a3 |  | note | METHOD: Visual
label | ea201d6e-1a35-4bf0-a09b-2a0be535e1ed |  | note | ---------------------------------
label | 3bf9caff-8615-4ff3-885a-3a641121195b |  | note | FREQUENCY: Each lot
label | c39306d7-b12a-4e20-8d5a-313cffcd2341 |  | note | ---------------------------------
label | db1fba75-adb4-4a24-9e13-c0e1ce291a38 |  | note | CATEGORY: IP
label | 3509622b-8db2-4cf6-9d30-784caf38a8f5 |  | note | ---------------------------------
label | 0d613dd0-ab38-4ecf-bbb6-91c7e2a43c70 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 37029378-6354-4964-822c-94d71dac9514 |  | note | ---------------------------------
label | d50b632e-a809-4f78-8516-9d719b914157 |  | note | VERIFYING DOCUMENTS: This ITP
text | 08f963d9-25e3-442d-9a47-989b61d12335 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.17 Footpaths - Crack-control Joints / Weaken Plane Joints
label | 87a67ce6-9001-461a-a988-5e98701e5941 |  | note | REFERENCE: IFC Drawings
label | 468560c2-c23a-40f5-8505-afce2e18e5c0 |  | note | Relevant Council Drawings
label | bac3af98-ff68-4f03-a713-866884542a68 |  | note | 703.26 (b) (ii)
label | 0fac8c7a-717d-4630-a1ee-14bce4c763c7 |  | note | ---------------------------------
label | d807cae2-2f77-4ccc-aed8-e5687c19fab9 |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | 2c622479-8500-4cea-b524-ee1c4cf79e32 |  | note | ---------------------------------
label | 8748a526-60b9-4328-b752-71e1ab1f6657 |  | note | METHOD: Visual
label | ccbef603-aad4-42ad-b57b-e2094e042b6a |  | note | ---------------------------------
label | 777b22fe-4e98-4497-9d4b-82a1fab25cdc |  | note | FREQUENCY: Where applicable, each lot
label | eed8576d-da58-40af-a637-21bc9890db3d |  | note | ---------------------------------
label | 7e746da3-f5c9-45fd-8b90-5ec9b9974ad7 |  | note | CATEGORY: IP
label | 495650a5-53f0-4f86-a30e-be2f6fc62411 |  | note | ---------------------------------
label | 2d82cc03-a81b-4086-b56c-47454790e805 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 7b24368b-8626-47e2-a59e-59bb66b40619 |  | note | ---------------------------------
label | dc4a236c-c0af-45fa-8255-8962035a8849 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8eafd9d6-ee07-4104-86ed-40e57c3622b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.18 Curing
label | daf73e5f-9a9c-4b4e-9db8-a33cd0a5f9f5 |  | note | REFERENCE: 703.10
label | 3256a2fb-33bd-4cd3-914c-38ac55fe4443 |  | note | ---------------------------------
label | 96cb89fd-4dd3-4029-8ee1-0af44dda9497 |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | aafde184-518a-472e-9806-271bcf43e6d8 |  | note | Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | 37d871c1-9ef7-4ee7-aa70-6859b03e7950 |  | note | The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | 887b4a73-9cd5-4589-b430-9256f9467e14 |  | note | Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | ca9b9e30-2afe-4a96-8fe0-acd2e1de315f |  | note | Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | dac9e088-b818-448b-9252-ba418c3fd9b0 |  | note | ---------------------------------
label | 49f6c12c-ecab-4a9e-9e8d-31694eba8a5a |  | note | METHOD: Visual
label | ce6eb688-276b-44a7-aebb-a23c2b317ef4 |  | note | ---------------------------------
label | d41fdac8-35be-4815-b28c-9c58e4889e74 |  | note | FREQUENCY: Each lot
label | 942bd805-4f3f-4d3a-936f-11a489961ff6 |  | note | ---------------------------------
label | a8e0d679-25ce-4625-966b-06b16ddd4ab1 |  | note | CATEGORY: IP
label | 8cff0cc9-c60f-4d56-bbfa-a4bfd250d07e |  | note | ---------------------------------
label | d716a33f-1f79-4855-a080-d2247899bfdd |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 3255c5e9-74c0-4d3e-be61-0ab43b2d7625 |  | note | ---------------------------------
label | f11e3817-088d-458e-9eda-9fd5ce224154 |  | note | VERIFYING DOCUMENTS: This ITP
text | d465321e-d32b-4f11-b880-884736ec3c18 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Shared User Paths - Crack-control Joints / Weaken Plane Joints
label | 7329dadb-b5f5-4b5c-ab97-4400fd10e91b |  | note | REFERENCE: IFC Drawings
label | bc368423-076f-4c86-b4b2-813015cb1608 |  | note | Relevant Council Drawings
label | a14c891b-030a-4d05-a1ef-4f92f87f1c4d |  | note | 703.26 (b) (ii)
label | 401e1c1f-435e-4c14-89b7-64765a42b807 |  | note | ---------------------------------
label | ea56a803-7625-4406-a3a8-c4c2dafa8dd9 |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | 97ffa1bd-fac6-4091-b6ae-49fe4e2b6774 |  | note | <20°C = within 24 hours of finishing operations
label | 367c6a36-dbbb-46b4-8774-842a9dde67b2 |  | note | ≥20°C - 35°C = within 4 hours of finishing operations
label | cfcccacb-c918-416b-9c6f-981a20db8967 |  | note | ---------------------------------
label | 0d2996d7-d306-483b-82b1-a916a3becc19 |  | note | METHOD: Visual
label | bdad8846-ec17-42af-9b12-8702082a7998 |  | note | ---------------------------------
label | 418e7756-20e8-4176-b37c-265ea4fb74f9 |  | note | FREQUENCY: Where applicable, each lot
label | 84b2372a-5ab4-4d4c-b239-52ac80e13df7 |  | note | ---------------------------------
label | bdb78c8c-8ebf-4365-9c8b-cfe5b08560ac |  | note | CATEGORY: IP
label | be1dd102-0b2e-4ddc-bfdc-4a7815109c48 |  | note | ---------------------------------
label | 0f3a4c65-54f4-43bb-a75b-35ab7f5e1309 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | cf100573-f337-4a42-9429-9924c86584e4 |  | note | ---------------------------------
label | ca7e5fa2-84de-43d3-9a06-59e7cc58502b |  | note | VERIFYING DOCUMENTS: This ITP
text | 0c843fbd-b025-4668-ac59-d65053d9293e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Protection of Newly Poured Concrete
label | e4afa30f-36d1-4a6e-a5bf-2b499de3c41a |  | note | REFERENCE: 703.27
label | 611095eb-1566-4c24-a6ec-7c34dbf7c730 |  | note | ---------------------------------
label | afe87f6e-2745-4327-8e42-3ca4c9def8ce |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | bca147c0-3717-47ef-8795-2a85fe5ec430 |  | note | Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | 2c80e356-dbbe-45f7-baf8-7dd18d1430d6 |  | note | ---------------------------------
label | d813c039-245a-48a4-a979-a82728d7dede |  | note | METHOD: Visual
label | 07ab5d34-810d-4428-af91-894779a7b70f |  | note | ---------------------------------
label | 7061a582-42b7-405a-9632-a5c92ec43268 |  | note | FREQUENCY: Where applicable, each lot
label | b500c974-d747-4442-baee-0e7cfad150a5 |  | note | ---------------------------------
label | 46718281-78f2-4771-a496-51606675214d |  | note | CATEGORY: IP
label | d33bf862-b971-4ec2-8848-298081225a5a |  | note | ---------------------------------
label | 64935bd1-6028-48cf-b815-cfcb78d390dc |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | bd45b5a1-9690-41a0-b97a-9378f17e6f5a |  | note | ---------------------------------
label | 62833124-393d-40a8-b07a-845ce35f6015 |  | note | VERIFYING DOCUMENTS: This ITP
text | a8151346-e87f-416e-acd0-68e415ce2ff0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Stripping Formwork
label | 3d2ac942-e276-4092-990b-3ee815235c1c |  | note | REFERENCE: 703.12
label | 4b2df7bc-7e42-4695-a7c2-62dd0afbc1c8 |  | note | AS3610 Table C2
label | 12465621-3fc2-4bd5-a272-89ca1d5926ff |  | note | ---------------------------------
label | d153c399-842c-47c2-bca8-664822bc4025 |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | 25efc9d1-abd4-4885-937c-586538ed02a9 |  | note | i. 2 days for vertical formwork on external surfaces; and
label | 1e789a30-751f-4281-98b7-00980ab2652a |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | ebc0d186-69b4-48d0-a6b9-2aac219227af |  | note | ---------------------------------
label | 008a6d35-3b9d-47aa-b14d-0f138cc3d835 |  | note | METHOD: Visual
label | bcd9aae5-2472-4c55-b2db-03ac4fa9a7c1 |  | note | ---------------------------------
label | 11e90f2d-4deb-4f56-8902-9c907f242897 |  | note | FREQUENCY: Each lot
label | 2d0ed3c5-4295-4746-8acb-795022de217e |  | note | ---------------------------------
label | 0295e0e0-966e-4678-adae-21ff2ead11f0 |  | note | CATEGORY: IP
label | dc28802f-4568-4f4d-a44e-56ecccaf2c81 |  | note | ---------------------------------
label | b664cdad-109e-4e86-8942-c39fb9883ae3 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 9d7fc65a-e616-44ae-b0f4-feb3ddfd4814 |  | note | ---------------------------------
label | aaf28c1e-b1c9-4566-b646-60b18f811c2f |  | note | VERIFYING DOCUMENTS: This ITP
text | 21a61a1c-13b0-4292-86f8-2cf4f43922eb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Backfilling & Pavement Restoration
label | d34349cc-eb82-4645-b0b2-783749160ae8 |  | note | REFERENCE: 703.29
label | d4855658-41d7-42f7-bb12-dda7064324c4 |  | note | ---------------------------------
label | 3be0cc8a-4ca0-4ee5-b5c4-58af94af2299 |  | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | af6a0395-4362-46f2-a409-065dde7cb91d |  | note | ---------------------------------
label | 7f818548-5c4c-43dc-b90c-f178bc1fd21d |  | note | METHOD: Visual Measure
label | 1e814697-800b-4b32-881b-00e07c150f45 |  | note | ---------------------------------
label | c4d9533a-0f09-4001-a2e0-9ba9dc2557f2 |  | note | FREQUENCY: Each lot
label | b2abf6df-acd0-4674-b56b-cca4e97c418e |  | note | ---------------------------------
label | 02c45cbf-b432-4c15-9590-9804068ed07b |  | note | CATEGORY: IP
label | 2edb1cf9-916c-4c6a-b18f-7eba207b3f6e |  | note | ---------------------------------
label | d29b79ad-e365-45cd-a7a5-d65877903942 |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 6d01e1de-c0cf-49cb-a632-b71c595b45d1 |  | note | ---------------------------------
label | 4baea288-145b-4e3e-9b2a-94c47581146c |  | note | VERIFYING DOCUMENTS: This ITP
text | 01857ae4-3c9d-41cb-8fd4-7ba430ea4a77 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Surface Inspection - Cracks
label | ae3923c4-1838-482e-94eb-d8d08216ed49 |  | note | REFERENCE: 703.3
label | 888196b4-4487-4c31-b9c0-be91fea897fe |  | note | ---------------------------------
label | d060e504-a8e3-4893-b803-3a278f66fac0 |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | 9ff532e8-b32c-4b36-add7-84cc1f830535 |  | note | If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 3d0a290f-2311-4189-93ae-87fdbc148e30 |  | note | ---------------------------------
label | 07ee1cb3-6705-45f7-943d-9a7876743263 |  | note | METHOD: Visual Measure
label | 22b24567-fec2-4518-87ce-afa868a1a41b |  | note | ---------------------------------
label | d8678f47-5295-4a19-ba81-a64478ee4c4a |  | note | FREQUENCY: Where applicable, each lot
label | 10d93f7f-c88d-4651-a7af-b9c2921ccdc4 |  | note | ---------------------------------
label | fb74088a-33ba-4825-90b5-5c20b16e6bc9 |  | note | CATEGORY: IP
label | 76e4a4ee-bb3b-44fc-8d2e-249ffee935d7 |  | note | ---------------------------------
label | 95e900dc-0b28-45f5-8e9d-b8f8da5b212c |  | note | RESPONSIBILITY: SE/PE/SPE
label | ad7d1670-1ec8-43bf-8fa2-3be1b2a566cc |  | note | ---------------------------------
label | 0f7c0c69-26cf-495e-98f4-74d6332a2a6e |  | note | VERIFYING DOCUMENTS: This ITP
text | 94940d11-d482-493a-aa3e-7fe848d1cc3a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Surface Inspection - Surface Finish
label | 061dfd2a-703d-4554-a7b1-ce2890853bd5 |  | note | REFERENCE: IFC Drawings
label | 61f47ecb-ff24-46f1-b255-290e20ad49ef |  | note | Relevant Council Drawings
label | af151f7e-d72d-4e5f-ad37-7743eaeb2ec7 |  | note | 703.25
label | 5ffaca4b-1f3b-4994-8b02-e41840b8a1d7 |  | note | 703.10 (a)
label | a01896cf-3bc1-47b2-9568-4dc1562b4239 |  | note | AS3610 Clause 3.2
label | 103a8ff0-583a-4458-b069-561bfb25f59b |  | note | ---------------------------------
label | 33efca9e-af38-4085-8106-fef7500469c4 |  | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | 178022d9-b818-4d0a-8f6e-7c88db11f8eb |  | note | All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | e1510328-76ea-42ca-988d-8d47de445295 |  | note | Class of finish:
label | 2401c5fa-5061-40cd-ba7e-bf8045af70a0 |  | note | Permanently hidden surfaces = Class 4
label | 5dc427e0-b302-45c8-b9f1-8bd432b6dcef |  | note | All other surfaces = Class 3
label | 6756adf9-0760-47c7-bc7f-be33c4149373 |  | note | At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
label | ecfe1095-bdf5-41a0-8927-6775fffd7ece |  | note | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | fb319ce7-dde6-437b-b3b2-f4599d24d506 |  | note | ---------------------------------
label | d8897987-a509-4a66-a13b-8b8234f3ff45 |  | note | METHOD: Visual
label | 69a25d09-cb60-4627-ac46-29613b3afb01 |  | note | ---------------------------------
label | 3fd2cfdd-0604-4733-9bf6-624c1bd77758 |  | note | FREQUENCY: Each lot
label | df394893-c2dc-410f-b51b-0a93a3ae5821 |  | note | ---------------------------------
label | 8886637a-8a02-47a6-addf-767519e9dec6 |  | note | CATEGORY: IP
label | 3595e05c-7875-4a24-a73c-7ed74d6f433d |  | note | ---------------------------------
label | 4cff590d-660d-415c-af12-1ef0698ca807 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 63b9be58-03f2-47e5-a89e-f20eb999878d |  | note | ---------------------------------
label | 70267856-aa0b-4ff0-a3c2-f5af5860085b |  | note | VERIFYING DOCUMENTS: This ITP
text | 91c43297-323d-4fc9-9b73-2957c2cca30d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Compressive Strength Test Results
label | b1142923-fbb6-4e49-b0eb-9ac744ec989d |  | note | REFERENCE: IFC Drawings
label | 83e721c1-a8fe-4815-bc74-010e241849f9 |  | note | Relevant Council Drawings
label | 31af4dee-d05d-42fc-bf38-75bfa475daf9 |  | note | 703.11
label | cc9d1f23-60ff-42a1-94e4-371757a66ee1 |  | note | Table 703.111
label | 024332d4-d66c-4285-8ac5-fc46d3741f9f |  | note | Table 610.05.051
label | 97fafeba-a1db-417a-a3c8-0747f8da7172 |  | note | 610.16 (g)
label | 1868640e-166e-41cc-af27-3eadd2d449ac |  | note | ---------------------------------
label | d8fa6c12-61c6-49e6-a455-6cfa26d3813b |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | bc02ac01-bec5-45a0-99ad-f0a83502a3a6 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 198b3bff-2cda-439c-bb02-e5847f82615a |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 53a603a4-c3c4-4cd6-a0ca-efae621345b8 |  | note | Attach: Compressive Strength Test Results
label | 4a73bffd-dbaf-4b1e-a3ad-f4157fd219c3 |  | note | ---------------------------------
label | a87dbfc1-75e8-4a23-99d6-20a7e8c8c4e0 |  | note | METHOD: Document Review
label | fcdc0aec-a022-4db8-bd91-7e110c7ddedb |  | note | ---------------------------------
label | ab0fc7ec-0c93-4bab-a153-523c32ea4ba7 |  | note | FREQUENCY: Each cylinder
label | 9a1d0d78-2705-4fd5-979a-206da1475be3 |  | note | ---------------------------------
label | 84cebe47-e478-43d2-8498-51dfcea74580 |  | note | CATEGORY: IP
label | 8e51541b-8bac-4776-a27f-a6e02e763cad |  | note | ---------------------------------
label | 56b316b0-5c60-4fbe-b967-a8a3e5e45e01 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 52371cd2-5038-4256-a13e-1bf35d6a2ec6 |  | note | ---------------------------------
label | 91211260-26b7-4e64-933d-13511706b334 |  | note | VERIFYING DOCUMENTS: This ITP
text | 61679152-c785-4a2b-9ee6-a2922899834c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 As-built Survey
label | 3d7f9b09-1dce-427e-a008-21cef1e74f00 |  | note | REFERENCE: IFC Drawings
label | ca65457b-f86e-40df-93fd-0d093c2e8871 |  | note | 703.15
label | 8eee844a-f7de-432f-9c85-5e8b7cf7df81 |  | note | ---------------------------------
label | 4ea0a4be-818d-40af-9c18-8d20810d6289 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 3847a4b0-4d41-44ed-88a6-86fbc2f95a2d |  | note | Departure from RL = ±10mm
label | 40400130-82a2-4807-a0a5-6abbdb88704f |  | note | Departure from alignment = ±10mm
label | c009d510-b231-44c8-a2ee-21db88f3cca1 |  | note | Rate of change of deviation from RL or alignment = 10mm in 10m
label | 65269645-168b-4201-b709-f66b7e3e5862 |  | note | Irregularities in alignment = 5mm in 3m
label | 33bde3ea-68a8-48dd-969d-daef4adcf8f1 |  | note | Section dimensions = ±5mm
label | 9ad3f03f-d452-4a30-a9d6-007411659de5 |  | note | Section dimensions (less than 25mm) = ±3mm
label | 0a1f6e23-0941-4d3c-ac0d-7be1b7f7e2c1 |  | note | Width of pavement = -5mm, +15mm
label | 7d9a4fd6-e38b-4164-96df-436551a930d5 |  | note | Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
label | 40fc8883-12e8-4e1f-a8e2-6f92247c9db4 |  | note | Attach: Survey As-builts / Survey Report
label | a7f4a419-46b7-496f-8b26-5019e91ab806 |  | note | ---------------------------------
label | 431231fc-89c1-47f5-8ea2-810c486dbdce |  | note | METHOD: Document Review
label | eecbec80-8049-45eb-833f-d59d29d6f118 |  | note | ---------------------------------
label | 4a42fc1d-cf73-4abc-995b-63bc2c7cda0e |  | note | FREQUENCY: Each lot
label | 5d8facdf-4dab-4942-94d1-216210f2718d |  | note | ---------------------------------
label | e67d1ffa-9f71-40c6-981a-01ccc034abb1 |  | note | CATEGORY: IP
label | 91802094-8a70-4010-9542-d2762e2a287f |  | note | ---------------------------------
label | dcdcf1dd-669b-41bc-8c7f-924246283236 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 6a5fe4d9-04c4-4655-a37e-9804af20f9b4 |  | note | ---------------------------------
label | 88996478-ff34-42b7-9d0a-84aa70e3c823 |  | note | VERIFYING DOCUMENTS: This ITP
text | 046a38a7-f7d5-4e80-89cd-5b8f5160f57b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Non-conformance Report (NCR) Closure
label | 8fa2f7b9-9ef3-48b3-8e6c-d710a2ee1532 |  | note | REFERENCE: MRPA Quality Management Plan
label | 22b78439-87ce-4941-8df2-9a2c25bc2051 |  | note | ---------------------------------
label | 4820b7d8-7b9f-4660-bf06-9d3d49f55012 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | a0f4e3c9-df0c-4e2a-9ed9-f0bdac6c208f |  | note | ---------------------------------
label | b4c13851-eb0e-4851-9774-a737500bb259 |  | note | METHOD: Document Review
label | cbdcfb71-84c6-4d8f-b847-1924e8cfa778 |  | note | ---------------------------------
label | 64c60370-0246-43e6-bbda-da9c29ebce56 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 3fdc1ba7-b0f2-4899-8d1c-1d0e061316bc |  | note | ---------------------------------
label | df864b75-02bb-4545-ad0b-8781b2f80a00 |  | note | CATEGORY: HP*
label | c9da3be0-5a85-45c6-8f26-a09aa38cb0f7 |  | note | ---------------------------------
label | f983c3a5-7c3f-4811-95b3-ae61b2fbbcbf |  | note | RESPONSIBILITY: SE/PE/SPE
label | 5b0aeab4-9c9b-4a9c-8d1a-2c5233064c7e |  | note | ---------------------------------
label | 50a064a7-a496-4588-a764-df9079d3611a |  | note | VERIFYING DOCUMENTS: This ITP
text | 204b8a0b-baba-4f5c-b655-19fb372343b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 38d8cbb9-4d55-4133-b4dc-78d3af7df52c |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 090d32bd-d483-4487-87c0-81822b60d6c4 |  | textbox | Name:
text | 1224bc35-bfe2-40d8-9444-455f56c4787c |  | textbox | Position:
text | d6b32225-8d47-4518-a1fe-0db54cb339f2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Installation of Drainage Blanket Rev 0 | itp |  |  |  | Yes | ITP-CIV-Installation of Drainage Blanket Rev 0 | e7f20fc9-0c92-4235-88c6-e7f4ff2eeb38
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Referenced Documentation
label | 615581cb-dc99-5707-a233-9a72acbd26b4 |  | note | ITP Description: Installation of Drainage Blanket
label | e0465e67-e942-5204-8be8-9329ced66d28 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | e514c7c3-4124-58a2-8186-ebed6770964a |  | note | Revision Number: 0
label | 1f3460f2-3797-53e3-9f49-3fe1748b11b3 |  | note | Revision Date: 15/12/2021
label | f38d9746-43c5-5c1a-b323-fbebe6a480e8 |  | note | ITP created by: Isaac El Zayat
label | 5991b544-b30d-5d5e-ac16-f7e30f275716 |  | note | 1.1 VicRoads Section 702 (May 2019)
label | 1c2d6f02-ac2d-5955-8303-1f2e4b6c462f |  | note | 1.2 VicRoads Section 204 (Dec 2015)
label | b332675b-24dd-5d28-acf5-dc6696add7f2 |  | note | 1.3 IFC Drawings
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Granular fill
label | fae38fcf-8700-58d8-8c80-eb1b39be133f |  | note | REFERENCE: IFC Drawings
label | 9822e1cb-32cf-538f-b537-00b585f3fcdc |  | note | 702.05
label | 998511be-e2fa-54fc-86d7-ce35d2ae74b3 |  | note | ACCEPTANCE CRITERIA: Granular fill material or ballast in accordance with Vic Roads B4 specification or equivalent permeability
text | 04b4a953-cf24-551a-b40f-a9a325645755 |  | textbox | Enter Teambinder Material Approval Number
label | a513b86c-6899-51ca-9cbd-32b195c5986d |  | note | METHOD: Prior to Commencement
label | c2c7e03b-78be-5501-9fcd-27abc44347c4 |  | note | FREQUENCY: 0
label | 70ef34ce-883d-5386-aed8-969176a8fed7 |  | note | CATEGORY: HP
label | de59d978-670f-5742-a23a-4a35bed82a7f |  | note | RESPONSIBILITY: Nominated Authority
label | 2284ba00-4592-5ee3-a93f-368d69a87044 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 3e93e385-a0c5-5cd9-84c5-6dcfb7a757c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Geotextiles
label | 24a1cb69-7ab0-597e-9108-e02b01940ff2 |  | note | REFERENCE: IFC Drawings
label | 86a1ebe4-b07b-5db5-a186-2490e3649c13 |  | note | 702.06
label | 1a4bf943-a5c7-5059-91ff-6e24744722e4 |  | note | ACCEPTANCE CRITERIA: Bidim A34 geotextile
label | 3aea1bd6-94ce-5793-a9fd-49422362be47 |  | note | Enter Teambinder Material Approval Number
label | 05271c1a-7d52-5579-87dd-98e92e9872fc |  | note | METHOD: Prior to Commencement
label | 9a3bd186-e5bd-5cbb-a065-86ea82d51edc |  | note | FREQUENCY: 0
label | 093b7a92-b21f-5fef-8d3f-3a0d9755b700 |  | note | CATEGORY: HP
label | 3a0b1fc7-6a27-5459-9a45-bbb9c75f9e41 |  | note | RESPONSIBILITY: Nominated Authority
label | 5791f278-bd97-5bd9-8755-40e40043b3fa |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 08f47fb6-4569-51c4-85b5-ad83374db816 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Separation sheet
label | 3c12382e-0430-5dd4-902e-81993a63877c |  | note | REFERENCE: IFC Drawings
label | 31d88e52-ad80-5d6e-a160-6cd1f6c42aaf |  | note | MRP-016-C-ACD-DRG-17-NWA-CSW-1794
label | 17936835-b688-53d8-b7b3-3c6a4a37bb2d |  | note | ACCEPTANCE CRITERIA: 300 Micron thickness polyethylene sheet
label | e1b495fa-285c-5eef-bf3b-e9d649e69f83 |  | note | METHOD: Prior to Commencement
label | 3733217a-41fe-5a70-8cdf-a146a32e9fc2 |  | note | FREQUENCY: 0
label | bff28eeb-8369-5a2c-91c2-ada39e8097bb |  | note | CATEGORY: HP
label | abf9cc7b-6108-5b23-84cb-66c94e728e64 |  | note | RESPONSIBILITY: Nominated Authority
label | bf3b01e8-6247-53bf-be6f-8a582cc51c6a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 287b1d1e-38e4-5df3-a036-ce36d3c34fd6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 9d506c6f-a8bb-578e-b902-8a862951c0c9 |  | note | REFERENCE: Section 702.3
label | 191878ce-af10-5be0-be1a-70173c27a895 |  | note | IFC drawings
label | 36ef6455-b7f5-5b49-8b0c-016475e6539f |  | note | ACCEPTANCE CRITERIA: Survey pegs in place and clearly marks out the limits of the Works.
label | 43b4f66d-bc50-5a4d-ae63-a39aea637b61 |  | note | METHOD: Measure, Visual
label | d4ee8718-c7d4-56fe-8829-90bf5f8fb37b |  | note | FREQUENCY: Each element
label | d480f1f1-4acb-5c03-9dfb-8b2e41a1cc18 |  | note | CATEGORY: IP
label | d23a79c0-9404-54c2-8bbe-759673591f2c |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f1c731fb-afbe-571a-9588-54e10bf89572 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ce3104cc-afe2-5e81-a21a-b6511a489d99 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Cut Floor Level
label | 733354b8-8ad8-58c8-81c2-c1bae4bb0e3f |  | note | REFERENCE: 204.03
label | 06b3f0b7-2d67-530c-82eb-3f797985dc7f |  | note | ACCEPTANCE CRITERIA: Earthworks shall be finished to conform to the levels, lines, grades and cross sections specified or shown on the relevant drawings within the following limits:
label | 105eb5db-92ed-5ae4-b942-ab16fac023f1 |  | note | Mean value range: +15mm to -30mm
label | 386b7797-b71d-54bc-9d35-91777007d34f |  | note | METHOD: Measure
label | 1349bdf6-2253-5678-80c7-7918b7d9d3ca |  | note | FREQUENCY: Each lot
label | 18b0450b-c9df-5467-b4aa-5d6979f9dbf3 |  | note | CATEGORY: IP
label | d22e5c92-21fb-53b4-b866-80706ef8acaa |  | note | RESPONSIBILITY: Surveyor/SE/Site Supervisor
label | 854aaabb-2afb-545c-82f0-c40de3fcfa62 |  | note | VERIFYING DOCUMENTS: Sign ITP, Survey Pick Up Report
text | 0ba5eaa2-ea23-518f-97e3-daff4a5f4294 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Cut Floor Inspection
label | 4ae6f3cd-4db7-5a64-ba05-64ae12e78193 |  | note | REFERENCE: IFC Drawings
label | 22343918-7eda-5125-a3da-0b4c4bb1bd7a |  | note | ACCEPTANCE CRITERIA: Formation level of foundations shall be approved by the design geotechnical engineer before placement of blinding concrete or reinforcement commences.
label | 8f55eb2d-44c2-54c3-9fd3-531ca4cb076f |  | note | Required bearing capacities are to be confirmed on site by the design geotechnical engineer prior to the placement of any concrete for foundations.
label | 5e88c42f-a6a5-5c41-8ece-7a4c7b1553f5 |  | note | METHOD: Measure
label | 12cb91ff-2997-5bb1-b880-2adcd4e08285 |  | note | FREQUENCY: Each lot
label | f1507798-ec68-5913-9057-f8cee4a8631c |  | note | CATEGORY: IP
label | e5e23360-4eaa-5353-913b-0650b0ff5373 |  | note | RESPONSIBILITY: SE/Design Geotechnical Engineer
label | b02d9652-6f85-5628-99ed-8dc61220717d |  | note | VERIFYING DOCUMENTS: Signed ITP , Record Bearing Capacity
text | 31c24344-f9ca-55c4-b84d-ed39962fdacd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Test Rolling
label | 2c8c4e51-cbf8-5cdd-8a4a-533140483d77 |  | note | REFERENCE: Section 173.03
label | fb4f4bcf-5c41-5815-81f2-bfa8950ad052 |  | note | Section 204.12
label | 702863b5-d989-5b8e-998f-d34d991d2d4e |  | note | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173.
label | 02faa447-7b38-538e-a69c-d4b269b87b1e |  | note | METHOD: Visual
label | d1821217-8c19-5d32-9667-eaed26a8457a |  | note | FREQUENCY: Each layer
label | ecb99dea-b7b7-5dfe-a646-fe714c536fb2 |  | note | CATEGORY: HP
label | 0cd9a48f-fbf2-5c05-b491-5e4458eebec1 |  | note | RESPONSIBILITY: SE/Nominated Authority
label | e5f52fa7-4a02-5ccb-90f3-6a36bf6faa11 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 7c9a6853-8d04-5dfd-8694-e25d4aaa2c5f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Placement of geofabric
label | 9500a3e8-2fc2-522f-be9c-334efd3c1cd5 |  | note | REFERENCE: IFC Drawings
label | 1c7d49e2-35d9-5442-a02a-b1dcc3209236 |  | note | 702.09 (f)
label | b6629e87-9970-5fd8-88c6-e8d7d7f2b342 |  | note | ACCEPTANCE CRITERIA: A34 Bidim to be placed along base, wrapping around drainage blanket and tied in to precast wall strip drains. Refer to IFC drawings for detail.
label | 12697069-6de8-53bb-8af8-50c1a41f8a7b |  | note | The minimum width of geotextile used for wrapping shall be 450 mm
label | aae05d9c-4bca-5941-93ed-bd2a17701b81 |  | note | METHOD: Visual
label | 69aea5f2-fa74-5200-a13e-12811e03bc39 |  | note | FREQUENCY: Each layer
label | 1b9290c0-184a-51e5-bb13-0b730a0fcd08 |  | note | CATEGORY: IP
label | 355a1038-9481-5184-b414-c64524b365c5 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f52067b6-5cd5-56c5-97ac-6e7b354d1ce6 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 026d7205-b2a8-5317-bd22-5cc272e40cd1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Placement of granular filter
label | 15961422-f117-5f20-acbb-b18c2d75cd0c |  | note | REFERENCE: IFC Drawings
label | 513539c5-243d-596e-9819-2f090dbc4f56 |  | note | ACCEPTANCE CRITERIA: Spread and level off the layer of Granular Filter Material = Minimum 300mm thickness to underside of blinding.
label | 8d81f9ed-2ad9-5a6b-a1e6-c33e84326147 |  | note | METHOD: Visual
label | 993804ae-c95d-56e5-8f3e-a18ffcc1de9e |  | note | FREQUENCY: Each layer
label | 9f82e182-af0d-5c6b-983a-2b77df98d259 |  | note | CATEGORY: IP
label | 93241d07-103c-593a-b449-fa0431adfc2e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ebc36d0a-11b0-5c92-9000-261e17e9df68 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | d938fb12-8915-5262-9ead-b99cb0fe8e27 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Preparation of final surface
label | f0bc5235-a7d6-502f-a603-feecce4a48b0 |  | note | REFERENCE: IFC Drawings
label | c6427688-adbe-5131-990f-c347ce2cd985 |  | note | ACCEPTANCE CRITERIA: The top of the drainage blanket shall be finished to allow 75mm thick blinding layer
label | 5277448f-e743-51a7-baa5-a6a419b1e4a8 |  | note | METHOD: Visual
label | de45fdfa-d6d3-5994-9e2e-b6d37d1c598f |  | note | FREQUENCY: Top layer
label | 21c837c2-b0c6-5bbb-9f78-4c30d437d974 |  | note | CATEGORY: IP
label | bdc83646-54f1-5164-a558-703feb4f2646 |  | note | RESPONSIBILITY: Surveyor/SE/Site Supervisor
label | 4877d8c0-07e4-5b0b-8a84-51b5478075c2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | dc77f680-8a46-5cf3-8c9c-a39b25f20947 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Placement of separation sheet
label | 0b237835-483e-5cdb-bdd0-ebb523ebcc39 |  | note | REFERENCE: IFC Drawings
label | 3276c255-b968-5128-8392-8326dd29cb98 |  | note | ACCEPTANCE CRITERIA: 300 Micron thickness polyethylene sheet placed between blinding and granular fill layer
label | 4aac7a39-bd28-547e-8ed8-6ce2eecaa75f |  | note | METHOD: 0
label | f4d6053e-3c58-5e07-a873-a1b6330e8772 |  | note | FREQUENCY: 0
label | 8bee760e-00ac-5490-bcb4-d1bb4a94a5e5 |  | note | CATEGORY: 0
label | 81daff92-2fd4-5016-acfa-1cae4d950133 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7a61ff22-2173-5e3f-8bfc-087038240e82 |  | note | VERIFYING DOCUMENTS: 0
text | e7082419-964a-5f97-a51d-c1319f777296 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 5.1 As-built Survey
label | f32d21aa-1bf4-5206-a7b2-c0781ce4fb5a |  | note | REFERENCE: IFC Drawings
label | 91d78e1c-eea1-5523-be82-30127413529f |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | 585db596-3e17-5f52-9569-7a334d204c5c |  | note | Attach: Survey As-builts / Survey Report
label | 788dfc86-a0ac-5d15-bed1-82246b07ee19 |  | note | METHOD: Document Review
label | 0b268423-0c8c-5d49-bce6-ff2e53528af8 |  | note | FREQUENCY: Each element
label | 95e337c4-9100-5b51-b023-1cd7f54fd5f5 |  | note | CATEGORY: IP
label | f7ab71f3-c3d9-5718-8922-ca6ff02027c0 |  | note | RESPONSIBILITY: Surveyor SE/PE/SPE
label | 6883f1f2-d3ed-5ab4-89ee-db94dd57d483 |  | note | VERIFYING DOCUMENTS: This ITP
text | c21fc8dc-2d41-5b52-ba23-d4c4f85f402a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | 57b50317-5c6a-5187-a5e9-7e98053f1b6d |  | note | REFERENCE: MRPA Quality Management Plan
label | af629fde-eaf2-5233-8eb4-e0a826edc4ee |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | fa975b7f-d25d-5b60-a01e-c941120415e2 |  | note | METHOD: Document Review
label | e5ba29b2-8efe-5bfa-964d-38cb3679ffb1 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | c3810a26-b705-58b9-8009-7e014bcfcbb8 |  | note | CATEGORY: HP*
label | c7ff607c-8fe1-54aa-9277-1dd185924e28 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0de2b24f-0da2-51aa-8cd7-9eec67388367 |  | note | VERIFYING DOCUMENTS: This ITP
text | 830d23c6-4ad4-5891-bd1d-bec2cd813b28 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 4d08c9c5-67b1-5e7d-aa6f-0243c7056702 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5c3b7031-89f0-5bd4-9ee1-d0e89f0bda57 |  | textbox | Name:
text | a08e416e-85c4-56d9-8730-9cd1d303efbc |  | textbox | Position:
text | f744e6a4-7cc1-5b75-aa2f-6c3281d9bf98 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Bored Piling Rev 5 | itp |  |  |  | Yes | ITP-STR-Bored Piling Rev 5 | e987df5b-a85f-4697-8d4a-598805263e82
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 4ce27a64-6072-4635-9beb-2667e04f06fa |  | note | Document Title: ITP-STR-Bored Piling
label | bcad1d37-a71f-4cec-9adb-40efb5180451 |  | note | ITP Description: Bored Piling
label | 59cac514-c645-4f30-99a1-8e05c3a7b9e8 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 397e2448-56c7-48bb-bb75-ec25c0a7b0c0 |  | note | Revision Number: 5
label | 642e2366-7285-4151-854f-4b8255b244ea |  | note | Revision Date: 12/05/2021
label | c2bb026f-15c0-455a-b602-fa783d59745a |  | note | ITP created by: Mike Freeman
label | 68187e2f-c04a-4148-846e-582b97873920 |  | note | 1.1 VicRoads Section 606 July 2017
label | 59d1c62e-cde3-47d5-84e9-80a09ca90a24 |  | note | 1.2 VicRoads Section 610 June 2019
label | 409ecd45-d7d6-4856-81ef-7f55ab6ba6a8 |  | note | 1.3 VicRoads Section 611 November 2018
label | 321f7abc-10fb-4210-85ab-eec4b58112ec |  | note | 1.4 AS2159-2009
label | be1d894a-ed94-43ac-93fd-a214fc00f166 |  | note | 1.5 AS3810.1 2018
label | b58506dc-164b-4e15-970a-357d843eba87 |  | note | 1.6 AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 3586338a-7fc4-4f83-8b7b-45b11d29c376 |  | note | REFERENCE: 610.07
label | 78e5449e-b90f-4736-ac47-6d5cdc17c7c4 |  | note | Table 610.071
label | c29d366e-55cc-4b5a-a9e2-8d8471965461 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | b55f202f-99c5-4dcd-8d83-fb3454307197 |  | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 9142bd13-2714-40cb-a5e5-f73272f9b913 |  | textbox | Enter: Teambinder Material Approval number
label | 939fa100-4c63-4996-9f0b-92bfbcff6276 |  | note | METHOD: Document Review
label | 630464ba-fcec-4d50-845b-37a65dd3fe8a |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | b284cb9e-e026-47b0-9401-6002b2205975 |  | note | CATEGORY: HP
label | 445634e9-85eb-4d12-8c6f-d1c9b211d85b |  | note | RESPONSIBILITY: Nominated Authority
label | abe0279c-cf5e-45e5-9a90-e65c61b5c986 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9dfee121-81a3-4ed9-ba7e-219ec1c04d15 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 46df5941-f9eb-4c77-adaa-414262c0a71e |  | note | REFERENCE: 611.05 (a)
label | f2d62a80-e3d7-46f3-9727-a57d6961ebbd |  | note | Table 610.071
label | 51094f65-820c-4fcf-9fbd-b2e848dc8604 |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | bfd4c56b-e876-4f0d-8f63-05a26506854e |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | f2917206-a4f1-4525-af90-853c2027aefe |  | textbox | Enter: Teambinder Material Approval number
label | eef530c0-f16d-4551-a0a1-babcec465e52 |  | note | METHOD: Document Review
label | dd7a2abd-8b1e-4ef7-9a7e-0add6ba192a5 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 1d16cbb4-034b-48f9-a020-d82f3498373a |  | note | CATEGORY: WP
label | 37d56fae-7f1e-4185-af45-b562577351d3 |  | note | RESPONSIBILITY: Nominated Authority
label | b3462f5e-7c41-47b7-b512-ddbcc51e9dd7 |  | note | VERIFYING DOCUMENTS: This ITP
text | f54d2639-af17-4108-8b6a-2b3129c3cc0f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 2ad69838-33f3-4615-b0b5-0327fc6ecc42 |  | note | REFERENCE: 610.26 (a)
label | 0bf669a7-fc17-4593-ab92-d32e247bf2e9 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | 873830b0-a929-4c23-9999-521999f8b5f1 |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 84c18b4c-3c6d-4aeb-ac99-5f831db3c34e |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | fee9439c-a624-409e-bed0-a29506b35878 |  | textbox | Enter: Teambinder Material Approval number
label | f10c0aeb-5b67-401d-bb7e-f7f816b0b4e2 |  | note | METHOD: Document Review
label | 29a31b61-963c-41c0-8d7d-09524cff68ae |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | eb6ba838-946d-40fc-a76b-734a3d7459f9 |  | note | CATEGORY: WP
label | 023bd231-f9ce-4ffc-8538-7346b72e13bf |  | note | RESPONSIBILITY: Nominated Authority
label | 544dde91-e1a3-4a02-899a-94b174cd4ed4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4c866a36-88de-4b64-86ad-0b11cca9a139 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Piling Operations Work Procedure
label | 57714457-3083-4c43-9db8-5ff311f2fa38 |  | note | REFERENCE: 606.03 (a)
label | 24b85304-51b7-4327-a7ea-b369a9669734 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 6dff5fd1-e7b7-4f9f-8d3b-84330d347b7f |  | textbox | Enter: Teambinder Approval number
label | be2f43cd-f68e-48bf-a11b-f03dcdf166bd |  | note | METHOD: Document Review
label | 96921752-0a1b-4d77-acbf-a92818e0a599 |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | fbc7a8f8-3cdc-404c-ac00-6875e7e6c079 |  | note | CATEGORY: HP
label | a71126eb-6fae-416f-8fee-ccf3b8a4d5db |  | note | RESPONSIBILITY: Nominated Authority
label | ac227da2-b5e2-48a0-9eeb-d4ff2e455645 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 14982e56-b79a-4406-88e5-07f867b3af4e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Temporary Steel Casings
label | 890e20aa-b4bd-47c8-ba83-678dc700e41c |  | note | REFERENCE: 606.03 (b)
label | f249c9bd-8d16-44a9-ae9c-c63bfe2e66cb |  | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | 7d853f5b-9cab-40b3-a7fd-4188c182333e |  | note | Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 63625a48-2a3c-41d6-8e04-9113bccc9615 |  | note | The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | cea87cdd-3118-417c-919d-8c3fa206cc73 |  | textbox | Enter: Teambinder Approval number
label | 1e306228-9a39-4f28-a6c2-8a6438751c32 |  | note | METHOD: Document Review
label | 07fcb19b-9ca8-408c-a188-b2fa6372ed00 |  | note | FREQUENCY: Where applicable, once, prior to use
label | bc5772db-6a53-470a-80f3-d3b0fc46b0e8 |  | note | CATEGORY: WP
label | 04edda40-fb73-46ab-8c1a-32bf4fbd9333 |  | note | RESPONSIBILITY: Nominated Authority
label | 122a6a53-13ce-4e7a-aa48-a5a1b338ce4d |  | note | VERIFYING DOCUMENTS: This ITP
text | c1e8de60-20c9-4776-977e-04a040108bd5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Casting Under Water Procedure
label | 4ea04ae9-cb4a-4907-ad1d-8f8af98fb5cd |  | note | REFERENCE: 606.06 (a)
label | 5f43017f-b401-437c-a000-5907b4b7c03e |  | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | d16f2622-87b2-4ead-924b-d178c7c0acc5 |  | textbox | Enter: Teambinder Approval number
label | 4790ffbb-5c64-45ac-8f15-aa659a4c50e3 |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 3b3ce3b9-fef3-43f3-88a9-f00011e03477 |  | note | METHOD: Document Review
label | 35fcf868-14a3-4088-b8fd-f57c0a774399 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | cd1cc6c1-e319-4093-b698-9185b2811d8f |  | note | CATEGORY: WP
label | 710bd197-d82f-48ba-838c-d9876ef0b5e3 |  | note | RESPONSIBILITY: Nominated Authority
label | 206375bb-9da9-4eab-b316-769cc77e061f |  | note | VERIFYING DOCUMENTS: This ITP
text | 3078a295-5230-4aab-b0b2-33642f10ae8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Boring With Bentonite or Polymer Fluids
label | 6f7a3030-25ed-48a9-ab81-9817da14663e |  | note | REFERENCE: 606.06 (c)
label | b8cb22c7-e4ef-48f6-a32c-b2add8820515 |  | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 32502ad2-409e-4eff-b576-7f684936ec0d |  | textbox | Enter: Teambinder Approval number
label | 1c089cac-15df-4eac-8fe2-74851b7aed0a |  | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 06f3aa9a-8daf-4331-92ee-41d32edab5e8 |  | note | METHOD: Document Review
label | 85da2c07-e0ce-437e-af14-54c8f891d240 |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | 64359c33-ace1-4077-8398-a136256c6ce1 |  | note | CATEGORY: WP
label | 8a47f66e-ea24-4dda-9283-c6902f9ba85d |  | note | RESPONSIBILITY: Nominated Authority
label | ddeedfaf-0d18-46cf-a51d-0c1c60abd2c8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1383ce2b-a3df-4b31-a9d9-423e36d07373 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Dynamic Pile Testing Procedure
label | 6fec49f2-f53c-4d1b-9ae1-a4f28b6933e1 |  | note | REFERENCE: 606.07 (c)
label | e5abe783-b111-4b32-ae83-47f9369c377a |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | 4925717c-779a-4459-b537-d18216008a76 |  | textbox | Enter: Teambinder Approval number
label | e4670812-5fc9-47fa-8965-2703ef0c2119 |  | note | METHOD: Document Review
label | f8f65fb7-1d40-47f5-a276-90adea551595 |  | note | FREQUENCY: Once, prior to testing
label | b41bf695-e214-483c-b6e9-30e20083496f |  | note | CATEGORY: WP
label | 356cd7da-d0a3-4206-9b4e-f60a1cf48196 |  | note | RESPONSIBILITY: Nominated Authority
label | bf4af1e6-9ca9-45a6-8063-d176e579b884 |  | note | VERIFYING DOCUMENTS: This ITP
text | 00e80e6a-3f3a-402c-b173-fe4ca9759e40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Pre-qualified Pile Testing Consultant
label | a1c81245-e826-4ec5-810b-2398ffb596b3 |  | note | REFERENCE: 606.07
label | dbd7d7f5-38ab-4c2c-8903-db050ec63ea3 |  | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a pre-qualified consultant who is independent of the piling contractor.
label | 5d81bf53-461d-477d-b877-1e64bc42a4f9 |  | note | Details of the consultant to be submitted for review to the Nominated Authority.
text | 35293069-1b81-4270-b22b-779c85b86229 |  | textbox | Enter: Teambinder Approval number
label | 1bbd8a28-1cd9-4ee8-89ee-5ece5e2ea654 |  | note | METHOD: Document Review
label | e55498d4-24f0-4a2e-a947-44362fad9b7a |  | note | FREQUENCY: Once, prior to testing
label | 2d45fff7-8f7d-43eb-a58d-9e37ef9ae9bd |  | note | CATEGORY: HP
label | c2972f6a-033b-4910-9c24-d8de088ba84a |  | note | RESPONSIBILITY: Nominated Authority
label | 5d3280d3-4904-494c-9da0-7d4ba22f4c1b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | a843d675-cc52-456a-9ef9-eccab21e8f21 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
label | 13f94e35-7438-40da-9e46-fa4cc2197b31 |  | note | REFERENCE: 611.13 (a)
label | 827092fc-bb29-4b51-9f38-d64f0f7fa4d9 |  | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
label | 042039ad-c34e-4a5f-8b75-cc62c613e5f5 |  | note | 611.14 (b)
label | c0f7944c-7bb2-483c-8e5a-38f0f96bb761 |  | note | ACCEPTANCE CRITERIA: Welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | f64b4587-fd89-422c-b46c-0b7c076406a6 |  | textbox | Enter: Teambinder Approval number
label | 7a83c3aa-80dd-4a3b-beee-d668111c2093 |  | note | Note: Tack welding requires the same documentation but is a Witness Point
label | 3e054c06-5f0a-4d37-9478-e71199053b4a |  | note | METHOD: Document Review
label | 68cf42f0-b1e3-4ab6-862c-6c399d3c09c1 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 7b60b193-50ac-426b-8828-558ec43b5fd0 |  | note | CATEGORY: HP
label | ee53201e-a8f0-40b5-9ff5-3f5be638d148 |  | note | RESPONSIBILITY: Nominated Authority
label | f965c57e-0ccd-47d6-9c2f-b80e8c6a8eca |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ffecc083-44b7-4653-8000-eb5f2d6adcd7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 3e70abb4-a470-4a5b-a1cb-e574dde79cb7 |  | note | REFERENCE: MRPA Quality Management Plan
label | b4caba83-36ef-49c1-aa7d-c42641b47262 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 29d8b3c4-e7bc-49ef-8ab7-8ce42b75c3f7 |  | note | METHOD: Document Review
label | 7c0456e7-12b2-4dc6-849e-ed7deaf25e0f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | c0035182-1d43-4d8d-972d-892ebad349f0 |  | note | CATEGORY: HP*
label | 1ec4888b-70d8-436b-9cc2-0e0fc442a025 |  | note | RESPONSIBILITY: All
label | d17a1cde-7e80-4e42-8d19-dc490219642b |  | note | VERIFYING DOCUMENTS: This ITP
text | 8871ed34-c621-4421-aec8-26dd72453987 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | 28ac12d5-23fa-4658-8030-67db454d2ee1 |  | note | REFERENCE: IFC Drawings
label | 844bba13-8c8d-4b10-ac2c-680870783156 |  | note | 606.08 (a - c)
label | 43029986-25fa-4286-b098-8c746262cc2c |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | d60cafc8-5a83-4b7c-8c9f-1e381555b193 |  | note | METHOD: Measure , Visual
label | a4c0e3fc-2dec-46a2-9a04-e6fb18b3a9fe |  | note | FREQUENCY: Each pile
label | 09d8c1ab-07d3-4565-b61f-a461e3f74c0e |  | note | CATEGORY: IP
label | f8eb96ab-57d1-433f-84f5-f26d2c22eb4d |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 843106f9-24bc-4810-9a47-937d5c53241b |  | note | VERIFYING DOCUMENTS: This ITP
text | a48976e0-81a0-4284-b8ea-b9bf0e1f645d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | cb58e212-850d-43bf-9391-1041d4cc1ea2 |  | note | REFERENCE: 606.04
label | aeb7c34b-f3bf-438d-b6cd-9916c1e56de5 |  | note | ACCEPTANCE CRITERIA: Pile construction shall not:
label | 62522a97-d1f3-4b16-8bd4-420c6bc623a2 |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | b8fabc60-6c61-4757-887c-2146280aafb2 |  | note | ii. commence within 2.5m from newly cast piles if that pile concrete strength <15MPa
label | 5ba557d7-15ff-456f-99b3-092a5999d94c |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 15eedd64-a3c9-4d53-8093-7aa2c948f2ce |  | note | METHOD: Measure , Visual
label | e70880a8-64e3-410d-8624-67965fd07d70 |  | note | FREQUENCY: Each pile
label | f378614f-1112-4c19-b934-f0d65bba895c |  | note | CATEGORY: IP
label | d5c84765-6b91-492b-a15d-0e0f9bb23240 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 3395ae19-a87d-4f48-9850-ed1e32c27f70 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4cdc1f57-3f3a-442b-91c3-ff1e7257eaa9 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | f54b29a0-5e33-486f-9ef2-4fa2b5119f24 |  | note | REFERENCE: IFC Drawings
label | f7f3ab74-3c28-4d03-8d79-6e904b815dd8 |  | note | 606.03 (a)
label | 68edcdf5-e643-4fdf-8445-7a856be63f17 |  | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | cdae7343-a00b-4b50-bb5c-5fff4a9a683a |  | note | Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 50ae8e73-e275-4a1d-8a68-ea1b48ea00ad |  | note | Excavation clean and de-watered (where applicable) for inspection.
label | c5b60b2c-98a7-4ace-b4c6-7537f1a1d3f6 |  | note | Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 3fd4073e-0d22-41e8-a46a-89a98c5dd3b2 |  | note | Excavated material to be disposed of as appropriate to maintain a clean site.
label | 03824e49-0575-4475-8753-f596911fa337 |  | note | METHOD: Measure , Visual
label | c9bf1ff2-7f63-4769-b796-372a413e968f |  | note | FREQUENCY: Each pile
label | 29d448e5-aedf-45f0-9f5d-5acbbf336519 |  | note | CATEGORY: IP
label | 077343ed-32f9-4194-8792-9bf987668c43 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | fb40bbc0-d6b3-4372-888d-4b20af637c71 |  | note | VERIFYING DOCUMENTS: This ITP
text | fa04eb4e-30cc-406d-b5d2-3819d56d5143 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | 171147d3-9f4c-43ae-8cbe-99f0cb672a50 |  | note | REFERENCE: IFC Drawings
label | 6b4e7729-cc90-4688-a8ab-b8e983b3d3a5 |  | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | ec52fb94-4d55-4df0-984f-5960c42af3c5 |  | note | METHOD: Measure , Visual
label | bb956dbd-65ff-4f73-9ed1-22c19a9ad157 |  | note | FREQUENCY: Where applicable, each pile
label | f8408021-ac6b-428d-97a0-d02d80940c16 |  | note | CATEGORY: IP
label | 252d6702-a361-49ce-8bac-5548c27a8a30 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | adee2ae4-137c-4879-99f7-30393b19e99e |  | note | VERIFYING DOCUMENTS: This ITP
text | 04a50c30-f476-40af-a4f3-4d99e60c90ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | 625fae7a-4999-4033-a9c0-0a894867e0a1 |  | note | REFERENCE: 606.05
label | 4bbd0267-8ed2-466b-b913-2adf9759e0db |  | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | ad0f9a92-74c4-4e94-b5c4-ab00177d2ed3 |  | note | Attach: Geotechnical Field Sheet or Report
label | 903ea199-1f42-41f5-86ea-c83770778220 |  | note | METHOD: Measure , Visual
label | 5aa4a731-74c4-40fe-ba7c-03666bbc80e2 |  | note | FREQUENCY: Each pile
label | c1a9f0d9-a4a5-4286-9120-5fb5e19a9342 |  | note | CATEGORY: HP
label | 4d396aaa-7bbb-4653-9187-535b614ba6d7 |  | note | RESPONSIBILITY: Geotechnical Engineer or Nominated Authority
label | 67182c9b-1f59-4989-b026-3bce014d5228 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 86b2604c-63dd-4e3a-888e-5df0fdce5057 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement - Placement
label | ea1dc11e-5633-4b9f-859d-99266519374b |  | note | REFERENCE: IFC Drawings
label | d4b3ef9e-a16e-43aa-a3c9-daebbe615081 |  | note | 611.06
label | 81a72bb0-bfed-457c-b400-56fbb013ddee |  | note | 611.09
label | 6587dcde-db22-42a1-8395-9421a2b8f088 |  | note | 611.1
label | ae9e24cc-7100-454c-b454-4f1c0b7b5a9f |  | note | 611.11
label | b71cfbfd-7782-41e5-8a77-3aa87e6aa7b5 |  | note | 611.12
label | eb03a509-dd2c-43ec-a393-a39cb9cee28e |  | note | 606.06 (a)
label | ec502a6a-c88f-4041-9530-e22180692805 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 90b2e3bb-217f-4fd0-aff5-66b3adcc49f4 |  | note | Projecting reinforcement is the correct length and location.
label | fa3b141d-2fde-4fb5-8a22-e654d8c888e2 |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | c2acb6bc-9b88-475e-8938-a254681c9c9f |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 75cbd0b0-259b-4e5c-a588-0dd68c05fa7d |  | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 2010cd7d-9b75-4ec5-85e5-dbd5fe00acf9 |  | note | Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 6d2adfc3-7c3b-42d3-b361-babecd13e8c0 |  | note | METHOD: Measure , Visual
label | 507214f0-10f5-44a3-8461-89c7774c4b55 |  | note | FREQUENCY: Each pile
label | ba643e76-36d5-48f0-8ca8-8d684607bcdd |  | note | CATEGORY: IP
label | 881d3484-55cd-480d-a16c-a4e12dcde1b2 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | ee1aabc5-478b-4a2a-b867-bb1326119f1c |  | note | VERIFYING DOCUMENTS: This ITP
text | 8a7d89f4-fb91-49e8-85d4-0eb65ff04fe3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | 703c5fa5-4260-4a4e-b19e-4ac16b08550d |  | note | REFERENCE: IFC Drawings
label | 9f2b5798-11f1-498f-98d3-128fc4111a17 |  | note | 610.29 (d)
label | d65c6239-2b5e-468a-b4f4-202bb24756b4 |  | note | 610.43
label | ebf3122a-5a5d-411e-bd12-3d07b09cd079 |  | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
label | 549d66b4-909a-43b9-9cf2-3e82e5d32cad |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 5e5900a8-883d-4eff-b18b-2adef6a6ea75 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | c4412293-408d-4170-bba8-ecd5bd4561bb |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 0291900e-2fd9-4b18-9a2d-d39599519873 |  | note | Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 60d2df14-dd19-4b83-9b16-113532455243 |  | note | Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | e36d5337-af52-4b46-b48e-e49eedb4dc2c |  | note | METHOD: Measure , Visual
label | 47d46334-5cae-4a3c-9266-e01ffa3df43e |  | note | FREQUENCY: Where applicable, each pile
label | 88c138ff-960e-4b1d-a059-85bba1a3277f |  | note | CATEGORY: IP
label | cdea8469-0c2a-43b0-b60b-ecb298c7d22b |  | note | RESPONSIBILITY: Earthing Engineer , SE/PE/SPE
label | e0200b28-7d36-4249-bc1f-c5ef2dde5d99 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8353142d-216c-404d-855f-d53e858ba3f5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | 8bdec2f9-4702-4446-bfde-030d4f65a3bb |  | note | REFERENCE: IFC Drawings
label | a720829f-5cf7-4025-90e0-2e97f7ebcb43 |  | note | 610.46 (a),
label | e02f6703-eca4-4058-b9ef-d510527f049d |  | note | Table 610.462
label | 26481499-7e05-447b-b521-b83caea14eba |  | note | (November 2018)
label | 1a9258de-9c21-41d8-9f96-e528f0a24383 |  | note | 610.47 (a)
label | c0125be7-8acc-4de3-a563-a3ecb1242c8f |  | note | Table 610.472
label | 0fffadfe-7d38-45c4-93bd-50c1a043055d |  | note | (March/June 2019)
label | 5f69c605-151f-4176-8865-a3d66c47ce8d |  | note | AS3810.1 Table 3.3.6.2
label | b87ee896-3f2e-41f7-9051-9033ec1c589c |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | 758bf293-eb97-4da8-af9e-ac4af16a9822 |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | addadc43-b113-442e-91db-4c3d8b3df9d4 |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 8b56f3e1-4acc-45c1-8632-2e88c24a3fc1 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 7533d66c-9527-4cc6-b386-07d44c9adfe3 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 3ba6fe61-e08f-453b-89ce-44d6a669e259 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 09365aeb-6469-465f-9b82-167dc5699dbd |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 402b8700-3b63-4db9-8a71-31e7c7ef615f |  | note | iii. Ducts and conduit location = ±12mm
label | 370e38ea-add0-47f1-8fa9-3c242cc8832e |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 837b07bd-1741-4bbf-9136-47f877e733dd |  | note | METHOD: Measure , Visual
label | ed78e3d3-30df-4ddb-8014-e5b5fd30d6df |  | note | FREQUENCY: Where applicable, each pile
label | d25a62cb-9f40-4d78-9dbf-133eb61de6e7 |  | note | CATEGORY: IP
label | 86074b5c-9ea7-4b71-b4bc-a25073df87ee |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | fcc69ba3-38d5-4b49-840b-ca9cbc6bd0d7 |  | note | VERIFYING DOCUMENTS: This ITP
text | fcff4233-ccbd-4411-ab26-f00714021991 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | 5eb30069-b8dc-450a-9dc0-a48540805d2b |  | note | REFERENCE: IFC Drawings
label | 73e514b9-1178-4d93-9741-680362d7d4a4 |  | note | 610.18 (a) (ii) & (iii)
label | 09cb9eda-6235-486f-8336-8dc021a4668a |  | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | 9a284f10-ec4d-4110-9cba-5774b64372a0 |  | note | All foreign material has been completely removed from the excavation.
label | b8a97a11-078c-417e-9e0a-955b421eb57c |  | note | METHOD: Measure , Visual
label | c4f8e8a3-3b1c-4701-8349-894b6031d800 |  | note | FREQUENCY: Each pile
label | 85cb4717-2fc3-415d-975b-505b3289cf05 |  | note | CATEGORY: HP
label | f1a41fda-7acd-4a89-8ebf-4b033325530b |  | note | RESPONSIBILITY: Nominated Authority
label | a0530d26-0d09-45ec-9fe0-1dae5e2e3fce |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | dd4065df-37e5-4278-8624-d568f2c16bee |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | 13dfc8bc-5189-45d7-8971-38be416b3926 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
label | 74951cf5-4a18-46c9-a670-c545a338c4e9 |  | note | 610.17
label | 5481b9d4-9bdc-415d-9f40-dd205db3601f |  | note | 610.17 (a) & (e)
label | 4a274ef0-d25a-420a-9f5c-36fb09b0622e |  | note | Table 610.171
label | f90a9826-5ef2-4ea1-8ff9-bb493f732e97 |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 089749f3-7b37-4d4c-9116-ffa664a2d09d |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | e55fee87-0dbd-4e98-ac28-cd8bf854f614 |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 258d74b1-02a0-4c57-b17a-f3175dfc0b37 |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 155b3666-c4c9-4625-86d3-3c0097099828 |  | note | Record: Required information on the Concrete Pour Record.
label | 793cad2a-ee54-41ad-b17b-d8bccd28b932 |  | note | METHOD: Measure , Visual
label | bff73a7c-50d4-43dd-9e0a-f759e8e37415 |  | note | FREQUENCY: Each pile
label | 2e7c7290-6cfb-416e-9399-30e9a3c5741e |  | note | CATEGORY: IP
label | 0b6baf18-d859-477d-9eda-2200478e772d |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 04fd6793-f652-4ce8-aa95-c01d1bffed69 |  | note | VERIFYING DOCUMENTS: This ITP
text | d853b390-c6c4-4f1e-9647-9bf3616808ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | dea5ac38-3765-44d5-8412-b34c249cd08e |  | note | REFERENCE: Site Sampling & Testing Procedure
label | f38f2003-9154-425d-9fd6-f01aca3c5c98 |  | note | 610.16 (b)
label | bd4db532-fb5d-461f-be1b-aac72f407002 |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 6807f8e1-13d0-4c18-8b66-a0cd1751d471 |  | note | 0m³ to 10m³ = 1 sample
label | 57a935a7-80d3-4f5e-b529-cd3ee819836f |  | note | 10m³ to 25m³ = 2 samples
label | 95faef3b-a96c-4eb2-b936-4c9e79c0b927 |  | note | 25m³ to 50m³ = 3 samples
label | bfd79e90-70ae-4ee3-a437-f13d4eedba1f |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 58657bbf-b547-4a02-a2bb-1715640ec6e2 |  | note | For each additional 50m³ and additional sample shall be taken.
label | ee8bb965-8096-48d4-ae91-28b20463984d |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 49c5e0f0-b49a-42e5-868d-4ce9644853ab |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | cf9f0678-21e0-4176-8a02-d8dd9922194a |  | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | ae077ddb-de49-4604-aa8f-25d30db10497 |  | note | Record: Required information on the Concrete Pour Record.
label | fc31f4c1-9efb-46b5-86a8-94c662d1795e |  | note | METHOD: Test
label | e9d1d11c-f4c1-4fb7-bf6e-9b69c505b597 |  | note | FREQUENCY: Each pile
label | fcef2738-50d9-4378-9765-492063e526d9 |  | note | CATEGORY: IP
label | 4e4d7438-1e52-4bc3-b8e8-50cc926c5c1e |  | note | RESPONSIBILITY: Concrete Tester , Foreman , SE/PE/SPE
label | 9ef455d0-c868-4df4-a0d9-9735441ace5e |  | note | VERIFYING DOCUMENTS: This ITP
text | 152b05d4-01f7-4044-bf60-6e2f92f263bf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | e306100d-5fe4-472f-8894-675002baf6b4 |  | note | REFERENCE: 610.13 (b)
label | 7e6f749b-ff82-46f7-8f67-fc03ed6bb649 |  | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
label | 5caed2d5-83eb-46c5-9e59-02a1032e9862 |  | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | f3fcdaa2-5095-4faa-beb6-b7f4ca6f8f7d |  | note | Passability = ≤10mm (aggregate height differential)
label | 52ce8ae8-867c-40ad-b034-a61382c8dffa |  | note | Record: Required information on the Concrete Pour Record.
label | 54b10a14-2017-4ed9-894c-320d1813d7b6 |  | note | METHOD: Test
label | c2d44c1f-c3ba-4d47-9b92-c0e295cad230 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 016525dc-dcb1-4063-b49b-ff99333b04f9 |  | note | CATEGORY: IP
label | 7c88ef01-dcf7-49e0-8181-0947a602de20 |  | note | RESPONSIBILITY: Concrete Tester
label | 3b3dae37-f30c-4323-870e-cdec58da14e3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 473ca3dd-fada-491d-b3c0-a446952cc67c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | b63fc3a3-37b7-4ac9-ad47-9eaf279a897b |  | note | REFERENCE: Site Sampling & Testing Procedure
label | e6d014b8-d4fc-49e4-9c60-04a726875117 |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | d5de5ba9-25ed-4abf-b98b-a475481b9c8f |  | note | Record: Required information on the Concrete Pour Record.
label | 69307755-00d2-481c-81f4-1870dee4dbde |  | note | METHOD: Test
label | d4e52f89-afdc-4d97-a6be-cbb05b0a59d7 |  | note | FREQUENCY: Each sample
label | 1ffcce85-a885-46cb-9b61-d6c25300da21 |  | note | CATEGORY: IP
label | df8eeeac-33b3-4625-bacb-3342c1620443 |  | note | RESPONSIBILITY: Concrete Tester
label | 247ff6b4-5c7a-4ee0-8f2c-a2f865174a4d |  | note | VERIFYING DOCUMENTS: This ITP
text | 53fd216b-f377-42d7-b988-837bfbef9bec |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | 7ff43118-7587-4f34-b9ca-4b3248840b54 |  | note | REFERENCE: Piling Quality Procedure
label | 89c7cf50-b4cc-42d3-b460-681c61954b4c |  | note | 610.18 (a) & (b)
label | 4e11cbde-a9ac-4217-add6-6ce27fcc773a |  | note | 610.18 (d) (i)
label | a2cb6003-b757-4f59-84cd-a913d2632920 |  | note | 606.06 (a & b)
label | afde1153-4f4e-4f9e-a936-e126412f5ecd |  | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | 641ed19b-fbda-45e6-84aa-f0d1219ab5dd |  | note | All concrete batches are traceable.
label | c6ead33c-5108-4f81-8e8d-23135474cce0 |  | note | Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | 2e6dc2af-4ea0-41e8-bf80-3ae6d15c63ef |  | note | The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 2622346c-07d3-4875-9a50-49051432e903 |  | note | When placing under water, the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 0f07cf2c-fea3-4954-b154-7536aee0c639 |  | note | Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 0fd07e9b-a311-472e-b660-fe00c8b138fc |  | note | Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 6bbb3577-2e14-4fb6-9312-3f1933e35e6c |  | note | Record: Required information on the Concrete Pour Record.
label | a2441358-fad6-4d70-951c-9721dd7eb1f6 |  | note | Attach: Concrete Pour Record
label | 581a7887-440a-470e-adf5-ab1fc3f72340 |  | note | Attach: Concrete Dockets
label | 8771d1ce-f518-4c3f-8114-30cd600a536d |  | note | METHOD: Visual
label | 82935369-c78d-4a39-84b3-c9f7c46092f8 |  | note | FREQUENCY: Each load
label | ac91128b-1b5e-4515-8829-bcd4ea873198 |  | note | CATEGORY: SP
label | 3e37e72d-6951-422c-8e25-3941b546539a |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
text | 4242ac6a-1ad1-4192-9233-799629147c88 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 66f13522-3b51-4deb-ba3e-e06106f87639 |  | note | REFERENCE: IFC Drawings
label | 62f88edc-221e-4e67-a11b-44989c29dcda |  | note | 610.31
label | 83b3f301-4c97-4abb-a6a2-7f24522b40cd |  | note | 610.2
label | b5a796bf-1156-4c25-b4dd-b22e42298f32 |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | 6d778437-b203-4e8c-9b0e-9151fd812bfe |  | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 82cb8284-e0e7-49c9-89d7-2e2aab6f08be |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | afabe188-dc2c-4843-9ee1-5d93cecd6cc8 |  | note | METHOD: Visual
label | cf937fad-3106-4f7e-9f93-aaea9c048307 |  | note | FREQUENCY: Each pile
label | cb8ca219-dddb-4d9f-9c3b-70258bdce427 |  | note | CATEGORY: IP
label | c721fb88-eda2-4db2-96ad-2949ff2bcbb1 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | e4e4ae65-68c6-479f-a3f7-13d3b8afcbf4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2ac53d43-6049-483a-a0e9-239d244383eb |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | d1d5d446-02b4-4160-84f1-f1baa226ff82 |  | note | REFERENCE: IFC Drawings
label | b14f0138-eb8a-43f2-82e5-4a8e728a1cb8 |  | note | AS2159 Clause 7.2.2 - 3
label | eeb7d372-0a09-4022-9195-6fbe821443c7 |  | note | 606.06 (a & b)
label | 29abbff2-4dd5-48d2-b983-30bd818e5e52 |  | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.\
label | 4551876a-7351-4b64-892d-3aeb68c445ef |  | note | Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | d04de5fb-032e-4332-b5c2-0667531e51d5 |  | note | Any weak or damaged concrete shall be removed back to sound concrete.
label | 1f6f8e1b-4cd7-4358-9f81-6b5e5af560e0 |  | note | METHOD: Measure , Visual
label | 03aa42ab-6d08-4d01-8a55-7651c30cfe98 |  | note | FREQUENCY: Where applicable, each pile
label | 1edf2590-9c85-4cbf-b98c-e8c68d40edfc |  | note | CATEGORY: IP
label | 62a34320-d0a3-4d77-b60b-a85445fdb713 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e1861c84-fd59-4697-b824-11ffb443275f |  | note | VERIFYING DOCUMENTS: This ITP
text | 32c172e0-6afd-4cdc-a085-a6ef0a628290 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 1b2b8462-75a9-4952-9b6b-bdc1661cd2d9 |  | note | REFERENCE: IFC Drawings
label | b85dfcd8-c70f-4df0-bc88-1e6056639bfa |  | note | Table 610.05.051
label | e88cd26d-be66-42e8-93b8-b63ddaeb8613 |  | note | 610.16 (g)
label | a4da2ec9-1df1-4567-864d-eacce977b658 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 92af7c64-4198-4a8a-9740-dbd869d3b675 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 8766b66b-def5-47ae-9479-28d381051164 |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 63123cbe-e463-4dc4-bd74-f571b4417609 |  | note | Attach: Compressive Strength Test Results
label | f6bf04b2-192b-47a2-880e-f5be5f0b8a5f |  | note | METHOD: Document Review
label | c32d6857-a2c6-4b28-baaa-6a73d0f0a260 |  | note | FREQUENCY: Each cylinder
label | 66a28743-30d4-4140-8749-af29d3b9a32b |  | note | CATEGORY: IP
label | ce830a85-8732-47a1-9983-d4efe9446500 |  | note | RESPONSIBILITY: SE/PE/SPE
label | a8cb0d88-0128-48f4-b4d6-4a5e764981ad |  | note | VERIFYING DOCUMENTS: This ITP
text | 3407a05e-8505-40a5-b59e-134cfd555e7e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 2b5716eb-10b1-43b0-afce-9afbbd70ebc7 |  | note | REFERENCE: 606.07 (a, d & e)
label | f7774ea3-4cf9-496b-9416-321f73ed1534 |  | note | AS2159 Clause 8.8
label | 9f3157b5-9cab-4b5f-8825-0c5183cc71d1 |  | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 680d2cbe-bd5a-4e03-930d-230cff1b3482 |  | note | Cross-sectional area = ≥95%
label | 1ef6e127-5626-46ec-9436-67cbe9701c99 |  | note | If any test fails, all piles shall be tested.
label | 5b366b54-22de-4b14-ab7e-3bac53bd7ede |  | note | Attach: Pile Integrity Test Report
label | b07aebc5-42f3-4763-b435-47889475e299 |  | note | METHOD: Document Review
label | bd68c6c2-e6ed-4f4a-ba3d-2e94b2f775fe |  | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | f1255442-82b4-4785-a7d7-b084d98e3d19 |  | note | CATEGORY: IP
label | 88e3b8a3-264d-4d44-abda-7ff551172f96 |  | note | RESPONSIBILITY: Testing Consultant SE/PE/SPE
label | 11b5810f-330f-4c46-b400-04fac8825fb2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 517b7c4c-c177-4b56-b093-15a5c6f373b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Static Load Testing
label | fc3971ba-6cab-4faa-b833-7c55583fbfb2 |  | note | REFERENCE: IFC Drawings
label | 9057c971-858d-47d4-9b2b-e45d7ef4bbbb |  | note | 606.07 (b, d & e)
label | e9a3a309-872c-4b40-9f7f-e449f1b00412 |  | note | AS2159 Clause 8.4
label | 68ab0768-c903-4002-bd95-d5f1a56409aa |  | note | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | 1e3346d4-7bf0-437e-a8c5-b99ed4c8de04 |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | f9c4e160-fcd5-4a2b-9b92-bd7451bb264c |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | a31e7e10-8a02-4ee4-a0d8-33421808eed9 |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | 06370530-41a9-48bd-9b4f-5a46ad472a75 |  | note | Attach: Static Load Test Report
label | a8700a9c-d3b1-4ec7-b8f0-166e7a2d950f |  | note | METHOD: Document Review
label | 90159633-9f89-4fe6-abae-e254e4897190 |  | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
label | fa7f813c-3ecc-4dd1-b1f3-68f37508b964 |  | note | CATEGORY: IP
label | 3a6ccc86-918d-4d2f-b6d7-80b934d4c09f |  | note | RESPONSIBILITY: Testing Consultant , SE/PE/SPE
label | f62efad8-047a-4e6b-bd98-a4d6e4e6be26 |  | note | VERIFYING DOCUMENTS: This ITP
text | bc1d967d-39f2-45bd-87bb-f211d67574d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | 515170de-6a48-40fc-ac1a-beb4cb85b686 |  | note | REFERENCE: 606.07 (c, d & e)
label | 83f9b8cd-df5d-4d8d-9502-9a5c3093fee7 |  | note | AS2159 Clause 8.7
label | 67aff411-9aa8-4ddd-ac90-e18a8687e8a4 |  | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | 52502f4c-c1fa-4c23-870b-a61a34df1f38 |  | note | Measured Ultimate capacity = ≥ values on IFC drawings
label | 0322b52f-a1de-4b35-92f3-18cd5405e30d |  | note | Attach: Dynamic Pile Test Report
label | 36f39a3d-522d-4eac-a126-6774e2dbe346 |  | note | METHOD: Document Review
label | 33f27b14-5a63-4746-9c92-b549728c5939 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | 6496f4b9-93b3-4601-bf62-503e9968963e |  | note | CATEGORY: IP
label | 6ba47f91-e945-4638-91ec-b046320da02f |  | note | RESPONSIBILITY: Testing Consultant SE/PE/SPE
label | d885ad10-4071-4f4b-8f1f-15a069e5eec9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8a21dd6f-c312-46d8-91d1-245f98b247b3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | 57847950-41ba-4a10-8b6b-50001d9aba83 |  | note | REFERENCE: IFC Drawings
label | f03c990a-95b5-4f9e-9231-128a41c7533d |  | note | 606.08 (a - c)
label | 31e26405-7a1d-4a44-aec4-0ecf49b1797a |  | note | AS2159 Clause 7.2.2
label | 7dbc8cd1-5335-4a03-b427-42cf758fcb3c |  | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
label | e952d03c-592c-41cc-be4e-727724cd7b29 |  | note | i. Pile head plan location = ±75mm
label | 4c95a758-bd5a-481f-b437-c5b64f2458f7 |  | note | ii. Variance from vertical or rake = 1:100
label | 7b728822-9919-4bfa-84fc-61056d40912a |  | note | iii. Irregularities in straightness = 1:100
label | 4177af16-05de-48e4-9cf2-f3ea01ef6777 |  | note | iv. RL = ±25mm
label | feffa8a8-ad33-4998-b82c-b373556c6577 |  | note | Attach: Survey As-builts / Survey Report
label | 74b5c54d-c03c-46c3-95d7-7fbcaf580d44 |  | note | METHOD: Document Review
label | f55191e6-6609-49c0-898b-5976903ed2af |  | note | FREQUENCY: Each pile
label | 81b08ccf-c622-44f0-b630-b8faa5824d77 |  | note | CATEGORY: IP
label | 053839df-dea7-489d-83ee-a6014b3b1102 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 3b377502-ce42-4400-b340-128ce5b0f358 |  | note | VERIFYING DOCUMENTS: This ITP
text | d245a07d-d913-471a-a34f-7be9cf5f4ffc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | 00f1c29c-2691-45a8-b9b3-f7b10df49f2f |  | note | REFERENCE: MRPA Quality Management Plan
label | 21efda6e-ef7b-4a2a-8d45-08cd55b159af |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | ae870be8-0793-4a97-9a8b-31a103e72cc6 |  | note | METHOD: Document Review
label | 54850229-8412-4f9a-aff4-778d0ff54919 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | a2e7d5ff-81c8-4f0d-aa21-22ecfb87f66d |  | note | CATEGORY: HP*
label | 40e718f0-2a08-4e2c-8063-6e1c6227ed12 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cf5821f3-063f-4208-88b6-29a17e79b269 |  | note | VERIFYING DOCUMENTS: This ITP
text | 58832145-468a-4c62-ab8b-f934237ec0ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 05f5693c-d1c4-49f4-8ac3-5513cd6da6ba |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d97eea69-6a6c-4b00-8655-5e5a3d2510a7 |  | textbox | Name:
text | bf4f1b3d-8be7-4d6b-afe2-6bd40a65297c |  | textbox | Position:
text | 01af0182-a438-4f50-877f-71759b91605f |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Sign Posting Rev 0 | itp |  |  |  | Yes | ITP-CIV-Signage (Supply and Install) Rev 0 | ecfe4df1-eecc-4d84-8c71-4e9598c3ba40
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 775bdde7-293c-4a0b-9d8d-59ccaa9cef25 |  | note | Document Title: ITP-CIV-Sign Posting
label | 06cf4ef1-7eaa-4515-8d03-aee044004759 |  | note | ITP Description: Sign Posting
label | 5e84d432-6e72-409e-a423-cc86cffeb97b |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00
label | 833485b5-1ff8-440f-9a4e-2563774f362f |  | note | Discipline (e.g. CIV/STR/RAIL0 CIV:
label | e3116b41-fe7a-438b-8d97-c13d72333632 |  | note | Revision Number: 0
label | 18dfa063-04c8-4920-87e1-d1a93f5032b7 |  | note | Revision Date: 24/09/20
label | 09317b41-4647-4af7-8518-e6b2e0ac172e |  | note | ITP created by: Romualdo Magpantay
label | 92cc1e30-fa1d-4e8f-8906-711c4be6535e |  | note | ITP approved for use by: Romualdo Magpantay
label | 69e8dfa6-c444-40d3-9307-158e504d6120 |  | note | 1.1 VicRoads Section 714 December 2018
label | 7776acfe-e510-4af8-8c2a-1e0d3c0731c4 |  | note | 1.2 AS 1743
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | 2.1 Obtain approval to supply bolts, nuts and washers from Independent Certifier (IC) including steel post other support systems.
label | f6351727-d694-4a36-83f3-9bd04ca24481 |  | note | REFERENCE: Vicroad 714
label | 3eaf9227-c66a-4d52-aa4f-50727d44a196 |  | note | IFC Drawing
label | 7bd58e37-15be-43c9-8fe9-2c89f288ea53 |  | note | AS/NZS 1252
label | 527c905a-a741-4e02-8739-21d7cec5693f |  | note | ACCEPTANCE CRITERIA: ● Submit to the Independent Verifier that ISO9001 certificate of the supplier, Certificate of conformance, details of the supplier, lot identifications and relevant test result
label | 8b649d63-77f8-4ba8-91c6-86aeadf29659 |  | note | ● Steel posts shall be manufactured from steel complying with AS/NZS 1163, AS 1397 or AS 1450, and having a minimum yield strength of 250 MPa.
label | 0762ab14-21c1-4f56-a600-9525e412cacb |  | note | METHOD: Review
label | 276b2271-c3b4-464f-a783-258e6e91c484 |  | note | FREQUENCY: Per Supplier
label | b0349fc6-0c70-4fb6-96f0-a16feff6e23f |  | note | CATEGORY: HP
label | cd20eb4e-356f-4e10-8e8f-046d6067ce05 |  | note | RESPONSIBILITY: Nominated Authority
label | b8104abf-960d-49b4-a687-11bf3a614ce5 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 69fb85c7-726d-425a-b1ba-b2c78c4c4326 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Obtain approval for commencement of sign manufacture
label | f8af54f6-e311-4d32-b950-d4d7dfe42f1a |  | note | REFERENCE: Vicroad 714
label | defdea74-cc1e-4174-bff1-a732d39b4022 |  | note | IFC Drawing
label | d94bc7b7-d7fc-42bc-995c-10968bf1cad4 |  | note | ACCEPTANCE CRITERIA: Submit prior to commencement of manufacture, a statement advising the brand(s) of retroreflective sheeting and details of the non-reflective background and legend material, to be used in the sign manufacture.
label | 5a1b7f4c-4f8e-4049-b9d2-c8b67bda6952 |  | note | METHOD: Review
label | fc58916d-9562-4be0-912d-b6ae2271e249 |  | note | FREQUENCY: Per Supplier
label | 874facc7-e3d6-4556-b0fa-3e7d81a79e23 |  | note | CATEGORY: HP
label | a889b8d2-032c-4768-8689-42ad8af21dd5 |  | note | RESPONSIBILITY: Nominated Authority
label | 46cbe48b-87be-4f73-a35a-88cf7c6909f9 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1025ab4c-893e-4c91-a64b-71317108b792 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 To inspect the manufactured signs prior to delivery & submit a conformance certification statement.
label | 81f180d5-fa2c-4da1-b1d8-c14eaa8d64c2 |  | note | REFERENCE: Vicroad 714
label | 08518d22-b1b7-4743-bbfe-432427bdca52 |  | note | IFC Drawing
label | 92760c57-4dee-4c40-bb83-0ee24a9b606b |  | note | ACCEPTANCE CRITERIA: Submit to inspect the signs prior to delivery:
label | 03de618f-c6d7-4df1-966a-feb1582b2edb |  | note | ● Statement certifying that the signs comply with the requirements of Vic roads and IFC drawings
label | 55013572-88ed-4f58-88f7-d9188d0e54c2 |  | note | METHOD: Review
label | 33b0e748-629a-426f-bb9d-d25b54772173 |  | note | FREQUENCY: Per Delivery
label | 1f9cd7c3-17ba-4b5d-bc7d-cdea71cee457 |  | note | CATEGORY: HP
label | a3115155-b8b7-4e50-9aaa-5e7944e52be7 |  | note | RESPONSIBILITY: Nominated Authority
label | 853e571f-aef4-467f-915c-7ec815a5bad3 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 51636cd8-f1b9-412f-b324-34df30ca00f0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Set out the works to ensure all signs and support structures are located in accordance with the design drawings
label | eea57669-34f8-41a3-8c59-f49e8f4fb86e |  | note | REFERENCE: Vicroad 714.06
label | b088e45c-6826-45fd-bf84-33d3ea4304a3 |  | note | IFC Drawing
label | 15ee2762-80a8-4abb-ad7f-d2e79d410b29 |  | note | ACCEPTANCE CRITERIA: Submit a Hold Point to inspect the proposed arrangement and alignment of each sign support structure, upon completion of setting out
label | b6616461-d38f-4b54-8239-06dc1e870e38 |  | note | METHOD: Visual Dimensional
label | 9861ebda-9e0d-41be-ac49-8a5d21387b64 |  | note | FREQUENCY: Per lot
label | ce899dbb-ae14-4c6a-909c-4807bf263d73 |  | note | CATEGORY: HP
label | e23bc662-fbc6-44e9-937b-d478d021f40d |  | note | RESPONSIBILITY: Nominated Authority
label | 91f997da-0b5a-4521-8cf6-315a6a4cac49 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 28d6e200-de45-4304-ba6f-a3d5839ac4d5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Clear the areas around the sign support structures
label | 19630d08-2554-4e1e-b41a-2917fa98ae18 |  | note | REFERENCE: Vicroad 714
label | 3ad3c3cd-b335-4995-ad2f-32f1362c9902 |  | note | IFC Drawing
label | b58c1c6b-180a-4e3a-8368-87323eafff12 |  | note | ACCEPTANCE CRITERIA: Submit a Hold Point for the intention to clear any trees & undergrowth within 3 metres of the sign support structure & along a motorist’s line of sights to the front of the sign are cleared and removed.
label | 4cbd1b00-3b14-40ec-8afc-54627b421e96 |  | note | METHOD: Visual Dimensional
label | e2463e88-2f61-4d99-ac6f-fb52ebbfb77a |  | note | FREQUENCY: Per lot
label | b4ec2e16-caa9-4e85-82f5-32ec45580070 |  | note | CATEGORY: HP
label | dd0623ce-a73d-4ae9-8907-7036be3190f3 |  | note | RESPONSIBILITY: Nominated Authority
label | 51d1b72b-12e3-42d8-bd13-67da5001c74e |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 952410d2-52cd-4e9b-be21-632384628bd0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Excavation of the foundations for signs
label | ebf30004-07dd-46b0-b046-d9fd30817a9d |  | note | REFERENCE: Vicroad 714
label | 681f4608-93b0-4e6e-b2e7-a9393217acc0 |  | note | IFC Drawing
label | 97705aae-b944-4c24-915e-f1c0ea62d551 |  | note | ACCEPTANCE CRITERIA: All posts shall be set in concrete foundations to the depths shown in the Sign and Post Schedule & Concrete used in foundations shall be 20 MPa complying with the requirements of Section 703
label | 8e7229fa-58dd-47d9-a24d-60527af7d440 |  | note | METHOD: Visual Dimensional
label | aa3325dc-48d3-49c0-8dc1-82cee06753d8 |  | note | FREQUENCY: Per lot/ Signage
label | 5e102c3f-f665-42dd-b102-6427f71fb3e0 |  | note | CATEGORY: IP
label | 419d0e35-fc19-4a87-8517-3da4f22e1698 |  | note | RESPONSIBILITY: Project /site Engineer
label | 5b0e1646-f857-429a-95d2-234c9927866f |  | note | VERIFYING DOCUMENTS: This ITP
text | 4a031863-1f00-4736-8c23-40508a97740b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Placement of Concrete
label | 3a3aa619-374d-47f8-a9c1-9b8026b35753 |  | note | REFERENCE: Vic road 610
label | 841d391e-d02d-4d59-bebc-52c146a645aa |  | note | ACCEPTANCE CRITERIA: Notify NA prior to intended time of commencing the placement of concrete, when fixing of formworks and reinforcements in position (if applicable) will be completed and when concrete will be placed for pre-pour inspection
label | ba110456-82d1-4531-a64b-61a1c5a74876 |  | note | METHOD: Visual Dimensional
label | daccf76b-bf00-4f0b-9dc8-d879eebfb8c4 |  | note | FREQUENCY: Per lot/ Signage Structure
label | 64e51421-6a1f-48e5-8743-319b0ef2186b |  | note | CATEGORY: HP
label | 366ca4f7-bb94-4ffb-8f14-b144c668b471 |  | note | RESPONSIBILITY: Nominated Authority
label | 2f477f5e-6667-4ee6-803e-6fed5e4c4ee8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 669c6aa5-c0aa-4ecc-a279-d780ab045227 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Erect posts for signs in according to design drawings
label | 83d77347-c78c-4dea-ad5a-5ae7ea9122c2 |  | note | REFERENCE: Vicroad 714
label | 6e958ee1-6505-49a4-a769-b45edddf423f |  | note | IFC Drawing
label | 1048b595-84be-496f-8db8-60502430e012 |  | note | ACCEPTANCE CRITERIA: ● Where posts are to be mounted in sockets, the post shall be securely fixed into the socket by an approved vandal-proof method.
label | 5d3c16d0-af60-4d8d-ac90-e20a49b029cf |  | note | ● Signs to be mounted on two or more posts shall have posts positioned such that the sign face is rotated away from the approaching traffic to avoid direct reflection. Posts shall be positioned such that the sign is rotated away from the cross section by an amount equal to one tenth of the width of the sign (approximately 5º).
label | a453a7d1-c411-464b-9adb-d0d0a347a426 |  | note | METHOD: Visual Dimensional
label | 40ec3115-8bca-4281-a6a3-9cc02b6c00c2 |  | note | FREQUENCY: Per Sign Structure
label | b80bf8d3-cb39-4270-8544-708463293a04 |  | note | CATEGORY: IP
label | 0455592f-1719-4a1e-b155-3261691417c3 |  | note | RESPONSIBILITY: Project /site Engineer
label | 9ddd4389-c4b4-4082-9276-d89fbfbf8f19 |  | note | VERIFYING DOCUMENTS: This ITP
text | eb159db3-2e5a-4d21-a6b2-435563666a73 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Attach sign panels to the supporting structures if fabricate on site
label | 86ee53e2-2854-4239-8a59-8276bceb9559 |  | note | REFERENCE: Vicroad 714
label | f2fe42b6-1754-4a1f-a98b-bf6855d6fbe3 |  | note | IFC Drawing
label | 33bf579f-b6f7-4fd2-a7bb-16ae11c6c247 |  | note | ACCEPTANCE CRITERIA: Installation of signs shall be in accordance with the Sign and Post Schedule(Vic roads 714.07).
checkpoint-status |  |  | checkpoint | 3.7 Masking of signs
label | 3eb7b1aa-dc7b-4e19-bfd8-0d0aadee97a1 |  | note | REFERENCE: Vicroad 714
label | 59a74363-a479-4841-a998-49a65e5259fb |  | note | IFC Drawing
label | f1cbe0d5-fc0b-4a2e-b81d-aaae2fd6753b |  | note | ACCEPTANCE CRITERIA: Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign.
label | 46bcde76-72c4-42fc-8ef3-85079ceb560a |  | note | Adhesive material shall only be applied to the masking material and not be applied to either the front or rear
label | 1b95616f-9e3a-449b-acaa-5d4ad9858aa6 |  | note | METHOD: Visual
label | 7f1139ff-dd88-4525-82ac-93d98ac15367 |  | note | FREQUENCY: Per lot
label | 7aa2a2e5-5c8e-4118-b8be-fe3f9e59ee5b |  | note | CATEGORY: IP
label | be97074d-08f8-43d2-9af9-5b62358cbc33 |  | note | RESPONSIBILITY: Project /site Engineer
label | 6ad783da-08ab-4ec5-8ee4-506bfdd6546c |  | note | VERIFYING DOCUMENTS: This ITP
text | afc7f034-ca11-4e67-8400-525c63ebabf2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Inspect and repair the installed signs for any surface damage (i.e. scratches)
label | 75be9540-c032-41b3-b775-f60056f2782a |  | note | REFERENCE: Vicroad 714
label | 92f8ee43-95ce-4788-986a-61a1a6e85d5f |  | note | IFC Drawing
label | 2e32243a-baff-42c9-8a35-fb50c4fd009f |  | note | ACCEPTANCE CRITERIA: ● Damaged galvanized coatings renovated with zinc-rich paint to at least equal to thickness specified by galvanized layer.
label | f265b72f-669a-4d06-b2e3-1ac6f231d375 |  | note | ● Any structure with a total damaged coating areas exceeding 2500 mm² have been regalvanised by the manufacturer.
label | a2357a8e-75fe-41f8-8c5e-6ec4456650fa |  | note | METHOD: Visual Dimensional
label | 6eccf965-3e9d-40b7-92de-6c33cccab99c |  | note | FREQUENCY: Per sign structure
label | fe8876bc-ef85-449e-84ab-482fbe0ee0f4 |  | note | CATEGORY: IP
label | 5cd9fbf2-dd0c-4870-91c6-b1689aa21366 |  | note | RESPONSIBILITY: Project /site Engineer
label | 67515c97-8197-4d63-ba41-6e60be8ed075 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2dd91391-e356-4a55-99af-518f460ccd8d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 As-built Survey /Asset Identification
label | 34fb7faf-d2cb-4bfe-a164-bea85fe886e5 |  | note | REFERENCE: As built Drawings
label | e39e5c96-ac4e-4176-be24-b7da94d78a3c |  | note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | 1de7202a-5054-41d7-a5cc-fd6432d090bb |  | note | METHOD: Document Review
label | 3a3eccb5-9bf3-44a5-ac97-99bcf2f8ec58 |  | note | FREQUENCY: Once
label | f0141d5f-eecb-4529-8b45-978ccbcc44e0 |  | note | CATEGORY: IP
label | 78ee979d-5f01-4c7e-95db-2e0904a73a3c |  | note | RESPONSIBILITY: Surveyor Site Engineer
label | f916a184-25da-4b8d-8185-c99310e1844c |  | note | VERIFYING DOCUMENTS: This ITP
text | 223a62d7-e29a-40a1-aa90-ccc28701daae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | d3272c96-fb58-4afc-8a1f-540f0943d01e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 94a34d7a-722a-412e-ba1e-bb08e3c7034b |  | textbox | Name:
text | cccf7d31-2bf2-403b-aa5a-842cc39aec97 |  | textbox | Position:
text | 0b8b7a08-af55-4fe4-8e9e-7e9b55e6ecdb |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | itp |  |  |  | Yes | ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3 | f30c4ea0-594c-4b95-90d3-d0d3e0524548
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | adae9d4d-b67e-4c8c-aaaa-ca344a1cd214 |  | note | Document Title: ITP-STR-Structural Steel Barrier Rail (Supply & Installation) Rev 3
label | 1d36f9ac-c9e7-4e17-aaeb-017851de1a0b |  | note | ITP Description: Structural Steel Barrier Rail (Supply & Installation)
label | 792bf003-8c59-4d58-9178-795580743704 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 5c6256de-ad4f-49d2-8146-fb0565543594 |  | note | Revision Number: 3
label | 4d780a5f-9ea4-4460-b3ca-6b6a9768570b |  | note | Revision Date: 4/05/21
label | 65f36246-429d-45a5-ac16-f2cbef85a2db |  | note | ITP created by: Mike Freeman
label | ad9a9a91-dc9f-4891-b621-cb6fc84ef27b |  | note | 1.1 VicRoads Section 610 November 2018
label | 0a57e4bc-0928-44d3-b036-66fad85d22d8 |  | note | 1.2 VicRoads Section 610 March 2019
label | 793e5c6e-9454-405e-90bd-1c89f1cfc756 |  | note | 1.3 VicRoads Section 610 June 2019
label | b47fa068-1e1d-47bd-9539-332bc982f002 |  | note | 1.4 VicRoads Section 630 October 2013
label | 894e378f-d39b-45b1-b9d0-8adc79b0929e |  | note | 1.5 VicRoads Section 631 February 2009
label | 35352c9e-4d3e-460e-9e06-b32e1e3e3d35 |  | note | 1.6 VicRoads Section 671 October 2013
label | 0e0e1850-379e-4faf-ba67-4b5af4125e13 |  | note | 1.7 AS5131-2016
label | e3deb57d-08e9-4b83-adf3-a9cbdc230d8b |  | note | 1.8 AS4680-2006
label | f40c4561-1199-4964-9817-c758f7ce7d51 |  | note | 1.9 AS2312.1-2014
label | 45a9e833-3a9f-4d31-a5be-f375892c1c5a |  | note | 1.10 AS4506-2005
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Structural Steel Components
label | 24ba9873-986a-43b0-aebd-66aa8b6eb822 |  | note | REFERENCE: IFC Drawings
label | 8ba2419d-0b76-419d-9889-bfdea3e350cc |  | note | MRPA Quality Management Plan
label | b0a2ac9f-a8d8-4c49-9fb9-96783a34faf8 |  | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | 2ae71416-f8ef-4432-a408-ec83d4b18a73 |  | note | Typically this consists of but not limited to:
label | a2f9837b-9e96-4511-a404-e61bf5295532 |  | note | i. Certificate of Compliance
label | ed1b38b3-5435-46a7-84f0-fce5a02994bf |  | note | ii. Completed ITP
label | 22a5d432-acef-44cf-bddb-8ea601fccb84 |  | note | iii. Weld Procedure Specifications
label | bae44cca-3c88-47bd-895e-3f0dafd8dc4a |  | note | iv. Weld Procedure Qualifications
label | e507cd92-82f5-446c-90d1-5684a8406b73 |  | note | v. Welder Qualifications
label | 675423c6-468f-431e-ae36-daee189c87d5 |  | note | vi. Material Certificates and traceability
label | 8cc03af0-098c-47e9-86e7-f544929d8f11 |  | note | vii. Quality Assurance check sheets
label | b4620a60-120c-4f60-bdfb-f99cff3a1b1d |  | note | viii. Welding Consumable batch certificates
label | ce8b8200-9d6a-42c6-bec2-de110e7b5c11 |  | note | ix. Coating certificate(s)
label | 47eb347b-4c8a-461b-8f5e-f59fb88217c3 |  | note | x. Non-destructive Testing (NDT) Reports
label | ccfd3af2-4f85-403b-ba3e-a5e0cce102fa |  | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | b5e9c16d-2956-4563-84c3-c4664686b5dd |  | note | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | e2cc4b4b-469e-4234-9617-2c5c06f0a781 |  | note | METHOD: Document Review
label | 7ef3e7e9-f596-4baa-88f6-10d30556176f |  | note | FREQUENCY: Each component
label | 1cf1b100-e5c1-4da4-b1c4-fe6a58c7001b |  | note | CATEGORY: IP
label | 44939e93-ab3b-4801-ac4e-f471ed49f1da |  | note | RESPONSIBILITY: PE/SE/SPE
label | be6db382-36bb-4886-9b97-f7e8ac6dca64 |  | note | VERIFYING DOCUMENTS: This ITP
text | 338e1872-e604-47ff-949b-ca0a82af5e7f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | 65824a36-7567-4d6b-bd1e-1fa3ee29cb72 |  | note | REFERENCE: IFC Drawings
label | 7116611b-467f-43af-ab67-33bb9724afe5 |  | note | 671.04
label | 0d7a902d-718c-48ce-a64f-fbd6a8b5c7c1 |  | note | 610.33
label | cebe679f-ed7c-483e-b269-9948b18544f3 |  | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | 29944583-3750-4d34-88ff-e8bc1515a4ed |  | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | 9888b049-32a9-48df-82dd-3a4fd1be21e7 |  | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | 88b793b5-64a7-4898-a1a8-9c654573ca2b |  | note | iii. have a flowable consistency
label | e2c5158c-dfef-44d9-a446-fdeab7c1a6b7 |  | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | f4caa0b0-dc8e-4a27-99f2-e034e8b6b9de |  | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
label | edfd52bc-fc37-4373-a36c-f366e3d8ddaf |  | note | Enter: Teambinder Material Approval number
label | 2a962a0e-f026-49a5-ba2a-b14365fcdcf2 |  | note | METHOD: Document Review
label | 186aa31e-7efd-48a7-a04c-33ad8d746167 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | d2ecd355-d8cc-4cc7-8ce9-3e2a1013b650 |  | note | CATEGORY: IP
label | fc8086bc-1325-417d-bd7b-972ba9ffdabc |  | note | RESPONSIBILITY: Nominated Authority
label | 9e5cb82d-16f2-4610-afc9-3a192c6bbe74 |  | note | VERIFYING DOCUMENTS: This ITP
text | 9288a082-f3b9-497d-ad5d-1698bc6f99ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Curing Compound
label | f397e5b5-d1cc-43c5-8820-486924d0ef27 |  | note | REFERENCE: 610.23 (d)
label | acc70afb-f477-4742-b58f-eb0a3f0196ff |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 1aadd829-bb9d-41d0-bc5b-5d23a1d1e37c |  | note | Note: This may be the same product used for the concrete curing
label | f715a5cb-917a-47ac-ab17-d8b8c3d3bce5 |  | note | Enter: Teambinder Material Approval number
label | fc27712b-b114-4925-9cb6-1be2100d2bdf |  | note | METHOD: Document Review
label | 28c57106-de44-4019-adc3-4751326396e3 |  | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | 338b68b6-4f77-4cf3-8773-4f62cacdfc35 |  | note | CATEGORY: IP
label | a5908c82-5e52-49b0-9f61-41008a791fdd |  | note | RESPONSIBILITY: Nominated Authority
label | 589f62e8-a15a-4725-84b2-281d15ba0d62 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2708e1e8-41ac-4384-b0dc-5dea0b5884e5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures
checkpoint-status |  |  | checkpoint | 3.1 Curing Methodology (for Grout and Mortar)
label | 875562d7-cf5b-44ef-b984-1a9a89ad1857 |  | note | REFERENCE: 610.23 (a)
label | 9de6b0a4-657a-4b36-9ef6-f3870500e030 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | 16fbf39b-38de-4c45-9579-37504d435ca3 |  | note | Note: This may be the same document used for the concrete curing.
label | 857647c4-ce33-4ad6-8a59-816bc48c377a |  | note | Enter: Teambinder Approval number
label | 5685c014-f7bd-4675-8a4a-2bcca30b89b3 |  | note | METHOD: Document Review
label | c4756361-759b-4322-bd29-dc8e4641eebc |  | note | FREQUENCY: Once, 4 weeks prior to placement of product
label | 5a1d76af-9235-4766-8b12-3ae103e9e915 |  | note | CATEGORY: HP
label | 2a8e3c44-94ba-49c5-a05c-733abc27e4e0 |  | note | RESPONSIBILITY: Nominated Authority
label | 2037a5c7-67d3-4bf1-b408-cdf83e575bf6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1ac4ee65-76e1-4910-b8fb-8071dfca6091 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 97ed0588-be40-4a21-9caf-918ee83815f0 |  | note | REFERENCE: MRPA Quality Management Plan
label | 89566f2a-79ec-4a28-a359-defd4f9a224c |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | b0c36f0d-68c4-403b-af54-1eaf01f98423 |  | note | METHOD: Document Review
label | 49122914-9b98-4f71-aa7d-913d898dbdb1 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | df60dee1-ce17-446d-b5ca-d1e47b2c246f |  | note | CATEGORY: HP*
label | 9a21a790-9e27-4477-bb0f-96f6727e69c3 |  | note | RESPONSIBILITY: All
label | 7ac017c5-882a-4b26-8789-8ca42e517b4e |  | note | VERIFYING DOCUMENTS: This ITP
text | 1adc9dc0-393f-4c9e-95c3-3e80b7d58ab7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Materials Inspection Checklist
label | 1cf5630f-1230-4b4b-8daf-987804c1b3d4 |  | note | REFERENCE: IFC Drawings
label | 59a0543f-60ac-47ab-bca5-74e5e9ba0d79 |  | note | 630.08
label | fb657cbf-8ccd-4140-a143-e5178064c86f |  | note | 630.09
label | 2a328178-fb1a-48f3-b49e-9e4798c6d365 |  | note | 630.20 (a)
label | 141e21ec-e84c-4731-91b9-cf75a3b2b587 |  | note | 631.06
label | b5d9a857-6cb8-4e8b-a098-4f5a40cb0d4f |  | note | AS4860 Clause 7
label | 276eaa04-056b-4656-9daa-eb5c0dafa100 |  | note | 631.11 (a)
label | e58e3859-1fef-4f07-9ed2-15403201efaa |  | note | AS2312 Clause 9.6.4 (i)
label | 4ef2e693-b97a-495a-b14e-e842389a055d |  | note | AS4506 Clause 2.3
label | 17ab2c08-2c14-410e-9334-8734e2e4b28e |  | note | MRPA Quality Management Plan
label | 06c9fd94-1f36-49c7-8a8c-e8d6622accea |  | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | e37b0f04-c69a-490b-817e-d10772720fe9 |  | note | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | f4f265d3-5472-4da6-ac27-12e326be5d16 |  | note | Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | 96e914ce-886d-4f8c-bcad-31ad9c638a6f |  | note | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | 1129b51b-7334-4cac-8d23-175a8217c628 |  | note | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | 8a33a754-efa3-492d-875d-196c481a939f |  | note | Complete: Materials Inspection Checklist in ConQA
label | 489b6819-8178-4da9-84a1-038359e65079 |  | note | METHOD: Measure , Visual
label | 66fef421-af83-4432-bc30-4d3a08ef178e |  | note | FREQUENCY: Each component
label | 5c3c3df8-5621-4ede-9387-1d0159be7d5b |  | note | CATEGORY: IP
label | bc1a3b08-cfbc-4ac3-867f-c4cbedcf6f46 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 393ee02a-37a4-4a34-8640-6a99143a4087 |  | note | VERIFYING DOCUMENTS: This ITP
text | d411b96d-dbda-4bb1-ad46-aed53ad127fa |  | textbox | Date Completed:
checkpoint-group |  |  | section | Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | a8979a74-ff16-4eea-ba26-7317c934bb90 |  | note | REFERENCE: IFC Drawings
label | 2c15f710-8366-4526-abf3-f6f44992378b |  | note | Product TDS
label | 206fc1d8-3811-4a79-a2bd-077d5706af66 |  | note | ACCEPTANCE CRITERIA: Prepare the surface in accordance with the Product TDS.
label | c6873c17-7a74-442a-9d6e-d45803caba3d |  | note | As a minimum, ensuring that it is clean and free from laitance.
label | eefd6b77-2659-434e-975f-1aabace684de |  | note | Note: Additional roughening / scabbling may be required unless the selected material clearly states that this is not necessary.
label | 8523ccff-4dbe-4831-91a4-fba87c5f6cc6 |  | note | METHOD: Measure , Visual
label | aed6f142-6089-41ae-a8c3-89adb4f7772f |  | note | FREQUENCY: Where applicable, each post location
label | e39ae37e-b065-4c0b-8adc-ae0b6bc18bab |  | note | CATEGORY: IP
label | 51046109-2670-4d69-880c-52d7e9a48171 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0cdd815c-bace-4560-82d3-6feb55cd05e0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2368695a-90ae-4a46-8ff8-993d3589eac0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Structural Steel Handling
label | 023aa73b-c30e-41ba-a333-efec6f1bb697 |  | note | REFERENCE: 630.09
label | c5f2670a-bc64-4680-8029-a65df01c04f6 |  | note | 631.14
label | a72b0939-f202-4486-a4bf-ce496a0c114b |  | note | AS4100 Clause 15.2.2 & 3
label | ce7a3207-0e28-4836-8887-8a5fa0d8c97c |  | note | AS5131 Clause 11.5.6
label | d2493af3-9a12-4387-b663-a335ecf81be1 |  | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | 0d948f38-5989-466e-9369-cfdc17f6ad3a |  | note | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
label | 7e55525d-2211-46e2-99d8-5d17e2ef6c95 |  | note | METHOD: Visual
label | 20ef1ef2-40f5-4c36-8944-f84b7fd8bbd4 |  | note | FREQUENCY: Each component
label | edc1eb4d-cb65-4711-94c7-314c7f5075aa |  | note | CATEGORY: IP
label | a8234679-0256-49d8-a3ca-693648bf65ff |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9a14190e-51d0-42cb-b9d7-174a9c7885eb |  | note | VERIFYING DOCUMENTS: This ITP
text | 0ea1d0f7-01c0-4cec-b63a-542603443b9d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Structural Steel Erection
label | 2a801d1f-9bd7-4b85-9f6a-741a03a82262 |  | note | REFERENCE: AS4100 Clause 15.2.3
label | 4395999b-416f-4e96-8b82-8ee4b595a663 |  | note | AS5131 Clause 11.5.7
label | 1ec78c75-2854-4ce6-aed8-0f2b6a86847d |  | note | 630.12
label | 58359ad3-8bc5-42b1-81fb-9749d4dd4183 |  | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | ba91d928-b985-47c7-a345-bfb3ce5837f4 |  | note | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | 5c988e39-a283-4d9a-88d0-9dda9eff8424 |  | note | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
label | c50898e0-732b-4dd4-8dec-7ffdb8f825ce |  | note | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
label | 96571110-58c0-47ec-b24e-dc1ed3de9dc5 |  | note | Holes shall not exceed the greater of:
label | 2c2a3685-2cbc-4203-b05f-077ffe43914d |  | note | 1.25 x bolt dia. OR bolt dia. + 8mm
label | 31a129ad-e8c2-46b2-8122-023d587b4025 |  | note | Slots shall not exceed the greater of:
label | 20a282cf-7e19-4d9a-a023-885c68dd4c36 |  | note | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | 078d055c-3a8e-4a98-a92a-e201aa795131 |  | note | METHOD: Measure , Visual
label | c6a02271-dfe7-4817-ae19-324a0d770007 |  | note | FREQUENCY: Each component
label | 09cb488b-ffe1-47f4-9e43-1a1484c72cb9 |  | note | CATEGORY: IP
label | a8823ece-c9a1-4ec3-8b99-d4c4fa33caad |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ec10c4b-6da0-4a17-bff5-0344165f8a11 |  | note | VERIFYING DOCUMENTS: This ITP
text | d4ba7532-1a8d-47b8-b3b8-2b01fe6a6930 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | bc34da90-b9e0-4ab4-95c7-c50038a2fad7 |  | note | REFERENCE: IFC Drawings
label | d2ec75a0-e0e1-45e0-9b8b-295ed2a9ddff |  | note | 630.20 (a) & (c)
label | fda4fa86-81c1-4040-93e7-8c5e7626edc4 |  | note | AS4100 Clause 14.3.5.2
label | fd3a7455-8e65-40ab-951e-754ac258c7e6 |  | note | AS5131 Clause 6.7.4
label | 770780e0-3143-43a8-a71b-10a4cb87c994 |  | note | AS4100 Clause 15.2.5.2 (a)
label | f9ed3133-bad3-4494-87a4-39b67344e28a |  | note | AS5131 Clause 8.3
label | 9a49125d-ec7d-4097-9699-c99892b4db09 |  | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | 6db9d23e-70cf-4664-81d7-0591aa177073 |  | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
label | 17cbcd94-fcb6-4540-b3b2-0b680d40c073 |  | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | b845b681-a234-4f90-b7b3-3150d6cdb266 |  | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podgier spanner.
label | b4dbe196-1fb2-4902-bddd-fccee394d272 |  | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | 9deade1a-63f5-4701-bdc2-021172775b94 |  | note | METHOD: Measure , Visual
label | 148a2e8d-e241-4886-825d-a9061e857670 |  | note | FREQUENCY: Each bolted connection
label | 15026e97-81eb-4b80-8b94-7bc71125b8b0 |  | note | CATEGORY: IP
label | bfc87069-62fa-4821-aab2-092cfc102538 |  | note | RESPONSIBILITY: SE/PE/SPE
label | c5516ecd-3b78-402e-9926-c67eb62646be |  | note | VERIFYING DOCUMENTS: This ITP
text | 1b284228-e681-4a56-8146-4f5ad4e3887e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Survey Conformance
label | 83ae5c26-8740-4c86-8d60-bde5dc3d1b26 |  | note | REFERENCE: IFC Drawings
label | 1866abde-26a1-46bc-9f1a-413ce8eabc52 |  | note | 671.06
label | 52c2e729-f399-40a6-85f1-44530f5cbbe6 |  | note | AS4100 Clause 15.3.1 - 7
label | d996070c-84c5-444e-b0c9-dac3331d4d5d |  | note | AS5131 Appendix F, Table F3*
label | 5dbf100d-a253-4845-be6f-582f342dbf6d |  | note | ACCEPTANCE CRITERIA: Railing posts shall not be grouted until verification that the Works meet level and location requirements within the tolerances below:
label | 2c1c6756-9e02-4a8a-8952-6752395d28c7 |  | note | Departure from RL = ±10mm*
label | 9b3cee75-90c5-451e-b6db-8b2d19ef35f2 |  | note | Departure from plan position = ±25mm
label | 6e72b565-d14e-4dc8-831c-ac9be196877e |  | note | Departure from alignment = ±5mm
label | 31b6a611-676c-433d-997d-679b07a227dd |  | note | Irregularities in alignment = 3mm in 3m
label | 9b8e385b-d372-4f1b-899c-8aa3eae29688 |  | note | Variation in joint gap width = ±3mm
label | 17c4710c-eaaa-416c-9175-4f1be5b1c42d |  | note | Projection of bolt = +25mm, 5mm
label | be539dff-513d-477f-bb4c-0a79eb5fefb2 |  | note | Attach: Survey Report
label | c6b68eca-dd20-49d5-9d6c-ebe71cf3975f |  | note | METHOD: Measure , Visual
label | 923e4b58-16aa-48c9-887e-d61aff74c7b0 |  | note | FREQUENCY: Each post location
label | b9c591d0-f182-4f7b-8d86-961459d76c01 |  | note | CATEGORY: HP
label | d691a511-f7d0-4873-a157-c8707740a66b |  | note | RESPONSIBILITY: Nominated Authority
label | 8ca25511-2a96-44af-b16d-496a0c6e82e6 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 73f82146-01f0-4f19-8027-ea8120884931 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Base Plate Formwork Construction & Placement
label | 9ff622d8-ff24-46af-9ccd-f415969a1754 |  | note | REFERENCE: IFC Drawings
label | 5f4f80d6-bd60-4d79-a509-d32e8209eef6 |  | note | ACCEPTANCE CRITERIA: Dimensions as per drawings (typically flush with base-plate sides and underside).
label | ddffbf4e-b81d-43d8-94ed-ad45f6373607 |  | note | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | 4433e25a-4eb6-4909-b5a3-40c12c29228d |  | note | METHOD: Measure , Visual
label | 95244109-caec-424a-a40e-f2b6f805aa4c |  | note | FREQUENCY: Each post location
label | 4b0c7391-4b91-4d1f-9315-bdcb839a07b0 |  | note | CATEGORY: IP
label | 59759c1a-51b2-4cd3-b2fe-fd2268044a63 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 493c896f-06b6-4522-9956-88352074473b |  | note | VERIFYING DOCUMENTS: This ITP
text | e23648d8-cfcc-43f8-9c63-5243c9b2d3e7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-soaking Concrete Surface
label | 68bafdeb-10a1-440d-b091-b45f0aa7dd15 |  | note | REFERENCE: Product TDS
label | 27bce66a-0c40-47d2-b397-0bb50cd2222f |  | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | e36a7c5f-422b-48b3-aa06-222e2399d13b |  | note | Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | 0af2f6a7-dc1d-4928-97e8-f1686ebd078e |  | note | METHOD: Visual
label | b315d835-2983-42e3-86ff-28932cbf0f8d |  | note | FREQUENCY: Where applicable, each post location
label | e8ae89f8-6a41-4041-b266-a3aa444bbf4e |  | note | CATEGORY: IP
label | 1e07cfce-9e7d-43cc-aead-aab159abe444 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4f52e84f-f981-4614-8aec-7c9d66a251a9 |  | note | VERIFYING DOCUMENTS: This ITP
text | d074d7fe-dc26-42fe-a7a4-555da426a8d2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions
label | 1c99cd6f-048e-4a3d-bfa7-795e3e48aaa4 |  | note | REFERENCE: 610.17
label | 5892b3cf-9551-4b08-a266-91aae9d18c4e |  | note | Table 610.171
label | 67239f9c-c2ea-46df-9e40-058e30b04f46 |  | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | 8420ce35-f614-4164-9d61-ef74b6a796d3 |  | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 73a43a26-ff86-4842-b858-65975704725b |  | note | Record: Required information on the Grout Pour Record.
label | 16539809-ade1-4884-a09c-e9186db136fb |  | note | METHOD: Measure , Visual
label | d9e5dc6a-4d78-4ece-8157-e29e713eb967 |  | note | FREQUENCY: Each lot
label | bf44f8ee-5dbe-482f-8edf-a02f52cc47fd |  | note | CATEGORY: IP
label | 4599fbab-5d65-491c-9cc8-01ccfd66854d |  | note | RESPONSIBILITY: Foreman SE/PE/SPE
label | 789a01a6-4bde-443b-ae51-4886374e309b |  | note | VERIFYING DOCUMENTS: This ITP
text | 2482e769-6792-49ff-9f91-1caa4e8733b8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Mixing Product
label | c8281654-1654-44ee-a762-42abb3e078fc |  | note | REFERENCE: Product TDS
label | ab723bf7-25c7-4aa7-8eab-1fcdb1e17bf0 |  | note | 610.28
label | b6aa5e1d-9f8e-4dd2-b5ca-1c156c1b0241 |  | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | 50e89f1a-1a75-45b9-a619-3ffdc46f7c21 |  | note | Only whole bags to be mixed with potable water.
label | fa0ec530-fe15-4f57-9b19-867842b2ef7c |  | note | Volume of water matches the required amount for flowable consistency and accurately measured.
label | 5884cd4e-57eb-41bb-99b2-689c989d9df4 |  | note | Product poured into the mixer slowly.
label | 25f18c00-269c-4199-b411-4ba881f6cb3a |  | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
label | c734638b-c38e-4165-b384-8e752c845bcb |  | note | Enter: Required information on the Grout Pour Record.
label | b0448c43-08f8-4b1f-8e4c-fa0006315cab |  | note | METHOD: Measure , Visual
label | a808b417-be61-495e-9dc8-d5130d01da93 |  | note | FREQUENCY: Each batch
label | 211ee0d3-10a5-4355-b4e2-52ededdfb695 |  | note | CATEGORY: IP
label | 1b27dbf0-f6ca-4118-8b4d-be6e86253309 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 58f1f11d-ed80-48aa-b069-7de13e885c7d |  | note | VERIFYING DOCUMENTS: This ITP
text | 21d910d4-8d2f-4f89-93a7-4028be6ba927 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Product Testing - Compressive Strength Cubes
label | 42ba2d43-d3ae-4032-8957-14210aa0203a |  | note | REFERENCE: 610.28
label | b68ffb99-bc47-4ca9-a306-1255fbbe91ad |  | note | 610.33
label | af9ef3d6-e74a-4aeb-9293-25b6cda1bd02 |  | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | 31996608-fde6-4acb-966d-41d1d7438333 |  | note | Testing is be in accordance with the following frequencies:
label | 64b095bb-6b41-453a-8761-be7a152735d4 |  | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | 853d8362-6d83-4548-95b0-51df3509c9e1 |  | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | e361237f-83bd-41a0-8eb3-50a84673690a |  | note | Enter: Required information on the Grout Pour Record.
label | 50308706-ee6f-45dc-9b40-efe0181f8d23 |  | note | METHOD: Test
label | 6dc91826-d0d4-4bbe-bb88-6b63dc583b38 |  | note | FREQUENCY: Each lot
label | 41931124-c56c-4e4b-badd-1d681a5a87c1 |  | note | CATEGORY: IP
label | 751a5a0c-d77b-4eb9-9813-79ad6e14e74c |  | note | RESPONSIBILITY: Tester , SE/PE/SPE
label | aac092ba-e9dc-4c89-846f-1db9523a7b91 |  | note | VERIFYING DOCUMENTS: This ITP
text | 94cb63e0-3ee0-46ab-b53c-e8ce72790bba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Placement & Compaction
label | f088ebed-3592-4123-b778-2f4339758e6d |  | note | REFERENCE: Product TDS
label | 32a8ba10-88ef-4e04-aeb4-773155b8ae53 |  | note | ACCEPTANCE CRITERIA: All batches are traceable.
label | e307c596-bdf3-4b81-922d-61177e910df2 |  | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | 6dc7bf3d-1f07-4779-bf45-7ead629ae744 |  | note | Product should flow to all areas and self consolidate.
label | f6ed13cf-37a8-4f3e-8dbf-4b7a0f29cfd3 |  | note | Product that stiffens or is showing signs of stiffening shall not be used.
label | d5f40cf5-7a4f-4ae7-8258-04d6ec50c6af |  | note | Enter: Required information on the Grout Pour Record
label | 9f921ce9-3908-4a45-a912-e815caa65802 |  | note | METHOD: Visual
label | 0cca327e-9a83-4402-b536-45cf328717c4 |  | note | FREQUENCY: Each post location
label | 2e55a8f2-3d38-4ad6-9f07-036ae57ee547 |  | note | CATEGORY: IP
label | dd266388-858b-4627-884a-cf6cc7d6ea2e |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 48b23b17-2c5a-4c8a-9ccc-b0391c5330e7 |  | note | VERIFYING DOCUMENTS: This ITP
text | d214f6ac-ddbe-4d31-9486-278e908a312b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Surface Finishes & Protection of Works
label | ace981c0-07f1-4357-ac1a-1f810793a9d8 |  | note | REFERENCE: IFC Drawings
label | 246f5d7e-4fbd-48ee-9fff-9c1995b18414 |  | note | 610.17
label | 0721160e-7900-49d2-b369-d8754776e541 |  | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | 4baa4a75-421c-43f1-bee3-a6ad0787420c |  | note | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | fd39a96a-85d5-4e1f-8ea3-126018406586 |  | note | METHOD: Visual
label | c670e816-5998-40a3-88c0-d135ad1cf990 |  | note | FREQUENCY: Each post location
label | b8da96f8-61e8-4044-a583-7fbf70518957 |  | note | CATEGORY: IP
label | 5dac41dd-90cb-47b9-9e63-eef4e12f022f |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 3dbb4239-3f39-44e9-92ed-a2b2803e20f5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 36ebf752-32bf-4a01-87ca-478cd3c8c735 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Curing
label | 543bc34f-8995-4266-a5d1-f2561747c121 |  | note | REFERENCE: Curing Methodology
label | 4602c0ff-f3fa-4683-859a-1b5285619890 |  | note | 610.23
label | eb6881bf-0770-4be3-be48-1cc8b2da4f65 |  | note | Table 610.231
label | 3ac877eb-d0c4-48c6-a824-4a8f22991b0d |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | fdc579c2-f455-46eb-9465-908c0984118f |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | e8fe8da4-e5a2-4507-bd5b-a4383d96e274 |  | note | METHOD: Visual
label | 433253a6-d757-42d3-9683-77a8fd31b7b1 |  | note | FREQUENCY: Each post location
label | f9fb252d-d4cf-45b1-b0f9-b357ee6b6f85 |  | note | CATEGORY: IP
label | c05f1761-92ae-4f2d-a2c8-2a94acfa3b80 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 6173bb2b-7cca-412d-940e-6498f3afcc38 |  | note | VERIFYING DOCUMENTS: This ITP
text | fcc969ec-16d8-43c6-9a3f-3f34be053f1d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Inspection of Coating
label | 0a1f3085-4550-4e42-8797-9974bcaed756 |  | note | REFERENCE: IFC Drawings
label | 712bc534-7327-466b-af20-6f4ba9620d01 |  | note | 631.15
label | d9429056-7e61-478a-9812-fa876c8f42a1 |  | note | AS4680 Clause 8.3 & 8.4
label | a12326fd-5862-40f3-ad73-a4677169e5e7 |  | note | AS4506 Appendix E
label | d9f77c06-a6e9-48ee-8e69-0b2298e00003 |  | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings .
label | 7069ac07-8f96-4831-8aae-43c2de4629ff |  | note | Where damage exists, it shall be repaired using an approved repair procedure.
label | f6c8743f-baf7-4add-9ac9-c6f3ebc0e5c7 |  | note | METHOD: Visual
label | 93956f1b-4a0b-4695-9628-a13eea5b3bac |  | note | FREQUENCY: Each component
label | b47be97c-71d6-40ec-8818-5ef2593a0bfa |  | note | CATEGORY: IP
label | 39d80471-79c9-45e1-bf39-665695d2055a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8e10dcc6-f5c5-488e-a6a7-41fd888ea76c |  | note | VERIFYING DOCUMENTS: This ITP
text | 3e52737e-5713-4f68-bae9-485a050aa00a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | b7347ea4-383d-4d30-979a-eaa90dec6f81 |  | note | REFERENCE: IFC Drawings
label | 0ed92d9c-26a8-4848-88a7-1f0fa3b9e6b8 |  | note | Product TDS
label | d7d4688b-c8fb-4bba-87b9-f926f591cc82 |  | note | 610.28
label | fceeca48-001c-4c33-9b55-9d63d208e177 |  | note | 610.33
label | 7eea0992-1749-476e-b72e-92fdc1f6ff90 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | 28ebbd6c-5bb7-49b7-8584-263901aad96f |  | note | 28 day compressive strength per sample comply with the design strength.
label | 76188b2a-219e-4728-a861-d897ae4adf78 |  | note | Attach: Compressive Strength Test Results
label | 7c7123a5-8db1-440b-a091-7a625f6e3808 |  | note | METHOD: Document Review
label | 4fd0907f-3b38-4a58-8199-e204aa3fb353 |  | note | FREQUENCY: Each cube
label | 0c158708-7996-423f-a5e4-a6ff65a55045 |  | note | CATEGORY: IP
label | 574382e9-8f84-42c0-8363-66dbc1f49580 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dd98eef6-bfd9-4386-a9cb-db7bf277318e |  | note | VERIFYING DOCUMENTS: This ITP
text | 6ac54f55-2784-4a37-8fb7-974fa13f19ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 As-built Survey
label | 5059e770-687f-4211-b884-b7bbec704616 |  | note | REFERENCE: IFC Drawings
label | 606114f0-1f95-4e33-a5c6-b11fbb55e1f5 |  | note | 671.06
label | 9baf6b69-5a44-4cbd-988c-e58254687485 |  | note | AS4100 Clause 15.3.1 - 7
label | a514014c-6ab5-4b08-9c2f-e7f87d21b63d |  | note | AS5131 Appendix F, Table F3*
label | 516e7563-152c-4774-b38c-2dfa7a4cce29 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 7c07e500-5502-4c90-99f3-f71c84db5c01 |  | note | Departure from RL = ±10mm*
label | e5c23d32-179c-4bce-a5e8-b40eb1d7b7b2 |  | note | Departure from plan position = ±25mm
label | ed2aff12-7f2e-4b03-9a91-6b970443feed |  | note | Departure from alignment = ±5mm
label | bd7eadf6-72be-4982-92c7-3b749529b4cb |  | note | Irregularities in alignment = 3mm in 3m
label | 78d670b2-e8a6-4331-ae4b-b60f9806dc6d |  | note | Variation in joint gap width = ±3mm
label | 88886655-a112-465a-955f-0a2d101b3499 |  | note | Projection of bolt = +25mm, 5mm
label | 3e733762-e86f-467e-894c-f4f91fe008d2 |  | note | Attach: Survey As-builts / Survey Report
label | 3ea5bb83-505c-40db-96f2-45d9f1ebecd8 |  | note | METHOD: Document Review
label | a281d4c8-fe33-41ae-b257-8ea894a58b5c |  | note | FREQUENCY: Each post location
label | 90f70d61-ea87-4266-838e-bba064d6badc |  | note | CATEGORY: IP
label | a373a05e-5efa-4b4c-a491-fbf5aab92190 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 252e35f0-9c17-41c1-bdd0-1ad38e1070af |  | note | VERIFYING DOCUMENTS: This ITP
text | fddf4fbd-5aed-402e-9aa4-4e239874c64a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | 87e9b031-15c3-4aa7-8b59-b80bdd347a89 |  | note | REFERENCE: MRPA Quality Management Plan
label | 86e3ad6b-bea2-4858-916d-a8fb91570e7a |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | aa14db83-f6e2-4641-ae89-4f4f8a29a0b1 |  | note | METHOD: Document Review
label | 8988be7e-5a6d-4c5a-a144-4e215efeeba4 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 3406899d-5b87-4d62-8859-487e24e556f2 |  | note | CATEGORY: HP*
label | 23ac5cdf-5f1c-4cc6-8fdb-c4ec6b55b367 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1b8119c7-bec1-47cc-942e-a9e48e094a43 |  | note | VERIFYING DOCUMENTS: This ITP
text | 23b28d35-c858-4c58-9fc5-5b22bd250857 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 6ad4a7d4-ddfe-4d26-8cef-b362e7ef1e66 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 39e74f11-9794-4284-8e50-a948fccefc9f |  | textbox | Name:
text | 5c2170dd-7a7d-4a8c-8d2c-68082e6cb0c8 |  | textbox | Position:
text | 57649ec3-a8e6-40f5-9c95-cf56ba425236 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Lighting (Supply and Install) - MTM Rev 0 | itp |  |  |  | Yes | ITP-CIV-Lighting (Supply and Install) - MTM Rev 0 | f64c706f-17f3-41bc-9f4d-b2e599a5ded3
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 9097f0c7-c8af-441d-afc5-38101ebe2858 |  | note | Document Title: ITP-CIV-Lighting (Supply and Install) - MTM
label | 2599c39b-4252-41ae-ae74-d16fe9c5bf20 |  | note | ITP Description: Lighting (Supply and Install) - MTM
label | 1230ec91-575f-477d-a4d0-dd3ba1309b0f |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 5205eef2-ec01-4b11-986e-d7d1756fab1c |  | note | Revision Number: 0
label | 600e282b-0d20-4fc8-9ad4-a52e340c1822 |  | note | Revision Date: 2/11/2020
label | db4e21d1-db81-4c34-a8a8-f382a4704214 |  | note | ITP created by: Mathew Velcek
label | 1a313e98-00d2-49b2-a6b7-3f233558e651 |  | note | ITP approved for use by: Romualdo Magpantay
label | d6c42969-0992-4764-b4c5-0cb17fb73edf |  | note | 1.1 L1-CHE-STD-059
label | b56778f7-4e78-429f-b031-63e200ca416f |  | note | 1.2 L1-CHE-STD-035
label | dffb6526-0ab6-4aee-9049-86351957b555 |  | note | 1.3 L1-CHE-SPE-155
label | 671ae12c-f4f4-4434-9f2a-f88124c98af5 |  | note | 1.4 AS/NZS 3000
label | a8b9208c-76e8-4671-a6ac-f495aa2f8330 |  | note | 1.5 AS/NZS 1158.3.1 (2005)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain and review manufacturer documentations for the supply of materials
label | c72223c6-b4ff-4664-9b98-9f203d1038f8 |  | note | REFERENCE: AS/NZS 3439.1
label | 24baf17d-0656-40e9-a7db-07a9b4aa4f56 |  | note | L1-CHE-STD-035
label | b2c4f3d6-e65a-4453-8d6d-65b2384d35e8 |  | note | AS/NZS 2053
label | cfdfda82-4ad6-4629-b333-c9c408d090b0 |  | note | IFC
label | 2d8351cc-acf1-427d-8f2f-53ff499f6a0c |  | note | Drawings
label | f5931376-87a5-461b-b558-069832cff362 |  | note | ACCEPTANCE CRITERIA: Materials comply with MTM Engineering standard Lighting and Power relevant specifications.
label | ba3055a2-df88-4b93-8f9b-ceeb0d4539c5 |  | note | All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
text | efa40a67-a23b-4ff6-9827-bbf820dea93e |  | textbox | Enter: Teambinder Material Approval number
label | cee510bb-8ae3-4de3-9626-0a477885efaf |  | note | METHOD: Document Review
label | 9e8e1f93-adac-43ee-a099-04d05e4c7b46 |  | note | FREQUENCY: Per Source
label | 0e97cbfa-db11-4512-a622-23e464d8727a |  | note | CATEGORY: HP*
label | 1c3fd888-4db2-42fb-bd60-39d6dbb0bc97 |  | note | RESPONSIBILITY: Nominated Authority
label | 02558382-974c-428b-bdb3-2f4ac7c2d727 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 0d48c3c1-ab84-4881-a491-f9d367f58fcc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Inspect supplied items upon delivery
label | 5cc66ef7-caec-4e75-b5f8-108d15fc185c |  | note | REFERENCE: QMP
label | d871c95d-8b1f-4215-ba9b-1b5b19f129bd |  | note | L1-CHE-SPE-155
label | 40b2beff-48c8-4acd-827a-9d5cfdebf239 |  | note | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
label | 91bc8974-6be5-4796-acb4-10f90d89792c |  | note | Luminaires: At the time of delivery, the supplier shall provide three hard copies of the following:
label | 8ea4e3b6-283c-48f0-bf9a-1f019ce1b3c8 |  | note | Installation Instruction Manual
label | e2081fd3-5a15-4a7e-91e3-99e39bec548c |  | note | Operation Instruction Manual
label | 7a508ef0-1b5e-472d-bcbf-06a4e96f1247 |  | note | Storage, handling, loading and off–loading instructions
label | 6d7fadd9-38e5-415e-aa70-9c37f898e1a9 |  | note | Test Certificates
label | 0bf305e4-b360-4018-81d1-f9581bc9ec6d |  | note | Warranty Information
label | 91c8bbdf-4a40-4a6c-9696-2c4ead3df279 |  | note | METHOD: Visual /Site Inspection & Document Review
label | e0db2283-41d6-43b3-bc0a-8a5add5c17fd |  | note | FREQUENCY: Per Delivery
label | e75877e2-1b5f-4a16-90b1-e19857af54aa |  | note | CATEGORY: IP
label | dbaa6e34-9d8a-43c1-a912-dca03365d182 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0b326b86-404a-46ca-a45e-ef1a21c52ffe |  | note | VERIFYING DOCUMENTS: This ITP Attach records required
text | 880cf479-9a5b-426a-a778-63d0ba217331 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Civil Works
checkpoint-status |  |  | checkpoint | 3.1 L1-CHE-STD-035
label | 53931dfb-9d98-4e3d-b67f-e8c7db27a386 |  | note | REFERENCE: IFC
label | 7996c4f2-9c75-41cc-b549-17c4943298b5 |  | note | Drawings
label | de087da0-a4bf-4b5c-8464-59610d50e54e |  | note | ACCEPTANCE CRITERIA: Conduit and Pit Installation works are to be recorded under ITP-CIV Pit and Conduit (Supply and Install) - MTM Car Park Lighting ITP in addition to Subcontractors Checklist.
label | ab641403-61ae-41a3-886f-721110ec7122 |  | note | METHOD: Document Review
label | 5bcf992c-d80a-401e-95e0-08d97880d01a |  | note | FREQUENCY: Per Lot
label | 2c80be86-8b2b-4a8c-a35c-7715b812bfd2 |  | note | CATEGORY: IP
label | 8a656044-ef83-4183-a717-1d552cc3502d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3c2be1b3-d025-41ae-b92f-521b9b7ee5fb |  | note | VERIFYING DOCUMENTS: This ITP Attach Subcontractor Checklist
text | de28e0d7-afaf-4ab6-a8be-d76cecff28c3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Prepare the plinth foundation(Excavation & levels)
label | aacb749b-f277-461c-9a5e-4df0521bd051 |  | note | REFERENCE: Drawings
label | a4e0f5e6-d08d-4782-9d4a-9e170e9407cf |  | note | IFC
label | 619d7131-2193-4bb5-95ba-ccdf9e16b9f7 |  | note | ACCEPTANCE CRITERIA: Check levels conform to relevant drawing depending on type of pole to be installed.
label | 7cb20a28-8fb0-4943-b878-9242122a1a88 |  | note | METHOD: Visual Survey
label | 9372412c-9900-4b3b-b984-f3fd35eeaf6c |  | note | FREQUENCY: Per Lot
label | f442927b-49b7-4d1e-b4d6-c3c7e891e59e |  | note | CATEGORY: IP
label | d72b4b08-e03c-4b5c-8e28-fb7ad90e35ce |  | note | RESPONSIBILITY: SE/PE/SPE
label | 5082e809-70f9-4c6f-8441-1ddde20b355e |  | note | VERIFYING DOCUMENTS: This ITP
text | 19f4f4ba-a3d0-455a-8572-b5ef4aec558b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Light Pole Works
checkpoint-status |  |  | checkpoint | 4.1 Installation lighting pole bases & columns
label | 4862b744-5471-41a5-b9b8-7e1aa58e184e |  | note | REFERENCE: IFC
label | d6918fbb-dcd0-4a87-90ea-d0ce93b8c275 |  | note | Drawings
label | 11c39b80-3d71-42d3-be46-9474bcb6adac |  | note | L1-CHE-STD-035
label | 70e20fb4-2585-4dc4-8726-529c7e0b14ec |  | note | ACCEPTANCE CRITERIA: Free standing platform lighting poles shall be at earth potential as mounted in ground or on structure. Light fittings shall be earthed by the earth cable from
label | e85d3aef-fbd9-47d8-9077-d4432dcb911f |  | note | Concrete and metallic poles at all new installations and station extensions that support low voltage equipment shall be earthed by an underground conductor that is connected to the earth at the origin from which the circuit is supplied in accordance with AS/NZS 3000.9.5.2
label | b9813500-d2a4-47c7-b02b-b27683dbc6da |  | note | Lighting installations shall be LED and comply with L1-CHE-SPE-155
label | b3896f2b-28ae-479a-9580-2278666a51cc |  | note | Car park poles shall be located as per IFC Drawings.
label | f0016233-f0db-4b80-9dd0-995acadde1d2 |  | note | Pole access hatches shall be orientated to allow unobstructed access.
label | 53c44c7e-bc08-4c58-b60a-987ff80ba2ac |  | note | Level formed ground shall be at each pole for access by ladder or EWP.
label | 52f54bac-0d0c-4368-8670-e55c078ec80e |  | note | METHOD: Visual / Site Inspection & Document Review
label | 6852058d-61a4-42a2-9f55-fe9107c5339b |  | note | FREQUENCY: Per Lot
label | b1692847-6266-442c-a45e-67e32579f332 |  | note | CATEGORY: IP
label | 7bc442d6-1b10-4876-962d-daa706921c89 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 64114451-5ce9-4185-adc2-2c91df2875e1 |  | note | VERIFYING DOCUMENTS: This ITP
text | cc2691df-c05a-418c-a833-4b043ae295b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Assembly of outreaches and luminaires
label | 6bf35be4-1b50-4f51-8d0d-497a8ecaf3e2 |  | note | REFERENCE: L1-CHE-STD-035
label | 4b3b125b-9dd0-4015-bc5c-3613bff4fcef |  | note | IFC
label | e87c23c0-9f80-4cca-b154-d6e7a936cbf7 |  | note | Drawings
label | f51008c7-c7c2-4ea3-abcf-0d96877aa057 |  | note | ACCEPTANCE CRITERIA: Outreach bracket to be installed to the pole spigot using the clamping bolt assemble
label | 586a4a7a-4df5-4ea4-af35-beeaad18e250 |  | note | Bracket and luminaire to align at right angles to vehicle path on road
label | ac6c8b57-52e6-44d3-ac60-2c66491cf4d7 |  | note | FREQUENCY: Per Lot
label | c077d372-6322-4142-a3ac-eaaaa522acdf |  | note | CATEGORY: IP
label | 42f6b049-b732-4e14-b32d-e0c7f00124f7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 8ec535e7-803d-42ee-96dd-7a3e6976e4cb |  | note | VERIFYING DOCUMENTS: This ITP
text | 61b95c0c-b9f1-4d73-be0d-a375bce2cb34 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Installation of lighting distribution cabinet
label | c68305de-4f91-4f1d-97bb-a784475878ac |  | note | REFERENCE: L1-CHE-STD-035
label | 8e3f5613-1e8a-4185-aaf7-d9c8c1c852fd |  | note | IFC
label | 55a01871-0035-439d-82d2-032167b713b9 |  | note | Drawings
label | 42229315-9118-4664-ab0e-f86834a8dd8b |  | note | ACCEPTANCE CRITERIA: The switchboard or distribution board shall be designed and manufactured from suitable materials appropriate to the location in accordance with AS/NZS 3439.1.
label | 3dfbc199-8525-412e-9dc5-31378e1a5783 |  | note | METHOD: Visual
label | 55d06d39-4ee1-4e05-82b7-020dd3571078 |  | note | FREQUENCY: Per lot
label | 6b1c1afe-761a-49a5-9495-39222f338d9d |  | note | CATEGORY: IP
label | 5c193b20-587b-4a65-b543-c96710795fee |  | note | RESPONSIBILITY: SE/PE/SPE
label | 0a61784a-633d-4d97-8efd-a1906ae78be9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1b6a925c-281b-41cd-af6e-e9841c0e5f3a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Installation of cabling
label | a9723a63-78b8-4332-9217-d75f2bb0a66b |  | note | REFERENCE: IFC Notes
label | 6e16826a-3dc3-497d-9dea-ad428d361148 |  | note | ACCEPTANCE CRITERIA: All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules)
label | 044591be-6540-48d6-867e-f22e4942e768 |  | note | Each pole to be cables from the pole circuit breaker
label | c1fbfb2a-a0a2-4c9d-ab89-646eafe4f76d |  | note | METHOD: Visual & Document Review
label | 50b749ef-33ae-40f9-92bf-1ec6d7102199 |  | note | FREQUENCY: Per Lot
label | 26c5ec35-55e7-44a0-a41e-336e1effc68d |  | note | CATEGORY: IP
label | 65ab7d98-b762-4273-af57-01b47fec2045 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 527590d4-cce6-42c0-9546-b80450fdb11a |  | note | VERIFYING DOCUMENTS: Test Certificate This ITP
text | 400a47aa-f91c-403e-bc2c-4842adf0e282 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Commissioning & testing
label | f27d992d-6733-4057-9263-c5915d16d9ad |  | note | REFERENCE: L1-CHE-STD-035
label | 245bc1fc-133e-4a61-9f3f-820b222b2bad |  | note | ACCEPTANCE CRITERIA: Upon final acceptance, the Contractor shall switch on the lighting installation at the distribution cabinet in automatic mode, and record the time, date and meter reading for contractual, warranty and power supply purposes and supply this record to the Superintendent within 48 hours
label | 328859b6-cfba-4f88-9ce7-05c2dc48faef |  | note | METHOD: Commissioning & testing
label | fa097e66-0407-49e2-9e9f-81ddfb3f2706 |  | note | FREQUENCY: Upon completion of each section
label | eb7cb266-710b-4b82-adaf-745006d5c481 |  | note | CATEGORY: HP*
label | 4e0dec17-2b93-4035-b029-a55f59edf523 |  | note | RESPONSIBILITY: SE/PE/SPE Services Engineer
label | c2c7e2b5-5e13-413b-b041-5571cb6242da |  | note | VERIFYING DOCUMENTS: This ITP Attach Certificate
text | d2fc4688-8907-4736-87b3-56e437ea5f9b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Labelling of Assets
label | ef901bb8-1bb4-48f3-b3f7-c69066729b2a |  | note | REFERENCE: L1-CHE-STD-035
label | 297ed795-2817-47df-8234-78e5cbc18f7a |  | note | MTM Standard
label | b4749b63-5370-4377-bfbb-fa541613f542 |  | note | ACCEPTANCE CRITERIA: Labels fixed to poles as per MTM standard. Pole numbering
label | 585fccc6-1bd7-4ace-b408-fb2838e1124c |  | note | Labelling of switchboards, distribution boards, circuit breakers, RCDs and all control devices shall be labelled as per Appendix B in MTM standard.
label | e9add75c-16e0-4189-a029-3d19fa5a5fb0 |  | note | Indelible Labelled drawings shall be permanently displayed at the point of supply. Permanent field markers shall clearly identify the extent of the EPZ locations.
label | 55e2c820-2416-40ee-ae73-888b27e1f042 |  | note | METHOD: Visual /Site Inspection & Document Review
label | 54dce4fa-1812-4de8-b278-2b00c8987d9c |  | note | FREQUENCY: Per Lot
label | 25ddbd62-9e89-40c5-888e-dc2a6c6883c4 |  | note | CATEGORY: IP
label | dc95af7b-b046-40c9-9ebd-342133028c72 |  | note | RESPONSIBILITY: SE/PE/SPE
label | be189bc7-e8ca-4b41-92f9-5c57da208a95 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0e5a558c-cc8e-45ed-89e2-172a7ebb6784 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | 5.1 Attached and verify Subcontractor conformance records/signed ITP including relevant verification sheets
label | d6aadda1-f0fd-435d-88d1-b120180f6f19 |  | note | REFERENCE: IFC Drawing Note
label | 5c861dfc-6beb-4503-8cb0-d165fd5ccfd0 |  | note | ACCEPTANCE CRITERIA: Check conformance report against project conformance criteria
label | 37c72a57-65e9-473f-877f-8143a795d0a2 |  | note | METHOD: Doc. Review
label | aedcdb87-44b4-40d9-835f-38fede409db6 |  | note | FREQUENCY: Each lot
label | 053d103d-cdab-4388-bf48-738680fa9c73 |  | note | CATEGORY: IP
label | 4ac4c22f-3689-48f6-beba-627e50a7118e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 29f5ecd9-a768-405c-b100-283944f22cd3 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach documents
text | dc90c02f-1d22-45b6-9061-49d0f54b40fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 As-Constructed Plans
label | b2a754f5-c600-46ba-9250-7bfbd0f13e74 |  | note | REFERENCE: IFC Drawing Note
label | 4fa17224-567b-4c30-b313-ecbe9d6b95ca |  | note | ACCEPTANCE CRITERIA: The Contractor shall supply to the Superintendent two copies of ‘As-Constructed’ plans along with a USB drive or other approved storage medium containing the CADD drawing files, and the same shall be supplied by the Contractor to the local distribution company if appropriate.
label | 948ae9b4-57a2-4ed8-82d7-a302bb38744a |  | note | METHOD: Document Review
label | ccc30cec-7c86-4b7a-974b-1e02734cb573 |  | note | FREQUENCY: Upon completion/ Work area
label | b118b5a6-5020-4282-ad18-5ceb1f8f74a8 |  | note | CATEGORY: HP*
label | ba2dadda-6b24-4825-8951-f504206d0072 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 42d2ec45-b488-4ca3-985e-d2ecc238ff42 |  | note | VERIFYING DOCUMENTS: Sign ITP Attach As Constructed Plans
text | a356d97a-3f66-406b-8b8f-dd36cbe671f7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Non-conformance Report (NCR) Closure
label | 62200ed0-70fe-4640-b1ef-04592ed70d64 |  | note | REFERENCE: MRPA Quality Management Plan
label | c78aa513-9e9d-4682-b2d2-75eac46c5be1 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | fa0e84d8-82c6-4917-b587-b303ed2bcfc1 |  | note | METHOD: Document Review
label | 9919ae07-5f09-4d5b-bb7d-593586c55ea7 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 6e40dad1-ebde-48c1-9807-f192909c02d2 |  | note | CATEGORY: HP*
label | 13eadf75-bc5e-4b7e-bda8-d17b3ba8d723 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3da6e3da-30d6-4b51-aed6-85e9028d98ee |  | note | VERIFYING DOCUMENTS: This ITP
text | 5e522aa1-f2fc-4e3f-88a7-4b384e103351 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 0c246129-d7d1-4933-afae-45b9d920becc |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 33904994-3243-40d9-b5f2-6215fefb9d7b |  | textbox | Name:
text | 6fe8a91b-c9f8-41a8-bf4a-f882f390a844 |  | textbox | Position:
text | 365523f4-d6d5-49c9-952d-6f5cc95c9c66 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Site Clearing and Grubbing | itp |  |  |  | Yes | ITP-CIV-Site Clearing and Grubbing Rev1 | f9008e07-2758-42aa-8500-cf96ccef8b31
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | References
label | 0dd2190e-1f9e-4a45-ba06-27c2f77b1b47 |  | note | Document Title: ITP-CIV-Site Clearing and Grubbing
label | 45fcd6d8-a7b3-4902-bad3-d8391b3b8a1b |  | note | ITP Description: Site Clearing and Grubbing
label | 1ce3e520-506d-4cae-aa79-7d6470b369e0 |  | note | Discipline: CIV
label | 57370afb-6a1d-4fbd-8ed0-1e2dea07ded8 |  | note | Revision Number: 1
label | 92d49dcf-bea7-440a-9f62-1eaab5999398 |  | note | Revision Date: 24/04/2020
label | ae0fe4f2-7043-413e-99bf-67d93d6ca615 |  | note | ITP created by: Mike Freeman
label | 8a7bf617-6c24-4e4b-b438-f5630881a964 |  | note | ITP approved for use by: Josie Pavlou
label | 22decfbb-98a0-4871-9e15-b9894411e032 |  | note | VicRoads Section 201 January 2016
label | cefbf6ce-b5d1-4b66-b229-cf6d5daf8fe0 |  | note | VicRoads Section 204 December 2015
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1-Environmental Controls
label | 29a137c0-6d08-4b09-89e8-362c1c4e06b6 |  | note | References - MRPA Environmental Management Plan
label | 6fc9e2b5-d90d-44af-b492-242f2eb4dcd3 |  | note | Acceptance criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | 74fc77f8-28ad-4270-9cef-891917f049e9 |  | note | Method - Visual
label | 3466a574-df12-424c-83c8-bcb32cb32678 |  | note | Frequency - Where applicable, prior to starting Works
label | d0acc6cf-25db-49de-ba74-2f90a0e59443 |  | note | Category-WP
label | 5bb8efed-5522-4e26-a62c-a48e35a3cce5 |  | note | Responsibility - Foreman SE/PE/SPE
label | 41ff5077-6535-46ec-b4cc-876e179d7766 |  | note | Verifying Documents - This ITP
checkpoint-status |  |  | checkpoint | 2.2-Vegetation Removal Permit
label | e2eeda8b-0703-4b96-8f01-bad37b7d6d85 |  | note | References - MRPA Environmental Management Plan
label | 6486c7be-ba09-458f-8c0d-e08f17ee65c1 |  | note | Acceptance criteria - Prior to removing any vegetation or habitat:
label | a2a532be-3da0-4f65-9597-943a1ec06a5a |  | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design
label | 0dc96946-789d-430f-99f0-19d5f9290e4d |  | note | Documents and any relevant permits.
label | 90fb9c97-98f5-4d8d-ace4-7ec37266f1c4 |  | note | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works
label | f910e52e-60ce-4623-b0a7-9192c3eccad7 |  | note | ii. fence and sign all sites nominated as No-Go Zones.
label | adc8f3ae-2464-4f69-8334-4d037abbfd80 |  | note | Attach: Vegetation Removal Permit
label | f1f27a4e-3ab8-4777-bd79-360b2a098e77 |  | note | Attach: Ecologist's Report
label | 561831a0-23e7-4dad-b924-ff19ec1b2369 |  | note | Method - Document Review Visual
label | 630e86ec-9210-4786-b870-de5614a84a18 |  | note | Frequency - Where applicable, prior to starting Works
label | 284eea83-e0c5-4d45-8b12-10b643930543 |  | note | Category-HP
label | 1b0e8062-f79e-4a23-9910-89ca05d0bfba |  | note | Responsibility - Foreman SE/PE/SPE
label | 07a0824f-76bf-4ac8-be7a-467715e73094 |  | note | Verifying Documents - This ITP
text | cb16a795-2fc3-4b1f-9d78-37007aefaaeb |  | textbox | Date Completed
holdpoint |  |  | signoff | Nominated Authority Holdpoint
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1-Survey Set-out / Limits of Work
label | a21d863d-618d-40d3-8dfa-0d79a4fdf8ea |  | note | References - IFC Drawings, 201.03
label | 82867e44-deec-433f-84af-74badbce4ba8 |  | note | Acceptance criteria - The limits of clearing and grubbing shall be:
label | 4d8c461b-290a-4164-9bb8-4e59fbde4abe |  | note | a. the limts defined on the IFC drawings
label | 38ef60c2-28fc-4469-8dfe-e7e15848d956 |  | note | b. the whole width between the outside edges of any batters, including any roundings, togther with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
label | 249bcf11-e5d1-477f-b49e-7be8b060b766 |  | note | c. no more than the width required for completion of the Work under the Contract
label | 9bd7108d-67b7-42c8-9b2e-99d0ee43ae73 |  | note | Method - Measure, Visual
label | 13b3a0dd-b079-4f00-9786-c29bca7b63ca |  | note | Frequency - Once, prior to starting Works
label | 4352c012-dba9-4b25-aa07-7a28b6a319ce |  | note | Category - IP
label | 5e715d54-d182-43fb-9b78-b62de960cd4d |  | note | Responsibility - Surveyor SE/PE/SPE
label | 5a7649d0-3d14-4ed2-9d0e-127d28881f8d |  | note | Verifying Documents - This ITP
text | 9e85d936-b9c1-45c6-8dc0-8dd6d1450954 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 3.2-Cultural Heritage and Areas of Significance
label | 87ae8a91-166a-4f60-bc86-1c10cd86614f |  | note | References - MRPA Environmental Management Plan, 201.10
label | c402acb8-278c-482b-b5d0-81092eaab228 |  | note | Acceptance criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | 2ed3b30b-b730-4227-b790-ae1e6a6bce1b |  | note | Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
label | 8287edb3-40c6-4888-bcde-0785b9ee406b |  | note | Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | f434f95f-e475-4ac9-9868-e1e81ae003fc |  | note | Attach: Cultural Heritage Report
label | 4e1037e7-53db-4442-8e6c-f1b866f0ab14 |  | note | Method - Document Review Visual
label | 518252c0-9ab7-40cb-96cd-c3c1c6e23b0f |  | note | Frequency - Where applicable, prior to starting Works
label | 4028dce0-dc71-4f1a-8676-229fa45661fe |  | note | Category - IP
label | fd62547f-fc62-4eb9-bcee-cf35788a12ce |  | note | Responsibility - Surveyor SE/PE/SPE
label | 498bf327-9711-4103-b5a2-a11dded93fba |  | note | Verifying Documents - This ITP
text | a1a326c2-c0f1-4cff-87c5-b209bd6a4989 |  | textbox | Date Completed
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1-Stripping of Topsoil
label | 88d4d33e-a055-4bb1-b826-d2d79a5e2c5f |  | note | References - Section 204.05
label | e590c85f-ddf1-4740-a597-37c62cbf54ff |  | note | Acceptance criteria - Topsoil shall be stripped for the full width of the formation.
label | 4a6a2c5d-4107-4bd2-9094-d0efeeb03ce1 |  | note | Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | 59b6c97e-e3ed-4d62-aaee-11b9842b52ee |  | note | Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | 4d0d59c4-f7f4-4152-ada7-b3b6bff7e2fd |  | note | Method - Visual
label | 9a4def3e-ec8f-44c7-a9f9-811af8de8e69 |  | note | Frequency - Each Site
label | 35f547ff-a24e-4655-90a6-88cbf6c0d9fc |  | note | Category - IP
label | 4d46ad0d-11ff-46e7-9ec0-e89e0029b72a |  | note | Responsibility - Foreman SE/PE/SPE
label | 23d64e7f-92ab-4271-bd9a-228d841432a7 |  | note | Verifying Documents - This ITP
text | a46eb09f-0c6a-4fd9-8c4e-36a81a756944 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 4.2-Stockpiling
label | 946dcd9e-a245-45ea-a40d-a8317e6f182b |  | note | References - Environmental Management Plan, Section 204.05
label | 56d333a8-474c-4a8f-9584-1525dd0135ab |  | note | Acceptance criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways. If this clearance is not possible,additional protection shall be provided. Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | 0587b6b7-20c9-473d-a6ba-113bfbf5b671 |  | note | Method - Visual
label | 3f622497-5e5e-4548-ad91-d8d402bf6208 |  | note | Frequency - Where applicable, each Site
label | 235ef78e-e704-42cd-af26-113494b3a915 |  | note | Category - IP
label | 860348a2-09b8-4b73-bd48-c4b72063ca41 |  | note | Responsibility - Foreman, SE/PE/SPE
label | 87a48164-aacd-4938-b2af-43c085b42cf1 |  | note | Verifying Documents - This ITP
text | 9e6ba0b8-4097-4b5e-9e4b-0a122f29d34a |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 4.3-Abandoned Services
label | b3d998ed-f106-44a2-8714-45ab02a29b3c |  | note | References - IFC Drawings, Excavation Permit, Section 201.05
label | d84adde5-9c11-4aeb-b4a8-efb32e06431f |  | note | Acceptance criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
label | f643eec6-8af7-4ce3-a8cc-bf673ebe51f1 |  | note | Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | f8a996f2-8ba1-4e06-b8d7-06aec35eb635 |  | note | Decommissioned services to be disposed of in a suitable manner.
label | 5e20daff-6a28-4910-b2e8-e835f1de51e7 |  | note | Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
label | d0d23877-9f68-42fb-9322-90d6e814292d |  | note | Method - Visual
label | 3b57192f-129b-4286-9943-7dc2e38019e1 |  | note | Frequency - Where applicable, each Site
label | 28680669-88e3-463b-8fbb-dcc3d1cf0303 |  | note | Category - IP
label | 2dabff08-6e41-474d-9e79-438b9386aa14 |  | note | Responsibility - Foreman SE/PE/SPE
label | 6ecb8927-d83a-448f-a7cd-3599e1f8e9a2 |  | note | Verifying Documents - This ITP
text | fa0a3ed0-15f5-4d17-a2e5-9ce7e58fb505 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 4.4-Clearing of Trees and Vegetation
label | e4707315-aa21-42c5-83cc-1d484a471fdb |  | note | References - Section 201.04
label | 6f142b39-0ee0-499a-9196-505bdd828cb0 |  | note | Acceptance criteria - Clearing work shall not be undertake outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | c988eae3-aac1-409d-8771-679fcd0633b0 |  | note | Method - Visual
label | a05e4316-aafc-43aa-ac64-a875c5a0811f |  | note | Frequency - Where applicable, each Site
label | f60ae2a2-4640-4e46-8e5f-e7bdfed65698 |  | note | Category - IP
label | 70a292d8-83cd-400c-a474-50b9df89f63c |  | note | Responsibility - Foreman SE/PE/SPE
label | 9ef31c0d-b73f-47f5-bad3-65fbb539ee34 |  | note | Verifying Documents - This ITP
text | defbecce-2012-45d8-bd79-cc872bb59079 |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | 4.5-Grubbing of Vegetation
label | 57f8ecbd-654e-4f05-9057-33ec99c23c1d |  | note | References - Section 201.05, Section 201.06
label | 80ac5d11-3a60-48bb-98fa-a8afd9b618b1 |  | note | Acceptance criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
label | 3e8a1a1a-7bc7-4324-962b-2fe4cda9351c |  | note | In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
label | f0161308-05af-46cd-a9f8-0d4c7401277e |  | note | Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
label | c1b1210a-59fd-4a67-a242-4a35e85a7426 |  | note | Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
label | 65189b1a-b823-4ef4-a898-46eadbeb516c |  | note | Method - Visual
label | 918eaede-f6d6-4302-aba2-2de75c997bb3 |  | note | Frequency - Where applicable, each Site
label | 1a28e8f1-4160-4d2f-aa91-489370f7ae1b |  | note | Category - IP
label | 446f05c5-9fc2-4a99-8b8a-1d830916b9b5 |  | note | Responsibility - Foreman SE/PE/SPE
label | 80a554db-080d-46cc-ac12-1c3f7b0fdd46 |  | note | Verifying Documents - This ITP
text | 2511281b-fee9-4be1-ad5a-bd365b147648 |  | textbox | Date Completed
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1-Disposal of Materials & Vegetation
label | 24194825-4b90-4f7d-9055-c3869d5e6a05 |  | note | References - Section 201.07
label | d7a1fa5c-9874-424a-8dc4-0c993894ab63 |  | note | Acceptance criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
label | b2eaa2dc-3d43-4fc7-8075-cebcfb9eeadc |  | note | Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
label | 0f33ecd8-4a16-469a-b647-3ea6b499f4cd |  | note | Tree trunks and large branches shall be removed from the site.
label | 6c5c5be2-8a72-4948-98d7-7764290570af |  | note | Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | 3ba79727-86e5-46d7-a511-7ba828f67f76 |  | note | Attach: Delivery Dockets (for Items sent off Site)
label | fe3b2a0f-106d-41c2-a62e-5cddaefe7c22 |  | note | Method - Visual
label | 15d05d8a-94d6-4c60-9ec5-737b8dec9db9 |  | note | Frequency - Where applicable, each Site
label | d03fa16a-afe9-4467-98ed-139e5e876a53 |  | note | Category - IP
label | 86bfdaad-60cb-49f5-81f2-8fd14995d62e |  | note | Responsibility - Foreman, SE/PE/SPE
label | 8f10db6b-2be5-49de-a2cb-24b782ee99cd |  | note | Verifying Documents - This ITP
text | f5f1d182-d85c-4f61-a128-27d61d05013d |  | textbox | Date Completed
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 5ab5f80c-8e4a-41ac-9d82-6b65b6efe63d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | ff35b538-7103-47ee-8cbf-04e99250d2c6 |  | textbox | Name
text | 83258ac8-0429-4e79-a221-7ab837317fd6 |  | textbox | Position
text | 0079383a-60c0-40b2-9eb0-74f8d688a888 |  | textbox | Date Completed
checklist-sectioned |  |  | checklist | ITP-CIV-Conduit and Pit (Supply and Install) - MTM OCS Rev 0 | itp |  |  |  | Yes | ITP-CIV-Conduit and Pit (Supply and Install) - MTM OCS Rev 0 | faaea9da-3f9d-4bff-9827-1a06b566849b
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 0f7fa7e0-af0a-42f8-af3c-42e50988342c |  | note | Document Title: ITP-CIV Conduit and Pit (Supply and Install) - MTM OCS
label | 07f90200-7770-4a4d-976e-154cbe8ba573 |  | note | ITP Description: Conduit and Pit (Supply and Install) - MTM OCS
label | b9e5e0c1-0d8c-4588-bb47-8ea4d8f323cc |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 775014d1-a8af-4f90-b7a1-a8ba71a27ecb |  | note | Revision Number: 0
label | 25b6f51c-e968-4fd8-8225-eec1b0036c27 |  | note | Revision Date: 5/11/20
label | c8baee1f-b87f-4d35-a819-bfeb12d0baee |  | note | ITP created by: Mathew Velcek
label | 6504bfaf-d9d1-42da-a940-3876b085ff51 |  | note | ITP approved for use by: Romualdo Magpantay
label | c24b82c5-b34b-4c70-b03f-72fea6219622 |  | note | 1.1 IFC Drawings
label | 33e842dc-e412-434f-a58b-f171ed12b52b |  | note | 1.2 L1-CHE-STD-077
label | 461e9f51-b4b8-443f-a6ad-e7e44a387952 |  | note | 1.3 L1-CHE-SPE-323
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Obtain and review manufacturer documentations for the supply of materials
label | d9872583-8ed3-4981-afaa-36b9fa74d0a7 |  | note | LV + HV Conduits
label | 908f43a5-07c6-4d20-bac0-c80d3f7142c0 |  | note | Communication Conduits
label | c132bf2d-cd79-4f9d-a5fb-f5794cbed4ef |  | note | Fixing and Supporting Materials
label | fd61ff07-f7a5-4f2b-8a2f-6b52cf677820 |  | note | Pits
label | 53f8d151-4a9f-4a3d-b349-7e1fd76ed291 |  | note | REFERENCE: IFC Drawing
label | 84ba71e3-1eff-4a4f-8348-61334e746d8e |  | note | Supplier Specification
label | 6af27a72-d684-4fc2-bffc-97905c0bb579 |  | note | AS /NZS 3000
label | f390f58f-34fa-4859-805a-93da15694c3f |  | note | ACCEPTANCE CRITERIA: Materials comply with relevant specifications.
label | ef525570-fb46-4d6d-8716-9840be9f7ee3 |  | note | Obtain conformance certificates and submit to the Nominated Authority prior inclusion into the works.
label | 909c7cd6-68b6-4160-9e22-897c40b20f91 |  | note | METHOD: Visual
label | e8767327-c125-4cdb-ae2d-f611a72b50bf |  | note | FREQUENCY: Once
label | a89ac65e-01ac-4e14-b3ad-e73f5abf9dc4 |  | note | CATEGORY: HP
label | b2cccad5-8e94-4b6e-9e2f-b2adfde5feba |  | note | RESPONSIBILITY: Nominated Authority
label | 6dcce7ea-4e53-45a0-a61c-31cc7c71fad5 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ef323254-c867-4776-a5ed-c4d096fe4ff0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Inspect supplied items upon delivery
label | 0774ea12-76c1-4267-a5f4-f2e53d7f7f6d |  | note | REFERENCE: IFC Drawing
label | 5b90467d-7dd2-400d-8ec2-610ba9329bf3 |  | note | Supplier Specification
label | b5a9adb1-eaf7-45d1-a5cb-7478472ecd26 |  | note | AS /NZS 3000
label | aa4681e4-5b76-4ab1-b012-5bbeaab41eba |  | note | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
label | 12e95d9e-161b-405d-85f5-2f3da0fcab35 |  | note | METHOD: Testing
label | 4931b3c2-c507-4331-a087-bf9b88f63828 |  | note | FREQUENCY: Once
label | 223154db-c898-4fae-91a7-31789bd4543b |  | note | CATEGORY: IP
label | dd00efae-a8d4-4a15-9d10-eb6a71ddbf7c |  | note | RESPONSIBILITY: Electricians Site /Project Engineer
label | 0ed023b6-f5a6-45a1-9151-a4f1f184c9a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 75833fd3-d369-4d62-ae61-1d303ace576e |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Pit and Trench Excavation
label | 9887f534-b44a-4bbc-88b7-c38e40a7a1d0 |  | note | REFERENCE: L1-CHE-STD-077 - cl 6.10.1c
label | ba9ecfbf-7402-4d19-a7ab-253dd7e351d2 |  | note | IFC
label | 67f0c897-f43b-4312-9d99-74f750b5d537 |  | note | Drawings
label | c5225160-bf30-465c-b320-6920ea8c198c |  | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
label | 953552ca-2405-4caa-8978-ba706bb60ad9 |  | note | Over excavate by a min. 50mm to allow for bedding and a min. 50mm wider to provide clearance from the outermost conduits.
label | 6a4bf9ee-2398-4fd5-ba53-d05da97c064c |  | note | Where the conduits run beneath a road, provide a minimum cover as per detail on drawing (Min 650mm below finished paving level).
label | eb25b77f-9159-48b7-8913-98771a6bb555 |  | note | METHOD: Inspection
label | b59501e8-4618-43d7-9d2a-e6852c93ee9d |  | note | FREQUENCY: Each Lot
label | e6f0de94-0656-4d50-b253-7ec2a10e7885 |  | note | CATEGORY: IP
label | 462e1cf4-4f0d-4435-950f-c5cf3d53e747 |  | note | RESPONSIBILITY: Supervisor /SE/PE
label | 683cfb40-ed05-466d-87b2-d3d26387be37 |  | note | VERIFYING DOCUMENTS: This ITP
text | 532f2884-d8b1-4e1f-996d-29ff290b15ef |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Installation of Bedding Sand and Conduits
label | cbdfa3d1-ee81-4448-b666-0b196cca3f77 |  | note | REFERENCE: L1-CHE-STD-077 - cl 6.10.7a
label | abc61f8f-fad0-44bf-972f-81725cbd226c |  | note | L1-CHE-STD-077 - cl 6.10.7d
label | 9a8921f7-58e9-40e9-989d-b3c6fa6c2ef1 |  | note | L1-CHE-STD-077 - cl 6.10.7e
label | d65e9815-4518-4ee3-bc51-9f6d55472956 |  | note | L1-CHE-STD-077 - cl 10.5.3b
label | c0be4871-aa3c-493e-8ec5-607b58fde483 |  | note | IFC Drawings
label | 23f88f52-3a00-42b6-a820-b89af7aba613 |  | note | ACCEPTANCE CRITERIA: Install a min. 50mm compacted sand for bedding if not shown on the design drawings.
label | d71b3ea2-b207-4c46-a0b2-f9ba665bd817 |  | note | Installation of the conduits to be in accordance in the design dwgs. Lay the conduit on a straight grade and line
label | b70ac2a1-488b-4cb3-a07a-c250c9537f82 |  | note | Backfill the conduits with bedding sand and compact 50mm above conduit.
label | eb92f197-7eab-4e0d-963e-7eff8c4e11c4 |  | note | Inspection of installed conduits, bends, pits, trench bedding and drainage (prior to trench backfill)
label | 287a32d8-f395-42ba-b8df-6f2d49927c34 |  | note | METHOD: Inspection
label | 8119eff0-db98-45e8-806c-8e163c708bf7 |  | note | FREQUENCY: Each Lot
label | 6e94a4cd-b81c-4dba-b4ab-f3a05b24db78 |  | note | CATEGORY: HP
label | 40494421-9e69-48ba-b237-e0de41176f3b |  | note | RESPONSIBILITY: Supervisor /PE/SPE MTM Rep
label | 3d9c23c6-bd59-4dbe-8e1d-5ca617a0aff7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 82ed6430-a23f-4d21-8929-1115e689709c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Conduit Installation
label | 8d95a331-ad91-4d5e-bc77-ea396b427c13 |  | note | REFERENCE: L1-CHE-STD-077 - cl 6.10.8a
label | 99112351-da72-4e05-96d8-ab9d74d59667 |  | note | IFC Drawings
label | ac4d5214-6f03-41b8-9c9a-8a8cc3932391 |  | note | ACCEPTANCE CRITERIA: Location of each conduit is as per Design Drawings
label | 57121032-a881-4250-b8a3-5ce9328ba19d |  | note | Conduits are inline & positioned evenly
label | bacfcbbb-0598-45ea-a0f9-4aa88aa2051e |  | note | Conduit joints shall be watertight and installed to manufacturer’s specification.
label | 449ac820-a1f9-4ce8-8a48-1425f4bd4258 |  | note | Conduits to be glued shall be cleaned and coated in glue
label | 8ad774ca-52d6-4393-9a3c-74545c2339fe |  | note | METHOD: Inspection
label | 8d9a1a62-d621-4b0d-8d41-79180c462916 |  | note | FREQUENCY: Each Lot
label | 2d1ce3c0-e7ad-43ae-8bea-6b0db6f13bb8 |  | note | CATEGORY: IP
label | 0e73fb86-3634-48ce-b989-503891eda7f4 |  | note | RESPONSIBILITY: Supervisor /SE/PE
label | 34cbfa33-0dfe-476e-9bc9-705fcea7ba8e |  | note | VERIFYING DOCUMENTS: This ITP
text | 3b4f8b61-5372-4fd4-941d-0166dabdda51 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Nomenclature Requirements
label | 0564b81b-5b4d-4d74-aad6-087ad2da60cf |  | note | REFERENCE: IFC Drawings
label | 6f00ae8d-cc88-4a6e-a221-112108421014 |  | note | L1-CHE-STD-077 - cl 8
label | c8782765-bb4a-4a79-8e9b-ab93cd2ae6e3 |  | note | L1-CHE-SPE-323
label | 73095f4a-a7f5-48e1-8be9-1175a2a76d62 |  | note | ACCEPTANCE CRITERIA: All site conduits shall be allocated an identification number of the form as detailed in L1-CHE-SPE-323
label | 13355bef-c33b-439a-b379-00623c09ac93 |  | note | All pit lids shall be identified “Communications” and shall be fitted with engraved or punched metal labels showing their assigned pit number
label | d4fa2818-33b1-431e-b085-d46d5d3cd5bc |  | note | Refer to the relevant IFC Drawings and references for further detail.
label | a67fe7d8-a062-4331-8805-d6f299415c74 |  | note | METHOD: Inspection
label | 6b0cc235-1548-4ed7-b854-209f4fd48d0d |  | note | FREQUENCY: Each Lot
label | 09e7e352-953d-4938-8ed4-077f43eb3e91 |  | note | CATEGORY: IP
label | c0831f2b-e286-447a-a131-c53c4f4f6b37 |  | note | RESPONSIBILITY: Supervisor /SE/PE
label | 63721e06-5781-4317-a5bb-3ed3d0cff9a8 |  | note | VERIFYING DOCUMENTS: This ITP
text | fa4ffb9e-d9f4-4b78-9069-057069fd7437 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Backfilling
label | 4e83b559-2718-4508-8718-9eb422f6b3c3 |  | note | REFERENCE: L1-CHE-STD-077 - cl 6.10.7
label | 2eee1b3a-6848-49e0-9ab6-6ed0deac68d4 |  | note | ACCEPTANCE CRITERIA: Backfill remaining trench with excavated material or nominated backfill material
label | 215db682-8c5b-4f7f-a63d-c5dfde143bd3 |  | note | Backfill to be placed and compacted in 150mm layers.
label | 04945975-06e8-4e52-9a7b-94f475f2f51b |  | note | METHOD: Inspection
label | 92dcd35b-a23d-455d-b057-09e0a0ad6e16 |  | note | FREQUENCY: Each Lot
label | 62dec04d-383b-4773-8a85-4ea5f57efbe9 |  | note | CATEGORY: IP
label | d77fe71d-9a9c-4308-91e5-3dbf2630058a |  | note | RESPONSIBILITY: Supervisor /SE/PE
label | e2350c98-bf1f-4a0f-a21e-f920876fb470 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8176ddae-aa97-4cbb-adeb-310a34a389a1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.6 Marker Tape
label | ae3fc595-a13c-4cb0-940d-8cc77d24e177 |  | note | REFERENCE: L1-CHE-STD-077 - cl 6.10.7e
label | 556ad038-1d64-4019-a89b-3f22c98bdcce |  | note | IFC
label | 42146952-69ee-4fe7-8411-75a888a6d79e |  | note | Drawings
label | 943b5ae4-ecfb-4c25-b460-4b2186e383f1 |  | note | ACCEPTANCE CRITERIA: Marker tape to be installed in a layer between 150mm and 300mm below finished surface level or approximately half the distance to the conduits cover
label | 12b79cfb-7a23-4350-9201-0936905dc506 |  | note | METHOD: Inspection
label | e3f9038b-4f17-4402-98ce-cce58c4c1e37 |  | note | FREQUENCY: Each Lot
label | 3738d7da-3cc9-4619-b27f-1a335aa261e9 |  | note | CATEGORY: IP
label | db572e18-231a-4742-804c-14ccc4d17251 |  | note | RESPONSIBILITY: Supervisor /SE/PE
label | f19c7c57-7300-4232-b620-8d8e840a5290 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4a8311a4-31ba-41a1-a678-2d8aeec89a5a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Install draw-in rope
label | e9646eab-96e1-4020-9860-29afce65eca9 |  | note | REFERENCE: IFC
label | b1c05afc-b3ac-41a6-9ec6-da4c0dbe99f7 |  | note | Drawings
label | 97758dd9-eadc-4849-abce-0fc252e039ab |  | note | QA & Work method of statement
label | 4ce6632b-072e-4154-8dd1-b9295d912c66 |  | note | ACCEPTANCE CRITERIA: Polypropylene draw rope to be installed in all conduits.
label | 4e173d90-a82a-4779-a5d3-ba795128faa4 |  | note | METHOD: Inspection
label | 8a4b62fb-2f63-4a66-8566-e5dc5d473d38 |  | note | FREQUENCY: Each Lot
label | cf4cdb33-06a0-4859-8e2e-bf6c8c13f80c |  | note | CATEGORY: IP
label | 629a29b0-021a-4ad0-b3b6-eef3f2ba20bd |  | note | RESPONSIBILITY: Supervisor /SE/PE
label | 327df8e1-2cdd-4bdf-802b-8b470c55ddd0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 575428a6-2189-4960-bf73-1498c931afa9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.8 Installation of OCS Pits
label | f6587492-d42c-4fd4-ba53-c8565e231d13 |  | note | REFERENCE: L1-CHE-STD-077 - cl 6.9.1a
label | b111f6e3-35f0-464d-972b-6346545ee3a7 |  | note | L1-CHE-STD-077 - cl 6.7.3
label | 826c0205-5a5b-40f8-b7d3-d596ae4f267e |  | note | IFC Drawings
label | 02f38fab-da96-45ca-9796-bd9cd8547fa3 |  | note | ACCEPTANCE CRITERIA: Correct pit as per the IFC drawings
label | 1a9f366a-095d-46fd-9dd9-c0eaeeb2e80e |  | note | All pits to be locked with F07 Barrri Bolt
label | 655db444-e154-405a-8937-e9e49821fd8f |  | note | All OCS pits shall be installed outside vehicle traffic areas, parking bays and vehicle overhang when parked to allow 24/7 access.
label | 70be8260-adf6-4b0c-973a-c4856ddfaadd |  | note | Pits in trafficable areas shall be provided with Class D “gatic” locking lids and load bearing concrete surrounds, and be finished to match the paved surface.
label | aa0e26ae-c994-48b2-9a22-d36ad7bef792 |  | note | Pit to be bedded on 20mm aggregate at 150mm depth.
label | aef5f1c6-bf33-4b64-8114-bcac080afd45 |  | note | Over excavation required to install the pit and conduit to be backfilled with 20mm aggregate material.
label | 515f02b1-1382-4ff1-9850-86f36a93f8d4 |  | note | METHOD: Inspection
label | f6c12e6b-3846-4cf1-95e4-fad400d902e8 |  | note | FREQUENCY: Each Lot
label | 05fb56b2-6783-493a-b9e0-93ed40605ed2 |  | note | CATEGORY: IP
label | d13f768d-440d-432c-95ac-2c1512252a18 |  | note | RESPONSIBILITY: Supervisor /SE/PE
label | 16941f19-835d-49d6-84da-5a05b91a8d36 |  | note | VERIFYING DOCUMENTS: This ITP
text | d298088f-12a1-4fc9-9ab6-6fa9729db96b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.9 Mandrelling
label | 34c85133-69d9-471a-b74f-b1dbb25f2021 |  | note | REFERENCE: L1-CHE-STD-077 - cl 6.11.3
label | 80b7565a-752f-4e70-a76b-b527b641407f |  | note | ACCEPTANCE CRITERIA: After cleaning the pits and conduits, every conduit shall be tested using a mandrel of at least 90% of the conduit inner diameter and length of at least 1.8× [nominal conduit inner diameter].
label | a1cab543-e7f1-40b4-bc74-9f75ad72c8da |  | note | To be witnessed by an MTM Representative.
label | 3a01980a-138c-4b52-8475-bc7cfb80b011 |  | note | METHOD: Inspection
label | 2c214d4f-3772-41e2-b3db-4b0c587b116b |  | note | FREQUENCY: Each Lot
label | 57a45514-d1f4-473d-aef3-bf1346d83a16 |  | note | CATEGORY: HP
label | 396001a3-1c6a-4068-bab8-77efd8ba480c |  | note | RESPONSIBILITY: Supervisor /PE/SPE MTM Rep
label | 83d1766a-2e6b-4f65-a035-7147a8df6c3b |  | note | VERIFYING DOCUMENTS: This ITP Attach Mandrelling Test Sheets
text | bb725e3d-e1f9-49f3-a10a-9566b896465c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.10 Commissioning Tests
label | 2d50cea0-3986-4302-b511-20c4f1f97b59 |  | note | REFERENCE: L1-CHE-STD-077 - cl 10
label | 65626ec2-0aca-412f-83b3-489d0e6d045f |  | note | ACCEPTANCE CRITERIA: Commissioning and acceptance tests are to be conducted by the MTM OCS construction site supervisor or nominated representative.
label | 136be287-7d29-4770-b368-2b2241bc167a |  | note | Refer to L1-CHE-STD-077 - cl 10 for details on the Commissioning and Acceptances Tests.
label | 1cd0cdbc-2fd5-4841-af3a-3945c81a4465 |  | note | METHOD: Inspection
label | fd9d6018-75c7-4e34-8163-f914e364c79d |  | note | FREQUENCY: Each Lot
label | 0c0dd8c5-3523-4acb-b459-c0de0a31aeb4 |  | note | CATEGORY: HP
label | 2689c178-a7dd-4188-bf5b-40aeac3ffeda |  | note | RESPONSIBILITY: Supervisor /PE/SPE MTM Rep
label | 3aeb8368-502f-4a30-b3ee-f5f4a4288ce3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 27eacfa6-dd4d-4ca3-8c0e-858ce6a4fdba |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | As-built Survey
checkpoint-status |  |  | checkpoint | 4.1 As-built Survey
label | c72214fb-d4dc-4f6d-8fa9-a03292f98295 |  | note | REFERENCE: IFC Drawings
label | 98b2b893-b5e3-4bd9-8bfb-b1ec79b78145 |  | note | L1-CHE-STD-077 - cl 7
label | 9fcf382f-522b-47f4-90f4-2dbaf811b28b |  | note | ACCEPTANCE CRITERIA: Attach: Pit schedule - a table listing every pit ID together with its manufacturer, lid and base model, and location easting and northing measured via differential GPS to accuracy better than ±100 mm.
label | 54471ec7-6128-462f-ae88-8f191b2ffdfb |  | note | Attach: Conduit schedule - a table listing every conduit ID, its start and end depth and length (to an accuracy of better than ±1m).
label | 91b7e4df-914f-4e8a-adc4-02b7c283356e |  | note | Records shall be supplied electronical in both native editable and PDF formats
label | 85bc7aff-09a0-4123-81f2-15646b408d45 |  | note | METHOD: Survey Document Review
label | 84372cba-7dcf-4627-9f68-6b50040311e2 |  | note | FREQUENCY: Per lot
label | 8bf7e3a4-ff64-4731-b22f-fdfc41a390e5 |  | note | CATEGORY: IP
label | 0353c501-07b9-49c8-b460-b2dd37a7a471 |  | note | RESPONSIBILITY: SE/PE
label | 3e0b1529-a381-4a2a-9fb3-7d68e1001bb5 |  | note | VERIFYING DOCUMENTS: This ITP Attach Pit and Conduit Schedules
text | 0a98068c-8000-4292-b1d2-61bdc1402b78 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 1640da38-e507-43f0-80b2-d99b7afa9c8e |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | cbd3ddda-add4-488b-afdf-0c8b1bb33eff |  | textbox | Name:
text | 2bd0cafd-f861-4ba4-90dd-8dc22aaa3a5c |  | textbox | Position:
text | 854a2e80-c2c1-4268-9ec3-fa3c08859949 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Clyde Rd Bridge Expansion Joints & Waterproofing (Supply & Installation) Rev 0 | itp |  |  |  | Yes | ITP-STR-Clyde Rd Bridge Expansion Joints & Waterproofing (Supply & Installation) Rev 0 | fab845d5-0205-4ef6-91a0-db946ff8f57c
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | ee1109eb-d0d5-42d8-b80c-c4d32d8a83f2 |  | note | Document Title: ITP-STR-Clyde Rd Bridge Expansion Joints & Waterproofing (Supply & Installation)
label | fcdaed39-de4e-4e94-bb32-e5a638387f1d |  | note | ITP Description: Clyde Rd Bridge Expansion Joints & Waterproofing (Supply & Installation)
label | 013355d2-b8db-4046-b9a6-6ddbed638283 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | bf102c4b-34df-4e4c-8e48-f5eb4f6aca83 |  | note | Revision Number: 0
label | a3957440-ff33-487a-a706-d25239ef586c |  | note | Revision Date: 5/01/2022
label | 71e444e7-0a7b-427c-bb75-9775ca36abdd |  | note | ITP created by: Justin Kreinberg
label | a4497fce-e333-4d65-9572-7ea172e40a2d |  | note | ITP approved for use by: Victor Mira
label | 3608ca00-d213-4682-b973-139facdca62c |  | note | 1.1 VicRoads Section 660 January 2018; VicRoads Section 691 November 2018
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Expansion Joint Design
label | 1ef4ff74-0b75-4a91-b9fd-bbd3fba97cab |  | note | REFERENCE: IFC Drawings
label | 7a354c0e-dd96-4ffd-8c16-72d88e408e35 |  | note | 660.03
label | 64f93410-f699-4d6d-94d0-14ac0dcccd26 |  | note | ACCEPTANCE CRITERIA: The expansion joint system shall match the drawings.
label | 9d362ec9-a935-4fcf-bcbd-c364889562a3 |  | note | Where an alternative product is nominated, the following criteria shall be met and information submitted, (where applicable) and approved by the Designer (for Design & Construct) or the Nominated Authority (for Design only):
label | ae7f56ea-4e16-4278-bb88-33d41c8510dd |  | note | i. details of provisions for inspection, maintenance and replacement
label | 940fa62c-4b3c-4c56-a693-379c3928541e |  | note | ii. anchorage system details
label | 3eea00ad-ad26-4ede-9a04-9d8f186889be |  | note | iii. geometry for casting block-out
label | f3ea1551-7283-4282-b2fd-fef50e0066f7 |  | note | iv. product shop drawing or similar
label | 1dcfbeca-5fc6-4ad9-ab0d-08fe3d3201b7 |  | note | v. treatment at kerbs, pedestrian footpaths and barriers
label | ef6c077c-4a73-4028-ad29-2874f9d52673 |  | note | vi. alteration of reinforcement and/or embedments
label | a7359e55-3926-4ce6-8cda-48ca7b4ebcfd |  | note | vii. details of nosing material, adhesive, backing rod, sealant and seal
label | 8e1262e0-a019-47c8-acb6-4628232436e7 |  | note | iix. evidence of satisfactory performance and durability of the product under equivalent conditions
text | 4831d265-de9d-4c15-9e8c-20733743eded |  | textbox | Enter: Teambinder Correspondence
label | 4a2f5d3b-81de-4c1d-9c88-660ea5bb963b |  | note | Approval or RFI number
label | f0b5a4cc-add9-470f-953b-7b463de232bc |  | note | METHOD: Document Review
label | 72fa77aa-754f-4300-b8fa-e913fadf3315 |  | note | FREQUENCY: Where applicable, once, within 4 weeks of acceptance of tender
label | bece15fd-7635-49b3-8ff9-61d9ad098715 |  | note | CATEGORY: WP
label | a5fc7853-a90e-48f1-b49b-7ff309025fea |  | note | RESPONSIBILITY: Nominated Authority
label | 6d9cda06-0975-4d6d-8230-bf7d3c939ca3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 51be9a37-6dc8-4a9d-9b8e-7751d4743f93 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Expansion Joint Components
label | b56a3a30-fac0-4d48-b1d9-4fcb3ca35357 |  | note | REFERENCE: IFC Drawings
label | c32c4426-55dd-47e8-aad0-786c5478477b |  | note | 660.03
label | eceb8094-8b8d-41b6-8678-4ba36c3bab23 |  | note | ACCEPTANCE CRITERIA: Where applicable the joint material shall match the drawings or be an equivalent product
text | 50e7e4da-e2e9-4088-bed7-80d10250c72d |  | textbox | Enter: Teambinder Material Approval number
label | 027d92c0-e30b-4163-aae8-111375bd9abf |  | note | METHOD: Document Review
label | c63e9670-b1b8-40cd-9a4c-75b01a4bcf5e |  | note | FREQUENCY: Where applicable, for each element
label | f76b5d61-2741-442f-ae10-124503d180b3 |  | note | CATEGORY: IP
label | 27fb352e-c093-4fd3-bcb9-50bc499bf10c |  | note | RESPONSIBILITY: PE/SPE
label | dfe6aaed-2901-4cdc-934e-7fe3fa9e67ed |  | note | VERIFYING DOCUMENTS: This ITP
text | 6f5c587f-6c68-4a2e-b82e-ff242ef514e2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Expansion Joint Sealant
label | 77fe0a0d-c110-4417-91a6-1c7655d6564c |  | note | REFERENCE: IFC Drawings
label | 11b5d27c-b814-4084-9c2c-d703e79f55b4 |  | note | Installation Manual
label | a7b0966c-d4cf-433a-8381-4c5239bbfba4 |  | note | 660.04
label | 7e8f9491-8520-4e1f-aef1-55fb8ef56adf |  | note | ACCEPTANCE CRITERIA: Where applicable, the joint sealant shall match the Drawings and installation manual or be an equivalent product for trafficable uses.
text | fae43183-6ac2-4cb0-a118-e3c635d4e82c |  | textbox | Enter: Teambinder Material Approval number
label | 0a461734-9527-46ae-aa01-478fb261bfb7 |  | note | METHOD: Document Review
label | 21944950-98d3-4e9d-822e-cbcadf81377b |  | note | FREQUENCY: Where applicable, once for each product
label | 60ff56b7-23a2-482f-9f9a-8593bc4e0926 |  | note | CATEGORY: IP
label | 0e92c5f5-cad6-4cf9-8122-69b25620a6ab |  | note | RESPONSIBILITY: Nominated Authority
label | 35250d46-bf11-4dff-8a70-fd139c2792b3 |  | note | VERIFYING DOCUMENTS: This ITP
text | a85e86b5-de99-47f0-a6c2-70ede3ce3fe9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 FRP Cover plates
label | 0bd776c0-ca39-42d2-9170-5da60b931eb8 |  | note | REFERENCE: IFC Drawings
label | 0cda1674-fb52-4a54-9526-c62a198bf9fe |  | note | MRP-016-C-ACD-DRG-16-NWA-CBR-1687
label | 1423ce54-31f9-46ce-9574-307a6e40d54d |  | note | ACCEPTANCE CRITERIA: FRP Cover plates to meet the following properties:
label | 3faf34cd-1d2c-4499-9283-2e07cf3689f9 |  | note | Tensile Strength (Length way) 207 Mpa
label | 1cf4b1c0-9712-46cc-af1d-e165406dc207 |  | note | Tensile Strength (Cross Way) 48 Mpa
label | 3f81521d-c400-48d2-a5f5-135968c21905 |  | note | Flexural Strength (LW) 207 Mpa
label | c91ef921-83c8-4643-bd4d-351f47714ad3 |  | note | Flexural Strength (CW) 69 Mpa
text | f94eee4b-5a2f-40a6-8933-52675a23b6fb |  | textbox | Enter: Teambinder Material Approval number
label | 8c75e01a-a5ef-4cb5-aee5-63df0f2551d2 |  | note | METHOD: Document Review
label | e8d59640-32cc-425f-8089-de88a72d44fa |  | note | FREQUENCY: Where applicable
label | 0b0f6fb6-be52-4f6f-abf9-aeffd21ce019 |  | note | CATEGORY: IP
text | 06f8cdf0-039d-4328-9123-f68195c62f99 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Waterproofing System Materials & Procedures
label | c47f8517-ca47-4885-9498-c5e7f268690f |  | note | REFERENCE: IFC Drawings
label | 480e7f42-559a-4f7f-adc3-7743ab5bdd8c |  | note | Installation Manual
label | a88283ba-4c67-4a28-8f86-09e9786a4078 |  | note | 691.04
label | c64670f7-d9c7-4a50-bf5e-9cac110754dd |  | note | ACCEPTANCE CRITERIA: Details of proposed procedures and surface preparation in accordance with clause 691.08 to be submitted for review to the Nominated Authority.
text | fbff5c2d-9efc-45bd-a346-3c85ea8f2d1a |  | textbox | Enter: Teambinder Approval Number
label | 465c10c6-6ce2-4b00-9c7e-f56cabe2587d |  | note | METHOD: Document Review
label | f82fc22b-0140-482c-9543-d7a5c23a1ca4 |  | note | FREQUENCY: Where applicable, for each element
label | 46891402-2444-4e5c-9a5b-8709ec25edf3 |  | note | CATEGORY: HP
label | 28af184f-a498-4475-8f76-171bc14ad18e |  | note | RESPONSIBILITY: Nominated Authority
label | d8e6410d-c2d2-41db-aac2-b9708a1b97df |  | note | VERIFYING DOCUMENTS: This ITP
text | 80850af5-936d-4a8a-aa13-13a228f2651b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Waterproofing Membrane System Materials
label | ee8a160d-3a6f-4518-838c-f9aa410cc614 |  | note | REFERENCE: 691.05
label | 04cf7424-edb2-4316-9477-cea907e4c2f8 |  | note | ACCEPTANCE CRITERIA: Details of waterproofing membrane materials in the form of a guarantee confirming that the waterproofing system and materials comply with the requirements of 691.05, to be submitted for review to the Nominated Authority.
text | 9fe66e7f-d9e5-444c-96a0-a409a1a139a5 |  | textbox | Enter: Teambinder Approval Number
label | 4784841c-a30a-4ea5-805b-252af2216935 |  | note | METHOD: Document Review
label | 1306e7e0-8393-44e1-a769-0516cd122714 |  | note | FREQUENCY: Where applicable, for each element
label | 7d2de3c7-ca4a-4893-a8fa-ce51cb92db86 |  | note | CATEGORY: HP
label | bbb72997-909b-4672-abd9-5a1e4beefcfd |  | note | RESPONSIBILITY: Nominated Authority
label | efcc9f36-dc72-4146-ae4a-5c6b4f66e20b |  | note | VERIFYING DOCUMENTS: This ITP
text | 63592a5e-1059-4415-9e21-f1bc239becfb |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Waterproofing Membrane System Materials
label | 9aee193b-7f4a-407d-bcd8-3eaafce95163 |  | note | REFERENCE: 691.07
label | 1d04d50d-fcc1-46ca-afcb-fc5f46cc237c |  | note | ACCEPTANCE CRITERIA: Submit Certificate of Conformity, including all relevant test results shown in Table 691.071 and Table 691.072, verifying conformity of the supplied materials for every lot/batch delivered, to be submitted for review to the Nominated Authority.
text | 9753bfe2-557b-4cae-85bb-2802985de7dd |  | textbox | Enter: Teambinder Approval Number
label | 8b0dcf6f-f3cf-486c-84bd-1b4169fcae03 |  | note | METHOD: Document Review
label | acbaca42-cbd7-432f-9b3d-7e76bd06bf01 |  | note | FREQUENCY: Where applicable, for each element
label | 33271aec-e83f-48ad-a4d7-b7836ee56a44 |  | note | CATEGORY: HP
label | 69af5d71-83fd-4c01-a259-e935441ae6c9 |  | note | RESPONSIBILITY: Nominated Authority
label | a565d7ab-b59f-4824-bfe6-9765995db6a5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3f980846-0442-4616-84b3-bc3ba36683a7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 3.1 Expansion Joint Installation Temperature
label | 88afd05e-dd84-47f5-8725-289a6d2ba7c0 |  | note | REFERENCE: 660.04
label | 9dd87583-21bb-4b06-9627-711aec373dbe |  | note | ACCEPTANCE CRITERIA: The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers.
label | 8d5919fb-0785-475f-9b19-7d3b6792cf2d |  | note | Planned pour time to also be within this temperature range or adjusted.
text | 1d4e2aad-7a29-4fcb-bbe4-b2d66e2e9c6d |  | textbox | Installation Temperature
label | 562136e7-4af3-4dc1-a881-d88bf9b91f3d |  | note | METHOD: Measure
label | d87dbb09-3bf7-4918-a229-328d299d64e4 |  | note | FREQUENCY: At the time of installation
label | c06e6dc1-8e25-4208-9856-377ff66ca5ef |  | note | CATEGORY: HP
label | 8256ab39-a39b-4195-8537-ea6cdc35bd25 |  | note | RESPONSIBILITY: Nominated Authority
label | 9cd21cc1-7adb-45ba-9a26-47be354e51b3 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 82f66b6c-1c82-43bf-80ee-4648bfa26272 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Post-pour Inspection of Expansion Joint Bearing Surface (Vertical Faces)
label | 5c4a73f3-34a7-40a7-9183-0af547d7322f |  | note | REFERENCE: 660.04
label | 466eeb26-9e26-4bb8-9306-a7bcd0ddef2d |  | note | ACCEPTANCE CRITERIA: The vertical faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
label | 6283d6f8-1542-46ca-95d8-0546e833a61e |  | note | If voids are present:
label | c63e0351-78b7-4d2b-bea2-50bcd8338d7f |  | note | Complete: Cementitious Patch Repair ITP
label | c628e583-0858-4800-90cf-15687105e33d |  | note | METHOD: Visual
label | bab4418d-ddf5-440b-a250-d5dfeec3d836 |  | note | FREQUENCY: Prior to joint sealant (where applicable)
label | dfc32b6a-eabf-4a21-8900-a23bdd87a347 |  | note | CATEGORY: HP
label | dbf78796-0f4e-4b2d-be07-e66b7f659117 |  | note | RESPONSIBILITY: Nominated Authority
label | 6e6e9412-3684-4ed1-a665-497516fddbd9 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 5ff6aadc-e821-42fa-9c44-4b1d66a456b8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Surface Preparation of Waterproofing Membrane
label | 6dd83e79-765a-425f-919a-588d38310589 |  | note | REFERENCE: 691.08
label | 1cfba70b-75f1-4d9c-b374-ee255afc45e3 |  | note | ACCEPTANCE CRITERIA: Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles.
label | dbc85e83-dcab-4f99-9dbc-c521cbe04bf3 |  | note | If the surface of the concrete is weak, honeycombed or characterised by loose surface layers more material shall be removed, and repaired in accordance with Cementitious Patch Repair ITP
label | 268a0756-8ffb-4386-abae-8070268d4506 |  | note | METHOD: Visual
label | 2394ac3a-483c-433f-931e-432257a4063d |  | note | CATEGORY: IP
label | bda38aa3-2641-42bb-bfaa-5f6095d79a76 |  | note | RESPONSIBILITY: SE/PE
label | dd4bdb21-27be-4633-b750-cdeb89220173 |  | note | VERIFYING DOCUMENTS: This ITP
text | 45123356-27ca-4c3a-a0d1-cc8118d3c0ed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.4 Material Handling and Storage
label | 2171829d-9006-4ee6-b055-cfbb27554936 |  | note | REFERENCE: VR 691.15
label | dd150edc-bc25-4b7f-8880-168e7977744e |  | note | ACCEPTANCE CRITERIA: All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers.
label | b5f49052-ce3d-42e9-a054-7cb739f4ca4f |  | note | The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming:
label | 0f97ed05-4a7c-4e7c-bde5-a8bbc7fb30c5 |  | note | (a) manufacturer’s name and address
label | ff84aa7e-5257-4542-a24c-d1d8d4efaefb |  | note | (b) product reference
label | 24054681-d058-4243-98e9-e245b310bb51 |  | note | (c) batch number of identification
label | a4f4f331-a997-43f3-aaf6-195f820c263e |  | note | (d) quantity manufactured in the batch
label | 1bef9b70-3a95-4483-b28a-e571505b1072 |  | note | (e) date of manufacture.
label | 9f06eb38-0eb3-4c16-b2f2-adb73760f5ae |  | note | All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients.
label | 85bf701d-f644-4898-8f0a-557d0de6b2f9 |  | note | METHOD: Inspection
label | d402b33b-3a5c-4120-bccf-ea25d8bc0b03 |  | note | FREQUENCY: Once Per Lot
label | edaafbd1-22c8-4a91-acea-cf5a9144bba7 |  | note | CATEGORY: WP
label | a7370204-1adb-42f9-a1b3-b3296e48537c |  | note | RESPONSIBILITY: SE/PE
label | 7a15d6b4-7c87-400e-afdf-4ee672cd6d5e |  | note | VERIFYING DOCUMENTS: This ITP
text | 799eb4bc-3f76-4435-a0cb-8909bdf28b0d |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Expansion Joint Placement (Wizflex WZ-50 & WZ-60 with relevant primer, Thioflex 600, and FRP cover plates)
label | dc2c3e6b-3161-455a-8602-b765dcb6d521 |  | note | REFERENCE: IFC Drawings
label | f5e70d1e-2c98-4d81-9f88-109179f5df12 |  | note | Shop Drawings
label | 1d2b5398-ac91-4c1e-8ff4-87435e07bd75 |  | note | Installation Manual
label | 412ffca4-8957-49d4-a08c-d6bcf0cc6017 |  | note | 660.04
label | e4063ed4-9771-475c-a0bf-0b51ec4878e5 |  | note | ACCEPTANCE CRITERIA: Place the expansion joint to the survey marks to achieve a top surface parallel with the longitudinal grade and cross-fall of the FSL and in compliance with the Drawings, installation manual and tolerances:
label | 5021ba03-a3b0-4d18-b0d6-fd82ca3e8cc9 |  | note | Joint gap = ±3mm
label | 95a2b60f-7572-48e8-83d2-bc2e4b3ff00f |  | note | Deviation from plan alignment = 5mm max.
label | ca45bb27-2415-49d8-a81a-fbbdf37d0ad2 |  | note | Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
label | 44d56a40-f50f-4adb-a7b8-74585dbf57fc |  | note | METHOD: Measure , Visual
label | c356ac04-a8d2-4b8f-b172-5c88c44cae8c |  | note | FREQUENCY: Each element
label | 91431361-aaf1-40ef-8e9c-adf1810e5a95 |  | note | CATEGORY: IP
label | 06e7418f-17a9-41df-a794-b76d404274a4 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | b59ed916-88c5-4601-8600-ff2be599c872 |  | note | VERIFYING DOCUMENTS: This ITP
text | 081dff5b-8958-4647-a7cd-f6363cb97b91 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Compression Seals, Inserts and Membranes
label | 11760c15-938c-4673-a941-8e16cccfb8f9 |  | note | REFERENCE: 660.04
label | 07e265a7-23f5-4437-80d9-1894b7393151 |  | note | ACCEPTANCE CRITERIA: Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
label | c58e967f-f922-47c3-8d80-6a140cb3b4cb |  | note | If seals are bonded with the nosing, the surface shall be prepared and primed and the adhesives placed in accordance with the adhesive TDS.
label | 5f988296-1885-4cc6-9441-13dba964f04b |  | note | Completed joints shall be watertight.
label | 700d5436-35ed-4be6-b8ef-e0edb8551bbe |  | note | METHOD: Visual
label | 0383c577-31ff-46c2-977a-b8c14f4cc6e3 |  | note | FREQUENCY: Where applicable, each element
label | b3427ed1-a838-40bc-a761-c50fec4a77e7 |  | note | CATEGORY: IP
label | 87227e4c-5d07-4775-a7e8-04fffd04b874 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6944983f-6444-4ab6-856c-0ca2895ac2a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 77a5261a-c6a6-40f7-af2d-c720b14e7315 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Environmental Conditions
label | 756f7809-76f2-408f-9241-040c8b16399b |  | note | REFERENCE: VR 691.14
label | f65a8888-e724-4299-a65a-4ed84fabc8ed |  | note | ACCEPTANCE CRITERIA: Waterproofing systems shall not be applied under any of the following conditions:
label | 2c296136-b677-4c47-92bd-93667a793b7e |  | note | (a) windy conditions where over spray and/or spatter may be generated
label | 753fd219-8d88-4379-b5ff-16c933b615fc |  | note | (b) when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane
label | b20414f3-446b-4a59-85ba-558a6e0c7893 |  | note | (c) when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer
label | e5989d9b-07ed-44ac-9387-de953a92c4bc |  | note | (d) when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period
label | 9fa472fa-574b-4671-842b-970620cdd9cd |  | note | e) when rain spatter or run-off, including leakage through deck joints, contaminating the surface and adversely affecting the adhesion to the substrate, may occur
label | e2e068f0-bd6e-4785-bb2d-c2e0b50912f6 |  | note | (f) when the substrate surface is wet or damp, unless the waterproofing system is specifically required to be applied on a damp concrete surface in accordance with the requirements of clause 691.05
label | 0c47d566-43f4-4e3f-b6ea-9901dd0124b1 |  | note | (g) the surface temperature of the substrate is less than 3°C above the dew point calculated in accordance with AS/NZS 2312 (Fig. 8.1) or exceeds 40°C.
label | 64dad463-a5ce-4637-8d8e-2934ddd911f3 |  | note | METHOD: Inspection
label | feff3163-aa08-42cf-8505-134f4e9ebd7c |  | note | FREQUENCY: Each element
label | cf1a0ebb-bcec-468a-94a9-954067dd2c96 |  | note | CATEGORY: WP
label | 26ec26ea-e31e-4c30-b87f-fef1b825c567 |  | note | RESPONSIBILITY: SE/PE
label | ca02d6c6-e076-47e5-8c73-c2363fb3b156 |  | note | VERIFYING DOCUMENTS: This ITP
text | f9510fef-c4f0-4688-807b-6f4c093ffdbc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Waterproofing Membrane Application (Preformed Waterproofing Membrane)
label | ebd999f9-3e36-4570-b082-6c402ac36976 |  | note | REFERENCE: 691.09
label | 46ce9a87-1a8f-4d57-8155-9aa646137c8d |  | note | IFC Drawings
label | cdbf2db5-fa78-449d-8bce-c15fd82d07a2 |  | note | Installation Manual
label | 86b65127-5259-4b39-bdea-93b8048bbc72 |  | note | ACCEPTANCE CRITERIA: All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application.
label | 920ffcac-f3ad-43ab-8ba7-ca1b91a8db17 |  | note | In addition, the membrane shall not be applied over any previously applied layer/coat which contains application defects or any damage until such defects have been repaired in accordance with clause 691.20.
label | 0c924019-1b29-48ea-9255-c0af587546cd |  | note | Air shall not be allowed to be trapped at the concrete/primer/membrane interfaces.
label | 782c3535-e257-497f-bfb2-a37b71a0b3f4 |  | note | The waterproofing membrane shall be applied with minimum side and end overlaps of 100mm and 150mm respectively.
label | e205db54-911f-4f79-8233-9cbdef18e899 |  | note | METHOD: Inspection
label | f95582d3-0392-4a55-8732-0a0ca825f648 |  | note | FREQUENCY: Once Per Lot
label | 954295d0-1da1-4d8d-88bf-5f072ea5e6b3 |  | note | CATEGORY: WP
label | 2b5014fd-e78f-4131-bb43-dd83f9cf4d74 |  | note | RESPONSIBILITY: SE/PE
label | 83c61202-1809-43e9-a0a7-4a12b1d0c804 |  | note | VERIFYING DOCUMENTS: This ITP
text | e9ac146c-6b3b-4fee-8c94-73fd3c6ba8c3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Final Inspection of installed membrane system including all accessories
label | c2d80b1d-47ae-4ccd-9b59-2bc8a1af7a0e |  | note | REFERENCE: 691.09
label | d59c0c12-2745-4aa9-9c11-f25d24d833af |  | note | IFC Drawings
label | 160d157e-a886-4b70-aa7b-54b91a4a60c7 |  | note | ACCEPTANCE CRITERIA: No visual damage to the installed membrane system
label | 9a68579c-83ff-4993-8faa-fd8db98a99e7 |  | note | METHOD: Inspection
label | 14bad202-1034-4c75-b102-72b1ec711e36 |  | note | FREQUENCY: Once per Lot
label | 24a74c74-b85d-401e-bc5b-57a5c160628a |  | note | CATEGORY: IP
label | 62a2e04a-4cd7-4b13-9b61-7037e3293d6e |  | note | RESPONSIBILITY: SE/PE
label | a510a36c-b704-45f8-b113-adf5566185d1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 23a118d1-13ca-4da2-916f-5c8453611244 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Patch Repair for membrane (if required)
label | 901a1719-fb6e-48bf-bf39-28bccb6136b2 |  | note | REFERENCE: Work Method Statement
label | b3276432-5fc0-4f22-b3b2-70b514a1c22c |  | note | ACCEPTANCE CRITERIA: All areas of waterproofing damaged by the Contractor during its operation shall be made good.
label | e2a3a0ac-da2d-4372-99cb-faa499e84aad |  | note | Where required, preformed sheets shall be repaired by cutting back the affected area using a sharp knife, or similar tool, until undamaged and well-bonded membrane is exposed. The area under repair shall be abraded and the primer applied by brush or spray.
label | 02b78392-f355-4a5c-b568-9ad0acd08ddd |  | note | METHOD: Inspection
label | a57085e3-d674-481e-a84e-0f511cc87729 |  | note | FREQUENCY: Every Weld that need repair
label | ac49a2ab-ec7e-4ed3-acea-76f755b2eb33 |  | note | CATEGORY: IP
label | 6363d6c2-e18b-4051-ac63-9c142f3a5284 |  | note | RESPONSIBILITY: SE/PE
label | b53055fe-e2ea-4b7a-a0d6-782594a8bac5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2957969f-577e-4687-820d-b9e4a0cec8f8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Trafficking of Joints During Construction
label | c5cb4ea3-5b20-4ba7-a597-22cee8bf024a |  | note | REFERENCE: 660.04
label | 1c8491ec-2a82-4d2d-931b-fe8161f31217 |  | note | ACCEPTANCE CRITERIA: Joints shall not be trafficked until all components of the joint have achieved adequate strength to support the traffic loads without damage.
label | 0234a323-033e-4bca-bbba-7bd347797460 |  | note | Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
label | df142074-1bb7-425f-9cb4-2d81ef75faf4 |  | note | METHOD: Visual
label | d1217db8-08f0-447e-9f78-2fa312660669 |  | note | FREQUENCY: Where applicable, each element
label | 582a4dd9-d693-4789-a755-04f7e48f651f |  | note | CATEGORY: IP
label | e3b4b589-dba6-45bb-8c81-51dc0a4effc0 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d65c3525-412f-4144-81da-fc21b9b65369 |  | note | VERIFYING DOCUMENTS: This ITP
text | b64e6aeb-0e75-4dbc-8ad7-e652e6eee6dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 As-built Survey
label | e3552479-8d1e-412e-8fe3-1a584508307f |  | note | REFERENCE: IFC Drawings
label | d2ea9298-c42f-4e0d-a701-7e90b420aa38 |  | note | 660.04
label | a10f2177-5b94-4af0-95f2-3cc664f76a25 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 4.1. above.
label | 60f479b8-df97-491e-b7f3-600c7c9512b8 |  | note | Attach: Survey As-builts / Survey Report
label | a521acb9-1f0f-4a50-9ace-1ccccb281407 |  | note | METHOD: Document Review
label | ad0b9e9c-3613-43b9-9451-56e2cace1d47 |  | note | FREQUENCY: Each element
label | 5824d64e-9ff9-4120-8a44-d230badee1d5 |  | note | CATEGORY: IP
label | 86452bbc-1d4d-40a7-b8ba-17f1ba71d561 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | c84d60ff-263b-42fa-94af-c4dc3e5dc750 |  | note | VERIFYING DOCUMENTS: This ITP
text | 29464625-120c-4a24-952d-b4c0e2dd3d71 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Subcontractor Product warranties obtained
label | 1f88fe5f-bc9e-4d71-8ea8-0a9eb015813c |  | note | REFERENCE: Work Method Statement
label | 43e1645a-b451-46de-ab11-d665c2b67fd3 |  | note | IFC Drawings
label | 52757c1f-8e01-4690-a206-b12bd7ae58d4 |  | note | ACCEPTANCE CRITERIA: Product warranties obtained and are compliant with what is specified in IFC Drawings
label | f4e491ff-b40a-406d-85b9-17da73139b27 |  | note | METHOD: Inspection, Document Review
label | 19d2d3a2-4c03-48e6-980a-d9de8869f42d |  | note | FREQUENCY: Once per Lot
label | 94b4bcfc-b664-4cef-8bd9-4c37ae4044e6 |  | note | CATEGORY: WP
label | 27b0e8e3-f830-4641-886f-de712b5cb3dc |  | note | RESPONSIBILITY: SE/PE
label | 0f965acb-4579-4e01-a2f5-87a0480f99d4 |  | note | VERIFYING DOCUMENTS: Copies of product warranties
text | 23cff0fb-f586-490f-8c9e-fa8f3d7475a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Non-conformance Report (NCR) Closure
label | 9617c732-18de-4b17-a152-3751e22601de |  | note | REFERENCE: MRPA Quality Management Plan
label | 2689d74d-47bc-4c96-85e0-9774a7a752c0 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | b882c845-be25-48e7-8fb5-a06527d9b587 |  | note | METHOD: Document Review
label | 240fd326-0064-44a2-9280-ad1bb6a8e6cd |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 3a518d9b-5305-4543-a4b1-b6758c6060fa |  | note | CATEGORY: HP*
label | 24dbf82f-26bf-4625-87d5-0c4a0d07ba29 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 6499e47a-1a2c-4c01-a769-d05882e41491 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8c6c823a-7cca-4626-b278-7d6685948889 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 183b0538-f0fa-4588-a94d-ed82c1be0b15 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | fb83bf47-0966-453c-8250-c5ebbc63617c |  | textbox | Name:
text | 6e9882b2-5b5e-4a1f-b5c8-fac77f5a66de |  | textbox | Position:
text | 5d7e0a2b-8b40-4036-99ec-08d02abbf261 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-Rock Fill Material (Supply and Install) Rev 0 | itp |  |  |  | Yes | ITP-CIV-Rock Fill Material (Supply and Install) Rev 0 | fb966436-7514-4a45-b875-2f41b34f160f
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  | checkpoint-no-status has incorrect meta.stepType checkpoint-status | checkpoint | Referenced Documentation
label | 30734986-ce14-56c1-9be2-589f4afaceec |  | note | Document Title: ITP-CIV-Rock Fill Material (Supply and Install)
label | 65edd17e-81cc-59b6-a999-1891a2be3449 |  | note | ITP Description: Rock Fill Material (Supply and Install)
label | 0e1382fd-fcbd-59df-b2d3-35fac84e5c8e |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 24ed1c01-f380-5913-b45c-dbb31f7dbf44 |  | note | Revision Number: 0
label | d454110c-e792-5e02-8bea-fed04c9ed7d0 |  | note | Revision Date: 20/12/21
label | 2c1ca7bb-0caa-5d40-972e-840249bddf0f |  | note | ITP created by: Isaac El Zayat
label | dd5b93a6-5add-5b1b-a3c9-ddf6ca220ab9 |  | note | 1.1 Reference Documents:
label | 33a5b2e7-ea6f-5ce8-8ab9-2136d079bdea |  | note | IFC Drawings
label | 85503d63-7968-5279-beb9-0db9dc6c90d6 |  | note | VicRoads Standard Section 204(29/12/2015)
label | 7a53fc8c-9b05-5214-a515-60b5e76d0e05 |  | note | VicRoads Standard Section 205 (2013)
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | 2.1 Material Supply
label | 468d2f96-234d-5509-873d-76d31aadf10f |  | note | REFERENCE: Section 205.03 (a)
label | ac712fa1-9c5d-5f00-9263-ac2bbb0ea621 |  | note | ACCEPTANCE CRITERIA: Prior to placement, rock fill material shall have no particle dimension exceeding 500 mm and minimal fine material.
text | 6d217ffe-e985-58ab-b3e8-1a6fc42c06a9 |  | textbox | Enter Teambinder Material approval Number:
label | 9d0750d7-92a1-5e40-9956-3d72970caa91 |  | note | METHOD: Doc. Review
label | fe325cf1-aacc-5f65-9111-643a6b3fd97c |  | note | FREQUENCY: Prior to Commencement
label | ce961494-3c75-503d-8c4f-093cd702d7c8 |  | note | CATEGORY: HP
label | 98461325-bf8e-5e0a-96a3-d991fd10f287 |  | note | RESPONSIBILITY: Nominated Authority
label | e4a9ca65-ac26-5b42-ba72-0fb7e7748b06 |  | note | VERIFYING DOCUMENTS: NATA Test Certificate
text | 8cac5d23-b377-5726-a105-96fa27028920 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Pre-Commencement of Rock Fill Works
label | 35544298-32e2-5f72-915d-eb0ec2373725 |  | note | REFERENCE: Section 205.05 (a)
label | 45a73e66-9ab3-54d8-b24e-d4c764bb6eb8 |  | note | ACCEPTANCE CRITERIA: Areas upon which rock fills are to be constructed shall be prepared Areas upon which fills are to be constructed shall be prepared in accordance with the requirements of Section 204.
label | 6f636bb7-f322-5b39-8b42-2dbdc8ad73e5 |  | note | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | 25e0d80a-0cad-56f4-ac57-a540388b9fb3 |  | note | METHOD: Visual Inspection
label | dee141a4-a909-5236-8643-690c6deef5a8 |  | note | FREQUENCY: Prior to commencement of rock fill works
label | 6f955b2b-6e66-5856-954e-692f48df2a22 |  | note | CATEGORY: HP
label | 352e24d7-6a3b-51c9-8364-4cdddabef67a |  | note | RESPONSIBILITY: Nominated Authority
label | ad3ac503-4ad9-511e-ab66-1b1f2b4e3806 |  | note | VERIFYING DOCUMENTS: Signed ITP
text | cbcff13d-ce61-510e-9611-1fdcfc1b0214 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Pre-Commencement of Rock Fill Works
label | 4215e586-1c3a-5fd6-bebd-e618cf4934f6 |  | note | REFERENCE: Section 205.05 (b)
label | ab92612f-d4ab-59b0-a282-0944ea5f7603 |  | note | ACCEPTANCE CRITERIA: Prior to placement of the first layer of rock fill, a 300 micron thick polyethylene sheet shall be placed as a separation layer. Drainage blanket to extend 1m beyond wall and key in to rock fill.
label | ac01abc2-9e9c-53c7-b305-dd2df2b812af |  | note | METHOD: Visual Inspection
label | 78f79e0e-e32f-5e4c-ac61-f018aa5a3f79 |  | note | FREQUENCY: Prior to placement of rock fill
label | 0b62dea7-efcd-58c7-83b1-313c65f22f42 |  | note | CATEGORY: IP
label | c8a375b4-1cd0-550f-83cf-e5a2c89209f9 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 6c3361cc-2cb1-51ab-9bcd-376ac24a2437 |  | note | VERIFYING DOCUMENTS: Signed ITP
text | ed2ed444-4dc0-5974-9112-6a39f7963b1b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Survey Pickup of base
label | 2d6cdbd2-5bf2-559b-a329-7688a80c8c81 |  | note | REFERENCE: IFC drawings
label | ed2aa939-f51e-55e5-8201-1b2368cdbabe |  | note | ACCEPTANCE CRITERIA: Prior to placing the first layer of rock fill, the underlying layer of material shall be surveyed.
label | c1b7f060-ea30-56b5-b367-f4911ada5b60 |  | note | METHOD: Monitor
label | ddb9132e-0533-55f9-988f-5809d689f43e |  | note | FREQUENCY: Prior to placement of rock fill
label | b064837b-f7db-530b-85df-f10f8febeaf6 |  | note | CATEGORY: IP
label | 8d357cfa-1214-5191-a8a9-4e39e2482cb8 |  | note | RESPONSIBILITY: Surveyor/SE/Site Supervisor
label | 72b8a716-3dce-5400-a4e0-0d9979639b83 |  | note | VERIFYING DOCUMENTS: Signed ITP
text | de754e0b-f580-5192-9a07-90d658c8f863 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Placement of Rock Fill
label | 06d6e5fc-cdf8-546e-8e9b-e272a8e90f4a |  | note | REFERENCE: Section 205.05 (b)
label | 55455f06-2d88-51e7-8c14-76d0a907e063 |  | note | Table 205.051
label | a80fdfaa-c816-50ca-a711-e29b2c14d2d5 |  | note | ACCEPTANCE CRITERIA: Fill layers shall be placed and compacted in layers not exceeding a compacted thickness of 200mm
label | 91c6fc24-5bfb-5439-b246-e235d7844cf4 |  | note | METHOD: Monitor
label | bd900f13-8f40-5fb5-a694-a6873afe0631 |  | note | FREQUENCY: Each layer
label | 1cd48f18-5d69-5e87-84f7-9f16f4bdaa5c |  | note | CATEGORY: IP
label | 174c51cb-56ee-5bce-aa5b-1aa201258c08 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7ee0cd50-e37f-5a40-b968-688fb6d21e2d |  | note | VERIFYING DOCUMENTS: Signed ITP
text | 60cc5b94-9ea6-5ba2-9cd5-2e08ed0da484 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Level Control
label | 492a8d6f-2f8b-5867-a370-70d81a245a8d |  | note | REFERENCE: Section 205.05 (d)
label | 10878166-9058-5c58-a352-210bd954b7f9 |  | note | ACCEPTANCE CRITERIA: Each layer of rock fill including cover layers shall be surveyed to confirm that placement is in accordance with the following tolerances:
label | b48b2510-50cc-5be1-89d3-86b383913f43 |  | note | Intermediate layers of rock fill shall be placed to a tolerance of +/- 100 mm.
label | 3ee157db-a1de-5655-9383-2bfc261b095a |  | note | The surface level tolerance of the top of final layer of rock fill or zone shall be finished to a tolerance of:
label | 07e09255-4f07-5be2-a8bf-684e16531964 |  | note | =+0 mm / -100 mm.
label | e78ed569-c828-5c41-82e8-3089d88d5257 |  | note | METHOD: Monitor
label | 6a47fa0d-5f76-5e6d-a165-a6279dc6ab72 |  | note | FREQUENCY: Each layer
label | 1bed3bc6-efdf-5f03-8ea0-7df46dc5e89c |  | note | CATEGORY: IP
label | 662575e4-e023-5dfc-8c3f-824fdb8ea682 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8109a637-29aa-58c3-920f-9ea403a5ff72 |  | note | VERIFYING DOCUMENTS: Signed ITP
text | 6fb50991-4036-5f7b-9cc9-ea0c75e912cd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Compaction of Rock Fill
label | 13e0ac1f-d3de-5d93-949c-1ef068304c4f |  | note | REFERENCE: MRPA Rock Fill Compaction Methodology
label | b0d64581-1938-5aab-af5c-af322e687f83 |  | note | ACCEPTANCE CRITERIA: Per the approved compaction methodology, each layer of fill shall undergo 5 passes with a twin drum roller on vibration setting, up to 300mm within structure.
label | 2b5ce804-d111-582a-862f-d53972668f18 |  | note | METHOD: Monitor
label | ac033240-9b93-531d-92a5-044971b31301 |  | note | FREQUENCY: Each Layer
label | 415d19cb-2732-5365-9f6b-436eb27e7ef0 |  | note | CATEGORY: IP
label | c8c02ded-9d0d-5bd2-a94d-eea72ff502be |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f4aef976-1118-5bf0-8165-1805cf1672ff |  | note | VERIFYING DOCUMENTS: Signed ITP
text | 7b4f565c-7fd1-522a-b23f-0ccdaa7be4f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Test Rolling
label | deae5e65-2c1f-54ce-9950-fa3893caf88b |  | note | REFERENCE: 205.07
label | 91d45b5f-a6ed-5f48-875e-330fd6e5e2e9 |  | note | ACCEPTANCE CRITERIA: All layers of rock fill shall be test rolled in accordance with Section 173
label | eda6dcfa-e1f4-56d5-9eaf-feb3fde5fdcf |  | note | METHOD: Measure
label | 3cfdcb35-3f78-516e-997d-72ebc0855395 |  | note | FREQUENCY: Each layer
label | 78f4ffc8-78c9-5276-8d2c-789853461dbe |  | note | CATEGORY: HP
label | ab7011a9-72aa-57db-b28f-db889988e498 |  | note | RESPONSIBILITY: Nominated Authority
label | fdae1410-ed01-573f-8659-81dc8f45655a |  | note | VERIFYING DOCUMENTS: Signed ITP
text | cea8d252-5bcc-5b8b-b48e-ddd500b211ee |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 Consolidation measurement of Rock Fill Layers
label | 5aab8d2c-4ba5-5aad-8589-c8a0ae48edb8 |  | note | REFERENCE: 205.08
label | a2c1849f-3a39-55f0-93e2-3a05fda308ff |  | note | Table 205.081
label | d07e79ff-b4df-5212-969b-d58455890720 |  | note | ACCEPTANCE CRITERIA: Every layer shall be monitored to verify that no further consolidation is occurring
label | 2cc5fe26-0659-5d27-951d-0743900a99b0 |  | note | Survey monitoring of consolidation of rock particles shall take to a number and location to the satisfaction of the Superintendent but less than 12 locations.
label | 4b453e20-fa37-553d-896f-8f43db143ced |  | note | Average cumulative deflection over the last three roller pass no greater than 5mm (less than 15mm across 3 passes)
label | 2eff4e9c-3ca9-53e1-9328-6e99721f6593 |  | note | METHOD: Measure
label | 4bbdb4d4-e5d1-57af-b9b4-04b48436b7e9 |  | note | FREQUENCY: Each layer
label | 98456e2f-9de3-575f-a7fd-56edc7fac3f1 |  | note | CATEGORY: HP
label | bc9bf7c3-875f-5795-a508-c3ba00451165 |  | note | RESPONSIBILITY: Surveyor/SE/Site Supervisor
label | 30a2dc98-d8fd-5aa1-91dc-c1c6f94817dc |  | note | VERIFYING DOCUMENTS: Survey report
text | 19d8c17c-afdb-52bc-862c-612fabe84490 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 Post compaction grading
label | 7c96862c-c7e8-5a2c-80bc-609edca30c63 |  | note | REFERENCE: 205.03 (a)
label | 4852adb5-af7e-52c6-8f0c-24cd6c3515a5 |  | note | Table 205.031
label | 92fd7968-8f72-5481-ab33-e7689389296f |  | note | ACCEPTANCE CRITERIA: % passing 75mm sieve = 100
label | f55bbdef-e278-5a83-9fd5-d6fb4993ad6b |  | note | % passing 37.5mm = 10 - 25
label | 345dcdfa-9f77-5c0a-a9d9-3eec24ad78b9 |  | note | METHOD: Measure
label | e0449f15-716b-5d4f-a941-12cdf3e97579 |  | note | FREQUENCY: Every third layer
label | e30e2794-ad64-5d3b-82e7-c4a35313275d |  | note | CATEGORY: IP
label | fcbcb6ed-2a26-5d6f-afd6-6ce1af54be46 |  | note | RESPONSIBILITY: SE
label | e1cce1f1-f820-5506-aaca-d223dd2136c9 |  | note | VERIFYING DOCUMENTS: NATA Test Certificate
text | a8b7b5ac-78e0-5cd0-9ff1-b3ebc4f50a1a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 42915a1a-2310-5a2f-9c9a-9fdc342f45ab |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | c7bbcdc4-dc12-50e5-8669-486e4670ec5a |  | textbox | Name:
text | 7b93b747-83fd-562b-8d71-6e6ee95b2f10 |  | textbox | Position:
text | bf52b142-d98e-551e-a658-cb89b3d5f461 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-STR-Shotcreting Rev 1 | itp |  |  |  | Yes | ITP-STR-Shotcreting Rev 1 | ff54d7df-47dd-473f-8201-997e0fd22a17
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | Referenced Documentation
label | 41adcd6e-0345-4936-8f19-cedf30d5db01 |  | note | Document Title: ITP-STR-Shotcreting
label | bf1feeb4-1c33-4a20-a5eb-3230369361cc |  | note | ITP Description: Shotcreting
label | 511c9f10-bfd6-4299-92a6-327dc4aff723 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 4829b04f-2721-4c60-bac5-eb5485ce82f7 |  | note | Revision Number: 1
label | 58334cee-f66a-4fc0-8dcb-50313b406a75 |  | note | Revision Date: 28/07/2021
label | 1a87b040-edff-4994-bdf7-8aa7be758b58 |  | note | ITP created by: Mike Freeman
label | 3abdd379-65a8-479e-8454-01894558b2a6 |  | note | ITP approved for use by: Mike Freeman
label | 9a029364-773b-4cc2-a2ff-d219580a1f71 |  | note | 1.1 - VicRoads Section 610 June 2019
label | 457348f9-b1c8-4c5a-9796-745ee40faaf9 |  | note | 1.2 - VicRoads Section 611 November 2018
label | 34a3001a-bc5a-4dca-88b2-9b02531f0536 |  | note | 1.3 - VicRoads Section 684 April 2019
label | 2f47a365-794d-4869-90ff-20ffbe710234 |  | note | 1.4 - AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | d155242e-606a-4869-a57d-f5e7997cee77 |  | note | REFERENCE: 684.04 (a)
label | cd47303e-b761-4842-bd1b-0f0f21d9c412 |  | note | 684.04 (d) (i & ii)
label | 9e3bb931-bbdb-44a0-8365-bd7211b0a3a7 |  | note | 684.05 (a) (i & ii)
label | dac8ee86-68aa-4240-8545-a6f78041d0ca |  | note | Table 684.051 684.05 (b)
label | 54910d22-bea2-4929-b844-1dfc4765f018 |  | note | Table 684.052 610.07
label | 73d087eb-b80e-4e5e-96dc-fc79e31559da |  | note | Table 610.071
label | dc73970b-9f07-42b2-aa1e-d11be0601c98 |  | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | cfaaff3a-f260-4093-aa9b-77b785667e6d |  | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
label | 2794c66a-6bba-4eac-a460-eb19a8e2a7d9 |  | note | Maximum drying shrinkage shall meet the values shown on table 684.052.
label | c4552330-4b80-4f6f-b1dc-e9ebd1923cb0 |  | note | Where applicable, steel fibres shall:
label | b000cf5c-c2c8-4294-9573-d73d5d44e128 |  | note | i. be deformed
label | bc0e4716-bf48-4690-9834-d31c54fb84d7 |  | note | ii. have a minimum tensile strength of 800MPa
label | 66c0225f-bbb9-45e4-ac38-b6ddd89b1aef |  | note | iii. have an aspect ratio between 40 and 70
label | 40839424-00fe-45a4-ad6c-11c63d76f339 |  | note | iv. have a minimum dosage rate as per table 684.051
text | cfc99e83-ffb0-4d34-8c2b-4d146cf6a765 |  | textbox | Enter: Teambinder Material Approval number
label | 70eb4438-6b94-4b1c-9056-1387804fc36c |  | note | METHOD: Document Review
label | b7a80d04-8964-48a7-a6f1-b61cb4deaccb |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | cc123db4-388a-47ab-975b-c129cd9bc160 |  | note | CATEGORY: HP
label | 97396fa8-75ae-4341-8560-3b296b1c2046 |  | note | RESPONSIBILITY: Nominated Authority
label | 701e7db2-0667-4869-a3d3-281a46e3cea8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 27e849a4-8109-451e-b3f2-2c5c3d29e58f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | e8813b7f-45f0-4d57-b23c-f851b6e4ca20 |  | note | REFERENCE: 684.04 (c)
label | df4af71f-3726-4e9b-8d51-ca9d41187736 |  | note | 611.05 (a)
label | 5c1349eb-b0b4-4a10-b5a0-3898514c483b |  | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
label | 1e3834eb-ade0-414e-ba79-803b9c2e0349 |  | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 189e12ce-4856-4545-a97f-d53149e42895 |  | textbox | Enter: Teambinder Material Approval number
label | f97fc394-4844-4d13-9dee-f72a1e53df58 |  | note | METHOD: Document Review
label | 06b35ade-c9c6-4729-9685-f75722186135 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | b415008e-36a5-4dcb-9d63-ec612fdd4750 |  | note | CATEGORY: WP
label | a01a368e-5aef-4ef1-aab7-be303f7aa70f |  | note | RESPONSIBILITY: Nominated Authority
label | 275c1555-87e7-4e12-9d08-118ea972bcaa |  | note | VERIFYING DOCUMENTS: This ITP
text | 5107be92-dd4e-4c97-b89f-3996031ad40d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Galvanising (for Reinforcement)
label | f72b6653-43a1-422f-94e9-4ce99cd36c40 |  | note | REFERENCE: 684.04 (c)
label | cb1edbd0-1f79-463e-83f2-97145c17ead1 |  | note | ACCEPTANCE CRITERIA: All reinforcement and tie wire used in the Works shall be hot-dipped galvanised in accordance with AS4680.
label | ee9216a6-147e-4c72-b364-fc09fe291683 |  | note | Note: MRPA has D.o.T direction and approval to use black anchor bars
label | d7577aa9-17d1-4eba-94db-a77d50a1af18 |  | note | See: MRP-016-C-ACD-REP-17-NWA-CSW-0001 (Clyde Road)
label | eab7aeee-c7aa-4294-9caf-91cfa780b656 |  | note | MRP-072-C-AURE-REP-20-DPK-CSW-0001
label | 3b8ac503-ea5b-4e6d-866f-e2aa1c1c6d1c |  | note | (Robinsons Road)
label | 69e0c471-e124-4580-bf3a-acf44215fa0a |  | note | Attach: Galvaniser's Certificate of Compliance
label | ae4b5b69-8f07-4272-a844-e433aa38bda7 |  | note | METHOD: Document Review
label | 13a90de2-9466-4801-a84f-e65feaba95f9 |  | note | FREQUENCY: For each reinforcement delivery from each galvaniser
label | 732e6a30-dacc-48a1-905b-f9e8a33d4c9a |  | note | CATEGORY: WP
label | bc5dc116-0800-4a8e-9cb4-935d3929c4a6 |  | note | RESPONSIBILITY: Nominated Authority
label | abc47b34-d603-4ef8-bdb6-ebc569711068 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7ce58341-ada8-4c86-95e8-7d7f050a61cf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Bar Chairs/Aspros Certification
label | 6347a3d8-51e3-4f23-a4cb-c6b01ffe4838 |  | note | REFERENCE: 610.26 (a)
label | fc304d97-dc54-40ae-a729-6f4a39dd59a5 |  | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | c374def6-575f-45b2-b692-5afa0a41986b |  | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 5bcc60ef-d9e1-4c73-95ba-6804338485a2 |  | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 7b19c8c8-edcd-4e30-b2bd-831b426b8c0a |  | textbox | Enter: Teambinder Material Approval number
label | 13dbd291-3c2d-4f65-ba65-795e3710e127 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 803f5b2c-d2d7-4420-94ec-081ea013f246 |  | note | CATEGORY: WP
label | 5ad100c8-3bdb-4186-9b55-a19e93290114 |  | note | RESPONSIBILITY: Nominated Authority
label | aa80ab91-36d5-4c83-9b6a-74e93fccfada |  | note | VERIFYING DOCUMENTS: This ITP
text | 1cbd9911-a2e2-4fab-9cce-dbbde98a8e4c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Evaporative Retardant
label | 21de5518-5f6c-4b8d-8c77-48aa12de4cb8 |  | note | REFERENCE: 684.10 (b)
label | 1a4a4aaa-d17d-4683-940d-608880939990 |  | note | 684.11
label | 8e7dcd68-808b-49df-82c9-4ec71cf343e1 |  | note | 610.17 (f)
label | f73ef01e-0702-47e1-b910-c3ceb12bdd01 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 937ec9db-5b85-41a9-bc59-542c5aaa98d5 |  | textbox | Enter: Teambinder Material Approval number
label | 354ce309-04cc-4bd7-a90e-cadecf78709f |  | note | METHOD: Document Review
label | b1124d79-d596-41ab-bda3-4d14db1d3248 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 50c2998b-0063-4543-ac95-1c23762a0182 |  | note | CATEGORY: WP
label | 30521dd0-7ab4-401c-9286-384de37c514e |  | note | RESPONSIBILITY: Nominated Authority
label | 624588c7-9e02-4737-9d38-336e4d326ed4 |  | note | VERIFYING DOCUMENTS: This ITP
text | b4097172-5ecd-454a-ba47-96c4e6448161 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Curing Compound
label | 072050a6-b5ba-4196-9ef1-0370e3080b45 |  | note | REFERENCE: 684.12
label | 5c792006-acc2-417d-b4d1-73453e6ef655 |  | note | 610.23 (d)
label | c7696cb4-e92c-4786-b8bd-8f022f652f10 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | dc359f60-5bc7-4754-84f9-483943dd3e8f |  | textbox | Enter: Teambinder Material Approval number
label | 98d69525-adb1-4e61-80bf-6b7c7f8c82f5 |  | note | METHOD: Document Review
label | 310fe358-f83d-4019-b42f-e531e38816f6 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 0cf7f08b-b1b7-4fb1-a11a-1b53bb03e5ba |  | note | CATEGORY: WP
label | 04bda8f6-ebe3-4c43-8cc6-453dd93473c7 |  | note | RESPONSIBILITY: Nominated Authority
label | e5f87d47-81be-44b1-aed3-6a0e04923301 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6bbdcc48-7a6e-4019-94c5-9d97885b57d8 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Shotcrete Work Method Statement
label | a7e13f0c-e007-4b56-b547-69043e451b7d |  | note | REFERENCE: 684.07 (a)
label | 51c70a05-cf9d-49d9-93da-64b440248198 |  | note | 684.07 (d) (i)
label | a68bc113-fe21-4fe2-8497-29f1bce23a66 |  | note | 684.07 (d)
label | 2f0034aa-d3e6-4160-84da-2e28510e653d |  | note | ACCEPTANCE CRITERIA: Shotcrete WMS, detailing the proposed equipment and preparation works, to be submitted for review to the Nominated Authority.
label | 0230df72-9d20-4426-8769-02cfcb033816 |  | note | Any changes to the approved WMS shall be deemed a new Hold Point.
text | ee53122d-ae6b-4e1e-9218-10503452b4a7 |  | textbox | Enter: Teambinder Correspondence Approval number
label | 2bfc23ea-1da9-4f5e-af9f-a71bfdfc2149 |  | note | METHOD: Document Review
label | e7d1859d-25d1-4f49-93fb-fa5235302f12 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | bba56401-3430-4fcc-853d-96e7320aa1f0 |  | note | CATEGORY: HP
label | 35834025-3d55-4bb8-94c9-5163b60d7f67 |  | note | RESPONSIBILITY: Nominated Authority
label | 9d9a4b15-81fd-4b2b-b00c-36373447f060 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 475a83ed-6801-49a2-80d7-883dfdbeee22 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Contractor Competency
label | c894212f-0b02-46f1-9d7a-f7c88ccac310 |  | note | REFERENCE: 684.06
label | cb98e004-9cdb-46b5-872f-8eed738bbfba |  | note | 684.07 (a)
label | d76facc1-b290-4a37-a5b5-cb0ddd430dfd |  | note | 684.07 (d)
label | d9fd99ac-40b4-40a3-8460-0cb107baaa4f |  | note | ACCEPTANCE CRITERIA: Personnel undertaking the shotcrete works, including the nozzle operator, supervisor and finisher, shall have a minimum of 5 years experience in shotcrete application.
label | 2e3ca2ce-b72c-4cf6-921d-e10f2b326d43 |  | note | Any changes to personnel shall be deemed a new Hold Point.
text | 4dbd81e1-16d5-4832-b684-498f18930512 |  | textbox | Enter: Teambinder Approval number
label | f402557b-1e41-45ae-9d2a-2a9811b533b7 |  | note | METHOD: Document Review
label | 1d7e0ac5-81cc-47de-b31d-3995d73e2027 |  | note | FREQUENCY: Once, 4 weeks prior to commencement of works and for any personnel changes
label | a5bbc02e-aa5f-4da4-a025-69ca5d37f5d7 |  | note | CATEGORY: HP
label | fb2b565c-9458-4f34-8b4b-415b704ee1b7 |  | note | RESPONSIBILITY: Nominated Authority
label | 574ac80b-7b6b-46e3-a15f-f82352eae9f7 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b8fd3925-ebbf-4dff-81ee-24e576a82ea5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 Test Panels
label | 45826a85-fac9-442f-8efa-7daef3e11904 |  | note | REFERENCE: 684.07 (b - d)
label | 12a49a83-cba9-424d-bdf7-0f29c7bbd7b9 |  | note | 684.07 (d) (i)
label | 93f23701-7718-45ac-a0b8-63e7bb213af2 |  | note | 684.10 (a)
label | f7b83e43-e50d-4e77-9c94-5f31249096f2 |  | note | ACCEPTANCE CRITERIA: For each combination of nozzle operator, concrete mix and spraying equipment, 2 no. test panels (750mm x 750mm x the maximum design thickness or 150mm min.), shall be cast.
label | 4a0f4bd4-6cb0-4c8f-82fb-4671788f9146 |  | note | The panels shall be cast using the same reinforcement design and in the same orientation as the Works - panels shall not be cast horizontally on the ground.
label | e14231eb-033a-4b22-97db-036774254315 |  | note | For each test panel, 8 no. core samples shall be taken, perpendicular to the surface, no closer than 125mm from the edge and after 48 hours minimum.
label | 4fbd9bee-92c3-4661-96ef-81716651ce5f |  | note | Core samples shall be tested for:
label | 5a0aca80-d0c5-4cf2-92f9-cccb5f4a4e92 |  | note | 1 no. 3 day compressive strength
label | 2e3d1e08-0858-4140-a768-63d8fa2555f1 |  | note | 1 no. 7 day compressive strength
label | 667ad2d6-4110-4c59-a3ea-e190aefffc86 |  | note | 2 no. 28 day compressive strength
label | e5c43163-8183-42ab-8b52-4d75ccda5c0c |  | note | 2 no. VPV tests
label | 2322e774-02f2-4325-af35-25abfada8693 |  | note | 2 no. visual inspection showing reinforcement encasement in concrete
label | efd9a5b4-4018-45ce-ac1a-5fe2e0c9f625 |  | note | Any changes to approved test panel combinations is deemed a new Hold Point.
label | bc4331ec-053a-4fa7-be43-0081c2d0b4f6 |  | note | Where existing test results for the same combinations exist, this is considered to be a pre-qualification and new test panels are not required.
text | d0b2db2b-3c7e-4c8f-8e7c-6478fe432590 |  | textbox | Enter: Teambinder Approval Number
label | 953905e7-1d7b-4281-acec-f12d63082e2e |  | note | METHOD: Document Review
label | 7861f990-8384-4a46-b006-b654819757d0 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete, for each combination of personnel, concrete mix and equipment
label | 313be4a4-e1b5-4411-b5cd-6ac9d262c4b6 |  | note | CATEGORY: HP
label | 23d3f406-3938-45c0-b50d-57ea5af35e12 |  | note | RESPONSIBILITY: Nominated Authority
label | c6e00682-a994-4930-a5f6-833f49f512fd |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e3ce912a-1ab4-43f6-97bc-1b5206c55466 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Concrete Sampling and Testing Procedure
label | 456c2665-cdac-4709-93f6-8233bf5758dc |  | note | REFERENCE: 684.08 (a)
label | 76792b43-f6f3-4fdb-9638-9629baab6dc1 |  | note | 610.18 (a) (v)
label | 85b31c6e-a31a-4b66-900c-a5780b9dd1bf |  | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | 2998479e-ed72-4330-b16d-e73b84d12539 |  | textbox | Enter: Teambinder Approval number
label | 6de1d7c6-86c2-4372-9cf4-474d6518b6bd |  | note | METHOD: Document Review
label | bc572843-206b-4bae-b512-b8589be769e0 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 8015a0b7-d8bb-43f1-be8b-ae787cfd9f93 |  | note | CATEGORY: HP
label | d4e82f98-a471-42d6-a71a-17d14a895fa6 |  | note | RESPONSIBILITY: Nominated Authority
label | 72006e69-0bc4-4566-a7b3-d2256b502866 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4cc95de1-0e89-49ba-bf11-62bd38182a56 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.5 Shotcrete Prequalification Toolbox Meeting
label | 246b9bb5-e5bd-45f8-88dc-3530f0633a94 |  | note | REFERENCE: 684.07 (d) (ii)
label | c107e1be-46ee-4700-8b02-bccb47442ee8 |  | note | ACCEPTANCE CRITERIA: Shotcrete prequalification toolbox meeting held to discuss the quality requirements.
label | 23126e75-c0d8-4e7f-9282-ccaf1088cc1f |  | note | Minutes of this meeting to be submitted to the Nominated Authority.
text | edb53fed-ca2e-47fd-9af2-e837dcb49ae9 |  | textbox | Enter: Teambinder Approval number
label | 0caf3553-849d-44ff-b443-8949b6898039 |  | note | METHOD: Document Review
label | 6c166043-9808-4fe9-b921-81bee2aea56f |  | note | FREQUENCY: Once, prior to placement of concrete
label | 53f97852-80a3-43bd-b56f-4649fe1453ce |  | note | CATEGORY: HP
label | ba6c36c1-93b5-4a5e-a955-164c38fe0830 |  | note | RESPONSIBILITY: Nominated Authority
label | 7fdb6486-40f2-45ed-9f12-8bbea7c0b051 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | cd048d3e-353b-4de9-a826-90bdd92eefc2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Hot and/or Cold Weather Concreting Procedure
label | 4b5735ef-8cd4-40ce-af2e-3fdea39a0108 |  | note | REFERENCE: 684.10 (b)
label | 7074c68a-6a39-417e-be38-fad2d8c0d3d5 |  | note | 610.17 (a)
label | 3389882d-b561-4c7e-ab20-5296aad1c862 |  | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | 401e9c05-3ee2-4b5b-a72b-873fad57daa7 |  | textbox | Enter: Teambinder Approval number
label | 7ff513e2-bc20-4e97-9522-ce42e9905c6b |  | note | METHOD: Document Review
label | 7859ea1f-b13c-4c96-bf8a-c4643e4500f6 |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | 0317a8b6-cc83-4a7c-92db-1769f0f0df1c |  | note | CATEGORY: WP
label | 2ff9a0e2-ff01-4f05-8703-6ac442c93363 |  | note | RESPONSIBILITY: Nominated Authority
label | 6c475607-c3c3-4c54-b2eb-556c1cb93c32 |  | note | VERIFYING DOCUMENTS: This ITP
text | 055ee742-3876-479f-aa64-1c6e5654a3b9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.7 Curing Methodology (for Concrete and Grout)
label | 3ade36cd-bcb0-4606-8b04-a950278422fc |  | note | REFERENCE: 684.12
label | 7bc78f50-d25f-46cd-9d08-4b1ee920c7a8 |  | note | 610.23 (a)
label | a4b47890-0973-41c4-b200-78146565e831 |  | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 300d6c80-d14e-4e87-88ee-382ba96c2885 |  | textbox | Enter: Teambinder Approval number
label | 0cf14049-8336-4549-81e9-41a44af91407 |  | note | METHOD: Document Review
label | 1e216253-0dfa-4460-9b56-cb936646dde5 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | d9072e26-21bb-4395-905d-5ef422571493 |  | note | CATEGORY: HP
label | 2a319890-11a9-4397-85ba-2be8052aa69d |  | note | RESPONSIBILITY: Nominated Authority
label | d47ba9a6-0580-4c50-bd67-3a0523d7e03b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | b67aae34-affd-4dd9-b074-d68765b1d217 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 7065d7df-50e5-4323-b6a9-fd9df270ef93 |  | note | REFERENCE: MRPA Quality Management Plan
label | 1cb61228-2128-4646-b230-81d89ade8795 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 4a6deb73-91e3-4e85-a882-0cf884474c24 |  | note | METHOD: Document Review
label | 3bb58844-2fa6-4216-af85-4207f4d2726e |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 8cf96be3-3685-4ae4-a626-332773142932 |  | note | CATEGORY: HP*
label | 894e6b91-f58d-47fc-aca7-898597bfaa8d |  | note | RESPONSIBILITY: All
label | f6bdf463-a828-4e3f-a62c-2bcb91f7335f |  | note | VERIFYING DOCUMENTS: This ITP
text | 834ac63f-067d-4516-b395-190b82d3f3ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Substrate Preparation
label | 035c680e-6d5b-4307-bcb0-118b5b536ec4 |  | note | REFERENCE: IFC Drawings
label | b3e61861-5b15-4baf-91b9-ce8d882684ff |  | note | Shotcrete WMS
label | b15bb8ac-2da4-4f38-b57d-5aea00572f92 |  | note | 684.09 (a - c)
label | 5b7a8b50-d7d0-4489-865d-ce58f9ebbc85 |  | note | ACCEPTANCE CRITERIA: Substrate shall be formed to the correct line and grade to provide adequate thickness for the works and shaped (or repaired - for concrete) to prevent any abrupt changes in thickness of the shotcrete.
label | 77f6f095-af8b-44de-b851-2accf4869009 |  | note | Any loose materials, oils, grease and coatings of any description shall be removed.
label | 22ccc597-7ea6-4161-a698-3e14d2712dbe |  | note | Smooth concrete substrates shall be roughened to create a construction joint.
label | 862180a2-4433-491e-a931-264a56de8d9f |  | note | METHOD: Measure , Visual
label | 4a7de42b-1488-458f-8222-bd5d0b274e40 |  | note | FREQUENCY: Each lot
label | e1a99575-ce83-4841-912b-3110029a1919 |  | note | CATEGORY: IP
label | 12adfbaa-65f8-4847-a668-97d1902ec693 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 9d0e2b34-74bc-42d1-bc2e-640f83f02501 |  | note | VERIFYING DOCUMENTS: This ITP
text | 62a5fc14-b1b3-4aa9-8552-2d60a50dcfed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Subsurface Drainage
label | a66cd44b-6334-4775-94b8-027b39ef5f5f |  | note | REFERENCE: IFC Drawings
label | 9370e551-9a70-4af3-946c-e7e4dc0a65e1 |  | note | 684.09 (a)
label | eb0b5d05-d140-475c-965a-3d01cdb1bb9f |  | note | 702.03
label | 9f1bf49c-c86a-4849-943b-446c76a14941 |  | note | 702.06
label | 02111ed5-f59a-484a-b28d-1b2f1327b0df |  | note | 702.07
label | acd5b049-0ecd-49d6-ac16-9e2e73da20ff |  | note | 702.09 (f)
label | e63366c8-df8b-4074-86c4-a4fe20e88fd5 |  | note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
label | df74a01e-6a9f-4e18-b134-47ed4e508f75 |  | note | The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings against the substrate to prevent encasement in concrete.
label | f5163164-3ede-4222-94d2-d5b6d6e51a05 |  | note | Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
label | e2001503-fbcb-4518-b73b-0e9c3ab414c2 |  | note | METHOD: Measure , Visual
label | 2bc723c3-bcb1-4b4f-90cb-750934a48942 |  | note | FREQUENCY: Where applicable, each lot
label | 359b45c8-6ec0-4ec8-93ac-39cfd502459c |  | note | CATEGORY: IP
label | 1478c259-674e-4967-bf81-c34c458f546a |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 64dfea6c-7003-43d8-9ec7-fd61e4fd96f1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 73a29f1e-d825-4c58-840c-bd73e6112f6d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Waterstop Seals, Compressible Seals & Isolation Joints
label | 6606e333-0e2d-42e5-8b2c-f5e32a486a0b |  | note | REFERENCE: IFC Drawings
label | 0d674b4d-bcc5-4471-980d-54f712024833 |  | note | Product TDS
label | 48251624-225a-4678-868b-ca63743d8f44 |  | note | ACCEPTANCE CRITERIA: Waterstop seals, compressible seals and isolation joints shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
label | c8f68e12-2aef-4f95-a690-40e19b43ce75 |  | note | Seals and isolation joints must be full height of the structural element(s) and located as per the IFC drawings.
label | a081992f-0357-4edd-8036-2400d01f1a6d |  | note | METHOD: Measure , Visual
label | af287750-988a-4e2b-a0e4-b069fca6d14b |  | note | FREQUENCY: Where applicable, at each existing structural element
label | f9e0789f-cca1-4e4e-93e6-ac3616556cdd |  | note | CATEGORY: IP
label | e66d912c-8b40-491d-8b4e-0ae3986d1570 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 2b7343d6-b265-48a6-bb8d-e77abd8b4e02 |  | note | VERIFYING DOCUMENTS: This ITP
text | 741e94d5-b86a-4224-944d-83b694c11794 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Reinforcement Placement
label | 6daa8186-61d5-4af8-9713-0ad0f13cf30f |  | note | REFERENCE: IFC Drawings
label | 7a38d420-94fb-4997-93b7-58b6e52a6e0f |  | note | 684.04 (c)
label | 886df7ab-7d5b-48db-8eac-6e003b71ddc6 |  | note | 684.09 (c)
label | 54fc25a7-9b4c-4839-8002-5fc861ee3763 |  | note | 611.06
label | 1b72cfc7-54b0-416e-8f6e-06211285e918 |  | note | 611.09
label | b73e9ea1-fdf6-4a3d-9125-55c7281c8446 |  | note | 611.1
label | e04e4c37-a94e-4ea8-b61a-165bf7d486d7 |  | note | 611.11
label | 7f0ea5aa-a47a-4fca-a414-f98a636a240d |  | note | 611.12
label | dffe4162-dcd2-497f-a351-46392e987fe0 |  | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | a91d29f2-6977-42b9-9db1-39388be8c7e9 |  | note | Tie wire is to match the reinforcement it is securing, with contact between dissimilar metals isolated with zinc-rich spray paint, electrical tape or have a minimum gap of 10mm.
label | cbfd92be-0d00-46df-98a6-da3576574162 |  | note | Layers are spaced apart using bent reinforcement, not bar chairs.
label | e56cb0d0-1d06-4dc1-8759-73189b5ce515 |  | note | Projecting reinforcement is the correct length and location.
label | 423a182d-624a-4350-a327-779703f79496 |  | note | Splice lengths achieve the minimum length and are in contact for this length.
label | 3d60fb88-34aa-47a9-ade9-203d1327f5c5 |  | note | The reinforcement surface condition is free from dirt, debris and damage.
label | 086a3967-95f3-4bc7-89b3-6169417c917e |  | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the shotcrete application.
label | 50cee997-526b-426f-a886-93dfc4d6ae52 |  | note | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | 84aca4b8-7b8c-43ce-b0c7-b548c142ac84 |  | note | METHOD: Measure , Visual
label | 60789238-f495-462c-8df5-f34e8d78999e |  | note | FREQUENCY: Each lot
label | 4be9fbf3-9ffc-44f9-bed8-9fc8cccb082f |  | note | CATEGORY: IP
label | 037f6828-fcb7-4b9c-aa27-f20a885c9c8c |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 94c45b2f-b7b1-4099-9d18-da98caaaaaba |  | note | VERIFYING DOCUMENTS: This ITP
text | f9fdb273-2b9d-40c6-b92f-f6d7e0785a87 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Cast-in Items
label | f063c5d0-6810-440f-96ba-80aa647c6a1b |  | note | REFERENCE: IFC Drawings
label | f747f68a-1a15-4348-8100-4aadd9a579ae |  | note | 610.47 (a)
label | ff2acf69-5b76-4b9a-b5de-8bb5b2e29229 |  | note | Table 610.472
label | 756f1012-ca30-4f94-9005-587ab422a025 |  | note | AS3810.1 Table 3.3.6.2
label | 5534ed4c-c3bb-46e5-8373-48c455b8b691 |  | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | ac0284b1-0a69-49d6-b464-30b88907b5ae |  | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 1ec31c4f-05b8-4027-9d5c-10a4f6a5121a |  | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | a7099a29-ff24-46ef-a966-24eb35d7b0f4 |  | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
label | df33e1f7-1c54-4c1b-98ec-60d8b4676ce2 |  | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | ad7b8fe4-0bf8-4178-abcd-5b834f420b9c |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | d92dd42e-0263-467c-b158-9e72fd53fc1b |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 2ae80667-694e-4677-bf03-3ba0bb3caf37 |  | note | iii. Ducts and conduit location = ±12mm
label | 93ceabae-d33b-4187-b26f-7ea2eeaed82e |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 0777275f-192a-4c2e-bae2-78c02a63c4cc |  | note | METHOD: Measure , Visual
label | 5594d6ea-da94-46d9-b281-2506d205bce7 |  | note | FREQUENCY: Where applicable, each element
label | f903e120-3bc9-4e40-8397-387b76e0bab6 |  | note | CATEGORY: IP
label | 0d8194c9-ae35-4500-a16e-6f4c1dbe4045 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | abac52a7-591e-4547-b83e-7b5259247f8b |  | note | VERIFYING DOCUMENTS: This ITP
text | b0c5c9d7-741f-499a-937a-4bc0f55098be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pre-pour Inspection
label | 69932611-758a-47b8-9dda-549313688388 |  | note | REFERENCE: IFC Drawings
label | c58f0450-6692-4fc2-bb3d-27d11b905c21 |  | note | Bonded Anchors ITP
label | e7c2f02c-b2ab-461d-8c6a-670e6c3acad8 |  | note | 684.10 (b)
label | ea8d1f5a-58df-4537-9cd1-40dfc2e3c398 |  | note | ACCEPTANCE CRITERIA: All preparation works on the substrate have been completed and the surface moistened without free-standing water to prevent premature drying of the shotcrete.
label | aae7c1b3-0aac-4f62-8083-bd7c96f95487 |  | note | Evidence that the reinforcement and embedments are conforming to the requirements of the specifications and the IFC drawings.
label | 0e67638b-71a3-45e0-9fb9-0748f4be83d8 |  | note | METHOD: Measure , Visual
label | 9c938b52-deaa-4ae9-bc55-6e9a2fb0a3d2 |  | note | FREQUENCY: Each lot
label | d761a7ac-f808-4993-bcd2-5d7fd3972d11 |  | note | CATEGORY: HP
label | bdebf9b0-3cce-402d-8c2c-77403629775a |  | note | RESPONSIBILITY: Nominated Authority
label | f885bec7-99b7-45cc-b75d-a25f15644023 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9f72a3ff-4920-4a9b-8757-f1c2d7c86dee |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Weather Conditions & Evaporation Limits
label | ea807600-0514-4ce9-9ffd-9d6ee3f399f9 |  | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
label | 94ab2fa4-b0ba-4364-9071-79bddbca086d |  | note | 684.10 (b)
label | cf61a046-b688-4677-a963-608a0dcbae8e |  | note | 610.17
label | d0d6bba5-4715-4400-bf45-29804a55d757 |  | note | 610.17 (a) & (e)
label | 83c3abbd-1f73-4b00-9dab-f1262cf4339e |  | note | Table 610.171
label | 7b559305-2bc4-4386-b192-d9d7f07cc6ff |  | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | e1d89f4d-a4da-47cd-8148-7877810acd01 |  | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | dbfd0f77-3865-4347-ae47-e806b56d48df |  | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | e118aef7-e130-4308-9720-be2f441891bd |  | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | 57da3947-cd22-4b14-8fd7-f373cc6f0da1 |  | note | Record: Required information on the Concrete Pour Record.
label | d4cec654-cfe3-48d3-87a5-d7b386837186 |  | note | METHOD: Measure , Visual
label | 9984abe4-296d-4350-8045-93f7605ab2c1 |  | note | FREQUENCY: Each lot
label | 365b55db-6307-4fa3-8de0-54d3d5f816d0 |  | note | CATEGORY: IP
label | 77fb0502-db5a-4c9d-80bd-6facabdaf1c9 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 3be73f60-14fa-4456-91bf-3278e82dfa4e |  | note | VERIFYING DOCUMENTS: This ITP
text | cf5fe15e-baa9-4768-b644-8acc3ad3b227 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Concrete Testing - Sampling Frequency
label | 3cf40926-fd44-4d03-96e6-d9b3d8362e13 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 279c2987-e3c2-48a7-b73a-606f8e430ea5 |  | note | 684.08 (a)
label | 0d2a30fb-4767-4337-b5be-6ccc7bc72ad2 |  | note | RC 377.01
label | e363f8f4-d236-4c2e-ac48-ae7f7c5c33a7 |  | note | 610.16 (b)
label | 2c301276-90f0-4413-9aa4-807ac2be294a |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 2ed33af1-9631-4c78-b3c4-99dc91191206 |  | note | 0m³ to 10m³ = 1 sample
label | 4bea8762-4a2e-40c8-aa22-4f14ff226dec |  | note | 10m³ to 25m³ = 2 samples
label | 91c55158-9ed8-48b7-9886-6926f0788a5e |  | note | 25m³ to 50m³ = 3 samples
label | 883cb0a1-17c5-4799-a1e8-a8878bffeb28 |  | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | 95896596-9cdb-4a05-a1fc-5355f19242e9 |  | note | For each additional 50m³ and additional sample shall be taken.
label | 602de633-ca0d-4623-9717-54645aa42416 |  | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 9ad6dd05-16d0-4896-8517-f0d60c74912d |  | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | cb6dda14-9fc0-489b-a4f0-71281e6e4a4c |  | note | Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
label | 3a199311-927b-4637-904b-6dc737207e5d |  | note | Record: Required information on the Concrete Pour Record.
label | 6abc1add-54c7-46d1-ba35-86ad00770940 |  | note | METHOD: Test
label | 4aedbc0d-2a53-4468-bc04-6ffdba543108 |  | note | FREQUENCY: Each lot
label | 5f421ddc-656b-4a01-bde9-3c7b7c4c9066 |  | note | CATEGORY: IP
label | 52d0ef4b-2705-488a-879f-1167cd09a4f4 |  | note | RESPONSIBILITY: Concrete Tester , Foreman , SE/PE/SPE
label | 227f84f6-c66d-4aea-9b13-675e423b45cf |  | note | VERIFYING DOCUMENTS: This ITP
text | cd3f47de-994f-48a7-a486-da76516d92e5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Concrete Testing - Slump
label | 48fbe640-6e7a-4c8f-adb3-88fbc2db03b2 |  | note | REFERENCE: 684.08 (a)
label | 638737d3-78a8-4862-9a59-f88b5596ce4e |  | note | 610.16 (c)
label | c77f9fcc-aa5b-411b-8992-4dc29975314a |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | 8cbff3ac-666e-4f83-9ba3-f54f0a86ccd4 |  | note | <60mm = ±10mm
label | 4504cb60-0602-4e36-bf45-0d5bc40040a1 |  | note | ≥60mm to ≤80mm = ±15mm
label | 2ff37ae4-0c2d-438b-91b6-030da6eba71a |  | note | >80mm to ≤110mm = ±20mm
label | c6bcaa25-26f8-4f67-a6bb-77480bc7fd42 |  | note | >110mm to ≤150mm = ±30mm
label | 781b7a53-2858-4e82-83de-5b55f9de9eb1 |  | note | >150mm = ±40mm
label | ccf68014-e233-414f-b659-9151e03fad56 |  | note | Record: Required information on the Concrete Pour Record.
label | 670c3d84-b9b4-49c0-9856-5e5a979498d5 |  | note | METHOD: Test
label | 3c885789-f8d1-4791-a289-b4e6fb48f6cd |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | 535ab6b8-b152-4f26-be17-aa49641dbdf1 |  | note | CATEGORY: IP
label | a91662e2-0b1a-4868-8f13-4ab98615f9d1 |  | note | RESPONSIBILITY: Concrete Tester
label | c5ba8356-c5e2-4c9d-ae83-de6c92ee3b16 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5c0dd82a-dc88-478b-a9f6-6919d337d05b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Concrete Testing - Compressive Strength Cylinders
label | 98ef6720-a48e-44d9-9868-e28e9f22d932 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | d2c44b96-026f-40f3-88c9-86f4f072348f |  | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
label | 60751016-0ae0-4581-b709-d087a9d9ab88 |  | note | Record: Required information on the Concrete Pour Record.
label | 66b5f01a-878d-441b-8877-47cd88bca8c0 |  | note | METHOD: Test
label | 9d48f9af-8eca-4e2c-8650-48b9b47a9273 |  | note | FREQUENCY: Each sample
label | 314fe36b-4302-4dd0-94f8-307d64434d3b |  | note | CATEGORY: IP
label | 09a55f61-7817-496b-afe9-911501b8ca01 |  | note | RESPONSIBILITY: Concrete Tester
label | 273abb97-b387-46a5-8cc6-ad075d9aa655 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8322a424-d230-4fb9-b07d-3b0b1b7370ba |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Supply & Discharge Rates
label | d6a1ee97-e6c1-4ebd-9505-ba83612b7894 |  | note | REFERENCE: 684.05 (c)
label | abec1b47-fece-4332-807e-4272d5302827 |  | note | 610.13 (a) & (f)
label | 52acf65e-0e3d-4db0-bfc4-c51482631ede |  | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | e617ff43-ba0b-44f1-929e-b46ba1d30213 |  | note | No water is to be added once discharge commences.
label | b6c897fa-37ab-4c38-9b2e-63360ac4a669 |  | note | Maximum time between batching trucks is 25 minutes.
label | e27b7f0d-88dd-45c3-bd01-1c742f2f7ed2 |  | note | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | 53de54ae-b94e-4f63-9750-568e0d6dfdd9 |  | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 61e6589c-6ffa-4ba7-93f5-1f9d09644ab4 |  | note | Record: Required information on the Concrete Pour Record.
label | 756f3355-340c-4bf6-ac8e-4b162c76ef40 |  | note | METHOD: Measure , Visual
label | 41d04dbc-4330-437c-8e72-1d9d4ab1a63e |  | note | FREQUENCY: Each load
label | f54f7b0c-e077-4db7-90be-66344d4fd6c7 |  | note | CATEGORY: IP
label | 03b68e50-779d-4974-bc88-d8ba1ec0204d |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 5b593e21-2bf2-4b41-a5b0-1718601cc63e |  | note | VERIFYING DOCUMENTS: This ITP
text | 8894c3ea-8d80-4942-b17b-98f2075f0b62 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Shotcrete Work Method Statement
label | 6113a39b-81c7-4e08-a257-3539c1a1e2b7 |  | note | REFERENCE: 684.10 (b)
label | f33eac60-61ad-47d3-b25f-00595dc6fd2a |  | note | 684.13
label | 5551661f-79d5-437f-a1cb-e0b66ae68914 |  | note | 610.18 (a) & (b)
label | fee3f88e-f334-4257-87c8-a5befc6f5252 |  | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
label | 32c2503e-8607-4444-95bb-df8d9f17b4cd |  | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | e41e898f-ecbd-48f1-9f96-5464daef6782 |  | note | Probes or non-corrosive thickness indicators shall be used during the application to determine the actual application thickness.
label | 58ebc98b-8714-4a15-98f9-6e6a46c8b2c7 |  | note | The spray nozzle shall be held to ensure placement of concrete behind and around all steel reinforcement.
label | 7ae4b159-4df7-4945-b7ae-b1df6bc74384 |  | note | For vertical surfaces, application shall commence at the bottom and overhead surfaces shall be applied from the shoulder to the crown.
label | c53332fc-1c47-4455-b17f-dcfa99b853d1 |  | note | Each layer of the sprayed concrete shall be built up by making several passes over the working area with a maximum layer thickness of 150mm.
label | f6e65e5f-ab84-4bc2-837b-5360ca881b37 |  | note | Concrete shall not be sprayed through more than one layer of reinforcement in one application.
label | 9ade1ac1-9295-48d0-bfc6-b6a3e4d4955e |  | note | Where a layer of sprayed concrete is to be covered by succeeding layers, it shall be allowed to set prior to application of the succeeding layer without the need for curing compounds.
label | a1003797-800a-440c-bea1-1016ffff36a9 |  | note | The surface shall be checked for soundness, segregated, loose or otherwise uncompacted sprayed concrete removed, repaired as specified, cleaned, and wetted using a blast of air and water, leaving a dense, homogenous monolithic layer.
label | 10989eec-f152-440f-81f0-0b564932b118 |  | note | Record: Required information on the Concrete Pour Record.
label | 6689d4a4-5456-42fc-9b83-dd2d1ccfe6b1 |  | note | Attach: Concrete Pour Record
label | 3c59aa8f-3ec1-430b-b127-65a5ce411d9a |  | note | Attach: Concrete Dockets
label | fcf23966-b8ac-4bcc-ad9a-05947a7dc98d |  | note | METHOD: Visual
label | d60b602c-a435-4016-9b50-83a61e95bddc |  | note | FREQUENCY: Each load
label | ba219edb-dec3-4978-925a-1d0e3ffa50cb |  | note | CATEGORY: SP
label | 71a0e764-c59b-4cc7-937a-8f731b38de95 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
text | 9b4c26e2-3db3-4793-aedc-b656a51643b4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Surface Finishes
label | d4f249b6-17b2-48e8-bb18-93154905ccee |  | note | REFERENCE: IFC Drawings
label | 244e55aa-003a-40a1-ae07-4d339cd10b42 |  | note | 684.11
label | 972cf51a-a389-4612-81c0-04d524fe1a1c |  | note | 684.14
label | b64762f4-0a5d-4315-878d-eae094a1f7c4 |  | note | 610.31
label | 1d570293-a9ec-4d60-b1ac-20935437ac8e |  | note | 610.2
label | ad208640-ab77-4dc9-8af5-b9ab1fa6da2c |  | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
label | b07cafe5-f3d7-4784-bf20-2b52d110ee78 |  | note | Where surface finish is not detailed, structural concrete retaining walls, soil nail walls, tunnel linings, CP Overlay and other structural components forming part of permanent Works shall have a class 2 finish to reduce the chance of cracking.
label | 631dde9a-11c5-49b6-9c26-05ca3da9deb6 |  | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 10ddb101-6a13-495d-a7c2-8860e3956d61 |  | note | METHOD: Visual
label | b49aeeef-0e4a-46bc-b3ef-a97d3304974d |  | note | FREQUENCY: Each element
label | 8bbd1b56-b959-4212-bd10-d8868a19f24e |  | note | CATEGORY: IP
label | 50a5c285-2702-479b-a447-137a9f830c6f |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | a4b79d1f-36b2-4fbb-a344-605279c6ef93 |  | note | VERIFYING DOCUMENTS: This ITP
text | 69fdefc7-70df-441e-8c30-8ad55f36de97 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Curing
label | d2a0241f-61e7-4d60-9204-103c143a8587 |  | note | REFERENCE: Curing Methodology
label | 5c7e1f78-bcde-4738-97b7-fa03f6460979 |  | note | 684.10 (b)
label | c64b2fda-a423-4f62-aae3-32d687a9519e |  | note | 610.23
label | 851b246a-e244-415e-84ca-935648b12194 |  | note | Table 610.231
label | f6bb2a43-766d-4821-aa00-4e4ebb1103a8 |  | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | 387ba238-723c-4af2-9c93-1f371e06648e |  | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | 91ad1077-1902-4c3f-8504-c16dbfeeb804 |  | note | METHOD: Visual
label | d40774b4-3c64-42f1-af93-5b123b9e7317 |  | note | FREQUENCY: Each lot
label | 367138df-4fa5-4c93-80b7-a5aadacd7cc5 |  | note | CATEGORY: SP
label | 352c3f32-d926-458d-9a8b-be56ddaa2ee6 |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 2e5467b5-edcc-4f04-949a-09e2b3a3a4a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8fc86315-3b04-4934-ac5e-9682af720077 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Concrete Testing - Core Sample Frequency
label | 4095e588-18f9-43b6-a436-8c3720642dd6 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 144e4f07-3a14-42e8-90a4-1cf75f332e5d |  | note | 684.04 (d)
label | 2b10a646-5e64-4fb1-8606-bcf4ae43fe49 |  | note | Table 684.041
label | 050b9e75-f098-4907-9230-3b7492a6003f |  | note | 610.16 (b)
label | ad66fc8f-dccc-46f1-bc60-8ad087713eac |  | note | ACCEPTANCE CRITERIA: 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
label | 1c02795e-30d6-4616-b8ed-a0249132083c |  | note | 0m³ to 25m³ = 1 sample
label | b15b60a9-f0b3-4745-9075-cf28decdd960 |  | note | 25m³ to 50m³ = 2 samples
label | 55cf6754-26a7-4229-a5c0-f039beec4df0 |  | note | For each additional 50m³ an additional sample shall be taken.
label | b2a90c1e-d928-451a-ac03-7f4a521ffdc5 |  | note | Each sample shall consist of 5 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
label | 93871d5f-ba22-4c52-ab2b-84899f096805 |  | note | Core samples shall be tested for:
label | c402fecf-df63-4e80-8fee-bd07216c01bc |  | note | 1 no. 7 day compressive strength
label | 031b131a-d57f-4fc4-ba7b-0033d8959b8a |  | note | 2 no. 28 day compressive strength
label | 2e6b90c3-cd7c-48e7-ae2d-15a1c6acfa22 |  | note | 2 no. VPV tests
label | f6e56e15-6a19-400d-8d97-8986b7a3520f |  | note | Note: MRPA has D.o.T acceptance to remove the 3 day core and take core samples on test panels in lieu of completed Works
label | 97b63043-e4a9-4a2c-bf15-6aaeeefc1e12 |  | note | See:
label | 41f74a87-d495-4b8e-9c88-575ae30eeefc |  | note | MRP-MRPA-GNC-XCN-0096
label | dbabf04b-f2cf-48b5-b861-2b4f3f1b22f3 |  | note | E-mail from D.o.T 7.06.2021
label | e2e8d0a5-67fe-42c3-9926-53fefd09c1f5 |  | note | METHOD: Test
label | f890d1c7-4b41-4522-a99c-bd5cc27840eb |  | note | FREQUENCY: Each lot
label | 2ed56aa2-4e24-4549-a4aa-4c7409744e89 |  | note | CATEGORY: IP
label | 97fff06d-3726-416a-850d-94ce1f9634eb |  | note | RESPONSIBILITY: Foreman , SE/PE/SPE
label | 46730626-b8c0-413b-8d95-8c7020cf47c9 |  | note | VERIFYING DOCUMENTS: This ITP
text | e2508878-8df8-483b-84e0-69b59708f705 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength & VPV Test Results
label | 4da5eeae-3d17-45a9-b63f-22fcee41d162 |  | note | REFERENCE: IFC Drawings
label | 51407a0d-6588-4c28-a71b-fb9b212f307b |  | note | 684.08 (e) (i - iii)
label | f8ea89ad-8363-4799-a39a-b290e468328f |  | note | Table 610.051
label | 397bf962-e515-4541-89d6-a3069552781c |  | note | Table 610.061
label | db936c22-7801-4bd8-92c1-303ea8d67e33 |  | note | 610.16 (g)
label | 5f797d50-2a29-4abd-94cb-e6444082cda4 |  | note | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 8970c6c2-a79a-4a61-b10c-4027234c17b8 |  | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
label | 71680a4c-4248-492e-ad80-075c87cdbb68 |  | note | Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
label | 2b5fa82c-2d39-451a-a941-abba0507c56b |  | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | d6645b40-8713-4ce7-91ae-2fee5a1e8a16 |  | note | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
label | 326e58ee-e7f6-4029-a8c7-36da0eba5f74 |  | note | Attach: Compressive Strength Test Results
label | ca3020da-09d4-4fb0-bba6-bd83cbc6d25b |  | note | Attach: Core Sample Compressive Strength Test Results
label | 4af7ff67-27b1-4eac-9331-017607522465 |  | note | METHOD: Document Review
label | 3c1d6d78-8dcf-43da-8573-5a08a84a2160 |  | note | FREQUENCY: Each cylinder and core sample
label | 042b26b6-4217-44d2-ab24-686c2d178fce |  | note | CATEGORY: IP
label | 5cdf8c7b-41c4-4dc7-bea2-dbf413419b51 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 2bf46c5c-275f-462c-bdff-e95d77f4fdbb |  | note | VERIFYING DOCUMENTS: This ITP
text | f51ec6ca-3115-43f4-8edd-0b219e128372 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Surface Inspection
label | 01541e35-39ba-47e7-8706-001a4658614b |  | note | REFERENCE: IFC Drawings
label | 42b3fce8-e9c0-4334-a70f-42ad938b21f5 |  | note | 684.08 (b)
label | fc91e928-3d8b-489e-998d-ccea04c2f39d |  | note | 684.15
label | 7b92f162-1286-46b9-9385-06daf295a087 |  | note | 684.16
label | ddf773d0-bd61-4777-9e75-9dcca74209f2 |  | note | 610.31 (a) - (n)
label | 6aa65662-6eb7-4bae-a9bf-6f052b9bfca6 |  | note | 610.32
label | a9157ebc-7271-4f33-b1fb-a1a1ac64536b |  | note | 610.24
label | 3dc128eb-e431-4216-9ed5-43d1e1631da1 |  | note | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
label | e245f38e-e186-43a8-9590-63b5a5269ccf |  | note | Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
label | d4d32443-e5d1-4f9a-9bbf-ee9c10ec14a6 |  | note | For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
label | 4b679161-3bd1-40af-858c-cb09d548fa0d |  | note | No cracks greater than 0.2mm (exposure classification B1)
label | 6d314723-8387-428a-8d58-812cfb4db172 |  | note | If cracking is observed, complete the Structural Concrete Crack Repair ITP for investigation and repair.
label | dd44757e-6c41-41fa-a5c9-5c01cea6442b |  | note | METHOD: Visual , Measure
label | caefc209-7c8b-4748-b6b8-79f3b30ca4c0 |  | note | FREQUENCY: Each element
label | d7f460e7-4a48-4f31-9311-55bcd3fd5222 |  | note | CATEGORY: IP
label | c772fc82-b173-470d-81a8-74679ef4aaf5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 05987f71-4c03-4ccf-90d0-0c12af8fadad |  | note | VERIFYING DOCUMENTS: This ITP and/or Structural Concrete Crack Repair ITP
text | 959bcc32-a4ea-47a8-a12b-ca8968457ec8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Fibre Wash-out Test Results
label | 3d3a51e9-3617-4226-9381-8c38e179af96 |  | note | REFERENCE: 684.08 (c)
label | ed615112-0562-4ceb-a9b3-38e7b6840421 |  | note | ACCEPTANCE CRITERIA: Fibre wash-out test results shall be within 1% of the concrete mix design fibre dosage rate.
label | 8e748919-65f0-4af9-8acf-637484487054 |  | note | Attach: Fibre Wash-out Test Results
label | f18c665e-f7ab-4b32-bf3b-6c20caa7c357 |  | note | METHOD: Document Review
label | 0a5bddf0-b196-428f-95ce-0820ff1ff0e2 |  | note | FREQUENCY: Where applicable, each test
label | 0f673c7c-f048-4cce-813f-5cb3566bc8e0 |  | note | CATEGORY: IP
label | d8f4101d-e029-4a16-9589-d9460c2bd6a2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | f11ea395-056a-47cf-9eb0-b07208aa0050 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2e72cf24-96fd-40ed-9401-8f9f11719dc7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 As-built Survey
label | c05addb1-e9fa-4e9d-9985-6902647f7f0b |  | note | REFERENCE: IFC Drawings
label | f1d2a83c-ec43-4c70-b98d-911379fe8c5a |  | note | 684.13
label | 33dc3645-7a2a-42ae-b8d2-ec2eb9054f95 |  | note | 610.47
label | c95067bd-1bd7-412c-8efc-4a5a5832e949 |  | note | Table 610.472
label | 0257dd40-bd4b-4340-b454-644f7957ef36 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | e71b2456-764d-4427-819d-a18841e6e631 |  | note | Where a shape is required, ±25mm with no depressions greater than 15mm.
label | dd5c1a2b-9b60-4fd0-9a13-172481e836dd |  | note | Attach: Survey As-builts / Survey Report
label | f581e297-ccfe-4284-be2c-a8415fe9f236 |  | note | METHOD: Document Review
label | f5147482-cd45-45cc-9101-0a2294cd83e1 |  | note | FREQUENCY: Each element
label | 542ad597-62c1-4e24-99a5-99f348419bdb |  | note | CATEGORY: IP
label | 1a24b77a-8e18-4274-9267-15cba6af3ca9 |  | note | RESPONSIBILITY: Surveyor , SE/PE/SPE
label | 457a5b92-ed79-4768-8c5c-9bf8c11be929 |  | note | VERIFYING DOCUMENTS: This ITP
text | d0a7a3af-11b3-4da8-9536-239d3f50c5ac |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | 5c2f1d21-3e0d-48d3-9f2c-68ea2f9c1c3f |  | note | REFERENCE: MRPA Quality Management Plan
label | f750f7af-2203-42c9-ac2c-51a450309a37 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | e0406cc6-a5d0-46c1-932d-b62e542eb8f8 |  | note | METHOD: Document Review
label | 469fe4f8-4bad-4255-9c21-0e799f001587 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 6b6b1442-cfda-4737-bb37-c25fd6963e85 |  | note | CATEGORY: HP*
label | 2f1962c3-2d9c-4f20-aaa5-04a32cf40c45 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d0da31f8-ef86-4a24-a1fd-5f609b828a5b |  | note | VERIFYING DOCUMENTS: This ITP
text | 78df584b-43bd-4e9b-a93d-ee19acd430ca |  | textbox | Date Completed: