## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-001-CIV-Stormwater Drainage Pipes Installation | itp |  |  |  |  | CHK-001-CIV-Stormwater Drainage Pipes Installation
checkpoint | CHK-001-CIV-Stormwater Drainage Pipes Installation
label | Document Title: CHK-CIV-RSS Walls-Fill Placement
label | Check list Description: Stormwater Drainage Pipes Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: [Date of Approval]
label | ITP created by: Jon De Castro
label | ITP approved for use by: Aldrin Guinchoma
checkpoint | 1 - Pipes - Survey Set-out
label | REFERENCE:
label | • Section 701.10
label | • IFC Drawings
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 4.1
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Pipes are set-out in accordance to IFC Drawings and Section 701.10 with the following tolerances below.
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ---------------------------------
label | METHOD: Survey
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: HP*
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Survey Report
label | ---------------------------------
textbox | Date Completed:
checkpoint | 2 - Pipes - Trench Excavation
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.15
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.12
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Excavation for pipe have a horizontal clearance between the pipe and the excavation wall as per below.
label | > 300mm, < 600mm for RCP
label | > 150mm for Flexible Pipe
label | 2. The base of the trench have been compacted to refusal using mechanical plant.
textbox | Trench depth :
textbox | Drawing Reference No:
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 3 - Pipes - Bedding Placement
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.16
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.13
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Bedding material provided and placed in the full width of the trench to the below minimum:
label | > 100mm where D<1500mm
label | > 200mmwhwere D≥1500mm
label | 2. Bedding material placed and compacted in layers <150mm loose thickness
label | @Jesse - please check bedding requirements as per design (use sand bedding?)
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 4 - Pipes - Bedding Testting
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.20
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.14
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding).
label | 2. Three (3) tests done per lot.
label | 2. Bedding compacted to refusal by hand held mechanical equipment & material (Swell ≥ 2.5%) mean moisture ratio of 92% between the completion of rolling and the placement of overlaying laye.
label | Responsible Engineer to confirm if the bedding testing is required for this lot.
label | ---------------------------------
label | METHOD: Compaction Test
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Test Reports
label | ---------------------------------
textbox | Date Completed:
checkpoint | 5 - Pipes - Placement of Pipe - RCP
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.17
label | • Section 701.20
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.15
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Correct size of pipe installed
textbox | Pipe Dia ________;
textbox | Drawing Reference No.
label | 2. Pipes phycially checked and confirmed No Damage prior to install
label | 3. Rebate and socket ends of pipe segments placed facing upstream and be fully engaged
label | 4. Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 5. Lower portion of pipe in contact with the bedding layer and shaped to accomodate the joint collar
label | 6. Correct type and size of rubber rings used and properly installed at pipe joints
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 6 - Pipes - Placement of Pipe - Flexible Pipe
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.17
label | • Section 701.22
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.16
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Correct size of pipe installed
textbox | Pipe Dia ________;
textbox | Drawing Reference No.
label | 2. Pipes phycially checked and confirmed No Damage prior to install
label | 3. Rebate and socket ends of pipe segments placed facing upstream and be fully engaged
label | 4. Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 5. Lower portion of pipe in contact with the bedding layer and shaped to accomodate the joint collar
label | 6. Correct type and size of rubber rings used and properly installed at pipe joints
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 7 - Pipes - Lifting Holes
label | REFERENCE:
label | • Section 701.18
label | • ITP-008-CIV-Stormwater Drainage - Item 5.17
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Lifting holes plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | ---------------------------------
label | METHOD: Visual inspection
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 8 - Pipes - Survey Conformance
label | REFERENCE:
label | • Section 710.10
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.18
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | Each run of underground drainage shall be Survey verified prior to backfilling.
label | - Offset pits to kerb +/- 20mm
textbox | Drawing Ref No.
label | - Plan location pits not adjacent to kerb +/- 100mm
textbox | Drawing Ref No.
label | - Invert level of pipes at pits +/- 50mm
textbox | Drawing Ref No.
label | - Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
textbox | Drawing Ref No.
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Survey Report
label | ---------------------------------
textbox | Date Completed:
checkpoint | 9 - Pipes - Backfill Placement
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.16
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.19
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Correct type of Backfill material used.
label | 2. Backfill material placed full width of bedding material and compacted in layers <150mm loose thickness.
label | 3. Filling not placed within 2.0m of the open end of the pipe.
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 10 - Pipes - Backfill Testing
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.20
label | • Section 701.29
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.20
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill).
label | 2. Backfill material compacted to a density ratio > 97%.
label | 3. Material with ≥ 2.5% have been maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer.
label | ---------------------------------
label | METHOD: Compaction Test
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: HP*
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Test Results
label | ---------------------------------
textbox | Date Completed:
checkpoint | 11 - Flushing & CCTV
label | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.1
label | ---------------------------------
label | ACCEPTANCE CRITERIA: In accordance with Section 701.28, Section 701.30
label | ---------------------------------
label | METHOD: Record Review
label | ---------------------------------
label | FREQUENCY: Each lot
label | ---------------------------------
label | CATEGORY: HP
label | ---------------------------------
label | RESPONSIBILITY: Nominated Authority
label | ---------------------------------
label | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | ---------------------------------
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 12 - As Built Survey
label | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.2
label | ---------------------------------
label | ACCEPTANCE CRITERIA: In accordance with Section 701.10
label | ---------------------------------
label | METHOD: Document Review
label | ---------------------------------
label | FREQUENCY: Each lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | ---------------------------------
textbox | Date Completed:
checkpoint | 13 - Repairs to Damaged Pipes
label | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.3
label | ---------------------------------
label | ACCEPTANCE CRITERIA: In accordance with Section 701.31
label | ---------------------------------
label | METHOD:
label | • Document Review for Repair Procedure
label | • CCTV Report Review
label | • Visual Inspection
label | ---------------------------------
label | FREQUENCY: Each lot
label | ---------------------------------
label | CATEGORY: HP
label | ---------------------------------
label | RESPONSIBILITY: Nominated Authority
label | ---------------------------------
label | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | ---------------------------------
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 14 - Non-conformance Report (NCR) Closure
label | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.4
label | ---------------------------------
label | ACCEPTANCE CRITERIA: In accordance with MRPA Quality Management Plan
label | ---------------------------------
label | METHOD: Document Review
label | ---------------------------------
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | ---------------------------------
label | CATEGORY: HP*
label | ---------------------------------
label | RESPONSIBILITY: PE
label | ---------------------------------
label | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | ---------------------------------
textbox | Date Completed: