## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-002-CIV-Stormwater Drainage Pits Installation | itp |  |  |  |  | CHK-002-CIV-Stormwater Drainage Pits Installation
checkpoint | CHK-002-CIV-Stormwater Drainage Pits Installation
label | Document Title: CHK-002-CIV-Stormwater Drainage Pits Installation
label | Check list Description: Stormwater Drainage Pits Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: [Date of Approval]
label | ITP created by: Jon De Castro
label | ITP approved for use by: Aldrin Guinchoma
checkpoint | 1 - Pits - Survey Set-out
label | REFERENCE:
label | • Section 701.10
label | • IFC Drawings
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 4.1
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Pits are set-out in accordance to IFC Drawings and Section 701.10 with the following tolerances below.
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of Pits at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ---------------------------------
label | METHOD: Survey
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: HP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Survey Report
label | ---------------------------------
textbox | Date Completed:
signoff | HOLDPOINT
checkpoint | 2 - Pits - Excavation
label | REFERENCE:
label | • IFC Drawings
label | • Section 705.05
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.1
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Excavation depth as indicated on the IFC Drawings
textbox | Excavation depth:
textbox | Drawing Reference No:
label | 2. For precast pits the excavation to have minimum clearance of 400mm from face of the excavation
textbox | Excavation depth:
textbox | Minimum clearance from all faces of pit to face of excavation:
textbox | Drawing Reference No:
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 3 - Pits - Placement of Bedding Material
label | REFERENCE:
label | • IFC Drawings
label | • Section 705.05
label | • ITP-008-CIV-Stormwater Drainage Suppy & Installation - Item 5.2
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | > 80mm for clay foundations
label | > 150mm for rock foundations
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 4 - Pits - Bedding Testting
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.20
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.3
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding).
label | 2. Three (3) tests done per lot.
label | 2. Bedding compacted to refusal by hand held mechanical equipment & material (Swell ≥ 2.5%) mean moisture ratio of 92% between the completion of rolling and the placement of overlaying laye.
label | Responsible Engineer to confirm if the bedding testing is required for this lot.
label | ---------------------------------
label | METHOD: Compaction Test
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Test Reports
label | ---------------------------------
textbox | Date Completed:
checkpoint | 5 - Pits - Placement of Precast Drainage Pit
label | REFERENCE:
label | • IFC Drawings
label | • Section 701.10
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.4
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Pits phycially checked and confirmed No Damage prior to install
label | 2. Survey pick-up to verify:
label | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 6 - Pits - Cast in Place Drainage Pit
label | REFERENCE:
label | • IFC Drawings
label | • Section 705.06
label | • Section 610
label | • Section 611
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.5
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Cast in place drainage pits shall be constructed at locations and to the dimensions shown on the IFC Drawings and in accordance with Sections 610 and 611.
textbox | – Concrete Mix Design:
textbox | – Reinforcement & Formwork Checks:
textbox | – Min Cover:
textbox | – Drawing Ref No.
label | 2. Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 7 - Pits - Jointing & Drainage Connections
label | REFERENCE:
label | • IFC Drawings
label | • Section 705.11
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.6
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. All connections to drainage pits neatly made in accordance with Section 705.11.
label | 2. Openings into drainage pit walls neatly saw cut to the required size not more than 50mm greater than pipe diameter.
label | 3. Breaking out of holes is not permitted.
label | 4. Drainage pits to be replaced if cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 5. Exposed reinforcement to be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 8 - Pits - Shaping of Floor
label | REFERENCE:
label | • Section 705.13
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.7
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Drainage pit floors smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • This Checklist
label | • Survey Report
label | ---------------------------------
textbox | Date Completed:
checkpoint | 9 - Pits - Step Irons
label | REFERENCE:
label | • IFC Drawings
label | • Section 705.12
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.8
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Drainage pits greater than 1.0m deep fitted with step irons in accordance with 705.12.
label | 2. Ladder rungs to not obstruct openings and that water does not discharge on them.
label | 3. Step rungs do not come within 50mm of the top of the riser.
label | 4. Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | ---------------------------------
label | METHOD:
label | Visual inspection
label | Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 10 - Pits - Fitting of Covers
label | REFERENCE:
label | • IFC Drawings
label | • Section 705.17
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.9
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Frames for drainage pit covers to be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement.
label | 2. Height within 10mm of the design level.
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 11 - Pits - Pit Lids
label | REFERENCE:
label | • IFC Drawings
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.10
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. All stormwater pits to be provided with locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | ---------------------------------
label | METHOD: Visual inspection
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed:
checkpoint | 12 - Pits - Backfilling Around Drainage Pits
label | REFERENCE:
label | • Section 705.18
label | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.11
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | 1. Backfilling around drainage pits placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | ---------------------------------
label | METHOD:
label | • Visual inspection
label | • Measure
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: This Checklist
label | ---------------------------------
textbox | Date Completed: