## Pipes Installation Checklist
ConQA Team Notes:
Document Title: |  | CHK-003-CIV-Reinforced Concrete Pipe (RCP)-Material Delivery Inspection
Check list Description: |  | Reinforced Concrete Pipe (RCP)-Material Delivery Inspection
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | [Date of Approval]
ITP created by: |  | Jon De Castro
ITP approved for use by: |  | Aldrin Guinchoma
Special Notes to ConQA Team : |  | This Checklist is only to be used in Camms Rd Project
Item | Task/Activity Description | Reference / ITP Reference | Acceptance Criteria | Pass | Fail | N/A | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
[7 empty] | Method | Frequency | Category
1 | Materials - Fabrication | IFC Drawings Section 620 Section 701 | (1) Precast items manufactured in accordnace with IFC Drawings - Drawing Ref No. _____________________________________ |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket
2 | Materials - Delivery | IFC Drawings Section 620 Section 701 | (1) Purchase Order and Material Description and Qtys matches (2) Ensure precast concrete elements are as per IFC Drawings upon delivery and no damage evident. (3) Lifting and Manufacture compliance certification provided - Purchase Order No. __________________________________ |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket Purchase Order
3 | Materials - Manufacture's Certificate of Compliance | IFC Drawings Section 620 Section 701 | (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting. |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket Compliance Certificate
4 | Materials - Delivery to site | IFC Drawings Section 620 Section 701 | (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element. |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket
5 | Materials - Others | IFC Drawings Section 620 Section 701 | (For Additional Comments) |  |  |  | Visual Inspection | Each Lot | IP | SE | Material Delivery Docket