## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-003-CIV-Reinforced Concrete Pipe (RCP)-Material Delivery Inspection | itp |  |  |  |  | CHK-003-CIV-Reinforced Concrete Pipe (RCP)-Material Delivery Inspection
checkpoint | CHK-003-CIV-Reinforced Concrete Pipe (RCP)-Material Delivery Inspection
label | Document Title: CHK-003-CIV-Reinforced Concrete Pipe (RCP)-Material Delivery Inspection
label | Check list Description: Reinforced Concrete Pipe (RCP)-Material Delivery Inspection
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: [Date of Approval]
label | ITP created by: Jon De Castro
label | ITP approved for use by: Aldrin Guinchoma
checkpoint | 1 - Materials - Fabrication
label | REFERENCE:
label | • IFC Drawings
label | • Section 620
label | • Section 701
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | (1) Precast items manufactured in accordnace with IFC Drawings
textbox | – Drawing Ref No.
label | ---------------------------------
label | METHOD: Visual Inspection
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 2 - Materials - Delivery
label | REFERENCE:
label | • IFC Drawings
label | • Section 620
label | • Section 701
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | (1) Purchase Order and Material Description and Qtys matches
label | (2) Ensure precast concrete elements are as per IFC Drawings upon delivery and no damage evident.
label | (3) Lifting and Manufacture compliance certification provided
textbox | - Purchase Order No.
label | ---------------------------------
label | METHOD: Visual Inspection
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • Material Delivery Docket
label | • Purchase Order
label | ---------------------------------
textbox | Date Completed:
checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
label | REFERENCE:
label | • IFC Drawings
label | • Section 620
label | • Section 701
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
label | ---------------------------------
label | METHOD: Visual Inspection
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS:
label | • Material Delivery Docket
label | • Compliance Certificate
label | ---------------------------------
textbox | Date Completed:
checkpoint | 4 - Materials - Delivery to site
label | REFERENCE:
label | • IFC Drawings
label | • Section 620
label | • Section 701
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
label | (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
label | ---------------------------------
label | METHOD: Visual Inspection
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: Material Delivery Docket
label | ---------------------------------
textbox | Date Completed:
checkpoint | 5 - Materials - Others
label | REFERENCE:
label | • IFC Drawings
label | • Section 620
label | • Section 701
label | ---------------------------------
label | ACCEPTANCE CRITERIA:
textbox | (For Additional Comments)
label | ---------------------------------
label | METHOD: Visual Inspection
label | ---------------------------------
label | FREQUENCY: Each Lot
label | ---------------------------------
label | CATEGORY: IP
label | ---------------------------------
label | RESPONSIBILITY: SE
label | ---------------------------------
label | VERIFYING DOCUMENTS: Material Delivery Docket
label | ---------------------------------
textbox | Date Completed: