## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | e454aedb-c9b5-446d-b725-4bd812c46a76
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Stopping Works |  |  |  |  | Yes | Add Stopping Works Checklist | c37cd6ba-293f-4f5c-a8c1-ec5e46215b51
checkpoint-group |  |  | section | Area prep
select | 8c2a9368-2ff8-4961-bc76-e2a90dcfb52a | Data not allowed on checkpoint-group. | dropdown | Area | External,Internal
checkpoint-status |  |  | checkpoint | Area ready and accessible
checkpoint-status |  |  | checkpoint | Gib level and plumb
checkpoint-group |  |  | section | Stopping QA
checkpoint-status |  |  | checkpoint | First Coat completed
checkpoint-status |  |  | checkpoint | Second coat completed
checkpoint-status |  |  | checkpoint | Finny coat completed
checkpoint-status |  |  | checkpoint | Check the following
boolean | 4ba779b5-1414-435e-bfac-f35a3e6dde8d |  | tickbox | Joints
boolean | 7ca02982-1f27-4dbe-ae7b-1dc604c31f38 |  | tickbox | Screws
boolean | c9de260a-5d1e-4895-b0a3-aec8471b20e9 |  | tickbox | Slimlines
boolean | 2f019231-ad4f-495d-b973-96252b2e6d79 |  | tickbox | Interior corners
boolean | fbb23b35-43e1-462c-926f-2cec023d6437 |  | tickbox | Square stopping
boolean | 560503df-9069-4777-a51d-e41220779f5b |  | tickbox | Negative detail
boolean | 3335462c-8029-43a1-a400-e5a4196d4538 |  | tickbox | Casing bead
boolean | 5c82c944-8d79-4796-8f2f-cd32eee2e1b7 |  | tickbox | Gib Cove
boolean | 0fe8bd62-bb76-4a5f-82ff-7c989ab34a15 |  | tickbox | Access Hatch
boolean | 6c779101-3c8f-4666-887b-1b3affcbd150 |  | tickbox | Screws and gaps around doors and windows
checkpoint-status |  |  | checkpoint | Light check - Stopping remedials
checkpoint-status |  |  | checkpoint | Light check - Sanding remedials
checkpoint-status |  |  | checkpoint | Damage reviewed and fixed
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area clean and tidy
checkpoint-status |  |  | checkpoint | Floors scraped
checkpoint-status |  |  | checkpoint | Aluminium Joinery cleaned
checkpoint-status |  |  | checkpoint | Exposed concrete surfaces cleaned
checkpoint-status |  |  | checkpoint | Exposed pipes/ structural steel cleaned
checkpoint-status |  |  | checkpoint | Finishing lines cleaned
checkpoint-status |  |  | checkpoint | Penetrations cleaned
checkpoint-status |  |  | checkpoint | Painter signoff
holdpoint |  |  | signoff | Signature
checkpoint-status |  |  | checkpoint | Contractor Signature
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | Exterior Painting QA |  |  |  |  | Yes | Add Exterior Painting Checklist | ad74b1fd-2ea1-4a28-85e1-8c143e96dda9
checkpoint-group |  |  | section | Area prestart checks
checkpoint-status |  |  | checkpoint | Colour schedule received
checkpoint-status |  |  | checkpoint | Samples Approved
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-status |  |  | checkpoint | Scaffolding/Ladders required and available
checkpoint-status |  |  | checkpoint | Check with Main Contractor for advise to DOL for Working Heights
checkpoint-status |  |  | checkpoint | Work area clean/dustfree/Safe to work
checkpoint-group |  |  | section | Painting QA
checkpoint-status |  |  | checkpoint | Preliminary checks on Cladding/ Substrate
checkpoint-status |  |  | checkpoint | Installation/Nails punched
checkpoint-status |  |  | checkpoint | Scribers/Corner coverboards installed
checkpoint-status |  |  | checkpoint | Fascia Board - Filled/Sand and applied with onecoat sealer and 2 top coats
checkpoint-status |  |  | checkpoint | Soffit - Flushing
checkpoint-status |  |  | checkpoint | Soffit - Painted with One Sealer and 2 Top Coats
checkpoint-status |  |  | checkpoint | Masking/Protection in Place
checkpoint-status |  |  | checkpoint | Sealer coat applied to walls
checkpoint-status |  |  | checkpoint | Nail holes filled/Sanded
checkpoint-status |  |  | checkpoint | No more gabs filled
checkpoint-status |  |  | checkpoint | Sealer coat sanded
checkpoint-status |  |  | checkpoint | Apply first top coat
text | 808f86c6-bb22-4ab5-8be7-a45a77140927 |  | textbox | Microns
checkpoint-status |  |  | checkpoint | Sanding between top coat
text | a846a780-e38c-4204-b85f-52daacd8bea1 |  | textbox | Microns
checkpoint-status |  |  | checkpoint | Apply second top coat
text | 29c6a023-88ea-4b74-bfa8-606f3bc7b593 |  | textbox | Microns
checkpoint-status |  |  | checkpoint | Window scriber/Frames and surround painted
checkpoint-status |  |  | checkpoint | Corner cover board painted
checkpoint-status |  |  | checkpoint | Roller brush marks visible Q/A
checkpoint-group |  |  | section | Completion and handover
checkpoint-status |  |  | checkpoint | Masking removed/Disposed
checkpoint-status |  |  | checkpoint | Concrete flor/Pavers cleaned
checkpoint-status |  |  | checkpoint | Empty buckets removed and disposed
checkpoint-status |  |  | checkpoint | All fixers/Fittings cleaned of paint
checkpoint-status |  |  | checkpoint | Aluminium joinery cleaned of paint
checkpoint-status |  |  | checkpoint | Remedial painting rectified
checkpoint-status |  |  | checkpoint | Painter signoff
holdpoint |  |  | signoff | Signature
checkpoint-status |  |  | checkpoint | Contractor Signature
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | Plastering QA |  |  |  |  | Yes | Add Plastering QA | 84707651-a531-428b-91ed-f7d6e4cbb144
checkpoint-group |  |  | section | Preapplication QA
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
holdpoint |  |  | signoff | Request Review/Raise remedial
checkpoint-group |  |  | section | Fire Stopping
checkpoint-status |  |  | checkpoint | Fire Stopping installed and completed
checkpoint-group |  |  | section | GIB Stopping for walls
checkpoint-status |  |  | checkpoint | Sanding completed for walls
checkpoint-group |  |  | section | GIB Stopping for Ceiling
checkpoint-status |  |  | checkpoint | Sanding completed (1st go)
checkpoint-status |  |  | checkpoint | Coving completed
checkpoint-status |  |  | checkpoint | Square stopping completed
checkpoint-status |  |  | checkpoint | Sanding completed (2nd go)
checkpoint-group |  |  | section | Handover checks
checkpoint-status |  |  | checkpoint | Area left tidy
checkpoint-status |  |  | checkpoint | All works completed 100% as per spec
holdpoint |  |  | signoff | Request Review/Raise remedial
checklist-sectioned |  |  | checklist | Painting QA |  |  |  |  | Yes | Add Room Painting QA | c4259789-85eb-4a46-aa6a-dc33cd6c717e
checkpoint-group |  |  | section | Preapplication QA
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable and ok to begin work
holdpoint |  |  | signoff | Request Review/Raise remedial
checkpoint-group |  |  | section | Painting
checkpoint-status |  |  | checkpoint | Prep work for windows and doors completed
checkpoint-status |  |  | checkpoint | Sealer coat completed
checkpoint-status |  |  | checkpoint | Light check completed
checkpoint-status |  |  | checkpoint | Stopping/ Filling/ Silicone works completed
checkpoint-status |  |  | checkpoint | Prepping and sanding completed and ready to paint
checkpoint-status |  |  | checkpoint | First top coat completed
checkpoint-status |  |  | checkpoint | Second top coat completed
checkpoint-status |  |  | checkpoint | Final checks completed
checkpoint-group |  |  | section | Handover checks
checkpoint-status |  |  | checkpoint | Area left tidy
checkpoint-status |  |  | checkpoint | All works completed 100% as per spec
holdpoint |  |  | signoff | Request Review/Raise remedial
checklist-sectioned |  |  | checklist | Interior Painting QA |  |  |  |  | Yes | Add Interior Painting Checklist | a9b9ba83-af0d-465f-8dbc-97ed4c6568f4
checkpoint-group |  |  | section | Area prestart checks
checkpoint-status |  |  | checkpoint | Colour schedule received
checkpoint-status |  |  | checkpoint | Samples Approved
checkpoint-status |  |  | checkpoint | Weather recorded
checkpoint-status |  |  | checkpoint | Work area clean/dustfree/Safe to work
checkpoint-status |  |  | checkpoint | Avoid over spray on concrete
checkpoint-status |  |  | checkpoint | Floors/protection in place
checkpoint-group |  |  | section | Painting QA
checkpoint-status |  |  | checkpoint | Preliminary checks on stopping for Trowel marks or defects
checkpoint-status |  |  | checkpoint | Check for any factors that could affect the painting of the board
checkpoint-status |  |  | checkpoint | Masking/Protection in place
checkpoint-status |  |  | checkpoint | Sprinklers covered
checkpoint-status |  |  | checkpoint | Doors removed/ Hinges kept in a safe place
checkpoint-status |  |  | checkpoint | Sealer coat applied
checkpoint-status |  |  | checkpoint | Nail holes filled/Sanded on timber joinery
checkpoint-status |  |  | checkpoint | Sealer coat sanded on Wall and ceilings
checkpoint-status |  |  | checkpoint | Stopper return for light check
checkpoint-status |  |  | checkpoint | Remedial stopping carried out
checkpoint-status |  |  | checkpoint | Reseal remedied stopping areas
checkpoint-status |  |  | checkpoint | Top coat mixed well/strainer
checkpoint-status |  |  | checkpoint | Apply first top coat
text | a514f2b8-3c4b-4311-8f60-d4833f1df0c6 |  | textbox | Microns
checkpoint-status |  |  | checkpoint | Doors painted
checkpoint-status |  |  | checkpoint | Door jambs/Stopper/Architraves painted
checkpoint-status |  |  | checkpoint | Window liner/Frames painted
checkpoint-status |  |  | checkpoint | Skirtings painted
checkpoint-status |  |  | checkpoint | Doors painted in place
checkpoint-status |  |  | checkpoint | Roller brush marks visible Q/A
checkpoint-group |  |  | section | Completion and handover
checkpoint-status |  |  | checkpoint | Masking removed and disposed
checkpoint-status |  |  | checkpoint | Empty buckets removed and disposed
checkpoint-status |  |  | checkpoint | aluminium joinery cleaned of paint
checkpoint-status |  |  | checkpoint | Vinyl floors / Tiles cleaned
checkpoint-status |  |  | checkpoint | All fixtures, fittings, WC, Bath and vanity/Toilet RSU holders/Light fittings cleaned
checkpoint-status |  |  | checkpoint | Door handles, hinges and door seal rubbers cleaned
checkpoint-status |  |  | checkpoint | Kitchen benchtop cleaned
checkpoint-status |  |  | checkpoint | Remedial painting rectified
checkpoint-status |  |  | checkpoint | Painter signoff
holdpoint |  |  | signoff | Signature
checkpoint-status |  |  | checkpoint | Contractor Signature
holdpoint |  |  | signoff | Signature