## QA Folder Structure
QA Folder Structure
Offsite / Pre-start |  | Offsite / Pre-start
Site QA
| Car Lift 1 | Lift Installation Checklist
| Car Lift 2 | Lift Installation Checklist
| Commercial Lift | Lift Installation Checklist
| Residential Lift 1 | Lift Installation Checklist
| Residential Lift 2 | Lift Installation Checklist

## Checklists ITPs
type | name | values | prefix | postfix
checklist-flat | Offsite / Pre-start
checkpoint | Shop drawings prepared and submitted
checkpoint | Samples submitted - All materials used to be as per the specified common area finishes shedule. Materials to be documented within shop drawings.
checkpoint | Manufacture of lift equipment - Lift equipment manufactured inaccordance with approved construction drawings and relevant lift standards:
label | AS3000:2007, AS1735 parts 1,2 11 and 12, EN81.1:1998 to Appendix A of AS 1735 Part 1
checkpoint | Calibration of equipment / tools - Equipment and tools to be calibrated/serviced as per the manufacturers requirements
checkpoint | Kapitol Group representative signature attached below to confirm Nordic Elevators are ready to begin lift installations
checklist | Lift Installation Checklist
section | Installation of Lift Equipment
checkpoint | Sling built level and square using laser (within 5mm)
checkpoint | Main rail alignment within 2mm (full length of shaft)
checkpoint | Rail DBG within 1mm at all mounting brackets
checkpoint | Safety gear has been correctly adjusted by a qualified trained person
checkpoint | Car guide shoes/rollers correctly adjusted or shimmed to give a smooth ride
checkpoint | Lift car is square and level
checkpoint | Landing doors at the correct height as per builders RL's
checkpoint | Landing doors correctly aligned to the car sill top and bottom eg. 30mm as per drawing
checkpoint | All lift ropes are under correct even tension and bottles, split pins and clamps checked
checkpoint | Emergency phone line active and tested
checkpoint | Car load cells calibrated for correct weight
checkpoint | Wiring installation to comply with building Code of Australia and AS 3000
section | Installation of Lift Car Interior
checkpoint | Lift car interior to be in accordance with approved shop drawings and Lift Specification Tung's Development - Vertical Transportation Specification
checkpoint | Lift car interior to be in accordance with AS1735
checkpoint | Lift car finishes and surface protection to be in accordance with approved shop drawings and Lift Specification Tung's Development - Vertical Transportation Specification
section | Lift Required For Construction Use
checkpoint | Inspection and maintenance of the the lifts during construction use is to be in accordance with Lift Specification Tung's Development - Vertical Transportation Specification
checkpoint | Doors are to be inspected for damage prior to the lifts being handed over. Door frames to be protected prior to operation of lifts
checkpoint | Carry out comprehensive maintenance on all associated lift equipment throughout the period of use
checkpoint | Fully clean the lift installation of all construction debris, dust etc to ensure an as new installation
section | Testing & Commissioning
checkpoint | Lifts to be tested and commissioned in accordance with Lift Specification Tung's Development - Vertical Transportation Specification
label | Any relevant test records / documents attached to the relevant checkpoint below
checkpoint | Speed test (Full load and no load). Compare results
checkpoint | Balance test (Voltage readings in both directions)
checkpoint | Levelling test (All levels with load and no load)
checkpoint | Overload Test
checkpoint | Control systems performance test
section | Sign Off
checkpoint | Kapitol Group Representative signature attached below to confirm works completed in accordance with Lift Specification Tung's Development - Vertical Transportation Specification