## Breakdown
NCS - Nellie Melba
QA - Building B05
Basement
Car Park
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Lobby
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Comms Room
Prewire
Comms Room Build
Commissioning
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Lobby
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Level 0 - Ground
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Lobby/Hallway
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Apartment G60
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G61
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G62
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G63
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G64
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G65
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G66
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G67
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G68
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G69
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Level 1
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Lobby/Hallway
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Apartment 160
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 161
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 162
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 163
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 164
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 165
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 166
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 167
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 168
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 169
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Level 2
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Lobby/Hallway
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Apartment 260
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 261
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 262
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 263
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 264
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 265
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 266
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 267
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 268
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G69
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Level 3
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Lobby/Hallway
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Apartment G63
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 361
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 362
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 363
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 364
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 365
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 366
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 367
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 368
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment 369
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Level 4
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Lobby/Hallway
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff
Apartment G60
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G61
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G62
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Apartment G63
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Termination & Testing
Level 5- Plant Deck
Stairs
|  |  |  | pre-populate | Prewire
|  |  |  | pre-populate | Fitoff

## Checklists
type | name
checklist | Pre-Commencement Checklist
checkpoint | Quality Management Plan Completed, Agreed and Attached
checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint | Relevant Breakdown & Checklist Setup on Conqa & Reviewed by Main Contractor
checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint | Matrix/Insight Setup (if required)
checklist | Prewire
checkpoint | Access available
checkpoint | Framework available
checkpoint | Kitchen Phone/Data (photos attached)
checkpoint | Lounge TV/data (photos attached)
checkpoint | Study Phonr/Data (photos attached)
checkpoint | ODL (photos attached)
checkpoint | WC Nursecall (photos attached)
checkpoint | Shower Nursecall (photos attached)
checkpoint | Ensuit Nursecall (photos attached)
checkpoint | Ensuit Shower Nursecall (photos attached)
checkpoint | WIFI Prewire (photos attached)
checkpoint | Master Bed Nursecall (photos attached)
checkpoint | Master Bed Phone (photos attached)
checkpoint | Master Bed TV/Data (photos attached)
checkpoint | Bed 2 TV/Data (photos attached)
checkpoint | Bed 2 Phone (photos attached)
checkpoint | Bed 3 TV/Data (photos attached)
checkpoint | Bed 3 Phone (photos attached)
checkpoint | Client Extras (photos attached)
checkpoint | Comms Boc/NBN conduit/Phone & Data Lead in Cables (add signature)
checkpoint | Attach photos of Fire penetrations & specify location (photos attached)
checklist | Termination & Testing
checkpoint | Cut out (add signature)
checkpoint | Comms Box Fitted
checkpoint | Kitchen Phone/Data (photos attached)
checkpoint | Lounge TV/data (photos attached)
checkpoint | Study Phonr/Data (photos attached)
checkpoint | ODL (photos attached)
checkpoint | WC Nursecall (photos attached)
checkpoint | Shower Nursecall (photos attached)
checkpoint | Ensuit Nursecall (photos attached)
checkpoint | Ensuit Shower Nursecall (photos attached)
checkpoint | WIFI Prewire (photos attached)
checkpoint | Master Bed Nursecall (photos attached)
checkpoint | Master Bed Phone (photos attached)
checkpoint | Master Bed TV/Data (photos attached)
checkpoint | Bed 2 TV/Data (photos attached)
checkpoint | Bed 2 Phone (photos attached)
checkpoint | Bed 3 TV/Data (photos attached)
checkpoint | Bed 3 Phone (photos attached)
checkpoint | Client Extras (photos attached)
checkpoint | Never Alone PIR installed (photos attached)
checkpoint | Lan Test Data Cables (add signature)
checklist | Commissioning Comms Room
checkpoint | Patch panel installed and tested (add photo & signature)
checkpoint | Nurse call system programmed
checkpoint | Nurse call system commissioned (add signature)
checkpoint | Fire alarm interface programmed
checkpoint | Fire alarm interface commissioned (add signature)
checkpoint | CCTV programmed
checkpoint | CCTV commissioned (add signature)
checkpoint | MATV commissioned (add signature)
checkpoint | Access Contol programmed
checkpoint | Access Contol commissioned (add signature)
checklist | Comms Room Build
checkpoint | Walls built and painted -Request sign off/remedial
checkpoint | Install cable tray (photo attached)
checkpoint | Loom cables (photo attached)
checkpoint | Terminate Fibre (photo attached)
checkpoint | Terminate patch panels (photo attached)
checkpoint | Terminate phone lead in (photo attached)
checkpoint | Install Nurse Call Head end (photo attached)
checkpoint | Install UPS (photo attached)
checkpoint | Build MATV Head end (photo attached)
checkpoint | Build access control head end (photo attached)
checklist | Prewire Comms Room
checkpoint | Reticulation cables run
checkpoint | Attach photos of fire penetrations & specific locations
checklist | Prewire Common Ares
checkpoint | Access available
checkpoint | Framework available
checkpoint | CCTV Cabling completed (photos attached)
checkpoint | Nurse call Cabling completed (photos attached)
checkpoint | Access Control Cabling completed (photos attached)
checkpoint | Intercom Cabling completed (photos attached)
checkpoint | NBN Conduit/Tray installed (photos attached)
checkpoint | Attach photos of Fire penetrations & specify location
checklist | Fitoff Common Areas
checkpoint | CCTV fitted off (photos attached)
checkpoint | Nurse Call fitted off (photos attached)
checkpoint | Access Control fitted off (photos attached)
checkpoint | Intercom fitted off (photos attached)