## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 072a8ee2-f9c7-43b5-ab6c-aa9d4609bb76 |  | checklist | Completion documents |  |  |  |  | Yes | SYS - Completion documents | 01a3979b-0266-4c15-9f49-0d37908079a3
checkpoint-status | b8b4602a-474a-4594-bd03-c26b76e89664 |  | checkpoint | PS3 attached
checkpoint-status | 926b9f48-7a91-446b-97b0-1d05f8c6ea7d |  | checkpoint | As-built plans attached
checkpoint-status | 3f31f05d-bd54-4630-8f4a-6f305f82de92 |  | checkpoint | Any other completion documents attached
checklist-flat | c2278dd3-6d92-468e-a8b6-89872cd38c66 |  | checklist | Fit off |  |  |  |  | Yes | Fit off | 02b5098d-3895-4a35-a0c2-117f7dd50529
checkpoint-status | fc0276b8-df1e-4751-a60a-fd03ecc18e60 |  | checkpoint | Tv/Data Fit Off (Photos Attached)
checkpoint-status | 1d222d57-e1a1-4173-8b00-c5fc8f563a35 |  | checkpoint | Nurse Call Fit Off (Photos Attached)
checklist-flat | 947afd46-b99c-4343-9881-ec671d705b27 |  | checklist | Pre-Commencment Checks |  |  |  |  | Yes | SYS - Pre-Commencment Checks | 07f3fd53-fc58-448f-86a5-3b9def5fd246
checkpoint-status | a1b40658-36f2-46ba-937c-6d03691ca6d4 |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status | aba4e060-83d3-4e83-bed0-7dd6c3535375 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | c4528ad0-d02e-4bbc-a758-f05e730c1e24 |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | ea3465d7-3785-48ec-bfd5-37382f547f5c |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | b941d096-84f6-49b5-9085-6c2595e7926f |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | e42b54ae-4276-42a5-92a1-dbec3398e393 |  | checkpoint | Matrix/insights Setup (if required)
checklist-flat | e9d65372-e2fc-475d-a003-5274fcafa621 |  | checklist | Fit off |  |  |  |  | Yes | Fit off | 0d248d0c-59e7-4009-83ea-e392c505e022
checkpoint-status | 8670cdda-dc21-46f7-8822-49104e2d0448 |  | checkpoint | Nurse Call Fit Off (Photos Attached)
checkpoint-status | 6dde0911-5dd2-4078-87ae-1c347df3b1b5 |  | checkpoint | Camera Fit Off (Photos Attached)
checkpoint-status | 4a99e701-cd6a-4260-a1ed-39de08f51026 |  | checkpoint | Intercom Fit Off (Photos Attached)
checkpoint-status | 45f83f37-0c3e-49c5-be0f-0dc749372257 |  | checkpoint | Ac-Mags Fit Off (Photos Attached)
checkpoint-status | fd1b2f45-2660-4b16-8641-51faa6b92ef5 |  | checkpoint | Ac Fit Off (Photos Attached)
checkpoint-status | 6be826f6-4386-4ff4-b85e-079f48c27c1e |  | checkpoint | Repeaters Installed (Photos Attached)
checklist-flat | dee31cb2-670e-4bf4-95e0-c60cb7171d3d |  | checklist | NCS - Floor Commissioning |  |  |  |  | Yes | NCS - Floor Commissioning | 0e97f391-3ec3-4ca2-8a07-4e9b02345808
checkpoint-status | 45c7c8b3-0170-42fe-b6e1-e74260f606be |  | checkpoint | Separate and Tone Cables (Add Signature)
checkpoint-status | 16e3926d-a376-4ce8-bfc0-78e111e1167b |  | checkpoint | Cable Riser (Photos Attached)
checklist-sectioned | 76e81ed6-2abb-4f61-9cb5-57841b5cd542 |  | checklist | Common area sign off |  |  |  |  | Yes | SYS - Common area sign off | 1020185c-ac47-4bdd-a431-9bc5c4970326
checkpoint-group | 9e0ffe7f-d7b8-4b5d-9193-d0183f338ec5 |  | section | Pre Wire
checkpoint-status | 363d522b-f227-4865-9e0a-3ebac611323e |  | checkpoint | Cabling Complete
checkpoint-status | 1d1f4ddb-451a-4476-8938-33fa229f44a5 |  | checkpoint | Nogs Installed
checkpoint-status | 77529b97-8465-43de-a470-22376845fa1a |  | checkpoint | Flush Box Fire Box Installed (Photos Attached Of Fire Box)
checkpoint-status | 78d44513-c267-44ae-a59f-3cd028891c57 |  | checkpoint | Attach Photos Of Fire Penetrations
checkpoint-group | d4b89f63-0f1c-4c12-8bc1-177e4deae7ee |  | section | Terminated And Tested
checkpoint-status | 60442c82-26d6-45a9-86a7-ffa53d6194eb |  | checkpoint | Lan Test Complete
checkpoint-group | 2c91b251-b918-4c90-b846-887c8ea2b050 |  | section | Fit Off
checkpoint-status | a021c10a-97a6-42c8-87bf-4656b9fbe90c |  | checkpoint | Nurse Call Fit Off
checkpoint-status | e9fbb75b-2dbe-4073-b769-71804364809f |  | checkpoint | Camera Fit Off
checkpoint-status | 0bbdf9e1-c15b-4224-95ff-fef0620c9872 |  | checkpoint | Intercom Fit Off
checkpoint-status | 5d159c66-fb4a-4f08-8ba2-9d65e3088c1d |  | checkpoint | Ac-Mags Fit Off
checkpoint-status | 25571205-c945-4d70-a51b-32800d1a16e7 |  | checkpoint | Ac Fit Off
checklist-sectioned | 81922e64-00b8-406e-994f-2a9a1ab7376c |  | checklist | NCS - Common Area Sign-Off |  |  |  |  | Yes | NCS - Common Area Sign-Off | 19b3e238-6341-4a42-9b53-bcb2e53f1b14
checkpoint-group | 5fb29400-07ae-4d56-bc29-1ce1874d4400 |  | section | Prewire
checkpoint-status | 07285d55-da67-412e-8f8e-58353e76a922 |  | checkpoint | Cabling completed
checkpoint-status | df9af2ce-35de-4c9a-b0c6-10b2004bc481 |  | checkpoint | Flush box fire box installed - Attach photos below
checkpoint-status | 712ac0e6-44a5-4829-8b26-2db7bc8f2c5d |  | checkpoint | Attach photos of fire penetrations - Attach photos below
checkpoint-status | 44312bd3-66a5-41b4-9b6d-f31ccd2361c6 |  | checkpoint | Prewire works completed to specification/drawings - Area left clean & tidy
label | e32d22b3-a3aa-58b4-96c7-f3118434084d |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group | 4fc38b3d-4578-4c2d-8c6d-7e424f7c2ccd |  | section | Termination & Testing
checkpoint-status | 52cad2c2-5c41-4caf-92ed-52fc6b0d80bd |  | checkpoint | LAN test complete
checkpoint-group | 34532220-74cb-4a57-9b23-749f4004aff3 |  | section | Fitoff
checkpoint-status | 6a67e1e8-7182-4acb-9a32-8a6815f6fbd0 |  | checkpoint | Nurse Call fit off completed - Attach photos below
checkpoint-status | 27d600e6-5569-43b5-9215-d5e412329872 |  | checkpoint | Camera fit off completed
checkpoint-status | 62d637a7-ebcd-4083-94c3-e108e1a8c744 |  | checkpoint | Intercom fit off completed
checkpoint-status | 4e6dd14a-f8f1-46c7-b092-72a4f4d2488f |  | checkpoint | AC-mags fit off completed
checkpoint-status | a9d4cdac-6a20-4d33-9503-13d8b2180bed |  | checkpoint | AC fit off completed
checkpoint-status | fef5951f-89b6-4ea6-b880-a29ae1f1ab98 |  | checkpoint | Fitoff works completed to specification/drawings - Area left clean & tidy
label | 60960ddc-5ec5-5d6b-8629-9d8dd7bb2008 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat | 92a03391-0c83-4f9d-bfa0-d939bf034b80 |  | checklist | Building Commissioning |  |  |  |  | Yes | SYS - Building Commissioning v3 | 294f32f0-6a4f-4aa0-be22-f293df437898
checkpoint-status | cf45ddde-6f63-49b1-9f76-cd38357d2a1a |  | checkpoint | Separate Cables (Add Signature)
checkpoint-status | 2e807713-8654-44c6-99e3-5421f99f3f47 |  | checkpoint | Separate Security Cables (Add Signature)
checkpoint-status | 2697200a-882a-408b-89e5-8077e03d94ff |  | checkpoint | Complete Cable Riser (Add Signature)
checkpoint-status | ac0513a3-2ff4-4087-bcc0-852c35303504 |  | checkpoint | Build Patch Panels (Attach photos)
checkpoint-status | 2da52b88-1566-4a26-8cc8-71998fa39412 |  | checkpoint | Build Nurse Call System (Attach photos)
checkpoint-status | ff136c95-3ded-4429-a4e4-fb1b0e0346e2 |  | checkpoint | Build Matv System (Attach photos)
checkpoint-status | 4e444450-807d-4cbb-9786-17f50401e874 |  | checkpoint | Build Security Panels (Attach photos)
checkpoint-status | 71fb88ef-3a18-4c08-8b7b-94b1ad281f6b |  | checkpoint | Program Nurse Call System (Add Signature)
checkpoint-status | d44ef6ae-d364-447b-9623-cf70cebf3fe6 |  | checkpoint | Commission Nurse Call System (Attach photos)
checkpoint-status | 37c23431-c18c-48c9-9055-322bc9233f2f |  | checkpoint | Commission Security System (Attach photos)
checkpoint-status | 83b85a7e-5447-44f2-b520-c4b27bc42d0c |  | checkpoint | Commission Fire Interface (Attach photos)
checklist-flat | 488107d8-f430-462c-96ae-79cc775ce19f |  | checklist | NCS - Floor Commissioning |  |  |  |  | Yes | NCS - Floor Commissioning | 2e28ac00-f506-4f6f-9d3d-d8576c3d76d1
checkpoint-status | 3154b114-2250-4273-afaf-f615a5fdf886 |  | checkpoint | Tone cables Comissioned - Attach Signature Sign-Off below
checkpoint-status | c70d3d55-a887-49a7-970b-463ec553d516 |  | checkpoint | Separate cables Comissioned - Attach Signature Sign-Off below
checkpoint-status | 93fafc2b-f386-4e61-868c-047b46f4e7b1 |  | checkpoint | Cable riser Comissioned - Attach Signature Sign-Off below
checklist-sectioned | 8d216522-cdfe-46ca-a449-eb6edf524c40 |  | checklist | Rooms Install |  |  |  |  | Yes | SYS - Rooms Install Checklist | 35289ae2-cd7b-4b0e-9922-1dc360d12d33
checkpoint-group | 9b7f3832-d8aa-49c2-a9c1-6d6e80b997cb |  | section | Prewire
checkpoint-status | 057801cd-a8fc-42f9-9041-d582258848d9 |  | checkpoint | Access available
checkpoint-status | f7a16e26-4465-4b53-af41-8c057508ad26 |  | checkpoint | Framework available
checkpoint-status | 04602415-0759-43cc-a03b-eefce7211e67 |  | checkpoint | Cabling completed (photos attached)
checkpoint-status | bda469c9-cf6f-4996-a476-578268390cb6 |  | checkpoint | Nogs installed
checkpoint-status | 050d108d-41ce-4cfc-9779-3fd7a25ed6d1 |  | checkpoint | Flush/Fire boxes installed (photos attached)
checkpoint-status | b8e4849a-f9e4-480c-9e09-ee4e15b782d3 |  | checkpoint | Attach photos of Fire Baffles & specify location
checkpoint-status | d0f720b6-7386-468a-8dcb-fabb680cb393 |  | checkpoint | Attach photos of Fire penetrations & specify location
checkpoint-group | 1ff85606-7a2c-4d8d-8744-08378ef4201c |  | section | Termination & Testing
checkpoint-status | d97e7c92-8584-40a8-a2a9-7660419666b4 |  | checkpoint | LAN test completed (add signature)
checkpoint-status | 2d8799d2-16d2-48b2-8ec8-9ea0ba55b0aa |  | checkpoint | Endpoints bagged (photos attached)
checkpoint-group | a47dd089-88c6-4db3-b3a1-dfcf11e54521 |  | section | Fitoff
checkpoint-status | cd930137-2e8e-4fdf-8dea-b866d6bc6c49 |  | checkpoint | Nurse Call faceplates fitted off (photos attached)
checkpoint-status | 3c9a84c8-771e-4ab6-991b-59150d274551 |  | checkpoint | Camera faceplates fitted off (photos attached)
checkpoint-status | 03309d66-4ca2-4513-bc69-1082f1a508ec |  | checkpoint | Intercom faceplates fitted off (photos attached)
checkpoint-status | b323d347-6b70-4299-8b3d-a377db963f83 |  | checkpoint | AC- Mags faceplates fitted off (photos attached)
checkpoint-status | 2f5890c5-f581-4798-876d-394856caa17d |  | checkpoint | AC- Plates fitted off (photos attached)
checklist-sectioned | c97a7104-f3fb-4305-af49-04d7d8740d96 |  | checklist | "COMMON AREA SIGN OFF" |  |  |  |  | Yes | SYS - "COMMON AREA SIGN OFF" | 354ecafb-02c6-4ae7-8ab5-6d2ff5dd0f72
checkpoint-group | 5e261cf6-ec10-4a3e-ba5a-5a359e5758aa |  | section | Pre wire
checkpoint-status | cb1aada5-82d1-4a73-8f22-98636e769d71 |  | checkpoint | cabling complete
checkpoint-status | 98d0385f-2988-4fc6-9177-9fae402c20df |  | checkpoint | flush box fire box installed (photos attached of fire box)
checkpoint-status | b7c36d39-f169-4368-aac3-35a64064d988 |  | checkpoint | attach photos of fire penetrations
checkpoint-group | a9c56fb6-15ce-4666-849a-1f73638be26b |  | section | terminated and tested
checkpoint-status | c5b71252-7741-4c23-aa72-15ce05f4d30d |  | checkpoint | LAN test complete
checkpoint-group | 368825ed-3745-4d9e-8edb-7d8e65305cb3 |  | section | fit off
checkpoint-status | dfb1ee3e-7241-4db0-a5e5-fafa4e6495ff |  | checkpoint | nurse call fit off
checkpoint-status | c8e06d51-b31d-4aa8-86a8-a79ff784336f |  | checkpoint | camera fit off
checkpoint-status | 46ef8215-ef1b-4e16-8a8f-295ab62f3d2c |  | checkpoint | intercom fit off
checkpoint-status | 51069ff1-a366-4858-a71e-37bb81f33c53 |  | checkpoint | AC-mags fit off
checkpoint-status | cbe810db-650a-4edd-818d-09ebbef6a061 |  | checkpoint | AC fit off
checklist-sectioned | c8eab9f2-0db8-4eba-9818-77d30be3f86f |  | checklist | Common Area signoff |  |  |  |  | Yes | SYS - Common Area signoff v1 | 35e2108c-b685-4986-8468-cd280b840bbe
checkpoint-group | 97ac4923-ecd3-440e-9c34-9bd8af405280 |  | section | Pre Wire
checkpoint-status | 9530aa28-671c-49aa-b027-88849916e197 |  | checkpoint | Cabling Complete
checkpoint-status | 646d1999-caac-4f8f-af4a-f9fbdab08387 |  | checkpoint | Flush Box Fire Box Installed (Photos Attached Of Fire Box)
checkpoint-status | 8d7a69d0-62a5-49f0-929a-81bce0d9c97b |  | checkpoint | Attach Photos Of Fire Penetrations
checkpoint-group | 04cef331-a5f6-437f-b0fe-97d050def086 |  | section | Terminated And Tested
checkpoint-status | bc50276e-8249-4d2d-982e-e1e05182b6e1 |  | checkpoint | Lan Test Complete
checkpoint-group | a903a778-12b6-41a5-a450-f900d5c61a25 |  | section | Fit Off
checkpoint-status | efaf3a4a-883f-4e68-93ae-683319cc8f2e |  | checkpoint | Nurse Call Fit Off
checkpoint-status | c837b4ef-6b96-43b3-9629-a1bb412c0ca6 |  | checkpoint | Camera Fit Off
checkpoint-status | 7ae80e2d-fba7-408f-bde0-1c4db6c9fb70 |  | checkpoint | Intercom Fit Off
checkpoint-status | 5ca96a42-1fe4-4a3b-a042-01d50845311d |  | checkpoint | Ac-Mags Fit Off
checkpoint-status | 33b1dc29-5643-4a5d-8cf0-f2f47ba17d44 |  | checkpoint | Ac Fit Off
checkpoint-status | 70458b06-e4ea-4407-b6dc-ec47f41c75a8 |  | checkpoint | Repeaters Installed.
checklist-sectioned | ce22ba37-b10e-49cb-a344-96d18dfdfdc9 |  | checklist | NCS Checklist |  |  |  |  | Yes | SYS - NCS Checklist | 3df3b1c1-340a-4f30-97ad-2cd8333726ef
checkpoint-group | 6a102554-a219-42b0-b6b4-0c9c52e1a7c6 |  | section | Prewire
checkpoint-status | 5c235750-1a7c-48fa-b5a6-9d43a12b188f |  | checkpoint | Access available
checkpoint-status | 6ab2990f-4b9e-42b6-b217-f99bb72b0ff1 |  | checkpoint | Framework available
checkpoint-status | 07852b42-f1d6-4e50-87d1-b08449af79e0 |  | checkpoint | Cabling completed (photos attached)
checkpoint-status | 8a8d6750-c53e-4942-92a7-0c6b2973f148 |  | checkpoint | Nogs installed
checkpoint-status | c91fa523-ffc2-4c27-a501-3383be20bcce |  | checkpoint | Flush/Fire boxes installed (photos attached)
checkpoint-status | e2ab1e80-0316-4a02-b847-3debd24d2a69 |  | checkpoint | Attach photos of Fire Baffles & specify location
checkpoint-status | a3c8fb6f-d6f8-4a67-a40d-f00d73d4760f |  | checkpoint | Attach photos of Fire penetrations & specify location
checkpoint-group | da897137-9844-4366-872d-95882614b013 |  | section | Termination & Testing
checkpoint-status | 67e69e3f-8cf2-4a34-b03e-89bcbaf8d001 |  | checkpoint | LAN test completed (add signature)
checkpoint-status | 5eea33fa-a27b-42d1-8d4d-21e239d17301 |  | checkpoint | Endpoints bagged (photos attached)
checkpoint-group | f2a90180-3ea3-4dae-88de-7fcd7ba1c1a9 |  | section | Fitoff
checkpoint-status | f72a6d93-9599-4e67-96d5-9adf91261e01 |  | checkpoint | Nurse Call faceplates fitted off (photos attached)
checkpoint-status | 226bb094-039d-426e-b55b-4755a8f927ef |  | checkpoint | Camera faceplates fitted off (photos attached)
checkpoint-status | ed99dfb1-fdb0-47d7-86cd-459d85b70a1e |  | checkpoint | Intercom faceplates fitted off (photos attached)
checkpoint-status | 20a1b54a-4298-49f8-baf6-b082c40e7dad |  | checkpoint | AC- Mags faceplates fitted off (photos attached)
checkpoint-status | 0f220693-4e5c-4aff-a38b-407f80cf93e6 |  | checkpoint | AC- Plates fitted off (photos attached)
checkpoint-status | ffe861cd-fb1d-4e34-a4dd-915c7f507cee |  | checkpoint | QA has been reviewed and approved by the main contractor
holdpoint | 172f74aa-e4fc-41a0-a535-e79ce37a07c6 |  | signoff | Raise Remedial/ Main Contractor Signoff
checklist-sectioned | 8b1fb519-1a99-4956-99f1-834d75273136 |  | checklist | Apartment Signoff v1 |  |  |  |  | Yes | SYS - Apartment Signoff v1 | 4213e6af-2388-402f-b036-a6fbb0fc939c
checkpoint-group | 1afb67fb-12df-4350-8295-75f360577cc7 |  | section | Pre Wire
checkpoint-status | 2bd130b5-157c-4b70-8f2f-8a2455c0cd75 |  | checkpoint | Internal Cabling Complete
checkpoint-status | ca799598-7d09-44ad-abed-4af7f44098ac |  | checkpoint | Main Cabling Complete (Photos Attached)
checkpoint-status | ec7d9a09-6c11-451d-a333-6ab4773d0192 |  | checkpoint | Nogs Installed
checkpoint-status | b05c6995-850d-4132-9052-cdbb5630a299 |  | checkpoint | Flush Boxes Installed
checkpoint-status | 0e06b479-37a0-41c4-8a74-e3234a6b69de |  | checkpoint | Fire Boxes Installed (Photos Attached)
checkpoint-status | efc16303-2960-4e3e-8d27-988ad20c640a |  | checkpoint | Fire Walls Point Of Entry (Photos Attached)
checkpoint-group | 594cbf76-0f2b-4b76-934e-465a2f9c0e64 |  | section | Terminated And Tested
checkpoint-status | 8cb2ff7f-0d9b-4dbc-afdc-fb5cbc5033b6 |  | checkpoint | Install Db
checkpoint-status | b86a8810-4a83-4e79-99da-6ecb38dbb66c |  | checkpoint | Fit Off Data Jacks
checkpoint-status | 0db2c6b2-1acc-4d55-ba74-e0152c8bf859 |  | checkpoint | Fit Off F Connectors
checkpoint-status | 83d8cb06-b68c-4954-82d7-7f8ba31993c2 |  | checkpoint | Fit Off Db (Photo Attached)
checkpoint-status | 22c6ad88-de8c-4ddf-b1fc-66eaaa5b067b |  | checkpoint | Lan Test Internals (Add Signature)
checkpoint-group | 07d2999c-3743-4773-bfef-0a192de8ed27 |  | section | Fit Off
checkpoint-status | 35861c52-2e95-476a-99b2-8e50542e692a |  | checkpoint | Tv/Data Fit Off (Photos Attached)
checkpoint-status | 063ca576-d96a-4497-89d8-253c4ba523c4 |  | checkpoint | Nurse Call Fit Off (Photos Attached)
checklist-flat | ddcbedf8-1880-4b7c-a288-2d81cc6ebb27 |  | checklist | Building Commissioning |  |  |  |  | Yes | SYS - Building Commissioning Checklist | 4c6617fb-f4d9-4871-861c-7fceeadb9387
checkpoint-status | 2a51bc48-04bb-4993-a9f8-118c27a80337 |  | checkpoint | Build Comms Room (add signature)
checkpoint-status | c9268624-163d-4b32-8ff8-01796663c8de |  | checkpoint | Build Patch Panels (add signature)
checkpoint-status | b2289b1a-843b-41a8-8991-66479d7fd411 |  | checkpoint | Build Nurse Call System (add signature)
checkpoint-status | e69d8c29-3685-45c8-ae8b-ce019ff9d9e7 |  | checkpoint | Build MATV System (add signature)
checkpoint-status | d98437c8-efac-4097-8eca-ffdeaab432d9 |  | checkpoint | Separate Security Cables (add signature)
checkpoint-status | 48b57852-956c-4b8d-80a5-ebf13f49dd9e |  | checkpoint | LAN test (add signature)
checkpoint-status | 4216aef7-5502-44c3-990f-059d49c748d8 |  | checkpoint | Program Nurse Call (add signature)
checkpoint-status | ed47ff83-3f36-4720-bdbb-cbbf053898a7 |  | checkpoint | Commission Nurse Call (add signature)
checkpoint-status | 375d6c7c-58ed-4997-ace1-543da110f733 |  | checkpoint | Fire Interface (add signature)
checkpoint-status | b473daf4-da29-48c1-8f0c-dceca2d78a98 |  | checkpoint | Commission Security System (add signature)
checklist-flat | 4b341905-7e52-4a03-ae29-484610855ab7 |  | checklist | Building Commissioning v1 |  |  |  |  | Yes | SYS - Building Commissioning v1 | 534fefb2-f90c-41f8-a44f-468c6cd0013a
checkpoint-status | 3ba78e56-648e-4eef-a9a5-c1c6a578fe47 |  | checkpoint | Build Comms Room (add signature)
checkpoint-status | a8282f65-5e9a-4f93-b6da-7e971c41c8c3 |  | checkpoint | Build Patch Panels (add signature)
checkpoint-status | 8feb0161-eff9-487f-8358-a83a9799f207 |  | checkpoint | Build Nurse Call System (add signature)
checkpoint-status | 6bd2475e-0d78-49a6-bf04-d91e451b17dc |  | checkpoint | Build MATV System (add signature)
checkpoint-status | 6b6922f4-eb32-4eb8-905a-8ac77d0f1001 |  | checkpoint | Separate Security Cables (add signature)
checkpoint-status | 5dd4f230-f36e-4a36-9e36-68c9f80cae77 |  | checkpoint | LAN test (add signature)
checkpoint-status | c5b309b9-8718-4a0d-902e-f6dc04276a78 |  | checkpoint | Program Nurse Call (add signature)
checkpoint-status | 53abb1cd-2b6b-4adb-8eaa-3bc1e1c03ac1 |  | checkpoint | Commission Nurse Call (add signature)
checkpoint-status | a03bb9e1-dc6e-4274-bbb9-4fa21559d21b |  | checkpoint | Fire Interface (add signature)
checkpoint-status | a713ad33-dcd5-484f-a516-edd78fc43742 |  | checkpoint | Commission Security System (add signature)
checkpoint-status | ebffd59f-916a-4a85-84ee-45681cd3e1ea |  | checkpoint | QA has been reviewed and approved by the main contractor
holdpoint | b52225d2-638f-4a2e-a22f-4514b71f21ad |  | signoff | Raise Remedial/ Main Contractor Signoff
checklist-flat | ed679388-59c5-485d-a865-b3b4bba71d37 |  | checklist | Pre Wire |  |  |  |  | Yes | Pre Wire | 53bdd071-b5fa-4095-a680-110571e4362b
checkpoint-status | 2b2563ea-547d-40e4-ade9-5022168d7f82 |  | checkpoint | Internal Cabling Complete
checkpoint-status | feeadf44-3dc7-4652-9cb1-42d3483ceefe |  | checkpoint | Main Cabling Complete (Photos Attached)
checkpoint-status | 6799b202-678e-4315-b406-05f24ef6f865 |  | checkpoint | Flush Boxes Installed (Photos Attached)
checkpoint-status | f7e57110-4682-4e12-9bfc-1bc3c3a44f94 |  | checkpoint | Fire Boxes Installed (Photos Attached)
checkpoint-status | 99078910-22c7-4dd5-b84a-410e9a7900de |  | checkpoint | Fire Walls Point Of Entry (Photos Attached)
checklist-flat | ba6654df-e2e6-4440-bb89-63a10017132a |  | checklist | Pre Wire |  |  |  |  | Yes | Pre Wire | 6017dcd7-1287-456b-9ae2-df79dd1bc5ca
checkpoint-status | 32a10f6e-7e0d-4d94-8c3d-51fd7f4c7bcf |  | checkpoint | Cabling Complete
checkpoint-status | 43e88622-df6a-4928-8541-f25e2c77dda0 |  | checkpoint | Flush Box Fire Box Installed (Photos Attached Of Fire Box)
checkpoint-status | b3f9a0aa-6f2b-40d1-876f-8557b9ae0a7b |  | checkpoint | Attach Photos Of Fire Penetrations
checklist-sectioned | 9cf04966-1ea5-4a26-83ff-7c3828198055 |  | checklist | "APARTMENT SIGN OFF" |  |  |  |  | Yes | SYS - "APARTMENT SIGN OFF" | 66f34ee1-7fa1-4b0b-9aee-2a574da293fe
checkpoint-group | cf7970e6-1661-4534-8fa1-ae1b6cdd0605 |  | section | Pre wire
checkpoint-status | 816912f7-b035-4b34-bc1c-bd5e66cc38a3 |  | checkpoint | internal cabling complete
checkpoint-status | 598b669e-41bc-4efb-9303-506e0a29827e |  | checkpoint | main cabling complete (photos attached)
checkpoint-status | 5c5484a4-1840-4d97-94a7-ed1044573693 |  | checkpoint | flush boxes installed
checkpoint-status | 77889c5b-10bf-4528-be8a-9a5480642f68 |  | checkpoint | fire boxes installed (photos attached)
checkpoint-status | 7af93b83-efb3-4f4e-aedd-4b3c120e85c9 |  | checkpoint | fire walls point of entry (photos attached)
checkpoint-group | a94115f9-f3eb-4b42-a424-31e59a5a57e5 |  | section | termination and testing
checkpoint-status | cf49a931-413a-4e90-99dc-60949fea4037 |  | checkpoint | install DB
checkpoint-status | 5f75157a-eb41-454b-bb86-ad454f45e2d1 |  | checkpoint | fit off DB (photo attached)
checkpoint-status | eaf0dce8-d7a6-4f6d-80e1-e7033e249180 |  | checkpoint | LAN test internals (add signature)
checkpoint-group | 6e794431-3338-4e6b-a82b-8fbe5dd4c7cc |  | section | fit off
checkpoint-status | 713ddd8a-1f1c-4a39-bea9-003b3e4980fa |  | checkpoint | TV/DATA fit off (photos attached)
checkpoint-status | a6f509c3-21ba-4156-b05e-e57a98eab4be |  | checkpoint | nurse call fit off (photos attached)
checklist-sectioned | 0a14d26c-6b5a-4003-b5d7-a2ad66995ded |  | checklist | Apartment Signoff |  |  |  |  | Yes | SYS - Apartment Signoff v3 | 6c95051d-f03d-4682-a930-b596bbf24240
checkpoint-group | 3250f6e1-ed20-4c05-8e58-58320732a56f |  | section | Pre Wire
checkpoint-status | 85f8e4e9-1135-47b5-91ad-bf313f3287ec |  | checkpoint | Internal Cabling Complete
checkpoint-status | d6fbc253-71fe-4155-8a89-ab79114278cf |  | checkpoint | Main Cabling Complete (Photos Attached)
checkpoint-status | b5c75516-a745-4224-af26-c1c569d874a3 |  | checkpoint | Flush Boxes Installed
checkpoint-status | a9777593-a96f-4492-b653-b33e3fbcb604 |  | checkpoint | Fire Boxes Installed (Photos Attached)
checkpoint-status | 0fd3d15b-8427-459b-ac3e-5d13c0dc8711 |  | checkpoint | Fire Walls Point Of Entry (Photos Attached)
checkpoint-status | ef2fa961-9405-4f4a-a5e0-b434b47cf282 |  | checkpoint | Termination And Testing
checkpoint-group | 45e9cc09-fc57-4b5b-8531-6605827a5e99 |  | section | Install Db
checkpoint-status | 4fb444b0-07df-4a01-a743-0ae2156cd544 |  | checkpoint | Fit Off Db (Photo Attached)
checkpoint-status | 4d50c464-481a-4a87-890a-2db85fa4ac19 |  | checkpoint | Lan Test Internals (Add Signature)
checkpoint-group | c63edf32-114f-4912-8c1c-b13ce484564c |  | section | Fit Off
checkpoint-status | 49be5b60-5164-454f-ba3a-8d53e474e475 |  | checkpoint | Tv/Data Fit Off (Photos Attached)
checkpoint-status | e97d8799-6c98-4752-bfbe-751f7c5ac15f |  | checkpoint | Nurse Call Fit Off (Photos Attached)
checklist-flat | b5853379-eb88-4d89-a397-bc96ba7cedd6 |  | checklist | NCS - Completion Documents |  |  |  |  | Yes | NCS - Completion Documents | 813aaf5b-c479-4a53-8ee7-61bdb7037c3d
checkpoint-status | 1fb2d5f0-9bd5-4f9e-8925-7309468422ce |  | checkpoint | Producer statements PS3s
checkpoint-status | ecf0f0ca-e331-4ff0-9428-42c3ace55552 |  | checkpoint | As built plan
checkpoint-status | 09aa6691-2442-4be7-a228-0b9ffaae40ed |  | checkpoint | O & M Manual
checkpoint-status | a314ea37-5357-4c19-a29f-25fb93198fb1 |  | checkpoint | Other required documents
checklist-flat | 7f4682af-e156-4adb-9fcb-9ffeae0970d4 |  | checklist | Building Commissioning |  |  |  |  | Yes | SYS - Building Commissioning | 9a4fd384-32b9-4fec-a2bd-f1b5ac1a3097
checkpoint-status | 861e674f-2710-4f74-8f9b-f4ab27b4a0da |  | checkpoint | separate cables (add signature)
checkpoint-status | 86dd7884-2d54-4820-9114-da4d11824d0e |  | checkpoint | separate security cables (add signature)
checkpoint-status | 9fcdc2c2-d2b9-4e67-96ac-497032235c0f |  | checkpoint | complete cable riser (add signature)
checkpoint-status | a93fa0d2-288a-4f2c-9ebe-4a3d5d38aa63 |  | checkpoint | build patch panels (attach photo's)
checkpoint-status | 769f609d-be8c-4537-9a25-26ce98497d16 |  | checkpoint | build nurse call system (attach photo's)
checkpoint-status | cdc43904-d083-41ea-900a-1b2452528dfa |  | checkpoint | build MATV system (attach photo's)
checkpoint-status | 421ce810-532e-4883-9b35-88299fcd61c6 |  | checkpoint | build security panels (attach photo's)
checkpoint-status | a618f3ae-f57d-4f59-be97-7215c8a1fdbb |  | checkpoint | program nurse call system (add signature)
checkpoint-status | 5d639fd3-d938-4a39-a31f-a7e289703d0a |  | checkpoint | Commission nurse call system (attach photo's)
checkpoint-status | f6f351a1-2d35-4d69-95ec-2d1654239564 |  | checkpoint | Commission Security system (attach photo's)
checkpoint-status | 556f6d74-4d08-488c-8ad0-e2f2ccfe3076 |  | checkpoint | Commission Fire interface (attach photo's)
checklist-sectioned | 3fafd9ef-b78c-443f-bf5f-c8565f293683 |  | checklist | Common Area Install |  |  |  |  | Yes | SYS - Common Area Install Checklist | ab21891b-1b51-4fba-8816-887424877ae8
checkpoint-group | 6bed90bc-2f1a-4f3b-912e-f988af6ca575 |  | section | Prewire
checkpoint-status | a7379524-c120-4abc-a072-e91cdca5504f |  | checkpoint | Access available
checkpoint-status | 0ca98c3e-9e71-48d9-9e68-ccb5c1402d4f |  | checkpoint | Framework available
checkpoint-status | 5faab02d-7e1f-42dc-acce-e01b410e3262 |  | checkpoint | Cabling completed (photos attached)
checkpoint-status | 853a5580-1852-4a43-8eff-c00753cffdf1 |  | checkpoint | Nogs installed
checkpoint-status | 1e379584-1916-4ecf-9e32-655288aac5e1 |  | checkpoint | Flush/Fire boxes installed (photos attached)
checkpoint-status | 9defdbef-ea60-4594-b083-45fec94bcb71 |  | checkpoint | Attach photos of Fire Baffles & specify location
checkpoint-status | 7cfa1428-bbc9-4dbb-b86b-c3de1e4c982c |  | checkpoint | Attach photos of Fire penetrations & specify location
checkpoint-group | 1c5f0a2f-a6ab-4f41-83a1-3607f15e8f1f |  | section | Termination & Testing
checkpoint-status | b0076ea5-df7a-41ab-a23d-4219e080899d |  | checkpoint | LAN test completed (add signature)
checkpoint-status | 81b46d10-7995-4d47-bb89-d58f6ffb5586 |  | checkpoint | Endpoints bagged (photos attached)
checkpoint-group | 9c898aca-386b-47fb-b4da-2f6f02d3fac8 |  | section | Fitoff
checkpoint-status | 6e36c085-3b9f-465d-b480-ceda8838610d |  | checkpoint | Nurse Call faceplates fitted off (photos attached)
checkpoint-status | eb69b8a5-aacd-4021-ab99-b02a3ba9dd68 |  | checkpoint | Camera faceplates fitted off (photos attached)
checkpoint-status | e1cf9ce5-bb78-4b88-b3d4-261fec60db68 |  | checkpoint | Intercom faceplates fitted off (photos attached)
checkpoint-status | 1fb207dc-1f59-4929-8874-e6d4092a7468 |  | checkpoint | AC- Mags faceplates fitted off (photos attached)
checkpoint-status | c9acae25-a810-4ba5-b625-c46ba40f2958 |  | checkpoint | AC- Plates fitted off (photos attached)
checklist-flat | cf07fd28-0adc-4bc1-9bcb-b310b371590f |  | checklist | "FLOOR COMMISIONING" |  |  |  |  | Yes | SYS - "FLOOR COMMISIONING" | ae840c13-0d9b-4146-b07c-ae0c25d92388
checkpoint-status | e758db8d-1433-44a5-bc06-fb7d2cc1adac |  | checkpoint | tone cables (add signature)
checkpoint-status | fe290d01-573b-4273-b50f-d9eb4a4e85f2 |  | checkpoint | separate cables (add signature)
checkpoint-status | 1bfd1789-d5af-4bd4-8201-466b036bbcda |  | checkpoint | cable riser (add signature)
checklist-sectioned | ab2453a8-fa44-423f-bfde-fd8663aae5c5 |  | checklist | Apartment Signoff v2 |  |  |  |  | Yes | SYS - Apartment Signoff v2 | b411e2e9-c724-4cef-8e6c-a39768397a02
checkpoint-group | 0ffa6eab-626b-43d5-bf29-b446c417910c |  | section | Prewire
checkpoint-status | 2739956a-65c7-414a-9ef5-ec072142b3e4 |  | checkpoint | Access available
checkpoint-status | 5fdeeb6c-f2eb-439e-bd05-85563d376863 |  | checkpoint | Framework available
checkpoint-status | 662c461c-5a8e-4644-83b0-622709df592f |  | checkpoint | Internal Cabling completed (photos attached)
checkpoint-status | 7e0b1a8b-f159-4514-b7c5-6cc989270295 |  | checkpoint | Mains Cabling completed (photos attached)
checkpoint-status | a7de8d7e-941f-4aa6-b192-15a1dfc60286 |  | checkpoint | Nogs installed
checkpoint-status | 5106f08b-39bb-49f2-82a6-0b821c55135d |  | checkpoint | Flush boxes installed
checkpoint-status | 69abdf95-3e4a-4034-b1ed-145084ff3066 |  | checkpoint | Fire boxes installed (photos attached)
checkpoint-status | 8dc5e357-ef4c-4ecb-a003-33af8ab46d3d |  | checkpoint | Attach photos of Cabling (Point of entry/Within Fire wall
checkpoint-status | 9e1e16dc-db7d-4114-b1a2-424393eb2a9a |  | checkpoint | Attach photos of Fire box (Attach photos of each fire box)
checkpoint-group | 4eb45201-9cf2-47af-a99b-1cf9d041cf78 |  | section | Termination & testing
checkpoint-status | b77cee2c-ad6e-4f6d-86c6-b52cdf540089 |  | checkpoint | Install DB
checkpoint-status | 59d61ce1-1fc7-4773-9e1a-f8958291a205 |  | checkpoint | Fitoff data jacks
checkpoint-status | 9d657626-c827-4dc9-8572-c7dcd7a19147 |  | checkpoint | Fitoff F connectors for TV
checkpoint-status | cc5376f2-86d6-42e1-9ee2-77e5c7d15166 |  | checkpoint | Fitoff DB
checkpoint-status | 88198ef1-2f47-44e0-b4fd-83a0aeb3fb97 |  | checkpoint | LAN test internals (add signature)
checkpoint-status | 26ad1959-f14b-4a0b-9839-d950584e8dce |  | checkpoint | Endpoints bagged (photos attached)
checkpoint-group | 494536d9-e0b8-47db-8c77-13dbff37c6e4 |  | section | Fitoff
checkpoint-status | 35ebb8a6-538e-445e-9828-498e2df36c6d |  | checkpoint | TV/Data faceplate fitted off (photos attached)
checkpoint-status | 8085dd46-e800-4afc-ae9e-353cd466ac74 |  | checkpoint | Nurse Call faceplates fitted off (photos attached)
checklist-sectioned | 7198dfa0-f8c9-4894-8ed8-5627603bf101 |  | checklist | NCS - Apartment Sign-Off |  |  |  |  | Yes | NCS - Apartment Sign-Off | c23e8133-fb35-4169-9077-f341a6f7b48f
checkpoint-group | cd6d416d-50bb-4148-8a50-19d2f17c6832 |  | section | Prewire
checkpoint-status | 94811440-dc1d-4420-a9c8-e358bd7ab03a |  | checkpoint | Internal cabling completed
checkpoint-status | 7ee58c7d-aff1-402e-a68d-2dfc4c2f41da |  | checkpoint | Main cabling completed - Attach photos below
checkpoint-status | f731c1e5-0cda-48e3-9a3d-d5207273ad2b |  | checkpoint | Flush boxes installed
checkpoint-status | 13dc047b-cf98-40c2-8c37-e41fbb191ef8 |  | checkpoint | Fire boxes installed - Attach photos below
checkpoint-status | 873399ed-bf32-4410-bd36-e036abc22346 |  | checkpoint | Fire walls point of entry - Attach photos below
checkpoint-status | cc3d6954-1f96-4904-8ef5-2086eea438d9 |  | checkpoint | Prewire works completed to specification/drawings - Area left clean & tidy
label | 914dd878-f0c6-58f3-aa55-391dd4b861f4 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checkpoint-group | a4ed848e-787f-4fd4-9102-199a6fb8a4fc |  | section | Termination & Testing
checkpoint-status | 41a2f1f8-d8dc-4a60-8e0e-443f2b4703b0 |  | checkpoint | Install DB
checkpoint-status | 925aa898-32d6-45e6-9ef1-539128ff09db |  | checkpoint | Fit off DB - Attach photos below
checkpoint-status | 61901c65-0de4-4d77-bf06-2330b06b21ac |  | checkpoint | LAN test internals - Attach Signature below
checkpoint-group | ef9015b9-018c-44b2-b6c7-b40ed6ae4184 |  | section | Fitoff
checkpoint-status | 2783fbfb-d6c5-4d3c-9d0c-75b702b5f6fb |  | checkpoint | TV/DATA fit off - Attach photos below
checkpoint-status | 6b6442d1-c5d5-42dd-814e-d0f8ba0b02fa |  | checkpoint | Nurse Call fit off completed - Attach photos below
checkpoint-status | b5a769c8-c386-446a-a017-461ca4c43bf1 |  | checkpoint | Fitoff works completed to specification/drawings - Area left clean & tidy
label | a354d05f-00ce-5c53-8acc-262577cac1e6 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist-flat | 1f6845d4-963d-4f4c-8962-556de94568e0 |  | checklist | Floor Commissioning v2 |  |  |  |  | Yes | SYS - Floor Commissioning v2 | c2a931a5-ae5e-46fe-954c-4e3a5f252d5d
checkpoint-status | fcca9286-ace3-4b6e-8c13-c92541b4042b |  | checkpoint | Tone Cables (Add Signature)
checkpoint-status | 7c685c47-7c44-41a4-99ca-b48c0b434bea |  | checkpoint | Separate Cables (Add Signature)
checkpoint-status | ff851040-335a-4d73-abc9-97bdbaa5923f |  | checkpoint | Cable Riser (Add Signature)
checklist-flat | e150f2fc-0af4-4720-91b0-545138006526 |  | checklist | Completion Documents |  |  |  |  | Yes | SYS - Completion Documents | c80c63a5-218e-49c2-a93c-1da6b97d9f88
checkpoint-status | 405e0405-82a7-4f0d-b654-c4f7c637d542 |  | checkpoint | PS3 attached
checkpoint-status | e83572d7-c5ec-4699-862e-d8529403ead6 |  | checkpoint | As-built plans attached
checkpoint-status | e77a5d12-1623-4983-9fd5-026532196f3a |  | checkpoint | Any other completion documents attached
checklist-flat | 245dae65-e803-4c9f-bd00-f123695576c3 |  | checklist | Floor Commissioning v1 |  |  |  |  | Yes | SYS - Floor Commissioning v1 | d2f7ec2c-381f-46aa-b3e9-7cd90b3466b1
checkpoint-status | 1839dfce-41d1-4c0c-9e06-27852308d2b2 |  | checkpoint | Build Comms Room (add signature)
checkpoint-status | 2827acc6-3fbd-4b59-ba04-d2db6a514102 |  | checkpoint | Cable Riser Installed (add signature)
checkpoint-status | d8794e21-8351-45ee-aabc-b8a7eb5e2018 |  | checkpoint | Tone Cables (add signature)
checkpoint-status | 56ca1041-abc1-45b5-9c34-49c816ee85fd |  | checkpoint | Separate Cables (add signature)
checkpoint-status | 211f35b6-9a81-412b-8f95-ab59a0c46d6f |  | checkpoint | QA has been reviewed and approved by the main contractor
holdpoint | 368fa7ee-dc5c-4b5a-ba4f-947a36813ea5 |  | signoff | Raise Remedial/ Main Contractor Signoff
checklist-flat | cddc33cc-1ae3-49b9-b3d4-507b46aafe40 |  | checklist | NCS - Building Commissioning |  |  |  |  | Yes | NCS - Building Commissioning | d6a21848-918f-42b7-9b6c-ee1eeaefc7fe
checkpoint-status | 3faecb49-6b7b-41a5-83e8-6e00a9a273ed |  | checkpoint | Separate cables Comissioned - Attach Signature Sign-Off below
checkpoint-status | 66f09901-38ec-436f-87af-94fa2bb5db96 |  | checkpoint | Separate security cables Comissioned - Attach Signature Sign-Off below
checkpoint-status | 0526e35f-a63a-4563-9e37-3dbe43a16047 |  | checkpoint | Complete cable riser Comissioned - Attach Signature Sign-Off below
checkpoint-status | bc6dbb73-d0c9-41c8-ba33-d4778c2f7da5 |  | checkpoint | Build patch panels Commissioned - Attach photos below
checkpoint-status | c16ca7ea-4394-47d1-ac04-3875c24b9802 |  | checkpoint | Build nurse call system Commissioned - Attach photos below
checkpoint-status | 18ba616f-332e-4c9d-be27-853bad6b7114 |  | checkpoint | Build MATV system Commissioned - Attach photos below
checkpoint-status | 4f180cbb-b32a-49cb-81de-1aba64b68045 |  | checkpoint | Build security panels Commissioned - Attach photos below
checkpoint-status | 696957ea-dc9e-4df1-a270-79b6890a5271 |  | checkpoint | Program nurse call system Comissioned - Attach Signature Sign-Off below
checkpoint-status | 518e98d6-ea22-4b53-b433-9130d0802985 |  | checkpoint | Commission nurse call system - Attach photos below
checkpoint-status | 6a394f1d-db36-4dfd-bb00-68f78ef43066 |  | checkpoint | Commission Security system - Attach photos below
checkpoint-status | 55e25dc2-2cb2-4984-9cdc-09456a948e21 |  | checkpoint | Commission Fire interface - Attach photos below
checklist-flat | c6d46122-6943-4a69-b9d6-795dd602bc59 |  | checklist | Floor Commissioning |  |  |  |  | Yes | SYS - Floor Commissioning Checklist | dcf1c7bb-9352-42c0-a652-7a86fc29c954
checkpoint-status | 49bc2d36-8af7-41b7-bf65-ff238028f248 |  | checkpoint | Build Comms Room (add signature)
checkpoint-status | 525903c3-c9c0-4727-8008-ce337f497b0f |  | checkpoint | Cable Riser Installed (add signature)
checkpoint-status | ad458c41-22ff-473f-a94a-e90f273671b9 |  | checkpoint | Tone Cables (add signature)
checkpoint-status | 079b3aef-1cc1-4b8f-9898-b19764d87079 |  | checkpoint | Separate Cables (add signature)
checklist-flat | 92ef8a9e-dab8-46d5-994f-340b4fa3b6a8 |  | checklist | Terminated & Tested |  |  |  |  | Yes | Terminated & Tested | dfb2574e-d1e8-4d89-84b2-4b5c83f8f64e
checkpoint-status | 7625e7b1-502b-44b2-8267-ffb85c8fa3c7 |  | checkpoint | Lan Test Complete
checkpoint-status |  |  | checklist | Install DB |  |  |  |  | Yes | Install DB | e266e430-4466-4d5e-9032-6e1bbe814c4a
checkpoint-status |  |  | checklist | Fit off DB - Attach photos below |  |  |  |  | Yes | Fit off DB - Attach photos below | ec88e507-a5f3-4ad2-b877-486759ecf5e1
checklist-flat | 58dbd71c-b682-4dca-9d44-19573a30859d |  | checklist | NCS - Building Commissioning |  |  |  |  | Yes | NCS - Building Commissioning | f071f2d4-837b-48c2-8059-86b57a53aa22
checkpoint-status | 07fdc15a-facf-49e6-b30c-d5a5c08d174b |  | checkpoint | Separate and Tone Security Cables (Add Signature)
checkpoint-status | 9a4f7937-88a7-499d-a3c3-b560a2872349 |  | checkpoint | Build Security Panels (Attach Photos)
checkpoint-status | 443aea8a-0daf-445f-b137-010bdd8ca434 |  | checkpoint | Build Patch Panels (Attach Photos)
checkpoint-status | aee52a27-e945-4e41-978e-bd9732cfe0ae |  | checkpoint | Build Nurse Call System (Attach Photos)
checkpoint-status | 409cafc9-56d4-46d5-804b-d0a87709f89f |  | checkpoint | Build Matv System (Attach Photos)
checkpoint-status | 15efba0d-28c7-42e7-bde0-7e4618f74376 |  | checkpoint | Program Nurse Call System (Add Signature)
checkpoint-status | d858427c-e6d1-4d8d-a9ac-e4ca071000ae |  | checkpoint | Commission Nurse Call System (Attach Photos)
checkpoint-status | d4569427-d5c9-4d9a-ac9c-42d8cfd1a745 |  | checkpoint | Commission Security System (Attach Photos)
checkpoint-status | 7bc76228-5a87-4b7c-82e5-04e7a56ab181 |  | checkpoint | Commission Fire Interface (Attach Photos)
checklist-flat | 600062c1-6eca-4805-9eef-d82182465f34 |  | checklist | NCS - Completion Documents |  |  |  |  | Yes | NCS - Completion Documents | f18aacf3-1fdd-44c2-ae39-47b76adf376b
checkpoint-status | cc23f047-7a46-4a07-a017-808f0b7860fc |  | checkpoint | PS3 Completed - Attached below
checkpoint-status | bc95226e-a5db-4cb0-8c83-1859db100fb0 |  | checkpoint | As-built plans Completed/Updated - Attached below
checkpoint-status | c966f365-06ef-48f7-a060-1fbbba7ff987 |  | checkpoint | Any other completion documents Completed - Attached below
checklist-flat | d1aefc89-7e8d-411f-9ce8-d79968a8c1ec |  | checklist | Install DB |  |  |  |  | Yes | Install DB | f5a36419-5866-45de-897a-df3565815fc2
checkpoint-status | 43467d54-bdbd-41e0-9b09-6021a8f28c9b |  | checkpoint | Fit Off Db (Photo Attached)
checkpoint-status | 011bc0b4-55ac-4643-ad77-de6871374af2 |  | checkpoint | Lan Test Internals (Add Signature)
checklist-flat | 509f5130-4894-4585-9277-598b31d488c9 |  | checklist | Building Commissioning v2 |  |  |  |  | Yes | SYS - Building Commissioning v2 | f6a044a1-0554-44e3-8b83-fb99907e9c50
checkpoint-status | e4d9aec2-5882-4fa1-ae4a-5b4748a55a35 |  | checkpoint | Separate Cables (Add Signature)
checkpoint-status | 62cc20ff-246f-41cb-bf15-9fc8aa251fc0 |  | checkpoint | Separate Security Cables (Add Signature)
checkpoint-status | 73b838f2-19f3-4ad5-bac1-62b9e6f43f5a |  | checkpoint | Complete Cable Riser (Add Signature)
checkpoint-status | fadc09cf-22d9-4af5-860f-d7115894e095 |  | checkpoint | Build Patch Panels (Attach Photos)
checkpoint-status | 6964c63c-3aa9-44d5-a736-1a541c999778 |  | checkpoint | Build Nurse Call System (Attach Photos)
checkpoint-status | 6f034332-7548-4e5d-af71-9916a18177ff |  | checkpoint | Build Matv System (Attach Photos)
checkpoint-status | a19ad82d-c962-42f5-8ed0-008b66a5ca6f |  | checkpoint | Build Security Panels (Attach Photos)
checkpoint-status | 37062f82-8ce9-49bd-ba8a-3da1805619f5 |  | checkpoint | Program Nurse Call System (Add Signature)
checkpoint-status | 8386d87c-7bab-4d7d-adb6-b04b68bd9cc0 |  | checkpoint | Commission Nurse Call System (Attach Photos)
checkpoint-status | 6ac0a103-9d26-44b2-9001-1c6c2335234c |  | checkpoint | Commission Security System (Attach Photos)
checkpoint-status | 67098efe-dcf1-4420-835a-e2c11b722072 |  | checkpoint | Commission Fire Interface (Attach Photos)