## Breakdown
Nurse Call- Kevin Hickman
Project Build QA
Stage 3 - THB11, THB13
THB11 (TH33, TH34, TH35, TH36)
|  |  |  | TH33 | Pre-populate | Townhouse Unit Installation
|  |  |  | TH34 | Pre-populate | Townhouse Unit Installation
|  |  |  | TH35 | Pre-populate | Townhouse Unit Installation
|  |  |  | TH36 | Pre-populate | Townhouse Unit Installation
THB13 (TH37, TH38, TH39)
|  |  |  | TH37 | Pre-populate | Townhouse Unit Installation
|  |  |  | TH38 | Pre-populate | Townhouse Unit Installation
|  |  |  | TH39 | Pre-populate | Townhouse Unit Installation
Completion Documents
| Stage 3 - THB11, THB13 |  |  |  | Pre-populate | CST-S-Completion Documents

## Checklist
type | name | values
checklist | Townhouse Unit Installation
section | Pre-wire
checkpoint | Area is left clean and tidy and approval to start work is obtained
checkpoint | Internal cabling complete
checkpoint | Main cabling complete (photos attached)
checkpoint | Flush boxes installed
holdpoint | Request sign off
section | Termination & Testing
checkpoint | Install DB
checkpoint | Fit off DB (photos attached)
checkpoint | LAN test internals
holdpoint | Request sign off
section | Fit off
checkpoint | Area is left clean and tidy and approved to start work is obtained
checkpoint | TV/DATA fit off (photos attached)
checkpoint | Nurse call fit off (photos attached)
holdpoint | Request sign off
type | name | values
Checklist | CST-S-Completion Documents
Checkpoint | All relevant Compliance Documentation completed and attached above
Checkpoint | Any Additional Compliance Documentation (Required under Section C and by consultants) - Completed and Attached
Checkpoint | Do not "Pass HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff