## Sheet1
Foundation
Stage 1
|  | Basement | Lift 1 | "APARTMENT SIGN OFF" | Pre wire | internal cabling complete
|  |  | Lift 2 |  |  | main cabling complete (photos attached)
|  |  | Lift Lobby |  |  | flush boxes installed
|  |  | Car Park Lift Lobby |  |  | fire boxes installed (photos attached)
|  |  | Car Park Staircase |  |  | fire walls point of entry (photos attached)
[5 empty] | termination and testing | install DB
|  | GF Data | D-G-1 |  |  | fit off DB (photo attached)
|  |  | D-G-2 |  |  | LAN test internals (add signature)
D-G-3
D-G-4
|  |  | D-G-5 |  | fit off | TV/DATA fit off (photos attached)
|  |  | D-G-6 |  |  | nurse call fit off (photos attached)
D-G-7
D-G-8
|  |  | D-G-9 | "COMMON AREA SIGN OFF" | Pre wire | cabling complete
|  |  | D-G-10 |  |  | flush box fire box installed (photos attached of fire box)
|  |  | D-G-11 |  |  | attach photos of fire penetrations
D-G-12
D-G-13
|  |  | D-G-14 |  | terminated and tested | LAN test complete
D-G-15
|  |  | D-G-16 |  | fit off | nurse call fit off
|  |  | D-G-17 |  |  | camera fit off
|  |  | D-G-18 |  |  | intercom fit off
|  |  | D-G-19 |  |  | Data Jacks Fit off
|  |  | D-G-20 |  |  | WiFi Fit off
|  |  | D-G-21 |  |  | Repeaters Installed.
D-G-22
|  |  | D-G-23 | "FLOOR COMMISIONING" | tone cables (add signature)
|  |  | D-G-24 |  | separate cables (add signature)
|  |  | D-G-25 |  | cable riser (add signature)
D-G-26
D-G-27
|  |  | D-G-28 | Building Commissioning | separate cables (add signature)
|  |  | D-G-29 |  | separate security cables (add signature)
|  |  | D-G-30 |  | complete cable riser (add signature)
|  |  | D-G-31 |  | build patch panels (attach photo's)
|  |  | D-G-32 |  | build nurse call system (attach photo's)
|  |  | D-G-33 |  | build MATV system (attach photo's)
|  |  | D-G-34 |  | build security panels (attach photo's)
|  |  | D-G-35 |  | program nurse call system (add signature)
|  |  | D-G-36 |  | Commission nurse call system (attach photo's)
|  |  | D-G-37 |  | Commission Security system (attach photo's)
|  |  | D-G-38 |  | Commission Fire interface (attach photo's)
D-G-39
D-G-40
D-G-41
D-G-42
D-G-43
D-G-44
D-G-45
D-G-46
D-G-47
D-G-48
D-G-49
D-G-50
D-G-51
D-G-52
D-G-53
D-G-54
D-G-55
D-G-56
D-G-57
D-G-58
D-G-59
D-G-60
D-G-61
D-G-62
D-G-63
D-G-64
D-G-65
D-G-66
D-G-67
D-G-68
D-G-69
D-G-70
D-G-71
D-G-72
D-G-73
D-G-74
D-G-75
D-G-76
D-G-77
D-G-78
D-G-79
D-G-80
D-G-81
D-G-82
D-G-83
D-G-84
D-G-85
D-G-86
D-G-87
D-G-88
D-G-89
D-G-90
D-G-91
D-G-92
D-G-93
D-G-94
D-G-95
D-G-96
D-G-97
D-G-98
D-G-99
D-G-100
D-G-101
D-G-102
D-G-103
D-G-104
D-G-105
D-G-106
D-G-107
D-G-108
D-G-109
D-G-110
D-G-111
D-G-112
D-G-113
D-G-114
D-G-115
D-G-116
D-G-117
D-G-118
D-G-119
D-G-120
D-G-121
D-G-122
D-G-123
D-G-124
D-G-125
D-G-126
D-G-127
D-G-128
D-G-129
D-G-130
D-G-131
D-G-132
D-G-133
D-G-134
D-G-135
D-G-136
D-G-137
D-G-138
D-G-139
D-G-140
D-G-141
D-G-142
D-G-143
D-G-144
D-G-145
D-G-146
D-G-147
D-G-148
D-G-149
D-G-150
D-G-151
D-G-152
D-G-153
D-G-154
D-G-155
D-G-156
D-G-157
GF Data Comissioning
|  | GF CCTV | AG-C001
AG-C002
AG-C003
AG-C004
AG-C005
AG-C006
AG-C007
AG-C008
AG-C009
AG-C010
AG-C011
AG-C012
GF CCTV Comissioning
|  | GF Intercom | AG-IC01
AG-IC02
AG-IC03
GF Intercom Comissioning
|  | GF Access Control | AG-DR001
AG-DR002
AG-DR003
AG-DR004
AG-DR005
AG-DR006
AG-DR007
AG-DR008
AG-DR009
AG-DR010
AG-DR011
AG-DR012
AG-DR013
GF Access Control Comissioning
|  | GF Intrusion | AG-RS01
AG-RS02
AG-RS03
AG-RS04
AG-RS05
GF Intrusion Comissioning
|  | L1 Apartments | APT 1C
APT 2U
APT 3H
APT 4B
APT 5B
APT 6G
APT 7F
APT 8V
APT 9E
APT 10A
APT 11A
APT 12A
Level 1 Commisioning
|  | L1 CCTV | A1-C001
A1-C002
A1-C003
L1 CCTV Commisioning
|  | L1 Intercom | A1-IC01
A1-IC02
A1-IC03
A1-IC04
A1-IC05
A1-IC06
A1-IC07
A1-IC08
A1-IC09
A1-IC10
A1-IC11
A1-IC12
Level 1 Intercom Commisioning
|  | L2 Apartments | APT 13B
APT 14U
APT 15H
APT 16B
APT 17B
APT 18G
APT 19F
APT 20V
APT 21E
APT 22A
APT 23A
APT 24A
Level 2 Commisioning
|  | L2 CCTV | A2-C001
A2-C002
A2-C003
Level 2 CCTV Commisioning
|  | L2 Intercom | A2-IC01
A2-IC02
A2-IC03
A2-IC04
A2-IC05
A2-IC06
A2-IC07
A2-IC08
A2-IC09
A2-IC10
A2-IC11
A2-IC12
L2 Intercom Commisioning
|  | L2 CCTV | A2-C001
A2-C002
A2-C003
L2 CCTV Commisioning
|  | L2 Access Control | A2-DR001
A2-DR002
A2-DR003
L2 Access Control Commisioning
|  | L2 Vincard | A2-VC01
A2-VC02
A2-VC03
A2-VC04
A2-VC05
A2-VC06
A2-VC07
A2-VC08
A2-VC09
A2-VC10
A2-VC11
A2-VC12
L2 Vincard Commisioning
|  | L3 Apartments | APT 25S
APT 26T
APT 27K
APT 28L
APT 29L
APT 30M
APT 31N
APT 32O
APT 33C
APT 34C
APT 35C
Level 3 Commisioning
|  | L3 Intercom | A3-IC01
A3-IC02
A3-IC03
A3-IC04
A3-IC05
A3-IC06
A3-IC07
A3-IC08
A3-IC09
A3-IC10
A3-IC11
Level 3 Intercom Commisioning
|  | L3 CCTV | A3-C001
A3-C002
A3-C003
Level 3 CCTV Commisioning
|  | L3 Access Control | A3-DR001
A3-DR002
A3-DR003
L3 Access Control Commisioning
|  | L3 Vincard | A3-VC01
A3-VC02
A3-VC03
A3-VC04
A3-VC05
A3-VC06
A3-VC07
A3-VC08
A3-VC09
A3-VC10
A3-VC11
L3 Vincard Commisioning
|  | L4 Apartments | APT 36S
APT 37T
APT 38K
APT 39L
APT 40L
APT 41M
APT 42Q
APT 43R
APT 44C
APT 45C
Level 4 Commisioning
|  | L4 CCTV | A4-C001
A4-C002
A4-C003
Level 4 CCTV Commisioning
|  | L4 Intercom | A4-IC01
A4-IC02
A4-IC03
A4-IC04
A4-IC05
A4-IC06
A4-IC07
A4-IC08
A4-IC09
A4-IC10
A4-IC11
Level 4 Intercom Commisioning
|  | L4 Access Control | A4-DR001
A4-DR002
A4-DR003
L4 Access Control Commisioning
|  | L4 Lift Control | A4-LFC01
A4-LFC02
L4 Lift Control Commisioning
|  | L4 Vincard | A4-VC01
A4-VC02
A4-VC03
A4-VC04
A4-VC05
A4-VC06
A4-VC07
A4-VC08
A4-VC09
A4-VC10
A4-VC11
L4 Vincard Commisioning