## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fire Damper Schedule - GPL-QSE-ITP-SERV-002 (Rev 01) |  |  |  |  | Yes | Fire Damper Schedule - GPL-QSE-ITP-SERV-002 (Rev 01) | 01519fda-f9f1-46ab-a2cd-9fc868f966dd
checkpoint-status |  |  | checkpoint | Confirm access for fire damper adequate ie access panel in duct or access panel
checkpoint-status |  |  | checkpoint | Confirm adjacent fire rated walls are structurally adequate ie no damaged or incomplete walls
checkpoint-status |  |  | checkpoint | Confirm label installed identifying manufacturer and type of damper
checkpoint-status |  |  | checkpoint | Confirm fusible link installed – Not applicable for in tumescent damper type
checkpoint-status |  |  | checkpoint | Confirm airflow assists with closure of blade
checkpoint-status |  |  | checkpoint | Confirm flanges are installed and mounted all around damper
checkpoint-status |  |  | checkpoint | Confirm break away joint installed if ductwork attached
checkpoint-status |  |  | checkpoint | Confirm wall penetration not shared with other services, ie no cables in wall penetration
checkpoint-status |  |  | checkpoint | Confirm fire damper installed in line of wall
checkpoint-status |  |  | checkpoint | Confirm any voids in walls have correct amount of fire-seal
checkpoint-status |  |  | checkpoint | Confirm Damper in good condition and not activated
checkpoint-status |  |  | checkpoint | Mechanical Subcontractor ITP received
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-SERV-002 (Rev 01)
label | deb4895d-774c-5bdb-8ae0-77c7ffc35ad5 |  | note | Authorised By: FA
label | b553a44a-4bd6-5f44-b0dc-f41b18fc5098 |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Mechanical Services Rough In - GPL-QSE-ITP-SERV-005 (Rev 01) |  |  |  |  | Yes | Mechanical Services Rough In - GPL-QSE-ITP-SERV-005 (Rev 01) | 0d86e0c4-0848-4401-8cb6-8b12ccafc9b0
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any duct penetrating fire-rated walls or shafts are sealed both sides of penetration with Intumescent fire mastic up to 20mm
checkpoint-status |  |  | checkpoint | Confirm the following services have a clearance from any mechanical fire dampers as per BCA C315
boolean | 3e9d1696-f15a-5f1a-ba68-b417f237ed5f |  | tickbox | 100mm from services cables and wires
boolean | 9a837537-324e-5db9-81c9-f181893527af |  | tickbox | 200mm from pipes
checkpoint-status |  |  | checkpoint | Confirm any duct penetrating thru fire rated wall to have drop off nycon rivets
checkpoint-status |  |  | checkpoint | Confirm fire dampers installed both sides sealed correctly, as per manufacturer’s requirement and have access panels (refer to separate “Fire Damper ITP”)
checkpoint-status |  |  | checkpoint | Fire damper approval Data sheet cited and signed
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Acoustic Requirements
checkpoint-group |  |  | section | Acoustic Requirement
checkpoint-status |  |  | checkpoint | Confirm flexible ductwork is acoustic (Inner flex is perforated and insulation lining between inner and outer flex)
checkpoint-status |  |  | checkpoint | Confirm that the AC fan coil unit is vibration isolated with in shear rubber mount or springs from the structure and ductwork
checkpoint-status |  |  | checkpoint | Confirm toilet/kitchen exhaust fans are vibration isolated with in shear rubber mounts
checkpoint-status |  |  | checkpoint | Confirm sheet metal ductwork has inner acoustic lining if required
checkpoint-status |  |  | checkpoint | Confirm that all metal ductwork is not fixed directly to concrete soffit
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Mechanical Services
checkpoint-group |  |  | section | Performance Requirements - Prior to Sheeting Walls
checkpoint-status |  |  | checkpoint | Confirm all flexible and sheet metal ducting has been installed as per drawings
checkpoint-status |  |  | checkpoint | Confirm wiring of AC controls are located as per architectural requirements
checkpoint-status |  |  | checkpoint | Confirm all supply and return piping from riser to FCU in place and charged
checkpoint-status |  |  | checkpoint | Confirm no flexible ductwork is torn or damaged
checkpoint-status |  |  | checkpoint | “Emer” duct seal to all sheet metal ductwork holes
checkpoint-status |  |  | checkpoint | Confirm sealing of flexible connections between kitchen/ toilet exhaust fan and metal ducting (mechanically fixed required)
checkpoint-status |  |  | checkpoint | Confirm electrical panel and filters are accessible on FCU from access panel for future inspections
checkpoint-status |  |  | checkpoint | Confirm spreaders are installed to flexible duct hanging system to prevent squashing of flexi
checkpoint-status |  |  | checkpoint | Confirm all equipment is wired and complete (Ready for making active)
checkpoint-status |  |  | checkpoint | Confirm all condensate drains and trays (incl safety tray have been connected to hydraulic wastes and wet tested Pig tails to be accessible from Access panel Attach Test Sheet from subcontractor)
checkpoint-status |  |  | checkpoint | Confirm all refrigerant or condenser water testing required has been carried out (Attach test sheet) Insulated as required
checkpoint-status |  |  | checkpoint | Confirm all ceiling and bulkhead plenum boxes have been installed as per RCP drawings
checkpoint-status |  |  | checkpoint | Confirm access panel locations marked out and identified on slab below (review arch RCP location) Ensure clear access to controls and filters
checkpoint-status |  |  | checkpoint | Confirm all pipework is supported correctly with uni-strut/timber blocks/ saddles and insulation Drainage has fallen to tundish
checkpoint-status |  |  | checkpoint | Confirm all Dampers are fully open
checkpoint-status |  |  | checkpoint | Check quality and position of electronic dampers and controls
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-SERV-005 (Rev 01)
label | 615bf7c1-db09-5c61-ab56-465ed5d91dd6 |  | note | Authorised By: FA
label | f1f9d1b1-01d0-5b10-aa98-89030857d432 |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Waterproofing - Rooftop Areas |  |  |  |  | Yes | Waterproofing - Rooftop Areas | 116f9a99-c4c2-4d32-920a-0a390a2e0b79
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Floor wastes are free of waste material and are in correct location & signed off by plumber
checkpoint-status |  |  | checkpoint | Confirm concrete floor has structurally fall to wastes
checkpoint-status |  |  | checkpoint | Confirm concrete floor slab 100% clean, free of water, dirt dust and other condiments
checkpoint-status |  |  | checkpoint | Confirm no ponding of water by completing water testing to slab
checkpoint-status |  |  | checkpoint | If ponding of water occurs, localized topping of slab required to create fall and water test again
checkpoint-status |  |  | checkpoint | Confirm primer used to floors and walls as per manufacturers requirements
checkpoint-status |  |  | checkpoint | HOLD POINT
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | TESTING OF MEMBRANE: Confirm no pinholes with holiday detector “spark test” after minimum drying time
checkpoint-status |  |  | checkpoint | If pinholes are found – patch and confirm which area and spark test again
checkpoint-status |  |  | checkpoint | Fill floors with water to height of setdown: Leave for 24 hours, If leaks were found – re-tank and confirm which area and floor test again
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed with sand cement topping
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-011 (Rev 01)
label | 52320663-9abc-5db3-bf04-72698476d927 |  | note | Authorised By: FA
label | ed8557d6-1061-5660-b83d-125f68328106 |  | note | Issue Date: 301118
checklist-sectioned |  |  | checklist | Louvres - ITP (Rev00) |  |  |  |  | Yes | Louvres - ITP (Rev00) | 11716884-e63c-41b0-9fd5-552ecc04b699
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Confirm correct Louvre type as per architectural drawings and shop drawings
checkpoint-status |  |  | checkpoint | Confirm structural opening for louvres is as per design
checkpoint-status |  |  | checkpoint | Confirm louvre profile constructed as per approved shop drawings prior to installation
checkpoint-status |  |  | checkpoint | Confirm louvre colour is correct as per shop drawings and approved sample
label | 4c517eb1-ee4a-592b-843c-0e63313ef707 |  | note | Refer Architectural drawings & Shop Drawings
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm louvre fixings as correct as per approved shop drawings and have been approved for relevant wind loads
checkpoint-status |  |  | checkpoint | Confirm louvres in correct location on façade, installed true and plumb
checkpoint-status |  |  | checkpoint | Confirm any caulking and sealing completed on louvres/brackets
checkpoint-status |  |  | checkpoint | Confirm slotted holes in louvre fixing zones to allow for slab deflection
checkpoint-status |  |  | checkpoint | Confirm all fixings are stainless steel
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Louvres - Hurstville ITP (Rev00)
label | 3b2a8112-739f-5207-9cc9-dff55d352eae |  | note | Authorised By: GN
label | 72db1b57-f462-5534-9762-1b422520a88d |  | note | Issue Date: 250620
checklist-sectioned |  |  | checklist | Masonry - GPL-QSE-ITP-FAC-002 (Rev 00) |  |  |  |  | Yes | Masonry - GPL-QSE-ITP-FAC-002 (Rev 00) | 198e3f44-099a-4491-8882-3dc9c796a22f
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Inspected and accepted the work area and surfaces and structure ready to commence work
checkpoint-status |  |  | checkpoint | Confirm set out of walls as per Architectural Drawings
label | e79938cf-6dc6-58de-a2db-cf6a6f578072 |  | note | Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Confirm that all penetrations as required for services are identified and marked (ie mechanical, electrical, fire, hydraulic, etc)
checkpoint-status |  |  | checkpoint | Confirm bricks/blocks are correct manufacturer, colour and size as per drawings, specs and finishes schedules
checkpoint-status |  |  | checkpoint | Confirm brick laying pattern (ie stretcher bond, stack bond etc) is as per drawings, specs and finishes schedules
checkpoint-status |  |  | checkpoint | Confirm mortar and caulking colours are as per specs and finishes schedules
checkpoint-status |  |  | checkpoint | Confirm vermin/insect/ fire protection requirements are compiled to for all masonry sundries (stainless steel weep hole cassettes, cavity mesh, brick ties etc)
checkpoint-status |  |  | checkpoint | Confirm FRL’s and that bricks/blocks will achieve requirements as per specs and relevant fire reports
checkpoint-status |  |  | checkpoint | Obtain certificate of verification from supervising engineer Confirmed Site storage requirements for bricks/blocks, mortar and sundries
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm Shelf Angles are Installed as per installation certificate, Confirm shelf angle RL’s work to brick gauge requirements prior to installing
checkpoint-status |  |  | checkpoint | All damp proof course built in
checkpoint-status |  |  | checkpoint | All flashings and wall ties built in
checkpoint-status |  |  | checkpoint | Confirm that ties are installed at correct centers (verify with engineer’s advice or installation guidelines)
checkpoint-status |  |  | checkpoint | All cavities clean and clear
label | d4788e9e-87cd-5495-89bd-29a83cd4ba69 |  | note | Ensure all Damp Proof Courses/flashings are free of damage and clean (photo evidence)
checkpoint-status |  |  | checkpoint | Gaps closed below soffit overhead beams
checkpoint-status |  |  | checkpoint | Ensure weepholes are installed at correct centers and cleared before completing area
label | 93775f65-2872-55af-9340-7e424f56a638 |  | note | Confirm overflows are installed as per the design intent and heights/orientation are consistent
checkpoint-status |  |  | checkpoint | Ensure all sill/header courses are laid level, all joint sizes are consistent and ironed correctly and no chips are visible
checkpoint-status |  |  | checkpoint | Confirm joint and perp sizes are consistent and joints are evenly ironed as required (photo evidence)
checkpoint-status |  |  | checkpoint | Check verticality between panels and that no steps in face work are present
checkpoint-status |  |  | checkpoint | Inspect all joints are caulked where required and colour is correct as spec’d
checkpoint-status |  |  | checkpoint | Final brick/block clean
label | 15b44c4a-3153-5fde-ba95-e99eae0ec6f7 |  | note | Confirm cleaning method complies to manufacturers specs and brick cleaner is THINK accredited
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Installation Certificate
label | 060eae56-df75-531a-86df-4546afbfe5a8 |  | note | Attach Installation Certificate
checkpoint-status |  |  | checkpoint | External Sign Off (Inspection by architect/client required prior to scaffold dismantle)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FAC-002 (Rev 00)
label | 042f3114-22e8-5706-9005-bd00c6dc742a |  | note | Authorised By: FA
label | 5408e382-2682-5953-b24f-2a9665fce77c |  | note | Issue Date: 220319
checklist-sectioned |  |  | checklist | Level Compliance - GPL-QSE-ITP-FIN-014(Rev 00) |  |  |  |  | Yes | Level Compliance - GPL-QSE-ITP-FIN-014(Rev 00) | 1d680c9a-f700-4c09-b180-d5401b9dca89
checkpoint-group |  |  | section | Hebel
checkpoint-status |  |  | checkpoint | Attach Hebel Inspection Report
checkpoint-status |  |  | checkpoint | Confirm all outstanding items have been signed off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-group |  |  | section | Fire Compliance
checkpoint-status |  |  | checkpoint | Attach Fire Compliance Inspection Report
checkpoint-status |  |  | checkpoint | Confirm all outstanding Items have been Signed off
checkpoint-status |  |  | checkpoint | Attach Fire Penetration Register
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-group |  |  | section | Acoustic Compliance
checkpoint-status |  |  | checkpoint | Attach Acoustic Consultant Inspection Report of ALL Walls
checkpoint-status |  |  | checkpoint | Confirm all outstanding items have been closed out
holdpoint |  |  | signoff | HOLD POINT - ATTACH ACOUSTIC COMPLIANCE CLOSE-OUT & PHOTOS
checkpoint-group |  |  | section | Access Compliance
checkpoint-status |  |  | checkpoint | Attach Access Inspection Report of ALL Areas
checkpoint-status |  |  | checkpoint | Confirm all outstanding items have been closed out
holdpoint |  |  | signoff | HOLD POINT - ATTACH ACCESS COMPLIANCE CLOSE-OUT & PHOTOS
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-014(Rev 00)
label | 96ed0163-ee1a-5395-8dfb-f1bc8bd5ab54 |  | note | Authorised By: FA
label | 2f123ac8-fdea-5861-9c6e-d53766ba50cc |  | note | Issue Date: 301118
checklist-sectioned |  |  | checklist | Electrical Rough In - GPL-QSE-ITP-SERV-001 (Rev 01) |  |  |  |  | Yes | Electrical Rough In - GPL-QSE-ITP-SERV-001 (Rev 01) | 1df025f3-1773-4cf1-9d81-5b01eef232f7
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any cable/conduit penetrating Fire rated walls are sealed both sides with Intumescent fire mastic up to 20mm
checkpoint-status |  |  | checkpoint | Confirm Fire Rated walls have not been chased in for any electrical services
checkpoint-status |  |  | checkpoint | Confirm cabling not bunched excessively through penetration
checkpoint-status |  |  | checkpoint | Confirm fire rated boxes installed (2hr) and sealed with Intumescent mastic both sides and not chased into hebel more than 15mm (Check acoustic requirement)
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to proceed to electrical services
checkpoint-group |  |  | section | Electrical Services
checkpoint-status |  |  | checkpoint | Confirm height and location of the following
text | 9ef35a5f-661b-5e8d-a038-6cdc77034221 |  | textbox | Internal GPOs/ TV & data |  | mm above FFL
text | a522badb-bd25-5b6b-9827-8a28ac00ed86 |  | textbox | Fridge GPO |  | mm above FFL
text | c87b82d0-b821-5982-b041-b5547cf49520 |  | textbox | Kitchen GPO |  | mm above FFL
text | e480beb7-331a-5d16-a87d-8c7f33b3cc3b |  | textbox | Bathroom GPO |  | mm above FFL
text | 9eb61813-19de-5f4b-9a51-314f3557487c |  | textbox | Light switches |  | mm above FFL
text | 7f4ba568-5022-57fd-b611-1f8d95ff40bb |  | textbox | Security Intercom |  | mm above FFL
text | 6364196b-5332-577f-a6da-9dc28c01fe55 |  | textbox | External GPO |  | mm above FFL
checkpoint-status |  |  | checkpoint | Confirm wiring for switches are in place
checkpoint-status |  |  | checkpoint | Confirm TV and GPO locations in place
checkpoint-status |  |  | checkpoint | Confirm location of bathroom GPO has been coordinated with joinery shop drawings
checkpoint-status |  |  | checkpoint | Confirm light allocations as per the drawings
checkpoint-status |  |  | checkpoint | Confirm location of NBN wiring has been coordinated with joinery shop drawings
checkpoint-status |  |  | checkpoint | Confirm location of DB board has been coordinated with kitchen shop drawings
checkpoint-status |  |  | checkpoint | Confirm intercom wiring in place
checkpoint-status |  |  | checkpoint | Confirm wiring to kitchen appliances in place as per kitchen joinery shop drawing
checkpoint-status |  |  | checkpoint | Confirm wiring to external lights confirmed
checkpoint-status |  |  | checkpoint | Confirm wiring to FCU and exhaust motors in place
checkpoint-status |  |  | checkpoint | Confirm fire speaker cabling is installed
checkpoint-status |  |  | checkpoint | Confirm adaptable unit requirements if applicable
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-SERV-001 (Rev 01)
label | 89e91972-a0db-5032-964e-0142f1713385 |  | note | Authorised By: FA
label | 2ebabc4a-7b3e-5dd3-b5ad-6a459548e083 |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Balustrades |  |  |  |  | Yes | Balustrades | 1e0f93f1-416f-43e6-b114-34682a811c6f
checkpoint-group |  |  | section | Prior to work
checkpoint-status |  |  | checkpoint | Confirm correct balustrade type as per architectural drawings.
checkpoint-status |  |  | checkpoint | Confirm revised access strategy to/from balcony (if required) prior to commencing works.
checkpoint-group |  |  | section | During to work
checkpoint-status |  |  | checkpoint | Confirm balustrade complies with BCA requirements:
checkpoint-status |  |  | checkpoint | No foot hold between 150mm and 760mm.
checkpoint-status |  |  | checkpoint | Confirm balustrade complies with BCA requirement:
checkpoint-status |  |  | checkpoint | Height of balustrade1000mm minimum from FFL.
checkpoint-status |  |  | checkpoint | Confirm balustrade complies with BCA requirement:
checkpoint-status |  |  | checkpoint | 125mm maximum distance between verticals posts and walls.
checkpoint-status |  |  | checkpoint | Confirm that adjoining balustrades have common level or line.
checkpoint-status |  |  | checkpoint | Confirm base plate installed to posts.
checkpoint-status |  |  | checkpoint | Confirm bottom track of balustrade is same RL as window subsill.
checkpoint-status |  |  | checkpoint | Confirm overflow strategy is installed and consistent with design.
checkpoint-status |  |  | checkpoint | Confirm all aluminum is powder coated as specified.
checkpoint-status |  |  | checkpoint | Confirm all exposed toughened glass is polished at ends.
checkpoint-status |  |  | checkpoint | Confirm top rail is installed as specified
checkpoint-group |  |  | section | After Work
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP.
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checklist-flat |  |  | checklist | Kitchen Joinery - GPL-QSE-ITP-FIN-002 (Rev 00) |  |  |  |  | Yes | Kitchen Joinery - GPL-QSE-ITP-FIN-002 (Rev 00) | 1f733ddb-41e2-4647-a2e6-4d7bd696f4ba
checkpoint-status |  |  | checkpoint | Confirm colour schedules with contract or purchaser schedules
checkpoint-status |  |  | checkpoint | Confirm kitchen island installed square
checkpoint-status |  |  | checkpoint | Confirm laminate to run in required direction
checkpoint-status |  |  | checkpoint | Confirm no joints visible to laminate
checkpoint-status |  |  | checkpoint | Kickboard to be installed AFTER tiling is completed
checkpoint-status |  |  | checkpoint | All finish panels installed
checkpoint-status |  |  | checkpoint | Confirm all screw caps installed
checkpoint-status |  |  | checkpoint | Confirm skirting installed to fridge and pantry
checkpoint-status |  |  | checkpoint | Confirm all rough cuts have been rectified
checkpoint-status |  |  | checkpoint | Confirm alignment of doors and draws
checkpoint-status |  |  | checkpoint | Confirm all edges strips align properly
checkpoint-status |  |  | checkpoint | Confirm kitchen handle installed
checkpoint-status |  |  | checkpoint | Confirm cutlery tray installed
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT - Orwell to Inspect
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-002 (Rev 00)
label | 9872951b-975f-5005-a7c2-c3b8f1dfdf4b |  | note | Authorised By: FA
label | afb70aae-12ee-5b8d-bfd8-5e74b602ee23 |  | note | Issue Date: 011914
checklist-sectioned |  |  | checklist | Scaffold |  |  |  |  | Yes | Scaffold | 22014a83-85ec-49a9-b7a5-76b3d2df36e8
checkpoint-group |  |  | section | North Elevation
checkpoint-status |  |  | checkpoint | Confirm the following ITP's have been closed out
boolean | d4c68f67-d742-5220-bab9-ef216401879e |  | tickbox | Masonry
boolean | ace27a5a-b870-57d3-a437-7d6f75802365 |  | tickbox | Windows
boolean | d5f431c0-fda8-5eb9-8115-3c4933a11408 |  | tickbox | Cladding
boolean | f88e65f3-b8d8-5c67-a705-e42ea40e7f1c |  | tickbox | Balustrade
checkpoint-status |  |  | checkpoint | Confirm level is water tight and all areas are adequately caulked
checkpoint-status |  |  | checkpoint | Confirm all Ties have been removed, brick has been reinstated and acid wash has been completed.
checkpoint-status |  |  | checkpoint | Confirm overflows are square and installed at the correct height
checkpoint-status |  |  | checkpoint | Confirm render is defect free
checkpoint-status |  |  | checkpoint | Confirm final paint is complete prior to balustrade install
checkpoint-status |  |  | checkpoint | Confirm balustrade is installed with no defects (scratches, flush with wall)
checkpoint-status |  |  | checkpoint | Confirm façade is clean and ready to strip
checkpoint-status |  |  | checkpoint | Commence Scaffold Strip
checkpoint-group |  |  | section | South Elevation
checkpoint-status |  |  | checkpoint | Confirm the following ITP's have been closed out
boolean | 3a29768d-00fd-506d-951f-ec5607fea3de |  | tickbox | Masonry
boolean | e3492cbf-dc96-578c-ab00-9bfab875ff8d |  | tickbox | Windows
boolean | f8158419-451d-5384-9801-1b06e74582ee |  | tickbox | Cladding
boolean | 4d602bbd-0e0c-58cf-9813-f7214253d409 |  | tickbox | Balustrade
checkpoint-status |  |  | checkpoint | Confirm level is water tight and all areas are adequately caulked
checkpoint-status |  |  | checkpoint | Confirm all Ties have been removed, brick has been reinstated and acid wash has been completed.
checkpoint-status |  |  | checkpoint | Confirm overflows are square and installed at the correct height
checkpoint-status |  |  | checkpoint | Confirm render is defect free
checkpoint-status |  |  | checkpoint | Confirm final paint is complete prior to balustrade install
checkpoint-status |  |  | checkpoint | Confirm balustrade is installed with no defects (scratches, flush with wall)
checkpoint-status |  |  | checkpoint | Confirm façade is clean and ready to strip
checkpoint-status |  |  | checkpoint | Commence Scaffold Strip
checkpoint-group |  |  | section | East Elevation
checkpoint-status |  |  | checkpoint | Confirm the following ITP's have been closed out
boolean | 622bc6e3-4a18-55cd-8cd8-69b5b68e87d5 |  | tickbox | Masonry
boolean | d25259fd-fc80-5079-849c-e3ec8294fdf2 |  | tickbox | Windows
boolean | 8c2d4b32-0d84-5798-bf5e-4731c38d878e |  | tickbox | Cladding
boolean | 067c39a1-2a52-5fd1-b3be-aacbc263e81a |  | tickbox | Balustrade
checkpoint-status |  |  | checkpoint | Confirm level is water tight and all areas are adequately caulked
checkpoint-status |  |  | checkpoint | Confirm all Ties have been removed, brick has been reinstated and acid wash has been completed.
checkpoint-status |  |  | checkpoint | Confirm overflows are square and installed at the correct height
checkpoint-status |  |  | checkpoint | Confirm render is defect free
checkpoint-status |  |  | checkpoint | Confirm final paint is complete prior to balustrade install
checkpoint-status |  |  | checkpoint | Confirm balustrade is installed with no defects (scratches, flush with wall)
checkpoint-status |  |  | checkpoint | Confirm façade is clean and ready to strip
checkpoint-status |  |  | checkpoint | Commence Scaffold Strip
checkpoint-group |  |  | section | West Elevation
checkpoint-status |  |  | checkpoint | Confirm the following ITP's have been closed out
boolean | f0a6a661-f944-5e5c-8fe4-a045d01c1b26 |  | tickbox | Masonry
boolean | 267b38da-ca40-5466-ade8-464f4b5fc064 |  | tickbox | Windows
boolean | f958ab84-e72d-52ec-845d-f6404d56dc61 |  | tickbox | Cladding
boolean | 48eb280c-a715-55d8-a1d1-75e420b5abb3 |  | tickbox | Balustrade
checkpoint-status |  |  | checkpoint | Confirm level is water tight and all areas are adequately caulked
checkpoint-status |  |  | checkpoint | Confirm all Ties have been removed, brick has been reinstated and acid wash has been completed.
checkpoint-status |  |  | checkpoint | Confirm overflows are square and installed at the correct height
checkpoint-status |  |  | checkpoint | Confirm render is defect free
checkpoint-status |  |  | checkpoint | Confirm final paint is complete prior to balustrade install
checkpoint-status |  |  | checkpoint | Confirm balustrade is installed with no defects (scratches, flush with wall)
checkpoint-status |  |  | checkpoint | Confirm façade is clean and ready to strip
checkpoint-status |  |  | checkpoint | Commence Scaffold Strip
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checklist-sectioned |  |  | checklist | Slab on Ground - GPL-QSE-ITP-STRUC-004 (Rev 01) |  |  |  |  | Yes | Slab on Ground - GPL-QSE-ITP-STRUC-004 (Rev 01) | 28d411c7-1c25-4c43-9a23-12860da8540c
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm RL of slab concrete finish
checkpoint-status |  |  | checkpoint | Confirm vapour barrier installed over correct subbase
checkpoint-status |  |  | checkpoint | Confirm slab thickenings are as per the structural requirements
text | 3af44da9-a971-535c-852a-9d9133b2b8f6 |  | textbox | Minimum thickening
checkpoint-status |  |  | checkpoint | Confirm Lightning protection installed to footings as per Electricians requirements
checkpoint-status |  |  | checkpoint | Check for reinforcement cover
checkpoint-status |  |  | checkpoint | Confirm hydraulic pits installed as per hydraulic detail (Attach hydraulic ITP)
checkpoint-status |  |  | checkpoint | Confirm starter bars to columns and walls installed in correct location and spacing
checkpoint-status |  |  | checkpoint | Check for set downs to wet areas Heights checked as correct
checkpoint-status |  |  | checkpoint | Confirm all cast in elements to Construction joints installed – key joints, construction joints, expansion joints
checkpoint-status |  |  | checkpoint | Confirm bond breaker has been applied to key joints
checkpoint-status |  |  | checkpoint | Engineer to issue certificate prior to concrete pour Have all items been signed off – Reinspect if required (Attach Sign Off)
checkpoint-status |  |  | checkpoint | Ensure safety rails around perimeter, stairs and penetrations
checkpoint-status |  |  | checkpoint | Confirm all mesh has been installed with minimum laps of 1 square plus 25mm or engineer’s requirements
checkpoint-status |  |  | checkpoint | Check if concrete has falls as per Architectural and Structural drawings
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
checkpoint-status |  |  | checkpoint | Confirm Slump Mix of concrete off structural drawings prior to ordering
text | 52c5200d-8fb8-52c8-b55e-e0d1dac4936a |  | textbox | Slump:
checkpoint-status |  |  | checkpoint | Check strength of concrete off structural drawings prior to ordering
text | 9beb135f-c9a4-5bd9-a2b4-8dca68804607 |  | textbox | Mpa
checkpoint-status |  |  | checkpoint | All forms and substrate clean and clear of debris
checkpoint-status |  |  | checkpoint | As builts of services to be marked up prior to concrete pour
checkpoint-status |  |  | checkpoint | Attach hydraulic ITP (cast in conduits and pipework)
checkpoint-status |  |  | checkpoint | Attach electrical ITP (cast in conduits - if applicable)
checkpoint-status |  |  | checkpoint | Attach mechanical ITP (cast in conduits)
checkpoint-status |  |  | checkpoint | Attach reinforcement placement checklist from steel fixing subcontractor
checkpoint-status |  |  | checkpoint | Attach structural engineer inspection prior to concrete pour (all items closed out)
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm supervision of pour by Services supervisor Sign off to be provided
checkpoint-status |  |  | checkpoint | Confirm falls to drainage points in slab
checkpoint-status |  |  | checkpoint | Cure concrete same day of concrete pour
checkpoint-status |  |  | checkpoint | Confirm all edge boards secure and square
checkpoint-status |  |  | checkpoint | Confirm concrete is vibrated as per specifications
checkpoint-status |  |  | checkpoint | Check if spoon drains are installed correctly
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Obtain all concrete tests to be carried out on all concrete pours
checkpoint-status |  |  | checkpoint | Confirm Sawn joints installed (SCJ) within saw cuts time limits
checkpoint-status |  |  | checkpoint | Obtain all concrete tests to be carried out on all concrete pours
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-004 (Rev 01) Slab on Ground
label | 7490facb-e624-588b-b52f-f4a89e8a5129 |  | note | Authorised By: FA
label | ff68fbf3-05e2-51ff-9f2b-7f4ea65a2eb1 |  | note | Issue Date: 51218
checklist-sectioned |  |  | checklist | Retaining Walls GPL-QSE-ITP-FIN-013 |  |  |  |  | Yes | Retaining Walls GPL-QSE-ITP-FIN-013 | 3ea87e29-cdf4-455e-bab1-3083b2eca067
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Inspected and accepted the work area and surfaces and structure ready to commence work
text | a3c8c080-36ec-5938-95cb-6669680ce469 |  | textbox | Architectural Drawing No & Revision
text | feac62bf-d0b9-5348-b5bb-94f257896858 |  | textbox | Structural Drawing No & Revision
checkpoint-status |  |  | checkpoint | Confirm set out of walls as per Architectural Drawings
checkpoint-status |  |  | checkpoint | Confirm that all penetrations as required for services are identified and marked (ie mechanical, electrical, fire, hydraulic, etc)
checkpoint-status |  |  | checkpoint | Obtain certificate of verification from supervising engineer Confirmed Site storage requirements for bricks/blocks, mortar and sundries
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm Shelf Angles are Installed as per installation certificate
checkpoint-status |  |  | checkpoint | All damp proof course built in
checkpoint-status |  |  | checkpoint | All flashings and wall ties built in
checkpoint-status |  |  | checkpoint | Confirm that ties are installed at correct centers (verify with engineer’s advice or installation guidelines)
checkpoint-status |  |  | checkpoint | All cavities clean and clear
checkpoint-status |  |  | checkpoint | Gaps closed below soffit overhead beams
checkpoint-status |  |  | checkpoint | Completed sills and header courses
checkpoint-status |  |  | checkpoint | Ensure weep holes are installed at correct centers and cleared before completing area
checkpoint-status |  |  | checkpoint | Final brick/block clean
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off - Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | Installation Certificate - Attach Installation Certificate
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
label | 6027ef52-0b9e-5b94-bd48-06ee4bda461e |  | note | Issue to Project Engineer within 24 hours
text | ac58b9ce-adce-508b-aac3-2e10b843144a |  | textbox | Outstanding Items/ Non Conformances to be issued:
checklist-sectioned |  |  | checklist | Tiling - External Areas - GPL-QSE-ITP-FIN-005 (Rev 01) |  |  |  |  | Yes | Tiling - External Areas - GPL-QSE-ITP-FIN-005 (Rev 01) | 4497291d-1a6e-45bd-8d90-6653ef6a2d56
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Confirm Series and Scheme of finish for unit
checkpoint-status |  |  | checkpoint | Confirm site samples match approved samples
checkpoint-status |  |  | checkpoint | Confirm that all floor wastes are plugged during tiling works
checkpoint-status |  |  | checkpoint | Confirm Acoustic mat or Asaphonic tile glue used and 4mm final bed depth – as per acoustic report
checkpoint-status |  |  | checkpoint | Stop wall and floor tiles 2-3mm short of edges and fill with resilient caulking compound
checkpoint-status |  |  | checkpoint | Confirm color of grout
checkpoint-status |  |  | checkpoint | HOLD POINT – Ensure waterproofing to balcony/terrace is sound and unblemished If reqd, conduct additional elcometer pinhole spark test to confirm waterproofing coverage before commencing with screed
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm sand/cement screed ratio is 1:3
checkpoint-status |  |  | checkpoint | Confirm installation of floor wastes is flush with or 1mm below floor tile level
checkpoint-status |  |  | checkpoint | Floor tiles laid to falls – minimum 1:100
checkpoint-status |  |  | checkpoint | Grouting checked for uniformity and quality
checkpoint-status |  |  | checkpoint | Ensure quality of tile installation is maintained, ie Alignment of joints, Minimisation of scratches & damage
checkpoint-status |  |  | checkpoint | Silicone jointing provided to all floor/wall tile junctions
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT – Ok to proceed painting
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-005 (Rev 01)
label | 7381e34c-0242-5e33-8fce-b2ce1cebf199 |  | note | Authorised By: FA
label | 6ecbeca9-fdad-573b-9ea7-c43ee123ef80 |  | note | Issue Date: 301118
checklist-sectioned |  |  | checklist | CFA Piling Operations - GPL-QSE-ITP-STRUC-008 (Rev 00) |  |  |  |  | Yes | CFA Piling Operations - GPL-QSE-ITP-STRUC-008 (Rev 00) | 4fc94954-408f-4a36-b3c9-2f4f543ee0a3
checkpoint-group |  |  | section | Prior to Piling Operations
checkpoint-status |  |  | checkpoint | Attach mark-up plan of CFA piles covered by this ITP (Refer to relevant drawings)
checkpoint-status |  |  | checkpoint | Attached/check relevant Dial-Before-You-Dig plans prior to piling if applicable
checkpoint-status |  |  | checkpoint | Obtain certification for the piling matt from the relevant geotechnical consultant prior to erection of the piling rig in the zone of works covered by this ITP
checkpoint-status |  |  | checkpoint | Ensure authority approvals as required are obtained prior to commencement/erection of piling rig (Council, SACL (to be called everyday), etc…)
checkpoint-status |  |  | checkpoint | Confirm RL’s to top of piles and/or pile caps
checkpoint-status |  |  | checkpoint | Confirm required reinforcement cover to pile cages in accordance with structural documentation
checkpoint-status |  |  | checkpoint | Confirm type of reinforcement required to tension piles prior to installation
checkpoint-status |  |  | checkpoint | Confirm position of pile, with the piling surveyor, is in accordance with the dimensions set-out on the relevant drawings (attached survey plan showing correct positions)
checkpoint-status |  |  | checkpoint | Confirm strength of concrete off structural drawings prior to ordering (If applicable)
checkpoint-status |  |  | checkpoint | Obtain classification of piling spoil and ensure correct disposal method is implemented (inc pH testing, etc…)
checkpoint-status |  |  | checkpoint | Confirm method of piling spoil removal is communicated and agreed with earthworks contractor
checkpoint-status |  |  | checkpoint | HOLDPOINT - OK to PILE
checkpoint-group |  |  | section | During Piling Operations
checkpoint-status |  |  | checkpoint | Confirm Concrete Tester onsite to take samples
checkpoint-status |  |  | checkpoint | Confirm correct segregation of piling spoil for disposal in accordance with waste providers guidelines (as required)
checkpoint-status |  |  | checkpoint | Foreman to ensure no movement in auger during drilling and report any variations to project engineer
checkpoint-status |  |  | checkpoint | Foreman to monitor Piles for excessive bleeding (>75mm)
checkpoint-status |  |  | checkpoint | Ensure starter bars are placed into wet concrete mix as documented on the approved structural and architectural concrete set-out plans
checkpoint-status |  |  | checkpoint | Ensure that adequate exclusion zones are set-up during piling operations as per SWMS
checkpoint-group |  |  | section | After Piling Operations
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces
boolean | 644d0a5b-7f92-5ac4-a8a4-6d7142965e57 |  | tickbox | 50mm +/- in correct plane
checkpoint-status |  |  | checkpoint | Obtain all concrete tests carried out on all concrete pours Attach Concrete Docket
checkpoint-status |  |  | checkpoint | Check concrete strength results comply with specification 14d ……… 28d ………
checkpoint-status |  |  | checkpoint | Obtain as-built survey of piling positons and top of piles/pile caps
checkpoint-status |  |  | checkpoint | Attach piling contractor ITP
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-008 Rev 00 CFA Piling Operations
label | a8470e24-331f-5b4f-b874-492594fd1215 |  | note | Authorised By: FA
label | 0d79478e-ccb6-5b42-a825-b873affdd85a |  | note | Issue date: 51218
checklist-sectioned |  |  | checklist | Plasterboard and Linings - GPL-QSE-ITP-FIN-003 (Rev 03) |  |  |  |  | Yes | Plasterboard and Linings - GPL-QSE-ITP-FIN-003 (Rev 03) | 52cd9e5e-bd67-42ab-935c-415acc5288e9
checkpoint-group |  |  | section | Survey/Wall Framing
checkpoint-status |  |  | checkpoint | Confirm set out of walls in correct locations & RL’s as required To tick
checkpoint-status |  |  | checkpoint | Confirm set out of Common/Party walls Hebel to correct side
checkpoint-status |  |  | checkpoint | Confirm set out of Wet Areas are square
checkpoint-status |  |  | checkpoint | Confirm wall type as per Architectural detail drawings
checkpoint-status |  |  | checkpoint | Ensure wall framing is straight, braced and rigid Noggins as required
checkpoint-status |  |  | checkpoint | Confirm studs not bridging against hydraulic pipes and mechanical units
checkpoint-status |  |  | checkpoint | Confirm that studs do not bridge to lift shaft walls and cavity is maintained
checkpoint-status |  |  | checkpoint | Confirm that joinery opening framing has been check measured for the required tolerance stipulated by the joinery contractor (eg max 5mm error) and check for wall verticality (check across the top, middle and bottom of the framing)
checkpoint-status |  |  | checkpoint | Confirm all noggins, trimming blocks, struts as required to have appropriate strength to support
boolean | 6af7dce5-962f-5851-883d-3ad85ab33bb5 |  | tickbox | Throughout Accessible Bathrooms
boolean | 33787852-30e4-5cf0-9e38-819de6eb03f4 |  | tickbox | Bathroom Accessories
boolean | ce7eb5a4-9874-52e0-bda1-8e6e54eabdbe |  | tickbox | Bathroom Vanities and Mirror Cabinets
boolean | 216bd84b-3c14-5b67-b20a-b8936238b4ba |  | tickbox | Service Boards (Per Commercial Tenancy)
boolean | f7782e5c-08f5-5f3d-ae40-9b5d3446a457 |  | tickbox | For kitchen joinery
checkpoint-group |  |  | section | Sheeting Walls
checkpoint-status |  |  | checkpoint | Confirm acoustic insulation installed as per Acoustic Specification
checkpoint-status |  |  | checkpoint | Confirm Thermal insulation installed as per Acoustic Specification (ensure insulation is complete slab to slab)
checkpoint-status |  |  | checkpoint | Confirm that there is a minimum of 60mm cavity between hebel panel and inside of stud If the cavity is < 60mm, ensure that the wall is double sheeted
checkpoint-status |  |  | checkpoint | Confirm door frames true, plumb and installed at correct orientation
checkpoint-status |  |  | checkpoint | Confirm Plasterboard lining to wet areas are sealed up to concrete soffit on both sides of wall where adjacent to a habitable rooms
checkpoint-status |  |  | checkpoint | Confirm all penetrations through wet area walls adjacent to habitable rooms are sealed and caulked
checkpoint-status |  |  | checkpoint | HOLD POINT – Confirm all services works completed
checkpoint-group |  |  | section | Sheeting Ceilings
checkpoint-status |  |  | checkpoint | Acoustic Engineer to inspect prior to sheeting PCA to inspect prior to sheeting (L1 minimum)
checkpoint-status |  |  | checkpoint | Confirm Ceiling insulation complete (where applicable)
checkpoint-status |  |  | checkpoint | Provision made in ceiling framing for access panels and air grilles where required
checkpoint-status |  |  | checkpoint | Confirm Ceiling framing is level and correct height
checkpoint-status |  |  | checkpoint | Confirm Ceiling framing Bulkheads are square and level
checkpoint-status |  |  | checkpoint | Confirm Access panels installed in correct locations for fire dampers and mechanical fans
checkpoint-status |  |  | checkpoint | Confirm Ceiling furring channels do not clash with other services (eg downlights, access panels, mechanical exhaust, sprinkler heads)
checkpoint-status |  |  | checkpoint | Ensure plasterboard sheets are AS compliant
checkpoint-status |  |  | checkpoint | Fire Rating Certifier has inspected the apartment prior to sheeting ceilings and issued apartment fire rating inspection report
checkpoint-status |  |  | checkpoint | Confirm plasterboard fixings are at the correct intervals
label | 5f9e19df-d696-5388-b3f9-001be3055b22 |  | note | For painted surfaces, screw fixing onto sheeted frames should be max 400mm spacing Refer to Manufacturer’s Installation guide
checkpoint-status |  |  | checkpoint | Confirm Villaboard fixings are of the correct intervals
label | 1da25b66-97ec-549c-85a4-9532e5480742 |  | note | For 6mm Villaboard: Tiled wall screw fixings must be max 200mm spacing, Max tile thickness must be 9mm for 600mm stud centres/ 13mm for 450mm stud centres Refer to Manufacturer’s Installation guide
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Painting
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-003 (Rev 03)
label | 0851c498-a343-5c70-a61b-19bab69daced |  | note | Authorised By: FA
label | 9e3c8262-b36f-50bd-b3f7-0fcc8b123f90 |  | note | Issue Date: 301118
checklist-sectioned |  |  | checklist | Pad Footings, Strip Footings, Lift Pits & Piles - GPL-QSE-ITP-STRUC-002 (Rev 03) |  |  |  |  | Yes | Pad Footings, Strip Footings, Lift Pits & Piles - GPL-QSE-ITP-STRUC-002 (Rev 03) | 553fdfe0-25f5-4744-9040-cfc4e5f25910
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Attach mark-up plan (Refer to Pad Register)
checkpoint-status |  |  | checkpoint | Confirm RL of sub-base
checkpoint-status |  |  | checkpoint | Confirm position of footing is in accordance with architectural setout design
checkpoint-status |  |  | checkpoint | Confirm starter bars to columns and walls installed in correct location
checkpoint-status |  |  | checkpoint | Check for reinforcement cover as per structural documents (especially at steps and ramps)
checkpoint-status |  |  | checkpoint | Obtain certificate from Structural Engineer and Geotechnical Engineer prior to concrete pour Attach certificates
checkpoint-status |  |  | checkpoint | Confirm strength of concrete off structural drwaings prior to ordering
checkpoint-status |  |  | checkpoint | Confirm waterproofing details installed as per manufacturer's specifications Attach waterproofer's completed ITP (Applicable to Lift Pit Only)
checkpoint-status |  |  | checkpoint | Attach piling contractor ITP
checkpoint-status |  |  | checkpoint | Attach photos prior to concrete pour
checkpoint-status |  |  | checkpoint | HOLDPOINT - OK to Pour
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Concrete Tester onsite to take samples
checkpoint-status |  |  | checkpoint | Ensure during pour that no water to be added to the concrete mix whether in the truck or pump (If there is evidence of this happening the concrete in the stated shall be rejected and replaced at the subcontractor's expense, including the delay time of the concrete pour)
checkpoint-status |  |  | checkpoint | Confirm supervision of pour by waterproofing contractor Attach sign off Applicable to lift pit only
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces
boolean | 16c742ee-086e-5f4c-86ee-5ef668b605f1 |  | tickbox | 50mm +/- in correct plane
boolean | 89f79e52-a0f9-5491-875c-b7e4ed07f6ee |  | tickbox | 50mm +/- from 30m straight edges
checkpoint-status |  |  | checkpoint | Obtain all concrete tests to be carried out on all concrete pours Attach Concrete Docket
checkpoint-status |  |  | checkpoint | Check concrete strength results complete with specification 14d… 28d…
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-002 (Rev 03) Pad Footings, Strip Footings, Lift Pits & Piles
label | 97982f64-54c9-5cf0-a71e-6b89deb6a0af |  | note | Authorised By: FA
label | a02bf288-2ab0-5c5d-9e5b-2b4b4ad8bdfe |  | note | Issue Date: 51218
checklist-sectioned |  |  | checklist | Suspended Slab - GPL-QSE-ITP-STRUC-005 (Rev 03) |  |  |  |  | Yes | Suspended Slab - GPL-QSE-ITP-STRUC-005 (Rev 03) | 64422f5a-39d2-4854-8a8a-cb478597cdec
checkpoint-group |  |  | section | Prior to Deck Handover
checkpoint-status |  |  | checkpoint | Confirm deck is safe, handrails installed and edge protection is provided to full perimeter of deck
checkpoint-status |  |  | checkpoint | Confirm means of access to deck, 2 x stretcher stair access
checkpoint-status |  |  | checkpoint | Confirm Formworkers Deck Handover Certificate and ITP is received and sighted
holdpoint |  |  | signoff | Attach Deck Handover Certificate
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm As-Built Survey of deck is complete
holdpoint |  |  | signoff | HOLD POINT - Attach As-Built Survey of Deck
checkpoint-status |  |  | checkpoint | Confirm Formworker has received As-Built Survey of deck, and has rectified errors prior to any trades commencing on deck
checkpoint-status |  |  | checkpoint | Confirm all beams and decks constructed as per Structural Concrete Profiles
checkpoint-status |  |  | checkpoint | Install slip joints to all load bearing walls and corbels where required
checkpoint-status |  |  | checkpoint | Clean off decks and beams prior to pour, and ensure all exposed off-form soffits are free of any dust, stains and rust marks Hose down if necessary
checkpoint-status |  |  | checkpoint | Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary Cross-check the following drawings:
boolean | 1e5deeb3-f3e3-5f8c-9e6d-fdd952ae3988 |  | tickbox | Hydraulic Drawings
boolean | 18c58eae-f045-58bf-9a32-052af4bfa7a8 |  | tickbox | Architectural Concrete Outlines
boolean | 91b5b502-66fb-599a-b2cb-43e8adc449c2 |  | tickbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Check top RLs for all reinforcement, ensuring adequate concrete cover Confirm with Concreter
checkpoint-status |  |  | checkpoint | Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits
checkpoint-status |  |  | checkpoint | Attach Formwork ITP
holdpoint |  |  | signoff | HOLD POINT - Attach Formwork ITP
checkpoint-status |  |  | checkpoint | Attach Formwork Engineer's sign off certificate Confirm that certificate references props, braces and compliance with design & AS3610
holdpoint |  |  | signoff | HOLD POINT - Attach Formwork Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach Hydraulic ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Electricians ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Fire Services ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Mechanical ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Precast ITP (for cast-in elements), including relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Reo Fixing ITP
checkpoint-status |  |  | checkpoint | Attach Principal Structural Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
holdpoint |  |  | signoff | HOLD POINT - Attach Principal Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach Post Tensioning Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
holdpoint |  |  | signoff | HOLD POINT - Attach Post Tensioning Engineer's Certificate
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
text | 4b8410fc-b5c2-5812-a4a0-62fd623674a5 |  | textbox | Total m3 (as measured by Site Engineer):
text | 86e0a55c-66a7-5568-9e4b-e3d26a47ae34 |  | textbox | Total m3 (as measured by Foreman):
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg size of concrete prior to ordering
text | a25ee0bd-b3bc-5239-bedd-be11ce1830df |  | textbox | MPa:
text | de19859f-2ea6-5456-8216-903de9147f0f |  | textbox | Slump:
text | 84b34e9d-6367-5042-96b3-fd60520b5406 |  | textbox | Agg:
checkpoint-group |  |  | section | During to Concrete Pour
checkpoint-status |  |  | checkpoint | Ensure concrete truck dockets have correct concrete strength, and attach delivery docket from each batch
checkpoint-status |  |  | checkpoint | Confirm concrete tester on site during concrete pour, and the following tests have been requested
boolean | 06849c8f-0093-5265-8631-93c0f822e65c |  | tickbox | 1 Day
boolean | 80640a09-0588-5446-b62a-ff0b0666cd43 |  | tickbox | 4 Day
boolean | e63c74f9-522c-5093-969a-8db4b5f49a96 |  | tickbox | 7 Day
boolean | eeea32cd-b8a5-54b5-a316-91b2a09db7da |  | tickbox | 28 Day
checkpoint-status |  |  | checkpoint | Ensure that no water is added to the concrete mix, whether in the truck or pump
label | fc82c1ab-d490-5aae-add6-e710f81032ea |  | note | (If there is evidence of this happening, concrete is to be rejected and replaced at the subcontractor’s expense, including the delay time of the concrete pour)
checkpoint-status |  |  | checkpoint | Confirm concrete has falls to drainage points in slab
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | 9dcf70d6-a0c5-5971-bc1d-7b2630114947 |  | tickbox | Formworker
boolean | 3cc4f720-7a3e-52fd-8c2e-014c085aa96c |  | tickbox | Electrician
boolean | d667d2be-98f9-571c-b6e5-6ba696639de0 |  | tickbox | Plumber
boolean | e3c79006-3f52-5189-b030-aa2a554b8c44 |  | tickbox | Post Tensioner
boolean | f582ed53-e8a1-503f-91e9-e76d82da5d55 |  | tickbox | Precast Installer
checkpoint-status |  |  | checkpoint | Confirm Formworker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry
checkpoint-status |  |  | checkpoint | Confirm that all protection to precast panels is maintained at all times during concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
holdpoint |  |  | signoff | HOLD POINT - Attach Survey Record
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
boolean | 3d49af94-a717-5e58-88ee-44a6a22878bf |  | tickbox | 6mm +/- from design RL
boolean | da5c9970-b501-5d01-a615-5c7da25f0ee3 |  | tickbox | 6mm +/- from 30m straight edges
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements, generally 36hrs after the pour
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | 6114ade2-c718-5367-9464-b33684655222 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | 7db9fbbd-1f6e-5c65-821d-4541d24b8736 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
holdpoint |  |  | signoff | HOLD POINT - Attach Stressing Records
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | 5fa043ef-af83-51db-bb75-3fd0eaf2935f |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | 28e4f050-53df-57cf-95df-bf2ff7c451d2 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-005 (Rev 03) Suspended Slab
label | df4f2b38-80ca-5c81-806e-cf09b0e7049a |  | note | Authorised By: FA
label | c6286ed5-6901-5dbd-a0f2-3a120ad91e12 |  | note | Issue Date: 51218
checklist-flat |  |  | checklist | Timber Floor - GPL-QSE-ITP-FIN-018(Rev 00) |  |  |  |  | Yes | Timber Floor - GPL-QSE-ITP-FIN-018(Rev 00) | 6d380359-314c-4af2-8595-3d92498a8ef1
checkpoint-status |  |  | checkpoint | Confirm the folloiwng has been installed
boolean | 880bea9f-b3cb-5676-9852-2a71715bede0 |  | tickbox | Timber Floor
boolean | ed5899a0-5fb8-5ba7-95d5-61db752a0144 |  | tickbox | Stone
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-018(Rev 00)
label | b12c166c-3786-51a8-9053-240e65b33ae7 |  | note | Authorised By: FA
label | 2b109b94-af85-54f7-b813-b39d17e508e8 |  | note | Issue Date: 301118
checklist-sectioned |  |  | checklist | Fire Services Rough In - GPL-QSE-ITP-SERV-003 (Rev 01) |  |  |  |  | Yes | Fire Services Rough In - GPL-QSE-ITP-SERV-003 (Rev 01) | 70f8b39c-3e0d-48ac-ad4c-cc62ae48705d
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Confirm any pipework and cabling penetrating partition walls are sealed through penetration with Intumescent fire mastic up to 20mm
checkpoint-status |  |  | checkpoint | Confirm any cracks or chips to hebel have been patched and repaired in accordance with manufacturer’s instructions
checkpoint-status |  |  | checkpoint | Confirm sprinkler pipework installed as per drawings
checkpoint-status |  |  | checkpoint | Confirm if any drenchers required have been installed
checkpoint-status |  |  | checkpoint | Confirm apartment and balcony sprinkler head brackets are installed to ceiling grids
checkpoint-status |  |  | checkpoint | Confirm pipework pressure test (Attach DA Design sign off)
checkpoint-status |  |  | checkpoint | Confirm sprinklers have been installed as per architectural RCP layout
checkpoint-status |  |  | checkpoint | Confirm red cabling installed for fire electrical speakers and detectors
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Plasterboard Sheeting
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-SERV-003 (Rev 01)
label | 5e7cd29a-ec72-5008-9055-d1ec0206f664 |  | note | Authorised By: FA
label | 6e5c54c8-0d9e-513b-84b9-7e47a60cce4a |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Masonry - GPL-QSE-ITP-FIN-013 (Rev01) |  |  |  |  | Yes | Masonry - GPL-QSE-ITP-FIN-013 (Rev01) | 7a94478d-f8cd-4188-8eaf-0f7628440cc4
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Inspected and accepted the work area and surfaces and structure ready to commence work
checkpoint-status |  |  | checkpoint | Confirm set out of walls as per Architectural Drawings
label | 23c17c49-3dc1-5344-8b63-709e9fd189c5 |  | note | Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Confirm that all penetrations as required for services are identified and marked (ie mechanical, electrical, fire, hydraulic, etc)
checkpoint-status |  |  | checkpoint | Obtain certificate of verification from supervising engineer Confirmed Site storage requirements for bricks/blocks, mortar and sundries
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm Shelf Angles are Installed as per installation certificate
checkpoint-status |  |  | checkpoint | All damp proof course built in
checkpoint-status |  |  | checkpoint | All flashings and wall ties built in
checkpoint-status |  |  | checkpoint | Confirm that ties are installed at correct centers (verify with engineer’s advice or installation guidelines)
checkpoint-status |  |  | checkpoint | All cavities clean and clear
checkpoint-status |  |  | checkpoint | Gaps closed below soffit overhead beams
checkpoint-status |  |  | checkpoint | Completed sills and header courses
checkpoint-status |  |  | checkpoint | Ensure weepholes are installed at correct centers and cleared before completing area
checkpoint-status |  |  | checkpoint | Final brick/block clean
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Installation Certificate
label | 1828a5f7-1bd6-55df-b5a5-275b944c885c |  | note | Attach Installation Certificate
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-013 (Rev01)
label | 0ac2d16e-4048-52c3-acc1-74a8de837b2a |  | note | Authorised By: FA
label | c904d4a1-44e6-5ef1-b71d-99738048aeda |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Sandstone Installation |  |  |  |  | Yes | Sandstone Installation | 81d4fafe-3079-4932-a213-542478c65ed7
checkpoint-group |  |  | section | Prior to work
checkpoint-status |  |  | checkpoint | Confirm structure and openings are as per Architectural
checkpoint-status |  |  | checkpoint | Confirm all aluminum reveals are installed square, to correct size and correct protrusion past substrate
checkpoint-status |  |  | checkpoint | Confirm all receals are free of unfixable in-situ defects
checkpoint-status |  |  | checkpoint | Confirm all waterproofing has been completed (including flashings to reveals)
checkpoint-status |  |  | checkpoint | Confirm subcontractor working to approved shop drawings
checkpoint-status |  |  | checkpoint | Confirm material arrived at site undamaged
checkpoint-status |  |  | checkpoint | Spot check corner sandstone blocks have specified mitre as per drawings
checkpoint-status |  |  | checkpoint | Spot check selected blocks are specified size
checkpoint-status |  |  | checkpoint | Spot checks of gouges and chips
holdpoint |  |  | signoff | Holdpoint- Architect hold point #1
checkpoint-status |  |  | checkpoint | Confirm any deviations from IFC shop drawings acceptable
checkpoint-status |  |  | checkpoint | Establish standards and expectations through visual inspection of key control visual inspection of key control items as outlined in the photo control booklet: -Colour range acceptable -Quality expectations -Acceptable defects range -Setout methodology
checkpoint-group |  |  | section | During to work
checkpoint-status |  |  | checkpoint | Confirm cavity setout is 40mm
checkpoint-status |  |  | checkpoint | Confirm pin fixings have been installed to specified spacing
checkpoint-status |  |  | checkpoint | Confirm pin fixings have been inspected by subcontractor’s engineer and signed off
checkpoint-status |  |  | checkpoint | Confirm pin fixing glue does not bridge to face of stone
checkpoint-status |  |  | checkpoint | Confirm stone has achieved minimum coursing overlap
checkpoint-status |  |  | checkpoint | All cavities clean and clear
holdpoint |  |  | signoff | Architect hold point #2
checkpoint-status |  |  | checkpoint | Identify all defects outside the limits as illustrated by the Photo Control Booklet
checkpoint-status |  |  | checkpoint | Visual inspection of detailing acceptable
checkpoint-status |  |  | checkpoint | Identify defects acceptable to remedial tolerances
checkpoint-status |  |  | checkpoint | Identify non-acceptable defects for replacement
checkpoint-group |  |  | section | After works
checkpoint-status |  |  | checkpoint | Confirm joint lines between stone is horizontal and consistent
checkpoint-status |  |  | checkpoint | Confirm installed stone is not damaged
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | Confirm Sandstone protection is installed to edges
holdpoint |  |  | signoff | Architect hold point #3
checkpoint-status |  |  | checkpoint | Final inspection to confirm defects rectified
checkpoint-status |  |  | checkpoint | Final inspection to confirm replacement panels adequate
checkpoint-status |  |  | checkpoint | Identify any damage or defects to adjacent trades
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checklist-sectioned |  |  | checklist | Windows and Glazing - GPL-QSE-ITP-FAC-001 (Rev 00-Hurstville) |  |  |  |  | Yes | Windows and Glazing - GPL-QSE-ITP-FAC-001 (Rev 00-Hurstville) | 86eaaf51-8d6b-4a49-947e-c783992d771b
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Inspected and accepted the work area and surfaces ready to commence work
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Confirmed Site storage requirements, packaging and preservation
checkpoint-status |  |  | checkpoint | All site measures for opening sizes complete prior to manufacture
label | 981f326b-244d-5639-ae4b-bf1c413ebc48 |  | note | Refer Architectural drawings
checkpoint-status |  |  | checkpoint | Colour samples issued for approval and signed off
label | 7514653f-087c-54c5-89db-2eca0a4a50bb |  | note | Refer sample sign off
checkpoint-status |  |  | checkpoint | All windows and doors delivered to site to be correct colour, grade and thickness
checkpoint-status |  |  | checkpoint | Compliance of glass thermal requirements confirmed and issued
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Waterproof membrane laid and dry prior to install subsill
checkpoint-status |  |  | checkpoint | All windows and doors fixed plumb, level, and heads in alignment
checkpoint-status |  |  | checkpoint | Confirm RL of windoews cross-checked against 1m mark
checkpoint-status |  |  | checkpoint | Confirm alignment of windows with levels below, and horizontally with adjacent windows
checkpoint-status |  |  | checkpoint | All sill flashings correctly maintained
checkpoint-status |  |  | checkpoint | Insect screens installed as required
checkpoint-status |  |  | checkpoint | All window and door hardware and locks installed and keyed alike
checkpoint-status |  |  | checkpoint | All glass and sliding tracks clean and clear
checkpoint-status |  |  | checkpoint | Ensure Fixings for curtain wall slab brackets are as per Shop Drawings (M12 x 60mm Long S/S bolt & nut with spring washer)
checkpoint-status |  |  | checkpoint | Ensure 055mm thick galvanised sheet continuous smoke seal installed between slab edge and curtain wall
checkpoint-status |  |  | checkpoint | Ensure sealant installed to curtain wall vertical and horizontal junctions as per approved product
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Review windows to ensure no visible damage to glass or aluminium components
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FAC-001 (Rev 00)
label | b9dc03d7-85ec-5917-b487-f5d7690e0820 |  | note | Authorised By: FA
label | eef0fb08-a783-5d7d-a921-f63ecfbbb7fc |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Defects - GPL- QSE-ITP-FIN-015(Rev 00) |  |  |  |  | Yes | Defects - GPL- QSE-ITP-FIN-015(Rev 00) | 87202008-68cc-4994-81e1-dd266a4d3d10
checkpoint-group |  |  | section | Kitchens
checkpoint-status |  |  | checkpoint | Nib wall straightness checked
checkpoint-status |  |  | checkpoint | Kitchen poly doors / Drawer faces installed
checkpoint-status |  |  | checkpoint | Open every door / drawer & check for joinery touch ups
checkpoint-status |  |  | checkpoint | All shelves installed
checkpoint-status |  |  | checkpoint | Check sink & cooktop for scratches
checkpoint-status |  |  | checkpoint | Install mech grilles
checkpoint-status |  |  | checkpoint | Electrical fit off complete, check all GPOs
checkpoint-status |  |  | checkpoint | Check rangehood connects to flex
checkpoint-status |  |  | checkpoint | Sink trapped
checkpoint-status |  |  | checkpoint | Splashback GPO installed
checkpoint-status |  |  | checkpoint | Check gas bayonet not interferring with drawer
checkpoint-status |  |  | checkpoint | Install kick face
checkpoint-status |  |  | checkpoint | Dishwasher / Oven GPO fitted off
checkpoint-group |  |  | section | Bathroom
checkpoint-status |  |  | checkpoint | Tiling complete, check for lipping & cracks
checkpoint-status |  |  | checkpoint | Grout completed, check for defects
checkpoint-status |  |  | checkpoint | Floor waste clean?
checkpoint-status |  |  | checkpoint | Ceiling final painted, check edges near silicon
checkpoint-status |  |  | checkpoint | Electrical fit off complete, check GPO in MSC
checkpoint-status |  |  | checkpoint | Hydraulic PC items installed
checkpoint-status |  |  | checkpoint | Flush buttons in stone check
checkpoint-status |  |  | checkpoint | Is tile angle clean?
checkpoint-status |  |  | checkpoint | Are screws missing on the door?
checkpoint-status |  |  | checkpoint | Top and base of door painted sealed
checkpoint-status |  |  | checkpoint | Door handle & door stop install, check for paint
checkpoint-status |  |  | checkpoint | Run water in shower, no leaks?
checkpoint-status |  |  | checkpoint | Silicone complete
checkpoint-group |  |  | section | General
checkpoint-status |  |  | checkpoint | Final Paint ceilings, check for marks at lights/sprinkler/edges
checkpoint-status |  |  | checkpoint | All floor finishes installed, check dipping against skirting
checkpoint-status |  |  | checkpoint | Check all windows open & close, and check for scratches
checkpoint-status |  |  | checkpoint | Entry door installed, check smoke seal & door closer & stop
checkpoint-status |  |  | checkpoint | Door stop installed for Entry door
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | QSE-ITP-FIN-015(Rev 00)
label | 0a392a76-4e22-576b-805f-9b2965db6349 |  | note | Authorised By: FA
label | d128c4dd-d669-5c0b-964a-4797112501a3 |  | note | Issue Date: 301118
checklist-sectioned |  |  | checklist | GPL-QSE-ITP-STRUC-016(Rev01) Double Wall Installation (Precast) V280420 |  |  |  |  | Yes | GPL-QSE-ITP-STRUC-016(Rev01) Double Wall Installation (Precast) V280420 | 8fe0a72b-914e-4206-983a-6352dd2c296a
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Confirm which panels & bracing details are being installed (write down panel numbers) and attach panel drawings
label | 665fb2b5-c83f-53bd-9e53-2cc22fc024c3 |  | note | Attach engineer drawings & bracing for precast panel
checkpoint-status |  |  | checkpoint | Confirm that panel, lifting & bracing drawings have been supplied, understood & that a general lift plan using GPL-QSE-FORM-031 has been completed
checkpoint-status |  |  | checkpoint | Attach manufacturer certificate for panels
boolean | e34fb14c-3b35-50c2-9e62-073bcf65f790 |  | tickbox | Attach manufacturer certificate
checkpoint-status |  |  | checkpoint | Confirm with supplier that all panels are cured & have achieved required strength of 25mPA
label | d3d0edb5-6159-52a7-b3e1-fbd717cca345 |  | note | Design Engineers's certificate of compliance outlining mPA & concrete test results of panel
checkpoint-status |  |  | checkpoint | Confirm that minimum 20mPA concrete slab strength has been reached as required by Structural Engineer for temporary bracing install
boolean | 07a6afd8-9238-5502-8e07-ebf285f80e08 |  | tickbox | Attach confirmation from Structural Engineer
checkpoint-status |  |  | checkpoint | Confirm that lifting requirements are understood for all panels (straight lift or tilt up)
checkpoint-status |  |  | checkpoint | Confirm that all lifting points reinforcement is fully embedded within the concrete shells If reo is exposed, take photos & send to GN site engineer
checkpoint-status |  |  | checkpoint | Confirm all precast panels have been inspected for damage prior to lifting off truck
checkpoint-status |  |  | checkpoint | Confirm set-out is provided for panels, prior to lifting any panels
checkpoint-status |  |  | checkpoint | Check existing dowel & starter bars are correct & verified against structural drawings
checkpoint-status |  |  | checkpoint | Confirm review of panel shop drawings for rigging requirements & communicated to crane crew
checkpoint-status |  |  | checkpoint | Confirm that the weight tag on the panel is consistent with the shop drawing weights
checkpoint-status |  |  | checkpoint | Confirm that traffic & pedestrian control is in place
checkpoint-status |  |  | checkpoint | Confirm that exclusion zones are set up prior to lifting
checkpoint-status |  |  | checkpoint | Confirm that weather & wind conditions are suitable to complete lifting
checkpoint-status |  |  | checkpoint | Confirm that precast contractor’s site manager has reviewed all panels on site prior to lifting
checkpoint-group |  |  | section | After Double Wall Installation
checkpoint-status |  |  | checkpoint | Confirm panels are installed in correct & final position Check alignment with adjacent elements
checkpoint-status |  |  | checkpoint | Confirm all panels have a minimum of 2 x props/braces per panel & comply with approved drawings
checkpoint-status |  |  | checkpoint | HOLD POINT - Attach double wall contractor’s installation ITP confirming bracing & lace reinforcement installation
label | 02cd62d7-4a22-5ca9-9054-953eeda74611 |  | note | Attach Precast installation certificate
holdpoint |  |  | signoff | Click to attach 'Precast installation certificate'
checkpoint-status |  |  | checkpoint | Confirm all gaps are even, sealed & closed off prior to pour, particularly sealing precast elements to formwork deck to avoid slurry runs
checkpoint-status |  |  | checkpoint | Confirm panels checked for cracks & chips following installation All such damage is to be recorded & advised to the precast installer immediately
checkpoint-status |  |  | checkpoint | Confirm that starter bars are installed by reinforcement contractor to top of wall
checkpoint-status |  |  | checkpoint | If panel has not been installed as per bracing layout Obtain & attach precast Engineer certificate for as built locations of props
label | 4ec23cad-02b3-5eee-a5c1-b35c078ea5a9 |  | note | Attach Precast Engineer signoff
checkpoint-status |  |  | checkpoint | HOLD POINT - Attach reinforcement contractor’s ITP
label | c98b1ddc-b9ac-54e9-8a87-ceac155e4391 |  | note | Attach Steel Fixing signoff
holdpoint |  |  | signoff | Click to attach 'Steel fixing signoff'
checkpoint-status |  |  | checkpoint | HOLD POINT – Attach project structural engineer’s signoff & close of all connections & reinforcement installed
label | f7d96d5a-36f0-5cb6-ae07-e4cb744921a1 |  | note | Attach structural engineer signoff
holdpoint |  |  | signoff | Click to attach 'Structural Engineer signoff'
checkpoint-group |  |  | section | During Double Wall Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm that pour rates have been provided by the precast supplier & has been issued to the concrete place contractor
checkpoint-status |  |  | checkpoint | Confirm that mix design has been ordered in accordance to approved structural mix
label | 15925cf4-7906-564d-a879-8bcde964f360 |  | note | Concrete Strength – 50MPa, 20mm aggregate, min 400kg/m3 180mm slump
checkpoint-status |  |  | checkpoint | Confirm that concrete tester on site during concrete pours & the following tests have been requested; 14 & 28 days
checkpoint-status |  |  | checkpoint | Ensure that no water is added to the concrete mix, whether in the truck or pump
checkpoint-group |  |  | section | After Double Wall Concrete Pour
checkpoint-status |  |  | checkpoint | Obtain test result at 14 day & attach results
label | 128b4c6b-163b-5598-9100-4f75d2f5ef7f |  | note | Attach concrete test results from concrete supplier
checkpoint-status |  |  | checkpoint | Obtain test result at 28 day & attach results Confirm that minimum concrete strength has been reached – 50MPa
label | 4194c686-bf7e-5034-b34d-b94fd4e47562 |  | note | Attach concrete test results from concrete supplier
checkpoint-status |  |  | checkpoint | Obtain double wall panel test results & confirm minimum concrete strength has been reached – 50MPa
label | 6088f979-dc93-5af4-88ed-5bae7fae38ea |  | note | Attach concrete test results from precast contractor
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | click to add 'Signature'
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-016(Rev 01) - Double Wall Installation (Precast)
label | 911e2bc2-fd11-559a-b13e-d915aa9c3d10 |  | note | Authorised By: CS
label | c2d21a1f-b90d-5e4e-a7c4-d7368ffb3e0a |  | note | Issue date: 230420
checklist-sectioned |  |  | checklist | Excavation & Shoring - GPL-QSE-ITP-STRUC-001 (Rev 02) |  |  |  |  | Yes | Excavation & Shoring - GPL-QSE-ITP-STRUC-001 (Rev 02) | 975df113-aee0-4b8a-b994-8758b832e1db
checkpoint-group |  |  | section | Shoring - Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Locate all existing services
checkpoint-status |  |  | checkpoint | Confirm set out and piling/spring remains within the boundary
checkpoint-status |  |  | checkpoint | Confirm vibration requirements
checkpoint-status |  |  | checkpoint | Confirm boundary set back to shoring wall
checkpoint-status |  |  | checkpoint | Confirm RL levels to top of shoring wall
checkpoint-group |  |  | section | Shoring - During Works
checkpoint-status |  |  | checkpoint | Confirm de-stressing procedure for anchors with engineer
checkpoint-status |  |  | checkpoint | Confirm level of excavation permissible with shoring wall
checkpoint-group |  |  | section | Excavation - Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Confirm dial before you dig documents are onsite
checkpoint-status |  |  | checkpoint | Confirm correct disposal of classified material
checkpoint-status |  |  | checkpoint | Obtain geotech report, including load bearing capacity for scaffolder
checkpoint-group |  |  | section | Excavation - During Works
checkpoint-status |  |  | checkpoint | Collection of tip dockets if required
checkpoint-status |  |  | checkpoint | Confirm set out of boundary's marked out
checkpoint-status |  |  | checkpoint | Confirm actual ERL is within design tolerance (nominal 20mm)
checkpoint-status |  |  | checkpoint | Confirm set out of footings and pads
checkpoint-status |  |  | checkpoint | Confirm set out of in ground drainage
checkpoint-status |  |  | checkpoint | Excavation of footings not to exceed size as detailed on structural drawings
checkpoint-status |  |  | checkpoint | Certifier to inspect foundation in accordance with DA Conditions
checkpoint-status |  |  | checkpoint | Geotech inspection of footings/lift pads
checkpoint-status |  |  | checkpoint | Confirm if and hand digging excavation close to underground services
checkpoint-status |  |  | checkpoint | Confirm top of concrete footings is below surrounding finishes
checkpoint-status |  |  | checkpoint | Confirm subbase is compliant with engineers requirements
text | e1327b0a-401e-519b-a3ac-fb0a9ca30de5 |  | textbox | Minimum thickening:
checkpoint-status |  |  | checkpoint | Confirm as civil engineer inspection
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach Subcontractor ITP
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-001 Excavation & Shoring Rev 02
label | aeffce65-971b-530d-ab1f-d6d7d755a94b |  | note | Authorised By: FA
label | d4869d9a-bffb-5320-a55a-24a28a33fe9a |  | note | Issue date: 51218
checklist-sectioned |  |  | checklist | Waterproofing - External Torch on Membrane - GPL-QSE-ITP-FIN-009 (Rev 01) |  |  |  |  | Yes | Waterproofing - External Torch on Membrane - GPL-QSE-ITP-FIN-009 (Rev 01) | a1485dd0-313b-4881-b0e8-caaf373b42fa
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Floor wastes are free of waste material and are in correct location & signed off by plumber
checkpoint-status |  |  | checkpoint | Confirm concrete floor slab 100% clean, free of water, dirt dust and other condiments
checkpoint-status |  |  | checkpoint | Confirm 50 x 50 sand cement fillet installed to all internal corners
checkpoint-status |  |  | checkpoint | Confirm all outlets are cut flush
checkpoint-status |  |  | checkpoint | Apply primer to all surfaces to receive membrane
checkpoint-status |  |  | checkpoint | HOLD POINT – Base membrane 3mm PARCHEM Index ‘Fidia’
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Apply reinforcing layer to movement joints Torch bond 200mm strip to one side only Other side to remain unbonded
checkpoint-status |  |  | checkpoint | Side laps to be 100mm
checkpoint-status |  |  | checkpoint | End laps to be 150mm
checkpoint-status |  |  | checkpoint | Base membrane inspected for imperfections
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Base membrane inspected for imperfections
checkpoint-status |  |  | checkpoint | All installation as per approved details
checkpoint-status |  |  | checkpoint | Confirm all floor wastes have waste flanges installed
checkpoint-status |  |  | checkpoint | Ensure membrane is terminated a minimum of 150mm up from the finished floor
checkpoint-status |  |  | checkpoint | Confirm reglet installed as per details with approved sealant, to block walls installed prior to membrane commencement
checkpoint-status |  |  | checkpoint | Confirm membrane carried underneath block walls to planters
checkpoint-status |  |  | checkpoint | Confirm all penetrations through planter box walls are sealed
checkpoint-status |  |  | checkpoint | Confirm protection board installed prior to finishes installation
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed with Finishes
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-009 (Rev 01)
label | f5b72e3f-d497-560a-938a-a26acb948d23 |  | note | Authorised By: FA
label | c25290fc-2acf-5197-b256-8c59a1ef025d |  | note | Issue Date: 301118
checklist-sectioned |  |  | checklist | Hydraulic Rough In - GPL-QSE-ITP-SERV-004 (Rev 01) |  |  |  |  | Yes | Hydraulic Rough In - GPL-QSE-ITP-SERV-004 (Rev 01) | a54e7adf-a0bd-4163-b7eb-7c5d986b280a
checkpoint-group |  |  | section | Fire Rating
checkpoint-status |  |  | checkpoint | Intumescent fire collars inspected and installed as per manufacturers details – centered within hebel
checkpoint-status |  |  | checkpoint | Fire collars sealed around fire rated wall penetrations with Intumescent fire mastic of up to 20mm thick
checkpoint-status |  |  | checkpoint | Copper pipe risers to be caulked with Intumescent fire mastic of up to 20mm thick at all floor penetrations
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Acoustic Requirements
checkpoint-group |  |  | section | Acoustic Requirement
checkpoint-status |  |  | checkpoint | Water pipes running through studs to be siliconed to prevent water hammer effects
checkpoint-status |  |  | checkpoint | All waste pipes kept a minimum of 15mm clear of any part of structure
checkpoint-status |  |  | checkpoint | Confirm all pipes not damaged or leaking prior to lagging and joints are glued (blue and red)
checkpoint-status |  |  | checkpoint | All PVC pipe work acoustically lagged and wrapped in accordance with Acoustic Logic Specification (Risers and underslung – 50mm overlap at joints)
checkpoint-status |  |  | checkpoint | Confirm all water pipe hanger shall have rubber mounts
checkpoint-status |  |  | checkpoint | Confirm PVC pipes are not bridging against metal studs (Minimum 5mm clearance is required after lagging)
checkpoint-status |  |  | checkpoint | Confirm no pipework is fixed to the hebel where there is a cavity – no pipework to bridge cavity
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Hydraulic Services
checkpoint-group |  |  | section | Hydraulic Services - Prior to Sheeting Walls
checkpoint-status |  |  | checkpoint | Confirm hot water supply is on the left and cold water supply on the right hand side to
boolean | ac3accf3-9013-5068-bbf0-bf6bebf6f2c3 |  | tickbox | Kitchen
boolean | 587bfbf6-15f7-5306-a59d-31160c8d7b2b |  | tickbox | Bathroom
checkpoint-status |  |  | checkpoint | Confirm kitchen rough in is as per kitchen shop drawing
checkpoint-status |  |  | checkpoint | Confirm location of gas meter as per Kitchen Shop Drawing
text | 62e08f8e-5e2c-5985-8a70-8ab3fec8dc3b |  | textbox | Kitchen Type
checkpoint-status |  |  | checkpoint | Confirm A/C tundish location has been supplied and trap prefilled
checkpoint-status |  |  | checkpoint | Confirm the following heights from architectural detail drawings
text | d6e08488-2c0b-5158-bb42-088cb82f76a1 |  | textbox | Shower head
text | 08577864-d72c-5366-a7b3-02a8f97083c8 |  | textbox | Shower mixer
text | d36c2e2a-1d79-5876-8750-8d29fd20c090 |  | textbox | Bathroom basin
checkpoint-status |  |  | checkpoint | Confirm in-built cistern has been installed
checkpoint-status |  |  | checkpoint | Confirm following test been undertaken (attached sign off)
boolean | 2233355a-f322-5c03-be70-51f8c3a2f7cc |  | tickbox | Pressure test for water and gas
boolean | 7cba4be5-6dbd-5775-a788-1fc33c65767e |  | tickbox | Drainage pipework
checkpoint-status |  |  | checkpoint | Confirm supply pipes have been charged
checkpoint-status |  |  | checkpoint | Confirm rough-in of wet area fixtures as per layout
checkpoint-status |  |  | checkpoint | Confirm PAPA valve is located within accessibility from access panel
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Plasterboard Sheeting
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-SERV-004 (Rev 01)
label | f3bf6651-6e25-5806-8788-cb705e52ec9d |  | note | Authorised By: FA
label | 4d5da74c-f1fe-549a-b3c2-d4c211ead122 |  | note | Issue Date: 051218
checklist-flat |  |  | checklist | Hebel/Fire Separation |  |  |  |  | Yes | Hebel/Fire Separation | b1e6b862-2069-4834-ae16-0f7c847374ac
checkpoint-status |  |  | checkpoint | Confirm deflection head or slotted angle has been used depending on ceiling height. Slotted angle top track to be used when < 3200mm, alternatively when > 3200mm standard U deflection top track to be used.
checkpoint-status |  |  | checkpoint | Confirm Rondo base angle has been fixed to slab at a maximum of 600mm spacing.
checkpoint-status |  |  | checkpoint | Confirm that Hebel Mortar has been installed to the base of the panel.
checkpoint-status |  |  | checkpoint | Confirm Hebel PowerPanel has been fixed to base angle with 1 × 14mm- 10× 65mm hex head Type 17 screw 50mm from each corner.
checkpoint-status |  |  | checkpoint | Confirm that a maximum of 15mm spacing have been left between the deflection head where fixed to concrete soffit and top of Hebel PowerPanel.
checkpoint-status |  |  | checkpoint | Confirm that If slotted angle deflection top track is being used have the panels been secured with 14mm- 10× 65mm hex head Type 17 at 900mm spacing.
checkpoint-status |  |  | checkpoint | Confirm that any 14mm - 10× 65mm hex head Type 17 secured to slotted angle, that it is positioned in the middle of the slotted hole.
checkpoint-status |  |  | checkpoint | Confirm deflection head has been caulked at junction with concrete soffit with Intumescent & Acoustic Sealant. In the case where a U deflection top track is being used, both sides must caulked, otherwise to one side if using a slotted angle deflection top track.
checkpoint-status |  |  | checkpoint | Confirm that all penetrations must have small pieces of Hebel installed neatly to within 15mm of the penetrating service so that it can be Fire/Acoustically sealed off
checkpoint-status |  |  | checkpoint | Ensure that Backing Rod is used behind Intumescent & Acoustic Sealant.
checkpoint-status |  |  | checkpoint | Confirm that Hebel Power Panels are glued edge to edge with Hebel adhesive.
checkpoint-status |  |  | checkpoint | Confirm all fire door frames fixed to Hebel wall panels must be filled with TRCO FYREFLEX.
checkpoint-status |  |  | checkpoint | Confirm that any panel to panel junction detail must be fastened together by 14- 10 × 150mm hex head coarse thread screw at 900mm maximum centres and be a maximum of 100mm from the panel end.
checkpoint-status |  |  | checkpoint | Confirm that any penetrations are neatly cut with a cover plate covering the area.
checkpoint-status |  |  | checkpoint | Confirm that all penetrations have been caulked to both side of penetration through Hebel panel with Intumescent & Acoustic Sealant.
checkpoint-status |  |  | checkpoint | Confirm level clean/cleared including scaffold.
checkpoint-status |  |  | checkpoint | Ensure that between construction joints Hebel Power Panels have a 10mm gap that has Intumescent & Acoustic Sealant applied to both side of the panel as well as a ROUND P35 non fire rated 22mm dia.
checkpoint-status |  |  | checkpoint | Nib walls that are under 270mm in width will require either Vertical Angles or Deflection for the entire height of these walls for additional support
checkpoint-status |  |  | checkpoint | Ensure that any Cut Reinforcement has been coated with the Hebel anti-corrosion protection paint.
checkpoint-status |  |  | checkpoint | Confirm that each penetration through fire-rated walls is tagged as per AS4072, and a photo of the penetration is taken.
holdpoint |  |  | signoff | HOLD POINT - Close out Level Compliance ITP prior to proceeding any further.
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-018 Rev 00 Hebel/Fire Separation
checklist-flat |  |  | checklist | Stone - GPL-QSE-ITP-FIN-016(Rev 00) |  |  |  |  | Yes | Stone - GPL-QSE-ITP-FIN-016(Rev 00) | c63d40bb-9757-43fd-8597-01391bb48bde
checkpoint-status |  |  | checkpoint | Confirm that stone is installed to
boolean | b75e86f2-6a8e-5708-a08d-86e38da3a73d |  | tickbox | Kitchen
boolean | 9d2de2cd-d190-504d-9da4-76e6dd64e66f |  | tickbox | Bathroom
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-016(Rev 00)
label | 0dd88ed2-dcba-522e-bdcc-023bf12309ff |  | note | Authorised By: FA
label | 1749cd18-d663-5ace-bfb5-d19d659735f0 |  | note | Issue Date: 301118
checklist-flat |  |  | checklist | Structure Handover to Fitout - GPL-QSE-ITP-STRUC-007 (REV 01) |  |  |  |  | Yes | Structure Handover to Fitout - GPL-QSE-ITP-STRUC-007 (REV 01) | c917e3dc-d601-43bc-bfe4-d9693b9a577f
checkpoint-status |  |  | checkpoint | Confirm all formwork materials have been removed from level
checkpoint-status |  |  | checkpoint | Confirm all nails have been removed from slab soffits
checkpoint-status |  |  | checkpoint | Confirm that all slabs have been broomed and cleaned of debris and excess concrete This includes areas where there is penetration mesh
checkpoint-status |  |  | checkpoint | Confirm that all balcony and wet area set downs have been reviewed and rectified due to incorrect setouts or issues of depth
checkpoint-status |  |  | checkpoint | Confirm that all formwork has been removed from penetrations
checkpoint-status |  |  | checkpoint | Confirm that all excess scaffolding equipment has been removed from the level
checkpoint-status |  |  | checkpoint | Confirm that final stress and grouting of PT ducts are completed
checkpoint-status |  |  | checkpoint | Confirm that all post tensioning grout tubes are cut flush to concrete slab and placed in rubbish bins
checkpoint-status |  |  | checkpoint | Confirm that all post tensioning pans has been filled and concreted
checkpoint-status |  |  | checkpoint | Confirm that all hydraulic cast-ins have been cut down and flush with the slab
checkpoint-status |  |  | checkpoint | Confirm that all precast stitch plates have been continuously welded and epoxy painted
checkpoint-status |  |  | checkpoint | Confirm that all precast stitch plates have been fire rated, in accordance with Structural Engineers Details
checkpoint-status |  |  | checkpoint | Confirm that all packers have been removed from base of precast panels
checkpoint-status |  |  | checkpoint | Confirm that all packers have been removed from sides of precast spandrels
checkpoint-status |  |  | checkpoint | Confirm that bases of precast load bearing columns have been fully grouted
checkpoint-status |  |  | checkpoint | Confirm that bases of non load bearing columns have soft joints (backing rod and caulking)
checkpoint-status |  |  | checkpoint | Confirm all caulking to precast (both horizontal & vertical) is complete
checkpoint-status |  |  | checkpoint | Confirm all precast props and excess material removed from level
checkpoint-status |  |  | checkpoint | Confirm that surveyor Benchmark and grid lines are visible on slab If not contact surveyor and re-instate
checkpoint-status |  |  | checkpoint | Confirm that all structural defects are rectified and signed off
checkpoint-status |  |  | checkpoint | Conduct walk with Finishes Foreman of entire floor, and agree handover
checkpoint-status |  |  | checkpoint | Authorised By: FA Issue Date: 51218
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-007 (Rev 01) Structure Handover to Fitout
label | f23782e9-78b7-5044-822f-c686bca029ca |  | note | Authorised By: FA
label | 55f1bc9c-0b5c-50dc-8aeb-096bdc703420 |  | note | Issue Date: 51218
checklist-sectioned |  |  | checklist | Stairs - GPL-QSE-ITP-STRUC-013 (Rev 02) |  |  |  |  | Yes | Stairs - GPL-QSE-ITP-STRUC-013 (Rev 02) | c91c9917-f423-479c-8e95-80e5a3487572
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm bottom of stair RL's on Architectural Concrete Outlines
text | e903b0e5-1c7a-5701-9e68-7ab9a5d434b2 |  | textbox | Bottom of Stair SSL:
text | 3cc02ef6-e2d3-526e-99a0-51b45a25c759 |  | textbox | Bottom of Stair FFL:
checkpoint-status |  |  | checkpoint | Confirm top of stair RL's on Architectural Concrete Outlines
text | 07681763-5a22-5937-b5da-b01d4b67e486 |  | textbox | Top of Stair SSL:
text | 61f0878d-1c0a-5acf-868f-d77094ae6915 |  | textbox | Top of Stair FFL:
checkpoint-status |  |  | checkpoint | Confirm mid landing RL's on Architectural Concrete Outlines
text | f8369437-d05f-51fa-b54d-8f4f811eabfd |  | textbox | Mid Landing SSL:
text | 10ea35be-52d4-5e2d-9ee4-921600e83297 |  | textbox | Mid Landing FFL:
checkpoint-status |  |  | checkpoint | Confirm Architectural and Structural Drawings are consistent
checkpoint-status |  |  | checkpoint | Confirm Re-boxes/cast-in bars are installed to correct heights at landings
checkpoint-status |  |  | checkpoint | Confirm any starter bars on landings for dividing walls, etc… are installed as per Structural Drawings, cross-check with Architectrual Drawings
checkpoint-status |  |  | checkpoint | Check for reinforcement cover as per Structural Drawings
checkpoint-status |  |  | checkpoint | Check for reinforcement lapping from landing into throat of stair as per Structural Details
checkpoint-status |  |  | checkpoint | Confirm position of block outs or penetrations installed for services (eg; fire hydrant, lighting, etc…)
checkpoint-status |  |  | checkpoint | Confirm all cast in elements installed (eg, stair handrails, etc…), cross-check with stair shopdrawings
checkpoint-status |  |  | checkpoint | Confirm all formwork is clean and free of debris
checkpoint-status |  |  | checkpoint | Confirm conventional stairs have been formed in accordance with the relevant shop drawings and standards
checkpoint-status |  |  | checkpoint | Confirm cast-in of anti-slip items (eg, carborundum powder, stair nosings, etc…);
checkpoint-status |  |  | checkpoint | Obtain certificate from Structural Engineer prior to concrete pour, and attached completed Inspection Report
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
text | 234c9cca-926a-5f87-8852-4f779e0734d2 |  | textbox | Total m3:
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg size of concrete prior to ordering
text | bbeb52d7-a295-5fbd-bd54-f41b063ccd87 |  | textbox | MPa:
text | 21a67c6d-ed53-513c-ad20-0a96ee67a62e |  | textbox | Slump:
text | 0b233c05-de96-5e4d-a5e3-4e2d5f4d259d |  | textbox | Agg:
checkpoint-status |  |  | checkpoint | In the case of pouring fire stairs, ensure appropriate clearances in accordance with the shop drawings and relevant standards
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | If the stairs are being used as access to a leading deck, ensure alternative access is established prior to pouring
checkpoint-status |  |  | checkpoint | Confirm concrete tester on site during concrete pour, and the following tests have been requested
boolean | 0688f0de-b8b1-560e-a5b7-fc628d2d45cc |  | tickbox | 7 Day
boolean | e6be8ef2-931b-58e7-af02-1853db9c6b49 |  | tickbox | 28 Day
checkpoint-status |  |  | checkpoint | Ensure that no water is added to the concrete mix, whether in the truck or pump
label | 92ec3b0c-6dfe-5808-a06b-d78f11f831ae |  | note | (If there is evidence of this happening, concrete is to be rejected and replaced at the subcontractor’s expense, including the delay time of the concrete pour)
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | ddbcca8d-e597-5e13-9e77-f337d4dc1c22 |  | tickbox | Formworker
boolean | d9950d0b-4cfa-5dca-a8f2-ed2d23a3ddb0 |  | tickbox | Electrician
boolean | 4486676f-ccf7-5f6f-a252-e7d651e20a49 |  | tickbox | Plumber / Fire Services
checkpoint-status |  |  | checkpoint | Ensure concreters have correct finishing tools (eg, carborundum powder, etc…)
checkpoint-status |  |  | checkpoint | Ensure only rubber tipped vibrators are used
checkpoint-status |  |  | checkpoint | Ensure Formworker labour is available to clean up any slurry runs at bottom of walls, immediately after pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
boolean | 853d5018-62e7-533e-987a-cd61a5930a88 |  | tickbox | 6mm +/- from design RL
boolean | 0b75baee-be57-587b-9afa-814da576aa40 |  | tickbox | 6mm +/- from 30m straight edges
checkpoint-status |  |  | checkpoint | If an as-built survey is required, confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 days, and attach test results
text | 51bdcee7-4e50-5b09-9cae-56a333581d46 |  | textbox | Test Strength MPa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 days, and attach test results
text | b02f49e0-8632-58a7-98d8-ad67ac8bff82 |  | textbox | Test Strength MPa
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-013 (Rev 02) Stairs
label | c42377ce-6702-560b-b547-8342fd36cb3c |  | note | Authorised By: FA
label | 774a12bd-556d-56b4-bae6-ffef7cd59c13 |  | note | Issue Date: 51218
checklist-sectioned |  |  | checklist | Waterproofing - Internal Areas - GPL-QSE-ITP-FIN-010 (Rev 01) |  |  |  |  | Yes | Waterproofing - Internal Areas - GPL-QSE-ITP-FIN-010 (Rev 01) | ca5d0590-33d0-448c-b9ce-df5cce5f8f77
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Floor wastes are free of waste material and are in correct location, flush and grinded down
checkpoint-status |  |  | checkpoint | Correct fall shave been made in wet areas
checkpoint-status |  |  | checkpoint | Confirm concrete floor slab 100% clean, free of water, dirt dust
checkpoint-status |  |  | checkpoint | Confirm primer used to floors and walls as per manufacturers requirements: Minimum Drying time 6 hours between coats, Maximum Drying time 48 hours between coats
checkpoint-status |  |  | checkpoint | Confirm angle at wet area door is sealed with urethane sealant and primed as per manufacturer’s requirements
checkpoint-status |  |  | checkpoint | HOLD POINT
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm sealant at wall/floor junction and wall/wall junction, as per manufacturers requirements
checkpoint-status |  |  | checkpoint | FLOOR MEMBRANE: Install coat of to floors and upturn 150mm at wall as per manufacturers requirements: Confirm exposed aluminium angles are not membrane over, Minimum Drying time as per manufacturers requirements
checkpoint-status |  |  | checkpoint | WALL MEMBRANE: Install coat of Newflex WAM to shower wall and basin hob wall as per manufacturers requirements: Confirm wall membrane overlaps floor upturns, Minimum drying time as per manufacturers requirements
checkpoint-status |  |  | checkpoint | HOLD POINT
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | FLOOD TESTING: Fill floors with water to height of door angle: Leave for 24 hours
checkpoint-status |  |  | checkpoint | Confirm no leaks
checkpoint-status |  |  | checkpoint | If leaks were found – re-tank and confirm which area and flood test again
checkpoint-status |  |  | checkpoint | Subcontractor ITP received
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to sand cement topping
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-010 (Rev 01)
label | de2c84fa-0c8f-5ac1-ba9f-2f118729b9db |  | note | Authorised By: FA
label | 53cd9359-4de8-59cd-8a67-77d89bb4703c |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Walls/Columns/Verticals/Precast - GPL-QSE-ITP-STRUC-006 (Rev 03 - 05122018) |  |  |  |  | Yes | Walls/Columns/Verticals/Precast - GPL-QSE-ITP-STRUC-006 (Rev 03 - 05122018) | d1c53f14-c3e5-42e1-baec-bc816befefc1
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm all precast panels have been inspected for damage prior to lifting off truck, and evidence issued to precast supplier
checkpoint-status |  |  | checkpoint | Confirm position of wall/column is in accordance with architectural set out from gridline, as noted in Architectural Concrete Profiles
checkpoint-status |  |  | checkpoint | Confirm positions of all precast panels have been verified by surveyor
holdpoint |  |  | signoff | HOLD POINT - Attach Survey Record
checkpoint-status |  |  | checkpoint | Confirm starter bars to columns and walls installed in correct location, as noted on Structural Drawings
checkpoint-status |  |  | checkpoint | Check for reinforcement cover as per structural documents, as noted on Structural Drawings
checkpoint-status |  |  | checkpoint | Confirm all hydraulic services installed and plumber marks up as built drawings ie Cast in Downpipes Attach Subcontractor sign off
checkpoint-status |  |  | checkpoint | Confirm position of block outs or penetrations installed to walls, as noted on:
boolean | ec3b3cd5-8b9a-595f-875f-b141dcb573eb |  | tickbox | Architectural Drawings
boolean | 878bfbce-7ba0-5b79-ad0c-b3f0262a36e9 |  | tickbox | Structural Drawings
boolean | c3265dfc-21b2-55a8-85cc-ce18518040f3 |  | tickbox | Lift Drawings
boolean | b2143257-4c5f-592f-9e78-0cfc8f5a0136 |  | tickbox | Mechanical Drawings
boolean | a7280a2d-fe5b-5f09-a1e2-a86166d10038 |  | tickbox | Electrical / Fire / Hydraulic Drawings
boolean | 351ace5d-bc73-564f-a30a-8dc38bc40f52 |  | tickbox | Window Drawings
checkpoint-status |  |  | checkpoint | Confirm RL to top of wall/column is acknowledged by Formworker and Concrete Placer
checkpoint-status |  |  | checkpoint | Confirm all cast-in elements have been installed, as noted on:
boolean | 8a13c3aa-e0f7-5d85-a61e-32685b9828a2 |  | tickbox | Architectural Drawings
boolean | eb6b45c5-bfa9-5871-9a60-96ecfa8caaf1 |  | tickbox | Structural Drawings
boolean | 43fa6121-233b-5788-aa6c-75e425cf76a5 |  | tickbox | Lift Drawings
boolean | 4c8419d1-50b1-594f-bf4b-f5a0fbab6134 |  | tickbox | Mechanical Drawings
boolean | eeb92a88-771a-5557-b9e5-0732496fa855 |  | tickbox | Electrical / Fire / Hydraulic Drawings
boolean | b1e83219-46a7-5302-a53e-954f52ce5246 |  | tickbox | Window Drawings
checkpoint-status |  |  | checkpoint | Confirm formwork is checked to achieve Class 2 finish to concrete:
boolean | 76c155be-3cb4-5973-bc8d-8326230eafef |  | tickbox | Formwork is clean and free of debris
boolean | 8dc0cf1f-d3dd-5665-9713-ed347692e6b1 |  | tickbox | Lipping of formwork between sheets
boolean | b5db1f50-f693-53c6-87e6-26645df47fe6 |  | tickbox | Fillets installed at all corners
boolean | 106ddd9c-664a-588d-9919-5b806b7ec956 |  | tickbox | Ties are installed at even spacing
boolean | 22cfe357-3209-59db-8947-5cc777fe8ec8 |  | tickbox | Bottom of wall/column is clean, free from debris, rubbish or sawdust
checkpoint-status |  |  | checkpoint | Obtain certificate from Structural Engineer prior to concrete pour, and attach certificate
checkpoint-status |  |  | checkpoint | Confirm strength of concrete off structural drawings prior to ordering
text | a0aa98f5-1c71-58d7-aada-f772ac5c7565 |  | textbox | Concrete Strength MPa
checkpoint-status |  |  | checkpoint | Confirm Quantity of concrete ordered
text | b7cf18fe-092a-549b-8336-d93baae0fb32 |  | textbox | Quantity m3
checkpoint-group |  |  | section | During Concrete Pour
checkpoint-status |  |  | checkpoint | Ensure concrete truck dockets have correct concrete strength, and attach delivery docket from each batch
checkpoint-status |  |  | checkpoint | Confirm concrete tester on site during concrete pour, and the following tests have been requested
boolean | 140f099e-77f4-509a-b653-22e2f49f98ef |  | tickbox | 1 Day
boolean | 9119fbc4-52ed-5a42-9657-df5bd93b83ea |  | tickbox | 4 Day
boolean | 9270be51-a296-5294-b5d2-5db36dedf4db |  | tickbox | 28 Day
checkpoint-status |  |  | checkpoint | Ensure that no water is added to the concrete mix, whether in the truck or pump
label | bf5f00cb-3912-5de4-8ab9-026029a00c48 |  | note | (If there is evidence of this happening, concrete is to be rejected and replaced at the subcontractor’s expense, including the delay time of the concrete pour)
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | f57adff1-9012-5e62-b338-f24ea9e0f34f |  | tickbox | Formworker
boolean | 9873f48a-f7a6-518b-8faf-2fcea8b0f015 |  | tickbox | Electrician
boolean | bc197847-f912-50d7-9755-6b3e5f40f16b |  | tickbox | Plumber
checkpoint-status |  |  | checkpoint | Ensure only rubber tipped vibrators are used, and care is taken not to damage shutters
checkpoint-status |  |  | checkpoint | Ensure Formworker labour is available to clean up any slurry runs at bottom of walls, immediately after pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces:
boolean | 218a513d-4c03-5a32-a22b-3f8e09d65f0d |  | tickbox | 5mm +/- from correct position
boolean | 30d16341-3d9a-5c25-8249-984c61c28cea |  | tickbox | 5mm +/- from 30m straight edges
boolean | 6ef65ce2-06f6-5a04-af81-506ca7867f22 |  | tickbox | 5mm +/- from plumb
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
holdpoint |  |  | signoff | HOLD POINT - Attach Survey Record
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 days, and attach test results
text | 443f2abc-2934-5639-a430-164f6e17242b |  | textbox | Test Strength MPa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 days, and attach test results
text | 3b62f500-8801-5bc0-a879-6dc2d170c7c2 |  | textbox | Test Strength MPa
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-006 (Rev 03) Walls/Columns/Verticals/Precast
label | a5d8e0a3-6b7d-56ad-9a4b-6c99bdecaccb |  | note | Authorised By: FA
label | 46787ea9-e001-5471-9275-3bcef3110bc9 |  | note | Issue Date: 51218
checklist-sectioned |  |  | checklist | Waterproofing - Balcony Areas - GPL-QSE-ITP-FIN-0008 (Rev01) |  |  |  |  | Yes | Waterproofing - Balcony Areas - GPL-QSE-ITP-FIN-0008 (Rev01) | db3bb985-9454-42a4-90ef-b16e609f1026
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Floor wastes are free of waste material and are in correct location & signed off by plumber
checkpoint-status |  |  | checkpoint | Confirm concrete floor slab 100% clean, free of water, dirt dust and other condiments
checkpoint-status |  |  | checkpoint | Confirm ASA N40 Primer used to PVC pipes at floor wastes as per manufacturer’s requirements
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Apply Seal’n’Fillet Urathane sealant at wall/floor junction and wall/wall junction, as per manufacturers requirements
label | a746bb44-ecf4-5143-acb5-9f680c8ea761 |  | note | Confirm 6mm x 6mm triangular fillet & Sealant not smeared
checkpoint-status |  |  | checkpoint | Install 1st coat to floors, upturn 150mm at wall as per manufacturers requirements
label | 5fc40354-fa51-5f7a-9ae4-1da6ac3da5ee |  | note | NOTE: Minimum Drying time 24hours between coats
label | 2d84367a-0bbe-58e2-a585-43c0a1ac0b63 |  | note | NOTE: Maximum Drying time 48hours between coats
checkpoint-status |  |  | checkpoint | Install 2nd coat to floors, upturn 150mm or to finish floor level at walls as per manufacturer's requirements
label | d1dcd3aa-ead6-510c-8058-5ec045aace87 |  | note | NOTE: Minimum Drying time 24hours between coats
label | a67aaba5-6432-5240-9a5d-526a121fb486 |  | note | NOTE: Maximum Drying time 72hours
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Confirm no pinholes with detector after minimum drying time 24hours
checkpoint-status |  |  | checkpoint | Carry out Flood Test
checkpoint-status |  |  | checkpoint | HOLD POINT – Take photo of actual flood test & attach (utilising ID board)
checkpoint-status |  |  | checkpoint | Install sand cement floor topping (3:1 ratio) over whole of Balcony area with minimum screed 25mm at floor wastes
checkpoint-status |  |  | checkpoint | Confirm falls are away from balcony sliding door at all locations
checkpoint-status |  |  | checkpoint | Allow 3-4 days drying time for sand cement screeds
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-0008 (Rev01)
label | badbe3c3-06d8-5f0f-b1e9-071d8d161732 |  | note | Authorised By: FA
label | 6a6bfc24-86f5-5d77-8253-b03a2ac3a60d |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Rock Anchoring GPL-QSE-ITP-STRUC-011 (Rev 0 - V080421) |  |  |  |  | Yes | Rock Anchoring GPL-QSE-ITP-STRUC-011 (Rev 0 - V080421) | df8b439c-ad7a-4c72-bada-2d5e4f5633fd
checkpoint-group |  |  | section | Prior to Works Commencing
checkpoint-status |  |  | checkpoint | Locate all existing services
checkpoint-status |  |  | checkpoint | Confirm set out and anchoring works remains within the boundary
checkpoint-status |  |  | checkpoint | Confirm type of anchor to be used
checkpoint-status |  |  | checkpoint | Confirm the working load of the anchor/ tendon
checkpoint-status |  |  | checkpoint | Confirm max depth for anchors
checkpoint-status |  |  | checkpoint | Confirm angle of anchors
checkpoint-status |  |  | checkpoint | Confirm strength of grout required
checkpoint-status |  |  | checkpoint | Confirm diameter for bore holes
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm de-stressing procedure for anchors with engineer
checkpoint-status |  |  | checkpoint | Confirm anchors are not damaged during insertion into bore hole
checkpoint-status |  |  | checkpoint | Confirm bore hole is being flushed clean – water/ air/ both?
checkpoint-status |  |  | checkpoint | Confirm grouting is taking place same day
checkpoint-status |  |  | checkpoint | Confirm grout testing is taking place (results to be returned 28 days later)
checkpoint-status |  |  | checkpoint | Confirm bore holes do not require re-drilling
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-status |  |  | checkpoint | Confirm grouting is reaching required strength after 7 days
checkpoint-status |  |  | checkpoint | Confirm stressing works have been completed
checkpoint-status |  |  | checkpoint | Confirm testing has been completed and passed loading test
checkpoint-status |  |  | checkpoint | Confirm anchors have not moved during testing
checkpoint-status |  |  | checkpoint | Confirm if additional anchors are required
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Capping Beam - GPL-QSE-ITP-STRUC-010 (Rev 01) |  |  |  |  | Yes | Capping Beam - GPL-QSE-ITP-STRUC-010 (Rev 01) | e64ab644-41da-45bf-b816-16f5e1a2f6af
checkpoint-group |  |  | section | Prior to Capping Beam Operations
checkpoint-status |  |  | checkpoint | Attach mark-up plan of Capping beam covered by this ITP (Refer to relevant drawings)
checkpoint-status |  |  | checkpoint | Confirm RL’s of capping beam
checkpoint-status |  |  | checkpoint | Confirm excavation for capping beam has been complete and ready for formwork to commence
checkpoint-status |  |  | checkpoint | Set out of capping beam
checkpoint-status |  |  | checkpoint | Confirm engineers design of capping beam
checkpoint-status |  |  | checkpoint | Concreting contractor to inspect reinforcement levels prior to pouring
checkpoint-status |  |  | checkpoint | Attach reinforcement placement checklist from steel fixing subcontractor
checkpoint-status |  |  | checkpoint | Attach structural engineer inspection prior to concrete pour (All items closed out)
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
checkpoint-status |  |  | checkpoint | Confirm mPa, slump and agg size of concrete prior to ordering
checkpoint-status |  |  | checkpoint | Confirm formwork faces are clean and will provide required class finish
checkpoint-status |  |  | checkpoint | Confirm formwork is adequately braced to reduce blow-out occurrence
checkpoint-status |  |  | checkpoint | Confirm pile connection bars are clean and free of debris
checkpoint-status |  |  | checkpoint | HOLD POINT - OK to Pour
checkpoint-group |  |  | section | During Capping Beam
checkpoint-status |  |  | checkpoint | Confirm Concrete Tester onsite to take samples
checkpoint-status |  |  | checkpoint | Confirm vibrating is occurring evenly and not excessively (as per specification)
checkpoint-status |  |  | checkpoint | Confirm no water has been added to the concrete mix
checkpoint-status |  |  | checkpoint | Confirm reinforcement has not moved by concrete placement
checkpoint-status |  |  | checkpoint | Confirm no blow-outs have occurred
checkpoint-group |  |  | section | After Capping Beam Poured
checkpoint-status |  |  | checkpoint | Attach surveyors spot check – Confirm tolerance of finished concrete surfaces (+/- 6mm from 30m straight edges) – Has movement to the capping beam occurred?
label | 903086f1-e0c9-59cc-b91f-88243d4b3384 |  | note | Confirm surveyor spot checks levels and attach mark up
checkpoint-status |  |  | checkpoint | Confirm stripping is complete All exposed faces are clear of formwork
checkpoint-status |  |  | checkpoint | Confirm vibration was adequate – no air pockets, agg evenly distributed If not, comment rectification method required
checkpoint-status |  |  | checkpoint | Confirm no blow-out occurred If occurred, comment rectification method required
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate (broom/trowel/helicopter finish)
label | 2074bee3-b8be-55e0-ab3e-c55cac70fd38 |  | note | Class 1, 2, 3 or 4 Refer to AS3610 table
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day
text | a9df8b60-79b0-51b6-8799-968cdba127a1 |  | textbox | Test Strength Mpa
label | 5d92a2b3-4a40-5dfa-a653-9789f71badf7 |  | note | Attach concrete test result
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 days
text | caa987bf-9880-5ffb-b67d-601d82c31d84 |  | textbox | Test Strength Mpa
label | 53da3762-23fa-5ed3-a6c4-dbc6675b9768 |  | note | Attach concrete test result
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 days
text | 8676f0c1-6363-5bb7-bbca-909901668263 |  | textbox | Test Strength Mpa
label | 0b67c941-a884-5896-a07c-82814c7d4eeb |  | note | Attach concrete test result
checkpoint-status |  |  | checkpoint | Attach subcontractor ITP
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-010 (Rev 01) Capping Beam
label | fa472190-6e44-5738-af87-729f870e570c |  | note | Authorised By: FA
label | 359f2de9-b61b-5d55-a389-5f686f358133 |  | note | Issue date: 51218
checklist-sectioned |  |  | checklist | Tiling - Internal Areas - GPL-QSE-ITP-FIN-006 (Rev 01) |  |  |  |  | Yes | Tiling - Internal Areas - GPL-QSE-ITP-FIN-006 (Rev 01) | eef64365-bc0f-4fe9-8392-652b7167707b
checkpoint-group |  |  | section | Prior to Works
checkpoint-status |  |  | checkpoint | Confirm Series and Scheme of finish for unit from Apartments Finishes Schedule
checkpoint-status |  |  | checkpoint | Confirm site samples match approved samples
checkpoint-status |  |  | checkpoint | Confirm Tile Set out prior to tiling and ensure consistency
checkpoint-status |  |  | checkpoint | Confirm tiles are from the same batch
checkpoint-status |  |  | checkpoint | Check joints will run in same direction as architectural or interior drawings
checkpoint-status |  |  | checkpoint | Confirm Tile Floor Finish level
checkpoint-status |  |  | checkpoint | Confirm Acoustic mat or Asaphonic tile glue used as per acoustic report
checkpoint-status |  |  | checkpoint | Confirm all floor wastes are plugged during tiling works
checkpoint-status |  |  | checkpoint | Confirm aluminium angle is not damaged or misaligned
checkpoint-status |  |  | checkpoint | Confirm top of aluminum angle is at the correct RL, and check against external floor finished level (ie flush, etc)
checkpoint-status |  |  | checkpoint | HOLD POINT – Ensure waterproofing is not damaged OK to proceed with Tiling works
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm sand/cement screed ratio is as per AS
checkpoint-status |  |  | checkpoint | Confirm minimum 25mm tile bed at floor waste
checkpoint-status |  |  | checkpoint | Confirm maximum tile and tile bed thickness at door threshold works with other floor finishes
checkpoint-status |  |  | checkpoint | Confirm installation of floor wastes is flush with or 1mm below floor tile level
checkpoint-status |  |  | checkpoint | Stop wall and floor tiles 2-3mm short of edges and fill with resilient caulking compound
checkpoint-status |  |  | checkpoint | Confirm that floor waste (normal/smart) and strip drain is installed correctly Tiling grout lines line up with tiles
checkpoint-status |  |  | checkpoint | Timber floor install to include: Skirting installed throughout whole apartment
checkpoint-group |  |  | section | After Tiling
checkpoint-status |  |  | checkpoint | Visually inspect all floor wastes, and confirm each one is clean and clear
checkpoint-status |  |  | checkpoint | Floor tiles laid to falls – min 1:100
checkpoint-status |  |  | checkpoint | Confirm all joints are aligned
checkpoint-status |  |  | checkpoint | Confirm colour of grout is consistent and uniform
checkpoint-status |  |  | checkpoint | Confirm all tile edges line up and are plumb
checkpoint-status |  |  | checkpoint | Confirm all silicon jointing provided to all floor/wall tile junctions
checkpoint-status |  |  | checkpoint | Confirm all excess silicon is removed from tiles and adjoining surfaces
checkpoint-status |  |  | checkpoint | Subcontractor ITP received
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-006 (Rev 01)
label | c1163172-c3b4-50a1-bcbf-3d047fb6e327 |  | note | Authorised By: FA
label | 9c98fbcc-7787-58c3-8ec0-9ea4d8f09afa |  | note | Issue Date: 051218
checklist-sectioned |  |  | checklist | Suspended Slab - GPL-QSE-ITP-STRUC-005 (Rev 03) |  |  |  |  | Yes | Suspended Slab - GPL-QSE-ITP-STRUC-005 (Rev 03) | f587c14c-8025-42a3-a613-f871dbe496bb
checkpoint-group |  |  | section | Prior to Deck Handover
checkpoint-status |  |  | checkpoint | Confirm deck is safe, handrails installed and edge protection is provided to full perimeter of deck
checkpoint-status |  |  | checkpoint | Confirm means of access to deck, 2 x stretcher stair access
checkpoint-status |  |  | checkpoint | Confirm Formworkers Deck Handover Certificate and ITP is received and sighted
holdpoint |  |  | signoff | Attach Deck Handover Certificate
checkpoint-group |  |  | section | Prior to Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm As-Built Survey of deck is complete
holdpoint |  |  | signoff | HOLD POINT - Attach As-Built Survey of Deck
checkpoint-status |  |  | checkpoint | Confirm Formworker has received As-Built Survey of deck, and has rectified errors prior to any trades commencing on deck
checkpoint-status |  |  | checkpoint | Confirm all beams and decks constructed as per Structural Concrete Profiles
checkpoint-status |  |  | checkpoint | Install slip joints to all load bearing walls and corbels where required
checkpoint-status |  |  | checkpoint | Clean off decks and beams prior to pour, and ensure all exposed off-form soffits are free of any dust, stains and rust marks Hose down if necessary
checkpoint-status |  |  | checkpoint | Check if concrete has falls, and ensure shutters, timbers, spacers are used to create folds where necessary Cross-check the following drawings:
boolean | 70c43916-1d15-52e9-a302-bc96ba9dce34 |  | tickbox | Hydraulic Drawings
boolean | 4533ffee-b60f-53c6-9bec-7226666f9210 |  | tickbox | Architectural Concrete Outlines
boolean | 7c69fe27-5910-5691-8a8f-a13e36b0e9a4 |  | tickbox | Structural Drawings
checkpoint-status |  |  | checkpoint | Check top RLs for all reinforcement, ensuring adequate concrete cover Confirm with Concreter
checkpoint-status |  |  | checkpoint | Confirm that plastic bar chairs are used everywhere, particularly at exposed off-form soffits
checkpoint-status |  |  | checkpoint | Attach Formwork ITP
holdpoint |  |  | signoff | HOLD POINT - Attach Formwork ITP
checkpoint-status |  |  | checkpoint | Attach Formwork Engineer's sign off certificate Confirm that certificate references props, braces and compliance with design & AS3610
holdpoint |  |  | signoff | HOLD POINT - Attach Formwork Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach Hydraulic ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Electricians ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Fire Services ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Mechanical ITP (for cast-in elements), include relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Precast ITP (for cast-in elements), including relevant mark-ups
checkpoint-status |  |  | checkpoint | Attach Reo Fixing ITP
checkpoint-status |  |  | checkpoint | Attach Principal Structural Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
holdpoint |  |  | signoff | HOLD POINT - Attach Principal Engineer's Certificate
checkpoint-status |  |  | checkpoint | Attach Post Tensioning Engineer Inspection Report, and confirm that all actions are closed out with photos sent to engineer
holdpoint |  |  | signoff | HOLD POINT - Attach Post Tensioning Engineer's Certificate
checkpoint-status |  |  | checkpoint | Check quantity of concrete required prior to ordering
text | 249390f9-c69a-55d9-acee-1aca2d85a3c5 |  | textbox | Total m3 (as measured by Site Engineer):
text | bf94975d-9d5e-5007-ad9e-f5f722460fcc |  | textbox | Total m3 (as measured by Foreman):
checkpoint-status |  |  | checkpoint | Confirm MPa, slump and agg size of concrete prior to ordering
text | ef1e9a3b-fcd8-5e9e-a6e8-caf68e1f6f46 |  | textbox | MPa:
text | 3bd92e8f-c572-5997-9a6a-5ceba83815b4 |  | textbox | Slump:
text | 1c1f9b06-cab4-50f5-b370-4e73e542c87c |  | textbox | Agg:
checkpoint-group |  |  | section | During to Concrete Pour
checkpoint-status |  |  | checkpoint | Ensure concrete truck dockets have correct concrete strength, and attach delivery docket from each batch
checkpoint-status |  |  | checkpoint | Confirm concrete tester on site during concrete pour, and the following tests have been requested
boolean | 1fc59e09-02ec-5864-88b8-e5f8eb00b16b |  | tickbox | 1 Day
boolean | 0a659eb9-e3b9-5c15-a8b6-d7e7936bccb0 |  | tickbox | 4 Day
boolean | 9e3b7216-ecaa-5500-9d36-bd4b1ec51ec7 |  | tickbox | 7 Day
boolean | ae0e8b28-66d9-5a1b-8a88-40a2e58184cd |  | tickbox | 28 Day
checkpoint-status |  |  | checkpoint | Ensure that no water is added to the concrete mix, whether in the truck or pump
label | ebf9e1b8-2291-59ac-bb2b-0171a58549a2 |  | note | (If there is evidence of this happening, concrete is to be rejected and replaced at the subcontractor’s expense, including the delay time of the concrete pour)
checkpoint-status |  |  | checkpoint | Confirm concrete has falls to drainage points in slab
checkpoint-status |  |  | checkpoint | Ensure a representative from each of the following is on site and witnessing the pour:
boolean | 1f006b8f-2455-502f-ad58-2f4ae8ba4eb2 |  | tickbox | Formworker
boolean | 0c0b5553-dae9-5d1d-841e-ab7d98c8e5a1 |  | tickbox | Electrician
boolean | 316b10a8-b1c2-5c18-8d01-1b562a9a9df5 |  | tickbox | Plumber
boolean | a754adf3-f208-54f7-bf01-c74035aad8d4 |  | tickbox | Post Tensioner
boolean | 575f1153-f0a9-5f06-8563-d3f3093ccd8d |  | tickbox | Precast Installer
checkpoint-status |  |  | checkpoint | Confirm Formworker has labour below deck inspecting all joints (particularly at columns & walls) and is immediately cleaning any slurry
checkpoint-status |  |  | checkpoint | Confirm that all protection to precast panels is maintained at all times during concrete pour
checkpoint-group |  |  | section | After Concrete Pour
checkpoint-status |  |  | checkpoint | Confirm Surveyor is out next day to carry out survey of finished concrete Attach As built Survey Plan
holdpoint |  |  | signoff | HOLD POINT - Attach Survey Record
checkpoint-status |  |  | checkpoint | Confirm tolerance of finished concrete surfaces are as follows:
boolean | 66d06ec7-4fcf-5320-87df-3b34b828e1a1 |  | tickbox | 6mm +/- from design RL
boolean | 64146831-68a2-586b-af59-b67d640ff924 |  | tickbox | 6mm +/- from 30m straight edges
checkpoint-status |  |  | checkpoint | Confirm saw joints are installed to engineers requirements, generally 36hrs after the pour
checkpoint-status |  |  | checkpoint | Confirm finish of concrete is adequate for application (broom/trowel/helicopter finish), refer to AS3610
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 1 day, and attach test results
text | d684a597-95bc-5527-8116-f9e4d23a9e98 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm initial stress is conducted day after the pour, after concrete has reached 10MPa on 1 Day results
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 4 day, and attach test results
text | a739149f-b769-521f-a62c-4552a8d66fbe |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Confirm final stress has occurred after concrete has reached 20MPa, and attach Stressing Records
holdpoint |  |  | signoff | HOLD POINT - Attach Stressing Records
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 7 day, and attach test results
text | bf6768f1-e3c0-5325-86ac-bcf6767a8265 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | Obtain all concrete tests at 28 day, and attach test results
text | 87bb9f46-bc12-5d9e-bb54-87e02ec542e9 |  | textbox | Test Strength Mpa
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-STRUC-005 (Rev 03) Suspended Slab
label | 3d2857bd-1e40-50eb-b19e-5dccfd454379 |  | note | Authorised By: FA
label | eac51f15-9de6-5ba8-8954-c09ae79f2f07 |  | note | Issue Date: 51218
checklist-sectioned |  |  | checklist | Metal Roofing - GPL-QSE-ITP-FIN-004 (Rev 01) |  |  |  |  | Yes | Metal Roofing - GPL-QSE-ITP-FIN-004 (Rev 01) | f8e9efd3-cdd0-4d3b-bb5e-346494384c3f
checkpoint-group |  |  | section | During Works
checkpoint-status |  |  | checkpoint | Confirm that Thermal Insulation blankets installed to comply with specified rating
checkpoint-status |  |  | checkpoint | Confirm insulation installed as per specification
checkpoint-status |  |  | checkpoint | Confirm pitch is in accordance with design
checkpoint-status |  |  | checkpoint | All opening sizes for skylights correct
checkpoint-status |  |  | checkpoint | Skylights installed in correct position
checkpoint-status |  |  | checkpoint | Confirm wall fire blanket between partition walls installed to underside of roof sheeting
checkpoint-status |  |  | checkpoint | Flashings turned down and installed in accordance with specification
checkpoint-status |  |  | checkpoint | All over flashings and under flashings installed
checkpoint-status |  |  | checkpoint | All box gutters to contain correct sized overflow outlets
checkpoint-status |  |  | checkpoint | Clean down roof and remove left over materials on completion
checkpoint-status |  |  | checkpoint | Remove metal filing, off-cuts, dust and other materials which could cause corrosion or blockages
checkpoint-status |  |  | checkpoint | Water test – Hose test of roof area for 4hr minimum
checkpoint-status |  |  | checkpoint | Water test roof penetrations
checkpoint-status |  |  | checkpoint | Water test roof flashings
checkpoint-group |  |  | section | After Works
checkpoint-status |  |  | checkpoint | HOLD POINT – OK to proceed to Painting
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Subcontractor Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Orwell Sign Off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | GPL-QSE-ITP-FIN-004 (Rev 01)
label | 77529ac3-2365-5de1-a719-dbe8970f2e04 |  | note | Authorised By: FA
label | 31916e22-7028-5b87-94d5-67f2ea7e2d98 |  | note | Issue Date: 301118