## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Concrete Slab/Columns/Wall Checklist |  |  |  |  | Yes | Concrete Slab/Columns/Wall Checklist | 240898c6-0cb0-43d1-a452-5d4d7c6203cc
checkpoint-group |  |  | section | Concrete Pre-Pour
checkpoint-status |  |  | checkpoint | Precast / Façade Castins are installed as per Manufacturers & Engineers Details
checkpoint-status |  |  | checkpoint | Reo - Current drawings revision checked **
text | 2fdd471b-a421-54aa-b92e-9712259a86e0 |  | textbox | Input all referenced drawings & revision numbers
checkpoint-status |  |  | checkpoint | Formwork Sign Off **
label | dc02fcad-05de-5444-8bdf-2a5682487fc3 |  | note | Evidence of sign off attached
checkpoint-status |  |  | checkpoint | Formwork Engineer sign off complete **
label | e762d1a4-acfd-5b69-b46d-2b784429b6c2 |  | note | Evidence of sign off attached
checkpoint-status |  |  | checkpoint | Engineer Reinforcement sign off complete by AusPT
label | a4b6c044-531b-56a0-93b8-d349086b8666 |  | note | Evidence of sign off attached
checkpoint-status |  |  | checkpoint | Concrete Mix Design Approved **
text | f99715a1-1ad4-50dd-b9d4-b29279f21e8d |  | textbox | Input Concrete Mix Design (columns or walls) & Engineer sign off Aconex Ref #
checkpoint-status |  |  | checkpoint | Concrete Delivery Booked / Confirmed **
text | 0ab63120-f4c5-5900-b6ab-4f4dcf1e9f77 |  | textbox | Input Concrete Strength (columns or walls) (Input Mpa)
checkpoint-status |  |  | checkpoint | Structural levels confirmed
label | ecc2ff80-eb9c-5234-8451-6a43b7cb3e9d |  | note | Areas to be nominated where RL's vary (shower, balcony setdowns/upstands, etc.)
label | 47b96fe7-4515-5353-8191-21faef5a69cd |  | note | Areas to be nominated where drainage fall is required
checkpoint-group |  |  | section | Concrete Placement
checkpoint-status |  |  | checkpoint | Kapitol Group Site Supervisor to review first delivery **
label | 01bcb7b1-b579-5c1f-a776-d0b367748870 |  | note | Confirm delivered concrete matches ordered specifications
label | aa73b470-1e56-5627-8e36-c5fa95c783b2 |  | note | Attach copy of initial delivery docket
holdpoint |  |  | signoff | Click here - kapitol Group Sign Off
checkpoint-status |  |  | checkpoint | Delivered Concrete matches project requirements / booking **
label | 2033a43b-4157-5539-ac74-ca49e0218584 |  | note | Attach copies of all delivery dockets showing concrete matches ordered specifications
checkpoint-status |  |  | checkpoint | Concrete is finished to all structural and architectural requirements
checkpoint-group |  |  | section | Concrete Post-Pour Sign-Off
checkpoint-status |  |  | checkpoint | Initial PT stress completed **
label | a13bc008-81ab-5493-afea-48042584b6b6 |  | note | 24hrs post pour to match PT Engineer requirements
checkpoint-status |  |  | checkpoint | Final PT Stress Completed & Inspected **
label | cfafede6-c88a-5733-93f7-8a280a118709 |  | note | PT Engineer Sign-Off Completed & Attached
label | 8cf04ac4-e46d-57a3-a90b-5ef2553227f1 |  | note | Attach test results / report
checkpoint-status |  |  | checkpoint | Concrete Testing has been completed and meets expected results **
label | 6f5f9a78-bf03-53c7-8efb-4cf22884cf28 |  | note | only click "PASS" when all tests (with positive results) received
boolean | 1650a88f-c660-58c4-8ee2-a7c679e6d6d6 |  | tickbox | 7 day test results attached
text | abca6cf2-aa0f-537e-8241-ac5393a140b2 |  | textbox | Input the 7 day test result (mPa)
boolean | 94d70cf7-9cec-5cd6-b854-d0a524063ed6 |  | tickbox | 28 day test results attached
text | fa501973-e5b0-53a4-a2cd-ebc6517e1f96 |  | textbox | Input the 28 day test result (mPa)
label | b25cbd38-129c-5cad-9049-ed073b71ad7f |  | note | Attach test result documents
boolean | 06a48d5a-6e79-5e99-adfd-df0bac62a853 |  | tickbox | 56 day test results attached
text | e7ae39ae-0ab5-59cb-9617-0497e38d22a6 |  | textbox | Input the 56 day test result (mPa)
label | 00423000-f880-59e5-a7a7-b068b5d530a3 |  | note | Attach test result documents
checklist-flat |  |  | checklist | Grouting of Concrete Precast Panels / Columns ITP |  |  |  |  | Yes | Grouting of Concrete Precast Panels / Columns ITP | 7de47311-702f-427a-b292-8c0b468d4650
checkpoint-status |  |  | checkpoint | Cube test Complete per day
checkpoint-status |  |  | checkpoint | Slump Test Complete per panel - photo below includes SS Mortar Bags with batch number on front
checkpoint-status |  |  | checkpoint | Ensure horizontal grout bed has begun to cure prior to filling grout tubes to avoid bedding blowout or use approved grout donuts
checkpoint-status |  |  | checkpoint | NMB - Fill grout tubes with SS High Strength flowable grout and ensure the grout is filled to the top of the tube **
label | ebc4b435-8b7e-5ee2-a683-428b407bdfa9 |  | note | NMB - Use preset measurement container / scales to ensure grout tubes are accurately fille
text | 764d8c37-75d1-50bf-a2f6-272cc92b53a3 |  | textbox | NMB - Indicate set measure (in litres) 2.2L per bag (2.3 for first bag)
label | 7814aa41-03e4-5929-90bd-5f8e4db22c0b |  | note | DO NOT VIBRATE OR USE MECHANICAL VIBRATOR TO ASSIST FLOW
checkpoint-status |  |  | checkpoint | TYPICAL PANEL / BASES - AK HS Tecgrout - Fill grout tubes with flowable grout and ensure the grout is filled to the top of the tube **
label | ca3909ab-fa9d-545d-9e94-eb4b1afebc5d |  | note | TYPICAL PANEL / BASES - Use preset measurement container / scales to ensure grout tubes are accurately filled
text | 6a969ea8-55a6-55f9-abf1-36a930af46e4 |  | textbox | TYPICAL PANEL / BASES - Indicate set measure 3.0 - 3.2L Trowelable / 3.8 - 4.0L Flowable
label | f306525b-09e4-5e26-b7f8-57195e95bb0d |  | note | DO NOT VIBRATE OR USE MECHANICAL VIBRATOR TO ASSIST FLOW
checkpoint-status |  |  | checkpoint | Ensure precast elements are not loaded until strength nominated by Engineer for the grout bed has been met (21MPa) **
label | 9ef19d49-c756-5072-8e17-e4899f52f33e |  | note | Grout tubes are confirmed to be filled and packed prior to patching face holes.
label | f1d9a4f2-a884-5de2-9eb6-1e9101ec4340 |  | note | Kapitol to be given notice for possible observance before filling
checkpoint-status |  |  | checkpoint | NMB/TYPICAL - Confirmation all Grout Tubes have been grouted - if not, how many have been missed? *Worker must raise issue with KG
text | b20549bd-57d0-5a8e-a36a-050f051cdae5 |  | textbox | Number of Tubes missed?
holdpoint |  |  | signoff | Click here - Kapitol Group Sign Off
checklist-flat |  |  | checklist | Precast Installation Checklist |  |  |  |  | Yes | Precast Installation Checklist | f1337711-fec7-4e68-9b33-682f80a3b688
checkpoint-status |  |  | checkpoint | Delivered Precast Panel matches the casting/installation sequence & dimensions **
label | 70826621-3595-5221-a895-df12b07d18d0 |  | note | Attach copy of the delivery docket
text | e245d90f-eea4-5639-8070-d909c97901cd |  | textbox | Input Install Date
checkpoint-status |  |  | checkpoint | Shim plate level/stable and set to nominal [RL (150x100mm or similar) Overall height not exceed 40mm] **
checkpoint-status |  |  | checkpoint | Starter bars are correctly aligned and the correct size & length **
checkpoint-status |  |  | checkpoint | Precast component correctly aligned & positioned
checkpoint-status |  |  | checkpoint | Braces of adequate capacity installed correctly: typically 45° to 60° and in accordance with the Erection Design **
label | d07b9a66-5243-5bcc-aae8-f5e3d50a56d6 |  | note | Show images of braces installed and secure
checkpoint-status |  |  | checkpoint | Top fix: [Bolt M20 4.6 Nexus NX20115 torque 150Nm]
checkpoint-status |  |  | checkpoint | Bottom fix: [Bolt M20 8.8 Bottom Fix: Nexus NX20115 torque 150Nm]
checkpoint-status |  |  | checkpoint | Provide tamperproof locks to all shear pins in braces
checkpoint-status |  |  | checkpoint | Panels/Columns are Plumb **
label | 31cba9a3-03ba-5d77-8d98-69cf915d2ff1 |  | note | Show image of erected panel (with sequence/panel number marked)
checkpoint-status |  |  | checkpoint | Completion of Works **
text | dbe392f0-c0c5-57d2-9a54-ded76e841c31 |  | textbox | Works Accepted by PCF Foreman
label | 4b84f8c6-04ad-5099-bb71-3cad5f85c853 |  | note | Signature sign-off added below (subcontractor signature)
checkpoint-status |  |  | checkpoint | Kapitol Group Acknowledgement of installation
label | 88ad5479-fa72-50fd-9e8f-2ea63c74e7ef |  | note | Press Yellow button below to send email to Site Supervisor for sign off
holdpoint |  |  | signoff | Click here - Kapitol Group Sign Off
checkpoint-status |  |  | checklist | Trowellable mixture placed as a bed underneath precast element to be installed, inclusive of in between donuts to ensure full contact bearing ** |  |  |  |  | Yes | TEMP - CP | f65de611-5988-450a-80d2-c96da0c72a71