## TO BUILD - Project Breakdown
Project Breakdown |  |  |  | Checklists
(PROJECT NAME: Puckapunyal Peter Douglas Centre
Site QA
LCA-20115-00-M-3000 Mechanical Services Ground Floor - East
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | FCU.G-01 | Equipment Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3001 Mechanical Services Ground Floor - West
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | AHU.G-01 | Equipment Checklist
|  |  | RAF.G-01 | Equipment Checklist
|  |  | FCU.G-02 | Equipment Checklist
|  |  | FCU.G-03 | Equipment Checklist
|  |  | FCU.G-04 | Equipment Checklist
|  |  | FCU.G-05 | Equipment Checklist
|  |  | FCU.G-06 | Equipment Checklist
|  |  | FCU.G-07 | Equipment Checklist
|  |  | PHHWP-01 | Equipment Checklist
|  |  | PHHWP-02 | Equipment Checklist
|  |  | SHHWP-01 | Equipment Checklist
|  |  | SHHWP-02 | Equipment Checklist
|  |  | FCU/ACC.CG-01 | Equipment Checklist
|  |  | Refrig. pipe | Refrigeration Pipe Checklist
|  |  | Drains | Drains Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
Ground floor CHW plantroom (inc. outdoor plantroom)
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | PCHWP-01 | Equipment Checklist
|  |  | PCHWP-02 | Equipment Checklist
|  |  | PCHWP-03 | Equipment Checklist
|  |  | PCHWP-04 | Equipment Checklist
|  |  | SCHWP-01 | Equipment Checklist
|  |  | SCHWP-02 | Equipment Checklist
|  |  | SAF.G-01 | Equipment Checklist
|  |  | GEF.G-01 | Equipment Checklist
|  |  | CH.G-01 | Equipment Checklist
|  |  | CH.G-02 | Equipment Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3002 Mechanical Services Level 1 - East
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | FCU.L1-01 | Equipment Checklist
|  |  | FCU.L1-02 | Equipment Checklist
|  |  | FCU.L1-04 | Equipment Checklist
|  |  | FCU.L1-05 | Equipment Checklist
|  |  | FCU.L1-06 | Equipment Checklist
|  |  | FCU.L1-07 | Equipment Checklist
|  |  | FCU.L1-08 | Equipment Checklist
|  |  | FCU/ACC.C1-01 | Equipment Checklist
|  |  | Refrig. pipe | Refrigeration Pipe Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3003 Mechanical Services Level 1 - West
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | AHU.L1-01 | Equipment Checklist
|  |  | RAF.L1-01 | Equipment Checklist
|  |  | FCU.L1-09 | Equipment Checklist
|  |  | FCU.L1-10 | Equipment Checklist
|  |  | FCU/ACC.C1-02 | Equipment Checklist
|  |  | Refrig. pipe | Refrigeration Pipe Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3004 Mechanical Services Level 2 - East
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | FCU.L2-02 | Equipment Checklist
|  |  | FCU.L2-03 | Equipment Checklist
|  |  | FCU.L2-04 | Equipment Checklist
|  |  | FCU.L2-05 | Equipment Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3005 Mechanical Services Level 2 - West
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | AHU.L2-01 | Equipment Checklist
|  |  | RAF.L2-01 | Equipment Checklist
|  |  | FCU/ACC.C2-01 | Equipment Checklist
|  |  | Refrig. pipe | Refrigeration Pipe Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3006 Mechanical Services Level 3 - East
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | FCU.L2-01 | Equipment Checklist
|  |  | FCU.L3-01 | Equipment Checklist
|  |  | FCU.L3-02 | Equipment Checklist
|  |  | FCU.L3-03 | Equipment Checklist
|  |  | FCU.L3-04 | Equipment Checklist
|  |  | FCU.L3-05 | Equipment Checklist
|  |  | TEF.L1-1 | Equipment Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3007 Mechanical Services Level 3 - West
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | Flex | Flex Checklist
|  |  | Cushion boxes | Cushion Boxes Checklist
|  |  | AHU.L3-01 | Equipment Checklist
|  |  | RAF.L3-01 | Equipment Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3008 Mechanical Services Roof - East
Mech Rough in
|  |  | OAF.R-01 | Equipment Checklist
|  |  | OAF.R-02 | Equipment Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
LCA-20115-00-M-3009 Mechanical Services Roof - West
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | AHU.L4-01 | Equipment Checklist
|  |  | TEF.L2-1 | Equipment Checklist
|  |  | TEF.L2-2 | Equipment Checklist
|  |  | Drains | Drains Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
AHU roof plantroom
Mech Rough in
|  |  | Ductwork | Ductwork Checklist
|  |  | AHU.L1-02 | Equipment Checklist
|  |  | AHU.L1-03 | Equipment Checklist
|  |  | AHU.L1-04 | Equipment Checklist
|  |  | AHU.L1-05 | Equipment Checklist
|  |  | AHU.L2-02 | Equipment Checklist
|  |  | AHU.L2-03 | Equipment Checklist
|  |  | AHU.L2-04 | Equipment Checklist
|  |  | AHU.L2-05 | Equipment Checklist
|  |  | AHU.L3-02 | Equipment Checklist
|  |  | AHU.L3-03 | Equipment Checklist
|  |  | AHU.L3-04 | Equipment Checklist
|  |  | AHU.L3-05 | Equipment Checklist
|  |  | Penetrations | Penetration Details
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Grilles | Grilles Fit-Off
|  |  | Drains | Drain Fit-Off Testing Checklist
Mechanical Services West Pipework riser
Mech Rough in
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Drains | Drain Fit-Off Testing Checklist
Mechanical Services East Pipework riser
Mech Rough in
|  |  | Pipework | Pipework Checklist
Mech Fit off
|  |  | Drains | Drain Fit-Off Testing Checklist

## ChecklistsITCs
type | name | values | prefix | postfix
checklist | Ductwork Checklist
checkpoint | Ductwork delivered, protected & clean - i.e plastic wrapped
checkpoint | Marked off on latest drawing
button | Installed as per latest drawing | Yes, No
button | Correct height as per drawing | Yes, No
button | Duct flanges firmly bolted & sealed where required | Yes, No
button | Cleats installed as required | Yes, No
button | Insulated as required/ damage free | Yes, No
checkpoint | Supported to requirements
button | Correct hanger spacing | Yes, No
button | Correct rod length | Yes, No
checkpoint | Volume dampers installed as per drawing
checkpoint | Motorised dampers installed as per drawing
button | Dampers open & free moving | Yes, No
checkpoint | Acoustic penetration sealing to requirements
checkpoint | Acoustic duct mounts to requirements
checkpoint | Seismic bracing to requirements
checkpoint | Damage free post-install & Area left clean/tidy (Any Issues comment below)
checklist | Equipment Checklist
checkpoint | Correct unit installed as per latest drawing & schedule
button | Correctly supported with anti vibration as required | Yes, No
checkpoint | Flexible connections installed as required
checkpoint | Access available & access panels marked on drawing
label | Marked up drawing attached below if applicable
button | Correctly labelled as per latest drawing | Yes, No
checkpoint | Seismic bracing to requirements
checkpoint | Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Refrigeration Pipe Checklist
checkpoint | Correct IDU & ODU installed as per latest drawing & schedule
checkpoint | Installed as per latest drawings
checkpoint | No other services suspended from pipe work (Attach Photos below)
checkpoint | Installation damage free (Any Issues comment/attach Photos below)
button | correct hanger spacing | Yes, No
checkpoint | Pipe labelled after insulation
bool | Photo of Label attached
checkpoint | Seismic bracing to requirements
checkpoint | Pipe Mains Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checkpoint | Pipework system pressure tested
checklist | Drains Checklist
checkpoint | Drains installed with fall to tundish
button | Pipes insulated as required | Yes, No
button | Tundish installed | Yes, No
checkpoint | Drain has been tested (Test results attached if applicable)
checkpoint | Drain(s) Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checkpoint | Drain has had final test, traps are full
checklist | Flex Checklist
checkpoint | Supported with duct saddle only, not from other trades materials
button | Not sagging on ceiling | Yes, No
button | Dampers fully open | Yes, No
checkpoint | Correct as per latest drawing
checkpoint | Flex Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Cushion Boxes Checklist
checkpoint | Correct size as per latest schedule
checkpoint | Secured & sealed
button | Flexible duct connected neat & secure | Yes, No
checkpoint | Cushion box damper installed & open
checkpoint | Diffuser cut out marked on ceiling (Attach Photos if applicable)
checkpoint | Cushion Box Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | As Builts Checklist
checkpoint | Update As-Built's of any know changes (Attach if applicable)
checklist | Access Panel Markup Checklist
checkpoint | Marked up completed & attached
button | Submitted to draftsman | Yes, No
checklist | Testing Checklist
checkpoint | Test passed with air/water
checkpoint | Test sighted by builder & signed off (Click to Add Signature below - If applicable)
button | Air bled from system | Yes, No
checklist | Pipework Checklist
checkpoint | Installed as per latest drawing | Pass/Fail
checkpoint | Correct heights i.e. underside as per drawings | Pass/Fail
checkpoint | Pipe fittings complete | Pass/Fail
checkpoint | Clips complete | Pass/Fail
checkpoint | Insulation complete | Pass/Fail
checkpoint | Air bleed complete (installed at all floor high points) | Pass/Fail
checkpoint | Drain points complete | Pass/Fail
checkpoint | Correct flow and return checked | Pass/Fail
checkpoint | Access to valve sets checked' | Pass/Fail
checkpoint | No other services suspended from pipe work | Pass/Fail
checkpoint | Welds checked | Pass/Fail
checkpoint | Damage free | Pass/Fail
checkpoint | Piping cleaned and flushed | Pass/Fail
checkpoint | Pipe tested and recorded as per Pipe Testing ITP | Pass/Fail
checkpoint | Initial pipe pressure test (attach photo below)
checkpoint | 24hr pipe pressure test (attach photo below)
checklist | Fit-Off Checklist (Full)
section | Drain Fit-Off Testing
checkpoint | Drain has been terminated into tundish
checkpoint | Drain has had final test, traps are full
section | Grilles Fit-Off
checkpoint | Grilles, Registers, Diffusers fit off as per latest drawing/ schedule
button | Free of any damage | Yes, No
button | Grilles installed flush to ceiling | Yes, No
button | Boxes sealed to grill | Yes, No
button | Grille finish/colour as per latest spec | Yes, No
checkpoint | Grilles Fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
section | Filters Fit-Off
checkpoint | Plenums clean of dirt & debris
checkpoint | Filters installed correctly as per schedule (Any Issues Comment below)
checklist | Drain Fit-Off Testing Checklist
checkpoint | Drain has been terminated into tundish
checkpoint | Drain has had final test, traps are full
checklist | Grilles Fit-Off Checklist
checkpoint | Grilles, Registers, Diffusers fit off as per latest drawing/ schedule
button | Free of any damage | Yes, No
button | Grilles installed flush to ceiling | Yes, No
button | Boxes sealed to grill | Yes, No
button | Grille finish/colour as per latest spec | Yes, No
checkpoint | Grilles Fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Filters Fit-Off Checklist
checkpoint | Plenums clean of dirt & debris
checkpoint | Filters installed correctly as per schedule (Any Issues Comment below)
checklist | Commissioning Checklist
checkpoint | Commissioning completed (Pass once below completed)
button | Any issues during commissioning | Yes, No
text | If Yes, please specify
bool | Any commissioning reports/results attached (If applicable)
checklist | Subbie Rough-in Progression Checklist
checkpoint | All work in Zone completed
label | Pass once all work complete
checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint | Rough-In completed to specification/drawings & Area left clean/tidy
label | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist | Subbie Fit-off Progression Checklist
checkpoint | All work in Zone completed
label | Pass once all work complete
checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint | Fit-Off completed to specification/drawings & Area left clean/tidy
label | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist | Subbie Testing Progression Checklist
checkpoint | All work in Zone completed
label | Pass once all work complete
checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint | Testing completed to specification/drawings & Area left clean/tidy
label | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist | Gripple Inspection Upload Checklist
checkpoint | Gripple Seismic inspection completed
label | Attach report as applicable below
button | Gripple inspector signature added below as applicable | Yes, No, N/A
holdpoint | If required - Click to request Gripple sign-off
checklist | Ductwork Checklist
checkpoint | Ductwork delivered, protected & clean - i.e plastic wrapped
checkpoint | Marked off on latest drawing
button | Installed as per latest drawing | Yes, No
button | Correct height as per drawing | Yes, No
button | Duct flanges firmly bolted & sealed where required | Yes, No
button | Cleats installed as required | Yes, No
button | Insulated as required/ damage free | Yes, No
checkpoint | Supported to requirements
button | Correct hanger spacing | Yes, No
button | Correct rod length | Yes, No
checkpoint | Volume dampers installed as per drawing
checkpoint | Smoke dampers installed as per drawing
button | Dampers open & free moving | Yes, No
checkpoint | Damage free post-install & Area left clean/tidy (Any Issues comment below)
checklist | Penetration Details
checkpoint | Studio wall penetration sealing to requirements