## TO BUILD - Project Breakdown
Project Breakdown |  |  |  | Checklists
PROJECT NAME: DHL
Site QA
General Layout
|  |  | As Built | As Builts Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Pipework | Pipe Mains Checklist
|  |  | Equipment | Equipment Checklist
|  |  | Flex Duct | Flex Checklist
|  |  | Cushion box | Cushion Boxes Checklist
|  |  | Seisimic check | Seisimic Checklist
|  |  | Mech-elec | Subbie Fit-off Progression Checklist
|  |  | Commissioning | Commissioning Checklist
Stage 1 Level G Indoor units
AC-1 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-3 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-4 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-5 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-6 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-7 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
Stage 1 Level 1 Indoor units
AC-8 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-9 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-10 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-11 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-12 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-13 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-14 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-15 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-16 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-17 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-18 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-19 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-20 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-21 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-54 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-55 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-56 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
Stage 1 Level 2 Indoor units
AC-22 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-23 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-24 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-25 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-26 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-27 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-28 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-29 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-30 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-31 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-32 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-33 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-34 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-35 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-36 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-37 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
Stage 2 Level G Indoor units
AC-38 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-39 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-40 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-41 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-42 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-52 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
Stage 2 Level 1 Indoor units
AC-43 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-44 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-45 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-46 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-47 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-48 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-53 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-49 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-50 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
AC-57 indoor
|  |  | Equipment | Equipment Checklist
|  |  | Pipework | Refrigeration Pipe Checklist
|  |  | Ductwork | Ductwork Checklist
|  |  | Drain(condensation pumps) | Drain Fit-Off Testing Checklist
|  |  | Seisimic check | Seisimic Checklist
Stage 1 Roof East
CU-6 Outdoor
Outdoor Equipment Checklist
CU-4 Outdoor
Outdoor Equipment Checklist
CU-3 Outdoor
Outdoor Equipment Checklist
CU-30 Outdoor
Outdoor Equipment Checklist
CU-10 Outdoor
Outdoor Equipment Checklist
CU-35 Outdoor
Outdoor Equipment Checklist
CU-22 Outdoor
Outdoor Equipment Checklist
CU-09 Outdoor
Outdoor Equipment Checklist
CU-56 Outdoor
Outdoor Equipment Checklist
CU-7 Outdoor
Outdoor Equipment Checklist
CU-25 Outdoor
Outdoor Equipment Checklist
CU-12 Outdoor
Outdoor Equipment Checklist
CU-1 Outdoor
Outdoor Equipment Checklist
CU-23 Outdoor
Outdoor Equipment Checklist
CU-20 Outdoor
Outdoor Equipment Checklist
CU-19 Outdoor
Outdoor Equipment Checklist
CU-36 Outdoor
Outdoor Equipment Checklist
CU-21 Outdoor
Outdoor Equipment Checklist
CU-11 Outdoor
Outdoor Equipment Checklist
CU-24 Outdoor
Outdoor Equipment Checklist
CU-05 Outdoor
Outdoor Equipment Checklist
Stage 1 Roof West
CU-33 Outdoor
Outdoor Equipment Checklist
CU-18 Outdoor
Outdoor Equipment Checklist
CU-13 Outdoor
Outdoor Equipment Checklist
CU-28 Outdoor
Outdoor Equipment Checklist
CU-16 Outdoor
Outdoor Equipment Checklist
CU-8 Outdoor
Outdoor Equipment Checklist
CU-34 Outdoor
Outdoor Equipment Checklist
CU-31 Outdoor
Outdoor Equipment Checklist
CU-17 Outdoor
Outdoor Equipment Checklist
CU-54 Outdoor
Outdoor Equipment Checklist
CU-32 Outdoor
Outdoor Equipment Checklist
CU-37 Outdoor
Outdoor Equipment Checklist
CU-29 Outdoor
Outdoor Equipment Checklist
CU-14 Outdoor
Outdoor Equipment Checklist
CU-15 Outdoor
Outdoor Equipment Checklist
CU-27 Outdoor
Outdoor Equipment Checklist
CU-55 Outdoor
Outdoor Equipment Checklist
CU-26 Outdoor
Outdoor Equipment Checklist
Stage 2 Roof
CU-42 Outdoor
Outdoor Equipment Checklist
CU-41 Outdoor
Outdoor Equipment Checklist
CU-38 Outdoor
Outdoor Equipment Checklist
CU-52 Outdoor
Outdoor Equipment Checklist
CU-53 Outdoor
Outdoor Equipment Checklist
CU-48 Outdoor
Outdoor Equipment Checklist
CU-47 Outdoor
Outdoor Equipment Checklist
CU-46 Outdoor
Outdoor Equipment Checklist
CU-50 Outdoor
Outdoor Equipment Checklist
CU-49 Outdoor
Outdoor Equipment Checklist
CU-43 Outdoor
Outdoor Equipment Checklist
CU-44 Outdoor
Outdoor Equipment Checklist
CU-45 Outdoor
Outdoor Equipment Checklist
CU-40 Outdoor
Outdoor Equipment Checklist
CU-39 Outdoor
Outdoor Equipment Checklist

## ChecklistsITCs
type | name | values | prefix | postfix
checklist | Ductwork Checklist
checkpoint | Ductwork delivered, protected & clean - i.e plastic wrapped
checkpoint | Marked off on latest drawing
button | Installed as per latest drawing | Yes, No
button | Correct height as per drawing | Yes, No
button | Duct flanges firmly bolted & sealed where required | Yes, No
button | Cleats installed as required | Yes, No
button | Insulated as required/ damage free | Yes, No
checkpoint | Supported to requirements
button | Correct hanger spacing | Yes, No
button | Correct rod length | Yes, No
checkpoint | Volume dampers installed as per drawing
checkpoint | Smoke dampers installed as per drawing
button | Dampers open & free moving | Yes, No
checkpoint | Damage free post-install & Area left clean/tidy (Any Issues comment below)
checklist | Equipment Checklist
checkpoint | Correct unit installed as per latest drawing & schedule
button | Correctly supported with anti vibration as required | Yes, No
checkpoint | Flexible connections installed as required
checkpoint | Access available & access panels marked on drawing
label | Marked up drawing attached below if applicable
button | Correctly labelled as per latest drawing | Yes, No
checkpoint | Filters installed as required per schedule
checkpoint | Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Fire Damper Checklist
checkpoint | Fire damper installed as per latest drawing
checkpoint | Fire damper installed as per manufacturer's installation guide
button | Fire damper sealed/angles tight | Yes, No
button | Fire damper fuse is in correct position | Yes, No
button | Fire damper curtain free of any impurities | Yes, No
checkpoint | Fire damper labelled with PJM sticker & photographed
bool | Photo of Label attached
checkpoint | Access panel installed in duct
checkpoint | Access panel documented on RCP for maintenance/inspection access
label | Marked up drawing attached below if applicable
checkpoint | Fire Damper Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Pipe Mains Checklist
checkpoint | Installed as per latest drawings
checkpoint | Correct heights, i.e. height to underside as per drawing
checkpoint | No other services suspended from pipe work (Attach Photos below)
checkpoint | Installation damage free (Any Issues comment/attach Photos below)
button | Air bleeds & drain points installed as required | Yes, No
button | Correct hanger and rod length | Yes, No
button | correct hanger spacing | Yes, No
button | expansion anchors installed as per drawing | Yes, No
checkpoint | Pipe labelled after insulation
bool | Photo of Label attached
checkpoint | Pipe Mains Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Valve Checklist
checkpoint | Valves installed as per schedule
button | Valves tested before being lagged (Any issues please comment below) | Yes, No
button | Valves installed in position to allow access from access panel | Yes, No
checkpoint | Valve(s) Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Drains Checklist
checkpoint | Drains installed with fall to tundish
button | Pipes insulated as required | Yes, No
button | Tundish installed | Yes, No
checkpoint | Drain has been tested (Test results attached if applicable)
checkpoint | Drain(s) Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Flex Checklist
checkpoint | Supported with duct saddle only, not from other trades materials
button | Not sagging on ceiling | Yes, No
button | Dampers fully open | Yes, No
checkpoint | Correct as per latest drawing
checkpoint | Flex Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Cushion Boxes Checklist
checkpoint | Correct size as per latest schedule
checkpoint | Secured & sealed
button | Flexible duct connected neat & secure | Yes, No
checkpoint | Cushion box damper installed & open
checkpoint | Diffuser cut out marked on ceiling (Attach Photos if applicable)
checkpoint | Cushion Box Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | As Builts Checklist
checkpoint | Update As-Built's of any know changes (Attach if applicable)
checklist | Access Panel Markup Checklist
checkpoint | Marked up completed & attached
button | Submitted to draftsman | Yes, No
checklist | Testing Checklist
checkpoint | Test passed with air/water
checkpoint | Test sighted by builder & signed off (Click to Add Signature below - If applicable)
button | Air bled from system | Yes, No
checklist | Fit-Off Checklist (Full)
section | Drain Fit-Off Testing
checkpoint | Drain has been terminated into tundish
checkpoint | Drain has had final test, traps are full
section | Grilles Fit-Off
checkpoint | Grilles, Registers, Diffusers fit off as per latest drawing/ schedule
button | Free of any damage | Yes, No
button | Grilles installed flush to ceiling | Yes, No
button | Boxes sealed to grill | Yes, No
button | Grille finish/colour as per latest spec | Yes, No
checkpoint | Grilles Fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
section | Filters Fit-Off
checkpoint | Plenums clean of dirt & debris
checkpoint | Filters installed correctly as per schedule (Any Issues Comment below)
checklist | Drain Fit-Off Testing Checklist
checkpoint | Drain has been terminated into tundish
checkpoint | Drain has had final test, traps are full
checklist | Grilles Fit-Off Checklist
checkpoint | Grilles, Registers, Diffusers fit off as per latest drawing/ schedule
button | Free of any damage | Yes, No
button | Grilles installed flush to ceiling | Yes, No
button | Boxes sealed to grill | Yes, No
button | Grille finish/colour as per latest spec | Yes, No
checkpoint | Grilles Fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checklist | Filters Fit-Off Checklist
checkpoint | Plenums clean of dirt & debris
checkpoint | Filters installed correctly as per schedule (Any Issues Comment below)
checklist | Commissioning Checklist
checkpoint | Commissioning completed (Pass once below completed)
button | Any issues during commissioning | Yes, No
text | If Yes, please specify
bool | Any commissioning reports/results attached (If applicable)
checklist | Subbie Rough-in Progression Checklist
checkpoint | All work in Zone completed
label | Pass once all work complete
checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint | Rough-In completed to specification/drawings & Area left clean/tidy
label | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist | Subbie Fit-off Progression Checklist
checkpoint | All work in Zone completed
label | Pass once all work complete
checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint | Fit-Off completed to specification/drawings & Area left clean/tidy
label | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist | Subbie Testing Progression Checklist
checkpoint | All work in Zone completed
label | Pass once all work complete
checkpoint | Any Progress Photos/File's attached for reference (Attach below)
checkpoint | Testing completed to specification/drawings & Area left clean/tidy
label | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
checklist | Gripple Inspection Upload Checklist
checkpoint | Gripple Seismic inspection completed
label | Attach report as applicable below
button | Gripple inspector signature added below as applicable | Yes, No, N/A
holdpoint | If required - Click to request Gripple sign-off
checklist | Ductwork Checklist
checkpoint | Ductwork delivered, protected & clean - i.e plastic wrapped
checkpoint | Marked off on latest drawing
button | Installed as per latest drawing | Yes, No
button | Correct height as per drawing | Yes, No
button | Duct flanges firmly bolted & sealed where required | Yes, No
button | Cleats installed as required | Yes, No
button | Insulated as required/ damage free | Yes, No
checkpoint | Supported to requirements
button | Correct hanger spacing | Yes, No
button | Correct rod length | Yes, No
checkpoint | Volume dampers installed as per drawing
checkpoint | Smoke dampers installed as per drawing
button | Dampers open & free moving | Yes, No
checkpoint | Damage free post-install & Area left clean/tidy (Any Issues comment below)
checklist | Seisimic Checklist
checkpoint | Seismic inspection completed
checkpoint | All units have been treated ,cables has been tightened
button | All thereaded rod are braced if Thereaded rod is longer than 500mm | Yes, No
holdpoint | If required - take pictures of the seisimic installation
checklist | Refrigeration Pipe Checklist
checkpoint | Correct IDU & ODU installed as per latest drawing & schedule
checkpoint | Installed as per latest drawings
checkpoint | No other services suspended from pipe work (Attach Photos below)
checkpoint | Installation damage free (Any Issues comment/attach Photos below)
button | correct hanger spacing | Yes, No
checkpoint | Pipe labelled after insulation
bool | Photo of Label attached
checkpoint | Pipe Mains Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
checkpoint | Pipework system pressure tested
checklist | Outdoor Equipment Checklist
checkpoint | Correct unit installed as per latest drawing & schedule
button | Correctly supported with anti vibration as required | Yes, No
checkpoint | Access available
label | Marked up drawing attached below if applicable
button | Correctly labelled as per latest drawing | Yes, No
checkpoint | Installation completed to drawings/specification & Area left clean/tidy (Any Issues comment below)