## Breakdown
Phormium Construction - 045 Kevin Hickman (Riccarton Park)
Stage 03 - THB11 & 13
|  | TH33 | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  | Timber Trusses |  | Pre-populate | ST - S - Roof structure - Timber Trusses
|  |  | External Envelope |  | Pre-populate | FC - S - External Envelope
|  |  | Windows, Sliders and Sealants |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  | Skirting, Architraves & Trims |  | Pre-populate | Post - S - Skirting/ Architraves & Trims
|  |  | Hardware |  | Pre-populate | Post - S - Hardware Installation
|  |  | Internal Doors |  | Pre-populate | Post - S - Internal door installation
|  |  | Handrails |  | Pre-populate | Post - S - Handrails
TH34
|  |  | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  | Timber Trusses |  | Pre-populate | ST - S - Roof structure - Timber Trusses
|  |  | External Envelope |  | Pre-populate | FC - S - External Envelope
|  |  | Windows, Sliders and Sealants |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  | Skirting, Architraves & Trims |  | Pre-populate | Post - S - Skirting/ Architraves & Trims
|  |  | Hardware |  | Pre-populate | Post - S - Hardware Installation
|  |  | Internal Doors |  | Pre-populate | Post - S - Internal door installation
|  |  | Handrails |  | Pre-populate | Post - S - Handrails
TH35
|  |  | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  | Timber Trusses |  | Pre-populate | ST - S - Roof structure - Timber Trusses
|  |  | External Envelope |  | Pre-populate | FC - S - External Envelope
|  |  | Windows, Sliders and Sealants |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  | Skirting, Architraves & Trims |  | Pre-populate | Post - S - Skirting/ Architraves & Trims
|  |  | Hardware |  | Pre-populate | Post - S - Hardware Installation
|  |  | Internal Doors |  | Pre-populate | Post - S - Internal door installation
|  |  | Handrails |  | Pre-populate | Post - S - Handrails
TH36
|  |  | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  | Timber Trusses |  | Pre-populate | ST - S - Roof structure - Timber Trusses
|  |  | External Envelope |  | Pre-populate | FC - S - External Envelope
|  |  | Windows, Sliders and Sealants |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  | Skirting, Architraves & Trims |  | Pre-populate | Post - S - Skirting/ Architraves & Trims
|  |  | Hardware |  | Pre-populate | Post - S - Hardware Installation
|  |  | Internal Doors |  | Pre-populate | Post - S - Internal door installation
|  |  | Handrails |  | Pre-populate | Post - S - Handrails
Pentrations
|  | TH37 | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  | Timber Trusses |  | Pre-populate | ST - S - Roof structure - Timber Trusses
|  |  | External Envelope |  | Pre-populate | FC - S - External Envelope
|  |  | Windows, Sliders and Sealants |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  | Skirting, Architraves & Trims |  | Pre-populate | Post - S - Skirting/ Architraves & Trims
|  |  | Hardware |  | Pre-populate | Post - S - Hardware Installation
|  |  | Internal Doors |  | Pre-populate | Post - S - Internal door installation
|  |  | Handrails |  | Pre-populate | Post - S - Handrails
TH38
|  |  | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  | Timber Trusses |  | Pre-populate | ST - S - Roof structure - Timber Trusses
|  |  | External Envelope |  | Pre-populate | FC - S - External Envelope
|  |  | Windows, Sliders and Sealants |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  | Skirting, Architraves & Trims |  | Pre-populate | Post - S - Skirting/ Architraves & Trims
|  |  | Hardware |  | Pre-populate | Post - S - Hardware Installation
|  |  | Internal Doors |  | Pre-populate | Post - S - Internal door installation
|  |  | Handrails |  | Pre-populate | Post - S - Handrails
TH39
|  |  | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  | Timber Trusses |  | Pre-populate | ST - S - Roof structure - Timber Trusses
|  |  | External Envelope |  | Pre-populate | FC - S - External Envelope
|  |  | Windows, Sliders and Sealants |  | Pre-populate | FC - S - Windows, Sliders and Sealants
|  |  | Skirting, Architraves & Trims |  | Pre-populate | Post - S - Skirting/ Architraves & Trims
|  |  | Hardware |  | Pre-populate | Post - S - Hardware Installation
|  |  | Internal Doors |  | Pre-populate | Post - S - Internal door installation
|  |  | Handrails |  | Pre-populate | Post - S - Handrails
Pentrations
Completion documents
|  | Stage 03 | Pre-populate | Cst - S - Completion Documents

## Checklist
Type | Name | Value
checklist | ST - S - Timber Framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square / Frames are plumb and level
checkpoint | Fixings are correct
checkpoint | Installed in corrct level, plumb, correct pitch and braced
checkpoint | Any bracing requirements installed
checkpoint | All framing completed correctly within tolerance in respective area
Type | Name | Value
checklist | ST - S - Roof structure - Timber Trusses
checkpoint | Truss hardware completed as specified
checkpoint | All fixings in place
checkpoint | Truss seating checked and accurate
checkpoint | Tile battens installed and acceptable
checkpoint | Underlay completed and acceptable
checkpoint | Pre-tile checks completed and no issues identified
checkpoint | Load tiles completed and acceptable
checkpoint | Installation and recheck completed and no issues identified
checkpoint | Lay capping completed and acceptable
checkpoint | Ridges installed and acceptable
checkpoint | Facia gutters installed and acceptable
checkpoint | Trusses are installed correctly and acceptable
Type | Name | Value
checklist | FC - S - Windows, Sliders and Sealants
checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint | Check taping around, before installing the windows and sliders
checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint | Jambs level and straight for finishing lines on the side
checkpoint | Door and window jambs flush to GIB Board
checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint | All joints detailed as per attached Detail Document
checkpoint | All framing completed correctly within tolerance in respective area
checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
Type | Name | Value
checklist | Post - S - Skirting/ Architraves & Trims
checkpoint | Architraves/ skirtings & trims are the correct size and profile
checkpoint | Skirting boards have been properly scribed, sanded, glued and mitred
checkpoint | Architraves/skirtings & trims have been installed with consistent even margins
checkpoint | Skirting/Architraves & trim work completed - specified level of finish achieved
Type | Name | Value
checklist | Post - S - Internal door installation
checkpoint | Door Number(s) / Location checked and accurate
checkpoint | Floor clearance - Adequate for proposed floor coverings
checkpoint | Fixings - Consider Jamb/Hinges, all installed & secure (Size & type)
checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
checkpoint | Door opening as required & is plumb
checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
Type | Name | Value
checklist | FC - S - External Envelope
checkpoint | Eco ply taped nailing checked
label | Supplied & installed by others
checkpoint | RAB board Fixing and spacings checked in accordance with manufacturers specs (Photos attached)
checkpoint | Fire strip installed (Photos attached)
checkpoint | Soffit checked and accurate (Photos attached)
checkpoint | Garage reveals checked and accurate (Photos attached)
checkpoint | DPC installed checked and accurate (Photos attached)
holdpoint | Request sign off
Type | Name | Value
checklist | Post - S - Handrails
checkpoint | Area & substrate acceptable
checkpoint | All handrails install completed correctly within tolerance in respective area
holdpoint | Raise Remedial/ Main Contractor Signoff
Type | Name | Value
Checklist | Post - S - Hardware Installation
checkpoint | Area accessible and ready to install the hardware
checkpoint | All hardware installation completed correctly within tolerance in respective area (Photos attached)
holdpoint | Raise Remedial/ Main Contractor Signoff
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff