## Breakdown
Phormium Construction - 045 Kevin Hickman (Riccarton Park)
401 - Stage 04 - B02
Façade
Letter Box Bank
|  |  |  | Groundwork/Concrete Footing |  | Pre-populate | ST - S - Concrete Reinforcing
|  |  |  | Timber Framing |  | Pre-populate | ST - S - Timber Framing
|  |  |  | Lintel |  | Pre-populate | FC - R - Lintels
|  |  |  | Flashing Cap |  | Pre-populate | FC - S - Flashing installation
Compliance Documents
|  | Stage 04 - Letter Box Bank |  | Pre-populate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist-flat | ST - S - Concrete Reinforcing
checkpoint | Size and type correct to specification
checkpoint | Reinforcing spacing and location correct
checkpoint | Specified covers checked/correct
checkpoint | Splice laps checked/correct
checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
bool | Appointment with the engineers confirmed (Enter date & time of the appointment)
bool | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint | Welding certificates sited and attached
checkpoint | Mill certificate reviewed, attached and approved
checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
Type | Name | Value
checklist-flat | ST - S - Timber Framing
checkpoint | Dimensions / locations checked and accurate
checkpoint | All frames are square / Frames are plumb and level
checkpoint | Fixings are correct
checkpoint | Installed in corrct level, plumb, correct pitch and braced
checkpoint | Any bracing requirements installed
checkpoint | All framing completed correctly within tolerance in respective area
Type | Name | Value
checklist | FC - S - Flashing installation
checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint | Aluminium window jamb side flashings are installed
checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
Type | Name | Value
checklist-flat | FC - R - Lintels
checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | Raise remedial / Request Signoff
checkpoint | Lintels completed and acceptable